## project_register
project_id | project_name | portfolio | project_type | city | client_type | contract_type | contract_value | tender_margin_pct | bac | planned_start | planned_finish | planned_months | design_maturity_pct | complexity | pm_experience_years | status | actual_finish | final_cost
PRJ001 | Mumbai Metro Viaduct 1 | Current portfolio | Metro Viaduct | Mumbai | Government | Item rate with price variation | 6069000000 | 13.5 | 5249685000 | 2025-05-26 | 2026-06-24 | 13 | 87 | 4 | 8 | In progress
PRJ002 | Pune IT Park 1 | Current portfolio | IT Park | Pune | Private | Lump sum | 4704000000 | 11.6 | 4158336000 | 2025-01-17 | 2026-05-22 | 16 | 51 | 2 | 21 | Completed | 2026-04-30 | 4166557000
PRJ003 | Delhi Residential Towers 1 | Current portfolio | Residential Towers | Delhi | Private | Cost plus fee | 2823000000 | 12.5 | 2470125000 | 2025-04-03 | 2026-03-30 | 11 | 54 | 3 | 18 | Completed | 2026-02-28 | 2579610000
PRJ004 | Noida Logistics Hub 1 | Current portfolio | Logistics Hub | Noida | Private | Lump sum | 4168000000 | 8.1 | 3830392000 | 2024-12-24 | 2026-05-03 | 17 | 71 | 2 | 15 | Completed | 2026-05-31 | 3952934000
PRJ005 | Gurugram Hospital Campus 1 | Current portfolio | Hospital Campus | Gurugram | Government | Item rate with price variation | 3186000000 | 6.2 | 2988468000 | 2025-06-11 | 2026-08-11 | 14 | 70 | 3 | 11 | In progress
PRJ006 | Bengaluru Industrial Plant 1 | Current portfolio | Industrial Plant | Bengaluru | Government | Item rate with price variation | 6103000000 | 13.1 | 5303507000 | 2025-06-19 | 2026-04-30 | 10 | 66 | 4 | 11 | Completed | 2026-08-31 | 5740035000
PRJ007 | Hyderabad Data Centre 1 | Current portfolio | Data Centre | Hyderabad | Government | Item rate with price variation | 5438000000 | 13 | 4731060000 | 2024-10-27 | 2026-04-03 | 18 | 62 | 3 | 18 | In progress
PRJ008 | Chennai Highway Package 1 | Current portfolio | Highway Package | Chennai | Government | Item rate with price variation | 2040000000 | 14.5 | 1744200000 | 2025-05-31 | 2026-03-27 | 10 | 56 | 1 | 16 | Completed | 2026-05-31 | 1834282000
PRJ009 | Ahmedabad Commercial Complex 1 | Current portfolio | Commercial Complex | Ahmedabad | Private | Cost plus fee | 3798000000 | 15.8 | 3197916000 | 2025-04-26 | 2026-06-06 | 14 | 70 | 3 | 12 | Completed | 2026-06-30 | 3384584000
PRJ010 | Kolkata Water Treatment Plant 1 | Current portfolio | Water Treatment Plant | Kolkata | Government | EPC lump sum | 1836000000 | 11.4 | 1626696000 | 2025-01-24 | 2026-08-14 | 19 | 28 | 4 | 6 | Completed | 2026-07-31 | 1674206000
PRJ011 | Jaipur Metro Viaduct 2 | Current portfolio | Metro Viaduct | Jaipur | Government | Item rate with price variation | 4017000000 | 12.2 | 3526926000 | 2025-05-05 | 2026-08-24 | 15 | 64 | 5 | 16 | In progress
PRJ012 | Kochi IT Park 2 | Current portfolio | IT Park | Kochi | Government | Item rate with price variation | 1205000000 | 14 | 1036300000 | 2025-01-09 | 2026-04-23 | 15 | 79 | 3 | 7 | Completed | 2026-07-31 | 1152884000
PRJ013 | Lucknow Residential Towers 2 | Current portfolio | Residential Towers | Lucknow | Private | Lump sum | 5283000000 | 7.2 | 4902624000 | 2025-02-05 | 2026-02-08 | 12 | 57 | 3 | 16 | Completed | 2026-06-30 | 5204146000
PRJ014 | Nagpur Logistics Hub 2 | Current portfolio | Logistics Hub | Nagpur | Private | Lump sum | 4087000000 | 10.9 | 3641517000 | 2024-11-02 | 2026-05-08 | 18 | 66 | 1 | 12 | Completed | 2026-04-30 | 3631186000
PRJ015 | Surat Hospital Campus 2 | Current portfolio | Hospital Campus | Surat | Government | Item rate with price variation | 5392000000 | 10.1 | 4847408000 | 2025-05-07 | 2026-03-02 | 10 | 98 | 4 | 12 | Completed | 2026-06-30 | 5489108000
PRJ016 | Mumbai Industrial Plant 2 | Current portfolio | Industrial Plant | Mumbai | Private | Cost plus fee | 5218000000 | 11.9 | 4597058000 | 2025-02-20 | 2026-07-14 | 17 | 52 | 2 | 13 | In progress
PRJ017 | Pune Data Centre 2 | Current portfolio | Data Centre | Pune | Government | Item rate with price variation | 6328000000 | 15 | 5378800000 | 2024-10-06 | 2026-06-16 | 20 | 62 | 4 | 10 | In progress
PRJ018 | Delhi Highway Package 2 | Current portfolio | Highway Package | Delhi | Private | Lump sum | 3065000000 | 10.9 | 2730915000 | 2024-12-13 | 2025-11-08 | 11 | 72 | 3 | 13 | Completed | 2025-12-31 | 2907794000
PRJ019 | Noida Commercial Complex 2 | Current portfolio | Commercial Complex | Noida | Private | Cost plus fee | 6400000000 | 9.3 | 5804800000 | 2025-04-16 | 2026-03-06 | 11 | 89 | 3 | 17 | Completed | 2026-04-30 | 5924759000
PRJ020 | Gurugram Water Treatment Plant 2 | Current portfolio | Water Treatment Plant | Gurugram | Government | Item rate with price variation | 3887000000 | 8.7 | 3548831000 | 2025-02-06 | 2025-12-23 | 10 | 81 | 3 | 15 | Completed | 2026-03-31 | 3724153000
PRJ021 | Bengaluru Metro Viaduct 3 | Current portfolio | Metro Viaduct | Bengaluru | Government | Item rate with price variation | 6191000000 | 8.4 | 5670956000 | 2025-05-15 | 2026-03-27 | 10 | 89 | 5 | 17 | Completed | 2026-06-30 | 6371479000
PRJ022 | Hyderabad IT Park 3 | Current portfolio | IT Park | Hyderabad | Government | EPC lump sum | 3574000000 | 11.1 | 3177286000 | 2024-11-17 | 2026-03-10 | 16 | 57 | 4 | 13 | Completed | 2026-02-28 | 3373561000
PRJ023 | Chennai Residential Towers 3 | Current portfolio | Residential Towers | Chennai | Private | Lump sum | 2562000000 | 5 | 2433900000 | 2024-10-20 | 2026-08-31 | 22 | 60 | 2 | 14 | In progress
PRJ024 | Ahmedabad Logistics Hub 3 | Current portfolio | Logistics Hub | Ahmedabad | Government | Item rate with price variation | 4437000000 | 13.4 | 3842442000 | 2025-03-17 | 2026-02-25 | 11 | 62 | 2 | 9 | Completed | 2026-02-28 | 3904768000
PRJ025 | Kolkata Hospital Campus 3 | Current portfolio | Hospital Campus | Kolkata | Government | Item rate with price variation | 2863000000 | 11.1 | 2545207000 | 2025-03-04 | 2026-03-16 | 12 | 69 | 5 | 8 | Completed | 2026-02-28 | 2675387000
PRJ026 | Jaipur Industrial Plant 3 | Current portfolio | Industrial Plant | Jaipur | Private | Cost plus fee | 5079000000 | 10.3 | 4555863000 | 2024-11-01 | 2026-08-22 | 21 | 73 | 4 | 23 | In progress
PRJ027 | Kochi Data Centre 3 | Current portfolio | Data Centre | Kochi | Private | Lump sum | 4122000000 | 11 | 3668580000 | 2024-11-26 | 2025-11-23 | 12 | 87 | 4 | 16 | Completed | 2025-12-31 | 4201590000
PRJ028 | Lucknow Highway Package 3 | Current portfolio | Highway Package | Lucknow | Government | Item rate with price variation | 5276000000 | 10.2 | 4737848000 | 2025-06-25 | 2026-05-19 | 11 | 64 | 2 | 20 | Completed | 2026-07-31 | 4905122000
PRJ029 | Nagpur Commercial Complex 3 | Current portfolio | Commercial Complex | Nagpur | Private | Cost plus fee | 3073000000 | 14.5 | 2627415000 | 2024-12-19 | 2025-11-26 | 11 | 75 | 3 | 12 | Completed | 2025-12-31 | 2865785000
PRJ030 | Surat Water Treatment Plant 3 | Current portfolio | Water Treatment Plant | Surat | Government | Item rate with price variation | 3775000000 | 7.2 | 3503200000 | 2025-03-22 | 2026-07-04 | 16 | 83 | 5 | 23 | In progress
HPR001 | Chennai Residential Towers 5 | Completed (history) | Residential Towers | Chennai | Government | Item rate with price variation | 2556000000 | 6.3 | 2394972000 | 2020-03-27 | 2022-01-27 | 22 | 46 | 2 | 24 | Completed | 2022-04-30 | 2539091000
HPR002 | Bengaluru Hospital Campus 7 | Completed (history) | Hospital Campus | Bengaluru | Government | Item rate with price variation | 4136100000 | 12.1 | 3635632000 | 2017-07-18 | 2019-09-18 | 26 | 75 | 5 | 11 | Completed | 2020-06-30 | 3878541000
HPR003 | Chennai Industrial Plant 6 | Completed (history) | Industrial Plant | Chennai | Government | Item rate with price variation | 4740400000 | 7.5 | 4384870000 | 2020-03-07 | 2021-09-07 | 18 | 71 | 2 | 18 | Completed | 2021-12-31 | 4503270000
HPR004 | Hyderabad Hospital Campus 5 | Completed (history) | Hospital Campus | Hyderabad | Government | Item rate with price variation | 2702000000 | 11.7 | 2385866000 | 2016-02-08 | 2018-04-08 | 26 | 64 | 5 | 5 | Completed | 2018-11-30 | 2796255000
HPR005 | Chennai IT Park 8 | Completed (history) | IT Park | Chennai | Private | Cost plus fee | 2990400000 | 12.2 | 2625571000 | 2018-10-26 | 2019-08-26 | 10 | 62 | 3 | 12 | Completed | 2019-08-31 | 2592770000
HPR006 | Kochi Industrial Plant 5 | Completed (history) | Industrial Plant | Kochi | Private | Lump sum | 9571000000 | 6.2 | 8977598000 | 2020-05-31 | 2022-09-30 | 28 | 37 | 4 | 14 | Completed | 2023-04-30 | 10736697000
HPR007 | Bengaluru Residential Towers 5 | Completed (history) | Residential Towers | Bengaluru | Government | Item rate with price variation | 5236100000 | 10.8 | 4670601000 | 2016-03-10 | 2018-05-10 | 26 | 48 | 3 | 16 | Completed | 2018-11-30 | 5042038000
HPR008 | Lucknow Hospital Campus 4 | Completed (history) | Hospital Campus | Lucknow | Government | Item rate with price variation | 3406300000 | 12.8 | 2970294000 | 2020-10-24 | 2023-01-24 | 27 | 69 | 4 | 18 | Completed | 2023-05-31 | 3424935000
HPR009 | Hyderabad Data Centre 7 | Completed (history) | Data Centre | Hyderabad | Private | Lump sum | 6577600000 | 9.6 | 5946150000 | 2022-12-17 | 2024-12-17 | 24 | 59 | 3 | 13 | Completed | 2025-02-28 | 6585820000
HPR010 | Noida Hospital Campus 5 | Completed (history) | Hospital Campus | Noida | Government | Item rate with price variation | 2826600000 | 8.4 | 2589166000 | 2016-06-16 | 2019-08-16 | 38 | 85 | 3 | 17 | Completed | 2020-05-31 | 2691862000
HPR011 | Kochi Water Treatment Plant 7 | Completed (history) | Water Treatment Plant | Kochi | Private | Lump sum | 1617900000 | 14.3 | 1386540000 | 2022-07-14 | 2023-05-14 | 10 | 56 | 3 | 14 | Completed | 2023-07-31 | 1471916000
HPR012 | Nagpur Data Centre 5 | Completed (history) | Data Centre | Nagpur | Private | Lump sum | 6122400000 | 8.2 | 5620363000 | 2018-04-24 | 2020-03-24 | 23 | 57 | 5 | 25 | Completed | 2020-08-31 | 6557159000
HPR013 | Lucknow Water Treatment Plant 5 | Completed (history) | Water Treatment Plant | Lucknow | Private | Lump sum | 2272800000 | 11.3 | 2015974000 | 2021-08-29 | 2022-10-29 | 14 | 83 | 3 | 6 | Completed | 2022-12-31 | 2284101000
HPR014 | Hyderabad Logistics Hub 6 | Completed (history) | Logistics Hub | Hyderabad | Private | Cost plus fee | 12019600000 | 12.9 | 10469072000 | 2021-03-25 | 2022-08-25 | 17 | 69 | 3 | 12 | Completed | 2022-08-31 | 11197738000
HPR015 | Lucknow Commercial Complex 5 | Completed (history) | Commercial Complex | Lucknow | Private | Cost plus fee | 3235200000 | 8.3 | 2966678000 | 2019-06-24 | 2020-05-24 | 11 | 83 | 3 | 15 | Completed | 2020-06-30 | 3044363000
HPR016 | Jaipur Residential Towers 6 | Completed (history) | Residential Towers | Jaipur | Private | Cost plus fee | 4623800000 | 12.5 | 4045825000 | 2021-08-16 | 2024-05-16 | 33 | 59 | 4 | 15 | Completed | 2024-11-30 | 4640391000
HPR017 | Gurugram Metro Viaduct 6 | Completed (history) | Metro Viaduct | Gurugram | Government | Item rate with price variation | 2782900000 | 8.9 | 2535222000 | 2019-12-25 | 2021-07-25 | 19 | 55 | 5 | 4 | Completed | 2022-01-31 | 2872134000
HPR018 | Pune Data Centre 5 | Completed (history) | Data Centre | Pune | Private | Cost plus fee | 3321200000 | 12 | 2922656000 | 2022-02-01 | 2022-12-01 | 10 | 87 | 4 | 10 | Completed | 2023-01-31 | 3175946000
HPR019 | Kolkata Industrial Plant 4 | Completed (history) | Industrial Plant | Kolkata | Private | Cost plus fee | 4298800000 | 10.9 | 3830231000 | 2016-09-17 | 2019-01-17 | 28 | 81 | 4 | 17 | Completed | 2019-03-31 | 4160825000
HPR020 | Delhi Hospital Campus 4 | Completed (history) | Hospital Campus | Delhi | Government | EPC lump sum | 6891600000 | 14.1 | 5919884000 | 2016-08-21 | 2018-11-21 | 27 | 28 | 3 | 16 | Completed | 2019-05-31 | 6325836000
HPR021 | Delhi Highway Package 6 | Completed (history) | Highway Package | Delhi | Government | EPC lump sum | 1772100000 | 13.6 | 1531094000 | 2020-03-17 | 2021-05-17 | 14 | 32 | 1 | 4 | Completed | 2021-10-31 | 1715221000
HPR022 | Hyderabad Hospital Campus 8 | Completed (history) | Hospital Campus | Hyderabad | Government | EPC lump sum | 2569400000 | 13.7 | 2217392000 | 2023-06-09 | 2024-11-09 | 17 | 78 | 3 | 12 | Completed | 2025-01-31 | 2292314000
HPR023 | Delhi Commercial Complex 6 | Completed (history) | Commercial Complex | Delhi | Government | Item rate with price variation | 2975400000 | 8.7 | 2716540000 | 2017-07-08 | 2019-01-08 | 18 | 73 | 3 | 15 | Completed | 2019-04-30 | 2821751000
HPR024 | Kochi Hospital Campus 8 | Completed (history) | Hospital Campus | Kochi | Government | Item rate with price variation | 7077200000 | 11.5 | 6263322000 | 2017-08-21 | 2019-07-21 | 23 | 98 | 3 | 13 | Completed | 2019-11-30 | 6489748000
HPR025 | Jaipur Logistics Hub 5 | Completed (history) | Logistics Hub | Jaipur | Private | Cost plus fee | 4893000000 | 9.3 | 4437951000 | 2020-09-29 | 2021-11-29 | 14 | 72 | 2 | 12 | Completed | 2022-01-31 | 4476022000
HPR026 | Lucknow Industrial Plant 6 | Completed (history) | Industrial Plant | Lucknow | Private | Cost plus fee | 4162100000 | 16.9 | 3458705000 | 2021-06-27 | 2022-06-27 | 12 | 70 | 4 | 4 | Completed | 2022-07-31 | 3680381000
HPR027 | Lucknow Commercial Complex 4 | Completed (history) | Commercial Complex | Lucknow | Private | Lump sum | 4469800000 | 10.5 | 4000471000 | 2023-04-21 | 2024-11-21 | 19 | 78 | 3 | 7 | Completed | 2025-02-28 | 4094881000
HPR028 | Jaipur Residential Towers 6 | Completed (history) | Residential Towers | Jaipur | Government | Item rate with price variation | 4398500000 | 10.7 | 3927860000 | 2023-05-27 | 2024-06-27 | 13 | 91 | 3 | 12 | Completed | 2024-07-31 | 4069226000
HPR029 | Bengaluru Industrial Plant 4 | Completed (history) | Industrial Plant | Bengaluru | Private | Cost plus fee | 4967900000 | 8.8 | 4530725000 | 2017-06-05 | 2018-05-05 | 11 | 71 | 2 | 20 | Completed | 2018-04-30 | 4547510000
HPR030 | Chennai Hospital Campus 6 | Completed (history) | Hospital Campus | Chennai | Government | Item rate with price variation | 2886100000 | 10.7 | 2577287000 | 2019-10-26 | 2021-01-26 | 15 | 67 | 5 | 10 | Completed | 2021-05-31 | 2887869000
HPR031 | Delhi Highway Package 7 | Completed (history) | Highway Package | Delhi | Government | EPC lump sum | 3864600000 | 8.3 | 3543838000 | 2017-07-10 | 2018-09-10 | 14 | 42 | 3 | 14 | Completed | 2019-02-28 | 3848706000
HPR032 | Lucknow Highway Package 6 | Completed (history) | Highway Package | Lucknow | Government | Item rate with price variation | 3356700000 | 12 | 2953896000 | 2018-07-23 | 2020-02-23 | 19 | 65 | 3 | 9 | Completed | 2020-08-31 | 3334497000
HPR033 | Jaipur Logistics Hub 4 | Completed (history) | Logistics Hub | Jaipur | Private | Cost plus fee | 4930700000 | 12.5 | 4314362000 | 2022-10-12 | 2024-08-12 | 22 | 76 | 2 | 14 | Completed | 2024-07-31 | 4236044000
HPR034 | Gurugram Water Treatment Plant 6 | Completed (history) | Water Treatment Plant | Gurugram | Government | Item rate with price variation | 2618200000 | 8.2 | 2403508000 | 2016-07-27 | 2017-06-27 | 11 | 92 | 2 | 20 | Completed | 2017-08-31 | 2445563000
HPR035 | Delhi Logistics Hub 6 | Completed (history) | Logistics Hub | Delhi | Government | Item rate with price variation | 2929800000 | 8.9 | 2669048000 | 2021-11-11 | 2023-06-11 | 19 | 78 | 4 | 13 | Completed | 2023-09-30 | 2888654000
HPR036 | Hyderabad Residential Towers 4 | Completed (history) | Residential Towers | Hyderabad | Private | Lump sum | 7015200000 | 12.7 | 6124270000 | 2018-03-07 | 2019-10-07 | 19 | 62 | 2 | 13 | Completed | 2019-12-31 | 6468102000
HPR037 | Chennai Water Treatment Plant 7 | Completed (history) | Water Treatment Plant | Chennai | Government | EPC lump sum | 3036300000 | 9.6 | 2744815000 | 2016-11-24 | 2018-09-24 | 22 | 42 | 3 | 19 | Completed | 2019-04-30 | 3138450000
HPR038 | Ahmedabad Hospital Campus 7 | Completed (history) | Hospital Campus | Ahmedabad | Government | Item rate with price variation | 3519300000 | 12.1 | 3093465000 | 2016-04-14 | 2018-01-14 | 21 | 60 | 3 | 9 | Completed | 2018-07-31 | 3240167000
HPR039 | Noida Data Centre 4 | Completed (history) | Data Centre | Noida | Government | EPC lump sum | 5955600000 | 8.2 | 5467241000 | 2019-07-14 | 2021-04-14 | 21 | 45 | 3 | 14 | Completed | 2021-11-30 | 6510302000
HPR040 | Gurugram Metro Viaduct 5 | Completed (history) | Metro Viaduct | Gurugram | Private | Cost plus fee | 12052600000 | 18 | 9883132000 | 2019-05-12 | 2020-12-12 | 19 | 49 | 3 | 10 | Completed | 2021-05-31 | 10498004000
HPR041 | Kolkata Residential Towers 8 | Completed (history) | Residential Towers | Kolkata | Private | Lump sum | 2499200000 | 5 | 2374240000 | 2018-08-16 | 2020-05-16 | 21 | 82 | 3 | 19 | Completed | 2020-10-31 | 2674781000
HPR042 | Surat Logistics Hub 5 | Completed (history) | Logistics Hub | Surat | Private | Cost plus fee | 6655300000 | 11.2 | 5909906000 | 2021-02-13 | 2022-08-13 | 18 | 73 | 1 | 12 | Completed | 2022-09-30 | 5963164000
HPR043 | Jaipur IT Park 6 | Completed (history) | IT Park | Jaipur | Private | Lump sum | 4266900000 | 11.6 | 3771940000 | 2017-11-26 | 2019-07-26 | 20 | 64 | 4 | 19 | Completed | 2019-07-31 | 4060907000
HPR044 | Mumbai Industrial Plant 5 | Completed (history) | Industrial Plant | Mumbai | Private | Lump sum | 3465900000 | 12.8 | 3022265000 | 2018-06-08 | 2020-02-08 | 20 | 69 | 2 | 23 | Completed | 2020-03-31 | 3110625000
HPR045 | Chennai Highway Package 6 | Completed (history) | Highway Package | Chennai | Private | Cost plus fee | 5596300000 | 8.1 | 5143000000 | 2022-10-24 | 2024-02-24 | 16 | 69 | 1 | 10 | Completed | 2024-07-31 | 5230309000
HPR046 | Ahmedabad Metro Viaduct 5 | Completed (history) | Metro Viaduct | Ahmedabad | Government | EPC lump sum | 1650600000 | 10.2 | 1482239000 | 2023-03-21 | 2024-01-21 | 10 | 48 | 2 | 20 | Completed | 2024-02-29 | 1539131000
HPR047 | Surat IT Park 5 | Completed (history) | IT Park | Surat | Private | Lump sum | 2017400000 | 10.9 | 1797503000 | 2022-09-27 | 2023-12-27 | 15 | 71 | 3 | 21 | Completed | 2024-01-31 | 1761972000
HPR048 | Ahmedabad Commercial Complex 7 | Completed (history) | Commercial Complex | Ahmedabad | Private | Cost plus fee | 14000000000 | 9.7 | 12642000000 | 2021-10-24 | 2022-10-24 | 12 | 84 | 5 | 13 | Completed | 2022-12-31 | 14081183000
HPR049 | Jaipur Residential Towers 6 | Completed (history) | Residential Towers | Jaipur | Government | Item rate with price variation | 4381400000 | 12.4 | 3838106000 | 2019-07-07 | 2021-04-07 | 21 | 82 | 4 | 10 | Completed | 2021-06-30 | 4001206000
HPR050 | Kolkata Commercial Complex 5 | Completed (history) | Commercial Complex | Kolkata | Private | Lump sum | 5159100000 | 10 | 4643190000 | 2017-09-29 | 2018-08-29 | 11 | 40 | 3 | 20 | Completed | 2018-10-31 | 4922807000
HPR051 | Jaipur IT Park 8 | Completed (history) | IT Park | Jaipur | Private | Lump sum | 5518300000 | 14.1 | 4740220000 | 2017-12-10 | 2019-07-10 | 19 | 74 | 3 | 14 | Completed | 2019-09-30 | 5363062000
HPR052 | Ahmedabad IT Park 8 | Completed (history) | IT Park | Ahmedabad | Private | Lump sum | 3484100000 | 9.4 | 3156595000 | 2016-12-10 | 2018-12-10 | 24 | 98 | 4 | 12 | Completed | 2019-02-28 | 3228879000
HPR053 | Kolkata Metro Viaduct 6 | Completed (history) | Metro Viaduct | Kolkata | Government | Item rate with price variation | 8411500000 | 7.1 | 7814284000 | 2022-12-17 | 2025-03-17 | 27 | 61 | 4 | 16 | Completed | 2025-09-30 | 8406274000
HPR054 | Nagpur Hospital Campus 6 | Completed (history) | Hospital Campus | Nagpur | Private | Lump sum | 4659700000 | 13.1 | 4049279000 | 2021-05-05 | 2023-06-05 | 25 | 76 | 4 | 13 | Completed | 2024-02-29 | 4538731000
HPR055 | Chennai Logistics Hub 5 | Completed (history) | Logistics Hub | Chennai | Government | Item rate with price variation | 4291500000 | 10.4 | 3845184000 | 2021-08-13 | 2022-10-13 | 14 | 64 | 3 | 15 | Completed | 2022-12-31 | 4046802000
HPR056 | Noida Metro Viaduct 4 | Completed (history) | Metro Viaduct | Noida | Private | Cost plus fee | 5495600000 | 9 | 5000996000 | 2023-05-16 | 2025-03-16 | 22 | 46 | 5 | 19 | Completed | 2025-10-31 | 5681877000
HPR057 | Surat Logistics Hub 4 | Completed (history) | Logistics Hub | Surat | Private | Lump sum | 3260600000 | 12.4 | 2856286000 | 2016-07-07 | 2017-07-07 | 12 | 88 | 4 | 16 | Completed | 2017-10-31 | 3100343000
HPR058 | Pune Residential Towers 8 | Completed (history) | Residential Towers | Pune | Government | Item rate with price variation | 2502800000 | 11.2 | 2222486000 | 2018-01-03 | 2020-05-03 | 28 | 81 | 4 | 11 | Completed | 2021-02-28 | 2363114000
HPR059 | Chennai Hospital Campus 6 | Completed (history) | Hospital Campus | Chennai | Government | Item rate with price variation | 2283800000 | 12.4 | 2000609000 | 2017-10-19 | 2018-08-19 | 10 | 38 | 4 | 15 | Completed | 2018-12-31 | 2227598000
HPR060 | Gurugram Logistics Hub 4 | Completed (history) | Logistics Hub | Gurugram | Private | Cost plus fee | 3401200000 | 7.2 | 3156314000 | 2019-03-13 | 2020-09-13 | 18 | 66 | 4 | 9 | Completed | 2020-12-31 | 3255051000
HPR061 | Gurugram Water Treatment Plant 7 | Completed (history) | Water Treatment Plant | Gurugram | Private | Cost plus fee | 4356600000 | 11.9 | 3838165000 | 2017-06-30 | 2019-05-30 | 23 | 78 | 4 | 7 | Completed | 2019-10-31 | 4483646000
HPR062 | Gurugram IT Park 4 | Completed (history) | IT Park | Gurugram | Private | Lump sum | 3359100000 | 13.2 | 2915699000 | 2017-10-01 | 2019-07-01 | 21 | 79 | 2 | 15 | Completed | 2019-06-30 | 2896953000
HPR063 | Ahmedabad Logistics Hub 8 | Completed (history) | Logistics Hub | Ahmedabad | Private | Cost plus fee | 2480500000 | 11.5 | 2195242000 | 2021-05-07 | 2022-08-07 | 15 | 49 | 2 | 18 | Completed | 2022-09-30 | 2325923000
HPR065 | Kolkata Metro Viaduct 6 | Completed (history) | Metro Viaduct | Kolkata | Government | Item rate with price variation | 5816100000 | 13.4 | 5036743000 | 2016-10-13 | 2019-04-13 | 30 | 72 | 4 | 20 | Completed | 2020-07-31 | 6109478000
HPR066 | Gurugram Highway Package 4 | Completed (history) | Highway Package | Gurugram | Government | Item rate with price variation | 4286700000 | 13.3 | 3716569000 | 2019-08-13 | 2021-06-13 | 22 | 49 | 4 | 26 | Completed | 2021-10-31 | 3968832000
HPR067 | Hyderabad Industrial Plant 6 | Completed (history) | Industrial Plant | Hyderabad | Government | Item rate with price variation | 8887600000 | 7.8 | 8194367000 | 2018-11-25 | 2020-10-25 | 23 | 66 | 3 | 23 | Completed | 2020-11-30 | 8314315000
HPR068 | Bengaluru Metro Viaduct 5 | Completed (history) | Metro Viaduct | Bengaluru | Government | EPC lump sum | 5926200000 | 7.5 | 5481735000 | 2022-04-02 | 2023-07-02 | 15 | 54 | 4 | 4 | Completed | 2023-10-31 | 6031344000
HPR069 | Lucknow Residential Towers 5 | Completed (history) | Residential Towers | Lucknow | Private | Cost plus fee | 3075400000 | 9.1 | 2795539000 | 2017-09-19 | 2020-02-19 | 29 | 84 | 2 | 17 | Completed | 2020-03-31 | 2851882000
HPR070 | Ahmedabad Residential Towers 8 | Completed (history) | Residential Towers | Ahmedabad | Private | Cost plus fee | 2372600000 | 11.5 | 2099751000 | 2016-02-21 | 2017-10-21 | 20 | 67 | 1 | 15 | Completed | 2017-12-31 | 2137532000
HPR071 | Lucknow Industrial Plant 4 | Completed (history) | Industrial Plant | Lucknow | Private | Cost plus fee | 9305600000 | 9.5 | 8421568000 | 2019-03-15 | 2020-11-15 | 20 | 90 | 4 | 18 | Completed | 2021-01-31 | 8692456000
HPR072 | Bengaluru IT Park 4 | Completed (history) | IT Park | Bengaluru | Government | EPC lump sum | 1734400000 | 9.2 | 1574835000 | 2018-08-01 | 2020-04-01 | 20 | 45 | 2 | 21 | Completed | 2020-06-30 | 1750985000
HPR073 | Pune Hospital Campus 7 | Completed (history) | Hospital Campus | Pune | Government | Item rate with price variation | 5378700000 | 7.1 | 4996812000 | 2021-07-18 | 2023-08-18 | 25 | 76 | 4 | 16 | Completed | 2024-01-31 | 5293705000
HPR074 | Lucknow Metro Viaduct 5 | Completed (history) | Metro Viaduct | Lucknow | Government | Item rate with price variation | 4269100000 | 11.7 | 3769615000 | 2019-05-12 | 2021-04-12 | 23 | 82 | 3 | 6 | Completed | 2021-09-30 | 4236321000
HPR075 | Kochi Commercial Complex 4 | Completed (history) | Commercial Complex | Kochi | Private | Lump sum | 9484200000 | 14.4 | 8118475000 | 2019-10-03 | 2020-09-03 | 11 | 56 | 3 | 11 | Completed | 2021-01-31 | 8890267000
HPR076 | Jaipur Logistics Hub 6 | Completed (history) | Logistics Hub | Jaipur | Private | Lump sum | 3334900000 | 10.5 | 2984736000 | 2019-01-28 | 2020-10-28 | 21 | 71 | 3 | 15 | Completed | 2020-12-31 | 3081991000
HPR077 | Surat Highway Package 4 | Completed (history) | Highway Package | Surat | Government | Item rate with price variation | 3658600000 | 14.6 | 3124444000 | 2020-09-17 | 2022-01-17 | 16 | 53 | 2 | 15 | Completed | 2022-03-31 | 3273141000
HPR078 | Ahmedabad Hospital Campus 4 | Completed (history) | Hospital Campus | Ahmedabad | Government | Item rate with price variation | 4545200000 | 9.7 | 4104316000 | 2020-11-17 | 2023-04-17 | 29 | 48 | 3 | 18 | Completed | 2023-11-30 | 4497075000
HPR079 | Bengaluru Logistics Hub 5 | Completed (history) | Logistics Hub | Bengaluru | Private | Lump sum | 2332700000 | 17.2 | 1931476000 | 2017-12-06 | 2019-10-06 | 22 | 60 | 2 | 15 | Completed | 2019-12-31 | 2007884000
HPR080 | Mumbai Logistics Hub 7 | Completed (history) | Logistics Hub | Mumbai | Private | Lump sum | 2643200000 | 6.9 | 2460819000 | 2019-03-16 | 2020-03-16 | 12 | 59 | 3 | 22 | Completed | 2020-03-31 | 2574189000
HPR081 | Gurugram Highway Package 6 | Completed (history) | Highway Package | Gurugram | Private | Cost plus fee | 7279000000 | 12.5 | 6369125000 | 2022-09-20 | 2024-04-20 | 19 | 69 | 3 | 9 | Completed | 2024-06-30 | 6730914000
HPR082 | Kochi Logistics Hub 8 | Completed (history) | Logistics Hub | Kochi | Private | Lump sum | 5376500000 | 9.6 | 4860356000 | 2016-09-13 | 2018-07-13 | 22 | 78 | 1 | 11 | Completed | 2018-09-30 | 5127152000
HPR083 | Surat Commercial Complex 6 | Completed (history) | Commercial Complex | Surat | Private | Lump sum | 5560700000 | 12.4 | 4871173000 | 2021-07-17 | 2022-07-17 | 12 | 69 | 2 | 19 | Completed | 2022-06-30 | 5246925000
HPR084 | Kochi Logistics Hub 8 | Completed (history) | Logistics Hub | Kochi | Government | EPC lump sum | 2560900000 | 5.6 | 2417490000 | 2022-03-18 | 2024-04-18 | 25 | 35 | 3 | 16 | Completed | 2024-08-31 | 2636128000
HPR085 | Bengaluru Hospital Campus 5 | Completed (history) | Hospital Campus | Bengaluru | Government | Item rate with price variation | 4917900000 | 10.2 | 4416274000 | 2020-07-27 | 2021-08-27 | 13 | 73 | 5 | 25 | Completed | 2021-11-30 | 4677361000
HPR086 | Lucknow Residential Towers 7 | Completed (history) | Residential Towers | Lucknow | Private | Lump sum | 3259000000 | 13.7 | 2812517000 | 2023-06-19 | 2024-04-19 | 10 | 56 | 4 | 9 | Completed | 2024-07-31 | 3191319000
HPR087 | Jaipur Highway Package 5 | Completed (history) | Highway Package | Jaipur | Government | Item rate with price variation | 1792800000 | 13.1 | 1557943000 | 2017-03-25 | 2018-09-25 | 18 | 70 | 2 | 4 | Completed | 2018-12-31 | 1600074000
HPR088 | Chennai Hospital Campus 6 | Completed (history) | Hospital Campus | Chennai | Government | Item rate with price variation | 2903100000 | 13 | 2525697000 | 2018-08-29 | 2020-08-29 | 24 | 88 | 3 | 12 | Completed | 2021-01-31 | 2589896000
HPR089 | Mumbai Water Treatment Plant 7 | Completed (history) | Water Treatment Plant | Mumbai | Government | EPC lump sum | 3381700000 | 13 | 2942079000 | 2022-03-05 | 2024-05-05 | 26 | 43 | 3 | 20 | Completed | 2024-10-31 | 3245413000
HPR090 | Delhi Metro Viaduct 8 | Completed (history) | Metro Viaduct | Delhi | Government | EPC lump sum | 3821500000 | 9 | 3477565000 | 2020-08-01 | 2023-02-01 | 30 | 20 | 3 | 10 | Completed | 2024-03-31 | 4220088000
HPR091 | Delhi Metro Viaduct 6 | Completed (history) | Metro Viaduct | Delhi | Government | Item rate with price variation | 4303500000 | 10.9 | 3834418000 | 2017-03-06 | 2019-07-06 | 28 | 34 | 4 | 9 | Completed | 2020-07-31 | 4676182000
HPR092 | Kolkata Water Treatment Plant 8 | Completed (history) | Water Treatment Plant | Kolkata | Government | Item rate with price variation | 4143400000 | 14.1 | 3559181000 | 2016-10-14 | 2018-08-14 | 22 | 83 | 4 | 17 | Completed | 2018-12-31 | 3813410000
HPR093 | Ahmedabad Commercial Complex 7 | Completed (history) | Commercial Complex | Ahmedabad | Private | Lump sum | 2150400000 | 5.8 | 2025677000 | 2018-04-27 | 2020-08-27 | 28 | 80 | 4 | 15 | Completed | 2020-10-31 | 2109438000
HPR094 | Delhi Commercial Complex 5 | Completed (history) | Commercial Complex | Delhi | Private | Lump sum | 3472000000 | 14.3 | 2975504000 | 2018-10-26 | 2020-01-26 | 15 | 69 | 4 | 15 | Completed | 2020-02-29 | 3274649000
HPR095 | Pune Logistics Hub 5 | Completed (history) | Logistics Hub | Pune | Private | Lump sum | 2550400000 | 14.2 | 2188243000 | 2021-03-27 | 2022-08-27 | 17 | 86 | 2 | 13 | Completed | 2022-09-30 | 2331271000
HPR096 | Hyderabad Hospital Campus 4 | Completed (history) | Hospital Campus | Hyderabad | Government | Item rate with price variation | 4284100000 | 10.1 | 3851406000 | 2016-10-06 | 2018-03-06 | 17 | 76 | 2 | 7 | Completed | 2018-05-31 | 3914910000
HPR097 | Gurugram Logistics Hub 8 | Completed (history) | Logistics Hub | Gurugram | Private | Lump sum | 4230200000 | 11.1 | 3760648000 | 2018-08-08 | 2019-08-08 | 12 | 79 | 2 | 26 | Completed | 2019-07-31 | 3868946000
HPR098 | Chennai Metro Viaduct 4 | Completed (history) | Metro Viaduct | Chennai | Government | Item rate with price variation | 4537100000 | 11.7 | 4006259000 | 2017-06-15 | 2018-12-15 | 18 | 57 | 4 | 11 | Completed | 2019-06-30 | 4374013000
HPR099 | Lucknow Industrial Plant 6 | Completed (history) | Industrial Plant | Lucknow | Private | Lump sum | 5714400000 | 9.2 | 5188675000 | 2019-10-12 | 2021-01-12 | 15 | 88 | 5 | 20 | Completed | 2021-05-31 | 5591502000
HPR100 | Nagpur IT Park 8 | Completed (history) | IT Park | Nagpur | Private | Cost plus fee | 8686500000 | 8.3 | 7965520000 | 2017-05-20 | 2018-04-20 | 11 | 98 | 4 | 5 | Completed | 2018-04-30 | 8462313000
HPR101 | Lucknow Commercial Complex 8 | Completed (history) | Commercial Complex | Lucknow | Private | Lump sum | 2732800000 | 10.4 | 2448589000 | 2020-09-02 | 2021-07-02 | 10 | 93 | 3 | 11 | Completed | 2021-09-30 | 2684401000
HPR102 | Gurugram Residential Towers 4 | Completed (history) | Residential Towers | Gurugram | Government | Item rate with price variation | 6815100000 | 14.8 | 5806465000 | 2018-09-10 | 2020-09-10 | 24 | 73 | 2 | 6 | Completed | 2020-11-30 | 6048244000
HPR103 | Lucknow Residential Towers 8 | Completed (history) | Residential Towers | Lucknow | Private | Cost plus fee | 7541400000 | 5.7 | 7111540000 | 2018-12-03 | 2020-05-03 | 17 | 76 | 3 | 7 | Completed | 2020-08-31 | 7746508000
HPR104 | Noida Commercial Complex 5 | Completed (history) | Commercial Complex | Noida | Private | Lump sum | 5605600000 | 12.4 | 4910506000 | 2023-04-30 | 2024-02-29 | 10 | 88 | 2 | 6 | Completed | 2024-03-31 | 5329706000
HPR105 | Gurugram Residential Towers 7 | Completed (history) | Residential Towers | Gurugram | Private | Lump sum | 3462400000 | 16.9 | 2877254000 | 2019-12-15 | 2021-01-15 | 13 | 66 | 2 | 17 | Completed | 2021-03-31 | 3090373000
HPR106 | Jaipur Data Centre 8 | Completed (history) | Data Centre | Jaipur | Government | Item rate with price variation | 6225500000 | 11.2 | 5528244000 | 2018-11-08 | 2020-02-08 | 15 | 85 | 3 | 13 | Completed | 2020-05-31 | 5769193000
HPR107 | Pune Industrial Plant 4 | Completed (history) | Industrial Plant | Pune | Government | Item rate with price variation | 3464300000 | 10.8 | 3090156000 | 2023-05-20 | 2025-07-20 | 26 | 60 | 2 | 16 | Completed | 2025-10-31 | 3233968000
HPR108 | Kolkata Hospital Campus 4 | Completed (history) | Hospital Campus | Kolkata | Private | Lump sum | 2435800000 | 8.4 | 2231193000 | 2020-06-23 | 2022-03-23 | 21 | 92 | 5 | 16 | Completed | 2022-06-30 | 2433446000
HPR109 | Pune Logistics Hub 5 | Completed (history) | Logistics Hub | Pune | Private | Lump sum | 1700600000 | 7.7 | 1569654000 | 2022-12-27 | 2023-12-27 | 12 | 90 | 2 | 7 | Completed | 2023-11-30 | 1541149000
HPR110 | Gurugram Metro Viaduct 5 | Completed (history) | Metro Viaduct | Gurugram | Private | Cost plus fee | 6077500000 | 8.9 | 5536602000 | 2016-06-27 | 2017-12-27 | 18 | 93 | 5 | 12 | Completed | 2018-03-31 | 6037784000
HPR111 | Surat Water Treatment Plant 7 | Completed (history) | Water Treatment Plant | Surat | Government | Item rate with price variation | 3119200000 | 12.2 | 2738658000 | 2019-05-30 | 2021-01-30 | 20 | 79 | 3 | 5 | Completed | 2021-07-31 | 3096186000
HPR112 | Mumbai Water Treatment Plant 6 | Completed (history) | Water Treatment Plant | Mumbai | Government | Item rate with price variation | 4007300000 | 8.3 | 3674694000 | 2022-01-23 | 2023-04-23 | 15 | 54 | 3 | 22 | Completed | 2023-08-31 | 4156156000
HPR113 | Kochi Data Centre 6 | Completed (history) | Data Centre | Kochi | Private | Cost plus fee | 5761700000 | 12.8 | 5024202000 | 2019-03-14 | 2020-08-14 | 17 | 76 | 4 | 17 | Completed | 2020-10-31 | 5620867000
HPR114 | Lucknow Commercial Complex 8 | Completed (history) | Commercial Complex | Lucknow | Private | Cost plus fee | 4628700000 | 8.7 | 4226003000 | 2017-07-16 | 2018-09-16 | 14 | 75 | 3 | 13 | Completed | 2019-01-31 | 4602042000
HPR115 | Pune Residential Towers 8 | Completed (history) | Residential Towers | Pune | Government | Item rate with price variation | 4418800000 | 11.3 | 3919476000 | 2022-08-29 | 2023-10-29 | 14 | 69 | 5 | 4 | Completed | 2024-03-31 | 4433713000
HPR116 | Chennai Industrial Plant 7 | Completed (history) | Industrial Plant | Chennai | Private | Lump sum | 3504000000 | 13 | 3048480000 | 2020-06-10 | 2022-03-10 | 21 | 71 | 2 | 20 | Completed | 2022-06-30 | 3276031000
HPR117 | Jaipur Highway Package 4 | Completed (history) | Highway Package | Jaipur | Government | Item rate with price variation | 3144900000 | 9.7 | 2839845000 | 2022-11-11 | 2023-12-11 | 13 | 98 | 3 | 10 | Completed | 2024-02-29 | 2969461000
HPR118 | Delhi Water Treatment Plant 6 | Completed (history) | Water Treatment Plant | Delhi | Government | Item rate with price variation | 5378100000 | 12.3 | 4716594000 | 2018-06-10 | 2020-08-10 | 26 | 77 | 3 | 7 | Completed | 2021-03-31 | 5012420000
HPR119 | Nagpur Logistics Hub 6 | Completed (history) | Logistics Hub | Nagpur | Private | Lump sum | 3180100000 | 8.5 | 2909792000 | 2016-04-13 | 2017-12-13 | 20 | 87 | 4 | 4 | Completed | 2018-03-31 | 3092626000
HPR120 | Jaipur Highway Package 7 | Completed (history) | Highway Package | Jaipur | Government | Item rate with price variation | 3358300000 | 9.1 | 3052695000 | 2018-02-24 | 2019-08-24 | 18 | 80 | 2 | 22 | Completed | 2019-12-31 | 3191317000
HPR121 | Lucknow Commercial Complex 5 | Completed (history) | Commercial Complex | Lucknow | Private | Lump sum | 2843000000 | 11.8 | 2507526000 | 2016-12-22 | 2017-10-22 | 10 | 63 | 3 | 19 | Completed | 2017-12-31 | 2708422000
HPR122 | Mumbai Industrial Plant 6 | Completed (history) | Industrial Plant | Mumbai | Private | Cost plus fee | 10069200000 | 14.8 | 8578958000 | 2018-11-27 | 2020-01-27 | 14 | 77 | 4 | 11 | Completed | 2020-06-30 | 9171867000
HPR123 | Chennai IT Park 6 | Completed (history) | IT Park | Chennai | Private | Cost plus fee | 1595400000 | 6.7 | 1488508000 | 2017-05-25 | 2018-07-25 | 14 | 68 | 3 | 18 | Completed | 2018-06-30 | 1532666000
HPR124 | Chennai Water Treatment Plant 7 | Completed (history) | Water Treatment Plant | Chennai | Government | Item rate with price variation | 3152700000 | 12.4 | 2761765000 | 2022-12-12 | 2024-06-12 | 18 | 85 | 3 | 4 | Completed | 2024-09-30 | 2870527000
HPR125 | Chennai Commercial Complex 6 | Completed (history) | Commercial Complex | Chennai | Government | Item rate with price variation | 5460000000 | 5 | 5187000000 | 2017-09-16 | 2019-05-16 | 20 | 60 | 3 | 21 | Completed | 2019-07-31 | 5615529000
HPR126 | Chennai Industrial Plant 6 | Completed (history) | Industrial Plant | Chennai | Private | Lump sum | 7113500000 | 9.3 | 6451944000 | 2018-05-27 | 2020-05-27 | 24 | 54 | 2 | 15 | Completed | 2020-05-31 | 6801912000
HPR127 | Bengaluru IT Park 5 | Completed (history) | IT Park | Bengaluru | Private | Lump sum | 4501800000 | 7.6 | 4159663000 | 2018-03-06 | 2019-01-06 | 10 | 71 | 4 | 23 | Completed | 2018-12-31 | 4312980000
HPR128 | Gurugram Residential Towers 4 | Completed (history) | Residential Towers | Gurugram | Private | Lump sum | 1558800000 | 9.3 | 1413832000 | 2016-11-21 | 2018-11-21 | 24 | 75 | 2 | 17 | Completed | 2018-11-30 | 1439070000
HPR129 | Bengaluru Hospital Campus 7 | Completed (history) | Hospital Campus | Bengaluru | Government | Item rate with price variation | 3679200000 | 9.3 | 3337034000 | 2017-10-19 | 2019-10-19 | 24 | 64 | 4 | 10 | Completed | 2020-04-30 | 3933427000
HPR130 | Pune Logistics Hub 8 | Completed (history) | Logistics Hub | Pune | Government | EPC lump sum | 5221100000 | 6.4 | 4886950000 | 2019-04-11 | 2020-04-11 | 12 | 40 | 3 | 6 | Completed | 2020-06-30 | 5132803000
HPR131 | Ahmedabad Residential Towers 6 | Completed (history) | Residential Towers | Ahmedabad | Private | Cost plus fee | 8482100000 | 13.8 | 7311570000 | 2023-08-04 | 2025-09-04 | 25 | 73 | 2 | 20 | Completed | 2026-01-31 | 8384965000
HPR132 | Pune Metro Viaduct 8 | Completed (history) | Metro Viaduct | Pune | Government | EPC lump sum | 10088600000 | 12 | 8877968000 | 2019-10-18 | 2021-02-18 | 16 | 45 | 4 | 8 | Completed | 2021-08-31 | 9865088000
HPR133 | Ahmedabad Residential Towers 5 | Completed (history) | Residential Towers | Ahmedabad | Private | Cost plus fee | 5226800000 | 9.3 | 4740708000 | 2022-06-16 | 2024-03-16 | 21 | 66 | 4 | 18 | Completed | 2024-06-30 | 4875766000
HPR134 | Delhi IT Park 4 | Completed (history) | IT Park | Delhi | Private | Cost plus fee | 4523300000 | 15 | 3844805000 | 2018-05-14 | 2019-03-14 | 10 | 84 | 5 | 20 | Completed | 2019-06-30 | 4255344000
HPR135 | Delhi Data Centre 4 | Completed (history) | Data Centre | Delhi | Private | Lump sum | 1545300000 | 13.1 | 1342866000 | 2020-08-15 | 2022-02-15 | 18 | 73 | 4 | 9 | Completed | 2022-02-28 | 1421158000
HPR136 | Chennai Water Treatment Plant 6 | Completed (history) | Water Treatment Plant | Chennai | Government | Item rate with price variation | 2242400000 | 11.8 | 1977797000 | 2018-08-04 | 2021-02-04 | 30 | 84 | 3 | 17 | Completed | 2021-06-30 | 2100522000
HPR137 | Jaipur Commercial Complex 7 | Completed (history) | Commercial Complex | Jaipur | Private | Cost plus fee | 6454900000 | 11.9 | 5686767000 | 2021-12-25 | 2023-06-25 | 18 | 79 | 3 | 20 | Completed | 2023-09-30 | 6088977000
HPR138 | Lucknow IT Park 8 | Completed (history) | IT Park | Lucknow | Private | Cost plus fee | 4675000000 | 9.5 | 4230875000 | 2018-07-07 | 2019-06-07 | 11 | 60 | 2 | 15 | Completed | 2019-06-30 | 4252703000
HPR139 | Pune Highway Package 7 | Completed (history) | Highway Package | Pune | Government | Item rate with price variation | 1019000000 | 11.6 | 900796000 | 2021-11-29 | 2023-07-29 | 20 | 69 | 4 | 10 | Completed | 2023-11-30 | 986230000
HPR140 | Delhi Commercial Complex 5 | Completed (history) | Commercial Complex | Delhi | Private | Lump sum | 8387600000 | 6.2 | 7867569000 | 2019-11-16 | 2021-05-16 | 18 | 85 | 4 | 4 | Completed | 2021-09-30 | 8680068000
HPR141 | Delhi Water Treatment Plant 7 | Completed (history) | Water Treatment Plant | Delhi | Private | Cost plus fee | 5049800000 | 11.2 | 4484222000 | 2021-07-10 | 2023-05-10 | 22 | 74 | 2 | 17 | Completed | 2023-07-31 | 4759296000
HPR142 | Surat Residential Towers 5 | Completed (history) | Residential Towers | Surat | Private | Lump sum | 4701300000 | 11.2 | 4174754000 | 2021-05-14 | 2023-05-14 | 24 | 96 | 1 | 12 | Completed | 2023-06-30 | 4410032000
HPR143 | Ahmedabad Hospital Campus 5 | Completed (history) | Hospital Campus | Ahmedabad | Government | Item rate with price variation | 3757500000 | 11.8 | 3314115000 | 2018-04-26 | 2020-02-26 | 22 | 71 | 3 | 9 | Completed | 2020-05-31 | 3445319000
HPR144 | Chennai IT Park 7 | Completed (history) | IT Park | Chennai | Government | Item rate with price variation | 2788400000 | 10 | 2509560000 | 2018-05-13 | 2020-04-13 | 23 | 68 | 3 | 11 | Completed | 2020-09-30 | 2778466000
HPR145 | Pune Water Treatment Plant 7 | Completed (history) | Water Treatment Plant | Pune | Private | Cost plus fee | 4776400000 | 9.3 | 4332195000 | 2018-05-14 | 2020-04-14 | 23 | 56 | 2 | 13 | Completed | 2020-10-31 | 5038053000
HPR146 | Bengaluru Residential Towers 5 | Completed (history) | Residential Towers | Bengaluru | Government | Item rate with price variation | 6317300000 | 9.3 | 5729791000 | 2021-08-29 | 2022-10-29 | 14 | 43 | 4 | 26 | Completed | 2022-11-30 | 6171396000
HPR147 | Jaipur Commercial Complex 6 | Completed (history) | Commercial Complex | Jaipur | Private | Lump sum | 2115500000 | 18 | 1734710000 | 2020-03-11 | 2022-05-11 | 26 | 56 | 3 | 14 | Completed | 2022-07-31 | 1863720000
HPR148 | Nagpur Hospital Campus 4 | Completed (history) | Hospital Campus | Nagpur | Government | Item rate with price variation | 2997000000 | 14 | 2577420000 | 2018-08-29 | 2021-07-29 | 35 | 95 | 4 | 20 | Completed | 2021-12-31 | 2636207000
HPR149 | Ahmedabad Highway Package 7 | Completed (history) | Highway Package | Ahmedabad | Government | Item rate with price variation | 5855800000 | 13.1 | 5088690000 | 2017-03-27 | 2018-06-27 | 15 | 46 | 3 | 9 | Completed | 2018-10-31 | 5500808000
HPR150 | Lucknow Highway Package 7 | Completed (history) | Highway Package | Lucknow | Private | Lump sum | 5758900000 | 9.2 | 5229081000 | 2018-06-14 | 2019-12-14 | 18 | 93 | 3 | 22 | Completed | 2020-03-31 | 5528741000
HPR151 | Hyderabad Commercial Complex 8 | Completed (history) | Commercial Complex | Hyderabad | Private | Lump sum | 9191200000 | 12.5 | 8042300000 | 2017-03-05 | 2018-09-05 | 18 | 83 | 2 | 14 | Completed | 2018-10-31 | 8156042000
HPR152 | Mumbai Data Centre 5 | Completed (history) | Data Centre | Mumbai | Private | Lump sum | 8262400000 | 10.5 | 7394848000 | 2017-10-07 | 2018-08-07 | 10 | 39 | 3 | 16 | Completed | 2018-10-31 | 7560977000
HPR153 | Ahmedabad Data Centre 5 | Completed (history) | Data Centre | Ahmedabad | Private | Cost plus fee | 5561800000 | 7 | 5172474000 | 2016-07-12 | 2017-08-12 | 13 | 60 | 4 | 11 | Completed | 2017-11-30 | 5816047000
HPR154 | Bengaluru Metro Viaduct 5 | Completed (history) | Metro Viaduct | Bengaluru | Private | Lump sum | 2581200000 | 13.6 | 2230157000 | 2017-04-30 | 2019-01-30 | 21 | 88 | 5 | 11 | Completed | 2019-05-31 | 2417735000
HPR155 | Noida Data Centre 8 | Completed (history) | Data Centre | Noida | Private | Lump sum | 7026800000 | 7.9 | 6471683000 | 2016-06-19 | 2017-04-19 | 10 | 89 | 5 | 8 | Completed | 2017-07-31 | 7259082000
HPR156 | Jaipur Industrial Plant 7 | Completed (history) | Industrial Plant | Jaipur | Private | Lump sum | 8933900000 | 9.2 | 8111981000 | 2020-09-06 | 2021-11-06 | 14 | 82 | 5 | 18 | Completed | 2022-02-28 | 9278763000
HPR157 | Ahmedabad Logistics Hub 8 | Completed (history) | Logistics Hub | Ahmedabad | Private | Lump sum | 6091900000 | 12.4 | 5336504000 | 2019-10-17 | 2020-12-17 | 14 | 76 | 3 | 20 | Completed | 2021-02-28 | 5894862000
HPR158 | Bengaluru Data Centre 6 | Completed (history) | Data Centre | Bengaluru | Private | Lump sum | 5152800000 | 10.9 | 4591145000 | 2016-08-20 | 2017-12-20 | 16 | 87 | 4 | 18 | Completed | 2018-04-30 | 5335465000
HPR159 | Surat Metro Viaduct 4 | Completed (history) | Metro Viaduct | Surat | Government | EPC lump sum | 4457600000 | 5 | 4234720000 | 2016-08-16 | 2019-03-16 | 31 | 52 | 3 | 14 | Completed | 2019-11-30 | 4632950000
HPR160 | Surat Metro Viaduct 8 | Completed (history) | Metro Viaduct | Surat | Government | EPC lump sum | 5433500000 | 6.7 | 5069456000 | 2016-01-24 | 2017-10-24 | 21 | 20 | 3 | 15 | Completed | 2018-03-31 | 5749846000
HPR161 | Kolkata IT Park 7 | Completed (history) | IT Park | Kolkata | Private | Lump sum | 3922100000 | 6 | 3686774000 | 2020-07-04 | 2021-11-04 | 16 | 59 | 2 | 21 | Completed | 2021-11-30 | 3763868000
HPR162 | Lucknow Commercial Complex 6 | Completed (history) | Commercial Complex | Lucknow | Private | Lump sum | 3422200000 | 15.9 | 2878070000 | 2016-07-10 | 2018-02-10 | 19 | 46 | 2 | 14 | Completed | 2018-05-31 | 3044582000
HPR163 | Chennai Metro Viaduct 5 | Completed (history) | Metro Viaduct | Chennai | Government | Item rate with price variation | 6525600000 | 10.3 | 5853463000 | 2018-02-04 | 2020-03-04 | 25 | 66 | 5 | 12 | Completed | 2021-01-31 | 7177810000
HPR164 | Gurugram Data Centre 6 | Completed (history) | Data Centre | Gurugram | Private | Lump sum | 8415200000 | 9.6 | 7607341000 | 2017-07-07 | 2019-03-07 | 20 | 95 | 4 | 15 | Completed | 2019-07-31 | 8622838000
HPR165 | Jaipur IT Park 5 | Completed (history) | IT Park | Jaipur | Private | Lump sum | 3039300000 | 12.4 | 2662427000 | 2020-05-09 | 2022-01-09 | 20 | 54 | 2 | 12 | Completed | 2022-03-31 | 2805885000
HPR166 | Hyderabad Data Centre 7 | Completed (history) | Data Centre | Hyderabad | Private | Lump sum | 5756900000 | 11.2 | 5112127000 | 2020-06-30 | 2021-04-30 | 10 | 43 | 3 | 18 | Completed | 2021-06-30 | 5621319000
HPR167 | Mumbai Logistics Hub 4 | Completed (history) | Logistics Hub | Mumbai | Private | Lump sum | 2312600000 | 8.8 | 2109091000 | 2019-04-05 | 2020-07-05 | 15 | 76 | 3 | 13 | Completed | 2020-09-30 | 2208531000
HPR168 | Hyderabad Water Treatment Plant 4 | Completed (history) | Water Treatment Plant | Hyderabad | Government | EPC lump sum | 5713200000 | 15.4 | 4833367000 | 2019-10-15 | 2021-03-15 | 17 | 20 | 3 | 8 | Completed | 2021-05-31 | 5190217000
HPR169 | Gurugram IT Park 4 | Completed (history) | IT Park | Gurugram | Private | Lump sum | 5874200000 | 16.3 | 4916705000 | 2018-08-08 | 2020-04-08 | 20 | 67 | 3 | 7 | Completed | 2020-06-30 | 5208239000
HPR170 | Hyderabad Water Treatment Plant 6 | Completed (history) | Water Treatment Plant | Hyderabad | Government | EPC lump sum | 6311500000 | 12.1 | 5547808000 | 2017-10-14 | 2020-01-14 | 27 | 48 | 2 | 6 | Completed | 2020-08-31 | 5863346000
HPR171 | Nagpur IT Park 8 | Completed (history) | IT Park | Nagpur | Private | Lump sum | 2915000000 | 8.3 | 2673055000 | 2017-05-19 | 2018-03-19 | 10 | 93 | 2 | 22 | Completed | 2018-03-31 | 2742824000
HPR172 | Chennai Water Treatment Plant 5 | Completed (history) | Water Treatment Plant | Chennai | Government | Item rate with price variation | 3386800000 | 12.9 | 2949903000 | 2019-02-02 | 2020-12-02 | 22 | 76 | 1 | 14 | Completed | 2021-06-30 | 3078857000
HPR173 | Kochi Residential Towers 7 | Completed (history) | Residential Towers | Kochi | Private | Lump sum | 8719200000 | 12.1 | 7664177000 | 2023-03-10 | 2024-08-10 | 17 | 98 | 3 | 21 | Completed | 2024-09-30 | 7924570000
HPR174 | Ahmedabad Residential Towers 5 | Completed (history) | Residential Towers | Ahmedabad | Private | Lump sum | 4947400000 | 13.1 | 4299291000 | 2017-10-17 | 2019-01-17 | 15 | 62 | 3 | 22 | Completed | 2019-01-31 | 4493422000
HPR175 | Kochi Water Treatment Plant 6 | Completed (history) | Water Treatment Plant | Kochi | Government | Item rate with price variation | 2271400000 | 14.8 | 1935233000 | 2017-10-23 | 2019-07-23 | 21 | 79 | 4 | 13 | Completed | 2019-11-30 | 2000974000
HPR176 | Hyderabad Hospital Campus 6 | Completed (history) | Hospital Campus | Hyderabad | Government | Item rate with price variation | 7238200000 | 12.2 | 6355140000 | 2022-06-24 | 2023-12-24 | 18 | 56 | 3 | 27 | Completed | 2024-04-30 | 6906175000
HPR177 | Lucknow Water Treatment Plant 4 | Completed (history) | Water Treatment Plant | Lucknow | Government | Item rate with price variation | 3846100000 | 13.4 | 3330723000 | 2018-08-14 | 2020-07-14 | 23 | 78 | 3 | 13 | Completed | 2020-11-30 | 3774403000
HPR178 | Noida Commercial Complex 4 | Completed (history) | Commercial Complex | Noida | Private | Lump sum | 8204300000 | 12.4 | 7186967000 | 2022-01-15 | 2023-12-15 | 23 | 85 | 2 | 16 | Completed | 2024-01-31 | 7519594000
HPR179 | Gurugram Logistics Hub 6 | Completed (history) | Logistics Hub | Gurugram | Private | Lump sum | 1892400000 | 9 | 1722084000 | 2022-11-23 | 2024-01-23 | 14 | 60 | 1 | 10 | Completed | 2024-03-31 | 1701316000
HPR180 | Kochi Highway Package 8 | Completed (history) | Highway Package | Kochi | Government | Item rate with price variation | 1114700000 | 9.1 | 1013262000 | 2018-11-26 | 2020-04-26 | 17 | 71 | 4 | 16 | Completed | 2020-10-31 | 1101604000
HPR181 | Mumbai Commercial Complex 8 | Completed (history) | Commercial Complex | Mumbai | Private | Lump sum | 5128500000 | 8.7 | 4682320000 | 2020-03-21 | 2021-07-21 | 16 | 71 | 1 | 12 | Completed | 2021-06-30 | 4800881000
HPR182 | Lucknow Industrial Plant 8 | Completed (history) | Industrial Plant | Lucknow | Private | Cost plus fee | 5185000000 | 10 | 4666500000 | 2018-05-26 | 2020-05-26 | 24 | 95 | 3 | 17 | Completed | 2020-08-31 | 4745887000
HPR183 | Delhi Industrial Plant 5 | Completed (history) | Industrial Plant | Delhi | Private | Cost plus fee | 1879600000 | 7.7 | 1734871000 | 2020-11-27 | 2022-12-27 | 25 | 71 | 4 | 23 | Completed | 2023-06-30 | 1960947000
HPR184 | Pune Highway Package 7 | Completed (history) | Highway Package | Pune | Government | Item rate with price variation | 3087800000 | 11 | 2748142000 | 2018-07-19 | 2020-05-19 | 22 | 66 | 2 | 17 | Completed | 2021-01-31 | 3032824000
HPR185 | Hyderabad Commercial Complex 5 | Completed (history) | Commercial Complex | Hyderabad | Private | Cost plus fee | 9832100000 | 14.8 | 8376949000 | 2022-10-30 | 2024-09-30 | 23 | 66 | 2 | 8 | Completed | 2025-02-28 | 9425494000
HPR186 | Bengaluru Highway Package 4 | Completed (history) | Highway Package | Bengaluru | Government | Item rate with price variation | 2502300000 | 10 | 2252070000 | 2018-07-30 | 2020-09-30 | 26 | 31 | 3 | 7 | Completed | 2021-02-28 | 2544307000
HPR187 | Jaipur Water Treatment Plant 8 | Completed (history) | Water Treatment Plant | Jaipur | Private | Lump sum | 2849300000 | 12.2 | 2501685000 | 2018-10-21 | 2021-05-21 | 31 | 64 | 2 | 9 | Completed | 2021-11-30 | 2641751000
HPR188 | Nagpur IT Park 6 | Completed (history) | IT Park | Nagpur | Private | Lump sum | 5318100000 | 9.8 | 4796926000 | 2020-01-15 | 2021-10-15 | 21 | 77 | 4 | 24 | Completed | 2021-12-31 | 5485384000
HPR189 | Kolkata IT Park 7 | Completed (history) | IT Park | Kolkata | Private | Cost plus fee | 5083200000 | 9.3 | 4610462000 | 2021-03-17 | 2022-10-17 | 19 | 63 | 1 | 11 | Completed | 2023-02-28 | 4764739000
HPR190 | Jaipur Highway Package 4 | Completed (history) | Highway Package | Jaipur | Private | Cost plus fee | 2810800000 | 11 | 2501612000 | 2018-05-31 | 2020-03-31 | 22 | 66 | 2 | 4 | Completed | 2020-03-31 | 2619760000
HPR191 | Jaipur Logistics Hub 5 | Completed (history) | Logistics Hub | Jaipur | Private | Lump sum | 11454300000 | 10.7 | 10228690000 | 2017-10-25 | 2019-11-25 | 25 | 72 | 3 | 10 | Completed | 2020-05-31 | 10789166000
HPR192 | Mumbai Highway Package 5 | Completed (history) | Highway Package | Mumbai | Government | Item rate with price variation | 2462700000 | 6.7 | 2297699000 | 2018-07-10 | 2019-12-10 | 17 | 84 | 2 | 16 | Completed | 2020-02-29 | 2429174000
HPR193 | Lucknow Data Centre 6 | Completed (history) | Data Centre | Lucknow | Private | Cost plus fee | 5542100000 | 9.7 | 5004516000 | 2020-12-10 | 2021-10-10 | 10 | 73 | 4 | 11 | Completed | 2021-11-30 | 5553433000
HPR194 | Nagpur Data Centre 8 | Completed (history) | Data Centre | Nagpur | Government | Item rate with price variation | 7864400000 | 9.8 | 7093689000 | 2020-12-30 | 2023-02-28 | 26 | 73 | 3 | 19 | Completed | 2023-05-31 | 7307521000
HPR195 | Hyderabad Commercial Complex 6 | Completed (history) | Commercial Complex | Hyderabad | Private | Lump sum | 5692600000 | 11.8 | 5020873000 | 2022-04-21 | 2023-02-21 | 10 | 74 | 2 | 21 | Completed | 2023-02-28 | 5088453000
HPR196 | Surat Data Centre 7 | Completed (history) | Data Centre | Surat | Private | Cost plus fee | 3984100000 | 9.9 | 3589674000 | 2018-09-30 | 2020-02-29 | 17 | 55 | 5 | 11 | Completed | 2020-06-30 | 3735006000
HPR197 | Mumbai Residential Towers 6 | Completed (history) | Residential Towers | Mumbai | Private | Lump sum | 2439200000 | 6.6 | 2278213000 | 2020-07-14 | 2022-11-14 | 28 | 53 | 2 | 21 | Completed | 2023-03-31 | 2603311000
HPR198 | Gurugram Commercial Complex 7 | Completed (history) | Commercial Complex | Gurugram | Government | Item rate with price variation | 4961500000 | 9 | 4514965000 | 2022-12-05 | 2024-10-05 | 22 | 53 | 2 | 10 | Completed | 2025-02-28 | 4984529000
HPR199 | Noida Data Centre 8 | Completed (history) | Data Centre | Noida | Private | Cost plus fee | 7316500000 | 7.8 | 6745813000 | 2019-11-10 | 2022-02-10 | 27 | 74 | 4 | 23 | Completed | 2022-09-30 | 7226099000
HPR200 | Surat Hospital Campus 4 | Completed (history) | Hospital Campus | Surat | Government | Item rate with price variation | 4529000000 | 9.5 | 4098745000 | 2016-11-27 | 2017-09-27 | 10 | 53 | 4 | 12 | Completed | 2017-12-31 | 4380313000
HPR201 | Nagpur Industrial Plant 6 | Completed (history) | Industrial Plant | Nagpur | Private | Lump sum | 14000000000 | 11.1 | 12446000000 | 2019-12-26 | 2021-02-26 | 14 | 78 | 3 | 22 | Completed | 2021-05-31 | 13453151000
HPR202 | Bengaluru Industrial Plant 6 | Completed (history) | Industrial Plant | Bengaluru | Government | Item rate with price variation | 13418000000 | 7.9 | 12357978000 | 2016-08-20 | 2018-05-20 | 21 | 56 | 3 | 14 | Completed | 2018-10-31 | 14508094000
HPR203 | Chennai Highway Package 7 | Completed (history) | Highway Package | Chennai | Government | Item rate with price variation | 8585100000 | 11.5 | 7597814000 | 2017-10-06 | 2020-11-06 | 37 | 67 | 4 | 10 | Completed | 2022-02-28 | 9220641000
HPR204 | Pune Residential Towers 8 | Completed (history) | Residential Towers | Pune | Private | Cost plus fee | 3284200000 | 15.1 | 2788286000 | 2016-09-15 | 2017-10-15 | 13 | 85 | 2 | 14 | Completed | 2017-12-31 | 2825427000
HPR205 | Kolkata Data Centre 6 | Completed (history) | Data Centre | Kolkata | Private | Cost plus fee | 2987800000 | 10.6 | 2671093000 | 2016-04-15 | 2018-03-15 | 23 | 98 | 4 | 15 | Completed | 2018-09-30 | 2751285000
HPR206 | Nagpur Commercial Complex 6 | Completed (history) | Commercial Complex | Nagpur | Private | Cost plus fee | 10819400000 | 10.4 | 9694182000 | 2017-02-09 | 2017-12-09 | 10 | 75 | 3 | 9 | Completed | 2018-01-31 | 9704906000
HPR207 | Lucknow IT Park 6 | Completed (history) | IT Park | Lucknow | Government | Item rate with price variation | 2717700000 | 9.1 | 2470389000 | 2022-05-09 | 2024-03-09 | 22 | 38 | 2 | 17 | Completed | 2024-09-30 | 2541634000
HPR208 | Nagpur IT Park 8 | Completed (history) | IT Park | Nagpur | Private | Cost plus fee | 2669300000 | 11.7 | 2356992000 | 2020-03-18 | 2021-05-18 | 14 | 65 | 4 | 8 | Completed | 2021-07-31 | 2512447000
HPR209 | Chennai Data Centre 8 | Completed (history) | Data Centre | Chennai | Government | Item rate with price variation | 5495500000 | 13.3 | 4764598000 | 2021-01-29 | 2022-08-29 | 19 | 77 | 4 | 8 | Completed | 2023-04-30 | 5848709000
HPR210 | Jaipur Logistics Hub 6 | Completed (history) | Logistics Hub | Jaipur | Private | Lump sum | 5673100000 | 12 | 4992328000 | 2020-05-05 | 2022-08-05 | 27 | 80 | 2 | 14 | Completed | 2022-09-30 | 5257883000
HPR211 | Lucknow Metro Viaduct 5 | Completed (history) | Metro Viaduct | Lucknow | Private | Lump sum | 4095900000 | 10.1 | 3682214000 | 2017-05-31 | 2020-04-30 | 35 | 57 | 5 | 17 | Completed | 2020-11-30 | 4382249000
HPR212 | Noida IT Park 7 | Completed (history) | IT Park | Noida | Private | Lump sum | 3594900000 | 16.5 | 3001742000 | 2019-01-01 | 2020-06-01 | 17 | 39 | 4 | 9 | Completed | 2020-11-30 | 3432766000
HPR213 | Ahmedabad Residential Towers 6 | Completed (history) | Residential Towers | Ahmedabad | Government | EPC lump sum | 2307000000 | 13.2 | 2002476000 | 2021-01-26 | 2022-04-26 | 15 | 43 | 2 | 16 | Completed | 2022-07-31 | 2202182000
HPR214 | Noida IT Park 4 | Completed (history) | IT Park | Noida | Private | Lump sum | 4061800000 | 11.1 | 3610940000 | 2017-03-25 | 2018-02-25 | 11 | 58 | 3 | 21 | Completed | 2018-04-30 | 3772607000
HPR215 | Ahmedabad Water Treatment Plant 4 | Completed (history) | Water Treatment Plant | Ahmedabad | Government | Item rate with price variation | 2920000000 | 6.8 | 2721440000 | 2021-03-05 | 2022-07-05 | 16 | 57 | 2 | 14 | Completed | 2022-12-31 | 2965698000
HPR216 | Mumbai Commercial Complex 5 | Completed (history) | Commercial Complex | Mumbai | Government | Item rate with price variation | 3104900000 | 12.7 | 2710578000 | 2021-11-06 | 2023-05-06 | 18 | 43 | 3 | 11 | Completed | 2023-07-31 | 2919119000
HPR217 | Gurugram Industrial Plant 7 | Completed (history) | Industrial Plant | Gurugram | Private | Cost plus fee | 3273000000 | 11.3 | 2903151000 | 2018-09-03 | 2020-01-03 | 16 | 69 | 3 | 20 | Completed | 2019-12-31 | 3002203000
HPR218 | Delhi Data Centre 5 | Completed (history) | Data Centre | Delhi | Private | Lump sum | 5131500000 | 8.3 | 4705586000 | 2023-04-22 | 2025-04-22 | 24 | 39 | 4 | 23 | Completed | 2026-02-28 | 5565824000
HPR219 | Lucknow Residential Towers 8 | Completed (history) | Residential Towers | Lucknow | Private | Lump sum | 5067100000 | 11.7 | 4474249000 | 2021-09-02 | 2022-11-02 | 14 | 59 | 3 | 13 | Completed | 2022-12-31 | 4826763000
HPR220 | Hyderabad Commercial Complex 6 | Completed (history) | Commercial Complex | Hyderabad | Private | Lump sum | 3427100000 | 13.1 | 2978150000 | 2022-07-04 | 2024-01-04 | 18 | 64 | 2 | 15 | Completed | 2024-05-31 | 3088851000
HPR221 | Nagpur Highway Package 4 | Completed (history) | Highway Package | Nagpur | Government | Item rate with price variation | 3304000000 | 16.6 | 2755536000 | 2018-03-04 | 2020-06-04 | 27 | 62 | 4 | 12 | Completed | 2021-01-31 | 2928086000
HPR222 | Kolkata Highway Package 4 | Completed (history) | Highway Package | Kolkata | Private | Cost plus fee | 5876900000 | 15.3 | 4977734000 | 2020-12-17 | 2022-05-17 | 17 | 67 | 2 | 17 | Completed | 2022-07-31 | 5031477000
HPR223 | Bengaluru Hospital Campus 8 | Completed (history) | Hospital Campus | Bengaluru | Government | Item rate with price variation | 5084600000 | 8.3 | 4662578000 | 2022-03-11 | 2023-09-11 | 18 | 89 | 4 | 20 | Completed | 2024-04-30 | 5457249000
HPR224 | Pune Hospital Campus 6 | Completed (history) | Hospital Campus | Pune | Government | Item rate with price variation | 4220200000 | 11.3 | 3743317000 | 2016-03-26 | 2018-08-26 | 29 | 91 | 3 | 10 | Completed | 2019-04-30 | 4026855000
HPR225 | Surat IT Park 4 | Completed (history) | IT Park | Surat | Private | Cost plus fee | 3680600000 | 14.2 | 3157955000 | 2021-11-12 | 2023-05-12 | 18 | 66 | 3 | 24 | Completed | 2023-05-31 | 3229145000
HPR226 | Kochi Industrial Plant 8 | Completed (history) | Industrial Plant | Kochi | Private | Lump sum | 4674300000 | 13.2 | 4057292000 | 2019-09-08 | 2021-06-08 | 21 | 55 | 2 | 14 | Completed | 2021-08-31 | 4409401000
HPR227 | Gurugram Logistics Hub 8 | Completed (history) | Logistics Hub | Gurugram | Government | Item rate with price variation | 3753000000 | 10.1 | 3373947000 | 2022-02-07 | 2024-02-07 | 24 | 50 | 3 | 13 | Completed | 2024-07-31 | 3849908000
HPR228 | Mumbai Highway Package 6 | Completed (history) | Highway Package | Mumbai | Government | Item rate with price variation | 4196900000 | 5 | 3987055000 | 2020-05-23 | 2022-05-23 | 24 | 51 | 3 | 17 | Completed | 2023-03-31 | 4687817000
HPR229 | Pune Logistics Hub 5 | Completed (history) | Logistics Hub | Pune | Private | Lump sum | 2304500000 | 10.3 | 2067136000 | 2020-12-26 | 2022-04-26 | 16 | 54 | 3 | 15 | Completed | 2022-05-31 | 2240901000
HPR230 | Delhi Water Treatment Plant 8 | Completed (history) | Water Treatment Plant | Delhi | Private | Lump sum | 2269100000 | 9.8 | 2046728000 | 2023-02-08 | 2024-05-08 | 15 | 78 | 3 | 15 | Completed | 2024-04-30 | 2050373000
HPR231 | Chennai Residential Towers 5 | Completed (history) | Residential Towers | Chennai | Government | EPC lump sum | 3965400000 | 8.3 | 3636272000 | 2020-07-09 | 2022-01-09 | 18 | 49 | 5 | 4 | Completed | 2022-07-31 | 4194118000
HPR232 | Surat Metro Viaduct 4 | Completed (history) | Metro Viaduct | Surat | Private | Lump sum | 10647300000 | 12.7 | 9295093000 | 2021-03-02 | 2022-06-02 | 15 | 52 | 4 | 24 | Completed | 2022-10-31 | 11210273000
HPR233 | Chennai Logistics Hub 6 | Completed (history) | Logistics Hub | Chennai | Private | Lump sum | 7832500000 | 13.7 | 6759448000 | 2018-02-12 | 2019-12-12 | 22 | 57 | 3 | 17 | Completed | 2020-02-29 | 7104398000
HPR234 | Kolkata Commercial Complex 5 | Completed (history) | Commercial Complex | Kolkata | Private | Lump sum | 2746500000 | 9.3 | 2491076000 | 2017-04-06 | 2019-07-06 | 27 | 86 | 2 | 15 | Completed | 2019-07-31 | 2584486000
HPR235 | Jaipur Highway Package 6 | Completed (history) | Highway Package | Jaipur | Government | EPC lump sum | 2359000000 | 10.8 | 2104228000 | 2021-04-01 | 2023-07-01 | 27 | 20 | 2 | 20 | Completed | 2024-03-31 | 2553931000
HPR236 | Lucknow Water Treatment Plant 4 | Completed (history) | Water Treatment Plant | Lucknow | Private | Lump sum | 2698100000 | 9.7 | 2436384000 | 2019-01-29 | 2020-02-29 | 13 | 74 | 4 | 13 | Completed | 2020-06-30 | 2628977000
HPR237 | Delhi Water Treatment Plant 5 | Completed (history) | Water Treatment Plant | Delhi | Government | Item rate with price variation | 2727600000 | 13.4 | 2362102000 | 2017-03-15 | 2018-10-15 | 19 | 84 | 2 | 13 | Completed | 2018-11-30 | 2469994000
HPR238 | Delhi Commercial Complex 6 | Completed (history) | Commercial Complex | Delhi | Private | Cost plus fee | 2844100000 | 15.5 | 2403264000 | 2022-08-09 | 2025-03-09 | 31 | 60 | 1 | 21 | Completed | 2025-02-28 | 2375844000
HPR239 | Hyderabad Water Treatment Plant 7 | Completed (history) | Water Treatment Plant | Hyderabad | Private | Lump sum | 2956700000 | 10.3 | 2652160000 | 2020-05-02 | 2022-04-02 | 23 | 77 | 2 | 10 | Completed | 2022-08-31 | 2831366000
HPR240 | Pune IT Park 5 | Completed (history) | IT Park | Pune | Private | Lump sum | 4197700000 | 13.6 | 3626813000 | 2023-05-28 | 2024-07-28 | 14 | 75 | 4 | 14 | Completed | 2024-09-30 | 3772316000

## fact_monthly_cost
row_id | project_id | period_month | cost_category | planned_value | earned_value | actual_cost
MCR000001 | PRJ001 | 2025-05-01 | Labor | 15583253 | 7557859 | 7445025
MCR000002 | PRJ001 | 2025-05-01 | Material | 37659806 | 18264961 | 16726718
MCR000003 | PRJ001 | 2025-05-01 | Equipment | 13755728 | 6671512 | 7292878
MCR000004 | PRJ001 | 2025-05-01 | Subcontract | 33399387 | 16198663 | 18684877
MCR000005 | PRJ001 | 2025-05-01 | Overhead | 9696782 | 4702928 | 36385452
MCR000006 | PRJ001 | 2025-06-01 | Labor | 42419825 | 31654581 | 34141616
MCR000007 | PRJ001 | 2025-06-01 | Material | 102515332 | 76499135 | 65796294
MCR000008 | PRJ001 | 2025-06-01 | Equipment | 37445042 | 27942292 | 27062492
MCR000009 | PRJ001 | 2025-06-01 | Subcontract | 90917868 | 67844859 | 66759052
MCR000010 | PRJ001 | 2025-06-01 | Overhead | 26396016 | 19697272 | 37717137
MCR000011 | PRJ001 | 2025-07-01 | Labor | 62951646 | 22513483 | 27360678
MCR000012 | PRJ001 | 2025-07-01 | Material | 152134266 | 54407983 | 66233629
MCR000013 | PRJ001 | 2025-07-01 | Equipment | 55568995 | 19873215 | 20648209
MCR000014 | PRJ001 | 2025-07-01 | Subcontract | 134923457 | 48252859 | 50226939
MCR000015 | PRJ001 | 2025-07-01 | Overhead | 39172077 | 14009163 | 32197888
MCR000016 | PRJ001 | 2025-08-01 | Labor | 77450216 | 37795671 | 33101211
MCR000017 | PRJ001 | 2025-08-01 | Material | 187172733 | 91340211 | 84085067
MCR000018 | PRJ001 | 2025-08-01 | Equipment | 68367245 | 33363186 | 32459875
MCR000019 | PRJ001 | 2025-08-01 | Subcontract | 165998055 | 81006978 | 79207911
MCR000020 | PRJ001 | 2025-08-01 | Overhead | 48193907 | 23518605 | 34202101
MCR000021 | PRJ001 | 2025-09-01 | Labor | 86213656 | 46935779 | 47651137
MCR000022 | PRJ001 | 2025-09-01 | Material | 208351203 | 113428968 | 114477164
MCR000023 | PRJ001 | 2025-09-01 | Equipment | 76102954 | 41431388 | 45225434
MCR000024 | PRJ001 | 2025-09-01 | Subcontract | 184780624 | 100596854 | 95354884
MCR000025 | PRJ001 | 2025-09-01 | Overhead | 53647016 | 29206098 | 35214719
MCR000026 | PRJ001 | 2025-10-01 | Labor | 89573354 | 63133088 | 68057026
MCR000027 | PRJ001 | 2025-10-01 | Material | 216470534 | 152572754 | 156723154
MCR000028 | PRJ001 | 2025-10-01 | Equipment | 79068644 | 55729159 | 60412506
MCR000029 | PRJ001 | 2025-10-01 | Subcontract | 191981423 | 135312340 | 146796174
MCR000030 | PRJ001 | 2025-10-01 | Overhead | 55737610 | 39284980 | 35577303
MCR000031 | PRJ001 | 2025-11-01 | Labor | 87903468 | 47295640 | 47640643
MCR000032 | PRJ001 | 2025-11-01 | Material | 212434945 | 114298640 | 119211783
MCR000033 | PRJ001 | 2025-11-01 | Equipment | 77594593 | 41749047 | 47787450
MCR000034 | PRJ001 | 2025-11-01 | Subcontract | 188402377 | 101368140 | 99109251
MCR000035 | PRJ001 | 2025-11-01 | Overhead | 54698512 | 29430024 | 35820733
MCR000036 | PRJ001 | 2025-12-01 | Labor | 81635210 | 89321930 | 94231331
MCR000037 | PRJ001 | 2025-12-01 | Material | 197286544 | 215862920 | 191559907
MCR000038 | PRJ001 | 2025-12-01 | Equipment | 72061445 | 78846705 | 77523714
MCR000039 | PRJ001 | 2025-12-01 | Subcontract | 174967700 | 191442548 | 205239489
MCR000040 | PRJ001 | 2025-12-01 | Overhead | 50798048 | 55581159 | 37078506
MCR000041 | PRJ001 | 2026-01-01 | Labor | 71279725 | 83706736 | 78724152
MCR000042 | PRJ001 | 2026-01-01 | Material | 172260605 | 202292769 | 224277984
MCR000043 | PRJ001 | 2026-01-01 | Equipment | 62920399 | 73890033 | 80150122
MCR000044 | PRJ001 | 2026-01-01 | Subcontract | 152772922 | 179407575 | 170434475
MCR000045 | PRJ001 | 2026-01-01 | Overhead | 44354279 | 52087068 | 34633850
MCR000046 | PRJ001 | 2026-02-01 | Labor | 57468034 | 67168529 | 63435775
MCR000047 | PRJ001 | 2026-02-01 | Material | 138882105 | 162325140 | 153102304
MCR000048 | PRJ001 | 2026-02-01 | Equipment | 50728473 | 59291343 | 61909981
MCR000049 | PRJ001 | 2026-02-01 | Subcontract | 123170501 | 143961447 | 167225617
MCR000050 | PRJ001 | 2026-02-01 | Overhead | 35759863 | 41796060 | 33734126
MCR000051 | PRJ001 | 2026-03-01 | Labor | 41030286 | 44307766 | 41817872
MCR000052 | PRJ001 | 2026-03-01 | Material | 99157254 | 107077889 | 125258267
MCR000053 | PRJ001 | 2026-03-01 | Equipment | 36218461 | 39111575 | 37191592
MCR000054 | PRJ001 | 2026-03-01 | Subcontract | 87939686 | 94964267 | 85438903
MCR000055 | PRJ001 | 2026-03-01 | Overhead | 25531366 | 27570799 | 35200731
MCR000056 | PRJ001 | 2026-04-01 | Labor | 23190271 | 79610782 | 83486758
MCR000057 | PRJ001 | 2026-04-01 | Material | 56043569 | 192394139 | 184285478
MCR000058 | PRJ001 | 2026-04-01 | Equipment | 20470633 | 70274431 | 69234349
MCR000059 | PRJ001 | 2026-04-01 | Subcontract | 49703412 | 170628769 | 181496174
MCR000060 | PRJ001 | 2026-04-01 | Overhead | 14430299 | 49538334 | 38198951
MCR000061 | PRJ001 | 2026-05-01 | Labor | 6361169 | 60582260 | 68310578
MCR000062 | PRJ001 | 2026-05-01 | Material | 15372938 | 146408207 | 140482202
MCR000063 | PRJ001 | 2026-05-01 | Equipment | 5615163 | 53477479 | 53171990
MCR000064 | PRJ001 | 2026-05-01 | Subcontract | 13633812 | 129845182 | 123251096
MCR000065 | PRJ001 | 2026-05-01 | Overhead | 3958279 | 37697711 | 37254488
MCR000066 | PRJ001 | 2026-06-01 | Labor | 0 | 36109838 | 37462490
MCR000067 | PRJ001 | 2026-06-01 | Material | 0 | 87266084 | 82048615
MCR000068 | PRJ001 | 2026-06-01 | Equipment | 0 | 31875058 | 41357768
MCR000069 | PRJ001 | 2026-06-01 | Subcontract | 0 | 77393753 | 75948795
MCR000070 | PRJ001 | 2026-06-01 | Overhead | 0 | 22469585 | 38253567
MCR000071 | PRJ001 | 2026-07-01 | Labor | 0 | 15996260 | 15338764
MCR000072 | PRJ001 | 2026-07-01 | Material | 0 | 38657912 | 51464781
MCR000073 | PRJ001 | 2026-07-01 | Equipment | 0 | 14120299 | 14721203
MCR000074 | PRJ001 | 2026-07-01 | Subcontract | 0 | 34284578 | 35442524
MCR000075 | PRJ001 | 2026-07-01 | Overhead | 0 | 9953778 | 38092066
MCR000076 | PRJ001 | 2026-08-01 | Labor | 0 | 5448312 | 4475800
MCR000077 | PRJ001 | 2026-08-01 | Material | 0 | 13166852 | 8687260
MCR000078 | PRJ001 | 2026-08-01 | Equipment | 0 | 4809362 | 4817088
MCR000079 | PRJ001 | 2026-08-01 | Subcontract | 0 | 11677298 | 11582166
MCR000080 | PRJ001 | 2026-08-01 | Overhead | 0 | 3390248 | 35524209
MCR000081 | PRJ002 | 2025-01-01 | Labor | 8143154 | 6813179 | 7125120
MCR000082 | PRJ002 | 2025-01-01 | Material | 17970924 | 15035836 | 15142508
MCR000083 | PRJ002 | 2025-01-01 | Equipment | 4646485 | 3887601 | 4015117
MCR000084 | PRJ002 | 2025-01-01 | Subcontract | 21885758 | 18311282 | 17605970
MCR000085 | PRJ002 | 2025-01-01 | Overhead | 5682464 | 4754380 | 25732775
MCR000086 | PRJ002 | 2025-02-01 | Labor | 22605287 | 22412768 | 23029258
MCR000087 | PRJ002 | 2025-02-01 | Material | 49887046 | 49462180 | 54330035
MCR000088 | PRJ002 | 2025-02-01 | Equipment | 12898580 | 12788729 | 13236207
MCR000089 | PRJ002 | 2025-02-01 | Subcontract | 60754572 | 60237152 | 60895905
MCR000090 | PRJ002 | 2025-02-01 | Overhead | 15774444 | 15640101 | 25235986
MCR000091 | PRJ002 | 2025-03-01 | Labor | 34394710 | 47693541 | 41489676
MCR000092 | PRJ002 | 2025-03-01 | Material | 75904831 | 105253692 | 109689711
MCR000093 | PRJ002 | 2025-03-01 | Equipment | 19625627 | 27213943 | 24471880
MCR000094 | PRJ002 | 2025-03-01 | Subcontract | 92440140 | 128182435 | 104260952
MCR000095 | PRJ002 | 2025-03-01 | Overhead | 24001352 | 33281556 | 22653231
MCR000096 | PRJ002 | 2025-04-01 | Labor | 43600832 | 46567144 | 46197140
MCR000097 | PRJ002 | 2025-04-01 | Material | 96221593 | 102767873 | 107422051
MCR000098 | PRJ002 | 2025-04-01 | Equipment | 24878642 | 26571220 | 26733166
MCR000099 | PRJ002 | 2025-04-01 | Subcontract | 117182759 | 125155098 | 131153426
MCR000100 | PRJ002 | 2025-04-01 | Overhead | 30425577 | 32495532 | 26649897
MCR000101 | PRJ002 | 2025-05-01 | Labor | 50319723 | 40390240 | 37584996
MCR000102 | PRJ002 | 2025-05-01 | Material | 111049347 | 89136219 | 87166760
MCR000103 | PRJ002 | 2025-05-01 | Equipment | 28712442 | 23046678 | 25713182
MCR000104 | PRJ002 | 2025-05-01 | Subcontract | 135240630 | 108553888 | 91779796
MCR000105 | PRJ002 | 2025-05-01 | Overhead | 35114161 | 28185159 | 24213681
MCR000106 | PRJ002 | 2025-06-01 | Labor | 54655342 | 43396427 | 38582445
MCR000107 | PRJ002 | 2025-06-01 | Material | 120617518 | 95770497 | 108282543
MCR000108 | PRJ002 | 2025-06-01 | Equipment | 31186348 | 24762009 | 23612723
MCR000109 | PRJ002 | 2025-06-01 | Subcontract | 146893157 | 116633396 | 106665931
MCR000110 | PRJ002 | 2025-06-01 | Overhead | 38139647 | 30282940 | 25071926
MCR000111 | PRJ002 | 2025-07-01 | Labor | 56721142 | 35913468 | 31492572
MCR000112 | PRJ002 | 2025-07-01 | Material | 125176479 | 79256541 | 78266471
MCR000113 | PRJ002 | 2025-07-01 | Equipment | 32365093 | 20492231 | 20114573
MCR000114 | PRJ002 | 2025-07-01 | Subcontract | 152445254 | 96521995 | 104243129
MCR000115 | PRJ002 | 2025-07-01 | Overhead | 39581206 | 25061173 | 24655871
MCR000116 | PRJ002 | 2025-08-01 | Labor | 56642218 | 72910350 | 67906572
MCR000117 | PRJ002 | 2025-08-01 | Material | 125002306 | 160904042 | 170384561
MCR000118 | PRJ002 | 2025-08-01 | Equipment | 32320059 | 41602658 | 40322041
MCR000119 | PRJ002 | 2025-08-01 | Subcontract | 152233138 | 195955803 | 171829776
MCR000120 | PRJ002 | 2025-08-01 | Overhead | 39526131 | 50878376 | 24126121
MCR000121 | PRJ002 | 2025-09-01 | Labor | 54558297 | 87677761 | 85165737
MCR000122 | PRJ002 | 2025-09-01 | Material | 120403352 | 193493873 | 208642630
MCR000123 | PRJ002 | 2025-09-01 | Equipment | 31130974 | 50028945 | 54319660
MCR000124 | PRJ002 | 2025-09-01 | Subcontract | 146632336 | 235645090 | 244943122
MCR000125 | PRJ002 | 2025-09-01 | Overhead | 38071927 | 61183386 | 25881671
MCR000126 | PRJ002 | 2025-10-01 | Labor | 50628022 | 36894733 | 31186389
MCR000127 | PRJ002 | 2025-10-01 | Material | 111729724 | 81422071 | 70729976
MCR000128 | PRJ002 | 2025-10-01 | Equipment | 28888358 | 21052141 | 16976401
MCR000129 | PRJ002 | 2025-10-01 | Subcontract | 136069222 | 99159270 | 67988857
MCR000130 | PRJ002 | 2025-10-01 | Overhead | 35329298 | 25745921 | 25074278
MCR000131 | PRJ002 | 2025-11-01 | Labor | 45035438 | 37697427 | 53565881
MCR000132 | PRJ002 | 2025-11-01 | Material | 99387590 | 83193516 | 117489079
MCR000133 | PRJ002 | 2025-11-01 | Equipment | 25697229 | 21510158 | 23213359
MCR000134 | PRJ002 | 2025-11-01 | Subcontract | 121038446 | 101316611 | 95955527
MCR000135 | PRJ002 | 2025-11-01 | Overhead | 31426676 | 26306058 | 21229621
MCR000136 | PRJ002 | 2025-12-01 | Labor | 38000448 | 40656472 | 55465662
MCR000137 | PRJ002 | 2025-12-01 | Material | 83862246 | 89723759 | 137709734
MCR000138 | PRJ002 | 2025-12-01 | Equipment | 21683062 | 23198590 | 25099624
MCR000139 | PRJ002 | 2025-12-01 | Subcontract | 102131019 | 109269419 | 104363632
MCR000140 | PRJ002 | 2025-12-01 | Overhead | 26517512 | 28370941 | 25781965
MCR000141 | PRJ002 | 2026-01-01 | Labor | 29797181 | 33549396 | 30627921
MCR000142 | PRJ002 | 2026-01-01 | Material | 65758660 | 74039329 | 72000347
MCR000143 | PRJ002 | 2026-01-01 | Equipment | 17002277 | 19143291 | 17576074
MCR000144 | PRJ002 | 2026-01-01 | Subcontract | 80083700 | 90168252 | 91129936
MCR000145 | PRJ002 | 2026-01-01 | Overhead | 20793100 | 23411474 | 23755314
MCR000146 | PRJ002 | 2026-02-01 | Labor | 20790735 | 11899875 | 11082059
MCR000147 | PRJ002 | 2026-02-01 | Material | 45882558 | 26261539 | 25972808
MCR000148 | PRJ002 | 2026-02-01 | Equipment | 11863197 | 6790071 | 7138531
MCR000149 | PRJ002 | 2026-02-01 | Subcontract | 55877735 | 31982422 | 31855561
MCR000150 | PRJ002 | 2026-02-01 | Overhead | 14508212 | 8303983 | 24824799
MCR000151 | PRJ002 | 2026-03-01 | Labor | 11528173 | 12410180 | 10808220
MCR000152 | PRJ002 | 2026-03-01 | Material | 25441239 | 27387718 | 26579790
MCR000153 | PRJ002 | 2026-03-01 | Equipment | 6577977 | 7081251 | 6765151
MCR000154 | PRJ002 | 2026-03-01 | Subcontract | 30983425 | 33353931 | 30161727
MCR000155 | PRJ002 | 2026-03-01 | Overhead | 8044602 | 8660085 | 25096858
MCR000156 | PRJ002 | 2026-04-01 | Labor | 3115478 | 3653219 | 4100315
MCR000157 | PRJ002 | 2026-04-01 | Material | 6875472 | 8062199 | 10864990
MCR000158 | PRJ002 | 2026-04-01 | Equipment | 1777692 | 2084528 | 2206620
MCR000159 | PRJ002 | 2026-04-01 | Subcontract | 8373243 | 9818490 | 9511023
MCR000160 | PRJ002 | 2026-04-01 | Overhead | 2174046 | 2549293 | 24630156
MCR000161 | PRJ003 | 2025-04-01 | Labor | 11571753 | 16472077 | 16978344
MCR000162 | PRJ003 | 2025-04-01 | Material | 24246295 | 34513943 | 34401014
MCR000163 | PRJ003 | 2025-04-01 | Equipment | 4364848 | 6213243 | 6163424
MCR000164 | PRJ003 | 2025-04-01 | Subcontract | 24717497 | 35184686 | 36993749
MCR000165 | PRJ003 | 2025-04-01 | Overhead | 6531368 | 9297225 | 20734029
MCR000166 | PRJ003 | 2025-05-01 | Labor | 30886544 | 29612660 | 28270472
MCR000167 | PRJ003 | 2025-05-01 | Material | 64716579 | 62047410 | 62721768
MCR000168 | PRJ003 | 2025-05-01 | Equipment | 11650359 | 11169852 | 12024791
MCR000169 | PRJ003 | 2025-05-01 | Subcontract | 65974278 | 63253237 | 66653612
MCR000170 | PRJ003 | 2025-05-01 | Overhead | 17433087 | 16714077 | 21253687
MCR000171 | PRJ003 | 2025-06-01 | Labor | 44661766 | 58491560 | 56076273
MCR000172 | PRJ003 | 2025-06-01 | Material | 93579803 | 122557371 | 117658158
MCR000173 | PRJ003 | 2025-06-01 | Equipment | 16846352 | 22062930 | 23111451
MCR000174 | PRJ003 | 2025-06-01 | Subcontract | 95398429 | 124939146 | 106510035
MCR000175 | PRJ003 | 2025-06-01 | Overhead | 25208145 | 33014003 | 20628381
MCR000176 | PRJ003 | 2025-07-01 | Labor | 53192507 | 52520948 | 52463811
MCR000177 | PRJ003 | 2025-07-01 | Material | 111454266 | 110047147 | 110707275
MCR000178 | PRJ003 | 2025-07-01 | Equipment | 20064135 | 19810824 | 18337454
MCR000179 | PRJ003 | 2025-07-01 | Subcontract | 113620264 | 112185799 | 130641382
MCR000180 | PRJ003 | 2025-07-01 | Overhead | 30023094 | 29644050 | 20272527
MCR000181 | PRJ003 | 2025-08-01 | Labor | 56810541 | 26321930 | 26863332
MCR000182 | PRJ003 | 2025-08-01 | Material | 119035131 | 55152342 | 60427790
MCR000183 | PRJ003 | 2025-08-01 | Equipment | 21428852 | 9928593 | 12548295
MCR000184 | PRJ003 | 2025-08-01 | Subcontract | 121348455 | 56224170 | 50926548
MCR000185 | PRJ003 | 2025-08-01 | Overhead | 32065197 | 14856712 | 19455701
MCR000186 | PRJ003 | 2025-09-01 | Labor | 55896315 | 49463406 | 45349975
MCR000187 | PRJ003 | 2025-09-01 | Material | 117119554 | 103640678 | 113215887
MCR000188 | PRJ003 | 2025-09-01 | Equipment | 21084007 | 18657524 | 21032943
MCR000189 | PRJ003 | 2025-09-01 | Subcontract | 119395650 | 105654827 | 103601877
MCR000190 | PRJ003 | 2025-09-01 | Overhead | 31549186 | 27918302 | 20702302
MCR000191 | PRJ003 | 2025-10-01 | Labor | 50898048 | 50642625 | 80732373
MCR000192 | PRJ003 | 2025-10-01 | Material | 106646684 | 106111498 | 125741866
MCR000193 | PRJ003 | 2025-10-01 | Equipment | 19198669 | 19102324 | 16875637
MCR000194 | PRJ003 | 2025-10-01 | Subcontract | 108719252 | 108173664 | 117070476
MCR000195 | PRJ003 | 2025-10-01 | Overhead | 28728048 | 28583881 | 20614531
MCR000196 | PRJ003 | 2025-11-01 | Labor | 42364874 | 49576444 | 67229119
MCR000197 | PRJ003 | 2025-11-01 | Material | 88767124 | 103877528 | 127935384
MCR000198 | PRJ003 | 2025-11-01 | Equipment | 15979968 | 18700161 | 19767396
MCR000199 | PRJ003 | 2025-11-01 | Subcontract | 90492221 | 105896279 | 116648303
MCR000200 | PRJ003 | 2025-11-01 | Overhead | 23911725 | 27982103 | 22139553
MCR000201 | PRJ003 | 2025-12-01 | Labor | 31012154 | 34948861 | 29045687
MCR000202 | PRJ003 | 2025-12-01 | Material | 64979770 | 73228351 | 76679069
MCR000203 | PRJ003 | 2025-12-01 | Equipment | 11697739 | 13182659 | 15802242
MCR000204 | PRJ003 | 2025-12-01 | Subcontract | 66242584 | 74651468 | 61126717
MCR000205 | PRJ003 | 2025-12-01 | Overhead | 17503985 | 19725954 | 18978325
MCR000206 | PRJ003 | 2026-01-01 | Labor | 17880470 | 25084871 | 24041347
MCR000207 | PRJ003 | 2026-01-01 | Material | 37464951 | 52560333 | 44435091
MCR000208 | PRJ003 | 2026-01-01 | Equipment | 6744487 | 9461976 | 8839507
MCR000209 | PRJ003 | 2026-01-01 | Subcontract | 38193044 | 53581789 | 65008641
MCR000210 | PRJ003 | 2026-01-01 | Overhead | 10092155 | 14158488 | 23107086
MCR000211 | PRJ003 | 2026-02-01 | Labor | 4978629 | 7018220 | 7906877
MCR000212 | PRJ003 | 2026-02-01 | Material | 10431722 | 14705278 | 15897972
MCR000213 | PRJ003 | 2026-02-01 | Equipment | 1877932 | 2647262 | 3101798
MCR000214 | PRJ003 | 2026-02-01 | Subcontract | 10634452 | 14991060 | 13547285
MCR000215 | PRJ003 | 2026-02-01 | Overhead | 2810055 | 3961248 | 20611629
MCR000216 | PRJ004 | 2024-12-01 | Labor | 6221258 | 3653346 | 4287622
MCR000217 | PRJ004 | 2024-12-01 | Material | 17845710 | 10479642 | 9951634
MCR000218 | PRJ004 | 2024-12-01 | Equipment | 4351620 | 2555427 | 2502355
MCR000219 | PRJ004 | 2024-12-01 | Subcontract | 15437496 | 9065452 | 8934950
MCR000220 | PRJ004 | 2024-12-01 | Overhead | 3895572 | 2287620 | 19463062
MCR000221 | PRJ004 | 2025-01-01 | Labor | 17354696 | 25738993 | 25655402
MCR000222 | PRJ004 | 2025-01-01 | Material | 49782036 | 73832437 | 64742651
MCR000223 | PRJ004 | 2025-01-01 | Equipment | 12139192 | 18003806 | 19340213
MCR000224 | PRJ004 | 2025-01-01 | Subcontract | 43064130 | 63869015 | 65960093
MCR000225 | PRJ004 | 2025-01-01 | Overhead | 10867010 | 16117015 | 18862281
MCR000226 | PRJ004 | 2025-02-01 | Labor | 26567188 | 23094490 | 25969860
MCR000227 | PRJ004 | 2025-02-01 | Material | 76208117 | 66246666 | 74551199
MCR000228 | PRJ004 | 2025-02-01 | Equipment | 18583108 | 16154040 | 14026706
MCR000229 | PRJ004 | 2025-02-01 | Subcontract | 65924107 | 57306918 | 50672737
MCR000230 | PRJ004 | 2025-02-01 | Overhead | 16635607 | 14461104 | 19929060
MCR000231 | PRJ004 | 2025-03-01 | Labor | 33918545 | 39295402 | 48395365
MCR000232 | PRJ004 | 2025-03-01 | Material | 97295524 | 112719066 | 100670576
MCR000233 | PRJ004 | 2025-03-01 | Equipment | 23725206 | 27486188 | 26132746
MCR000234 | PRJ004 | 2025-03-01 | Subcontract | 84165844 | 97508035 | 103670601
MCR000235 | PRJ004 | 2025-03-01 | Overhead | 21238815 | 24605648 | 17538306
MCR000236 | PRJ004 | 2025-04-01 | Labor | 39472706 | 39158759 | 43105662
MCR000237 | PRJ004 | 2025-04-01 | Material | 113227663 | 112327104 | 111637978
MCR000238 | PRJ004 | 2025-04-01 | Equipment | 27610208 | 27390609 | 28123385
MCR000239 | PRJ004 | 2025-04-01 | Subcontract | 97947998 | 97168966 | 106486504
MCR000240 | PRJ004 | 2025-04-01 | Overhead | 24716670 | 24520086 | 18916827
MCR000241 | PRJ004 | 2025-05-01 | Labor | 43298434 | 39577975 | 42624655
MCR000242 | PRJ004 | 2025-05-01 | Material | 124201784 | 113529628 | 119524124
MCR000243 | PRJ004 | 2025-05-01 | Equipment | 30286212 | 27683841 | 26174254
MCR000244 | PRJ004 | 2025-05-01 | Subcontract | 107441202 | 98209214 | 101106652
MCR000245 | PRJ004 | 2025-05-01 | Overhead | 27112231 | 24782587 | 16753006
MCR000246 | PRJ004 | 2025-06-01 | Labor | 45470214 | 44320138 | 47317034
MCR000247 | PRJ004 | 2025-06-01 | Material | 130431547 | 127132546 | 137424871
MCR000248 | PRJ004 | 2025-06-01 | Equipment | 31805320 | 31000869 | 33535469
MCR000249 | PRJ004 | 2025-06-01 | Subcontract | 112830280 | 109976468 | 111796959
MCR000250 | PRJ004 | 2025-06-01 | Overhead | 28472137 | 27751992 | 18513886
MCR000251 | PRJ004 | 2025-07-01 | Labor | 46069425 | 35175657 | 40111512
MCR000252 | PRJ004 | 2025-07-01 | Material | 132150385 | 100901555 | 105394645
MCR000253 | PRJ004 | 2025-07-01 | Equipment | 32224454 | 24604525 | 25997771
MCR000254 | PRJ004 | 2025-07-01 | Subcontract | 114317167 | 87285254 | 86883394
MCR000255 | PRJ004 | 2025-07-01 | Overhead | 28847345 | 22025982 | 19469519
MCR000256 | PRJ004 | 2025-08-01 | Labor | 45185911 | 29410567 | 27880436
MCR000257 | PRJ004 | 2025-08-01 | Material | 129616021 | 84364366 | 85682183
MCR000258 | PRJ004 | 2025-08-01 | Equipment | 31606457 | 20571984 | 16866267
MCR000259 | PRJ004 | 2025-08-01 | Subcontract | 112124807 | 72979699 | 71996651
MCR000260 | PRJ004 | 2025-08-01 | Overhead | 28294115 | 18416049 | 18978277
MCR000261 | PRJ004 | 2025-09-01 | Labor | 42920172 | 28943348 | 34871468
MCR000262 | PRJ004 | 2025-09-01 | Material | 123116738 | 83024146 | 90708481
MCR000263 | PRJ004 | 2025-09-01 | Equipment | 30021627 | 20245176 | 21100466
MCR000264 | PRJ004 | 2025-09-01 | Subcontract | 106502578 | 71820337 | 77265238
MCR000265 | PRJ004 | 2025-09-01 | Overhead | 26875374 | 18123490 | 19323420
MCR000266 | PRJ004 | 2025-10-01 | Labor | 39386509 | 31682025 | 37052804
MCR000267 | PRJ004 | 2025-10-01 | Material | 112980405 | 90880054 | 91601137
MCR000268 | PRJ004 | 2025-10-01 | Equipment | 27549915 | 22160814 | 21844215
MCR000269 | PRJ004 | 2025-10-01 | Subcontract | 97734107 | 78616118 | 83447778
MCR000270 | PRJ004 | 2025-10-01 | Overhead | 24662696 | 19838370 | 18801516
MCR000271 | PRJ004 | 2025-11-01 | Labor | 34717787 | 39471813 | 43614147
MCR000272 | PRJ004 | 2025-11-01 | Material | 99588154 | 113225103 | 122501370
MCR000273 | PRJ004 | 2025-11-01 | Equipment | 24284257 | 27609583 | 30385605
MCR000274 | PRJ004 | 2025-11-01 | Subcontract | 86149092 | 97945783 | 93186404
MCR000275 | PRJ004 | 2025-11-01 | Overhead | 21739277 | 24716111 | 18151074
MCR000276 | PRJ004 | 2025-12-01 | Labor | 29073136 | 34446996 | 35426629
MCR000277 | PRJ004 | 2025-12-01 | Material | 83396443 | 98811388 | 87206353
MCR000278 | PRJ004 | 2025-12-01 | Equipment | 20335959 | 24094845 | 21848640
MCR000279 | PRJ004 | 2025-12-01 | Subcontract | 72142393 | 85477148 | 73043367
MCR000280 | PRJ004 | 2025-12-01 | Overhead | 18204760 | 21569716 | 21367208
MCR000281 | PRJ004 | 2026-01-01 | Labor | 22651493 | 26777945 | 34611091
MCR000282 | PRJ004 | 2026-01-01 | Material | 64975926 | 76812674 | 95617661
MCR000283 | PRJ004 | 2026-01-01 | Equipment | 15844174 | 18730528 | 17042093
MCR000284 | PRJ004 | 2026-01-01 | Subcontract | 56207659 | 66447081 | 72721114
MCR000285 | PRJ004 | 2026-01-01 | Overhead | 14183712 | 16767577 | 17847644
MCR000286 | PRJ004 | 2026-02-01 | Labor | 15718763 | 31593465 | 35829952
MCR000287 | PRJ004 | 2026-02-01 | Material | 45089355 | 90626020 | 81324464
MCR000288 | PRJ004 | 2026-02-01 | Equipment | 10994897 | 22098868 | 21189605
MCR000289 | PRJ004 | 2026-02-01 | Subcontract | 39004709 | 78396365 | 78829772
MCR000290 | PRJ004 | 2026-02-01 | Overhead | 9842636 | 19782917 | 17748671
MCR000291 | PRJ004 | 2026-03-01 | Labor | 8675235 | 18645347 | 21516119
MCR000292 | PRJ004 | 2026-03-01 | Material | 24884957 | 53484274 | 55573313
MCR000293 | PRJ004 | 2026-03-01 | Equipment | 6068118 | 13041971 | 13796396
MCR000294 | PRJ004 | 2026-03-01 | Subcontract | 21526822 | 46266764 | 49027170
MCR000295 | PRJ004 | 2026-03-01 | Overhead | 5432182 | 11675179 | 17586059
MCR000296 | PRJ004 | 2026-04-01 | Labor | 2335790 | 5966913 | 5338097
MCR000297 | PRJ004 | 2026-04-01 | Material | 6700226 | 17116121 | 19276667
MCR000298 | PRJ004 | 2026-04-01 | Equipment | 1633829 | 4173712 | 5193967
MCR000299 | PRJ004 | 2026-04-01 | Subcontract | 5796055 | 14806362 | 16563484
MCR000300 | PRJ004 | 2026-04-01 | Overhead | 1462604 | 3736309 | 19017963
MCR000301 | PRJ004 | 2026-05-01 | Labor | 0 | 2084083 | 2609279
MCR000302 | PRJ004 | 2026-05-01 | Material | 0 | 5978204 | 4764748
MCR000303 | PRJ004 | 2026-05-01 | Equipment | 0 | 1457766 | 1229981
MCR000304 | PRJ004 | 2026-05-01 | Subcontract | 0 | 5171467 | 4422520
MCR000305 | PRJ004 | 2026-05-01 | Overhead | 0 | 1304993 | 17949721
MCR000306 | PRJ005 | 2025-06-01 | Labor | 6907110 | 5647553 | 5668809
MCR000307 | PRJ005 | 2025-06-01 | Material | 14189503 | 11601954 | 11657615
MCR000308 | PRJ005 | 2025-06-01 | Equipment | 2924251 | 2390994 | 2636581
MCR000309 | PRJ005 | 2025-06-01 | Subcontract | 25626737 | 20953532 | 20594493
MCR000310 | PRJ005 | 2025-06-01 | Overhead | 4663004 | 3812674 | 18705084
MCR000311 | PRJ005 | 2025-07-01 | Labor | 18944487 | 8745653 | 9977784
MCR000312 | PRJ005 | 2025-07-01 | Material | 38918284 | 17966482 | 16591888
MCR000313 | PRJ005 | 2025-07-01 | Equipment | 8020493 | 3702631 | 3727268
MCR000314 | PRJ005 | 2025-07-01 | Subcontract | 70287776 | 32448092 | 32437998
MCR000315 | PRJ005 | 2025-07-01 | Overhead | 12789461 | 5904208 | 18230290
MCR000316 | PRJ005 | 2025-08-01 | Labor | 28388397 | 14932378 | 17410742
MCR000317 | PRJ005 | 2025-08-01 | Material | 58319219 | 30676076 | 30044991
MCR000318 | PRJ005 | 2025-08-01 | Equipment | 12018744 | 6321894 | 6787634
MCR000319 | PRJ005 | 2025-08-01 | Subcontract | 105326539 | 55402062 | 55728657
MCR000320 | PRJ005 | 2025-08-01 | Overhead | 19165064 | 10080878 | 18167631
MCR000321 | PRJ005 | 2025-09-01 | Labor | 35340759 | 31305418 | 31642707
MCR000322 | PRJ005 | 2025-09-01 | Material | 72601685 | 64311750 | 61906073
MCR000323 | PRJ005 | 2025-09-01 | Equipment | 14962153 | 13253718 | 12994135
MCR000324 | PRJ005 | 2025-09-01 | Subcontract | 131121171 | 116149260 | 120529065
MCR000325 | PRJ005 | 2025-09-01 | Overhead | 23858617 | 21134350 | 16867509
MCR000326 | PRJ005 | 2025-10-01 | Labor | 39912535 | 33354756 | 36950217
MCR000327 | PRJ005 | 2025-10-01 | Material | 81993635 | 68521773 | 75873433
MCR000328 | PRJ005 | 2025-10-01 | Equipment | 16897698 | 14121342 | 13499836
MCR000329 | PRJ005 | 2025-10-01 | Subcontract | 148083360 | 123752708 | 111461582
MCR000330 | PRJ005 | 2025-10-01 | Overhead | 26945033 | 22517863 | 19120837
MCR000331 | PRJ005 | 2025-11-01 | Labor | 42225745 | 29280635 | 29593580
MCR000332 | PRJ005 | 2025-11-01 | Material | 86745739 | 60152172 | 66293762
MCR000333 | PRJ005 | 2025-11-01 | Equipment | 17877037 | 12396489 | 12575012
MCR000334 | PRJ005 | 2025-11-01 | Subcontract | 156665825 | 108636918 | 113509810
MCR000335 | PRJ005 | 2025-11-01 | Overhead | 28506685 | 19767415 | 17834230
MCR000336 | PRJ005 | 2025-12-01 | Labor | 42416250 | 25073832 | 28340536
MCR000337 | PRJ005 | 2025-12-01 | Material | 87137099 | 51509998 | 50040261
MCR000338 | PRJ005 | 2025-12-01 | Equipment | 17957691 | 10615463 | 12218817
MCR000339 | PRJ005 | 2025-12-01 | Subcontract | 157372635 | 93028850 | 76632135
MCR000340 | PRJ005 | 2025-12-01 | Overhead | 28635296 | 16927394 | 18327764
MCR000341 | PRJ005 | 2026-01-01 | Labor | 40637746 | 58800305 | 69191094
MCR000342 | PRJ005 | 2026-01-01 | Material | 83483459 | 120795403 | 136733915
MCR000343 | PRJ005 | 2026-01-01 | Equipment | 17204729 | 24894179 | 21013716
MCR000344 | PRJ005 | 2026-01-01 | Subcontract | 150774033 | 218160704 | 198840684
MCR000345 | PRJ005 | 2026-01-01 | Overhead | 27434624 | 39696204 | 18386796
MCR000346 | PRJ005 | 2026-02-01 | Labor | 37067776 | 28879045 | 28485590
MCR000347 | PRJ005 | 2026-02-01 | Material | 76149553 | 59327173 | 46078084
MCR000348 | PRJ005 | 2026-02-01 | Equipment | 15693317 | 12226469 | 16521946
MCR000349 | PRJ005 | 2026-02-01 | Subcontract | 137528745 | 107146940 | 124902321
MCR000350 | PRJ005 | 2026-02-01 | Overhead | 25024530 | 19496301 | 18679342
MCR000351 | PRJ005 | 2026-03-01 | Labor | 31917386 | 21895419 | 24370270
MCR000352 | PRJ005 | 2026-03-01 | Material | 65568937 | 44980479 | 48248287
MCR000353 | PRJ005 | 2026-03-01 | Equipment | 13512806 | 9269824 | 9430698
MCR000354 | PRJ005 | 2026-03-01 | Subcontract | 118419784 | 81236311 | 80257186
MCR000355 | PRJ005 | 2026-03-01 | Overhead | 21547491 | 14781641 | 17366096
MCR000356 | PRJ005 | 2026-04-01 | Labor | 25448015 | 37087193 | 40303396
MCR000357 | PRJ005 | 2026-04-01 | Material | 52278695 | 76189441 | 83183130
MCR000358 | PRJ005 | 2026-04-01 | Equipment | 10773880 | 15701537 | 14752390
MCR000359 | PRJ005 | 2026-04-01 | Subcontract | 94417143 | 137600783 | 126540012
MCR000360 | PRJ005 | 2026-04-01 | Overhead | 17180006 | 25037638 | 17211885
MCR000361 | PRJ005 | 2026-05-01 | Labor | 18005117 | 26661770 | 31048743
MCR000362 | PRJ005 | 2026-05-01 | Material | 36988505 | 54772153 | 55390224
MCR000363 | PRJ005 | 2026-05-01 | Equipment | 7622794 | 11287745 | 12864267
MCR000364 | PRJ005 | 2026-05-01 | Subcontract | 66802527 | 98920415 | 103427237
MCR000365 | PRJ005 | 2026-05-01 | Overhead | 12155291 | 17999415 | 17963076
MCR000366 | PRJ005 | 2026-06-01 | Labor | 10100953 | 18839963 | 19932193
MCR000367 | PRJ005 | 2026-06-01 | Material | 20750720 | 38703556 | 42302117
MCR000368 | PRJ005 | 2026-06-01 | Equipment | 4276422 | 7976241 | 9375212
MCR000369 | PRJ005 | 2026-06-01 | Subcontract | 37476523 | 69899970 | 61917033
MCR000370 | PRJ005 | 2026-06-01 | Overhead | 6819174 | 12718897 | 20086406
MCR000371 | PRJ005 | 2026-07-01 | Labor | 2754878 | 13046564 | 14572539
MCR000372 | PRJ005 | 2026-07-01 | Material | 5659436 | 26801986 | 22939523
MCR000373 | PRJ005 | 2026-07-01 | Equipment | 1166328 | 5523500 | 5158882
MCR000374 | PRJ005 | 2026-07-01 | Subcontract | 10221139 | 48405320 | 51303501
MCR000375 | PRJ005 | 2026-07-01 | Overhead | 1859824 | 8807761 | 19051669
MCR000376 | PRJ005 | 2026-08-01 | Labor | 0 | 7250764 | 8382394
MCR000377 | PRJ005 | 2026-08-01 | Material | 0 | 14895484 | 16926804
MCR000378 | PRJ005 | 2026-08-01 | Equipment | 0 | 3069743 | 3140135
MCR000379 | PRJ005 | 2026-08-01 | Subcontract | 0 | 26901763 | 25685509
MCR000380 | PRJ005 | 2026-08-01 | Overhead | 0 | 4895006 | 18621228
MCR000381 | PRJ006 | 2025-06-01 | Labor | 25475857 | 9997764 | 11301615
MCR000382 | PRJ006 | 2025-06-01 | Material | 59133899 | 23206551 | 19682795
MCR000383 | PRJ006 | 2025-06-01 | Equipment | 19194359 | 7532649 | 7555467
MCR000384 | PRJ006 | 2025-06-01 | Subcontract | 65541369 | 25721103 | 28863861
MCR000385 | PRJ006 | 2025-06-01 | Overhead | 14679408 | 5760798 | 43631522
MCR000386 | PRJ006 | 2025-07-01 | Labor | 67109801 | 21612659 | 20931459
MCR000387 | PRJ006 | 2025-07-01 | Material | 155773534 | 50166744 | 53208178
MCR000388 | PRJ006 | 2025-07-01 | Equipment | 50562761 | 16283697 | 18489509
MCR000389 | PRJ006 | 2025-07-01 | Subcontract | 172652418 | 55602575 | 56532896
MCR000390 | PRJ006 | 2025-07-01 | Overhead | 38669247 | 12453401 | 42506940
MCR000391 | PRJ006 | 2025-08-01 | Labor | 95320586 | 26701506 | 27906180
MCR000392 | PRJ006 | 2025-08-01 | Material | 221255678 | 61978845 | 60030124
MCR000393 | PRJ006 | 2025-08-01 | Equipment | 71817706 | 20117804 | 20458315
MCR000394 | PRJ006 | 2025-08-01 | Subcontract | 245229898 | 68694579 | 76221409
MCR000395 | PRJ006 | 2025-08-01 | Overhead | 54924545 | 15385638 | 43303126
MCR000396 | PRJ006 | 2025-09-01 | Labor | 110919439 | 84772526 | 93003391
MCR000397 | PRJ006 | 2025-09-01 | Material | 257463332 | 196771794 | 192913815
MCR000398 | PRJ006 | 2025-09-01 | Equipment | 83570402 | 63870446 | 70204339
MCR000399 | PRJ006 | 2025-09-01 | Subcontract | 285360841 | 218093055 | 236996214
MCR000400 | PRJ006 | 2025-09-01 | Overhead | 63912739 | 48846661 | 42164065
MCR000401 | PRJ006 | 2025-10-01 | Labor | 114834065 | 58399054 | 56220939
MCR000402 | PRJ006 | 2025-10-01 | Material | 266549860 | 135554372 | 131828996
MCR000403 | PRJ006 | 2025-10-01 | Equipment | 86519812 | 43999793 | 49100209
MCR000404 | PRJ006 | 2025-10-01 | Subcontract | 295431943 | 150242403 | 171179901
MCR000405 | PRJ006 | 2025-10-01 | Overhead | 66168380 | 33650039 | 42381298
MCR000406 | PRJ006 | 2025-11-01 | Labor | 108153762 | 71881944 | 77314019
MCR000407 | PRJ006 | 2025-11-01 | Material | 251043714 | 166850509 | 178166646
MCR000408 | PRJ006 | 2025-11-01 | Equipment | 81486649 | 54158252 | 63587079
MCR000409 | PRJ006 | 2025-11-01 | Subcontract | 278245623 | 184929641 | 198871644
MCR000410 | PRJ006 | 2025-11-01 | Overhead | 62319132 | 41418997 | 43642945
MCR000411 | PRJ006 | 2025-12-01 | Labor | 92207453 | 56821572 | 54671143
MCR000412 | PRJ006 | 2025-12-01 | Material | 214029553 | 131892762 | 130232954
MCR000413 | PRJ006 | 2025-12-01 | Equipment | 69472168 | 42811266 | 40954500
MCR000414 | PRJ006 | 2025-12-01 | Subcontract | 237220784 | 146184039 | 147491693
MCR000415 | PRJ006 | 2025-12-01 | Overhead | 53130730 | 32741080 | 41454110
MCR000416 | PRJ006 | 2026-01-01 | Labor | 68716809 | 67272138 | 71165938
MCR000417 | PRJ006 | 2026-01-01 | Material | 159503678 | 156150345 | 126987660
MCR000418 | PRJ006 | 2026-01-01 | Equipment | 51773534 | 50685071 | 47988329
MCR000419 | PRJ006 | 2026-01-01 | Subcontract | 176786742 | 173070059 | 192820537
MCR000420 | PRJ006 | 2026-01-01 | Overhead | 39595218 | 38762787 | 43860017
MCR000421 | PRJ006 | 2026-02-01 | Labor | 40167145 | 61990259 | 58288327
MCR000422 | PRJ006 | 2026-02-01 | Material | 93234937 | 143890186 | 164474904
MCR000423 | PRJ006 | 2026-02-01 | Equipment | 30263265 | 46705527 | 59662735
MCR000424 | PRJ006 | 2026-02-01 | Subcontract | 103337434 | 159481446 | 161247080
MCR000425 | PRJ006 | 2026-02-01 | Overhead | 23144656 | 35719323 | 37040541
MCR000426 | PRJ006 | 2026-03-01 | Labor | 11296756 | 82411271 | 89675024
MCR000427 | PRJ006 | 2026-03-01 | Material | 26221737 | 191290910 | 198202114
MCR000428 | PRJ006 | 2026-03-01 | Equipment | 8511352 | 62091398 | 68007158
MCR000429 | PRJ006 | 2026-03-01 | Subcontract | 29063001 | 212018289 | 235548822
MCR000430 | PRJ006 | 2026-03-01 | Overhead | 6509288 | 47486086 | 45103708
MCR000431 | PRJ006 | 2026-04-01 | Labor | 0 | 96982462 | 104376153
MCR000432 | PRJ006 | 2026-04-01 | Material | 0 | 225113182 | 207718586
MCR000433 | PRJ006 | 2026-04-01 | Equipment | 0 | 73069819 | 73302908
MCR000434 | PRJ006 | 2026-04-01 | Subcontract | 0 | 249505382 | 245625597
MCR000435 | PRJ006 | 2026-04-01 | Overhead | 0 | 55882132 | 42656305
MCR000436 | PRJ006 | 2026-05-01 | Labor | 0 | 53333603 | 64025702
MCR000437 | PRJ006 | 2026-05-01 | Material | 0 | 123796579 | 141017179
MCR000438 | PRJ006 | 2026-05-01 | Equipment | 0 | 40183314 | 41272556
MCR000439 | PRJ006 | 2026-05-01 | Subcontract | 0 | 137210591 | 175702349
MCR000440 | PRJ006 | 2026-05-01 | Overhead | 0 | 30731283 | 41826440
MCR000441 | PRJ006 | 2026-06-01 | Labor | 0 | 28837899 | 25214324
MCR000442 | PRJ006 | 2026-06-01 | Material | 0 | 66937785 | 62206600
MCR000443 | PRJ006 | 2026-06-01 | Equipment | 0 | 21727434 | 30293988
MCR000444 | PRJ006 | 2026-06-01 | Subcontract | 0 | 74190847 | 71350612
MCR000445 | PRJ006 | 2026-06-01 | Overhead | 0 | 16616646 | 39335979
MCR000446 | PRJ006 | 2026-07-01 | Labor | 0 | 10406056 | 11090118
MCR000447 | PRJ006 | 2026-07-01 | Material | 0 | 24154269 | 26870124
MCR000448 | PRJ006 | 2026-07-01 | Equipment | 0 | 7840270 | 10203056
MCR000449 | PRJ006 | 2026-07-01 | Subcontract | 0 | 26771511 | 27310310
MCR000450 | PRJ006 | 2026-07-01 | Overhead | 0 | 5996060 | 42404551
MCR000451 | PRJ006 | 2026-08-01 | Labor | 0 | 2780960 | 3244812
MCR000452 | PRJ006 | 2026-08-01 | Material | 0 | 6455091 | 7974514
MCR000453 | PRJ006 | 2026-08-01 | Equipment | 0 | 2095268 | 2072755
MCR000454 | PRJ006 | 2026-08-01 | Subcontract | 0 | 7154535 | 7081421
MCR000455 | PRJ006 | 2026-08-01 | Overhead | 0 | 1602413 | 42781574
MCR000456 | PRJ007 | 2024-10-01 | Labor | 5799498 | 3818216 | 4488995
MCR000457 | PRJ007 | 2024-10-01 | Material | 12162054 | 8007131 | 7781727
MCR000458 | PRJ007 | 2024-10-01 | Equipment | 2477811 | 1631316 | 1765002
MCR000459 | PRJ007 | 2024-10-01 | Subcontract | 27574148 | 18153991 | 20888046
MCR000460 | PRJ007 | 2024-10-01 | Overhead | 4749954 | 3127227 | 24085731
MCR000461 | PRJ007 | 2024-11-01 | Labor | 16247981 | 8199313 | 8309758
MCR000462 | PRJ007 | 2024-11-01 | Material | 34073435 | 17194675 | 17632355
MCR000463 | PRJ007 | 2024-11-01 | Equipment | 6941881 | 3503122 | 3716272
MCR000464 | PRJ007 | 2024-11-01 | Subcontract | 77252242 | 38984247 | 38528184
MCR000465 | PRJ007 | 2024-11-01 | Overhead | 13307560 | 6715471 | 24293604
MCR000466 | PRJ007 | 2024-12-01 | Labor | 25005925 | 14016005 | 14534443
MCR000467 | PRJ007 | 2024-12-01 | Material | 52439606 | 29392785 | 27416683
MCR000468 | PRJ007 | 2024-12-01 | Equipment | 10683675 | 5988278 | 6155483
MCR000469 | PRJ007 | 2024-12-01 | Subcontract | 118892538 | 66640141 | 56307559
MCR000470 | PRJ007 | 2024-12-01 | Overhead | 20480565 | 11479507 | 22001152
MCR000471 | PRJ007 | 2025-01-01 | Labor | 32122559 | 21529141 | 29416571
MCR000472 | PRJ007 | 2025-01-01 | Material | 67363808 | 45148487 | 49735829
MCR000473 | PRJ007 | 2025-01-01 | Equipment | 13724226 | 9198234 | 10121244
MCR000474 | PRJ007 | 2025-01-01 | Subcontract | 152729106 | 102361909 | 108342223
MCR000475 | PRJ007 | 2025-01-01 | Overhead | 26309291 | 17632980 | 23604068
MCR000476 | PRJ007 | 2025-02-01 | Labor | 37650275 | 18987207 | 16759485
MCR000477 | PRJ007 | 2025-02-01 | Material | 78955912 | 39817830 | 37395978
MCR000478 | PRJ007 | 2025-02-01 | Equipment | 16085919 | 8112203 | 7145856
MCR000479 | PRJ007 | 2025-02-01 | Subcontract | 179011046 | 90276096 | 98769264
MCR000480 | PRJ007 | 2025-02-01 | Overhead | 30836648 | 15551064 | 24498631
MCR000481 | PRJ007 | 2025-03-01 | Labor | 41645125 | 27395606 | 28738035
MCR000482 | PRJ007 | 2025-03-01 | Material | 87333459 | 57450977 | 52900415
MCR000483 | PRJ007 | 2025-03-01 | Equipment | 17792702 | 11704656 | 11835032
MCR000484 | PRJ007 | 2025-03-01 | Subcontract | 198004856 | 130254458 | 115739135
MCR000485 | PRJ007 | 2025-03-01 | Overhead | 34108544 | 22437782 | 24255084
MCR000486 | PRJ007 | 2025-04-01 | Labor | 44167440 | 21532006 | 23142790
MCR000487 | PRJ007 | 2025-04-01 | Material | 92622975 | 45154495 | 48584336
MCR000488 | PRJ007 | 2025-04-01 | Equipment | 18870350 | 9199458 | 10216526
MCR000489 | PRJ007 | 2025-04-01 | Subcontract | 209997393 | 102375532 | 109880722
MCR000490 | PRJ007 | 2025-04-01 | Overhead | 36174392 | 17635327 | 23424893
MCR000491 | PRJ007 | 2025-05-01 | Labor | 45282637 | 33871373 | 35566908
MCR000492 | PRJ007 | 2025-05-01 | Material | 94961640 | 71031224 | 75475951
MCR000493 | PRJ007 | 2025-05-01 | Equipment | 19346813 | 14471400 | 15453826
MCR000494 | PRJ007 | 2025-05-01 | Subcontract | 215299681 | 161043974 | 172794320
MCR000495 | PRJ007 | 2025-05-01 | Overhead | 37087770 | 27741620 | 22595857
MCR000496 | PRJ007 | 2025-06-01 | Labor | 45062263 | 44068112 | 49354831
MCR000497 | PRJ007 | 2025-06-01 | Material | 94499497 | 92414675 | 94573827
MCR000498 | PRJ007 | 2025-06-01 | Equipment | 19252660 | 18827913 | 19706997
MCR000499 | PRJ007 | 2025-06-01 | Subcontract | 214251896 | 209525129 | 212218709
MCR000500 | PRJ007 | 2025-06-01 | Overhead | 36907277 | 36093039 | 25021501
MCR000501 | PRJ007 | 2025-07-01 | Labor | 43585408 | 16423484 | 14280247
MCR000502 | PRJ007 | 2025-07-01 | Material | 91402403 | 34441478 | 33251671
MCR000503 | PRJ007 | 2025-07-01 | Equipment | 18621679 | 7016863 | 6671158
MCR000504 | PRJ007 | 2025-07-01 | Subcontract | 207230077 | 78086681 | 65203670
MCR000505 | PRJ007 | 2025-07-01 | Overhead | 35697691 | 13451301 | 23326686
MCR000506 | PRJ007 | 2025-08-01 | Labor | 40940663 | 19008993 | 22079556
MCR000507 | PRJ007 | 2025-08-01 | Material | 85856142 | 39863517 | 43241049
MCR000508 | PRJ007 | 2025-08-01 | Equipment | 17491724 | 8121511 | 8428514
MCR000509 | PRJ007 | 2025-08-01 | Subcontract | 194655442 | 90379678 | 90266921
MCR000510 | PRJ007 | 2025-08-01 | Overhead | 33531570 | 15568907 | 21374596
MCR000511 | PRJ007 | 2025-09-01 | Labor | 37228951 | 47305428 | 51968521
MCR000512 | PRJ007 | 2025-09-01 | Material | 78072358 | 99203610 | 99127021
MCR000513 | PRJ007 | 2025-09-01 | Equipment | 15905910 | 20211042 | 19885649
MCR000514 | PRJ007 | 2025-09-01 | Subcontract | 177007828 | 224917192 | 210095798
MCR000515 | PRJ007 | 2025-09-01 | Overhead | 30491572 | 38744494 | 23328543
MCR000516 | PRJ007 | 2025-10-01 | Labor | 32567809 | 29584737 | 29235409
MCR000517 | PRJ007 | 2025-10-01 | Material | 68297537 | 62041775 | 61301907
MCR000518 | PRJ007 | 2025-10-01 | Equipment | 13914457 | 12639953 | 13432519
MCR000519 | PRJ007 | 2025-10-01 | Subcontract | 154846082 | 140662844 | 144026034
MCR000520 | PRJ007 | 2025-10-01 | Overhead | 26673964 | 24230743 | 26001843
MCR000521 | PRJ007 | 2025-11-01 | Labor | 27098323 | 40587639 | 45573462
MCR000522 | PRJ007 | 2025-11-01 | Material | 56827547 | 85115820 | 81869454
MCR000523 | PRJ007 | 2025-11-01 | Equipment | 11577643 | 17340896 | 18021466
MCR000524 | PRJ007 | 2025-11-01 | Subcontract | 128841000 | 192976963 | 200556011
MCR000525 | PRJ007 | 2025-11-01 | Overhead | 22194298 | 33242433 | 22795433
MCR000526 | PRJ007 | 2025-12-01 | Labor | 20997352 | 22174778 | 24450327
MCR000527 | PRJ007 | 2025-12-01 | Material | 44033280 | 46502444 | 41992994
MCR000528 | PRJ007 | 2025-12-01 | Equipment | 8971029 | 9474079 | 10721865
MCR000529 | PRJ007 | 2025-12-01 | Subcontract | 99833481 | 105431638 | 101711319
MCR000530 | PRJ007 | 2025-12-01 | Overhead | 17197430 | 18161775 | 24097356
MCR000531 | PRJ007 | 2026-01-01 | Labor | 14502088 | 29357200 | 34426244
MCR000532 | PRJ007 | 2026-01-01 | Material | 30412143 | 61564611 | 73576297
MCR000533 | PRJ007 | 2026-01-01 | Equipment | 6195955 | 12542739 | 13006311
MCR000534 | PRJ007 | 2026-01-01 | Subcontract | 68951260 | 139581003 | 134128021
MCR000535 | PRJ007 | 2026-01-01 | Overhead | 11877623 | 24044384 | 23541171
MCR000536 | PRJ007 | 2026-02-01 | Labor | 7971137 | 24898231 | 23243361
MCR000537 | PRJ007 | 2026-02-01 | Material | 16716170 | 52213762 | 53876847
MCR000538 | PRJ007 | 2026-02-01 | Equipment | 3405634 | 10637663 | 9996132
MCR000539 | PRJ007 | 2026-02-01 | Subcontract | 37899367 | 118380498 | 116290567
MCR000540 | PRJ007 | 2026-02-01 | Overhead | 6528588 | 20392360 | 24766664
MCR000541 | PRJ007 | 2026-03-01 | Labor | 2139205 | 35960362 | 38945901
MCR000542 | PRJ007 | 2026-03-01 | Material | 4486100 | 75412017 | 75197237
MCR000543 | PRJ007 | 2026-03-01 | Equipment | 913966 | 15363911 | 15789678
MCR000544 | PRJ007 | 2026-03-01 | Subcontract | 10171010 | 170976229 | 160346329
MCR000545 | PRJ007 | 2026-03-01 | Overhead | 1752070 | 29452561 | 22669409
MCR000546 | PRJ007 | 2026-04-01 | Labor | 0 | 22983201 | 22419758
MCR000547 | PRJ007 | 2026-04-01 | Material | 0 | 48197779 | 47755850
MCR000548 | PRJ007 | 2026-04-01 | Equipment | 0 | 9819475 | 12209658
MCR000549 | PRJ007 | 2026-04-01 | Subcontract | 0 | 109275349 | 121279796
MCR000550 | PRJ007 | 2026-04-01 | Overhead | 0 | 18823897 | 24304810
MCR000551 | PRJ007 | 2026-05-01 | Labor | 0 | 7659837 | 9611183
MCR000552 | PRJ007 | 2026-05-01 | Material | 0 | 16063347 | 18728696
MCR000553 | PRJ007 | 2026-05-01 | Equipment | 0 | 3272633 | 2899108
MCR000554 | PRJ007 | 2026-05-01 | Subcontract | 0 | 36419269 | 36009516
MCR000555 | PRJ007 | 2026-05-01 | Overhead | 0 | 6273625 | 24159477
MCR000556 | PRJ007 | 2026-06-01 | Labor | 0 | 16006931 | 16049751
MCR000557 | PRJ007 | 2026-06-01 | Material | 0 | 33567931 | 22878712
MCR000558 | PRJ007 | 2026-06-01 | Equipment | 0 | 6838893 | 7667916
MCR000559 | PRJ007 | 2026-06-01 | Subcontract | 0 | 76106150 | 64892263
MCR000560 | PRJ007 | 2026-06-01 | Overhead | 0 | 13110133 | 25694382
MCR000561 | PRJ007 | 2026-07-01 | Labor | 0 | 6635949 | 8117288
MCR000562 | PRJ007 | 2026-07-01 | Material | 0 | 13916164 | 20153347
MCR000563 | PRJ007 | 2026-07-01 | Equipment | 0 | 2835181 | 3532724
MCR000564 | PRJ007 | 2026-07-01 | Subcontract | 0 | 31551115 | 35659613
MCR000565 | PRJ007 | 2026-07-01 | Overhead | 0 | 5435031 | 22659027
MCR000566 | PRJ007 | 2026-08-01 | Labor | 0 | 3211436 | 2988167
MCR000567 | PRJ007 | 2026-08-01 | Material | 0 | 6734661 | 7329120
MCR000568 | PRJ007 | 2026-08-01 | Equipment | 0 | 1372072 | 1516467
MCR000569 | PRJ007 | 2026-08-01 | Subcontract | 0 | 15269012 | 15072956
MCR000570 | PRJ007 | 2026-08-01 | Overhead | 0 | 2630257 | 23904362
MCR000571 | PRJ008 | 2025-05-01 | Labor | 5841798 | 3881161 | 3825685
MCR000572 | PRJ008 | 2025-05-01 | Material | 24111805 | 16019350 | 19373377
MCR000573 | PRJ008 | 2025-05-01 | Equipment | 13226499 | 8787393 | 9004472
MCR000574 | PRJ008 | 2025-05-01 | Subcontract | 11534130 | 7663021 | 7881673
MCR000575 | PRJ008 | 2025-05-01 | Overhead | 5807271 | 3858222 | 16773751
MCR000576 | PRJ008 | 2025-06-01 | Labor | 15388762 | 9351711 | 11413728
MCR000577 | PRJ008 | 2025-06-01 | Material | 63516547 | 38598842 | 36650421
MCR000578 | PRJ008 | 2025-06-01 | Equipment | 34841919 | 21173344 | 21681373
MCR000579 | PRJ008 | 2025-06-01 | Subcontract | 30383794 | 18464153 | 20538125
MCR000580 | PRJ008 | 2025-06-01 | Overhead | 15297810 | 9296440 | 16914326
MCR000581 | PRJ008 | 2025-07-01 | Labor | 21857699 | 12593448 | 13080347
MCR000582 | PRJ008 | 2025-07-01 | Material | 90216844 | 51978990 | 53629577
MCR000583 | PRJ008 | 2025-07-01 | Equipment | 49488332 | 28513007 | 23773019
MCR000584 | PRJ008 | 2025-07-01 | Subcontract | 43156157 | 24864685 | 24636367
MCR000585 | PRJ008 | 2025-07-01 | Overhead | 21728513 | 12519017 | 17777983
MCR000586 | PRJ008 | 2025-08-01 | Labor | 25434629 | 12302854 | 13132499
MCR000587 | PRJ008 | 2025-08-01 | Material | 104980489 | 50779576 | 55307553
MCR000588 | PRJ008 | 2025-08-01 | Equipment | 57586910 | 27855070 | 32934582
MCR000589 | PRJ008 | 2025-08-01 | Subcontract | 50218498 | 24290933 | 25978544
MCR000590 | PRJ008 | 2025-08-01 | Overhead | 25284302 | 12230141 | 16347362
MCR000591 | PRJ008 | 2025-09-01 | Labor | 26332281 | 23593475 | 23125692
MCR000592 | PRJ008 | 2025-09-01 | Material | 108685515 | 97381196 | 92863186
MCR000593 | PRJ008 | 2025-09-01 | Equipment | 59619297 | 53418327 | 52703038
MCR000594 | PRJ008 | 2025-09-01 | Subcontract | 51990835 | 46583298 | 45609795
MCR000595 | PRJ008 | 2025-09-01 | Overhead | 26176649 | 23454030 | 17068927
MCR000596 | PRJ008 | 2025-10-01 | Labor | 24800439 | 18026061 | 20036818
MCR000597 | PRJ008 | 2025-10-01 | Material | 102362894 | 74401898 | 79725535
MCR000598 | PRJ008 | 2025-10-01 | Equipment | 56151032 | 40813063 | 44198521
MCR000599 | PRJ008 | 2025-10-01 | Subcontract | 48966345 | 35590914 | 36721361
MCR000600 | PRJ008 | 2025-10-01 | Overhead | 24653861 | 17919521 | 15598003
MCR000601 | PRJ008 | 2025-11-01 | Labor | 21143835 | 14010332 | 16458602
MCR000602 | PRJ008 | 2025-11-01 | Material | 87270397 | 57827125 | 57839847
MCR000603 | PRJ008 | 2025-11-01 | Equipment | 47872062 | 31720994 | 28270331
MCR000604 | PRJ008 | 2025-11-01 | Subcontract | 41746693 | 27662201 | 23455009
MCR000605 | PRJ008 | 2025-11-01 | Overhead | 21018869 | 13927526 | 16742142
MCR000606 | PRJ008 | 2025-12-01 | Labor | 15757261 | 16281668 | 16254431
MCR000607 | PRJ008 | 2025-12-01 | Material | 65037510 | 67201981 | 65725431
MCR000608 | PRJ008 | 2025-12-01 | Equipment | 35676241 | 36863559 | 40983784
MCR000609 | PRJ008 | 2025-12-01 | Subcontract | 31111363 | 32146760 | 42101963
MCR000610 | PRJ008 | 2025-12-01 | Overhead | 15664130 | 16185438 | 16863548
MCR000611 | PRJ008 | 2026-01-01 | Labor | 9210617 | 20351525 | 21252370
MCR000612 | PRJ008 | 2026-01-01 | Material | 38016479 | 84000166 | 92558955
MCR000613 | PRJ008 | 2026-01-01 | Equipment | 20853890 | 46078181 | 44483532
MCR000614 | PRJ008 | 2026-01-01 | Subcontract | 18185574 | 40182344 | 31263460
MCR000615 | PRJ008 | 2026-01-01 | Overhead | 9156179 | 20231241 | 14949287
MCR000616 | PRJ008 | 2026-02-01 | Labor | 2590428 | 15480108 | 18097036
MCR000617 | PRJ008 | 2026-02-01 | Material | 10691895 | 63893574 | 55373868
MCR000618 | PRJ008 | 2026-02-01 | Equipment | 5865025 | 35048736 | 34891027
MCR000619 | PRJ008 | 2026-02-01 | Subcontract | 5114578 | 30564149 | 33846510
MCR000620 | PRJ008 | 2026-02-01 | Overhead | 2575118 | 15388616 | 17231268
MCR000621 | PRJ008 | 2026-03-01 | Labor | 0 | 13989624 | 16327819
MCR000622 | PRJ008 | 2026-03-01 | Material | 0 | 57741656 | 66178496
MCR000623 | PRJ008 | 2026-03-01 | Equipment | 0 | 31674109 | 37168373
MCR000624 | PRJ008 | 2026-03-01 | Subcontract | 0 | 27621316 | 28908129
MCR000625 | PRJ008 | 2026-03-01 | Overhead | 0 | 13906941 | 16969803
MCR000626 | PRJ008 | 2026-04-01 | Labor | 0 | 6763365 | 8337541
MCR000627 | PRJ008 | 2026-04-01 | Material | 0 | 27915539 | 28427958
MCR000628 | PRJ008 | 2026-04-01 | Equipment | 0 | 15313032 | 14229131
MCR000629 | PRJ008 | 2026-04-01 | Subcontract | 0 | 13353686 | 13814682
MCR000630 | PRJ008 | 2026-04-01 | Overhead | 0 | 6723391 | 15467230
MCR000631 | PRJ008 | 2026-05-01 | Labor | 0 | 1732416 | 1002641
MCR000632 | PRJ008 | 2026-05-01 | Material | 0 | 7150484 | 6103477
MCR000633 | PRJ008 | 2026-05-01 | Equipment | 0 | 3922389 | 5234573
MCR000634 | PRJ008 | 2026-05-01 | Subcontract | 0 | 3420508 | 3795591
MCR000635 | PRJ008 | 2026-05-01 | Overhead | 0 | 1722177 | 15368732
MCR000636 | PRJ009 | 2025-04-01 | Labor | 9733782 | 7887396 | 8255907
MCR000637 | PRJ009 | 2025-04-01 | Material | 19438391 | 15751153 | 16436749
MCR000638 | PRJ009 | 2025-04-01 | Equipment | 4576883 | 3708701 | 4193653
MCR000639 | PRJ009 | 2025-04-01 | Subcontract | 18602941 | 15074178 | 14746101
MCR000640 | PRJ009 | 2025-04-01 | Overhead | 5764989 | 4671437 | 23579560
MCR000641 | PRJ009 | 2025-05-01 | Labor | 26697347 | 20831195 | 21982759
MCR000642 | PRJ009 | 2025-05-01 | Material | 53314679 | 41599957 | 47787874
MCR000643 | PRJ009 | 2025-05-01 | Equipment | 12553253 | 9794953 | 9535337
MCR000644 | PRJ009 | 2025-05-01 | Subcontract | 51023247 | 39812016 | 42963417
MCR000645 | PRJ009 | 2025-05-01 | Overhead | 15811933 | 12337610 | 22732005
MCR000646 | PRJ009 | 2025-06-01 | Labor | 40006091 | 32066843 | 36231560
MCR000647 | PRJ009 | 2025-06-01 | Material | 79892280 | 64037579 | 54691309
MCR000648 | PRJ009 | 2025-06-01 | Equipment | 18811105 | 15078023 | 15611111
MCR000649 | PRJ009 | 2025-06-01 | Subcontract | 76458559 | 61285283 | 59854618
MCR000650 | PRJ009 | 2025-06-01 | Overhead | 23694251 | 18992104 | 22827173
MCR000651 | PRJ009 | 2025-07-01 | Labor | 49803644 | 26293149 | 31486856
MCR000652 | PRJ009 | 2025-07-01 | Material | 99458022 | 52507495 | 57962882
MCR000653 | PRJ009 | 2025-07-01 | Equipment | 23417973 | 12363197 | 12523229
MCR000654 | PRJ009 | 2025-07-01 | Subcontract | 95183377 | 50250755 | 49191907
MCR000655 | PRJ009 | 2025-07-01 | Overhead | 29497009 | 15572540 | 23455841
MCR000656 | PRJ009 | 2025-08-01 | Labor | 56246378 | 43076755 | 45847866
MCR000657 | PRJ009 | 2025-08-01 | Material | 112324181 | 86024405 | 104763311
MCR000658 | PRJ009 | 2025-08-01 | Equipment | 26447385 | 20254949 | 21177897
MCR000659 | PRJ009 | 2025-08-01 | Subcontract | 107496557 | 82327129 | 87668991
MCR000660 | PRJ009 | 2025-08-01 | Overhead | 33312822 | 25512901 | 22865599
MCR000661 | PRJ009 | 2025-09-01 | Labor | 59506249 | 71741952 | 78318911
MCR000662 | PRJ009 | 2025-09-01 | Material | 118834151 | 143268887 | 142524172
MCR000663 | PRJ009 | 2025-09-01 | Equipment | 27980196 | 33733497 | 25360192
MCR000664 | PRJ009 | 2025-09-01 | Subcontract | 113726733 | 137111278 | 137719368
MCR000665 | PRJ009 | 2025-09-01 | Overhead | 35243533 | 42490325 | 22668149
MCR000666 | PRJ009 | 2025-10-01 | Labor | 59774716 | 56600853 | 55867198
MCR000667 | PRJ009 | 2025-10-01 | Material | 119370281 | 113032069 | 121628669
MCR000668 | PRJ009 | 2025-10-01 | Equipment | 28106431 | 26614062 | 32900150
MCR000669 | PRJ009 | 2025-10-01 | Subcontract | 114239820 | 108174020 | 96985414
MCR000670 | PRJ009 | 2025-10-01 | Overhead | 35402537 | 33522766 | 21473315
MCR000671 | PRJ009 | 2025-11-01 | Labor | 57268374 | 58807699 | 64788659
MCR000672 | PRJ009 | 2025-11-01 | Material | 114365110 | 117439146 | 119696686
MCR000673 | PRJ009 | 2025-11-01 | Equipment | 26927934 | 27651734 | 29066670
MCR000674 | PRJ009 | 2025-11-01 | Subcontract | 109449768 | 112391684 | 111136867
MCR000675 | PRJ009 | 2025-11-01 | Overhead | 33918116 | 34829805 | 22314602
MCR000676 | PRJ009 | 2025-12-01 | Labor | 52237427 | 54378116 | 71323168
MCR000677 | PRJ009 | 2025-12-01 | Material | 104318294 | 108593256 | 150588077
MCR000678 | PRJ009 | 2025-12-01 | Equipment | 24562353 | 25568917 | 23137166
MCR000679 | PRJ009 | 2025-12-01 | Subcontract | 99834758 | 103925985 | 111820132
MCR000680 | PRJ009 | 2025-12-01 | Overhead | 30938456 | 32206314 | 22906859
MCR000681 | PRJ009 | 2026-01-01 | Labor | 44979287 | 48369849 | 77024254
MCR000682 | PRJ009 | 2026-01-01 | Material | 89823767 | 96594730 | 117483550
MCR000683 | PRJ009 | 2026-01-01 | Equipment | 21149531 | 22743794 | 23376792
MCR000684 | PRJ009 | 2026-01-01 | Subcontract | 85963197 | 92443148 | 83640189
MCR000685 | PRJ009 | 2026-01-01 | Overhead | 26639706 | 28647821 | 22013540
MCR000686 | PRJ009 | 2026-02-01 | Labor | 35862384 | 32329642 | 33597114
MCR000687 | PRJ009 | 2026-02-01 | Material | 71617285 | 64562388 | 60834263
MCR000688 | PRJ009 | 2026-02-01 | Equipment | 16862709 | 15201592 | 15521581
MCR000689 | PRJ009 | 2026-02-01 | Subcontract | 68539219 | 61787537 | 67024465
MCR000690 | PRJ009 | 2026-02-01 | Overhead | 21240074 | 19147750 | 22432604
MCR000691 | PRJ009 | 2026-03-01 | Labor | 25373548 | 36791647 | 36780509
MCR000692 | PRJ009 | 2026-03-01 | Material | 50671049 | 73473026 | 73396302
MCR000693 | PRJ009 | 2026-03-01 | Equipment | 11930795 | 17299654 | 18043982
MCR000694 | PRJ009 | 2026-03-01 | Subcontract | 48493238 | 70315200 | 74336008
MCR000695 | PRJ009 | 2026-03-01 | Overhead | 15027892 | 21790445 | 22668869
MCR000696 | PRJ009 | 2026-04-01 | Labor | 14234676 | 24266292 | 25461706
MCR000697 | PRJ009 | 2026-04-01 | Material | 28426690 | 48459856 | 51195408
MCR000698 | PRJ009 | 2026-04-01 | Equipment | 6693230 | 11410157 | 11154209
MCR000699 | PRJ009 | 2026-04-01 | Subcontract | 27204928 | 46377082 | 39921450
MCR000700 | PRJ009 | 2026-04-01 | Overhead | 8430716 | 14372102 | 21695717
MCR000701 | PRJ009 | 2026-05-01 | Labor | 3882287 | 17466296 | 18288672
MCR000702 | PRJ009 | 2026-05-01 | Material | 7752938 | 34880245 | 35553022
MCR000703 | PRJ009 | 2026-05-01 | Equipment | 1825475 | 8212758 | 8973065
MCR000704 | PRJ009 | 2026-05-01 | Subcontract | 7419721 | 33381113 | 36360014
MCR000705 | PRJ009 | 2026-05-01 | Overhead | 2299347 | 10344695 | 22856356
MCR000706 | PRJ009 | 2026-06-01 | Labor | 0 | 4698504 | 5726395
MCR000707 | PRJ009 | 2026-06-01 | Material | 0 | 9382926 | 9439731
MCR000708 | PRJ009 | 2026-06-01 | Equipment | 0 | 2209265 | 1493800
MCR000709 | PRJ009 | 2026-06-01 | Subcontract | 0 | 8979654 | 8391736
MCR000710 | PRJ009 | 2026-06-01 | Overhead | 0 | 2782764 | 19300888
MCR000711 | PRJ010 | 2025-01-01 | Labor | 1802104 | 2244536 | 2668297
MCR000712 | PRJ010 | 2025-01-01 | Material | 5073550 | 6319150 | 6297069
MCR000713 | PRJ010 | 2025-01-01 | Equipment | 1326735 | 1652460 | 1472869
MCR000714 | PRJ010 | 2025-01-01 | Subcontract | 6567025 | 8179286 | 7721961
MCR000715 | PRJ010 | 2025-01-01 | Overhead | 1555809 | 1937773 | 8052064
MCR000716 | PRJ010 | 2025-02-01 | Labor | 5068156 | 3757676 | 4546455
MCR000717 | PRJ010 | 2025-02-01 | Material | 14268620 | 10579165 | 10755309
MCR000718 | PRJ010 | 2025-02-01 | Equipment | 3731249 | 2766455 | 3015055
MCR000719 | PRJ010 | 2025-02-01 | Subcontract | 18468801 | 13693301 | 14289527
MCR000720 | PRJ010 | 2025-02-01 | Overhead | 4375485 | 3244111 | 7877122
MCR000721 | PRJ010 | 2025-03-01 | Labor | 7836735 | 9334234 | 10410144
MCR000722 | PRJ010 | 2025-03-01 | Material | 22063133 | 26279114 | 28777016
MCR000723 | PRJ010 | 2025-03-01 | Equipment | 5769517 | 6871998 | 7293841
MCR000724 | PRJ010 | 2025-03-01 | Subcontract | 28557746 | 34014764 | 31678885
MCR000725 | PRJ010 | 2025-03-01 | Overhead | 6765680 | 8058514 | 9136096
MCR000726 | PRJ010 | 2025-04-01 | Labor | 10121448 | 8603876 | 9742214
MCR000727 | PRJ010 | 2025-04-01 | Material | 28495395 | 24222900 | 22945162
MCR000728 | PRJ010 | 2025-04-01 | Equipment | 7451556 | 6334297 | 7756582
MCR000729 | PRJ010 | 2025-04-01 | Subcontract | 36883441 | 31353274 | 35323395
MCR000730 | PRJ010 | 2025-04-01 | Overhead | 8738139 | 7427975 | 8282631
MCR000731 | PRJ010 | 2025-05-01 | Labor | 11936719 | 9148679 | 9525789
MCR000732 | PRJ010 | 2025-05-01 | Material | 33606014 | 25756712 | 28971124
MCR000733 | PRJ010 | 2025-05-01 | Equipment | 8787985 | 6735390 | 6595012
MCR000734 | PRJ010 | 2025-05-01 | Subcontract | 43498447 | 33338586 | 34388658
MCR000735 | PRJ010 | 2025-05-01 | Overhead | 10305315 | 7898320 | 8278281
MCR000736 | PRJ010 | 2025-06-01 | Labor | 13297909 | 16783402 | 17622759
MCR000737 | PRJ010 | 2025-06-01 | Material | 37438236 | 47251110 | 51625620
MCR000738 | PRJ010 | 2025-06-01 | Equipment | 9790112 | 12356182 | 12886143
MCR000739 | PRJ010 | 2025-06-01 | Subcontract | 48458740 | 61160181 | 65275362
MCR000740 | PRJ010 | 2025-06-01 | Overhead | 11480469 | 14489596 | 8532677
MCR000741 | PRJ010 | 2025-07-01 | Labor | 14221462 | 11281260 | 13705362
MCR000742 | PRJ010 | 2025-07-01 | Material | 40038360 | 31760668 | 29021044
MCR000743 | PRJ010 | 2025-07-01 | Equipment | 10470046 | 8305426 | 9734326
MCR000744 | PRJ010 | 2025-07-01 | Subcontract | 51824250 | 41109896 | 40523657
MCR000745 | PRJ010 | 2025-07-01 | Overhead | 12277800 | 9739438 | 8114351
MCR000746 | PRJ010 | 2025-08-01 | Labor | 14725097 | 9339018 | 9388166
MCR000747 | PRJ010 | 2025-08-01 | Material | 41456265 | 26292582 | 23567153
MCR000748 | PRJ010 | 2025-08-01 | Equipment | 10840828 | 6875520 | 7264755
MCR000749 | PRJ010 | 2025-08-01 | Subcontract | 53659537 | 34032197 | 34929320
MCR000750 | PRJ010 | 2025-08-01 | Overhead | 12712602 | 8062644 | 8510096
MCR000751 | PRJ010 | 2025-09-01 | Labor | 14828039 | 10225429 | 12948519
MCR000752 | PRJ010 | 2025-09-01 | Material | 41746085 | 28788136 | 31791093
MCR000753 | PRJ010 | 2025-09-01 | Equipment | 10916616 | 7528108 | 7742663
MCR000754 | PRJ010 | 2025-09-01 | Subcontract | 54034670 | 37262355 | 35295436
MCR000755 | PRJ010 | 2025-09-01 | Overhead | 12801475 | 8827908 | 8464071
MCR000756 | PRJ010 | 2025-10-01 | Labor | 14551343 | 27178504 | 30982516
MCR000757 | PRJ010 | 2025-10-01 | Material | 40967088 | 76516935 | 72432236
MCR000758 | PRJ010 | 2025-10-01 | Equipment | 10712908 | 20009206 | 20433656
MCR000759 | PRJ010 | 2025-10-01 | Subcontract | 53026363 | 99040840 | 89943928
MCR000760 | PRJ010 | 2025-10-01 | Overhead | 12562595 | 23463989 | 8011914
MCR000761 | PRJ010 | 2025-11-01 | Labor | 13918305 | 16242077 | 17314680
MCR000762 | PRJ010 | 2025-11-01 | Material | 39184866 | 45727093 | 55025769
MCR000763 | PRJ010 | 2025-11-01 | Equipment | 10246857 | 11957651 | 15501228
MCR000764 | PRJ010 | 2025-11-01 | Subcontract | 50719518 | 59187547 | 64905393
MCR000765 | PRJ010 | 2025-11-01 | Overhead | 12016075 | 14022255 | 7879184
MCR000766 | PRJ010 | 2025-12-01 | Labor | 12955059 | 13888741 | 16557659
MCR000767 | PRJ010 | 2025-12-01 | Material | 36472996 | 39101634 | 33285721
MCR000768 | PRJ010 | 2025-12-01 | Equipment | 9537702 | 10225092 | 10397600
MCR000769 | PRJ010 | 2025-12-01 | Subcontract | 47209368 | 50611785 | 46233470
MCR000770 | PRJ010 | 2025-12-01 | Overhead | 11184478 | 11990552 | 7738006
MCR000771 | PRJ010 | 2026-01-01 | Labor | 11691423 | 10866036 | 10836872
MCR000772 | PRJ010 | 2026-01-01 | Material | 32915419 | 30591668 | 35209647
MCR000773 | PRJ010 | 2026-01-01 | Equipment | 8607394 | 7999732 | 8519257
MCR000774 | PRJ010 | 2026-01-01 | Subcontract | 42604565 | 39596784 | 44013336
MCR000775 | PRJ010 | 2026-01-01 | Overhead | 10093544 | 9380963 | 8000121
MCR000776 | PRJ010 | 2026-02-01 | Labor | 10162183 | 9449096 | 10481595
MCR000777 | PRJ010 | 2026-02-01 | Material | 28610079 | 26602490 | 27481721
MCR000778 | PRJ010 | 2026-02-01 | Equipment | 7481546 | 6956561 | 7418963
MCR000779 | PRJ010 | 2026-02-01 | Subcontract | 37031883 | 34433331 | 33744345
MCR000780 | PRJ010 | 2026-02-01 | Overhead | 8773307 | 8157678 | 8217155
MCR000781 | PRJ010 | 2026-03-01 | Labor | 8409188 | 8755012 | 9830642
MCR000782 | PRJ010 | 2026-03-01 | Material | 23674789 | 24648403 | 29231007
MCR000783 | PRJ010 | 2026-03-01 | Equipment | 6190966 | 6445566 | 7033135
MCR000784 | PRJ010 | 2026-03-01 | Subcontract | 30643817 | 31904029 | 34707893
MCR000785 | PRJ010 | 2026-03-01 | Overhead | 7259896 | 7558456 | 8056119
MCR000786 | PRJ010 | 2026-04-01 | Labor | 6485031 | 5630932 | 6575948
MCR000787 | PRJ010 | 2026-04-01 | Material | 18257617 | 15853031 | 13148797
MCR000788 | PRJ010 | 2026-04-01 | Equipment | 4774373 | 4145573 | 3871484
MCR000789 | PRJ010 | 2026-04-01 | Subcontract | 23632019 | 20519608 | 19481169
MCR000790 | PRJ010 | 2026-04-01 | Overhead | 5598715 | 4861347 | 7762076
MCR000791 | PRJ010 | 2026-05-01 | Labor | 4460467 | 4374443 | 3882408
MCR000792 | PRJ010 | 2026-05-01 | Material | 12557764 | 12315578 | 12785215
MCR000793 | PRJ010 | 2026-05-01 | Equipment | 3283860 | 3220528 | 3619033
MCR000794 | PRJ010 | 2026-05-01 | Subcontract | 16254330 | 15940853 | 15227735
MCR000795 | PRJ010 | 2026-05-01 | Overhead | 3850850 | 3776583 | 8785062
MCR000796 | PRJ010 | 2026-06-01 | Labor | 2442904 | 1728592 | 2357726
MCR000797 | PRJ010 | 2026-06-01 | Material | 6877624 | 4866589 | 5234480
MCR000798 | PRJ010 | 2026-06-01 | Equipment | 1798501 | 1272615 | 1535764
MCR000799 | PRJ010 | 2026-06-01 | Subcontract | 8902156 | 6299142 | 6655826
MCR000800 | PRJ010 | 2026-06-01 | Overhead | 2109030 | 1492344 | 7940982
MCR000801 | PRJ010 | 2026-07-01 | Labor | 653698 | 735726 | 784741
MCR000802 | PRJ010 | 2026-07-01 | Material | 1840387 | 2071325 | 1448551
MCR000803 | PRJ010 | 2026-07-01 | Equipment | 481262 | 541652 | 635494
MCR000804 | PRJ010 | 2026-07-01 | Subcontract | 2382133 | 2681051 | 2693185
MCR000805 | PRJ010 | 2026-07-01 | Overhead | 564357 | 635174 | 7612147
MCR000806 | PRJ011 | 2025-05-01 | Labor | 7006116 | 2776691 | 2979268
MCR000807 | PRJ011 | 2025-05-01 | Material | 21038635 | 8338113 | 9484890
MCR000808 | PRJ011 | 2025-05-01 | Equipment | 6508326 | 2579405 | 2751439
MCR000809 | PRJ011 | 2025-05-01 | Subcontract | 16049525 | 6360810 | 7472250
MCR000810 | PRJ011 | 2025-05-01 | Overhead | 5473936 | 2169451 | 21958404
MCR000811 | PRJ011 | 2025-06-01 | Labor | 19340497 | 21121665 | 23478323
MCR000812 | PRJ011 | 2025-06-01 | Material | 58077494 | 63426154 | 63114913
MCR000813 | PRJ011 | 2025-06-01 | Equipment | 17966341 | 19620955 | 18762925
MCR000814 | PRJ011 | 2025-06-01 | Subcontract | 44304975 | 48385251 | 46668906
MCR000815 | PRJ011 | 2025-06-01 | Overhead | 15110889 | 16502529 | 23209877
MCR000816 | PRJ011 | 2025-07-01 | Labor | 29220883 | 16605451 | 19196117
MCR000817 | PRJ011 | 2025-07-01 | Material | 87747260 | 49864435 | 45232614
MCR000818 | PRJ011 | 2025-07-01 | Equipment | 27144718 | 15425622 | 17106909
MCR000819 | PRJ011 | 2025-07-01 | Subcontract | 66938841 | 38039564 | 43648431
MCR000820 | PRJ011 | 2025-07-01 | Overhead | 22830515 | 12973974 | 21539327
MCR000821 | PRJ011 | 2025-08-01 | Labor | 36735961 | 27686345 | 32696786
MCR000822 | PRJ011 | 2025-08-01 | Material | 110314256 | 83139203 | 88883509
MCR000823 | PRJ011 | 2025-08-01 | Equipment | 34125845 | 25719210 | 24289667
MCR000824 | PRJ011 | 2025-08-01 | Subcontract | 84154291 | 63423540 | 73524941
MCR000825 | PRJ011 | 2025-08-01 | Overhead | 28702107 | 21631568 | 23977290
MCR000826 | PRJ011 | 2025-09-01 | Labor | 41981604 | 30143947 | 31795071
MCR000827 | PRJ011 | 2025-09-01 | Material | 126066375 | 90519125 | 98376628
MCR000828 | PRJ011 | 2025-09-01 | Equipment | 38998782 | 28002198 | 31304174
MCR000829 | PRJ011 | 2025-09-01 | Subcontract | 96170946 | 69053385 | 72737935
MCR000830 | PRJ011 | 2025-09-01 | Overhead | 32800571 | 23551712 | 22387297
MCR000831 | PRJ011 | 2025-10-01 | Labor | 45062316 | 29465751 | 38845921
MCR000832 | PRJ011 | 2025-10-01 | Material | 135317430 | 88482574 | 80606280
MCR000833 | PRJ011 | 2025-10-01 | Equipment | 41860606 | 27372189 | 30093496
MCR000834 | PRJ011 | 2025-10-01 | Subcontract | 103228202 | 67499782 | 67926413
MCR000835 | PRJ011 | 2025-10-01 | Overhead | 35207556 | 23021832 | 24264346
MCR000836 | PRJ011 | 2025-11-01 | Labor | 46093173 | 48163409 | 53942550
MCR000837 | PRJ011 | 2025-11-01 | Material | 138412987 | 144629691 | 149954447
MCR000838 | PRJ011 | 2025-11-01 | Equipment | 42818220 | 44741365 | 44589249
MCR000839 | PRJ011 | 2025-11-01 | Subcontract | 105589678 | 110332150 | 122849162
MCR000840 | PRJ011 | 2025-11-01 | Overhead | 36012973 | 37630466 | 21025662
MCR000841 | PRJ011 | 2025-12-01 | Labor | 45202513 | 23735795 | 24682671
MCR000842 | PRJ011 | 2025-12-01 | Material | 135738427 | 71276113 | 79272409
MCR000843 | PRJ011 | 2025-12-01 | Equipment | 41990842 | 22049350 | 24555370
MCR000844 | PRJ011 | 2025-12-01 | Subcontract | 103549364 | 54373668 | 63890182
MCR000845 | PRJ011 | 2025-12-01 | Overhead | 35317093 | 18544970 | 24119550
MCR000846 | PRJ011 | 2026-01-01 | Labor | 42535789 | 47518830 | 51896671
MCR000847 | PRJ011 | 2026-01-01 | Material | 127730533 | 142694085 | 138294276
MCR000848 | PRJ011 | 2026-01-01 | Equipment | 39513591 | 44142583 | 42737691
MCR000849 | PRJ011 | 2026-01-01 | Subcontract | 97440465 | 108855555 | 109556454
MCR000850 | PRJ011 | 2026-01-01 | Overhead | 33233560 | 37126850 | 24668983
MCR000851 | PRJ011 | 2026-02-01 | Labor | 38261395 | 32366493 | 40123359
MCR000852 | PRJ011 | 2026-02-01 | Material | 114894976 | 97193199 | 87324423
MCR000853 | PRJ011 | 2026-02-01 | Equipment | 35542896 | 30066830 | 32286860
MCR000854 | PRJ011 | 2026-02-01 | Subcontract | 87648737 | 74144766 | 85952757
MCR000855 | PRJ011 | 2026-02-01 | Overhead | 29893941 | 25288205 | 23575429
MCR000856 | PRJ011 | 2026-03-01 | Labor | 32580029 | 27413681 | 27704168
MCR000857 | PRJ011 | 2026-03-01 | Material | 97834427 | 82320421 | 94850928
MCR000858 | PRJ011 | 2026-03-01 | Equipment | 30265195 | 25465919 | 23355246
MCR000859 | PRJ011 | 2026-03-01 | Subcontract | 74633933 | 62798925 | 59729912
MCR000860 | PRJ011 | 2026-03-01 | Overhead | 25455043 | 21418533 | 24062109
MCR000861 | PRJ011 | 2026-04-01 | Labor | 25741117 | 29142374 | 40320981
MCR000862 | PRJ011 | 2026-04-01 | Material | 77297888 | 87511506 | 88613919
MCR000863 | PRJ011 | 2026-04-01 | Equipment | 23912193 | 27071787 | 30233670
MCR000864 | PRJ011 | 2026-04-01 | Subcontract | 58967437 | 66758993 | 73981886
MCR000865 | PRJ011 | 2026-04-01 | Overhead | 20111745 | 22769175 | 23170571
MCR000866 | PRJ011 | 2026-05-01 | Labor | 18075593 | 24433639 | 24017994
MCR000867 | PRJ011 | 2026-05-01 | Material | 54279120 | 73371668 | 70874211
MCR000868 | PRJ011 | 2026-05-01 | Equipment | 16791310 | 22697612 | 23262031
MCR000869 | PRJ011 | 2026-05-01 | Subcontract | 41407348 | 55972282 | 78180315
MCR000870 | PRJ011 | 2026-05-01 | Overhead | 14122609 | 19090202 | 21133563
MCR000871 | PRJ011 | 2026-06-01 | Labor | 10076848 | 32953782 | 43202357
MCR000872 | PRJ011 | 2026-06-01 | Material | 30259723 | 98956767 | 104440330
MCR000873 | PRJ011 | 2026-06-01 | Equipment | 9360881 | 30612392 | 34190377
MCR000874 | PRJ011 | 2026-06-01 | Subcontract | 23083920 | 75490121 | 91414802
MCR000875 | PRJ011 | 2026-06-01 | Overhead | 7873124 | 25747059 | 20636235
MCR000876 | PRJ011 | 2026-07-01 | Labor | 2734849 | 10372017 | 8940328
MCR000877 | PRJ011 | 2026-07-01 | Material | 8212465 | 31146084 | 26962274
MCR000878 | PRJ011 | 2026-07-01 | Equipment | 2540536 | 9635078 | 7933315
MCR000879 | PRJ011 | 2026-07-01 | Subcontract | 6264958 | 23760090 | 57030842
MCR000880 | PRJ011 | 2026-07-01 | Overhead | 2136760 | 8103742 | 24031407
MCR000881 | PRJ011 | 2026-08-01 | Labor | 0 | 12093275 | 14443393
MCR000882 | PRJ011 | 2026-08-01 | Material | 0 | 36314843 | 41170962
MCR000883 | PRJ011 | 2026-08-01 | Equipment | 0 | 11234039 | 11205664
MCR000884 | PRJ011 | 2026-08-01 | Subcontract | 0 | 27703127 | 39188406
MCR000885 | PRJ011 | 2026-08-01 | Overhead | 0 | 9448575 | 24239279
MCR000886 | PRJ012 | 2025-01-01 | Labor | 2084582 | 1052050 | 1107927
MCR000887 | PRJ012 | 2025-01-01 | Material | 4347356 | 2194029 | 2467227
MCR000888 | PRJ012 | 2025-01-01 | Equipment | 970293 | 489689 | 541407
MCR000889 | PRJ012 | 2025-01-01 | Subcontract | 7562903 | 3816856 | 3431656
MCR000890 | PRJ012 | 2025-01-01 | Overhead | 1511569 | 762861 | 6078821
MCR000891 | PRJ012 | 2025-02-01 | Labor | 5754524 | 4657212 | 4740536
MCR000892 | PRJ012 | 2025-02-01 | Material | 12000946 | 9712524 | 9469420
MCR000893 | PRJ012 | 2025-02-01 | Equipment | 2678510 | 2167754 | 2009640
MCR000894 | PRJ012 | 2025-02-01 | Subcontract | 20877518 | 16896451 | 15728293
MCR000895 | PRJ012 | 2025-02-01 | Overhead | 4172711 | 3377030 | 6601674
MCR000896 | PRJ012 | 2025-03-01 | Labor | 8694309 | 4858527 | 4638166
MCR000897 | PRJ012 | 2025-03-01 | Material | 18131811 | 10132363 | 10932493
MCR000898 | PRJ012 | 2025-03-01 | Equipment | 4046868 | 2261458 | 2114245
MCR000899 | PRJ012 | 2025-03-01 | Subcontract | 31543114 | 17626826 | 19130283
MCR000900 | PRJ012 | 2025-03-01 | Overhead | 6304404 | 3523008 | 6812633
MCR000901 | PRJ012 | 2025-04-01 | Labor | 10930327 | 4965554 | 5567851
MCR000902 | PRJ012 | 2025-04-01 | Material | 22794983 | 10355566 | 9986396
MCR000903 | PRJ012 | 2025-04-01 | Equipment | 5087648 | 2311275 | 2483598
MCR000904 | PRJ012 | 2025-04-01 | Subcontract | 39655429 | 18015123 | 18481543
MCR000905 | PRJ012 | 2025-04-01 | Overhead | 7925782 | 3600615 | 6897861
MCR000906 | PRJ012 | 2025-05-01 | Labor | 12491102 | 9003191 | 8999522
MCR000907 | PRJ012 | 2025-05-01 | Material | 26049950 | 18775979 | 18852357
MCR000908 | PRJ012 | 2025-05-01 | Equipment | 5814129 | 4190640 | 3858928
MCR000909 | PRJ012 | 2025-05-01 | Subcontract | 45317952 | 32663745 | 33678782
MCR000910 | PRJ012 | 2025-05-01 | Overhead | 9057529 | 6528380 | 5858599
MCR000911 | PRJ012 | 2025-06-01 | Labor | 13407730 | 8359089 | 7092272
MCR000912 | PRJ012 | 2025-06-01 | Material | 27961558 | 17432717 | 16919215
MCR000913 | PRJ012 | 2025-06-01 | Equipment | 6240784 | 3890836 | 4153419
MCR000914 | PRJ012 | 2025-06-01 | Subcontract | 48643492 | 30326931 | 31012868
MCR000915 | PRJ012 | 2025-06-01 | Overhead | 9722193 | 6061330 | 6624709
MCR000916 | PRJ012 | 2025-07-01 | Labor | 13714448 | 4499900 | 4928453
MCR000917 | PRJ012 | 2025-07-01 | Material | 28601214 | 9384454 | 10229140
MCR000918 | PRJ012 | 2025-07-01 | Equipment | 6383550 | 2094531 | 2250506
MCR000919 | PRJ012 | 2025-07-01 | Subcontract | 49756274 | 16325722 | 17462476
MCR000920 | PRJ012 | 2025-07-01 | Overhead | 9944600 | 3262961 | 6228479
MCR000921 | PRJ012 | 2025-08-01 | Labor | 13449443 | 11990870 | 12235407
MCR000922 | PRJ012 | 2025-08-01 | Material | 28048552 | 25006724 | 21780596
MCR000923 | PRJ012 | 2025-08-01 | Equipment | 6260201 | 5581290 | 6318296
MCR000924 | PRJ012 | 2025-08-01 | Subcontract | 48794831 | 43503098 | 41782242
MCR000925 | PRJ012 | 2025-08-01 | Overhead | 9752440 | 8694801 | 6761524
MCR000926 | PRJ012 | 2025-09-01 | Labor | 12655993 | 18463518 | 18664704
MCR000927 | PRJ012 | 2025-09-01 | Material | 26393826 | 38505306 | 45059125
MCR000928 | PRJ012 | 2025-09-01 | Equipment | 5890880 | 8594060 | 8416460
MCR000929 | PRJ012 | 2025-09-01 | Subcontract | 45916178 | 66985986 | 65750554
MCR000930 | PRJ012 | 2025-09-01 | Overhead | 9177094 | 13388238 | 5973574
MCR000931 | PRJ012 | 2025-10-01 | Labor | 11384201 | 9718211 | 9981579
MCR000932 | PRJ012 | 2025-10-01 | Material | 23741528 | 20267140 | 17993493
MCR000933 | PRJ012 | 2025-10-01 | Equipment | 5298909 | 4523455 | 5158831
MCR000934 | PRJ012 | 2025-10-01 | Subcontract | 41302092 | 35257852 | 37005125
MCR000935 | PRJ012 | 2025-10-01 | Overhead | 8254894 | 7046855 | 6245453
MCR000936 | PRJ012 | 2025-11-01 | Labor | 9693781 | 7806203 | 7454020
MCR000937 | PRJ012 | 2025-11-01 | Material | 20216191 | 16279684 | 18569879
MCR000938 | PRJ012 | 2025-11-01 | Equipment | 4512084 | 3633488 | 3586882
MCR000939 | PRJ012 | 2025-11-01 | Subcontract | 35169218 | 28321050 | 31367580
MCR000940 | PRJ012 | 2025-11-01 | Overhead | 7029140 | 5660422 | 6751767
MCR000941 | PRJ012 | 2025-12-01 | Labor | 7658948 | 8292576 | 8456665
MCR000942 | PRJ012 | 2025-12-01 | Material | 15972587 | 17294005 | 15947119
MCR000943 | PRJ012 | 2025-12-01 | Equipment | 3564947 | 3859876 | 3439318
MCR000944 | PRJ012 | 2025-12-01 | Subcontract | 27786806 | 30085620 | 28815060
MCR000945 | PRJ012 | 2025-12-01 | Overhead | 5553645 | 6013100 | 6267861
MCR000946 | PRJ012 | 2026-01-01 | Labor | 5378167 | 13957223 | 14341659
MCR000947 | PRJ012 | 2026-01-01 | Material | 11216063 | 29107516 | 31687427
MCR000948 | PRJ012 | 2026-01-01 | Equipment | 2503331 | 6496552 | 7268723
MCR000949 | PRJ012 | 2026-01-01 | Subcontract | 19512090 | 50637064 | 60304160
MCR000950 | PRJ012 | 2026-01-01 | Overhead | 3899808 | 10120640 | 6359110
MCR000951 | PRJ012 | 2026-02-01 | Labor | 2998240 | 7859947 | 8018903
MCR000952 | PRJ012 | 2026-02-01 | Material | 6252772 | 16391766 | 15200371
MCR000953 | PRJ012 | 2026-02-01 | Equipment | 1395566 | 3658504 | 3958206
MCR000954 | PRJ012 | 2026-02-01 | Subcontract | 10877672 | 28516034 | 40711551
MCR000955 | PRJ012 | 2026-02-01 | Overhead | 2174079 | 5699393 | 6370195
MCR000956 | PRJ012 | 2026-03-01 | Labor | 813720 | 5705597 | 7458011
MCR000957 | PRJ012 | 2026-03-01 | Material | 1696997 | 11898911 | 11312184
MCR000958 | PRJ012 | 2026-03-01 | Equipment | 378756 | 2655737 | 2263630
MCR000959 | PRJ012 | 2026-03-01 | Subcontract | 2952192 | 20700012 | 30534328
MCR000960 | PRJ012 | 2026-03-01 | Overhead | 590044 | 4137234 | 6782021
MCR000961 | PRJ012 | 2026-04-01 | Labor | 0 | 5137830 | 4005466
MCR000962 | PRJ012 | 2026-04-01 | Material | 0 | 10714845 | 12149492
MCR000963 | PRJ012 | 2026-04-01 | Equipment | 0 | 2391463 | 2322270
MCR000964 | PRJ012 | 2026-04-01 | Subcontract | 0 | 18640144 | 31499289
MCR000965 | PRJ012 | 2026-04-01 | Overhead | 0 | 3725536 | 6358854
MCR000966 | PRJ012 | 2026-05-01 | Labor | 0 | 2851567 | 3484588
MCR000967 | PRJ012 | 2026-05-01 | Material | 0 | 5946888 | 6364377
MCR000968 | PRJ012 | 2026-05-01 | Equipment | 0 | 1327295 | 1738742
MCR000969 | PRJ012 | 2026-05-01 | Subcontract | 0 | 10345539 | 21538896
MCR000970 | PRJ012 | 2026-05-01 | Overhead | 0 | 2067724 | 6221577
MCR000971 | PRJ012 | 2026-06-01 | Labor | 0 | 1682979 | 1688048
MCR000972 | PRJ012 | 2026-06-01 | Material | 0 | 3509821 | 3059508
MCR000973 | PRJ012 | 2026-06-01 | Equipment | 0 | 783362 | 792307
MCR000974 | PRJ012 | 2026-06-01 | Subcontract | 0 | 6105881 | 18683421
MCR000975 | PRJ012 | 2026-06-01 | Overhead | 0 | 1220359 | 5621030
MCR000976 | PRJ012 | 2026-07-01 | Labor | 0 | 247471 | 341254
MCR000977 | PRJ012 | 2026-07-01 | Material | 0 | 516095 | 661666
MCR000978 | PRJ012 | 2026-07-01 | Equipment | 0 | 115188 | 169576
MCR000979 | PRJ012 | 2026-07-01 | Subcontract | 0 | 897828 | 9828773
MCR000980 | PRJ012 | 2026-07-01 | Overhead | 0 | 179446 | 6629525
MCR000981 | PRJ013 | 2025-02-01 | Labor | 22497590 | 12490994 | 12139726
MCR000982 | PRJ013 | 2025-02-01 | Material | 36494729 | 20262413 | 19776086
MCR000983 | PRJ013 | 2025-02-01 | Equipment | 8480824 | 4708679 | 5032937
MCR000984 | PRJ013 | 2025-02-01 | Subcontract | 41746709 | 23178390 | 20873437
MCR000985 | PRJ013 | 2025-02-01 | Overhead | 10742162 | 5964207 | 35749723
MCR000986 | PRJ013 | 2025-03-01 | Labor | 60697236 | 31778564 | 28851817
MCR000987 | PRJ013 | 2025-03-01 | Material | 98460733 | 51549970 | 48108002
MCR000988 | PRJ013 | 2025-03-01 | Equipment | 22880788 | 11979435 | 11506846
MCR000989 | PRJ013 | 2025-03-01 | Subcontract | 112630280 | 58968560 | 63692215
MCR000990 | PRJ013 | 2025-03-01 | Overhead | 28981751 | 15173647 | 34244703
MCR000991 | PRJ013 | 2025-04-01 | Labor | 89030404 | 34882124 | 38232805
MCR000992 | PRJ013 | 2025-04-01 | Material | 144421714 | 56584447 | 51538827
MCR000993 | PRJ013 | 2025-04-01 | Equipment | 33561426 | 13149371 | 16179391
MCR000994 | PRJ013 | 2025-04-01 | Subcontract | 165205536 | 64727551 | 63833261
MCR000995 | PRJ013 | 2025-04-01 | Overhead | 42510289 | 16655537 | 38748946
MCR000996 | PRJ013 | 2025-05-01 | Labor | 107966980 | 82927808 | 76236121
MCR000997 | PRJ013 | 2025-05-01 | Material | 175139902 | 134522316 | 144855658
MCR000998 | PRJ013 | 2025-05-01 | Equipment | 40699869 | 31260955 | 32589030
MCR000999 | PRJ013 | 2025-05-01 | Subcontract | 200344398 | 153881509 | 171562948
MCR001000 | PRJ013 | 2025-05-01 | Overhead | 51552136 | 39596417 | 36474006
MCR001001 | PRJ013 | 2025-06-01 | Labor | 118028365 | 63604669 | 58149650
MCR001002 | PRJ013 | 2025-06-01 | Material | 191461096 | 103177060 | 105620988
MCR001003 | PRJ013 | 2025-06-01 | Equipment | 44492669 | 23976791 | 28134983
MCR001004 | PRJ013 | 2025-06-01 | Subcontract | 219014386 | 118025338 | 125092763
MCR001005 | PRJ013 | 2025-06-01 | Overhead | 56356252 | 30369994 | 38164633
MCR001006 | PRJ013 | 2025-07-01 | Labor | 119802048 | 53589548 | 57553100
MCR001007 | PRJ013 | 2025-07-01 | Material | 194338297 | 86930913 | 88749293
MCR001008 | PRJ013 | 2025-07-01 | Equipment | 45161287 | 20201432 | 18195848
MCR001009 | PRJ013 | 2025-07-01 | Subcontract | 222305646 | 99441197 | 89244183
MCR001010 | PRJ013 | 2025-07-01 | Overhead | 57203151 | 25587968 | 37356057
MCR001011 | PRJ013 | 2025-08-01 | Labor | 113963452 | 46432948 | 52825904
MCR001012 | PRJ013 | 2025-08-01 | Material | 184867150 | 75321752 | 90798085
MCR001013 | PRJ013 | 2025-08-01 | Equipment | 42960335 | 17503638 | 19085603
MCR001014 | PRJ013 | 2025-08-01 | Subcontract | 211471501 | 86161353 | 83607252
MCR001015 | PRJ013 | 2025-08-01 | Overhead | 54415335 | 22170831 | 37019638
MCR001016 | PRJ013 | 2025-09-01 | Labor | 101310828 | 93330752 | 101751556
MCR001017 | PRJ013 | 2025-09-01 | Material | 164342547 | 151397574 | 152715503
MCR001018 | PRJ013 | 2025-09-01 | Equipment | 38190727 | 35182511 | 36789720
MCR001019 | PRJ013 | 2025-09-01 | Subcontract | 187993189 | 173185296 | 203396689
MCR001020 | PRJ013 | 2025-09-01 | Overhead | 48373952 | 44563621 | 35505360
MCR001021 | PRJ013 | 2025-10-01 | Labor | 82826010 | 60604758 | 52826405
MCR001022 | PRJ013 | 2025-10-01 | Material | 134357183 | 98310718 | 97560027
MCR001023 | PRJ013 | 2025-10-01 | Equipment | 31222581 | 22845927 | 22506921
MCR001024 | PRJ013 | 2025-10-01 | Subcontract | 153692612 | 112458677 | 111176156
MCR001025 | PRJ013 | 2025-10-01 | Overhead | 39547811 | 28937595 | 34925850
MCR001026 | PRJ013 | 2025-11-01 | Labor | 59794584 | 100310559 | 105233460
MCR001027 | PRJ013 | 2025-11-01 | Material | 96996485 | 162719949 | 165791519
MCR001028 | PRJ013 | 2025-11-01 | Equipment | 22540519 | 37813660 | 34834034
MCR001029 | PRJ013 | 2025-11-01 | Subcontract | 110955312 | 186137082 | 176055601
MCR001030 | PRJ013 | 2025-11-01 | Overhead | 28550752 | 47896343 | 36103692
MCR001031 | PRJ013 | 2025-12-01 | Labor | 34099669 | 58131000 | 60130525
MCR001032 | PRJ013 | 2025-12-01 | Material | 55315178 | 94297883 | 95075650
MCR001033 | PRJ013 | 2025-12-01 | Equipment | 12854412 | 21913405 | 31243213
MCR001034 | PRJ013 | 2025-12-01 | Subcontract | 63275621 | 107868352 | 105026570
MCR001035 | PRJ013 | 2025-12-01 | Overhead | 16281930 | 27756423 | 35244101
MCR001036 | PRJ013 | 2026-01-01 | Labor | 9417412 | 149213207 | 165386875
MCR001037 | PRJ013 | 2026-01-01 | Material | 15276565 | 242047954 | 253914658
MCR001038 | PRJ013 | 2026-01-01 | Equipment | 3550043 | 56248291 | 52692180
MCR001039 | PRJ013 | 2026-01-01 | Subcontract | 17475025 | 276881231 | 269203362
MCR001040 | PRJ013 | 2026-01-01 | Overhead | 4496631 | 71246408 | 37215413
MCR001041 | PRJ013 | 2026-02-01 | Labor | 0 | 43069348 | 40043005
MCR001042 | PRJ013 | 2026-02-01 | Material | 0 | 69865448 | 75124323
MCR001043 | PRJ013 | 2026-02-01 | Equipment | 0 | 16235676 | 17442157
MCR001044 | PRJ013 | 2026-02-01 | Subcontract | 0 | 79919830 | 88830202
MCR001045 | PRJ013 | 2026-02-01 | Overhead | 0 | 20564777 | 35346181
MCR001046 | PRJ013 | 2026-03-01 | Labor | 0 | 42010073 | 41025041
MCR001047 | PRJ013 | 2026-03-01 | Material | 0 | 68147133 | 66879371
MCR001048 | PRJ013 | 2026-03-01 | Equipment | 0 | 15836365 | 19436920
MCR001049 | PRJ013 | 2026-03-01 | Subcontract | 0 | 77954231 | 75333686
MCR001050 | PRJ013 | 2026-03-01 | Overhead | 0 | 20058994 | 37299913
MCR001051 | PRJ013 | 2026-04-01 | Labor | 0 | 27729117 | 31895888
MCR001052 | PRJ013 | 2026-04-01 | Material | 0 | 44981112 | 40665913
MCR001053 | PRJ013 | 2026-04-01 | Equipment | 0 | 10452932 | 12395847
MCR001054 | PRJ013 | 2026-04-01 | Subcontract | 0 | 51454373 | 55111373
MCR001055 | PRJ013 | 2026-04-01 | Overhead | 0 | 13240115 | 38809799
MCR001056 | PRJ013 | 2026-05-01 | Labor | 0 | 16065729 | 14181607
MCR001057 | PRJ013 | 2026-05-01 | Material | 0 | 26061211 | 33639159
MCR001058 | PRJ013 | 2026-05-01 | Equipment | 0 | 6056232 | 6640565
MCR001059 | PRJ013 | 2026-05-01 | Subcontract | 0 | 29811697 | 34161779
MCR001060 | PRJ013 | 2026-05-01 | Overhead | 0 | 7671074 | 35583518
MCR001061 | PRJ013 | 2026-06-01 | Labor | 0 | 3263376 | 5116584
MCR001062 | PRJ013 | 2026-06-01 | Material | 0 | 5293724 | 5201270
MCR001063 | PRJ013 | 2026-06-01 | Equipment | 0 | 1230182 | 1403565
MCR001064 | PRJ013 | 2026-06-01 | Subcontract | 0 | 6055547 | 5397881
MCR001065 | PRJ013 | 2026-06-01 | Overhead | 0 | 1558199 | 35051402
MCR001066 | PRJ014 | 2024-11-01 | Labor | 4858954 | 3349801 | 3389388
MCR001067 | PRJ014 | 2024-11-01 | Material | 15621918 | 10769871 | 11308086
MCR001068 | PRJ014 | 2024-11-01 | Equipment | 3387112 | 2335101 | 2119671
MCR001069 | PRJ014 | 2024-11-01 | Subcontract | 13710772 | 9452312 | 10357010
MCR001070 | PRJ014 | 2024-11-01 | Overhead | 3033507 | 2091323 | 15026729
MCR001071 | PRJ014 | 2024-12-01 | Labor | 13612936 | 15241588 | 14529226
MCR001072 | PRJ014 | 2024-12-01 | Material | 43766652 | 49002895 | 50708614
MCR001073 | PRJ014 | 2024-12-01 | Equipment | 9489397 | 10624708 | 12897856
MCR001074 | PRJ014 | 2024-12-01 | Subcontract | 38412352 | 43008007 | 41412922
MCR001075 | PRJ014 | 2024-12-01 | Overhead | 8498730 | 9515518 | 14976893
MCR001076 | PRJ014 | 2025-01-01 | Labor | 20950545 | 40515789 | 41565266
MCR001077 | PRJ014 | 2025-01-01 | Material | 67357636 | 130261422 | 139992897
MCR001078 | PRJ014 | 2025-01-01 | Equipment | 14604346 | 28243017 | 33807212
MCR001079 | PRJ014 | 2025-01-01 | Subcontract | 59117276 | 114325574 | 111154824
MCR001080 | PRJ014 | 2025-01-01 | Overhead | 13079693 | 25294525 | 14864448
MCR001081 | PRJ014 | 2025-02-01 | Labor | 26913026 | 23237751 | 23321813
MCR001082 | PRJ014 | 2025-02-01 | Material | 86527478 | 74711181 | 66451224
MCR001083 | PRJ014 | 2025-02-01 | Equipment | 18760712 | 16198726 | 12390668
MCR001084 | PRJ014 | 2025-02-01 | Subcontract | 75941928 | 65571207 | 66772900
MCR001085 | PRJ014 | 2025-02-01 | Overhead | 16802146 | 14507625 | 16891860
MCR001086 | PRJ014 | 2025-03-01 | Labor | 31544275 | 29227268 | 29296699
MCR001087 | PRJ014 | 2025-03-01 | Material | 101417305 | 93967948 | 97038934
MCR001088 | PRJ014 | 2025-03-01 | Equipment | 21989094 | 20373940 | 23227015
MCR001089 | PRJ014 | 2025-03-01 | Subcontract | 89010173 | 82472151 | 77685969
MCR001090 | PRJ014 | 2025-03-01 | Overhead | 19693494 | 18246957 | 14727319
MCR001091 | PRJ014 | 2025-04-01 | Labor | 34891253 | 42485137 | 40865170
MCR001092 | PRJ014 | 2025-04-01 | Material | 112178099 | 136593031 | 139334721
MCR001093 | PRJ014 | 2025-04-01 | Equipment | 24322228 | 29615823 | 26059865
MCR001094 | PRJ014 | 2025-04-01 | Subcontract | 98454519 | 119882590 | 127081782
MCR001095 | PRJ014 | 2025-04-01 | Overhead | 21783055 | 26524014 | 15771008
MCR001096 | PRJ014 | 2025-05-01 | Labor | 37004507 | 39929719 | 39689342
MCR001097 | PRJ014 | 2025-05-01 | Material | 118972377 | 128377162 | 122462707
MCR001098 | PRJ014 | 2025-05-01 | Equipment | 25795349 | 27834475 | 29268781
MCR001099 | PRJ014 | 2025-05-01 | Subcontract | 104417602 | 112671830 | 123296179
MCR001100 | PRJ014 | 2025-05-01 | Overhead | 23102387 | 24928634 | 13285219
MCR001101 | PRJ014 | 2025-06-01 | Labor | 37938845 | 34881740 | 31279998
MCR001102 | PRJ014 | 2025-06-01 | Material | 121976347 | 112147517 | 104515676
MCR001103 | PRJ014 | 2025-06-01 | Equipment | 26446664 | 24315597 | 27294081
MCR001104 | PRJ014 | 2025-06-01 | Subcontract | 107054074 | 98427678 | 91198649
MCR001105 | PRJ014 | 2025-06-01 | Overhead | 23685706 | 21777116 | 14060654
MCR001106 | PRJ014 | 2025-07-01 | Labor | 37754210 | 27501760 | 27339277
MCR001107 | PRJ014 | 2025-07-01 | Material | 121382732 | 88420306 | 99726217
MCR001108 | PRJ014 | 2025-07-01 | Equipment | 26317957 | 19171111 | 20200083
MCR001109 | PRJ014 | 2025-07-01 | Subcontract | 106533081 | 77603193 | 83740683
MCR001110 | PRJ014 | 2025-07-01 | Overhead | 23570436 | 17169701 | 15021933
MCR001111 | PRJ014 | 2025-08-01 | Labor | 36516867 | 33660549 | 24765936
MCR001112 | PRJ014 | 2025-08-01 | Material | 117404576 | 108221293 | 118806968
MCR001113 | PRJ014 | 2025-08-01 | Equipment | 25455422 | 23464321 | 27191805
MCR001114 | PRJ014 | 2025-08-01 | Subcontract | 103041602 | 94981778 | 87787190
MCR001115 | PRJ014 | 2025-08-01 | Overhead | 22797947 | 21014711 | 15067006
MCR001116 | PRJ014 | 2025-09-01 | Labor | 34301038 | 22632720 | 25781428
MCR001117 | PRJ014 | 2025-09-01 | Material | 110280515 | 72765961 | 59882648
MCR001118 | PRJ014 | 2025-09-01 | Equipment | 23910797 | 15776968 | 13149388
MCR001119 | PRJ014 | 2025-09-01 | Subcontract | 96789080 | 63863960 | 61613668
MCR001120 | PRJ014 | 2025-09-01 | Overhead | 21414577 | 14129896 | 15349572
MCR001121 | PRJ014 | 2025-10-01 | Labor | 31191280 | 33185052 | 33205752
MCR001122 | PRJ014 | 2025-10-01 | Material | 100282398 | 106692531 | 106349389
MCR001123 | PRJ014 | 2025-10-01 | Equipment | 21743026 | 23132858 | 27536915
MCR001124 | PRJ014 | 2025-10-01 | Subcontract | 88014107 | 93640041 | 84637396
MCR001125 | PRJ014 | 2025-10-01 | Overhead | 19473115 | 20717852 | 14397966
MCR001126 | PRJ014 | 2025-11-01 | Labor | 27286067 | 31424490 | 24688303
MCR001127 | PRJ014 | 2025-11-01 | Material | 87726834 | 101032188 | 109370956
MCR001128 | PRJ014 | 2025-11-01 | Equipment | 19020754 | 21905594 | 19841195
MCR001129 | PRJ014 | 2025-11-01 | Subcontract | 76994559 | 88672170 | 84602564
MCR001130 | PRJ014 | 2025-11-01 | Overhead | 17035040 | 19618711 | 14408079
MCR001131 | PRJ014 | 2025-12-01 | Labor | 22703604 | 18775142 | 19751244
MCR001132 | PRJ014 | 2025-12-01 | Material | 72993859 | 60363548 | 62062364
MCR001133 | PRJ014 | 2025-12-01 | Equipment | 15826380 | 13087902 | 13309526
MCR001134 | PRJ014 | 2025-12-01 | Subcontract | 64063978 | 52978827 | 56512920
MCR001135 | PRJ014 | 2025-12-01 | Overhead | 14174150 | 11721561 | 15250916
MCR001136 | PRJ014 | 2026-01-01 | Labor | 17592070 | 16164461 | 14228277
MCR001137 | PRJ014 | 2026-01-01 | Material | 56559876 | 51970003 | 54405898
MCR001138 | PRJ014 | 2026-01-01 | Equipment | 12263197 | 11268030 | 11731296
MCR001139 | PRJ014 | 2026-01-01 | Subcontract | 49640486 | 45612126 | 43072789
MCR001140 | PRJ014 | 2026-01-01 | Overhead | 10982954 | 10091680 | 13868516
MCR001141 | PRJ014 | 2026-02-01 | Labor | 12150186 | 15401310 | 10634907
MCR001142 | PRJ014 | 2026-02-01 | Material | 39063796 | 49516413 | 47186493
MCR001143 | PRJ014 | 2026-02-01 | Equipment | 8469733 | 10736048 | 9985167
MCR001144 | PRJ014 | 2026-02-01 | Subcontract | 34284831 | 43458702 | 38773530
MCR001145 | PRJ014 | 2026-02-01 | Overhead | 7585516 | 9615235 | 14220077
MCR001146 | PRJ014 | 2026-03-01 | Labor | 6678404 | 6267831 | 7430501
MCR001147 | PRJ014 | 2026-03-01 | Material | 21471589 | 20151567 | 20808867
MCR001148 | PRJ014 | 2026-03-01 | Equipment | 4655426 | 4369222 | 4667046
MCR001149 | PRJ014 | 2026-03-01 | Subcontract | 18844810 | 17686276 | 23080198
MCR001150 | PRJ014 | 2026-03-01 | Overhead | 4169413 | 3913087 | 14941666
MCR001151 | PRJ014 | 2026-04-01 | Labor | 1792276 | 1798232 | 1998516
MCR001152 | PRJ014 | 2026-04-01 | Material | 5762306 | 5781458 | 6700733
MCR001153 | PRJ014 | 2026-04-01 | Equipment | 1249371 | 1253524 | 1535423
MCR001154 | PRJ014 | 2026-04-01 | Subcontract | 5057360 | 5074169 | 3868081
MCR001155 | PRJ014 | 2026-04-01 | Overhead | 1118941 | 1122660 | 15319093
MCR001156 | PRJ015 | 2025-05-01 | Labor | 21398282 | 15539669 | 16970355
MCR001157 | PRJ015 | 2025-05-01 | Material | 48760132 | 35410145 | 39245319
MCR001158 | PRJ015 | 2025-05-01 | Equipment | 10920234 | 7930395 | 8910691
MCR001159 | PRJ015 | 2025-05-01 | Subcontract | 73367794 | 53280501 | 63412597
MCR001160 | PRJ015 | 2025-05-01 | Overhead | 13752399 | 9987144 | 40404977
MCR001161 | PRJ015 | 2025-06-01 | Labor | 56368448 | 30589074 | 30830564
MCR001162 | PRJ015 | 2025-06-01 | Material | 128446427 | 69703130 | 65867966
MCR001163 | PRJ015 | 2025-06-01 | Equipment | 28766638 | 15610592 | 16687376
MCR001164 | PRJ015 | 2025-06-01 | Subcontract | 193269187 | 104880047 | 107492860
MCR001165 | PRJ015 | 2025-06-01 | Overhead | 36227272 | 19659202 | 40321616
MCR001166 | PRJ015 | 2025-07-01 | Labor | 80063916 | 26463714 | 31953587
MCR001167 | PRJ015 | 2025-07-01 | Material | 182441141 | 60302700 | 66507326
MCR001168 | PRJ015 | 2025-07-01 | Equipment | 40859201 | 13505288 | 13355214
MCR001169 | PRJ015 | 2025-07-01 | Subcontract | 274513288 | 90735523 | 103289683
MCR001170 | PRJ015 | 2025-07-01 | Overhead | 51456042 | 17007887 | 36924733
MCR001171 | PRJ015 | 2025-08-01 | Labor | 93166072 | 24307499 | 25867751
MCR001172 | PRJ015 | 2025-08-01 | Material | 212296943 | 55389346 | 55085053
MCR001173 | PRJ015 | 2025-08-01 | Equipment | 47545654 | 12404902 | 13000939
MCR001174 | PRJ015 | 2025-08-01 | Subcontract | 319436347 | 83342558 | 88576538
MCR001175 | PRJ015 | 2025-08-01 | Overhead | 59876629 | 15622115 | 40981808
MCR001176 | PRJ015 | 2025-09-01 | Labor | 96454137 | 81564875 | 83054605
MCR001177 | PRJ015 | 2025-09-01 | Material | 219789436 | 185861368 | 182943527
MCR001178 | PRJ015 | 2025-09-01 | Equipment | 49223660 | 41625189 | 45685430
MCR001179 | PRJ015 | 2025-09-01 | Subcontract | 330710059 | 279659592 | 331454750
MCR001180 | PRJ015 | 2025-09-01 | Overhead | 61989826 | 52420689 | 39389141
MCR001181 | PRJ015 | 2025-10-01 | Labor | 90843059 | 109820776 | 115701074
MCR001182 | PRJ015 | 2025-10-01 | Material | 207003508 | 250247912 | 268511554
MCR001183 | PRJ015 | 2025-10-01 | Equipment | 46360146 | 56045087 | 57155716
MCR001184 | PRJ015 | 2025-10-01 | Subcontract | 311471487 | 376539943 | 362785489
MCR001185 | PRJ015 | 2025-10-01 | Overhead | 58383658 | 70580391 | 37772560
MCR001186 | PRJ015 | 2025-11-01 | Labor | 77449059 | 51106513 | 55241455
MCR001187 | PRJ015 | 2025-11-01 | Material | 176482684 | 116456091 | 107904194
MCR001188 | PRJ015 | 2025-11-01 | Equipment | 39524755 | 26081304 | 25710600
MCR001189 | PRJ015 | 2025-11-01 | Subcontract | 265547790 | 175227715 | 189871380
MCR001190 | PRJ015 | 2025-11-01 | Overhead | 49775508 | 32845495 | 43606935
MCR001191 | PRJ015 | 2025-12-01 | Labor | 57718243 | 53128240 | 60439324
MCR001192 | PRJ015 | 2025-12-01 | Material | 131522198 | 121062987 | 131886194
MCR001193 | PRJ015 | 2025-12-01 | Equipment | 29455483 | 27113056 | 35065683
MCR001194 | PRJ015 | 2025-12-01 | Subcontract | 197897199 | 182159563 | 216470113
MCR001195 | PRJ015 | 2025-12-01 | Overhead | 37094768 | 34144832 | 40044209
MCR001196 | PRJ015 | 2026-01-01 | Labor | 33738136 | 67635911 | 70776064
MCR001197 | PRJ015 | 2026-01-01 | Material | 76878878 | 154121526 | 135481028
MCR001198 | PRJ015 | 2026-01-01 | Equipment | 17217660 | 34516789 | 29444878
MCR001199 | PRJ015 | 2026-01-01 | Subcontract | 115677162 | 231901678 | 238815110
MCR001200 | PRJ015 | 2026-01-01 | Overhead | 21683063 | 43468725 | 40175450
MCR001201 | PRJ015 | 2026-02-01 | Labor | 9488638 | 41924122 | 44259889
MCR001202 | PRJ015 | 2026-02-01 | Material | 21621699 | 95532233 | 97314586
MCR001203 | PRJ015 | 2026-02-01 | Equipment | 4842358 | 21395233 | 26298152
MCR001204 | PRJ015 | 2026-02-01 | Subcontract | 32533472 | 143744262 | 210171182
MCR001205 | PRJ015 | 2026-02-01 | Overhead | 6098225 | 26944090 | 40299053
MCR001206 | PRJ015 | 2026-03-01 | Labor | 0 | 68283330 | 81953790
MCR001207 | PRJ015 | 2026-03-01 | Material | 0 | 155596795 | 197664664
MCR001208 | PRJ015 | 2026-03-01 | Equipment | 0 | 34847188 | 35496913
MCR001209 | PRJ015 | 2026-03-01 | Subcontract | 0 | 234121467 | 300099015
MCR001210 | PRJ015 | 2026-03-01 | Overhead | 0 | 43884812 | 38837326
MCR001211 | PRJ015 | 2026-04-01 | Labor | 0 | 22881068 | 21823875
MCR001212 | PRJ015 | 2026-04-01 | Material | 0 | 52138947 | 30811954
MCR001213 | PRJ015 | 2026-04-01 | Equipment | 0 | 11676948 | 13117970
MCR001214 | PRJ015 | 2026-04-01 | Subcontract | 0 | 78451787 | 127407905
MCR001215 | PRJ015 | 2026-04-01 | Overhead | 0 | 14705366 | 40940356
MCR001216 | PRJ015 | 2026-05-01 | Labor | 0 | 19630206 | 22252007
MCR001217 | PRJ015 | 2026-05-01 | Material | 0 | 44731227 | 50911027
MCR001218 | PRJ015 | 2026-05-01 | Equipment | 0 | 10017928 | 11794164
MCR001219 | PRJ015 | 2026-05-01 | Subcontract | 0 | 67305632 | 133345537
MCR001220 | PRJ015 | 2026-05-01 | Overhead | 0 | 12616079 | 38509962
MCR001221 | PRJ015 | 2026-06-01 | Labor | 0 | 3812992 | 5063035
MCR001222 | PRJ015 | 2026-06-01 | Material | 0 | 8688642 | 4621372
MCR001223 | PRJ015 | 2026-06-01 | Equipment | 0 | 1945893 | 1752328
MCR001224 | PRJ015 | 2026-06-01 | Subcontract | 0 | 13073518 | 27932980
MCR001225 | PRJ015 | 2026-06-01 | Overhead | 0 | 2450561 | 35355645
MCR001226 | PRJ016 | 2025-02-01 | Labor | 7663962 | 7806992 | 8340028
MCR001227 | PRJ016 | 2025-02-01 | Material | 19390055 | 19751925 | 19338184
MCR001228 | PRJ016 | 2025-02-01 | Equipment | 5303821 | 5402805 | 5575577
MCR001229 | PRJ016 | 2025-02-01 | Subcontract | 20169219 | 20545631 | 19533143
MCR001230 | PRJ016 | 2025-02-01 | Overhead | 4782255 | 4871504 | 24221736
MCR001231 | PRJ016 | 2025-03-01 | Labor | 21379236 | 7744749 | 7826721
MCR001232 | PRJ016 | 2025-03-01 | Material | 54090110 | 19594448 | 22826751
MCR001233 | PRJ016 | 2025-03-01 | Equipment | 14795434 | 5359730 | 5816992
MCR001234 | PRJ016 | 2025-03-01 | Subcontract | 56263651 | 20381826 | 18725176
MCR001235 | PRJ016 | 2025-03-01 | Overhead | 13340482 | 4832665 | 22904765
MCR001236 | PRJ016 | 2025-04-01 | Labor | 32728097 | 26634286 | 28755754
MCR001237 | PRJ016 | 2025-04-01 | Material | 82803070 | 67385546 | 72982745
MCR001238 | PRJ016 | 2025-04-01 | Equipment | 22649378 | 18432176 | 18047121
MCR001239 | PRJ016 | 2025-04-01 | Subcontract | 86130404 | 70093347 | 64636237
MCR001240 | PRJ016 | 2025-04-01 | Overhead | 20422086 | 16619594 | 22766884
MCR001241 | PRJ016 | 2025-05-01 | Labor | 41784227 | 33564626 | 38588600
MCR001242 | PRJ016 | 2025-05-01 | Material | 105715354 | 84919513 | 80809076
MCR001243 | PRJ016 | 2025-05-01 | Equipment | 28916646 | 23228296 | 24280870
MCR001244 | PRJ016 | 2025-05-01 | Subcontract | 109963388 | 88331894 | 97534295
MCR001245 | PRJ016 | 2025-05-01 | Overhead | 26073044 | 20944074 | 23930493
MCR001246 | PRJ016 | 2025-06-01 | Labor | 48626394 | 46041580 | 44943865
MCR001247 | PRJ016 | 2025-06-01 | Material | 123026240 | 116486584 | 102545094
MCR001248 | PRJ016 | 2025-06-01 | Equipment | 33651746 | 31862934 | 32170240
MCR001249 | PRJ016 | 2025-06-01 | Subcontract | 127969890 | 121167447 | 111602687
MCR001250 | PRJ016 | 2025-06-01 | Overhead | 30342504 | 28729600 | 23182312
MCR001251 | PRJ016 | 2025-07-01 | Labor | 53339305 | 31606724 | 31552260
MCR001252 | PRJ016 | 2025-07-01 | Material | 134950047 | 79965963 | 82152469
MCR001253 | PRJ016 | 2025-07-01 | Equipment | 36913301 | 21873336 | 21501434
MCR001254 | PRJ016 | 2025-07-01 | Subcontract | 140372840 | 83179291 | 96753263
MCR001255 | PRJ016 | 2025-07-01 | Overhead | 33283325 | 19722358 | 21574012
MCR001256 | PRJ016 | 2025-08-01 | Labor | 56014719 | 29579053 | 35117934
MCR001257 | PRJ016 | 2025-08-01 | Material | 141718926 | 74835893 | 74868734
MCR001258 | PRJ016 | 2025-08-01 | Equipment | 38764813 | 20470092 | 21479341
MCR001259 | PRJ016 | 2025-08-01 | Subcontract | 147413717 | 77843077 | 81243565
MCR001260 | PRJ016 | 2025-08-01 | Overhead | 34952764 | 18457106 | 20327645
MCR001261 | PRJ016 | 2025-09-01 | Labor | 56752886 | 55485675 | 60144872
MCR001262 | PRJ016 | 2025-09-01 | Material | 143586510 | 140380428 | 145258194
MCR001263 | PRJ016 | 2025-09-01 | Equipment | 39275659 | 38398690 | 37018137
MCR001264 | PRJ016 | 2025-09-01 | Subcontract | 149356347 | 146021433 | 137729217
MCR001265 | PRJ016 | 2025-09-01 | Overhead | 35413374 | 34622644 | 24313585
MCR001266 | PRJ016 | 2025-10-01 | Labor | 55664486 | 51580128 | 50881301
MCR001267 | PRJ016 | 2025-10-01 | Material | 140832825 | 130499275 | 134253732
MCR001268 | PRJ016 | 2025-10-01 | Equipment | 38522436 | 35695868 | 33832626
MCR001269 | PRJ016 | 2025-10-01 | Subcontract | 146492010 | 135743220 | 140219065
MCR001270 | PRJ016 | 2025-10-01 | Overhead | 34734221 | 32185612 | 23030084
MCR001271 | PRJ016 | 2025-11-01 | Labor | 52873324 | 37832647 | 46731509
MCR001272 | PRJ016 | 2025-11-01 | Material | 133771102 | 95717735 | 113411489
MCR001273 | PRJ016 | 2025-11-01 | Equipment | 36590821 | 26181966 | 28192250
MCR001274 | PRJ016 | 2025-11-01 | Subcontract | 139146521 | 99564028 | 86552307
MCR001275 | PRJ016 | 2025-11-01 | Overhead | 32992557 | 23607287 | 23467176
MCR001276 | PRJ016 | 2025-12-01 | Labor | 48520207 | 46574626 | 51058394
MCR001277 | PRJ016 | 2025-12-01 | Material | 122757584 | 117835205 | 96710870
MCR001278 | PRJ016 | 2025-12-01 | Equipment | 33578259 | 32231826 | 28845143
MCR001279 | PRJ016 | 2025-12-01 | Subcontract | 127690439 | 122570260 | 124642004
MCR001280 | PRJ016 | 2025-12-01 | Overhead | 30276244 | 29062216 | 23158621
MCR001281 | PRJ016 | 2026-01-01 | Labor | 42768813 | 42692771 | 46674110
MCR001282 | PRJ016 | 2026-01-01 | Material | 108206385 | 108013996 | 117176144
MCR001283 | PRJ016 | 2026-01-01 | Equipment | 29598025 | 29545400 | 31178168
MCR001284 | PRJ016 | 2026-01-01 | Subcontract | 112554519 | 112354399 | 106211141
MCR001285 | PRJ016 | 2026-01-01 | Overhead | 26687418 | 26639968 | 22307234
MCR001286 | PRJ016 | 2026-02-01 | Labor | 35815172 | 46456629 | 51858404
MCR001287 | PRJ016 | 2026-02-01 | Material | 90613464 | 117536670 | 114036173
MCR001288 | PRJ016 | 2026-02-01 | Equipment | 24785779 | 32150167 | 32658120
MCR001289 | PRJ016 | 2026-02-01 | Subcontract | 94254648 | 122259729 | 122649543
MCR001290 | PRJ016 | 2026-02-01 | Overhead | 22348398 | 28988587 | 21696968
MCR001291 | PRJ016 | 2026-03-01 | Labor | 27904355 | 47186685 | 46212041
MCR001292 | PRJ016 | 2026-03-01 | Material | 70598859 | 119383733 | 117748870
MCR001293 | PRJ016 | 2026-03-01 | Equipment | 19311123 | 32655400 | 35689667
MCR001294 | PRJ016 | 2026-03-01 | Subcontract | 73435783 | 124181014 | 116107165
MCR001295 | PRJ016 | 2026-03-01 | Overhead | 17412108 | 29444136 | 25466199
MCR001296 | PRJ016 | 2026-04-01 | Labor | 19363932 | 29933791 | 35947034
MCR001297 | PRJ016 | 2026-04-01 | Material | 48991330 | 75733392 | 74649997
MCR001298 | PRJ016 | 2026-04-01 | Equipment | 13400749 | 20715588 | 23842217
MCR001299 | PRJ016 | 2026-04-01 | Subcontract | 50959983 | 78776640 | 91808935
MCR001300 | PRJ016 | 2026-04-01 | Overhead | 12082948 | 18678460 | 21500650
MCR001301 | PRJ016 | 2026-05-01 | Labor | 10687015 | 33837169 | 33127756
MCR001302 | PRJ016 | 2026-05-01 | Material | 27038469 | 85609057 | 100217023
MCR001303 | PRJ016 | 2026-05-01 | Equipment | 7395916 | 23416909 | 22660275
MCR001304 | PRJ016 | 2026-05-01 | Subcontract | 28124975 | 89049146 | 89276453
MCR001305 | PRJ016 | 2026-05-01 | Overhead | 6668617 | 21114139 | 23580737
MCR001306 | PRJ016 | 2026-06-01 | Labor | 2877458 | 21196989 | 23598269
MCR001307 | PRJ016 | 2026-06-01 | Material | 7280055 | 53629021 | 59039913
MCR001308 | PRJ016 | 2026-06-01 | Equipment | 1991336 | 14669311 | 14738238
MCR001309 | PRJ016 | 2026-06-01 | Subcontract | 7572595 | 55784034 | 59904177
MCR001310 | PRJ016 | 2026-06-01 | Overhead | 1795512 | 13226762 | 23570031
MCR001311 | PRJ016 | 2026-07-01 | Labor | 0 | 8897211 | 9473264
MCR001312 | PRJ016 | 2026-07-01 | Material | 0 | 22510212 | 17609088
MCR001313 | PRJ016 | 2026-07-01 | Equipment | 0 | 6157287 | 6166068
MCR001314 | PRJ016 | 2026-07-01 | Subcontract | 0 | 23414756 | 19727362
MCR001315 | PRJ016 | 2026-07-01 | Overhead | 0 | 5551793 | 21965937
MCR001316 | PRJ016 | 2026-08-01 | Labor | 0 | 6219915 | 6202443
MCR001317 | PRJ016 | 2026-08-01 | Material | 0 | 15736571 | 16060102
MCR001318 | PRJ016 | 2026-08-01 | Equipment | 0 | 4304473 | 3872975
MCR001319 | PRJ016 | 2026-08-01 | Subcontract | 0 | 16368925 | 16789789
MCR001320 | PRJ016 | 2026-08-01 | Overhead | 0 | 3881180 | 21701768
MCR001321 | PRJ017 | 2024-10-01 | Labor | 4258183 | 1764554 | 1921726
MCR001322 | PRJ017 | 2024-10-01 | Material | 13211181 | 5474598 | 5638473
MCR001323 | PRJ017 | 2024-10-01 | Equipment | 2434864 | 1008986 | 1099974
MCR001324 | PRJ017 | 2024-10-01 | Subcontract | 25243685 | 10460763 | 11859565
MCR001325 | PRJ017 | 2024-10-01 | Overhead | 3684651 | 1526887 | 18602201
MCR001326 | PRJ017 | 2024-11-01 | Labor | 12016540 | 3133129 | 3695122
MCR001327 | PRJ017 | 2024-11-01 | Material | 37281792 | 9720658 | 8741106
MCR001328 | PRJ017 | 2024-11-01 | Equipment | 6871156 | 1791549 | 2110818
MCR001329 | PRJ017 | 2024-11-01 | Subcontract | 71237371 | 18574057 | 18802801
MCR001330 | PRJ017 | 2024-11-01 | Overhead | 10398041 | 2711130 | 18009484
MCR001331 | PRJ017 | 2024-12-01 | Labor | 18658590 | 9043760 | 9935531
MCR001332 | PRJ017 | 2024-12-01 | Material | 57889016 | 28058626 | 28367547
MCR001333 | PRJ017 | 2024-12-01 | Equipment | 10669134 | 5171296 | 5673455
MCR001334 | PRJ017 | 2024-12-01 | Subcontract | 110613281 | 53613913 | 51285032
MCR001335 | PRJ017 | 2024-12-01 | Overhead | 16145479 | 7825663 | 20466343
MCR001336 | PRJ017 | 2025-01-01 | Labor | 24213114 | 17288440 | 18585637
MCR001337 | PRJ017 | 2025-01-01 | Material | 75122150 | 53638072 | 50670976
MCR001338 | PRJ017 | 2025-01-01 | Equipment | 13845256 | 9885671 | 9928012
MCR001339 | PRJ017 | 2025-01-01 | Subcontract | 143542039 | 102490654 | 105049502
MCR001340 | PRJ017 | 2025-01-01 | Overhead | 20951869 | 14959873 | 18457673
MCR001341 | PRJ017 | 2025-02-01 | Labor | 28710519 | 25359627 | 29066281
MCR001342 | PRJ017 | 2025-02-01 | Material | 89075529 | 78679252 | 67688991
MCR001343 | PRJ017 | 2025-02-01 | Equipment | 16416910 | 14500842 | 16298716
MCR001344 | PRJ017 | 2025-02-01 | Subcontract | 170203903 | 150338886 | 166795669
MCR001345 | PRJ017 | 2025-02-01 | Overhead | 24843522 | 21943959 | 21120771
MCR001346 | PRJ017 | 2025-03-01 | Labor | 32183059 | 33246823 | 35336827
MCR001347 | PRJ017 | 2025-03-01 | Material | 99849220 | 103149592 | 113243257
MCR001348 | PRJ017 | 2025-03-01 | Equipment | 18402536 | 19010805 | 18575087
MCR001349 | PRJ017 | 2025-03-01 | Subcontract | 190790076 | 197096366 | 191058681
MCR001350 | PRJ017 | 2025-03-01 | Overhead | 27848347 | 28768834 | 19244873
MCR001351 | PRJ017 | 2025-04-01 | Labor | 34665103 | 24877740 | 27440978
MCR001352 | PRJ017 | 2025-04-01 | Material | 107549861 | 77184178 | 71745236
MCR001353 | PRJ017 | 2025-04-01 | Equipment | 19821789 | 14225295 | 15280499
MCR001354 | PRJ017 | 2025-04-01 | Subcontract | 205504321 | 147482125 | 150734594
MCR001355 | PRJ017 | 2025-04-01 | Overhead | 29996087 | 21526976 | 21814575
MCR001356 | PRJ017 | 2025-05-01 | Labor | 36193478 | 25824066 | 27781341
MCR001357 | PRJ017 | 2025-05-01 | Material | 112291707 | 80120192 | 81880101
MCR001358 | PRJ017 | 2025-05-01 | Equipment | 20695727 | 14766412 | 15035992
MCR001359 | PRJ017 | 2025-05-01 | Subcontract | 214564954 | 153092207 | 190019726
MCR001360 | PRJ017 | 2025-05-01 | Overhead | 31318607 | 22345843 | 22074852
MCR001361 | PRJ017 | 2025-06-01 | Labor | 36807890 | 29916122 | 33652884
MCR001362 | PRJ017 | 2025-06-01 | Material | 114197945 | 92815958 | 88698210
MCR001363 | PRJ017 | 2025-06-01 | Equipment | 21047053 | 17106283 | 16862908
MCR001364 | PRJ017 | 2025-06-01 | Subcontract | 218207359 | 177351047 | 149241206
MCR001365 | PRJ017 | 2025-06-01 | Overhead | 31850264 | 25886743 | 22439735
MCR001366 | PRJ017 | 2025-07-01 | Labor | 36551468 | 14872137 | 13711572
MCR001367 | PRJ017 | 2025-07-01 | Material | 113402385 | 46141397 | 53917939
MCR001368 | PRJ017 | 2025-07-01 | Equipment | 20900428 | 8504009 | 10384661
MCR001369 | PRJ017 | 2025-07-01 | Subcontract | 216687217 | 88166143 | 101789281
MCR001370 | PRJ017 | 2025-07-01 | Overhead | 31628380 | 12869020 | 21755395
MCR001371 | PRJ017 | 2025-08-01 | Labor | 35471482 | 18529987 | 21493552
MCR001372 | PRJ017 | 2025-08-01 | Material | 110051683 | 57490023 | 59521219
MCR001373 | PRJ017 | 2025-08-01 | Equipment | 20282883 | 10595598 | 10503667
MCR001374 | PRJ017 | 2025-08-01 | Subcontract | 210284757 | 109850891 | 114494473
MCR001375 | PRJ017 | 2025-08-01 | Overhead | 30693855 | 16034198 | 20041709
MCR001376 | PRJ017 | 2025-09-01 | Labor | 33620304 | 27020647 | 24909199
MCR001377 | PRJ017 | 2025-09-01 | Material | 104308332 | 83832634 | 76666573
MCR001378 | PRJ017 | 2025-09-01 | Equipment | 19224365 | 15450627 | 16429996
MCR001379 | PRJ017 | 2025-09-01 | Subcontract | 199310466 | 160185873 | 127949108
MCR001380 | PRJ017 | 2025-09-01 | Overhead | 29092012 | 23381257 | 21188822
MCR001381 | PRJ017 | 2025-10-01 | Labor | 31056759 | 30433319 | 35558351
MCR001382 | PRJ017 | 2025-10-01 | Material | 96354831 | 94420584 | 102562996
MCR001383 | PRJ017 | 2025-10-01 | Equipment | 17758509 | 17402021 | 19960694
MCR001384 | PRJ017 | 2025-10-01 | Subcontract | 184113060 | 180417137 | 216630946
MCR001385 | PRJ017 | 2025-10-01 | Overhead | 26873748 | 26334279 | 21372467
MCR001386 | PRJ017 | 2025-11-01 | Labor | 27848058 | 16193750 | 16526824
MCR001387 | PRJ017 | 2025-11-01 | Material | 86399709 | 50241753 | 51376029
MCR001388 | PRJ017 | 2025-11-01 | Equipment | 15923747 | 9259718 | 9490291
MCR001389 | PRJ017 | 2025-11-01 | Subcontract | 165090994 | 96001029 | 69024073
MCR001390 | PRJ017 | 2025-11-01 | Overhead | 24097225 | 14012626 | 21402707
MCR001391 | PRJ017 | 2025-12-01 | Labor | 24072759 | 29043561 | 33013756
MCR001392 | PRJ017 | 2025-12-01 | Material | 74686692 | 90108804 | 90905486
MCR001393 | PRJ017 | 2025-12-01 | Equipment | 13765000 | 16607346 | 18179683
MCR001394 | PRJ017 | 2025-12-01 | Subcontract | 142709975 | 172178265 | 179166047
MCR001395 | PRJ017 | 2025-12-01 | Overhead | 20830418 | 25131706 | 20307677
MCR001396 | PRJ017 | 2026-01-01 | Labor | 19825548 | 13367932 | 14449535
MCR001397 | PRJ017 | 2026-01-01 | Material | 61509552 | 41474540 | 32489042
MCR001398 | PRJ017 | 2026-01-01 | Equipment | 11336410 | 7643892 | 7918104
MCR001399 | PRJ017 | 2026-01-01 | Subcontract | 117531334 | 79248797 | 89505187
MCR001400 | PRJ017 | 2026-01-01 | Overhead | 17155260 | 11567415 | 20803260
MCR001401 | PRJ017 | 2026-02-01 | Labor | 15225717 | 32612060 | 38631150
MCR001402 | PRJ017 | 2026-02-01 | Material | 47238392 | 101180214 | 99187991
MCR001403 | PRJ017 | 2026-02-01 | Equipment | 8706189 | 18647842 | 19672444
MCR001404 | PRJ017 | 2026-02-01 | Subcontract | 90262262 | 193333314 | 208098686
MCR001405 | PRJ017 | 2026-02-01 | Overhead | 13174977 | 28219567 | 19586996
MCR001406 | PRJ017 | 2026-03-01 | Labor | 10434230 | 19897963 | 22862829
MCR001407 | PRJ017 | 2026-03-01 | Material | 32372613 | 61734222 | 70766284
MCR001408 | PRJ017 | 2026-03-01 | Equipment | 5966378 | 11377818 | 10543559
MCR001409 | PRJ017 | 2026-03-01 | Subcontract | 61857001 | 117960630 | 87533188
MCR001410 | PRJ017 | 2026-03-01 | Overhead | 9028851 | 17217922 | 19451630
MCR001411 | PRJ017 | 2026-04-01 | Labor | 5696358 | 17044491 | 14982488
MCR001412 | PRJ017 | 2026-04-01 | Material | 17673179 | 52881213 | 46924807
MCR001413 | PRJ017 | 2026-04-01 | Equipment | 3257224 | 9746179 | 9909314
MCR001414 | PRJ017 | 2026-04-01 | Subcontract | 33769589 | 101044461 | 123216116
MCR001415 | PRJ017 | 2026-04-01 | Overhead | 4929120 | 14748782 | 20976063
MCR001416 | PRJ017 | 2026-05-01 | Labor | 1520340 | 19891350 | 22314333
MCR001417 | PRJ017 | 2026-05-01 | Material | 4716914 | 61713705 | 70417185
MCR001418 | PRJ017 | 2026-05-01 | Equipment | 869343 | 11374036 | 12283942
MCR001419 | PRJ017 | 2026-05-01 | Subcontract | 9012994 | 117921426 | 122013053
MCR001420 | PRJ017 | 2026-05-01 | Overhead | 1315566 | 17212199 | 21752832
MCR001421 | PRJ017 | 2026-06-01 | Labor | 0 | 15078186 | 16983724
MCR001422 | PRJ017 | 2026-06-01 | Material | 0 | 46780672 | 42782866
MCR001423 | PRJ017 | 2026-06-01 | Equipment | 0 | 8621830 | 9391102
MCR001424 | PRJ017 | 2026-06-01 | Subcontract | 0 | 89387659 | 82594462
MCR001425 | PRJ017 | 2026-06-01 | Overhead | 0 | 13047317 | 21247198
MCR001426 | PRJ017 | 2026-07-01 | Labor | 0 | 11922645 | 12940635
MCR001427 | PRJ017 | 2026-07-01 | Material | 0 | 36990481 | 39117932
MCR001428 | PRJ017 | 2026-07-01 | Equipment | 0 | 6817466 | 7807096
MCR001429 | PRJ017 | 2026-07-01 | Subcontract | 0 | 70680739 | 66223891
MCR001430 | PRJ017 | 2026-07-01 | Overhead | 0 | 10316793 | 19583498
MCR001431 | PRJ017 | 2026-08-01 | Labor | 0 | 6874869 | 8133613
MCR001432 | PRJ017 | 2026-08-01 | Material | 0 | 21329553 | 19312134
MCR001433 | PRJ017 | 2026-08-01 | Equipment | 0 | 3931106 | 4041325
MCR001434 | PRJ017 | 2026-08-01 | Subcontract | 0 | 40756123 | 50811976
MCR001435 | PRJ017 | 2026-08-01 | Overhead | 0 | 5948898 | 19773763
MCR001436 | PRJ018 | 2024-12-01 | Labor | 8767546 | 6599181 | 6673778
MCR001437 | PRJ018 | 2024-12-01 | Material | 29788908 | 22421600 | 22320961
MCR001438 | PRJ018 | 2024-12-01 | Equipment | 16242915 | 12225763 | 12193089
MCR001439 | PRJ018 | 2024-12-01 | Subcontract | 16900785 | 12720931 | 15006754
MCR001440 | PRJ018 | 2024-12-01 | Overhead | 7273204 | 5474416 | 23206570
MCR001441 | PRJ018 | 2025-01-01 | Labor | 23401743 | 25405143 | 30135929
MCR001442 | PRJ018 | 2025-01-01 | Material | 79510548 | 86317368 | 97021475
MCR001443 | PRJ018 | 2025-01-01 | Equipment | 43354495 | 47066031 | 57750475
MCR001444 | PRJ018 | 2025-01-01 | Subcontract | 45110439 | 48972299 | 45080402
MCR001445 | PRJ018 | 2025-01-01 | Overhead | 19413147 | 21075087 | 23823818
MCR001446 | PRJ018 | 2025-02-01 | Labor | 33838786 | 26439396 | 25032858
MCR001447 | PRJ018 | 2025-02-01 | Material | 114971798 | 89831380 | 91005179
MCR001448 | PRJ018 | 2025-02-01 | Equipment | 62690352 | 48982106 | 42467948
MCR001449 | PRJ018 | 2025-02-01 | Subcontract | 65229437 | 50965980 | 56942061
MCR001450 | PRJ018 | 2025-02-01 | Overhead | 28071299 | 21933062 | 24340433
MCR001451 | PRJ018 | 2025-03-01 | Labor | 40302255 | 36183342 | 38559195
MCR001452 | PRJ018 | 2025-03-01 | Material | 136932297 | 122937741 | 94973341
MCR001453 | PRJ018 | 2025-03-01 | Equipment | 74664692 | 67033920 | 72555603
MCR001454 | PRJ018 | 2025-03-01 | Subcontract | 77688762 | 69748928 | 80552596
MCR001455 | PRJ018 | 2025-03-01 | Overhead | 33433134 | 30016249 | 23322101
MCR001456 | PRJ018 | 2025-04-01 | Labor | 43043523 | 31612751 | 31739474
MCR001457 | PRJ018 | 2025-04-01 | Material | 146246120 | 107408546 | 132464094
MCR001458 | PRJ018 | 2025-04-01 | Equipment | 79743215 | 58566359 | 56546758
MCR001459 | PRJ018 | 2025-04-01 | Subcontract | 82972975 | 60938414 | 45719501
MCR001460 | PRJ018 | 2025-04-01 | Overhead | 35707179 | 26224670 | 25477104
MCR001461 | PRJ018 | 2025-05-01 | Labor | 42350843 | 37477833 | 38939927
MCR001462 | PRJ018 | 2025-05-01 | Material | 143892648 | 127335945 | 110190229
MCR001463 | PRJ018 | 2025-05-01 | Equipment | 78459943 | 69432116 | 80487160
MCR001464 | PRJ018 | 2025-05-01 | Subcontract | 81637728 | 72244256 | 75350877
MCR001465 | PRJ018 | 2025-05-01 | Overhead | 35132560 | 31090106 | 21399677
MCR001466 | PRJ018 | 2025-06-01 | Labor | 38563816 | 42544627 | 49593506
MCR001467 | PRJ018 | 2025-06-01 | Material | 131025720 | 144551056 | 167922908
MCR001468 | PRJ018 | 2025-06-01 | Equipment | 71444029 | 78818952 | 71525769
MCR001469 | PRJ018 | 2025-06-01 | Subcontract | 74337656 | 82011277 | 88325954
MCR001470 | PRJ018 | 2025-06-01 | Overhead | 31990995 | 35293316 | 22381462
MCR001471 | PRJ018 | 2025-07-01 | Labor | 32098504 | 25526899 | 25072143
MCR001472 | PRJ018 | 2025-07-01 | Material | 109058959 | 86731050 | 81501031
MCR001473 | PRJ018 | 2025-07-01 | Equipment | 59466275 | 47291598 | 47349285
MCR001474 | PRJ018 | 2025-07-01 | Subcontract | 61874778 | 49207002 | 45781693
MCR001475 | PRJ018 | 2025-07-01 | Overhead | 26627632 | 21176091 | 22666127
MCR001476 | PRJ018 | 2025-08-01 | Labor | 23496914 | 13262861 | 13764813
MCR001477 | PRJ018 | 2025-08-01 | Material | 79833904 | 45062341 | 50159793
MCR001478 | PRJ018 | 2025-08-01 | Equipment | 43530810 | 24571017 | 25847436
MCR001479 | PRJ018 | 2025-08-01 | Subcontract | 45293896 | 25566193 | 40912152
MCR001480 | PRJ018 | 2025-08-01 | Overhead | 19492097 | 11002337 | 23159219
MCR001481 | PRJ018 | 2025-09-01 | Labor | 13547458 | 17065031 | 17568866
MCR001482 | PRJ018 | 2025-09-01 | Material | 46029300 | 57980725 | 54505230
MCR001483 | PRJ018 | 2025-09-01 | Equipment | 25098268 | 31614988 | 35538264
MCR001484 | PRJ018 | 2025-09-01 | Subcontract | 26114798 | 32895459 | 43417930
MCR001485 | PRJ018 | 2025-09-01 | Overhead | 11238428 | 14156465 | 23251936
MCR001486 | PRJ018 | 2025-10-01 | Labor | 3772148 | 26340033 | 30616221
MCR001487 | PRJ018 | 2025-10-01 | Material | 12816375 | 89493781 | 103245045
MCR001488 | PRJ018 | 2025-10-01 | Equipment | 6988349 | 48798025 | 51564978
MCR001489 | PRJ018 | 2025-10-01 | Subcontract | 7271391 | 50774443 | 63476696
MCR001490 | PRJ018 | 2025-10-01 | Overhead | 3129222 | 21850634 | 23942222
MCR001491 | PRJ018 | 2025-11-01 | Labor | 0 | 9626162 | 8774979
MCR001492 | PRJ018 | 2025-11-01 | Material | 0 | 32706172 | 27540336
MCR001493 | PRJ018 | 2025-11-01 | Equipment | 0 | 17833603 | 16402483
MCR001494 | PRJ018 | 2025-11-01 | Subcontract | 0 | 18555900 | 29089498
MCR001495 | PRJ018 | 2025-11-01 | Overhead | 0 | 7985478 | 21993753
MCR001496 | PRJ018 | 2025-12-01 | Labor | 0 | 5100277 | 5979496
MCR001497 | PRJ018 | 2025-12-01 | Material | 0 | 17328873 | 19774116
MCR001498 | PRJ018 | 2025-12-01 | Equipment | 0 | 9448867 | 10656271
MCR001499 | PRJ018 | 2025-12-01 | Subcontract | 0 | 9831565 | 21701795
MCR001500 | PRJ018 | 2025-12-01 | Overhead | 0 | 4230985 | 21511051
MCR001501 | PRJ019 | 2025-04-01 | Labor | 24105813 | 18564937 | 17102564
MCR001502 | PRJ019 | 2025-04-01 | Material | 54112744 | 41674583 | 44019601
MCR001503 | PRJ019 | 2025-04-01 | Equipment | 12948809 | 9972443 | 9460613
MCR001504 | PRJ019 | 2025-04-01 | Subcontract | 60234794 | 46389440 | 45534798
MCR001505 | PRJ019 | 2025-04-01 | Overhead | 16462657 | 12678609 | 51056636
MCR001506 | PRJ019 | 2025-05-01 | Labor | 64341614 | 54929341 | 57144945
MCR001507 | PRJ019 | 2025-05-01 | Material | 144434096 | 123305417 | 123292911
MCR001508 | PRJ019 | 2025-05-01 | Equipment | 34562091 | 29506142 | 33104761
MCR001509 | PRJ019 | 2025-05-01 | Subcontract | 160774658 | 137255586 | 133517595
MCR001510 | PRJ019 | 2025-05-01 | Overhead | 43941015 | 37513062 | 49507296
MCR001511 | PRJ019 | 2025-06-01 | Labor | 93037607 | 88628323 | 89707939
MCR001512 | PRJ019 | 2025-06-01 | Material | 208850876 | 198952914 | 190425117
MCR001513 | PRJ019 | 2025-06-01 | Equipment | 49976585 | 47608071 | 44900606
MCR001514 | PRJ019 | 2025-06-01 | Subcontract | 232479237 | 221461467 | 276592757
MCR001515 | PRJ019 | 2025-06-01 | Overhead | 63538457 | 60527211 | 50759940
MCR001516 | PRJ019 | 2025-07-01 | Labor | 110808506 | 46941709 | 44084499
MCR001517 | PRJ019 | 2025-07-01 | Material | 248743001 | 105374778 | 118203487
MCR001518 | PRJ019 | 2025-07-01 | Equipment | 59522498 | 25215463 | 28621044
MCR001519 | PRJ019 | 2025-07-01 | Subcontract | 276884561 | 117296361 | 84021275
MCR001520 | PRJ019 | 2025-07-01 | Overhead | 75674791 | 32058045 | 53493014
MCR001521 | PRJ019 | 2025-08-01 | Labor | 118345448 | 93607140 | 90961719
MCR001522 | PRJ019 | 2025-08-01 | Material | 265661935 | 210129365 | 203744844
MCR001523 | PRJ019 | 2025-08-01 | Equipment | 63571083 | 50282519 | 54172268
MCR001524 | PRJ019 | 2025-08-01 | Subcontract | 295717619 | 233902368 | 251588386
MCR001525 | PRJ019 | 2025-08-01 | Overhead | 80822018 | 63927410 | 54173732
MCR001526 | PRJ019 | 2025-09-01 | Labor | 116440969 | 130145826 | 117508741
MCR001527 | PRJ019 | 2025-09-01 | Material | 261386758 | 292151430 | 294068402
MCR001528 | PRJ019 | 2025-09-01 | Equipment | 62548062 | 69909838 | 64388151
MCR001529 | PRJ019 | 2025-09-01 | Subcontract | 290958770 | 325204005 | 294641743
MCR001530 | PRJ019 | 2025-09-01 | Overhead | 79521387 | 88880886 | 54021554
MCR001531 | PRJ019 | 2025-10-01 | Labor | 106028779 | 82952986 | 81812598
MCR001532 | PRJ019 | 2025-10-01 | Material | 238013468 | 186212914 | 188202621
MCR001533 | PRJ019 | 2025-10-01 | Equipment | 56954994 | 44559476 | 47449981
MCR001534 | PRJ019 | 2025-10-01 | Subcontract | 264941141 | 207280126 | 220368712
MCR001535 | PRJ019 | 2025-10-01 | Overhead | 72410558 | 56651336 | 53653624
MCR001536 | PRJ019 | 2025-11-01 | Labor | 88252812 | 81673132 | 98617213
MCR001537 | PRJ019 | 2025-11-01 | Material | 198109966 | 183339897 | 199329274
MCR001538 | PRJ019 | 2025-11-01 | Equipment | 47406359 | 43871982 | 45576549
MCR001539 | PRJ019 | 2025-11-01 | Subcontract | 220523153 | 204082070 | 187972376
MCR001540 | PRJ019 | 2025-11-01 | Overhead | 60270762 | 55777281 | 53372893
MCR001541 | PRJ019 | 2025-12-01 | Labor | 64603281 | 86895998 | 84888577
MCR001542 | PRJ019 | 2025-12-01 | Material | 145021484 | 195064189 | 170446964
MCR001543 | PRJ019 | 2025-12-01 | Equipment | 34702649 | 46677525 | 54451319
MCR001544 | PRJ019 | 2025-12-01 | Subcontract | 161428501 | 217132791 | 212494913
MCR001545 | PRJ019 | 2025-12-01 | Overhead | 44119716 | 59344149 | 49082365
MCR001546 | PRJ019 | 2026-01-01 | Labor | 37247881 | 61058680 | 58329142
MCR001547 | PRJ019 | 2026-01-01 | Material | 83614067 | 137064562 | 133677721
MCR001548 | PRJ019 | 2026-01-01 | Equipment | 20008274 | 32798612 | 28650834
MCR001549 | PRJ019 | 2026-01-01 | Subcontract | 93073751 | 152571372 | 171141005
MCR001550 | PRJ019 | 2026-01-01 | Overhead | 25437809 | 41698991 | 48872893
MCR001551 | PRJ019 | 2026-02-01 | Labor | 10371281 | 56898604 | 64642797
MCR001552 | PRJ019 | 2026-02-01 | Material | 23281459 | 127726021 | 157828613
MCR001553 | PRJ019 | 2026-02-01 | Equipment | 5571094 | 30563963 | 30968172
MCR001554 | PRJ019 | 2026-02-01 | Subcontract | 25915409 | 142176315 | 124366108
MCR001555 | PRJ019 | 2026-02-01 | Overhead | 7082891 | 38857937 | 48400757
MCR001556 | PRJ019 | 2026-03-01 | Labor | 0 | 24165751 | 22610281
MCR001557 | PRJ019 | 2026-03-01 | Material | 0 | 54247292 | 45458840
MCR001558 | PRJ019 | 2026-03-01 | Equipment | 0 | 12981006 | 13824139
MCR001559 | PRJ019 | 2026-03-01 | Subcontract | 0 | 60384564 | 53811031
MCR001560 | PRJ019 | 2026-03-01 | Overhead | 0 | 16503590 | 50239519
MCR001561 | PRJ019 | 2026-04-01 | Labor | 0 | 7121565 | 7198383
MCR001562 | PRJ019 | 2026-04-01 | Material | 0 | 15986494 | 12207844
MCR001563 | PRJ019 | 2026-04-01 | Equipment | 0 | 3825459 | 3334925
MCR001564 | PRJ019 | 2026-04-01 | Subcontract | 0 | 17795127 | 26349744
MCR001565 | PRJ019 | 2026-04-01 | Overhead | 0 | 4863552 | 51305351
MCR001566 | PRJ020 | 2025-02-01 | Labor | 15412057 | 10026150 | 10025683
MCR001567 | PRJ020 | 2025-02-01 | Material | 36911457 | 24012356 | 28053673
MCR001568 | PRJ020 | 2025-02-01 | Equipment | 11282550 | 7339743 | 7357701
MCR001569 | PRJ020 | 2025-02-01 | Subcontract | 48845312 | 31775798 | 31669427
MCR001570 | PRJ020 | 2025-02-01 | Overhead | 10688509 | 6953296 | 30747521
MCR001571 | PRJ020 | 2025-03-01 | Labor | 40599226 | 24114160 | 22672253
MCR001572 | PRJ020 | 2025-03-01 | Material | 97234044 | 57752758 | 64579485
MCR001573 | PRJ020 | 2025-03-01 | Equipment | 29721069 | 17653012 | 17984132
MCR001574 | PRJ020 | 2025-03-01 | Subcontract | 128670815 | 76424821 | 75465314
MCR001575 | PRJ020 | 2025-03-01 | Overhead | 28156215 | 16723557 | 30451187
MCR001576 | PRJ020 | 2025-04-01 | Labor | 57665825 | 34765706 | 36836213
MCR001577 | PRJ020 | 2025-04-01 | Material | 138108083 | 83262922 | 79297272
MCR001578 | PRJ020 | 2025-04-01 | Equipment | 42214844 | 25450583 | 22690661
MCR001579 | PRJ020 | 2025-04-01 | Subcontract | 182759854 | 110182684 | 102838073
MCR001580 | PRJ020 | 2025-04-01 | Overhead | 39992175 | 24110575 | 28592650
MCR001581 | PRJ020 | 2025-05-01 | Labor | 67102618 | 51843591 | 54025893
MCR001582 | PRJ020 | 2025-05-01 | Material | 160708948 | 124163991 | 121079553
MCR001583 | PRJ020 | 2025-05-01 | Equipment | 49123143 | 37952619 | 40504872
MCR001584 | PRJ020 | 2025-05-01 | Subcontract | 212667812 | 164307492 | 152739974
MCR001585 | PRJ020 | 2025-05-01 | Overhead | 46536743 | 35954362 | 30264137
MCR001586 | PRJ020 | 2025-06-01 | Labor | 69470839 | 31200854 | 32294213
MCR001587 | PRJ020 | 2025-06-01 | Material | 166380771 | 74725199 | 71504251
MCR001588 | PRJ020 | 2025-06-01 | Equipment | 50856822 | 22840897 | 25958658
MCR001589 | PRJ020 | 2025-06-01 | Subcontract | 220173393 | 98884628 | 100377577
MCR001590 | PRJ020 | 2025-06-01 | Overhead | 48179142 | 21638293 | 30413080
MCR001591 | PRJ020 | 2025-07-01 | Labor | 65429475 | 31974198 | 32260880
MCR001592 | PRJ020 | 2025-07-01 | Material | 156701814 | 76577334 | 89435328
MCR001593 | PRJ020 | 2025-07-01 | Equipment | 47898301 | 23407031 | 26926820
MCR001594 | PRJ020 | 2025-07-01 | Subcontract | 207365130 | 101335578 | 109798200
MCR001595 | PRJ020 | 2025-07-01 | Overhead | 45376391 | 22174619 | 28034940
MCR001596 | PRJ020 | 2025-08-01 | Labor | 55782481 | 33257599 | 37954173
MCR001597 | PRJ020 | 2025-08-01 | Material | 133597527 | 79651047 | 70296414
MCR001598 | PRJ020 | 2025-08-01 | Equipment | 40836123 | 24346558 | 25681196
MCR001599 | PRJ020 | 2025-08-01 | Subcontract | 176790988 | 105403054 | 107090348
MCR001600 | PRJ020 | 2025-08-01 | Overhead | 38686046 | 23064679 | 32595650
MCR001601 | PRJ020 | 2025-09-01 | Labor | 41571413 | 59747426 | 68805358
MCR001602 | PRJ020 | 2025-09-01 | Material | 99562404 | 143093462 | 153256306
MCR001603 | PRJ020 | 2025-09-01 | Equipment | 30432768 | 43738700 | 45541587
MCR001604 | PRJ020 | 2025-09-01 | Subcontract | 131751958 | 189357056 | 168479760
MCR001605 | PRJ020 | 2025-09-01 | Overhead | 28830442 | 41435799 | 29302187
MCR001606 | PRJ020 | 2025-10-01 | Labor | 24299804 | 42050722 | 41331801
MCR001607 | PRJ020 | 2025-10-01 | Material | 58197369 | 100710338 | 89449813
MCR001608 | PRJ020 | 2025-10-01 | Equipment | 17788914 | 30783652 | 30920664
MCR001609 | PRJ020 | 2025-10-01 | Subcontract | 77013180 | 133271030 | 173206585
MCR001610 | PRJ020 | 2025-10-01 | Overhead | 16852304 | 29162851 | 24764927
MCR001611 | PRJ020 | 2025-11-01 | Labor | 6834166 | 32857106 | 39577932
MCR001612 | PRJ020 | 2025-11-01 | Material | 16367643 | 78691876 | 96365826
MCR001613 | PRJ020 | 2025-11-01 | Equipment | 5003020 | 24053373 | 23433551
MCR001614 | PRJ020 | 2025-11-01 | Subcontract | 21659471 | 104133773 | 71285154
MCR001615 | PRJ020 | 2025-11-01 | Overhead | 4739604 | 22786930 | 29054527
MCR001616 | PRJ020 | 2025-12-01 | Labor | 0 | 56103321 | 66238171
MCR001617 | PRJ020 | 2025-12-01 | Material | 0 | 134365930 | 123875162
MCR001618 | PRJ020 | 2025-12-01 | Equipment | 0 | 41070997 | 40831344
MCR001619 | PRJ020 | 2025-12-01 | Subcontract | 0 | 177807824 | 197663533
MCR001620 | PRJ020 | 2025-12-01 | Overhead | 0 | 38908554 | 31108292
MCR001621 | PRJ020 | 2026-01-01 | Labor | 0 | 22493121 | 23668156
MCR001622 | PRJ020 | 2026-01-01 | Material | 0 | 53870413 | 56778323
MCR001623 | PRJ020 | 2026-01-01 | Equipment | 0 | 16466314 | 21694329
MCR001624 | PRJ020 | 2026-01-01 | Subcontract | 0 | 71287275 | 69890627
MCR001625 | PRJ020 | 2026-01-01 | Overhead | 0 | 15599340 | 31280926
MCR001626 | PRJ020 | 2026-02-01 | Labor | 0 | 8865545 | 10680180
MCR001627 | PRJ020 | 2026-02-01 | Material | 0 | 21232740 | 22541184
MCR001628 | PRJ020 | 2026-02-01 | Equipment | 0 | 6490111 | 7090967
MCR001629 | PRJ020 | 2026-02-01 | Subcontract | 0 | 28097504 | 27042101
MCR001630 | PRJ020 | 2026-02-01 | Overhead | 0 | 6148398 | 33606121
MCR001631 | PRJ020 | 2026-03-01 | Labor | 0 | 4868404 | 4880421
MCR001632 | PRJ020 | 2026-03-01 | Material | 0 | 11659695 | 12024697
MCR001633 | PRJ020 | 2026-03-01 | Equipment | 0 | 3563964 | 4223645
MCR001634 | PRJ020 | 2026-03-01 | Subcontract | 0 | 15429395 | 15365818
MCR001635 | PRJ020 | 2026-03-01 | Overhead | 0 | 3376316 | 30396075
MCR001636 | PRJ021 | 2025-05-01 | Labor | 21606557 | 18259971 | 21546658
MCR001637 | PRJ021 | 2025-05-01 | Material | 71775399 | 60658285 | 64000575
MCR001638 | PRJ021 | 2025-05-01 | Equipment | 25094587 | 21207748 | 21613740
MCR001639 | PRJ021 | 2025-05-01 | Subcontract | 59117528 | 49960961 | 56303021
MCR001640 | PRJ021 | 2025-05-01 | Overhead | 19180829 | 16209958 | 53625162
MCR001641 | PRJ021 | 2025-06-01 | Labor | 56917096 | 34504165 | 34610727
MCR001642 | PRJ021 | 2025-06-01 | Material | 189074420 | 114620306 | 110878340
MCR001643 | PRJ021 | 2025-06-01 | Equipment | 66105441 | 40074304 | 37789479
MCR001644 | PRJ021 | 2025-06-01 | Subcontract | 155730410 | 94406569 | 111071835
MCR001645 | PRJ021 | 2025-06-01 | Overhead | 50527119 | 30630446 | 58482306
MCR001646 | PRJ021 | 2025-07-01 | Labor | 80843198 | 40320891 | 43348412
MCR001647 | PRJ021 | 2025-07-01 | Material | 268555178 | 133943044 | 135991489
MCR001648 | PRJ021 | 2025-07-01 | Equipment | 93894025 | 46830047 | 55983289
MCR001649 | PRJ021 | 2025-07-01 | Subcontract | 221194426 | 110321667 | 108610029
MCR001650 | PRJ021 | 2025-07-01 | Overhead | 71767081 | 35794139 | 58094151
MCR001651 | PRJ021 | 2025-08-01 | Labor | 94072881 | 31315911 | 32354591
MCR001652 | PRJ021 | 2025-08-01 | Material | 312503215 | 104029162 | 115636439
MCR001653 | PRJ021 | 2025-08-01 | Equipment | 109259427 | 36371359 | 37347401
MCR001654 | PRJ021 | 2025-08-01 | Subcontract | 257392057 | 85683214 | 107229312
MCR001655 | PRJ021 | 2025-08-01 | Overhead | 83511493 | 27800132 | 55778509
MCR001656 | PRJ021 | 2025-09-01 | Labor | 97392949 | 47691711 | 50556832
MCR001657 | PRJ021 | 2025-09-01 | Material | 323532239 | 158428369 | 147448191
MCR001658 | PRJ021 | 2025-09-01 | Equipment | 113115467 | 55390767 | 58704731
MCR001659 | PRJ021 | 2025-09-01 | Subcontract | 266476069 | 130488909 | 165988028
MCR001660 | PRJ021 | 2025-09-01 | Overhead | 86458823 | 42337451 | 52996632
MCR001661 | PRJ021 | 2025-10-01 | Labor | 91727258 | 119321457 | 123349691
MCR001662 | PRJ021 | 2025-10-01 | Material | 304711226 | 396377134 | 368719955
MCR001663 | PRJ021 | 2025-10-01 | Equipment | 106535140 | 138583977 | 138974181
MCR001664 | PRJ021 | 2025-10-01 | Subcontract | 250974215 | 326474483 | 370876230
MCR001665 | PRJ021 | 2025-10-01 | Overhead | 81429208 | 105925458 | 59405194
MCR001666 | PRJ021 | 2025-11-01 | Labor | 78202890 | 69357968 | 70761187
MCR001667 | PRJ021 | 2025-11-01 | Material | 259784269 | 230402085 | 252427316
MCR001668 | PRJ021 | 2025-11-01 | Equipment | 90827483 | 80554690 | 88014067
MCR001669 | PRJ021 | 2025-11-01 | Subcontract | 213970302 | 189769781 | 200621233
MCR001670 | PRJ021 | 2025-11-01 | Overhead | 69423196 | 61571277 | 51722445
MCR001671 | PRJ021 | 2025-12-01 | Labor | 58280029 | 66190154 | 71184148
MCR001672 | PRJ021 | 2025-12-01 | Material | 193601985 | 219878841 | 229391075
MCR001673 | PRJ021 | 2025-12-01 | Equipment | 67688398 | 76875485 | 89252938
MCR001674 | PRJ021 | 2025-12-01 | Subcontract | 159459521 | 181102351 | 228489620
MCR001675 | PRJ021 | 2025-12-01 | Overhead | 51737038 | 58759108 | 57420183
MCR001676 | PRJ021 | 2026-01-01 | Labor | 34066518 | 37901064 | 34691924
MCR001677 | PRJ021 | 2026-01-01 | Material | 113166474 | 125904555 | 112265478
MCR001678 | PRJ021 | 2026-01-01 | Equipment | 39566006 | 44019578 | 38234671
MCR001679 | PRJ021 | 2026-01-01 | Subcontract | 93209126 | 103700797 | 97631119
MCR001680 | PRJ021 | 2026-01-01 | Overhead | 30241933 | 33645981 | 55337124
MCR001681 | PRJ021 | 2026-02-01 | Labor | 9580993 | 58990928 | 63668734
MCR001682 | PRJ021 | 2026-02-01 | Material | 31827357 | 195963539 | 225610934
MCR001683 | PRJ021 | 2026-02-01 | Equipment | 11127689 | 68514060 | 76605467
MCR001684 | PRJ021 | 2026-02-01 | Subcontract | 26214478 | 161404606 | 225561550
MCR001685 | PRJ021 | 2026-02-01 | Overhead | 8505353 | 52368126 | 57193672
MCR001686 | PRJ021 | 2026-03-01 | Labor | 0 | 49878127 | 49862348
MCR001687 | PRJ021 | 2026-03-01 | Material | 0 | 165691480 | 162705458
MCR001688 | PRJ021 | 2026-03-01 | Equipment | 0 | 57930144 | 59718187
MCR001689 | PRJ021 | 2026-03-01 | Subcontract | 0 | 136471143 | 166737467
MCR001690 | PRJ021 | 2026-03-01 | Overhead | 0 | 44278401 | 54426731
MCR001691 | PRJ021 | 2026-04-01 | Labor | 0 | 27554896 | 32367923
MCR001692 | PRJ021 | 2026-04-01 | Material | 0 | 91535345 | 86300481
MCR001693 | PRJ021 | 2026-04-01 | Equipment | 0 | 32003188 | 32306369
MCR001694 | PRJ021 | 2026-04-01 | Subcontract | 0 | 75392730 | 110691864
MCR001695 | PRJ021 | 2026-04-01 | Overhead | 0 | 24461359 | 54020938
MCR001696 | PRJ021 | 2026-05-01 | Labor | 0 | 16258985 | 18521914
MCR001697 | PRJ021 | 2026-05-01 | Material | 0 | 54011156 | 60982630
MCR001698 | PRJ021 | 2026-05-01 | Equipment | 0 | 18883735 | 23592451
MCR001699 | PRJ021 | 2026-05-01 | Subcontract | 0 | 44486078 | 62960026
MCR001700 | PRJ021 | 2026-05-01 | Overhead | 0 | 14433619 | 58472083
MCR001701 | PRJ021 | 2026-06-01 | Labor | 0 | 5144141 | 3540517
MCR001702 | PRJ021 | 2026-06-01 | Material | 0 | 17088461 | 14425863
MCR001703 | PRJ021 | 2026-06-01 | Equipment | 0 | 5974580 | 8996604
MCR001704 | PRJ021 | 2026-06-01 | Subcontract | 0 | 14074844 | 75274260
MCR001705 | PRJ021 | 2026-06-01 | Overhead | 0 | 4566618 | 52174455
MCR001706 | PRJ022 | 2024-11-01 | Labor | 5603723 | 4924832 | 5547502
MCR001707 | PRJ022 | 2024-11-01 | Material | 14197890 | 12477816 | 12709040
MCR001708 | PRJ022 | 2024-11-01 | Equipment | 2783074 | 2445905 | 2761578
MCR001709 | PRJ022 | 2024-11-01 | Subcontract | 18253530 | 16042115 | 16588400
MCR001710 | PRJ022 | 2024-11-01 | Overhead | 3729425 | 3277605 | 15147917
MCR001711 | PRJ022 | 2024-12-01 | Labor | 15555861 | 16488796 | 17354180
MCR001712 | PRJ022 | 2024-12-01 | Material | 39413153 | 41776887 | 43046033
MCR001713 | PRJ022 | 2024-12-01 | Equipment | 7725777 | 8189117 | 7608279
MCR001714 | PRJ022 | 2024-12-01 | Subcontract | 50671555 | 53710492 | 54449221
MCR001715 | PRJ022 | 2024-12-01 | Overhead | 10352834 | 10973727 | 17514787
MCR001716 | PRJ022 | 2025-01-01 | Labor | 23668769 | 42384007 | 52392572
MCR001717 | PRJ022 | 2025-01-01 | Material | 59968448 | 107386368 | 113702062
MCR001718 | PRJ022 | 2025-01-01 | Equipment | 11755032 | 21049906 | 24076779
MCR001719 | PRJ022 | 2025-01-01 | Subcontract | 77098488 | 138061379 | 131861267
MCR001720 | PRJ022 | 2025-01-01 | Overhead | 15752188 | 28207672 | 16074060
MCR001721 | PRJ022 | 2025-02-01 | Labor | 30003975 | 47610901 | 49320742
MCR001722 | PRJ022 | 2025-02-01 | Material | 76019663 | 120629503 | 123392989
MCR001723 | PRJ022 | 2025-02-01 | Equipment | 14901396 | 23645829 | 24715046
MCR001724 | PRJ022 | 2025-02-01 | Subcontract | 97734746 | 155087426 | 170225466
MCR001725 | PRJ022 | 2025-02-01 | Overhead | 19968435 | 31686307 | 16483431
MCR001726 | PRJ022 | 2025-03-01 | Labor | 34627590 | 36705115 | 42625167
MCR001727 | PRJ022 | 2025-03-01 | Material | 87734298 | 92998026 | 103341411
MCR001728 | PRJ022 | 2025-03-01 | Equipment | 17197702 | 18229499 | 17684245
MCR001729 | PRJ022 | 2025-03-01 | Subcontract | 112795677 | 119562993 | 116123803
MCR001730 | PRJ022 | 2025-03-01 | Overhead | 23045572 | 24428219 | 16073976
MCR001731 | PRJ022 | 2025-04-01 | Labor | 37611153 | 20980976 | 19728299
MCR001732 | PRJ022 | 2025-04-01 | Material | 95293611 | 53158513 | 44000485
MCR001733 | PRJ022 | 2025-04-01 | Equipment | 18679481 | 10420147 | 11960240
MCR001734 | PRJ022 | 2025-04-01 | Subcontract | 122514314 | 68343288 | 85167073
MCR001735 | PRJ022 | 2025-04-01 | Overhead | 25031211 | 13963391 | 16845159
MCR001736 | PRJ022 | 2025-05-01 | Labor | 39032735 | 34777217 | 42612151
MCR001737 | PRJ022 | 2025-05-01 | Material | 98895408 | 88113402 | 93129091
MCR001738 | PRJ022 | 2025-05-01 | Equipment | 19385506 | 17272014 | 18931339
MCR001739 | PRJ022 | 2025-05-01 | Subcontract | 127144969 | 113283073 | 106467657
MCR001740 | PRJ022 | 2025-05-01 | Overhead | 25977312 | 23145153 | 18090291
MCR001741 | PRJ022 | 2025-06-01 | Labor | 38978424 | 45406321 | 47298011
MCR001742 | PRJ022 | 2025-06-01 | Material | 98757803 | 115043864 | 118553741
MCR001743 | PRJ022 | 2025-06-01 | Equipment | 19358532 | 22550931 | 23642117
MCR001744 | PRJ022 | 2025-06-01 | Subcontract | 126968056 | 147906244 | 143137588
MCR001745 | PRJ022 | 2025-06-01 | Overhead | 25941167 | 30219101 | 18508398
MCR001746 | PRJ022 | 2025-07-01 | Labor | 37544371 | 40594413 | 44325236
MCR001747 | PRJ022 | 2025-07-01 | Material | 95124409 | 102852156 | 122254144
MCR001748 | PRJ022 | 2025-07-01 | Equipment | 18646314 | 20161109 | 20118400
MCR001749 | PRJ022 | 2025-07-01 | Subcontract | 122296780 | 132231965 | 124596303
MCR001750 | PRJ022 | 2025-07-01 | Overhead | 24986766 | 27016649 | 16418602
MCR001751 | PRJ022 | 2025-08-01 | Labor | 34839746 | 20664654 | 23365236
MCR001752 | PRJ022 | 2025-08-01 | Material | 88271828 | 52357064 | 40182837
MCR001753 | PRJ022 | 2025-08-01 | Equipment | 17303069 | 10263046 | 12585152
MCR001754 | PRJ022 | 2025-08-01 | Subcontract | 113486753 | 67312905 | 88470187
MCR001755 | PRJ022 | 2025-08-01 | Overhead | 23186767 | 13752871 | 17380409
MCR001756 | PRJ022 | 2025-09-01 | Labor | 30991202 | 26298065 | 47702881
MCR001757 | PRJ022 | 2025-09-01 | Material | 78520952 | 66630173 | 89499706
MCR001758 | PRJ022 | 2025-09-01 | Equipment | 15391699 | 13060865 | 14876223
MCR001759 | PRJ022 | 2025-09-01 | Subcontract | 100950531 | 85663140 | 87183181
MCR001760 | PRJ022 | 2025-09-01 | Overhead | 20625460 | 17502054 | 17764307
MCR001761 | PRJ022 | 2025-10-01 | Labor | 26150063 | 20113576 | 40374314
MCR001762 | PRJ022 | 2025-10-01 | Material | 66255187 | 50960822 | 67188165
MCR001763 | PRJ022 | 2025-10-01 | Equipment | 12987361 | 9989355 | 9054363
MCR001764 | PRJ022 | 2025-10-01 | Subcontract | 85181040 | 65517825 | 62623650
MCR001765 | PRJ022 | 2025-10-01 | Overhead | 17403555 | 13386114 | 15601040
MCR001766 | PRJ022 | 2025-11-01 | Labor | 20504973 | 16176119 | 17987596
MCR001767 | PRJ022 | 2025-11-01 | Material | 51952488 | 40984672 | 41826280
MCR001768 | PRJ022 | 2025-11-01 | Equipment | 10183741 | 8033827 | 8591571
MCR001769 | PRJ022 | 2025-11-01 | Subcontract | 66792761 | 52691980 | 63015916
MCR001770 | PRJ022 | 2025-11-01 | Overhead | 13646599 | 10765632 | 16579880
MCR001771 | PRJ022 | 2025-12-01 | Labor | 14307175 | 13767191 | 16498940
MCR001772 | PRJ022 | 2025-12-01 | Material | 36249416 | 34881284 | 38187729
MCR001773 | PRJ022 | 2025-12-01 | Equipment | 7105621 | 6837439 | 6498084
MCR001774 | PRJ022 | 2025-12-01 | Subcontract | 46604094 | 44845154 | 42487186
MCR001775 | PRJ022 | 2025-12-01 | Overhead | 9521801 | 9162427 | 15280440
MCR001776 | PRJ022 | 2026-01-01 | Labor | 7933129 | 9889829 | 11429357
MCR001777 | PRJ022 | 2026-01-01 | Material | 20099796 | 25057395 | 24976061
MCR001778 | PRJ022 | 2026-01-01 | Equipment | 3939968 | 4911758 | 5093151
MCR001779 | PRJ022 | 2026-01-01 | Subcontract | 25841320 | 32215062 | 31249806
MCR001780 | PRJ022 | 2026-01-01 | Overhead | 5279706 | 6581941 | 16297496
MCR001781 | PRJ022 | 2026-02-01 | Labor | 2143921 | 2714799 | 3219356
MCR001782 | PRJ022 | 2026-02-01 | Material | 5431952 | 6878358 | 6090340
MCR001783 | PRJ022 | 2026-02-01 | Equipment | 1064773 | 1348298 | 1558615
MCR001784 | PRJ022 | 2026-02-01 | Subcontract | 6983593 | 8843167 | 8868926
MCR001785 | PRJ022 | 2026-02-01 | Overhead | 1426836 | 1806770 | 17368318
MCR001786 | PRJ023 | 2024-10-01 | Labor | 3067287 | 2718820 | 2642188
MCR001787 | PRJ023 | 2024-10-01 | Material | 6824509 | 6049192 | 6395349
MCR001788 | PRJ023 | 2024-10-01 | Equipment | 1426198 | 1264171 | 1226252
MCR001789 | PRJ023 | 2024-10-01 | Subcontract | 5217038 | 4624342 | 3990647
MCR001790 | PRJ023 | 2024-10-01 | Overhead | 1801040 | 1596428 | 10502643
MCR001791 | PRJ023 | 2024-11-01 | Labor | 8706693 | 4086563 | 4453926
MCR001792 | PRJ023 | 2024-11-01 | Material | 19371808 | 9092329 | 7640855
MCR001793 | PRJ023 | 2024-11-01 | Equipment | 4048354 | 1900131 | 1963704
MCR001794 | PRJ023 | 2024-11-01 | Subcontract | 14808899 | 6950688 | 7651784
MCR001795 | PRJ023 | 2024-11-01 | Overhead | 5112369 | 2399536 | 11539158
MCR001796 | PRJ023 | 2024-12-01 | Labor | 13615552 | 6689069 | 7079073
MCR001797 | PRJ023 | 2024-12-01 | Material | 30293690 | 14882730 | 15321552
MCR001798 | PRJ023 | 2024-12-01 | Equipment | 6330829 | 3110219 | 3561753
MCR001799 | PRJ023 | 2024-12-01 | Subcontract | 23158200 | 11377196 | 10094372
MCR001800 | PRJ023 | 2024-12-01 | Overhead | 7994738 | 3927667 | 11733001
MCR001801 | PRJ023 | 2025-01-01 | Labor | 17810763 | 10615924 | 9821471
MCR001802 | PRJ023 | 2025-01-01 | Material | 39627755 | 23619720 | 27300316
MCR001803 | PRJ023 | 2025-01-01 | Equipment | 8281478 | 4936091 | 5036838
MCR001804 | PRJ023 | 2025-01-01 | Subcontract | 30293684 | 18056242 | 17077478
MCR001805 | PRJ023 | 2025-01-01 | Overhead | 10458070 | 6233426 | 11151202
MCR001806 | PRJ023 | 2025-02-01 | Labor | 21310076 | 15144418 | 15626752
MCR001807 | PRJ023 | 2025-02-01 | Material | 47413492 | 33695317 | 31216264
MCR001808 | PRJ023 | 2025-02-01 | Equipment | 9908555 | 7041707 | 7135480
MCR001809 | PRJ023 | 2025-02-01 | Subcontract | 36245540 | 25758595 | 28080803
MCR001810 | PRJ023 | 2025-02-01 | Overhead | 12512786 | 8892454 | 11795506
MCR001811 | PRJ023 | 2025-03-01 | Labor | 24132195 | 17012607 | 18539167
MCR001812 | PRJ023 | 2025-03-01 | Material | 53692517 | 37851911 | 36643092
MCR001813 | PRJ023 | 2025-03-01 | Equipment | 11220757 | 7910359 | 8446885
MCR001814 | PRJ023 | 2025-03-01 | Subcontract | 41045580 | 28936129 | 28889302
MCR001815 | PRJ023 | 2025-03-01 | Overhead | 14169869 | 9989411 | 11633125
MCR001816 | PRJ023 | 2025-04-01 | Labor | 26296899 | 20305534 | 23221589
MCR001817 | PRJ023 | 2025-04-01 | Material | 58508839 | 45178454 | 44790990
MCR001818 | PRJ023 | 2025-04-01 | Equipment | 12227280 | 9441473 | 9536556
MCR001819 | PRJ023 | 2025-04-01 | Subcontract | 44727447 | 34536951 | 35262795
MCR001820 | PRJ023 | 2025-04-01 | Overhead | 15440934 | 11922942 | 11551893
MCR001821 | PRJ023 | 2025-05-01 | Labor | 27825196 | 13103298 | 12425644
MCR001822 | PRJ023 | 2025-05-01 | Material | 61909196 | 29153960 | 32938172
MCR001823 | PRJ023 | 2025-05-01 | Equipment | 12937893 | 6092646 | 7214673
MCR001824 | PRJ023 | 2025-05-01 | Subcontract | 47326871 | 22286926 | 22286768
MCR001825 | PRJ023 | 2025-05-01 | Overhead | 16338314 | 7693955 | 10886624
MCR001826 | PRJ023 | 2025-06-01 | Labor | 28739499 | 22055153 | 22625160
MCR001827 | PRJ023 | 2025-06-01 | Material | 63943460 | 49071237 | 41861587
MCR001828 | PRJ023 | 2025-06-01 | Equipment | 13363017 | 10254993 | 10053230
MCR001829 | PRJ023 | 2025-06-01 | Subcontract | 48881976 | 37512813 | 38541511
MCR001830 | PRJ023 | 2025-06-01 | Overhead | 16875172 | 12950278 | 10204633
MCR001831 | PRJ023 | 2025-07-01 | Labor | 29063858 | 19557345 | 19564948
MCR001832 | PRJ023 | 2025-07-01 | Material | 64665137 | 43513782 | 49852250
MCR001833 | PRJ023 | 2025-07-01 | Equipment | 13513834 | 9093587 | 10721354
MCR001834 | PRJ023 | 2025-07-01 | Subcontract | 49433667 | 33264382 | 35377526
MCR001835 | PRJ023 | 2025-07-01 | Overhead | 17065628 | 11483622 | 11037802
MCR001836 | PRJ023 | 2025-08-01 | Labor | 28824243 | 13614816 | 14806329
MCR001837 | PRJ023 | 2025-08-01 | Material | 64132009 | 30292053 | 23355094
MCR001838 | PRJ023 | 2025-08-01 | Equipment | 13402420 | 6330486 | 5725366
MCR001839 | PRJ023 | 2025-08-01 | Subcontract | 49026114 | 23156949 | 20209696
MCR001840 | PRJ023 | 2025-08-01 | Overhead | 16924932 | 7994306 | 10971313
MCR001841 | PRJ023 | 2025-09-01 | Labor | 28048911 | 36816973 | 36922022
MCR001842 | PRJ023 | 2025-09-01 | Material | 62406948 | 81915298 | 88701275
MCR001843 | PRJ023 | 2025-09-01 | Equipment | 13041914 | 17118803 | 15537011
MCR001844 | PRJ023 | 2025-09-01 | Subcontract | 47707381 | 62620660 | 62850456
MCR001845 | PRJ023 | 2025-09-01 | Overhead | 16469675 | 21618079 | 12057702
MCR001846 | PRJ023 | 2025-10-01 | Labor | 26768893 | 21447748 | 22943271
MCR001847 | PRJ023 | 2025-10-01 | Material | 59558994 | 47719802 | 50533022
MCR001848 | PRJ023 | 2025-10-01 | Equipment | 12446743 | 9972568 | 11650230
MCR001849 | PRJ023 | 2025-10-01 | Subcontract | 45530244 | 36479700 | 31592075
MCR001850 | PRJ023 | 2025-10-01 | Overhead | 15718078 | 12593624 | 10675304
MCR001851 | PRJ023 | 2025-11-01 | Labor | 25018644 | 23741700 | 25152630
MCR001852 | PRJ023 | 2025-11-01 | Material | 55664808 | 52823693 | 58246174
MCR001853 | PRJ023 | 2025-11-01 | Equipment | 11632929 | 11039188 | 11663945
MCR001854 | PRJ023 | 2025-11-01 | Subcontract | 42553309 | 40381401 | 44115116
MCR001855 | PRJ023 | 2025-11-01 | Overhead | 14690372 | 13940580 | 11439803
MCR001856 | PRJ023 | 2025-12-01 | Labor | 22836957 | 36555595 | 37090930
MCR001857 | PRJ023 | 2025-12-01 | Material | 50810700 | 81333750 | 89752392
MCR001858 | PRJ023 | 2025-12-01 | Equipment | 10618509 | 16997270 | 16626192
MCR001859 | PRJ023 | 2025-12-01 | Subcontract | 38842556 | 62176092 | 61107931
MCR001860 | PRJ023 | 2025-12-01 | Overhead | 13409335 | 21464604 | 10956195
MCR001861 | PRJ023 | 2026-01-01 | Labor | 20268281 | 23660992 | 27017496
MCR001862 | PRJ023 | 2026-01-01 | Material | 45095568 | 52644122 | 50440018
MCR001863 | PRJ023 | 2026-01-01 | Equipment | 9424151 | 11001661 | 9467273
MCR001864 | PRJ023 | 2026-01-01 | Subcontract | 34473588 | 40244127 | 37734470
MCR001865 | PRJ023 | 2026-01-01 | Overhead | 11901068 | 13893190 | 10913030
MCR001866 | PRJ023 | 2026-02-01 | Labor | 17364737 | 20554752 | 22679094
MCR001867 | PRJ023 | 2026-02-01 | Material | 38635376 | 45732947 | 47246536
MCR001868 | PRJ023 | 2026-02-01 | Equipment | 8074089 | 9557352 | 11634811
MCR001869 | PRJ023 | 2026-02-01 | Subcontract | 29535054 | 34960837 | 40458813
MCR001870 | PRJ023 | 2026-02-01 | Overhead | 10196174 | 12069277 | 10131792
MCR001871 | PRJ023 | 2026-03-01 | Labor | 14189383 | 27713670 | 32907626
MCR001872 | PRJ023 | 2026-03-01 | Material | 31570427 | 61661060 | 62524453
MCR001873 | PRJ023 | 2026-03-01 | Equipment | 6597643 | 12886037 | 13868102
MCR001874 | PRJ023 | 2026-03-01 | Subcontract | 24134210 | 47137182 | 49282306
MCR001875 | PRJ023 | 2026-03-01 | Overhead | 8331679 | 16272829 | 10446064
MCR001876 | PRJ023 | 2026-04-01 | Labor | 10822023 | 21523207 | 17440592
MCR001877 | PRJ023 | 2026-04-01 | Material | 24078276 | 47887693 | 40945477
MCR001878 | PRJ023 | 2026-04-01 | Equipment | 5031921 | 10007654 | 10892138
MCR001879 | PRJ023 | 2026-04-01 | Subcontract | 18406789 | 36608046 | 36134746
MCR001880 | PRJ023 | 2026-04-01 | Overhead | 6354443 | 12637931 | 10764629
MCR001881 | PRJ023 | 2026-05-01 | Labor | 7370925 | 15652949 | 19788381
MCR001882 | PRJ023 | 2026-05-01 | Material | 16399814 | 34826763 | 42974139
MCR001883 | PRJ023 | 2026-05-01 | Equipment | 3427262 | 7278158 | 6722485
MCR001884 | PRJ023 | 2026-05-01 | Subcontract | 12536940 | 26623536 | 23362764
MCR001885 | PRJ023 | 2026-05-01 | Overhead | 4328037 | 9191051 | 10680734
MCR001886 | PRJ023 | 2026-06-01 | Labor | 4002199 | 10981416 | 11300481
MCR001887 | PRJ023 | 2026-06-01 | Material | 8904625 | 24432914 | 22271592
MCR001888 | PRJ023 | 2026-06-01 | Equipment | 1860904 | 5106033 | 5492284
MCR001889 | PRJ023 | 2026-06-01 | Subcontract | 6807196 | 18677894 | 21999177
MCR001890 | PRJ023 | 2026-06-01 | Overhead | 2349999 | 6448034 | 9976438
MCR001891 | PRJ023 | 2026-07-01 | Labor | 1063436 | 7394642 | 7723971
MCR001892 | PRJ023 | 2026-07-01 | Material | 2366074 | 16452584 | 19676160
MCR001893 | PRJ023 | 2026-07-01 | Equipment | 494466 | 3438290 | 3349329
MCR001894 | PRJ023 | 2026-07-01 | Subcontract | 1808760 | 12577281 | 13382228
MCR001895 | PRJ023 | 2026-07-01 | Overhead | 624425 | 4341964 | 10753335
MCR001896 | PRJ023 | 2026-08-01 | Labor | 0 | 4307770 | 4746260
MCR001897 | PRJ023 | 2026-08-01 | Material | 0 | 9584499 | 8883712
MCR001898 | PRJ023 | 2026-08-01 | Equipment | 0 | 2002985 | 2185821
MCR001899 | PRJ023 | 2026-08-01 | Subcontract | 0 | 7326930 | 5957681
MCR001900 | PRJ023 | 2026-08-01 | Overhead | 0 | 2529423 | 10748917
MCR001901 | PRJ024 | 2025-03-01 | Labor | 12552466 | 11675978 | 11834843
MCR001902 | PRJ024 | 2025-03-01 | Material | 38679445 | 35978616 | 37767098
MCR001903 | PRJ024 | 2025-03-01 | Equipment | 10061140 | 9358611 | 10099988
MCR001904 | PRJ024 | 2025-03-01 | Subcontract | 40587748 | 37753669 | 35580885
MCR001905 | PRJ024 | 2025-03-01 | Overhead | 9236005 | 8591092 | 28457949
MCR001906 | PRJ024 | 2025-04-01 | Labor | 33504197 | 36177928 | 34321323
MCR001907 | PRJ024 | 2025-04-01 | Material | 103240572 | 111479466 | 115742226
MCR001908 | PRJ024 | 2025-04-01 | Equipment | 26854518 | 28997585 | 34467507
MCR001909 | PRJ024 | 2025-04-01 | Subcontract | 108334086 | 116979456 | 119860072
MCR001910 | PRJ024 | 2025-04-01 | Overhead | 24652123 | 26619433 | 29493937
MCR001911 | PRJ024 | 2025-05-01 | Labor | 48446878 | 48600258 | 50884612
MCR001912 | PRJ024 | 2025-05-01 | Material | 149285278 | 149757906 | 148693537
MCR001913 | PRJ024 | 2025-05-01 | Equipment | 38831479 | 38954417 | 35421637
MCR001914 | PRJ024 | 2025-05-01 | Subcontract | 156650469 | 157146415 | 140970234
MCR001915 | PRJ024 | 2025-05-01 | Overhead | 35646829 | 35759685 | 29526354
MCR001916 | PRJ024 | 2025-06-01 | Labor | 57700604 | 64784793 | 59635075
MCR001917 | PRJ024 | 2025-06-01 | Material | 177799915 | 199629291 | 193534616
MCR001918 | PRJ024 | 2025-06-01 | Equipment | 46248590 | 51926759 | 50252790
MCR001919 | PRJ024 | 2025-06-01 | Subcontract | 186571914 | 209478272 | 174376394
MCR001920 | PRJ024 | 2025-06-01 | Overhead | 42455648 | 47668138 | 28265008
MCR001921 | PRJ024 | 2025-07-01 | Labor | 61625268 | 38240862 | 43146187
MCR001922 | PRJ024 | 2025-07-01 | Material | 189893460 | 117836236 | 116499253
MCR001923 | PRJ024 | 2025-07-01 | Equipment | 49394314 | 30651082 | 33822591
MCR001924 | PRJ024 | 2025-07-01 | Subcontract | 199262111 | 123649846 | 131513488
MCR001925 | PRJ024 | 2025-07-01 | Overhead | 45343384 | 28137324 | 28813582
MCR001926 | PRJ024 | 2025-08-01 | Labor | 60633561 | 53190303 | 50822976
MCR001927 | PRJ024 | 2025-08-01 | Material | 186837592 | 163901772 | 177755476
MCR001928 | PRJ024 | 2025-08-01 | Equipment | 48599434 | 42633462 | 39586091
MCR001929 | PRJ024 | 2025-08-01 | Subcontract | 196055477 | 171988087 | 157809588
MCR001930 | PRJ024 | 2025-08-01 | Overhead | 44613694 | 39137003 | 27368849
MCR001931 | PRJ024 | 2025-09-01 | Labor | 55211688 | 76714998 | 73880870
MCR001932 | PRJ024 | 2025-09-01 | Material | 170130513 | 236391285 | 246406994
MCR001933 | PRJ024 | 2025-09-01 | Equipment | 44253657 | 61489139 | 68739019
MCR001934 | PRJ024 | 2025-09-01 | Subcontract | 178524132 | 248053969 | 267289670
MCR001935 | PRJ024 | 2025-09-01 | Overhead | 40624323 | 56446288 | 30068770
MCR001936 | PRJ024 | 2025-10-01 | Labor | 45955322 | 31709531 | 49535018
MCR001937 | PRJ024 | 2025-10-01 | Material | 141607743 | 97710449 | 123888023
MCR001938 | PRJ024 | 2025-10-01 | Equipment | 36834430 | 25416044 | 22988278
MCR001939 | PRJ024 | 2025-10-01 | Subcontract | 148594153 | 102531126 | 81500167
MCR001940 | PRJ024 | 2025-10-01 | Overhead | 33813562 | 23331622 | 28930240
MCR001941 | PRJ024 | 2025-11-01 | Labor | 33640453 | 19334476 | 38021130
MCR001942 | PRJ024 | 2025-11-01 | Material | 103660434 | 59577682 | 78300048
MCR001943 | PRJ024 | 2025-11-01 | Equipment | 26963730 | 15497104 | 13964133
MCR001944 | PRJ024 | 2025-11-01 | Subcontract | 108774662 | 62517027 | 58973370
MCR001945 | PRJ024 | 2025-11-01 | Overhead | 24752379 | 14226155 | 29152246
MCR001946 | PRJ024 | 2025-12-01 | Labor | 19395851 | 29061809 | 28739763
MCR001947 | PRJ024 | 2025-12-01 | Material | 59766803 | 89551700 | 94613138
MCR001948 | PRJ024 | 2025-12-01 | Equipment | 15546298 | 23293824 | 20209386
MCR001949 | PRJ024 | 2025-12-01 | Subcontract | 62715479 | 93969854 | 84349266
MCR001950 | PRJ024 | 2025-12-01 | Overhead | 14271314 | 21383449 | 27498829
MCR001951 | PRJ024 | 2026-01-01 | Labor | 5400571 | 19226851 | 22467292
MCR001952 | PRJ024 | 2026-01-01 | Material | 16641439 | 59246044 | 59681663
MCR001953 | PRJ024 | 2026-01-01 | Equipment | 4328703 | 15410840 | 16815578
MCR001954 | PRJ024 | 2026-01-01 | Subcontract | 17462467 | 62169027 | 68202552
MCR001955 | PRJ024 | 2026-01-01 | Overhead | 3973697 | 14146965 | 31142721
MCR001956 | PRJ024 | 2026-02-01 | Labor | 0 | 5349072 | 2924852
MCR001957 | PRJ024 | 2026-02-01 | Material | 0 | 16482748 | 16063276
MCR001958 | PRJ024 | 2026-02-01 | Equipment | 0 | 4287425 | 4344994
MCR001959 | PRJ024 | 2026-02-01 | Subcontract | 0 | 17295947 | 12854099
MCR001960 | PRJ024 | 2026-02-01 | Overhead | 0 | 3935805 | 26898352
MCR001961 | PRJ025 | 2025-03-01 | Labor | 8229165 | 10730570 | 10919658
MCR001962 | PRJ025 | 2025-03-01 | Material | 18176567 | 23701668 | 21941807
MCR001963 | PRJ025 | 2025-03-01 | Equipment | 4767217 | 6216300 | 6081895
MCR001964 | PRJ025 | 2025-03-01 | Subcontract | 25932625 | 33815321 | 34791272
MCR001965 | PRJ025 | 2025-03-01 | Overhead | 5172944 | 6745355 | 18574803
MCR001966 | PRJ025 | 2025-04-01 | Labor | 22201826 | 33814508 | 36910590
MCR001967 | PRJ025 | 2025-04-01 | Material | 49039359 | 74689435 | 73039098
MCR001968 | PRJ025 | 2025-04-01 | Equipment | 12861685 | 19589000 | 21538597
MCR001969 | PRJ025 | 2025-04-01 | Subcontract | 69964768 | 106559896 | 106267678
MCR001970 | PRJ025 | 2025-04-01 | Overhead | 13956312 | 21256173 | 16600945
MCR001971 | PRJ025 | 2025-05-01 | Labor | 32565528 | 32600058 | 37443599
MCR001972 | PRJ025 | 2025-05-01 | Material | 71930688 | 72006959 | 77119475
MCR001973 | PRJ025 | 2025-05-01 | Equipment | 18865456 | 18885460 | 20296694
MCR001974 | PRJ025 | 2025-05-01 | Subcontract | 102623974 | 102732791 | 112407838
MCR001975 | PRJ025 | 2025-05-01 | Overhead | 20471050 | 20492756 | 17276455
MCR001976 | PRJ025 | 2025-06-01 | Labor | 39492145 | 47089079 | 43182961
MCR001977 | PRJ025 | 2025-06-01 | Material | 87230191 | 104010288 | 97217638
MCR001978 | PRJ025 | 2025-06-01 | Equipment | 22878098 | 27279059 | 27386488
MCR001979 | PRJ025 | 2025-06-01 | Subcontract | 124451873 | 148392144 | 176974802
MCR001980 | PRJ025 | 2025-06-01 | Overhead | 24825198 | 29600715 | 16953472
MCR001981 | PRJ025 | 2025-07-01 | Labor | 43172397 | 33880378 | 48049537
MCR001982 | PRJ025 | 2025-07-01 | Material | 95359126 | 74834928 | 85202349
MCR001983 | PRJ025 | 2025-07-01 | Equipment | 25010095 | 19627158 | 20854327
MCR001984 | PRJ025 | 2025-07-01 | Subcontract | 136049477 | 106767471 | 107887329
MCR001985 | PRJ025 | 2025-07-01 | Overhead | 27138645 | 21297579 | 17704608
MCR001986 | PRJ025 | 2025-08-01 | Labor | 43821175 | 28913217 | 27344509
MCR001987 | PRJ025 | 2025-08-01 | Material | 96792145 | 63863471 | 53504354
MCR001988 | PRJ025 | 2025-08-01 | Equipment | 25385937 | 16749645 | 19235528
MCR001989 | PRJ025 | 2025-08-01 | Subcontract | 138093974 | 91114423 | 92376505
MCR001990 | PRJ025 | 2025-08-01 | Overhead | 27546474 | 18175167 | 15555560
MCR001991 | PRJ025 | 2025-09-01 | Labor | 41685534 | 27891115 | 33636069
MCR001992 | PRJ025 | 2025-09-01 | Material | 92074945 | 61605853 | 64032843
MCR001993 | PRJ025 | 2025-09-01 | Equipment | 24148744 | 16157533 | 16508020
MCR001994 | PRJ025 | 2025-09-01 | Subcontract | 131363914 | 87893465 | 98458364
MCR001995 | PRJ025 | 2025-09-01 | Overhead | 26203986 | 17532662 | 18738029
MCR001996 | PRJ025 | 2025-10-01 | Labor | 37057459 | 36389703 | 40107698
MCR001997 | PRJ025 | 2025-10-01 | Material | 81852460 | 80377521 | 85785479
MCR001998 | PRJ025 | 2025-10-01 | Equipment | 21467666 | 21080829 | 23381956
MCR001999 | PRJ025 | 2025-10-01 | Subcontract | 116779429 | 114675124 | 131400046
MCR002000 | PRJ025 | 2025-10-01 | Overhead | 23294727 | 22874968 | 16263965
MCR002001 | PRJ025 | 2025-11-01 | Labor | 30296085 | 45973900 | 49472963
MCR002002 | PRJ025 | 2025-11-01 | Material | 66917948 | 101547081 | 111117058
MCR002003 | PRJ025 | 2025-11-01 | Equipment | 17550751 | 26633027 | 29536288
MCR002004 | PRJ025 | 2025-11-01 | Subcontract | 95472265 | 144877872 | 144974212
MCR002005 | PRJ025 | 2025-11-01 | Overhead | 19044453 | 28899700 | 16456354
MCR002006 | PRJ025 | 2025-12-01 | Labor | 21871654 | 21827483 | 25595909
MCR002007 | PRJ025 | 2025-12-01 | Material | 48310076 | 48212511 | 39300442
MCR002008 | PRJ025 | 2025-12-01 | Equipment | 12670414 | 12644825 | 10498135
MCR002009 | PRJ025 | 2025-12-01 | Subcontract | 68924295 | 68785099 | 75945519
MCR002010 | PRJ025 | 2025-12-01 | Overhead | 13748763 | 13720996 | 17296781
MCR002011 | PRJ025 | 2026-01-01 | Labor | 12472972 | 13025996 | 13849120
MCR002012 | PRJ025 | 2026-01-01 | Material | 27550281 | 28771801 | 33162380
MCR002013 | PRJ025 | 2026-01-01 | Equipment | 7225687 | 7546058 | 9269020
MCR002014 | PRJ025 | 2026-01-01 | Subcontract | 39306163 | 41048914 | 45719346
MCR002015 | PRJ025 | 2026-01-01 | Overhead | 7840648 | 8188285 | 17114411
MCR002016 | PRJ025 | 2026-02-01 | Labor | 3444699 | 4174631 | 4861161
MCR002017 | PRJ025 | 2026-02-01 | Material | 7608647 | 9220918 | 10484464
MCR002018 | PRJ025 | 2026-02-01 | Equipment | 1995540 | 2418395 | 1724374
MCR002019 | PRJ025 | 2026-02-01 | Subcontract | 10855305 | 13155543 | 13261817
MCR002020 | PRJ025 | 2026-02-01 | Overhead | 2165376 | 2624219 | 16794253
MCR002021 | PRJ026 | 2024-11-01 | Labor | 4767821 | 2142318 | 2187801
MCR002022 | PRJ026 | 2024-11-01 | Material | 13185075 | 5924430 | 5599847
MCR002023 | PRJ026 | 2024-11-01 | Equipment | 3370483 | 1514454 | 1526290
MCR002024 | PRJ026 | 2024-11-01 | Subcontract | 13408325 | 6024743 | 6373072
MCR002025 | PRJ026 | 2024-11-01 | Overhead | 2864266 | 1286996 | 16544588
MCR002026 | PRJ026 | 2024-12-01 | Labor | 13496178 | 7294619 | 7679737
MCR002027 | PRJ026 | 2024-12-01 | Material | 37322737 | 20172758 | 20443001
MCR002028 | PRJ026 | 2024-12-01 | Equipment | 9540762 | 5156735 | 5650685
MCR002029 | PRJ026 | 2024-12-01 | Subcontract | 37954688 | 20514325 | 19469093
MCR002030 | PRJ026 | 2024-12-01 | Overhead | 8107822 | 4382238 | 16043957
MCR002031 | PRJ026 | 2025-01-01 | Labor | 21034533 | 14349686 | 14967397
MCR002032 | PRJ026 | 2025-01-01 | Material | 58169529 | 39683054 | 39424194
MCR002033 | PRJ026 | 2025-01-01 | Equipment | 14869799 | 10144126 | 10053503
MCR002034 | PRJ026 | 2025-01-01 | Subcontract | 59154459 | 40354970 | 40402288
MCR002035 | PRJ026 | 2025-01-01 | Overhead | 12636484 | 8620566 | 15518423
MCR002036 | PRJ026 | 2025-02-01 | Labor | 27411902 | 17850828 | 20126674
MCR002037 | PRJ026 | 2025-02-01 | Material | 75805699 | 49365217 | 52995534
MCR002038 | PRJ026 | 2025-02-01 | Equipment | 19378110 | 12619165 | 14260413
MCR002039 | PRJ026 | 2025-02-01 | Subcontract | 77089245 | 50201072 | 57228337
MCR002040 | PRJ026 | 2025-02-01 | Overhead | 16467685 | 10723875 | 16715236
MCR002041 | PRJ026 | 2025-03-01 | Labor | 32658850 | 21044061 | 21583412
MCR002042 | PRJ026 | 2025-03-01 | Material | 90315766 | 58195880 | 51705652
MCR002043 | PRJ026 | 2025-03-01 | Equipment | 23087299 | 14876535 | 13580968
MCR002044 | PRJ026 | 2025-03-01 | Subcontract | 91844998 | 59181256 | 61738199
MCR002045 | PRJ026 | 2025-03-01 | Overhead | 19619786 | 12642208 | 16240387
MCR002046 | PRJ026 | 2025-04-01 | Labor | 36807682 | 21151929 | 18481926
MCR002047 | PRJ026 | 2025-04-01 | Material | 101789071 | 58494180 | 68413989
MCR002048 | PRJ026 | 2025-04-01 | Equipment | 26020205 | 14952789 | 15038693
MCR002049 | PRJ026 | 2025-04-01 | Subcontract | 103512569 | 59484607 | 65429934
MCR002050 | PRJ026 | 2025-04-01 | Overhead | 22112195 | 12707010 | 15886661
MCR002051 | PRJ026 | 2025-05-01 | Labor | 39892687 | 24253813 | 24082733
MCR002052 | PRJ026 | 2025-05-01 | Material | 110320436 | 67072225 | 62765440
MCR002053 | PRJ026 | 2025-05-01 | Equipment | 28201066 | 17145584 | 20427364
MCR002054 | PRJ026 | 2025-05-01 | Subcontract | 112188388 | 68207896 | 62184929
MCR002055 | PRJ026 | 2025-05-01 | Overhead | 23965510 | 14570465 | 16813470
MCR002056 | PRJ026 | 2025-06-01 | Labor | 41950428 | 39533651 | 40611996
MCR002057 | PRJ026 | 2025-06-01 | Material | 116010977 | 109327547 | 119308064
MCR002058 | PRJ026 | 2025-06-01 | Equipment | 29655732 | 27947255 | 25532956
MCR002059 | PRJ026 | 2025-06-01 | Subcontract | 117975281 | 111178687 | 110687337
MCR002060 | PRJ026 | 2025-06-01 | Overhead | 25201697 | 23749819 | 16006609
MCR002061 | PRJ026 | 2025-07-01 | Labor | 43020110 | 24278190 | 22025612
MCR002062 | PRJ026 | 2025-07-01 | Material | 118969108 | 67139637 | 69834137
MCR002063 | PRJ026 | 2025-07-01 | Equipment | 30411915 | 17162816 | 17751094
MCR002064 | PRJ026 | 2025-07-01 | Subcontract | 120983499 | 68276449 | 80731164
MCR002065 | PRJ026 | 2025-07-01 | Overhead | 25844308 | 14585109 | 17536335
MCR002066 | PRJ026 | 2025-08-01 | Labor | 43144034 | 23665878 | 26339907
MCR002067 | PRJ026 | 2025-08-01 | Material | 119311811 | 65446330 | 58219181
MCR002068 | PRJ026 | 2025-08-01 | Equipment | 30499520 | 16729958 | 20629957
MCR002069 | PRJ026 | 2025-08-01 | Subcontract | 121332005 | 66554471 | 68087244
MCR002070 | PRJ026 | 2025-08-01 | Overhead | 25918755 | 14217263 | 16494422
MCR002071 | PRJ026 | 2025-09-01 | Labor | 42368191 | 43861932 | 45094762
MCR002072 | PRJ026 | 2025-09-01 | Material | 117166269 | 121297107 | 137376802
MCR002073 | PRJ026 | 2025-09-01 | Equipment | 29951058 | 31007018 | 27822551
MCR002074 | PRJ026 | 2025-09-01 | Subcontract | 119150135 | 123350917 | 126171337
MCR002075 | PRJ026 | 2025-09-01 | Overhead | 25452667 | 26350032 | 16351059
MCR002076 | PRJ026 | 2025-10-01 | Labor | 40743033 | 48850822 | 52714141
MCR002077 | PRJ026 | 2025-10-01 | Material | 112672009 | 135093534 | 131222687
MCR002078 | PRJ026 | 2025-10-01 | Equipment | 28802196 | 34533781 | 39115013
MCR002079 | PRJ026 | 2025-10-01 | Subcontract | 114579778 | 137380946 | 152000512
MCR002080 | PRJ026 | 2025-10-01 | Overhead | 24476355 | 29347105 | 15191438
MCR002081 | PRJ026 | 2025-11-01 | Labor | 38324525 | 30207279 | 27604108
MCR002082 | PRJ026 | 2025-11-01 | Material | 105983795 | 83536118 | 82506652
MCR002083 | PRJ026 | 2025-11-01 | Equipment | 27092497 | 21354227 | 20959462
MCR002084 | PRJ026 | 2025-11-01 | Subcontract | 107778319 | 84950556 | 89958521
MCR002085 | PRJ026 | 2025-11-01 | Overhead | 23023438 | 18147006 | 15522720
MCR002086 | PRJ026 | 2025-12-01 | Labor | 35175601 | 33092869 | 32289873
MCR002087 | PRJ026 | 2025-12-01 | Material | 97275665 | 91516015 | 77076892
MCR002088 | PRJ026 | 2025-12-01 | Equipment | 24866449 | 23394117 | 20302188
MCR002089 | PRJ026 | 2025-12-01 | Subcontract | 98922742 | 93065570 | 100304981
MCR002090 | PRJ026 | 2025-12-01 | Overhead | 21131723 | 19880523 | 17462009
MCR002091 | PRJ026 | 2026-01-01 | Labor | 31368272 | 43424933 | 45211264
MCR002092 | PRJ026 | 2026-01-01 | Material | 86746762 | 120088617 | 133561975
MCR002093 | PRJ026 | 2026-01-01 | Equipment | 22174960 | 30698094 | 31823326
MCR002094 | PRJ026 | 2026-01-01 | Subcontract | 88215564 | 122121964 | 147758180
MCR002095 | PRJ026 | 2026-01-01 | Overhead | 18844472 | 26087505 | 16406097
MCR002096 | PRJ026 | 2026-02-01 | Labor | 26986843 | 31010782 | 30614457
MCR002097 | PRJ026 | 2026-02-01 | Material | 74630228 | 85758150 | 85462133
MCR002098 | PRJ026 | 2026-02-01 | Equipment | 19077626 | 21922242 | 20947392
MCR002099 | PRJ026 | 2026-02-01 | Subcontract | 75893871 | 87210212 | 83089545
MCR002100 | PRJ026 | 2026-02-01 | Overhead | 16212331 | 18629710 | 16832679
MCR002101 | PRJ026 | 2026-03-01 | Labor | 22133127 | 21999339 | 19681467
MCR002102 | PRJ026 | 2026-03-01 | Material | 61207616 | 60837633 | 64269468
MCR002103 | PRJ026 | 2026-03-01 | Equipment | 15646422 | 15551843 | 18096574
MCR002104 | PRJ026 | 2026-03-01 | Subcontract | 62243987 | 61867739 | 63515698
MCR002105 | PRJ026 | 2026-03-01 | Overhead | 13296464 | 13216091 | 17020769
MCR002106 | PRJ026 | 2026-04-01 | Labor | 16935688 | 45292608 | 47443204
MCR002107 | PRJ026 | 2026-04-01 | Material | 46834461 | 125253542 | 114813944
MCR002108 | PRJ026 | 2026-04-01 | Equipment | 11972231 | 32018396 | 35017340
MCR002109 | PRJ026 | 2026-04-01 | Subcontract | 47627465 | 127374342 | 132976363
MCR002110 | PRJ026 | 2026-04-01 | Overhead | 10174105 | 27209510 | 16584781
MCR002111 | PRJ026 | 2026-05-01 | Labor | 11568488 | 16590108 | 16275947
MCR002112 | PRJ026 | 2026-05-01 | Material | 31991843 | 45878784 | 58191210
MCR002113 | PRJ026 | 2026-05-01 | Equipment | 8178032 | 11727933 | 10622260
MCR002114 | PRJ026 | 2026-05-01 | Subcontract | 32533531 | 46655606 | 55757773
MCR002115 | PRJ026 | 2026-05-01 | Overhead | 6949763 | 9966498 | 17172498
MCR002116 | PRJ026 | 2026-06-01 | Labor | 6297542 | 19664749 | 17780638
MCR002117 | PRJ026 | 2026-06-01 | Material | 17415412 | 54381487 | 50723089
MCR002118 | PRJ026 | 2026-06-01 | Equipment | 4451879 | 13901467 | 15038012
MCR002119 | PRJ026 | 2026-06-01 | Subcontract | 17710291 | 55302278 | 60919791
MCR002120 | PRJ026 | 2026-06-01 | Overhead | 3783245 | 11813587 | 15651337
MCR002121 | PRJ026 | 2026-07-01 | Labor | 1676874 | 15506071 | 16385169
MCR002122 | PRJ026 | 2026-07-01 | Material | 4637278 | 42880955 | 48569812
MCR002123 | PRJ026 | 2026-07-01 | Equipment | 1185421 | 10961602 | 10615087
MCR002124 | PRJ026 | 2026-07-01 | Subcontract | 4715796 | 43607018 | 47548735
MCR002125 | PRJ026 | 2026-07-01 | Overhead | 1007381 | 9315264 | 16992995
MCR002126 | PRJ026 | 2026-08-01 | Labor | 0 | 7518190 | 7637861
MCR002127 | PRJ026 | 2026-08-01 | Material | 0 | 20791028 | 18509047
MCR002128 | PRJ026 | 2026-08-01 | Equipment | 0 | 5314783 | 5234929
MCR002129 | PRJ026 | 2026-08-01 | Subcontract | 0 | 21143063 | 20427853
MCR002130 | PRJ026 | 2026-08-01 | Overhead | 0 | 4516548 | 16247231
MCR002131 | PRJ027 | 2024-11-01 | Labor | 8063840 | 5553169 | 6600154
MCR002132 | PRJ027 | 2024-11-01 | Material | 22863419 | 15744909 | 16242698
MCR002133 | PRJ027 | 2024-11-01 | Equipment | 4512920 | 3107826 | 2896526
MCR002134 | PRJ027 | 2024-11-01 | Subcontract | 46779095 | 32214456 | 34925035
MCR002135 | PRJ027 | 2024-11-01 | Overhead | 7546992 | 5197241 | 26120907
MCR002136 | PRJ027 | 2024-12-01 | Labor | 21755787 | 22598905 | 25769400
MCR002137 | PRJ027 | 2024-12-01 | Material | 61684222 | 64074715 | 64945400
MCR002138 | PRJ027 | 2024-12-01 | Equipment | 12175605 | 12647455 | 10952754
MCR002139 | PRJ027 | 2024-12-01 | Subcontract | 126207375 | 131098381 | 150837326
MCR002140 | PRJ027 | 2024-12-01 | Overhead | 20361361 | 21150440 | 25380500
MCR002141 | PRJ027 | 2025-01-01 | Labor | 31911281 | 29083502 | 32192538
MCR002142 | PRJ027 | 2025-01-01 | Material | 90478110 | 82460504 | 82576165
MCR002143 | PRJ027 | 2025-01-01 | Equipment | 17859117 | 16276554 | 18683884
MCR002144 | PRJ027 | 2025-01-01 | Subcontract | 185120351 | 168716140 | 170831732
MCR002145 | PRJ027 | 2025-01-01 | Overhead | 29865943 | 27219410 | 26963746
MCR002146 | PRJ027 | 2025-02-01 | Labor | 38698742 | 19631199 | 20578280
MCR002147 | PRJ027 | 2025-02-01 | Material | 109722609 | 55660373 | 61407064
MCR002148 | PRJ027 | 2025-02-01 | Equipment | 21657713 | 10986582 | 11240440
MCR002149 | PRJ027 | 2025-02-01 | Subcontract | 224495052 | 113882438 | 107838146
MCR002150 | PRJ027 | 2025-02-01 | Overhead | 36218365 | 18372947 | 25638731
MCR002151 | PRJ027 | 2025-03-01 | Labor | 42305057 | 33084392 | 36936478
MCR002152 | PRJ027 | 2025-03-01 | Material | 119947601 | 93804235 | 87848189
MCR002153 | PRJ027 | 2025-03-01 | Equipment | 23675984 | 18515648 | 20961191
MCR002154 | PRJ027 | 2025-03-01 | Subcontract | 245415626 | 191925682 | 205812514
MCR002155 | PRJ027 | 2025-03-01 | Overhead | 39593535 | 30963865 | 24192062
MCR002156 | PRJ027 | 2025-04-01 | Labor | 42940800 | 60311206 | 64035378
MCR002157 | PRJ027 | 2025-04-01 | Material | 121750125 | 171000469 | 176407081
MCR002158 | PRJ027 | 2025-04-01 | Equipment | 24031777 | 33753108 | 35074142
MCR002159 | PRJ027 | 2025-04-01 | Subcontract | 249103634 | 349871001 | 428483122
MCR002160 | PRJ027 | 2025-04-01 | Overhead | 40188531 | 56445590 | 25019172
MCR002161 | PRJ027 | 2025-05-01 | Labor | 40848065 | 41853261 | 45549326
MCR002162 | PRJ027 | 2025-05-01 | Material | 115816589 | 118666624 | 131999156
MCR002163 | PRJ027 | 2025-05-01 | Equipment | 22860580 | 23423137 | 21518398
MCR002164 | PRJ027 | 2025-05-01 | Subcontract | 236963479 | 242794718 | 232557148
MCR002165 | PRJ027 | 2025-05-01 | Overhead | 38229929 | 39170698 | 26553172
MCR002166 | PRJ027 | 2025-06-01 | Labor | 36312968 | 35831275 | 40065970
MCR002167 | PRJ027 | 2025-06-01 | Material | 102958223 | 101592477 | 96174417
MCR002168 | PRJ027 | 2025-06-01 | Equipment | 20322518 | 20052938 | 18010424
MCR002169 | PRJ027 | 2025-06-01 | Subcontract | 210654957 | 207860609 | 248166267
MCR002170 | PRJ027 | 2025-06-01 | Overhead | 33985507 | 33534688 | 25164037
MCR002171 | PRJ027 | 2025-07-01 | Labor | 29687432 | 28236577 | 28232746
MCR002172 | PRJ027 | 2025-07-01 | Material | 84172827 | 80059217 | 80917856
MCR002173 | PRJ027 | 2025-07-01 | Equipment | 16614542 | 15802573 | 17760022
MCR002174 | PRJ027 | 2025-07-01 | Subcontract | 172219594 | 163803049 | 210102349
MCR002175 | PRJ027 | 2025-07-01 | Overhead | 27784631 | 26426768 | 27008467
MCR002176 | PRJ027 | 2025-08-01 | Labor | 21432248 | 13779651 | 14379274
MCR002177 | PRJ027 | 2025-08-01 | Material | 60766892 | 39069469 | 41863348
MCR002178 | PRJ027 | 2025-08-01 | Equipment | 11994537 | 7711768 | 8459599
MCR002179 | PRJ027 | 2025-08-01 | Subcontract | 124330496 | 79937056 | 137999873
MCR002180 | PRJ027 | 2025-08-01 | Overhead | 20058559 | 12896451 | 23716275
MCR002181 | PRJ027 | 2025-09-01 | Labor | 12222388 | 14917013 | 18648752
MCR002182 | PRJ027 | 2025-09-01 | Material | 34654157 | 42294232 | 42635972
MCR002183 | PRJ027 | 2025-09-01 | Equipment | 6840247 | 8348292 | 7835507
MCR002184 | PRJ027 | 2025-09-01 | Subcontract | 70903225 | 86534999 | 125481197
MCR002185 | PRJ027 | 2025-09-01 | Overhead | 11439000 | 13960914 | 23572406
MCR002186 | PRJ027 | 2025-10-01 | Labor | 3375495 | 16399929 | 15897674
MCR002187 | PRJ027 | 2025-10-01 | Material | 9570546 | 46498746 | 47971908
MCR002188 | PRJ027 | 2025-10-01 | Equipment | 1889092 | 9178204 | 9374578
MCR002189 | PRJ027 | 2025-10-01 | Subcontract | 19581564 | 95137534 | 135753652
MCR002190 | PRJ027 | 2025-10-01 | Overhead | 3159144 | 15348784 | 25222997
MCR002191 | PRJ027 | 2025-11-01 | Labor | 0 | 5733857 | 6850499
MCR002192 | PRJ027 | 2025-11-01 | Material | 0 | 16257214 | 16518198
MCR002193 | PRJ027 | 2025-11-01 | Equipment | 0 | 3208947 | 3069588
MCR002194 | PRJ027 | 2025-11-01 | Subcontract | 0 | 33262644 | 106039031
MCR002195 | PRJ027 | 2025-11-01 | Overhead | 0 | 5366348 | 23970314
MCR002196 | PRJ027 | 2025-12-01 | Labor | 0 | 2540165 | 2585364
MCR002197 | PRJ027 | 2025-12-01 | Material | 0 | 7202135 | 7929158
MCR002198 | PRJ027 | 2025-12-01 | Equipment | 0 | 1421601 | 1643566
MCR002199 | PRJ027 | 2025-12-01 | Subcontract | 0 | 14735739 | 51006379
MCR002200 | PRJ027 | 2025-12-01 | Overhead | 0 | 2377355 | 25994674
MCR002201 | PRJ028 | 2025-06-01 | Labor | 14665771 | 10305404 | 10247240
MCR002202 | PRJ028 | 2025-06-01 | Material | 50346223 | 35377489 | 35026320
MCR002203 | PRJ028 | 2025-06-01 | Equipment | 26657277 | 18731644 | 17949232
MCR002204 | PRJ028 | 2025-06-01 | Subcontract | 34217015 | 24043752 | 28346240
MCR002205 | PRJ028 | 2025-06-01 | Overhead | 11124119 | 7816741 | 33475214
MCR002206 | PRJ028 | 2025-07-01 | Labor | 39144888 | 18394460 | 18907003
MCR002207 | PRJ028 | 2025-07-01 | Material | 134380749 | 63146465 | 64382777
MCR002208 | PRJ028 | 2025-07-01 | Equipment | 71151809 | 33434738 | 36354468
MCR002209 | PRJ028 | 2025-07-01 | Subcontract | 91329753 | 42916497 | 42374530
MCR002210 | PRJ028 | 2025-07-01 | Overhead | 29691750 | 13952363 | 30337820
MCR002211 | PRJ028 | 2025-08-01 | Labor | 56603284 | 30789070 | 27862359
MCR002212 | PRJ028 | 2025-08-01 | Material | 194313794 | 105696005 | 102317026
MCR002213 | PRJ028 | 2025-08-01 | Equipment | 102885109 | 55963834 | 58029272
MCR002214 | PRJ028 | 2025-08-01 | Subcontract | 132062300 | 71834620 | 72044038
MCR002215 | PRJ028 | 2025-08-01 | Overhead | 42934101 | 23353787 | 34827865
MCR002216 | PRJ028 | 2025-09-01 | Labor | 67414948 | 52138527 | 56716087
MCR002217 | PRJ028 | 2025-09-01 | Material | 231429225 | 178986698 | 156601449
MCR002218 | PRJ028 | 2025-09-01 | Equipment | 122536957 | 94769731 | 87719130
MCR002219 | PRJ028 | 2025-09-01 | Subcontract | 157287216 | 121645482 | 124348517
MCR002220 | PRJ028 | 2025-09-01 | Overhead | 51134844 | 39547542 | 34988793
MCR002221 | PRJ028 | 2025-10-01 | Labor | 72000359 | 97125045 | 93719209
MCR002222 | PRJ028 | 2025-10-01 | Material | 247170514 | 333421218 | 368662842
MCR002223 | PRJ028 | 2025-10-01 | Equipment | 130871642 | 176539594 | 167846190
MCR002224 | PRJ028 | 2025-10-01 | Subcontract | 167985535 | 226604463 | 213698188
MCR002225 | PRJ028 | 2025-10-01 | Overhead | 54612920 | 73670221 | 35791864
MCR002226 | PRJ028 | 2025-11-01 | Labor | 70841690 | 46217205 | 35926033
MCR002227 | PRJ028 | 2025-11-01 | Material | 243192912 | 158659353 | 158399754
MCR002228 | PRJ028 | 2025-11-01 | Equipment | 128765584 | 84006825 | 112547703
MCR002229 | PRJ028 | 2025-11-01 | Subcontract | 165282220 | 107830323 | 118285310
MCR002230 | PRJ028 | 2025-11-01 | Overhead | 53734059 | 35056166 | 34389793
MCR002231 | PRJ028 | 2025-12-01 | Labor | 64507003 | 57173405 | 58951496
MCR002232 | PRJ028 | 2025-12-01 | Material | 221446522 | 196270963 | 199340363
MCR002233 | PRJ028 | 2025-12-01 | Equipment | 117251323 | 103921389 | 107821278
MCR002234 | PRJ028 | 2025-12-01 | Subcontract | 150502630 | 133392459 | 152147093
MCR002235 | PRJ028 | 2025-12-01 | Overhead | 48929142 | 43366542 | 36890886
MCR002236 | PRJ028 | 2026-01-01 | Labor | 53692256 | 45145469 | 48610538
MCR002237 | PRJ028 | 2026-01-01 | Material | 184320506 | 154980183 | 148821433
MCR002238 | PRJ028 | 2026-01-01 | Equipment | 97593871 | 82058780 | 74600798
MCR002239 | PRJ028 | 2026-01-01 | Subcontract | 125270520 | 105329832 | 102999126
MCR002240 | PRJ028 | 2026-01-01 | Overhead | 40726060 | 34243245 | 35018060
MCR002241 | PRJ028 | 2026-02-01 | Labor | 39304084 | 60164780 | 53989479
MCR002242 | PRJ028 | 2026-02-01 | Material | 134927252 | 206540075 | 225241787
MCR002243 | PRJ028 | 2026-02-01 | Equipment | 71441171 | 109358670 | 132657562
MCR002244 | PRJ028 | 2026-02-01 | Subcontract | 91701175 | 140371698 | 140396969
MCR002245 | PRJ028 | 2026-02-01 | Overhead | 29812501 | 45635527 | 36208484
MCR002246 | PRJ028 | 2026-03-01 | Labor | 22661293 | 33688091 | 31355855
MCR002247 | PRJ028 | 2026-03-01 | Material | 77794103 | 115648073 | 108113423
MCR002248 | PRJ028 | 2026-03-01 | Equipment | 41190358 | 61233247 | 56114634
MCR002249 | PRJ028 | 2026-03-01 | Subcontract | 52871533 | 78598385 | 92708881
MCR002250 | PRJ028 | 2026-03-01 | Overhead | 17188794 | 25552720 | 36253570
MCR002251 | PRJ028 | 2026-04-01 | Labor | 6309799 | 28772913 | 28929116
MCR002252 | PRJ028 | 2026-04-01 | Material | 21660951 | 98774726 | 102845438
MCR002253 | PRJ028 | 2026-04-01 | Equipment | 11469023 | 52299161 | 55147725
MCR002254 | PRJ028 | 2026-04-01 | Subcontract | 14721523 | 67130682 | 64429128
MCR002255 | PRJ028 | 2026-04-01 | Overhead | 4786039 | 21824513 | 36504261
MCR002256 | PRJ028 | 2026-05-01 | Labor | 0 | 16062570 | 15281400
MCR002257 | PRJ028 | 2026-05-01 | Material | 0 | 55141305 | 45455039
MCR002258 | PRJ028 | 2026-05-01 | Equipment | 0 | 29196173 | 22702475
MCR002259 | PRJ028 | 2026-05-01 | Subcontract | 0 | 37475917 | 35940084
MCR002260 | PRJ028 | 2026-05-01 | Overhead | 0 | 12183604 | 31374473
MCR002261 | PRJ028 | 2026-06-01 | Labor | 0 | 9348548 | 7313013
MCR002262 | PRJ028 | 2026-06-01 | Material | 0 | 32092693 | 35217660
MCR002263 | PRJ028 | 2026-06-01 | Equipment | 0 | 16992413 | 19527134
MCR002264 | PRJ028 | 2026-06-01 | Subcontract | 0 | 21811292 | 26206418
MCR002265 | PRJ028 | 2026-06-01 | Overhead | 0 | 7090958 | 36801696
MCR002266 | PRJ028 | 2026-07-01 | Labor | 0 | 1819888 | 1953462
MCR002267 | PRJ028 | 2026-07-01 | Material | 0 | 6247505 | 6259032
MCR002268 | PRJ028 | 2026-07-01 | Equipment | 0 | 3307924 | 3398342
MCR002269 | PRJ028 | 2026-07-01 | Subcontract | 0 | 4246018 | 2862886
MCR002270 | PRJ028 | 2026-07-01 | Overhead | 0 | 1380401 | 36609644
MCR002271 | PRJ029 | 2024-12-01 | Labor | 10426910 | 6291291 | 6665605
MCR002272 | PRJ029 | 2024-12-01 | Material | 23594074 | 14235970 | 14335063
MCR002273 | PRJ029 | 2024-12-01 | Equipment | 5067698 | 3057700 | 3294106
MCR002274 | PRJ029 | 2024-12-01 | Subcontract | 30397366 | 18340877 | 19271400
MCR002275 | PRJ029 | 2024-12-01 | Overhead | 6494267 | 3918450 | 18912719
MCR002276 | PRJ029 | 2025-01-01 | Labor | 27830808 | 23285610 | 25018579
MCR002277 | PRJ029 | 2025-01-01 | Material | 62975715 | 52690816 | 52492031
MCR002278 | PRJ029 | 2025-01-01 | Equipment | 13526359 | 11317298 | 10337866
MCR002279 | PRJ029 | 2025-01-01 | Subcontract | 81134604 | 67884080 | 65873061
MCR002280 | PRJ029 | 2025-01-01 | Overhead | 17334061 | 14503143 | 19658234
MCR002281 | PRJ029 | 2025-02-01 | Labor | 40243189 | 21134117 | 19486178
MCR002282 | PRJ029 | 2025-02-01 | Material | 91062524 | 47822405 | 47857221
MCR002283 | PRJ029 | 2025-02-01 | Equipment | 19559038 | 10271627 | 12267118
MCR002284 | PRJ029 | 2025-02-01 | Subcontract | 117320173 | 61611875 | 59223581
MCR002285 | PRJ029 | 2025-02-01 | Overhead | 25064953 | 13163113 | 20391434
MCR002286 | PRJ029 | 2025-03-01 | Labor | 47929947 | 39344462 | 40972442
MCR002287 | PRJ029 | 2025-03-01 | Material | 108456167 | 89028881 | 103214790
MCR002288 | PRJ029 | 2025-03-01 | Equipment | 23294965 | 19122238 | 17600815
MCR002289 | PRJ029 | 2025-03-01 | Subcontract | 139729229 | 114700135 | 131132762
MCR002290 | PRJ029 | 2025-03-01 | Overhead | 29852552 | 24505193 | 17091973
MCR002291 | PRJ029 | 2025-04-01 | Labor | 51190033 | 51756541 | 46483184
MCR002292 | PRJ029 | 2025-04-01 | Material | 115833109 | 117115007 | 103697690
MCR002293 | PRJ029 | 2025-04-01 | Equipment | 24879436 | 25154771 | 27966499
MCR002294 | PRJ029 | 2025-04-01 | Subcontract | 149233294 | 150884823 | 154006582
MCR002295 | PRJ029 | 2025-04-01 | Overhead | 31883055 | 32235897 | 20345335
MCR002296 | PRJ029 | 2025-05-01 | Labor | 50366255 | 34966801 | 38738116
MCR002297 | PRJ029 | 2025-05-01 | Material | 113969060 | 79123084 | 88746194
MCR002298 | PRJ029 | 2025-05-01 | Equipment | 24479062 | 16994603 | 15455372
MCR002299 | PRJ029 | 2025-05-01 | Subcontract | 146831751 | 101938026 | 129345934
MCR002300 | PRJ029 | 2025-05-01 | Overhead | 31369975 | 21778623 | 21555102
MCR002301 | PRJ029 | 2025-06-01 | Labor | 45862488 | 33026923 | 35405015
MCR002302 | PRJ029 | 2025-06-01 | Material | 103777909 | 74733515 | 65538516
MCR002303 | PRJ029 | 2025-06-01 | Equipment | 22290137 | 16051781 | 16500846
MCR002304 | PRJ029 | 2025-06-01 | Subcontract | 133702007 | 96282736 | 85809821
MCR002305 | PRJ029 | 2025-06-01 | Overhead | 28564862 | 20570395 | 20752258
MCR002306 | PRJ029 | 2025-07-01 | Labor | 38173537 | 39279785 | 39812855
MCR002307 | PRJ029 | 2025-07-01 | Material | 86379305 | 88882529 | 99919898
MCR002308 | PRJ029 | 2025-07-01 | Equipment | 18553144 | 19090804 | 20571768
MCR002309 | PRJ029 | 2025-07-01 | Subcontract | 111286560 | 114511582 | 110276196
MCR002310 | PRJ029 | 2025-07-01 | Overhead | 23775897 | 24464910 | 21180328
MCR002311 | PRJ029 | 2025-08-01 | Labor | 27943991 | 40274951 | 47757054
MCR002312 | PRJ029 | 2025-08-01 | Material | 63231826 | 91134397 | 96168667
MCR002313 | PRJ029 | 2025-08-01 | Equipment | 13581369 | 19574476 | 20400628
MCR002314 | PRJ029 | 2025-08-01 | Subcontract | 81464564 | 117412771 | 163671874
MCR002315 | PRJ029 | 2025-08-01 | Overhead | 17404556 | 25084736 | 19445739
MCR002316 | PRJ029 | 2025-09-01 | Labor | 16111480 | 35921977 | 34219144
MCR002317 | PRJ029 | 2025-09-01 | Material | 36457151 | 81284462 | 80547888
MCR002318 | PRJ029 | 2025-09-01 | Equipment | 7830519 | 17458839 | 16863788
MCR002319 | PRJ029 | 2025-09-01 | Subcontract | 46969479 | 104722631 | 134917986
MCR002320 | PRJ029 | 2025-09-01 | Overhead | 10034828 | 22373542 | 22433852
MCR002321 | PRJ029 | 2025-10-01 | Labor | 4486072 | 20452302 | 24742286
MCR002322 | PRJ029 | 2025-10-01 | Material | 10151111 | 46279590 | 44471722
MCR002323 | PRJ029 | 2025-10-01 | Equipment | 2180326 | 9940250 | 11094731
MCR002324 | PRJ029 | 2025-10-01 | Subcontract | 13078158 | 59624193 | 77616108
MCR002325 | PRJ029 | 2025-10-01 | Overhead | 2794093 | 12738454 | 21645228
MCR002326 | PRJ029 | 2025-11-01 | Labor | 0 | 11112552 | 11093030
MCR002327 | PRJ029 | 2025-11-01 | Material | 0 | 25145547 | 24291304
MCR002328 | PRJ029 | 2025-11-01 | Equipment | 0 | 5400934 | 4700720
MCR002329 | PRJ029 | 2025-11-01 | Subcontract | 0 | 32396203 | 56509043
MCR002330 | PRJ029 | 2025-11-01 | Overhead | 0 | 6921310 | 20600415
MCR002331 | PRJ029 | 2025-12-01 | Labor | 0 | 3717397 | 4156847
MCR002332 | PRJ029 | 2025-12-01 | Material | 0 | 8411748 | 9682602
MCR002333 | PRJ029 | 2025-12-01 | Equipment | 0 | 1806733 | 2392621
MCR002334 | PRJ029 | 2025-12-01 | Subcontract | 0 | 10837254 | 29677182
MCR002335 | PRJ029 | 2025-12-01 | Overhead | 0 | 2315333 | 19480551
MCR002336 | PRJ030 | 2025-03-01 | Labor | 6587564 | 4011660 | 4167201
MCR002337 | PRJ030 | 2025-03-01 | Material | 14320364 | 8720740 | 9858697
MCR002338 | PRJ030 | 2025-03-01 | Equipment | 4560960 | 2777510 | 2971472
MCR002339 | PRJ030 | 2025-03-01 | Subcontract | 18564333 | 11305210 | 13871956
MCR002340 | PRJ030 | 2025-03-01 | Overhead | 5106002 | 3109426 | 23776297
MCR002341 | PRJ030 | 2025-04-01 | Labor | 18286989 | 12297905 | 14194341
MCR002342 | PRJ030 | 2025-04-01 | Material | 39753140 | 26733781 | 26734037
MCR002343 | PRJ030 | 2025-04-01 | Equipment | 12661164 | 8514568 | 9818396
MCR002344 | PRJ030 | 2025-04-01 | Subcontract | 51534341 | 34656577 | 33146192
MCR002345 | PRJ030 | 2025-04-01 | Overhead | 14174193 | 9532072 | 22003722
MCR002346 | PRJ030 | 2025-05-01 | Labor | 27824273 | 17525817 | 13968103
MCR002347 | PRJ030 | 2025-05-01 | Material | 60485750 | 38098468 | 42020782
MCR002348 | PRJ030 | 2025-05-01 | Equipment | 19264391 | 12134160 | 12649764
MCR002349 | PRJ030 | 2025-05-01 | Subcontract | 78411246 | 49389291 | 54186255
MCR002350 | PRJ030 | 2025-05-01 | Overhead | 21566516 | 13584211 | 22830082
MCR002351 | PRJ030 | 2025-06-01 | Labor | 35271745 | 18698513 | 22561285
MCR002352 | PRJ030 | 2025-06-01 | Material | 76675426 | 40647731 | 34962629
MCR002353 | PRJ030 | 2025-06-01 | Equipment | 24420717 | 12946087 | 13444407
MCR002354 | PRJ030 | 2025-06-01 | Subcontract | 99398877 | 52694052 | 59128909
MCR002355 | PRJ030 | 2025-06-01 | Overhead | 27339031 | 14493165 | 23602030
MCR002356 | PRJ030 | 2025-07-01 | Labor | 40707124 | 16424101 | 14039424
MCR002357 | PRJ030 | 2025-07-01 | Material | 88491114 | 35703505 | 41159359
MCR002358 | PRJ030 | 2025-07-01 | Equipment | 28183951 | 11371377 | 11656055
MCR002359 | PRJ030 | 2025-07-01 | Subcontract | 114716251 | 46284559 | 47288738
MCR002360 | PRJ030 | 2025-07-01 | Overhead | 31551977 | 12730274 | 21812838
MCR002361 | PRJ030 | 2025-08-01 | Labor | 44214508 | 24984861 | 27701717
MCR002362 | PRJ030 | 2025-08-01 | Material | 96115635 | 54313300 | 49996488
MCR002363 | PRJ030 | 2025-08-01 | Equipment | 30612320 | 17298498 | 16822876
MCR002364 | PRJ030 | 2025-08-01 | Subcontract | 124600368 | 70409535 | 82315774
MCR002365 | PRJ030 | 2025-08-01 | Overhead | 34270541 | 19365696 | 23810438
MCR002366 | PRJ030 | 2025-09-01 | Labor | 45885677 | 36262193 | 31024739
MCR002367 | PRJ030 | 2025-09-01 | Material | 99748503 | 78828508 | 82394018
MCR002368 | PRJ030 | 2025-09-01 | Equipment | 31769369 | 25106462 | 24792222
MCR002369 | PRJ030 | 2025-09-01 | Subcontract | 129309868 | 102190045 | 90594011
MCR002370 | PRJ030 | 2025-09-01 | Overhead | 35565859 | 28106724 | 22802465
MCR002371 | PRJ030 | 2025-10-01 | Labor | 45821830 | 50999973 | 54909298
MCR002372 | PRJ030 | 2025-10-01 | Material | 99609710 | 110866208 | 107055815
MCR002373 | PRJ030 | 2025-10-01 | Equipment | 31725165 | 35310299 | 38316782
MCR002374 | PRJ030 | 2025-10-01 | Subcontract | 129129943 | 143722405 | 156942031
MCR002375 | PRJ030 | 2025-10-01 | Overhead | 35516372 | 39529936 | 23891487
MCR002376 | PRJ030 | 2025-11-01 | Labor | 44136001 | 31229653 | 26824800
MCR002377 | PRJ030 | 2025-11-01 | Material | 95944974 | 67888530 | 72263608
MCR002378 | PRJ030 | 2025-11-01 | Equipment | 30557966 | 21622137 | 24815918
MCR002379 | PRJ030 | 2025-11-01 | Subcontract | 124379130 | 88007906 | 112283653
MCR002380 | PRJ030 | 2025-11-01 | Overhead | 34209691 | 24206016 | 22145870
MCR002381 | PRJ030 | 2025-12-01 | Labor | 40956528 | 45430487 | 46946927
MCR002382 | PRJ030 | 2025-12-01 | Material | 89033281 | 98758990 | 86947901
MCR002383 | PRJ030 | 2025-12-01 | Equipment | 28356628 | 31454215 | 31287713
MCR002384 | PRJ030 | 2025-12-01 | Subcontract | 115419094 | 128027104 | 136998736
MCR002385 | PRJ030 | 2025-12-01 | Overhead | 31745290 | 35213043 | 23588091
MCR002386 | PRJ030 | 2026-01-01 | Labor | 36432298 | 26429465 | 28555855
MCR002387 | PRJ030 | 2026-01-01 | Material | 79198292 | 57453649 | 65094413
MCR002388 | PRJ030 | 2026-01-01 | Equipment | 25224236 | 18298683 | 16567021
MCR002389 | PRJ030 | 2026-01-01 | Subcontract | 102669417 | 74480555 | 78866160
MCR002390 | PRJ030 | 2026-01-01 | Overhead | 28238572 | 20485404 | 19934170
MCR002391 | PRJ030 | 2026-02-01 | Labor | 30741206 | 28487445 | 27764876
MCR002392 | PRJ030 | 2026-02-01 | Material | 66826720 | 61927386 | 55919236
MCR002393 | PRJ030 | 2026-02-01 | Equipment | 21283956 | 19723544 | 24264617
MCR002394 | PRJ030 | 2026-02-01 | Subcontract | 86631419 | 80280123 | 101878490
MCR002395 | PRJ030 | 2026-02-01 | Overhead | 23827422 | 22080539 | 23777292
MCR002396 | PRJ030 | 2026-03-01 | Labor | 24105012 | 23111884 | 25844734
MCR002397 | PRJ030 | 2026-03-01 | Material | 52400642 | 50241731 | 50227880
MCR002398 | PRJ030 | 2026-03-01 | Equipment | 16689327 | 16001725 | 15675272
MCR002399 | PRJ030 | 2026-03-01 | Subcontract | 67930043 | 65131320 | 69080912
MCR002400 | PRJ030 | 2026-03-01 | Overhead | 18683727 | 17913956 | 21317778
MCR002401 | PRJ030 | 2026-04-01 | Labor | 16819072 | 37034380 | 38399934
MCR002402 | PRJ030 | 2026-04-01 | Material | 36562112 | 80507125 | 92036142
MCR002403 | PRJ030 | 2026-04-01 | Equipment | 11644839 | 25641093 | 20729169
MCR002404 | PRJ030 | 2026-04-01 | Subcontract | 47397622 | 104366136 | 106725457
MCR002405 | PRJ030 | 2026-04-01 | Overhead | 13036415 | 28705244 | 24067327
MCR002406 | PRJ030 | 2026-05-01 | Labor | 9325941 | 40538858 | 40952646
MCR002407 | PRJ030 | 2026-05-01 | Material | 20273181 | 88125329 | 91256274
MCR002408 | PRJ030 | 2026-05-01 | Equipment | 6456901 | 28067450 | 32134553
MCR002409 | PRJ030 | 2026-05-01 | Subcontract | 26281321 | 114242063 | 195762265
MCR002410 | PRJ030 | 2026-05-01 | Overhead | 7228511 | 31421555 | 23878916
MCR002411 | PRJ030 | 2026-06-01 | Labor | 2520327 | 23664041 | 25641092
MCR002412 | PRJ030 | 2026-06-01 | Material | 5478809 | 51442037 | 50843779
MCR002413 | PRJ030 | 2026-06-01 | Equipment | 1744972 | 16384016 | 15732705
MCR002414 | PRJ030 | 2026-06-01 | Subcontract | 7102503 | 66687348 | 83477780
MCR002415 | PRJ030 | 2026-06-01 | Overhead | 1953498 | 18341932 | 23907875
MCR002416 | PRJ030 | 2026-07-01 | Labor | 0 | 13111313 | 12050989
MCR002417 | PRJ030 | 2026-07-01 | Material | 0 | 28502006 | 28718429
MCR002418 | PRJ030 | 2026-07-01 | Equipment | 0 | 9077738 | 10642281
MCR002419 | PRJ030 | 2026-07-01 | Subcontract | 0 | 36948832 | 53283080
MCR002420 | PRJ030 | 2026-07-01 | Overhead | 0 | 10162542 | 23364525
MCR002421 | PRJ030 | 2026-08-01 | Labor | 0 | 11225378 | 12257912
MCR002422 | PRJ030 | 2026-08-01 | Material | 0 | 24402269 | 21683387
MCR002423 | PRJ030 | 2026-08-01 | Equipment | 0 | 7771993 | 8701450
MCR002424 | PRJ030 | 2026-08-01 | Subcontract | 0 | 31634101 | 62089302
MCR002425 | PRJ030 | 2026-08-01 | Overhead | 0 | 8700759 | 21587077
MCR002426 | HPR001 | 2020-03-01 | Labor | 3106437 | 2338864 | 2378959
MCR002427 | HPR001 | 2020-03-01 | Material | 5965935 | 4491804 | 4955155
MCR002428 | HPR001 | 2020-03-01 | Equipment | 1352296 | 1018155 | 1119184
MCR002429 | HPR001 | 2020-03-01 | Subcontract | 6116660 | 4605286 | 4673070
MCR002430 | HPR001 | 2020-03-01 | Overhead | 1501476 | 1130474 | 9626292
MCR002431 | HPR001 | 2020-04-01 | Labor | 8817823 | 8337117 | 9314334
MCR002432 | HPR001 | 2020-04-01 | Material | 16934690 | 16011492 | 16304530
MCR002433 | HPR001 | 2020-04-01 | Equipment | 3838580 | 3629319 | 3636079
MCR002434 | HPR001 | 2020-04-01 | Subcontract | 17362533 | 16416011 | 17665792
MCR002435 | HPR001 | 2020-04-01 | Overhead | 4262036 | 4029690 | 8754235
MCR002436 | HPR001 | 2020-05-01 | Labor | 13789337 | 11445320 | 11369642
MCR002437 | HPR001 | 2020-05-01 | Material | 26482518 | 21980817 | 22490706
MCR002438 | HPR001 | 2020-05-01 | Equipment | 6002782 | 4982383 | 5682186
MCR002439 | HPR001 | 2020-05-01 | Subcontract | 27151581 | 22536147 | 23444149
MCR002440 | HPR001 | 2020-05-01 | Overhead | 6664984 | 5532019 | 9515610
MCR002441 | HPR001 | 2020-06-01 | Labor | 18038095 | 12809929 | 12102647
MCR002442 | HPR001 | 2020-06-01 | Material | 34642288 | 24601559 | 23473674
MCR002443 | HPR001 | 2020-06-01 | Equipment | 7852354 | 5576426 | 6041970
MCR002444 | HPR001 | 2020-06-01 | Subcontract | 35517501 | 25223100 | 21752637
MCR002445 | HPR001 | 2020-06-01 | Overhead | 8718593 | 6191594 | 8581245
MCR002446 | HPR001 | 2020-07-01 | Labor | 21582073 | 17565585 | 20905074
MCR002447 | HPR001 | 2020-07-01 | Material | 41448522 | 33734830 | 32337004
MCR002448 | HPR001 | 2020-07-01 | Equipment | 9395120 | 7646661 | 7400606
MCR002449 | HPR001 | 2020-07-01 | Subcontract | 42495690 | 34587117 | 35265406
MCR002450 | HPR001 | 2020-07-01 | Overhead | 10431551 | 8490209 | 8982899
MCR002451 | HPR001 | 2020-08-01 | Labor | 24440212 | 9516615 | 9333094
MCR002452 | HPR001 | 2020-08-01 | Material | 46937599 | 18276725 | 20384314
MCR002453 | HPR001 | 2020-08-01 | Equipment | 10639327 | 4142778 | 4700631
MCR002454 | HPR001 | 2020-08-01 | Subcontract | 48123444 | 18738474 | 15251802
MCR002455 | HPR001 | 2020-08-01 | Overhead | 11813014 | 4599792 | 9088732
MCR002456 | HPR001 | 2020-09-01 | Labor | 26632546 | 26253402 | 29083118
MCR002457 | HPR001 | 2020-09-01 | Material | 51147992 | 50419843 | 55536005
MCR002458 | HPR001 | 2020-09-01 | Equipment | 11593695 | 11428646 | 11069245
MCR002459 | HPR001 | 2020-09-01 | Subcontract | 52440210 | 51693665 | 51054457
MCR002460 | HPR001 | 2020-09-01 | Overhead | 12872664 | 12689407 | 9628020
MCR002461 | HPR001 | 2020-10-01 | Labor | 28180349 | 29597335 | 28933569
MCR002462 | HPR001 | 2020-10-01 | Material | 54120558 | 56841889 | 54596646
MCR002463 | HPR001 | 2020-10-01 | Equipment | 12267486 | 12884329 | 13108428
MCR002464 | HPR001 | 2020-10-01 | Subcontract | 55487877 | 58277960 | 56216582
MCR002465 | HPR001 | 2020-10-01 | Overhead | 13620785 | 14305675 | 8327341
MCR002466 | HPR001 | 2020-11-01 | Labor | 29106322 | 36131038 | 41255444
MCR002467 | HPR001 | 2020-11-01 | Material | 55898896 | 69389912 | 69967764
MCR002468 | HPR001 | 2020-11-01 | Equipment | 12670581 | 15728584 | 15360126
MCR002469 | HPR001 | 2020-11-01 | Subcontract | 57311143 | 71143000 | 75646434
MCR002470 | HPR001 | 2020-11-01 | Overhead | 14068347 | 17463697 | 8929261
MCR002471 | HPR001 | 2020-12-01 | Labor | 29434821 | 24220197 | 24155370
MCR002472 | HPR001 | 2020-12-01 | Material | 56529781 | 46515059 | 45968733
MCR002473 | HPR001 | 2020-12-01 | Equipment | 12813583 | 10543550 | 11394230
MCR002474 | HPR001 | 2020-12-01 | Subcontract | 57957966 | 47690229 | 42037428
MCR002475 | HPR001 | 2020-12-01 | Overhead | 14227125 | 11706671 | 9488329
MCR002476 | HPR001 | 2021-01-01 | Labor | 29192148 | 29683796 | 34969067
MCR002477 | HPR001 | 2021-01-01 | Material | 56063725 | 57007938 | 54431741
MCR002478 | HPR001 | 2021-01-01 | Equipment | 12707942 | 12921967 | 11762317
MCR002479 | HPR001 | 2021-01-01 | Subcontract | 57480135 | 58448204 | 52494722
MCR002480 | HPR001 | 2021-01-01 | Overhead | 14109831 | 14347466 | 9045305
MCR002481 | HPR001 | 2021-02-01 | Labor | 28406920 | 21811333 | 17472127
MCR002482 | HPR001 | 2021-02-01 | Material | 54555689 | 41888817 | 38439181
MCR002483 | HPR001 | 2021-02-01 | Equipment | 12366117 | 9494922 | 10276354
MCR002484 | HPR001 | 2021-02-01 | Subcontract | 55934001 | 42947109 | 45762052
MCR002485 | HPR001 | 2021-02-01 | Overhead | 13730296 | 10542363 | 9528233
MCR002486 | HPR001 | 2021-03-01 | Labor | 27110564 | 31473680 | 30754534
MCR002487 | HPR001 | 2021-03-01 | Material | 52066029 | 60445423 | 66780884
MCR002488 | HPR001 | 2021-03-01 | Equipment | 11801786 | 13701140 | 16197079
MCR002489 | HPR001 | 2021-03-01 | Subcontract | 53381441 | 61972534 | 61843145
MCR002490 | HPR001 | 2021-03-01 | Overhead | 13103711 | 15212594 | 9251553
MCR002491 | HPR001 | 2021-04-01 | Labor | 25337976 | 11294960 | 14013892
MCR002492 | HPR001 | 2021-04-01 | Material | 48661760 | 21692050 | 21215592
MCR002493 | HPR001 | 2021-04-01 | Equipment | 11030142 | 4916928 | 3397895
MCR002494 | HPR001 | 2021-04-01 | Subcontract | 49891166 | 22240084 | 20439460
MCR002495 | HPR001 | 2021-04-01 | Overhead | 12246942 | 5459344 | 9252986
MCR002496 | HPR001 | 2021-05-01 | Labor | 23128442 | 21997768 | 20575481
MCR002497 | HPR001 | 2021-05-01 | Material | 44418335 | 42246867 | 47249589
MCR002498 | HPR001 | 2021-05-01 | Equipment | 10068287 | 9576081 | 10139439
MCR002499 | HPR001 | 2021-05-01 | Subcontract | 45540534 | 43314205 | 41777085
MCR002500 | HPR001 | 2021-05-01 | Overhead | 11178979 | 10632475 | 9226737
MCR002501 | HPR001 | 2021-06-01 | Labor | 20526980 | 15857055 | 19337570
MCR002502 | HPR001 | 2021-06-01 | Material | 39422210 | 30453586 | 30131645
MCR002503 | HPR001 | 2021-06-01 | Equipment | 8935817 | 6902902 | 8114986
MCR002504 | HPR001 | 2021-06-01 | Subcontract | 40418184 | 31222975 | 32771789
MCR002505 | HPR001 | 2021-06-01 | Overhead | 9921580 | 7664402 | 9274683
MCR002506 | HPR001 | 2021-07-01 | Labor | 17586376 | 18880854 | 45190169
MCR002507 | HPR001 | 2021-07-01 | Material | 33774758 | 36260813 | 49094445
MCR002508 | HPR001 | 2021-07-01 | Equipment | 7655711 | 8219224 | 7057376
MCR002509 | HPR001 | 2021-07-01 | Subcontract | 34628054 | 37176917 | 35264558
MCR002510 | HPR001 | 2021-07-01 | Overhead | 8500258 | 9125935 | 9596217
MCR002511 | HPR001 | 2021-08-01 | Labor | 14370493 | 14326180 | 34295013
MCR002512 | HPR001 | 2021-08-01 | Material | 27598632 | 27513530 | 50316160
MCR002513 | HPR001 | 2021-08-01 | Equipment | 6255771 | 6236481 | 6298391
MCR002514 | HPR001 | 2021-08-01 | Subcontract | 28295892 | 28208640 | 32491789
MCR002515 | HPR001 | 2021-08-01 | Overhead | 6945882 | 6924464 | 10114978
MCR002516 | HPR001 | 2021-09-01 | Labor | 10960153 | 17454218 | 14658121
MCR002517 | HPR001 | 2021-09-01 | Material | 21049050 | 33520949 | 32468070
MCR002518 | HPR001 | 2021-09-01 | Equipment | 4771180 | 7598180 | 8731694
MCR002519 | HPR001 | 2021-09-01 | Subcontract | 21580840 | 34367832 | 31462744
MCR002520 | HPR001 | 2021-09-01 | Overhead | 5297517 | 8436380 | 8879512
MCR002521 | HPR001 | 2021-10-01 | Labor | 7465005 | 14550887 | 17929600
MCR002522 | HPR001 | 2021-10-01 | Material | 14336595 | 27945081 | 31778585
MCR002523 | HPR001 | 2021-10-01 | Equipment | 3249670 | 6334301 | 6510246
MCR002524 | HPR001 | 2021-10-01 | Subcontract | 14698799 | 28651094 | 24361905
MCR002525 | HPR001 | 2021-10-01 | Overhead | 3608161 | 7033075 | 8998116
MCR002526 | HPR001 | 2021-11-01 | Labor | 4053282 | 9853012 | 9885877
MCR002527 | HPR001 | 2021-11-01 | Material | 7784357 | 18922779 | 19777604
MCR002528 | HPR001 | 2021-11-01 | Equipment | 1764477 | 4289219 | 4297919
MCR002529 | HPR001 | 2021-11-01 | Subcontract | 7981024 | 19400850 | 21510600
MCR002530 | HPR001 | 2021-11-01 | Overhead | 1959127 | 4762388 | 9430582
MCR002531 | HPR001 | 2021-12-01 | Labor | 1077009 | 8288247 | 8389425
MCR002532 | HPR001 | 2021-12-01 | Material | 2068404 | 15917637 | 18364237
MCR002533 | HPR001 | 2021-12-01 | Equipment | 468844 | 3608044 | 3302731
MCR002534 | HPR001 | 2021-12-01 | Subcontract | 2120661 | 16319785 | 17371814
MCR002535 | HPR001 | 2021-12-01 | Overhead | 520565 | 4006069 | 8665665
MCR002536 | HPR001 | 2022-01-01 | Labor | 0 | 9240620 | 10280205
MCR002537 | HPR001 | 2022-01-01 | Material | 0 | 17746675 | 19643100
MCR002538 | HPR001 | 2022-01-01 | Equipment | 0 | 4022632 | 4045226
MCR002539 | HPR001 | 2022-01-01 | Subcontract | 0 | 18195032 | 15513914
MCR002540 | HPR001 | 2022-01-01 | Overhead | 0 | 4466392 | 9198076
MCR002541 | HPR001 | 2022-02-01 | Labor | 0 | 5857279 | 5440031
MCR002542 | HPR001 | 2022-02-01 | Material | 0 | 11248946 | 13057898
MCR002543 | HPR001 | 2022-02-01 | Equipment | 0 | 2549794 | 2712720
MCR002544 | HPR001 | 2022-02-01 | Subcontract | 0 | 11533143 | 11695296
MCR002545 | HPR001 | 2022-02-01 | Overhead | 0 | 2831077 | 9387339
MCR002546 | HPR001 | 2022-03-01 | Labor | 0 | 2461657 | 2708886
MCR002547 | HPR001 | 2022-03-01 | Material | 0 | 4727630 | 4432939
MCR002548 | HPR001 | 2022-03-01 | Equipment | 0 | 1071610 | 1295289
MCR002549 | HPR001 | 2022-03-01 | Subcontract | 0 | 4847071 | 5185749
MCR002550 | HPR001 | 2022-03-01 | Overhead | 0 | 1189826 | 9058375
MCR002551 | HPR001 | 2022-04-01 | Labor | 0 | 1096416 | 1234175
MCR002552 | HPR001 | 2022-04-01 | Material | 0 | 2105674 | 1818037
MCR002553 | HPR001 | 2022-04-01 | Equipment | 0 | 477292 | 421062
MCR002554 | HPR001 | 2022-04-01 | Subcontract | 0 | 2158872 | 2058969
MCR002555 | HPR001 | 2022-04-01 | Overhead | 0 | 529945 | 9194154
MCR002556 | HPR002 | 2017-07-01 | Labor | 2478469 | 1009366 | 1029472
MCR002557 | HPR002 | 2017-07-01 | Material | 5759999 | 2345781 | 2091574
MCR002558 | HPR002 | 2017-07-01 | Equipment | 1251020 | 509482 | 533361
MCR002559 | HPR002 | 2017-07-01 | Subcontract | 8488336 | 3456907 | 3308737
MCR002560 | HPR002 | 2017-07-01 | Overhead | 1754900 | 714690 | 11343818
MCR002561 | HPR002 | 2017-08-01 | Labor | 7098113 | 2155232 | 2514778
MCR002562 | HPR002 | 2017-08-01 | Material | 16496122 | 5008791 | 5507736
MCR002563 | HPR002 | 2017-08-01 | Equipment | 3582808 | 1087864 | 1042493
MCR002564 | HPR002 | 2017-08-01 | Subcontract | 24309836 | 7381304 | 7834096
MCR002565 | HPR002 | 2017-08-01 | Overhead | 5025877 | 1526029 | 12141611
MCR002566 | HPR002 | 2017-09-01 | Labor | 11218778 | 6989420 | 7386922
MCR002567 | HPR002 | 2017-09-01 | Material | 26072609 | 16243518 | 15592703
MCR002568 | HPR002 | 2017-09-01 | Equipment | 5662735 | 3527945 | 3589165
MCR002569 | HPR002 | 2017-09-01 | Subcontract | 38422415 | 23937581 | 23185164
MCR002570 | HPR002 | 2017-09-01 | Overhead | 7943547 | 4948916 | 12969064
MCR002571 | HPR002 | 2017-10-01 | Labor | 14850036 | 8023663 | 10182555
MCR002572 | HPR002 | 2017-10-01 | Material | 34511708 | 18647114 | 18058015
MCR002573 | HPR002 | 2017-10-01 | Equipment | 7495630 | 4049984 | 4137855
MCR002574 | HPR002 | 2017-10-01 | Subcontract | 50858859 | 27479687 | 28168840
MCR002575 | HPR002 | 2017-10-01 | Overhead | 10514688 | 5681220 | 13716070
MCR002576 | HPR002 | 2017-11-01 | Labor | 18001857 | 11352140 | 13203698
MCR002577 | HPR002 | 2017-11-01 | Material | 41836588 | 26382545 | 26902128
MCR002578 | HPR002 | 2017-11-01 | Equipment | 9086528 | 5730050 | 6535798
MCR002579 | HPR002 | 2017-11-01 | Subcontract | 61653314 | 38879158 | 35407031
MCR002580 | HPR002 | 2017-11-01 | Overhead | 12746361 | 8037975 | 12779095
MCR002581 | HPR002 | 2017-12-01 | Labor | 20684647 | 13825396 | 15624399
MCR002582 | HPR002 | 2017-12-01 | Material | 48071432 | 32130428 | 27311789
MCR002583 | HPR002 | 2017-12-01 | Equipment | 10440680 | 6978438 | 7195593
MCR002584 | HPR002 | 2017-12-01 | Subcontract | 70841415 | 47349639 | 49854472
MCR002585 | HPR002 | 2017-12-01 | Overhead | 14645932 | 9789183 | 12504870
MCR002586 | HPR002 | 2018-01-01 | Labor | 22909292 | 17521204 | 20343120
MCR002587 | HPR002 | 2018-01-01 | Material | 53241539 | 40719543 | 47909495
MCR002588 | HPR002 | 2018-01-01 | Equipment | 11563580 | 8843916 | 9600942
MCR002589 | HPR002 | 2018-01-01 | Subcontract | 78460445 | 60007158 | 52108704
MCR002590 | HPR002 | 2018-01-01 | Overhead | 16221109 | 12406031 | 12535645
MCR002591 | HPR002 | 2018-02-01 | Labor | 24687210 | 25289047 | 26144989
MCR002592 | HPR002 | 2018-02-01 | Material | 57373448 | 58772127 | 61051648
MCR002593 | HPR002 | 2018-02-01 | Equipment | 12460993 | 12764774 | 13969074
MCR002594 | HPR002 | 2018-02-01 | Subcontract | 84549514 | 86610705 | 99895016
MCR002595 | HPR002 | 2018-02-01 | Overhead | 17479979 | 17906115 | 12689935
MCR002596 | HPR002 | 2018-03-01 | Labor | 26030417 | 12694419 | 14185089
MCR002597 | HPR002 | 2018-03-01 | Material | 60495081 | 29502021 | 29735569
MCR002598 | HPR002 | 2018-03-01 | Equipment | 13138984 | 6407572 | 6222725
MCR002599 | HPR002 | 2018-03-01 | Subcontract | 89149771 | 43476236 | 41841276
MCR002600 | HPR002 | 2018-03-01 | Overhead | 18431048 | 8988386 | 13493058
MCR002601 | HPR002 | 2018-04-01 | Labor | 26951597 | 15067250 | 20756118
MCR002602 | HPR002 | 2018-04-01 | Material | 62635917 | 35016515 | 32236415
MCR002603 | HPR002 | 2018-04-01 | Equipment | 13603954 | 7605270 | 7932185
MCR002604 | HPR002 | 2018-04-01 | Subcontract | 92304656 | 51602779 | 51768338
MCR002605 | HPR002 | 2018-04-01 | Overhead | 19083296 | 10668488 | 12086816
MCR002606 | HPR002 | 2018-05-01 | Labor | 27464191 | 25000177 | 29248473
MCR002607 | HPR002 | 2018-05-01 | Material | 63827193 | 58100789 | 61995399
MCR002608 | HPR002 | 2018-05-01 | Equipment | 13862688 | 12618965 | 10903220
MCR002609 | HPR002 | 2018-05-01 | Subcontract | 94060203 | 85621375 | 79176981
MCR002610 | HPR002 | 2018-05-01 | Overhead | 19446243 | 17701578 | 11786959
MCR002611 | HPR002 | 2018-06-01 | Labor | 27582503 | 20488543 | 21576524
MCR002612 | HPR002 | 2018-06-01 | Material | 64102153 | 47615681 | 44625393
MCR002613 | HPR002 | 2018-06-01 | Equipment | 13922407 | 10341695 | 13363736
MCR002614 | HPR002 | 2018-06-01 | Subcontract | 94465403 | 70169789 | 81679752
MCR002615 | HPR002 | 2018-06-01 | Overhead | 19530015 | 14507078 | 12397902
MCR002616 | HPR002 | 2018-07-01 | Labor | 27321834 | 23731021 | 26119452
MCR002617 | HPR002 | 2018-07-01 | Material | 63496354 | 55151249 | 61701026
MCR002618 | HPR002 | 2018-07-01 | Equipment | 13790833 | 11978352 | 9848243
MCR002619 | HPR002 | 2018-07-01 | Subcontract | 93572656 | 81274727 | 84232056
MCR002620 | HPR002 | 2018-07-01 | Overhead | 19345446 | 16802941 | 12628793
MCR002621 | HPR002 | 2018-08-01 | Labor | 26698642 | 13926212 | 15865957
MCR002622 | HPR002 | 2018-08-01 | Material | 62048047 | 32364726 | 31681483
MCR002623 | HPR002 | 2018-08-01 | Equipment | 13476274 | 7029326 | 9058935
MCR002624 | HPR002 | 2018-08-01 | Subcontract | 91438329 | 47694918 | 43293062
MCR002625 | HPR002 | 2018-08-01 | Overhead | 18904190 | 9860567 | 12919254
MCR002626 | HPR002 | 2018-09-01 | Labor | 25730750 | 16403251 | 19059774
MCR002627 | HPR002 | 2018-09-01 | Material | 59798650 | 38121402 | 39155549
MCR002628 | HPR002 | 2018-09-01 | Equipment | 12987726 | 8279623 | 8165326
MCR002629 | HPR002 | 2018-09-01 | Subcontract | 88123462 | 56178357 | 57477510
MCR002630 | HPR002 | 2018-09-01 | Overhead | 18218866 | 11614455 | 12657247
MCR002631 | HPR002 | 2018-10-01 | Labor | 24437612 | 17352888 | 18880673
MCR002632 | HPR002 | 2018-10-01 | Material | 56793377 | 40328374 | 40050676
MCR002633 | HPR002 | 2018-10-01 | Equipment | 12335007 | 8758958 | 11386130
MCR002634 | HPR002 | 2018-10-01 | Subcontract | 83694682 | 59430705 | 57614276
MCR002635 | HPR002 | 2018-10-01 | Overhead | 17303249 | 12286853 | 13203847
MCR002636 | HPR002 | 2018-11-01 | Labor | 22840664 | 10623750 | 11718100
MCR002637 | HPR002 | 2018-11-01 | Material | 53082048 | 24689755 | 26863880
MCR002638 | HPR002 | 2018-11-01 | Equipment | 11528940 | 5362391 | 4817566
MCR002639 | HPR002 | 2018-11-01 | Subcontract | 78225408 | 36384545 | 37248542
MCR002640 | HPR002 | 2018-11-01 | Overhead | 16172517 | 7522232 | 12867956
MCR002641 | HPR002 | 2018-12-01 | Labor | 20963805 | 16249865 | 18727292
MCR002642 | HPR002 | 2018-12-01 | Material | 48720198 | 37764930 | 39338936
MCR002643 | HPR002 | 2018-12-01 | Equipment | 10581586 | 8202201 | 8761471
MCR002644 | HPR002 | 2018-12-01 | Subcontract | 71797482 | 55653035 | 52969126
MCR002645 | HPR002 | 2018-12-01 | Overhead | 14843592 | 11505848 | 11388319
MCR002646 | HPR002 | 2019-01-01 | Labor | 18834055 | 21419092 | 26223523
MCR002647 | HPR002 | 2019-01-01 | Material | 43770628 | 49778291 | 52116839
MCR002648 | HPR002 | 2019-01-01 | Equipment | 9506584 | 10811394 | 10345106
MCR002649 | HPR002 | 2019-01-01 | Subcontract | 64503450 | 73356762 | 73029737
MCR002650 | HPR002 | 2019-01-01 | Overhead | 13335605 | 15165961 | 11853334
MCR002651 | HPR002 | 2019-02-01 | Labor | 16482533 | 26577441 | 25620989
MCR002652 | HPR002 | 2019-02-01 | Material | 38305655 | 61766374 | 57875558
MCR002653 | HPR002 | 2019-02-01 | Equipment | 8319642 | 13415097 | 16641640
MCR002654 | HPR002 | 2019-02-01 | Subcontract | 56449885 | 91023237 | 101351934
MCR002655 | HPR002 | 2019-02-01 | Overhead | 11670591 | 18818373 | 13026459
MCR002656 | HPR002 | 2019-03-01 | Labor | 13945934 | 18116220 | 21197371
MCR002657 | HPR002 | 2019-03-01 | Material | 32410560 | 42102369 | 46851059
MCR002658 | HPR002 | 2019-03-01 | Equipment | 7039280 | 9144253 | 8017818
MCR002659 | HPR002 | 2019-03-01 | Subcontract | 47762462 | 62044987 | 46983771
MCR002660 | HPR002 | 2019-03-01 | Overhead | 9874531 | 12827336 | 12161569
MCR002661 | HPR002 | 2019-04-01 | Labor | 11268948 | 12470462 | 12965447
MCR002662 | HPR002 | 2019-04-01 | Material | 26189206 | 28981542 | 27694015
MCR002663 | HPR002 | 2019-04-01 | Equipment | 5688058 | 6294529 | 6531217
MCR002664 | HPR002 | 2019-04-01 | Subcontract | 38594240 | 42709221 | 49272905
MCR002665 | HPR002 | 2019-04-01 | Overhead | 7979070 | 8829812 | 12084525
MCR002666 | HPR002 | 2019-05-01 | Labor | 8508572 | 25406173 | 30272861
MCR002667 | HPR002 | 2019-05-01 | Material | 19774049 | 59044329 | 58577606
MCR002668 | HPR002 | 2019-05-01 | Equipment | 4294745 | 12823894 | 11884928
MCR002669 | HPR002 | 2019-05-01 | Subcontract | 29140418 | 87011841 | 80977159
MCR002670 | HPR002 | 2019-05-01 | Overhead | 6024563 | 17989046 | 13196724
MCR002671 | HPR002 | 2019-06-01 | Labor | 5742851 | 15031462 | 17113503
MCR002672 | HPR002 | 2019-06-01 | Material | 13346472 | 34933345 | 37215279
MCR002673 | HPR002 | 2019-06-01 | Equipment | 2898733 | 7587206 | 8842705
MCR002674 | HPR002 | 2019-06-01 | Subcontract | 19668293 | 51480214 | 62987660
MCR002675 | HPR002 | 2019-06-01 | Overhead | 4066272 | 10643149 | 13123071
MCR002676 | HPR002 | 2019-07-01 | Labor | 3092911 | 5607880 | 6186738
MCR002677 | HPR002 | 2019-07-01 | Material | 7187972 | 13032798 | 13592559
MCR002678 | HPR002 | 2019-07-01 | Equipment | 1561162 | 2830606 | 3546981
MCR002679 | HPR002 | 2019-07-01 | Subcontract | 10592697 | 19206039 | 16021332
MCR002680 | HPR002 | 2019-07-01 | Overhead | 2189961 | 3970705 | 12013289
MCR002681 | HPR002 | 2019-08-01 | Labor | 816302 | 5817881 | 7267504
MCR002682 | HPR002 | 2019-08-01 | Material | 1897098 | 13520843 | 14198330
MCR002683 | HPR002 | 2019-08-01 | Equipment | 412032 | 2936605 | 2697750
MCR002684 | HPR002 | 2019-08-01 | Subcontract | 2795696 | 19925258 | 18577202
MCR002685 | HPR002 | 2019-08-01 | Overhead | 577989 | 4119398 | 14142404
MCR002686 | HPR002 | 2019-09-01 | Labor | 0 | 9663729 | 10704110
MCR002687 | HPR002 | 2019-09-01 | Material | 0 | 22458652 | 20225387
MCR002688 | HPR002 | 2019-09-01 | Equipment | 0 | 4877816 | 4953894
MCR002689 | HPR002 | 2019-09-01 | Subcontract | 0 | 33096637 | 33636801
MCR002690 | HPR002 | 2019-09-01 | Overhead | 0 | 6842482 | 12799071
MCR002691 | HPR002 | 2019-10-01 | Labor | 0 | 14775762 | 16236342
MCR002692 | HPR002 | 2019-10-01 | Material | 0 | 34339092 | 35132217
MCR002693 | HPR002 | 2019-10-01 | Equipment | 0 | 7458140 | 7998586
MCR002694 | HPR002 | 2019-10-01 | Subcontract | 0 | 50604482 | 53460044
MCR002695 | HPR002 | 2019-10-01 | Overhead | 0 | 10462098 | 13036149
MCR002696 | HPR002 | 2019-11-01 | Labor | 0 | 9987272 | 12273299
MCR002697 | HPR002 | 2019-11-01 | Material | 0 | 23210571 | 26085775
MCR002698 | HPR002 | 2019-11-01 | Equipment | 0 | 5041126 | 5578636
MCR002699 | HPR002 | 2019-11-01 | Subcontract | 0 | 34204716 | 33443687
MCR002700 | HPR002 | 2019-11-01 | Overhead | 0 | 7071569 | 11869913
MCR002701 | HPR002 | 2019-12-01 | Labor | 0 | 13762821 | 17417032
MCR002702 | HPR002 | 2019-12-01 | Material | 0 | 31985002 | 34151762
MCR002703 | HPR002 | 2019-12-01 | Equipment | 0 | 6946853 | 8156437
MCR002704 | HPR002 | 2019-12-01 | Subcontract | 0 | 47135330 | 56918513
MCR002705 | HPR002 | 2019-12-01 | Overhead | 0 | 9744877 | 12896229
MCR002706 | HPR002 | 2020-01-01 | Labor | 0 | 6240745 | 5882809
MCR002707 | HPR002 | 2020-01-01 | Material | 0 | 14503585 | 14822850
MCR002708 | HPR002 | 2020-01-01 | Equipment | 0 | 3150047 | 2947743
MCR002709 | HPR002 | 2020-01-01 | Subcontract | 0 | 21373495 | 18356820
MCR002710 | HPR002 | 2020-01-01 | Overhead | 0 | 4418810 | 12425904
MCR002711 | HPR002 | 2020-02-01 | Labor | 0 | 5300216 | 6194052
MCR002712 | HPR002 | 2020-02-01 | Material | 0 | 12317781 | 13789814
MCR002713 | HPR002 | 2020-02-01 | Equipment | 0 | 2675311 | 3159765
MCR002714 | HPR002 | 2020-02-01 | Subcontract | 0 | 18152341 | 17297591
MCR002715 | HPR002 | 2020-02-01 | Overhead | 0 | 3752861 | 12159035
MCR002716 | HPR002 | 2020-03-01 | Labor | 0 | 3061212 | 3769039
MCR002717 | HPR002 | 2020-03-01 | Material | 0 | 7114302 | 7097278
MCR002718 | HPR002 | 2020-03-01 | Equipment | 0 | 1545162 | 1930260
MCR002719 | HPR002 | 2020-03-01 | Subcontract | 0 | 10484132 | 11074978
MCR002720 | HPR002 | 2020-03-01 | Overhead | 0 | 2167516 | 12001170
MCR002721 | HPR002 | 2020-04-01 | Labor | 0 | 4619116 | 5439806
MCR002722 | HPR002 | 2020-04-01 | Material | 0 | 10734895 | 9795065
MCR002723 | HPR002 | 2020-04-01 | Equipment | 0 | 2331522 | 2998462
MCR002724 | HPR002 | 2020-04-01 | Subcontract | 0 | 15819689 | 15928953
MCR002725 | HPR002 | 2020-04-01 | Overhead | 0 | 3270602 | 11984379
MCR002726 | HPR002 | 2020-05-01 | Labor | 0 | 793817 | 1052045
MCR002727 | HPR002 | 2020-05-01 | Material | 0 | 1844842 | 2474889
MCR002728 | HPR002 | 2020-05-01 | Equipment | 0 | 400683 | 428590
MCR002729 | HPR002 | 2020-05-01 | Subcontract | 0 | 2718687 | 2561581
MCR002730 | HPR002 | 2020-05-01 | Overhead | 0 | 562068 | 13384348
MCR002731 | HPR002 | 2020-06-01 | Labor | 0 | 288380 | 390231
MCR002732 | HPR002 | 2020-06-01 | Material | 0 | 670199 | 767631
MCR002733 | HPR002 | 2020-06-01 | Equipment | 0 | 145561 | 155931
MCR002734 | HPR002 | 2020-06-01 | Subcontract | 0 | 987652 | 1102441
MCR002735 | HPR002 | 2020-06-01 | Overhead | 0 | 204190 | 11299699
MCR002736 | HPR003 | 2020-03-01 | Labor | 5987637 | 3546275 | 3184133
MCR002737 | HPR003 | 2020-03-01 | Material | 18252120 | 10810112 | 10911534
MCR002738 | HPR003 | 2020-03-01 | Equipment | 4728837 | 2800730 | 3002554
MCR002739 | HPR003 | 2020-03-01 | Subcontract | 15177395 | 8989057 | 9000425
MCR002740 | HPR003 | 2020-03-01 | Overhead | 4756570 | 2817155 | 22793472
MCR002741 | HPR003 | 2020-04-01 | Labor | 16775074 | 10572285 | 9748201
MCR002742 | HPR003 | 2020-04-01 | Material | 51135474 | 32227506 | 37368772
MCR002743 | HPR003 | 2020-04-01 | Equipment | 13248396 | 8349640 | 9101742
MCR002744 | HPR003 | 2020-04-01 | Subcontract | 42521270 | 26798510 | 22079481
MCR002745 | HPR003 | 2020-04-01 | Overhead | 13326094 | 8398608 | 24703853
MCR002746 | HPR003 | 2020-05-01 | Labor | 25817130 | 13918456 | 14571603
MCR002747 | HPR003 | 2020-05-01 | Material | 78698381 | 42427643 | 38075802
MCR002748 | HPR003 | 2020-05-01 | Equipment | 20389511 | 10992334 | 10931308
MCR002749 | HPR003 | 2020-05-01 | Subcontract | 65440971 | 35280347 | 36236243
MCR002750 | HPR003 | 2020-05-01 | Overhead | 20509090 | 11056801 | 22569146
MCR002751 | HPR003 | 2020-06-01 | Labor | 33164631 | 16981139 | 14814996
MCR002752 | HPR003 | 2020-06-01 | Material | 101095775 | 51763623 | 46014766
MCR002753 | HPR003 | 2020-06-01 | Equipment | 26192324 | 13411140 | 12868133
MCR002754 | HPR003 | 2020-06-01 | Subcontract | 84065335 | 43043602 | 41852944
MCR002755 | HPR003 | 2020-06-01 | Overhead | 26345934 | 13489792 | 24971883
MCR002756 | HPR003 | 2020-07-01 | Labor | 38871669 | 20390932 | 20067046
MCR002757 | HPR003 | 2020-07-01 | Material | 118492545 | 62157698 | 71730933
MCR002758 | HPR003 | 2020-07-01 | Equipment | 30699553 | 16104081 | 16577367
MCR002759 | HPR003 | 2020-07-01 | Subcontract | 98531472 | 51686707 | 41702193
MCR002760 | HPR003 | 2020-07-01 | Overhead | 30879596 | 16198526 | 22715720
MCR002761 | HPR003 | 2020-08-01 | Labor | 42996113 | 34386617 | 34303667
MCR002762 | HPR003 | 2020-08-01 | Material | 131065093 | 104820756 | 108946523
MCR002763 | HPR003 | 2020-08-01 | Equipment | 33956902 | 27157408 | 29295388
MCR002764 | HPR003 | 2020-08-01 | Subcontract | 108986067 | 87162811 | 96012666
MCR002765 | HPR003 | 2020-08-01 | Overhead | 34156049 | 27316677 | 22128839
MCR002766 | HPR003 | 2020-09-01 | Labor | 45600254 | 39860576 | 37979606
MCR002767 | HPR003 | 2020-09-01 | Material | 139003297 | 121507030 | 124244012
MCR002768 | HPR003 | 2020-09-01 | Equipment | 36013566 | 31480558 | 31914332
MCR002769 | HPR003 | 2020-09-01 | Subcontract | 115587013 | 101038141 | 99513370
MCR002770 | HPR003 | 2020-09-01 | Overhead | 36224774 | 31665182 | 22933000
MCR002771 | HPR003 | 2020-10-01 | Labor | 46751629 | 37984823 | 41843016
MCR002772 | HPR003 | 2020-10-01 | Material | 142513034 | 115789171 | 124083754
MCR002773 | HPR003 | 2020-10-01 | Equipment | 36922883 | 29999151 | 30075552
MCR002774 | HPR003 | 2020-10-01 | Subcontract | 118505505 | 96283504 | 89840023
MCR002775 | HPR003 | 2020-10-01 | Overhead | 37139425 | 30175087 | 23994667
MCR002776 | HPR003 | 2020-11-01 | Labor | 46524106 | 29316376 | 27420333
MCR002777 | HPR003 | 2020-11-01 | Material | 141819475 | 89365137 | 79151803
MCR002778 | HPR003 | 2020-11-01 | Equipment | 36743193 | 23153100 | 25305812
MCR002779 | HPR003 | 2020-11-01 | Subcontract | 117928782 | 74310822 | 64191454
MCR002780 | HPR003 | 2020-11-01 | Overhead | 36958681 | 23288886 | 22955772
MCR002781 | HPR003 | 2020-12-01 | Labor | 44999340 | 38206517 | 40539464
MCR002782 | HPR003 | 2020-12-01 | Material | 137171532 | 116464963 | 121815285
MCR002783 | HPR003 | 2020-12-01 | Equipment | 35538984 | 30174238 | 30596724
MCR002784 | HPR003 | 2020-12-01 | Subcontract | 114063824 | 96845452 | 92306481
MCR002785 | HPR003 | 2020-12-01 | Overhead | 35747409 | 30351201 | 25225245
MCR002786 | HPR003 | 2021-01-01 | Labor | 42268799 | 45093643 | 44667897
MCR002787 | HPR003 | 2021-01-01 | Material | 128848020 | 137458995 | 152758284
MCR002788 | HPR003 | 2021-01-01 | Equipment | 33382493 | 35613461 | 40679755
MCR002789 | HPR003 | 2021-01-01 | Subcontract | 107142479 | 114302862 | 115243251
MCR002790 | HPR003 | 2021-01-01 | Overhead | 33578271 | 35822323 | 23149653
MCR002791 | HPR003 | 2021-02-01 | Labor | 38436677 | 31840140 | 35351873
MCR002792 | HPR003 | 2021-02-01 | Material | 117166558 | 97058327 | 81733689
MCR002793 | HPR003 | 2021-02-01 | Equipment | 30356010 | 25146284 | 21168953
MCR002794 | HPR003 | 2021-02-01 | Subcontract | 97428858 | 80708029 | 76395894
MCR002795 | HPR003 | 2021-02-01 | Overhead | 30534039 | 25293760 | 25584020
MCR002796 | HPR003 | 2021-03-01 | Labor | 33624325 | 57300810 | 49100385
MCR002797 | HPR003 | 2021-03-01 | Material | 102497062 | 174670113 | 177577473
MCR002798 | HPR003 | 2021-03-01 | Equipment | 26555375 | 45254276 | 46052901
MCR002799 | HPR003 | 2021-03-01 | Subcontract | 85230563 | 145245452 | 130118429
MCR002800 | HPR003 | 2021-03-01 | Overhead | 26711114 | 45519679 | 23567983
MCR002801 | HPR003 | 2021-04-01 | Labor | 27977406 | 30387749 | 39853020
MCR002802 | HPR003 | 2021-04-01 | Material | 85283553 | 92631003 | 118667734
MCR002803 | HPR003 | 2021-04-01 | Equipment | 22095626 | 23999234 | 23973772
MCR002804 | HPR003 | 2021-04-01 | Subcontract | 70916816 | 77026525 | 80061285
MCR002805 | HPR003 | 2021-04-01 | Overhead | 22225210 | 24139983 | 22854052
MCR002806 | HPR003 | 2021-05-01 | Labor | 21678517 | 24728050 | 24222447
MCR002807 | HPR003 | 2021-05-01 | Material | 66082644 | 75378539 | 70197168
MCR002808 | HPR003 | 2021-05-01 | Equipment | 17120973 | 19529393 | 22785058
MCR002809 | HPR003 | 2021-05-01 | Subcontract | 54950463 | 62680385 | 53464722
MCR002810 | HPR003 | 2021-05-01 | Overhead | 17221382 | 19643926 | 25508858
MCR002811 | HPR003 | 2021-06-01 | Labor | 14972543 | 37995458 | 41671396
MCR002812 | HPR003 | 2021-06-01 | Material | 45640816 | 115821589 | 115777596
MCR002813 | HPR003 | 2021-06-01 | Equipment | 11824817 | 30007550 | 32033855
MCR002814 | HPR003 | 2021-06-01 | Subcontract | 37952234 | 96310461 | 94551238
MCR002815 | HPR003 | 2021-06-01 | Overhead | 11894166 | 30183535 | 23903993
MCR002816 | HPR003 | 2021-07-01 | Labor | 8229725 | 21278894 | 22336974
MCR002817 | HPR003 | 2021-07-01 | Material | 25086678 | 64864473 | 70135374
MCR002818 | HPR003 | 2021-07-01 | Equipment | 6499563 | 16805364 | 13588031
MCR002819 | HPR003 | 2021-07-01 | Subcontract | 20860614 | 53937502 | 62093708
MCR002820 | HPR003 | 2021-07-01 | Overhead | 6537681 | 16903922 | 26526909
MCR002821 | HPR003 | 2021-08-01 | Labor | 2208602 | 14753750 | 15924887
MCR002822 | HPR003 | 2021-08-01 | Material | 6732483 | 44973871 | 45035095
MCR002823 | HPR003 | 2021-08-01 | Equipment | 1744280 | 11652022 | 15454958
MCR002824 | HPR003 | 2021-08-01 | Subcontract | 5598339 | 37397642 | 31801686
MCR002825 | HPR003 | 2021-08-01 | Overhead | 1754510 | 11720358 | 23363609
MCR002826 | HPR003 | 2021-09-01 | Labor | 0 | 11086236 | 13617140
MCR002827 | HPR003 | 2021-09-01 | Material | 0 | 33794183 | 33601523
MCR002828 | HPR003 | 2021-09-01 | Equipment | 0 | 8755541 | 8280505
MCR002829 | HPR003 | 2021-09-01 | Subcontract | 0 | 28101266 | 26170228
MCR002830 | HPR003 | 2021-09-01 | Overhead | 0 | 8806889 | 23611833
MCR002831 | HPR003 | 2021-10-01 | Labor | 0 | 9785081 | 9349849
MCR002832 | HPR003 | 2021-10-01 | Material | 0 | 29827873 | 34581167
MCR002833 | HPR003 | 2021-10-01 | Equipment | 0 | 7727932 | 9197649
MCR002834 | HPR003 | 2021-10-01 | Subcontract | 0 | 24803115 | 25196385
MCR002835 | HPR003 | 2021-10-01 | Overhead | 0 | 7773254 | 21635923
MCR002836 | HPR003 | 2021-11-01 | Labor | 0 | 6259514 | 7102488
MCR002837 | HPR003 | 2021-11-01 | Material | 0 | 19080882 | 19355216
MCR002838 | HPR003 | 2021-11-01 | Equipment | 0 | 4943556 | 4856023
MCR002839 | HPR003 | 2021-11-01 | Subcontract | 0 | 15866545 | 14961431
MCR002840 | HPR003 | 2021-11-01 | Overhead | 0 | 4972548 | 24208883
MCR002841 | HPR003 | 2021-12-01 | Labor | 0 | 1210856 | 1196119
MCR002842 | HPR003 | 2021-12-01 | Material | 0 | 3691054 | 4038492
MCR002843 | HPR003 | 2021-12-01 | Equipment | 0 | 956294 | 1414784
MCR002844 | HPR003 | 2021-12-01 | Subcontract | 0 | 3069265 | 2904114
MCR002845 | HPR003 | 2021-12-01 | Overhead | 0 | 961902 | 24841618
MCR002846 | HPR004 | 2016-02-01 | Labor | 1514045 | 920786 | 946337
MCR002847 | HPR004 | 2016-02-01 | Material | 3553210 | 2160930 | 2220189
MCR002848 | HPR004 | 2016-02-01 | Equipment | 730810 | 444451 | 481489
MCR002849 | HPR004 | 2016-02-01 | Subcontract | 5795729 | 3524746 | 3571833
MCR002850 | HPR004 | 2016-02-01 | Overhead | 1355709 | 824492 | 9433461
MCR002851 | HPR004 | 2016-03-01 | Labor | 4336090 | 2195884 | 2212503
MCR002852 | HPR004 | 2016-03-01 | Material | 10176077 | 5153370 | 5586917
MCR002853 | HPR004 | 2016-03-01 | Equipment | 2092975 | 1059925 | 1137800
MCR002854 | HPR004 | 2016-03-01 | Subcontract | 16598452 | 8405790 | 8251664
MCR002855 | HPR004 | 2016-03-01 | Overhead | 3882631 | 1966242 | 9956609
MCR002856 | HPR004 | 2016-04-01 | Labor | 6853319 | 5961424 | 7176291
MCR002857 | HPR004 | 2016-04-01 | Material | 16083591 | 13990463 | 13618844
MCR002858 | HPR004 | 2016-04-01 | Equipment | 3308009 | 2877502 | 2865764
MCR002859 | HPR004 | 2016-04-01 | Subcontract | 26234344 | 22820190 | 24200759
MCR002860 | HPR004 | 2016-04-01 | Overhead | 6136613 | 5337990 | 9012179
MCR002861 | HPR004 | 2016-05-01 | Labor | 9071580 | 4771153 | 4489617
MCR002862 | HPR004 | 2016-05-01 | Material | 21289476 | 11197096 | 11919978
MCR002863 | HPR004 | 2016-05-01 | Equipment | 4378734 | 2302974 | 2381541
MCR002864 | HPR004 | 2016-05-01 | Subcontract | 34725792 | 18263862 | 18096916
MCR002865 | HPR004 | 2016-05-01 | Overhead | 8122892 | 4272195 | 9530422
MCR002866 | HPR004 | 2016-06-01 | Labor | 10996962 | 6316605 | 7501541
MCR002867 | HPR004 | 2016-06-01 | Material | 25808025 | 14824012 | 12849564
MCR002868 | HPR004 | 2016-06-01 | Equipment | 5308091 | 3048943 | 3226426
MCR002869 | HPR004 | 2016-06-01 | Subcontract | 42096110 | 24179814 | 24410655
MCR002870 | HPR004 | 2016-06-01 | Overhead | 9846922 | 5656027 | 9686775
MCR002871 | HPR004 | 2016-07-01 | Labor | 12635823 | 7725891 | 9258109
MCR002872 | HPR004 | 2016-07-01 | Material | 29654157 | 18131371 | 20725929
MCR002873 | HPR004 | 2016-07-01 | Equipment | 6099148 | 3729188 | 3790616
MCR002874 | HPR004 | 2016-07-01 | Subcontract | 48369630 | 29574529 | 23930316
MCR002875 | HPR004 | 2016-07-01 | Overhead | 11314393 | 6917933 | 9832585
MCR002876 | HPR004 | 2016-08-01 | Labor | 13994812 | 6278779 | 5749786
MCR002877 | HPR004 | 2016-08-01 | Material | 32843476 | 14735241 | 14030606
MCR002878 | HPR004 | 2016-08-01 | Equipment | 6755115 | 3030685 | 3030189
MCR002879 | HPR004 | 2016-08-01 | Subcontract | 53571809 | 24035017 | 27109350
MCR002880 | HPR004 | 2016-08-01 | Overhead | 12531262 | 5622157 | 9954377
MCR002881 | HPR004 | 2016-09-01 | Labor | 15080905 | 8874505 | 10255765
MCR002882 | HPR004 | 2016-09-01 | Material | 35392356 | 20826974 | 21572302
MCR002883 | HPR004 | 2016-09-01 | Equipment | 7279358 | 4283609 | 4696474
MCR002884 | HPR004 | 2016-09-01 | Subcontract | 57729349 | 33971393 | 38475027
MCR002885 | HPR004 | 2016-09-01 | Overhead | 13503774 | 7946426 | 9374456
MCR002886 | HPR004 | 2016-10-01 | Labor | 15901443 | 6267616 | 7874360
MCR002887 | HPR004 | 2016-10-01 | Material | 37318019 | 14709042 | 14238188
MCR002888 | HPR004 | 2016-10-01 | Equipment | 7675421 | 3025297 | 2743223
MCR002889 | HPR004 | 2016-10-01 | Subcontract | 60870347 | 23992284 | 25762930
MCR002890 | HPR004 | 2016-10-01 | Overhead | 14238501 | 5612161 | 9628316
MCR002891 | HPR004 | 2016-11-01 | Labor | 16464173 | 9105407 | 10345046
MCR002892 | HPR004 | 2016-11-01 | Material | 38638652 | 21368863 | 21932666
MCR002893 | HPR004 | 2016-11-01 | Equipment | 7947043 | 4395062 | 5078866
MCR002894 | HPR004 | 2016-11-01 | Subcontract | 63024463 | 34855283 | 39568629
MCR002895 | HPR004 | 2016-11-01 | Overhead | 14742382 | 8153182 | 9476440
MCR002896 | HPR004 | 2016-12-01 | Labor | 16777306 | 12351370 | 13351033
MCR002897 | HPR004 | 2016-12-01 | Material | 39373522 | 28986593 | 30533617
MCR002898 | HPR004 | 2016-12-01 | Equipment | 8098188 | 5961846 | 6515089
MCR002899 | HPR004 | 2016-12-01 | Subcontract | 64223128 | 47280751 | 48989452
MCR002900 | HPR004 | 2016-12-01 | Overhead | 15022768 | 11059688 | 9713779
MCR002901 | HPR004 | 2017-01-01 | Labor | 16849580 | 9812358 | 10637651
MCR002902 | HPR004 | 2017-01-01 | Material | 39543138 | 23027957 | 19532685
MCR002903 | HPR004 | 2017-01-01 | Equipment | 8133075 | 4736298 | 4563701
MCR002904 | HPR004 | 2017-01-01 | Subcontract | 64499794 | 37561472 | 41858137
MCR002905 | HPR004 | 2017-01-01 | Overhead | 15087484 | 8786201 | 9383323
MCR002906 | HPR004 | 2017-02-01 | Labor | 16690343 | 18040220 | 19166482
MCR002907 | HPR004 | 2017-02-01 | Material | 39169435 | 42337370 | 40046096
MCR002908 | HPR004 | 2017-02-01 | Equipment | 8056213 | 8707781 | 8530761
MCR002909 | HPR004 | 2017-02-01 | Subcontract | 63890237 | 69057533 | 74156942
MCR002910 | HPR004 | 2017-02-01 | Overhead | 14944900 | 16153609 | 9190063
MCR002911 | HPR004 | 2017-03-01 | Labor | 16309648 | 12309763 | 12840445
MCR002912 | HPR004 | 2017-03-01 | Material | 38276008 | 28888949 | 33223573
MCR002913 | HPR004 | 2017-03-01 | Equipment | 7872456 | 5941763 | 6705165
MCR002914 | HPR004 | 2017-03-01 | Subcontract | 62432945 | 47121481 | 40622530
MCR002915 | HPR004 | 2017-03-01 | Overhead | 14604017 | 11022432 | 9586656
MCR002916 | HPR004 | 2017-04-01 | Labor | 15718382 | 12384611 | 16707882
MCR002917 | HPR004 | 2017-04-01 | Material | 36888407 | 29064605 | 27189574
MCR002918 | HPR004 | 2017-04-01 | Equipment | 7587060 | 5977892 | 5520194
MCR002919 | HPR004 | 2017-04-01 | Subcontract | 60169596 | 47407997 | 52112893
MCR002920 | HPR004 | 2017-04-01 | Overhead | 14074585 | 11089453 | 10062360
MCR002921 | HPR004 | 2017-05-01 | Labor | 14928431 | 17430623 | 34613061
MCR002922 | HPR004 | 2017-05-01 | Material | 35034523 | 40906748 | 60959033
MCR002923 | HPR004 | 2017-05-01 | Equipment | 7205761 | 8413536 | 8608518
MCR002924 | HPR004 | 2017-05-01 | Subcontract | 57145680 | 66724011 | 70674110
MCR002925 | HPR004 | 2017-05-01 | Overhead | 13367245 | 15607763 | 9388571
MCR002926 | HPR004 | 2017-06-01 | Labor | 13952889 | 14120777 | 28002722
MCR002927 | HPR004 | 2017-06-01 | Material | 32745090 | 33139095 | 39629254
MCR002928 | HPR004 | 2017-06-01 | Equipment | 6734879 | 6815917 | 8260181
MCR002929 | HPR004 | 2017-06-01 | Subcontract | 53411328 | 54054000 | 52231524
MCR002930 | HPR004 | 2017-06-01 | Overhead | 12493723 | 12644054 | 10180970
MCR002931 | HPR004 | 2017-07-01 | Labor | 12806354 | 12011755 | 16032068
MCR002932 | HPR004 | 2017-07-01 | Material | 30054365 | 28189575 | 28485327
MCR002933 | HPR004 | 2017-07-01 | Equipment | 6181462 | 5797919 | 5395914
MCR002934 | HPR004 | 2017-07-01 | Subcontract | 49022421 | 45980715 | 43390127
MCR002935 | HPR004 | 2017-07-01 | Overhead | 11467091 | 10755590 | 9459194
MCR002936 | HPR004 | 2017-08-01 | Labor | 11505334 | 6057955 | 5626455
MCR002937 | HPR004 | 2017-08-01 | Material | 27001090 | 14217003 | 15847162
MCR002938 | HPR004 | 2017-08-01 | Equipment | 5553476 | 2924096 | 2993172
MCR002939 | HPR004 | 2017-08-01 | Subcontract | 44042147 | 23189707 | 26614669
MCR002940 | HPR004 | 2017-08-01 | Overhead | 10302129 | 5424426 | 9696311
MCR002941 | HPR004 | 2017-09-01 | Labor | 10068838 | 12014999 | 13291360
MCR002942 | HPR004 | 2017-09-01 | Material | 23629874 | 28197187 | 28006216
MCR002943 | HPR004 | 2017-09-01 | Equipment | 4860098 | 5799485 | 5882500
MCR002944 | HPR004 | 2017-09-01 | Subcontract | 38543274 | 45993131 | 40880819
MCR002945 | HPR004 | 2017-09-01 | Overhead | 9015859 | 10758494 | 9552520
MCR002946 | HPR004 | 2017-10-01 | Labor | 8519282 | 13214010 | 14071499
MCR002947 | HPR004 | 2017-10-01 | Material | 19993327 | 31011065 | 34707367
MCR002948 | HPR004 | 2017-10-01 | Equipment | 4112147 | 6378232 | 6944518
MCR002949 | HPR004 | 2017-10-01 | Subcontract | 32611611 | 50582917 | 53800821
MCR002950 | HPR004 | 2017-10-01 | Overhead | 7628353 | 11832115 | 9420111
MCR002951 | HPR004 | 2017-11-01 | Labor | 6883967 | 10315295 | 12170924
MCR002952 | HPR004 | 2017-11-01 | Material | 16155516 | 24208267 | 19910227
MCR002953 | HPR004 | 2017-11-01 | Equipment | 3322802 | 4979060 | 5025391
MCR002954 | HPR004 | 2017-11-01 | Subcontract | 26351663 | 39486705 | 44757079
MCR002955 | HPR004 | 2017-11-01 | Overhead | 6164056 | 9236542 | 9861673
MCR002956 | HPR004 | 2017-12-01 | Labor | 5197710 | 11999360 | 14202100
MCR002957 | HPR004 | 2017-12-01 | Material | 12198155 | 28160485 | 33414688
MCR002958 | HPR004 | 2017-12-01 | Equipment | 2508868 | 5791936 | 5962810
MCR002959 | HPR004 | 2017-12-01 | Subcontract | 19896713 | 45933266 | 42629885
MCR002960 | HPR004 | 2017-12-01 | Overhead | 4654144 | 10744491 | 9523583
MCR002961 | HPR004 | 2018-01-01 | Labor | 3508189 | 16043231 | 18686839
MCR002962 | HPR004 | 2018-01-01 | Material | 8233131 | 37650771 | 34897157
MCR002963 | HPR004 | 2018-01-01 | Equipment | 1693357 | 7743860 | 8242122
MCR002964 | HPR004 | 2018-01-01 | Subcontract | 13429264 | 61413107 | 103718812
MCR002965 | HPR004 | 2018-01-01 | Overhead | 3141309 | 14365461 | 10300993
MCR002966 | HPR004 | 2018-02-01 | Labor | 1889395 | 8192181 | 8062265
MCR002967 | HPR004 | 2018-02-01 | Material | 4434094 | 19225675 | 18292914
MCR002968 | HPR004 | 2018-02-01 | Equipment | 911987 | 3954260 | 4108792
MCR002969 | HPR004 | 2018-02-01 | Subcontract | 7232561 | 31359476 | 44890922
MCR002970 | HPR004 | 2018-02-01 | Overhead | 1691806 | 7335459 | 9117404
MCR002971 | HPR004 | 2018-03-01 | Labor | 498662 | 7046173 | 9129449
MCR002972 | HPR004 | 2018-03-01 | Material | 1170276 | 16536187 | 18151877
MCR002973 | HPR004 | 2018-03-01 | Equipment | 240698 | 3401097 | 3662138
MCR002974 | HPR004 | 2018-03-01 | Subcontract | 1908866 | 26972584 | 61073481
MCR002975 | HPR004 | 2018-03-01 | Overhead | 446513 | 6309298 | 9572377
MCR002976 | HPR004 | 2018-04-01 | Labor | 0 | 8685205 | 10473865
MCR002977 | HPR004 | 2018-04-01 | Material | 0 | 20382719 | 19648609
MCR002978 | HPR004 | 2018-04-01 | Equipment | 0 | 4192236 | 4729627
MCR002979 | HPR004 | 2018-04-01 | Subcontract | 0 | 33246759 | 36540323
MCR002980 | HPR004 | 2018-04-01 | Overhead | 0 | 7776923 | 9363878
MCR002981 | HPR004 | 2018-05-01 | Labor | 0 | 5274731 | 5743288
MCR002982 | HPR004 | 2018-05-01 | Material | 0 | 12378910 | 13395513
MCR002983 | HPR004 | 2018-05-01 | Equipment | 0 | 2546045 | 2414739
MCR002984 | HPR004 | 2018-05-01 | Subcontract | 0 | 20191547 | 33273711
MCR002985 | HPR004 | 2018-05-01 | Overhead | 0 | 4723111 | 9527419
MCR002986 | HPR004 | 2018-06-01 | Labor | 0 | 4998164 | 5883691
MCR002987 | HPR004 | 2018-06-01 | Material | 0 | 11729853 | 13396889
MCR002988 | HPR004 | 2018-06-01 | Equipment | 0 | 2412549 | 2522049
MCR002989 | HPR004 | 2018-06-01 | Subcontract | 0 | 19132854 | 32460922
MCR002990 | HPR004 | 2018-06-01 | Overhead | 0 | 4475466 | 8679383
MCR002991 | HPR004 | 2018-07-01 | Labor | 0 | 1792254 | 2109990
MCR002992 | HPR004 | 2018-07-01 | Material | 0 | 4206118 | 3661252
MCR002993 | HPR004 | 2018-07-01 | Equipment | 0 | 865098 | 977525
MCR002994 | HPR004 | 2018-07-01 | Subcontract | 0 | 6860704 | 19654651
MCR002995 | HPR004 | 2018-07-01 | Overhead | 0 | 1604823 | 8989132
MCR002996 | HPR004 | 2018-08-01 | Labor | 0 | 2278201 | 2790714
MCR002997 | HPR004 | 2018-08-01 | Material | 0 | 5346555 | 5342913
MCR002998 | HPR004 | 2018-08-01 | Equipment | 0 | 1099658 | 1390827
MCR002999 | HPR004 | 2018-08-01 | Subcontract | 0 | 8720899 | 21714688
MCR003000 | HPR004 | 2018-08-01 | Overhead | 0 | 2039951 | 9373810
MCR003001 | HPR004 | 2018-09-01 | Labor | 0 | 3331872 | 3939634
MCR003002 | HPR004 | 2018-09-01 | Material | 0 | 7819344 | 7813425
MCR003003 | HPR004 | 2018-09-01 | Equipment | 0 | 1608251 | 1909825
MCR003004 | HPR004 | 2018-09-01 | Subcontract | 0 | 12754326 | 30397257
MCR003005 | HPR004 | 2018-09-01 | Overhead | 0 | 2983431 | 9816537
MCR003006 | HPR004 | 2018-10-01 | Labor | 0 | 614749 | 756512
MCR003007 | HPR004 | 2018-10-01 | Material | 0 | 1442713 | 1499889
MCR003008 | HPR004 | 2018-10-01 | Equipment | 0 | 296731 | 382473
MCR003009 | HPR004 | 2018-10-01 | Subcontract | 0 | 2353244 | 22581419
MCR003010 | HPR004 | 2018-10-01 | Overhead | 0 | 550460 | 9453514
MCR003011 | HPR004 | 2018-11-01 | Labor | 0 | 215560 | 260226
MCR003012 | HPR004 | 2018-11-01 | Material | 0 | 505882 | 564686
MCR003013 | HPR004 | 2018-11-01 | Equipment | 0 | 104048 | 119766
MCR003014 | HPR004 | 2018-11-01 | Subcontract | 0 | 825157 | 26882081
MCR003015 | HPR004 | 2018-11-01 | Overhead | 0 | 193017 | 9865864
MCR003016 | HPR005 | 2018-10-01 | Labor | 13633939 | 12690576 | 12473685
MCR003017 | HPR005 | 2018-10-01 | Material | 24805154 | 23088829 | 25706991
MCR003018 | HPR005 | 2018-10-01 | Equipment | 6267039 | 5833408 | 6596255
MCR003019 | HPR005 | 2018-10-01 | Subcontract | 37101581 | 34534439 | 33142370
MCR003020 | HPR005 | 2018-10-01 | Overhead | 9296234 | 8653006 | 25025071
MCR003021 | HPR005 | 2018-11-01 | Labor | 35915219 | 22093961 | 22322399
MCR003022 | HPR005 | 2018-11-01 | Material | 65343003 | 40197047 | 36756967
MCR003023 | HPR005 | 2018-11-01 | Equipment | 16508953 | 10155811 | 9743939
MCR003024 | HPR005 | 2018-11-01 | Subcontract | 97734878 | 60123554 | 51872715
MCR003025 | HPR005 | 2018-11-01 | Overhead | 24488614 | 15064658 | 26061442
MCR003026 | HPR005 | 2018-12-01 | Labor | 51012812 | 46274298 | 46506022
MCR003027 | HPR005 | 2018-12-01 | Material | 92811083 | 84189981 | 83834183
MCR003028 | HPR005 | 2018-12-01 | Equipment | 23448782 | 21270655 | 22165048
MCR003029 | HPR005 | 2018-12-01 | Subcontract | 138819452 | 125924693 | 121605887
MCR003030 | HPR005 | 2018-12-01 | Overhead | 34782833 | 31551901 | 29716078
MCR003031 | HPR005 | 2019-01-01 | Labor | 59360866 | 51812139 | 46532549
MCR003032 | HPR005 | 2019-01-01 | Material | 107999265 | 94265352 | 93133451
MCR003033 | HPR005 | 2019-01-01 | Equipment | 27286086 | 23816204 | 21986214
MCR003034 | HPR005 | 2019-01-01 | Subcontract | 161536730 | 140994633 | 124433223
MCR003035 | HPR005 | 2019-01-01 | Overhead | 40474912 | 35327850 | 26599439
MCR003036 | HPR005 | 2019-02-01 | Labor | 61455860 | 40976760 | 46651907
MCR003037 | HPR005 | 2019-02-01 | Material | 111810830 | 74551810 | 73520188
MCR003038 | HPR005 | 2019-02-01 | Equipment | 28249081 | 18835565 | 20432009
MCR003039 | HPR005 | 2019-02-01 | Subcontract | 167237767 | 111508681 | 104227408
MCR003040 | HPR005 | 2019-02-01 | Overhead | 41903373 | 27939801 | 26237619
MCR003041 | HPR005 | 2019-03-01 | Labor | 57880755 | 48088021 | 42919381
MCR003042 | HPR005 | 2019-03-01 | Material | 105306399 | 87489810 | 90520393
MCR003043 | HPR005 | 2019-03-01 | Equipment | 26605732 | 22104359 | 21714847
MCR003044 | HPR005 | 2019-03-01 | Subcontract | 157508956 | 130860315 | 129691261
MCR003045 | HPR005 | 2019-03-01 | Overhead | 39465706 | 32788578 | 27541793
MCR003046 | HPR005 | 2019-04-01 | Labor | 49346753 | 59929924 | 56975640
MCR003047 | HPR005 | 2019-04-01 | Material | 89779908 | 109034591 | 122090230
MCR003048 | HPR005 | 2019-04-01 | Equipment | 22682954 | 27547662 | 28889733
MCR003049 | HPR005 | 2019-04-01 | Subcontract | 134285662 | 163085289 | 161048799
MCR003050 | HPR005 | 2019-04-01 | Overhead | 33646839 | 40862921 | 25857373
MCR003051 | HPR005 | 2019-05-01 | Labor | 36775242 | 56402006 | 64123737
MCR003052 | HPR005 | 2019-05-01 | Material | 66907702 | 102616011 | 101885218
MCR003053 | HPR005 | 2019-05-01 | Equipment | 16904276 | 25926004 | 24735642
MCR003054 | HPR005 | 2019-05-01 | Subcontract | 100075231 | 153484886 | 132308023
MCR003055 | HPR005 | 2019-05-01 | Overhead | 25075017 | 38457429 | 27981427
MCR003056 | HPR005 | 2019-06-01 | Labor | 21496290 | 28118673 | 25145195
MCR003057 | HPR005 | 2019-06-01 | Material | 39109665 | 51158216 | 46383574
MCR003058 | HPR005 | 2019-06-01 | Equipment | 9881083 | 12925158 | 12865820
MCR003059 | HPR005 | 2019-06-01 | Subcontract | 58497133 | 76518400 | 75185112
MCR003060 | HPR005 | 2019-06-01 | Overhead | 14657139 | 19172578 | 24941096
MCR003061 | HPR005 | 2019-07-01 | Labor | 6045696 | 22499519 | 21567434
MCR003062 | HPR005 | 2019-07-01 | Material | 10999346 | 40934907 | 47151407
MCR003063 | HPR005 | 2019-07-01 | Equipment | 2778992 | 10342232 | 11066652
MCR003064 | HPR005 | 2019-07-01 | Subcontract | 16451949 | 61227186 | 50114867
MCR003065 | HPR005 | 2019-07-01 | Overhead | 4122228 | 15341186 | 27917069
MCR003066 | HPR005 | 2019-08-01 | Labor | 0 | 4037556 | 4057117
MCR003067 | HPR005 | 2019-08-01 | Material | 0 | 7345800 | 5846608
MCR003068 | HPR005 | 2019-08-01 | Equipment | 0 | 1855921 | 1305858
MCR003069 | HPR005 | 2019-08-01 | Subcontract | 0 | 10987265 | 16352111
MCR003070 | HPR005 | 2019-08-01 | Overhead | 0 | 2752987 | 27303724
MCR003071 | HPR006 | 2020-05-01 | Labor | 6054427 | 6166897 | 6266956
MCR003072 | HPR006 | 2020-05-01 | Material | 15416157 | 15702535 | 14821108
MCR003073 | HPR006 | 2020-05-01 | Equipment | 3983058 | 4057050 | 3765710
MCR003074 | HPR006 | 2020-05-01 | Subcontract | 13663984 | 13917813 | 13514314
MCR003075 | HPR006 | 2020-05-01 | Overhead | 2999342 | 3055060 | 22688512
MCR003076 | HPR006 | 2020-06-01 | Labor | 17399313 | 19457930 | 22462671
MCR003077 | HPR006 | 2020-06-01 | Material | 44303210 | 49544987 | 49544801
MCR003078 | HPR006 | 2020-06-01 | Equipment | 11446580 | 12800893 | 12582148
MCR003079 | HPR006 | 2020-06-01 | Subcontract | 39267787 | 43913792 | 46635104
MCR003080 | HPR006 | 2020-06-01 | Overhead | 8619561 | 9639392 | 20868125
MCR003081 | HPR006 | 2020-07-01 | Labor | 27612824 | 13622179 | 16442465
MCR003082 | HPR006 | 2020-07-01 | Material | 70309485 | 34685637 | 36980681
MCR003083 | HPR006 | 2020-07-01 | Equipment | 18165798 | 8961697 | 8898047
MCR003084 | HPR006 | 2020-07-01 | Subcontract | 62318235 | 30743330 | 32635969
MCR003085 | HPR006 | 2020-07-01 | Overhead | 13679299 | 6748381 | 22475370
MCR003086 | HPR006 | 2020-08-01 | Labor | 36714961 | 13610867 | 14714184
MCR003087 | HPR006 | 2020-08-01 | Material | 93485909 | 34656834 | 36001685
MCR003088 | HPR006 | 2020-08-01 | Equipment | 24153869 | 8954255 | 9802772
MCR003089 | HPR006 | 2020-08-01 | Subcontract | 82860468 | 30717801 | 33678684
MCR003090 | HPR006 | 2020-08-01 | Overhead | 18188467 | 6742777 | 22409176
MCR003091 | HPR006 | 2020-09-01 | Labor | 44726483 | 36614428 | 41765567
MCR003092 | HPR006 | 2020-09-01 | Material | 113885345 | 93229928 | 95979165
MCR003093 | HPR006 | 2020-09-01 | Equipment | 29424453 | 24087732 | 26048714
MCR003094 | HPR006 | 2020-09-01 | Subcontract | 100941341 | 82633581 | 93009028
MCR003095 | HPR006 | 2020-09-01 | Overhead | 22157348 | 18138663 | 22702163
MCR003096 | HPR006 | 2020-10-01 | Labor | 51668983 | 68036966 | 64109629
MCR003097 | HPR006 | 2020-10-01 | Material | 131562769 | 173239941 | 186326566
MCR003098 | HPR006 | 2020-10-01 | Equipment | 33991753 | 44759846 | 44982489
MCR003099 | HPR006 | 2020-10-01 | Subcontract | 116609580 | 153549799 | 164542737
MCR003100 | HPR006 | 2020-10-01 | Overhead | 25596639 | 33705281 | 24120374
MCR003101 | HPR006 | 2020-11-01 | Labor | 57564959 | 34534321 | 39131028
MCR003102 | HPR006 | 2020-11-01 | Material | 146575467 | 87933431 | 75295817
MCR003103 | HPR006 | 2020-11-01 | Equipment | 37870570 | 22719281 | 28351890
MCR003104 | HPR006 | 2020-11-01 | Subcontract | 129915962 | 77939074 | 84984017
MCR003105 | HPR006 | 2020-11-01 | Overhead | 28517485 | 17108185 | 20706904
MCR003106 | HPR006 | 2020-12-01 | Labor | 62437906 | 62003334 | 72168107
MCR003107 | HPR006 | 2020-12-01 | Material | 158983268 | 157876733 | 157202556
MCR003108 | HPR006 | 2020-12-01 | Equipment | 41076362 | 40790468 | 41393664
MCR003109 | HPR006 | 2020-12-01 | Subcontract | 140913514 | 139932746 | 133777698
MCR003110 | HPR006 | 2020-12-01 | Overhead | 30931526 | 30716241 | 23527265
MCR003111 | HPR006 | 2021-01-01 | Labor | 66312424 | 29558915 | 24330461
MCR003112 | HPR006 | 2021-01-01 | Material | 168848806 | 75264743 | 83192375
MCR003113 | HPR006 | 2021-01-01 | Equipment | 43625312 | 19446083 | 20554319
MCR003114 | HPR006 | 2021-01-01 | Subcontract | 149657753 | 66710287 | 75277333
MCR003115 | HPR006 | 2021-01-01 | Overhead | 32850949 | 14643386 | 24216863
MCR003116 | HPR006 | 2021-02-01 | Labor | 69214336 | 44165066 | 46627516
MCR003117 | HPR006 | 2021-02-01 | Material | 176237835 | 112455829 | 128754989
MCR003118 | HPR006 | 2021-02-01 | Equipment | 45534409 | 29055110 | 28037419
MCR003119 | HPR006 | 2021-02-01 | Subcontract | 156206958 | 99674301 | 102462448
MCR003120 | HPR006 | 2021-02-01 | Overhead | 34288547 | 21879223 | 23002491
MCR003121 | HPR006 | 2021-03-01 | Labor | 71170834 | 81120868 | 92761410
MCR003122 | HPR006 | 2021-03-01 | Material | 181219591 | 206554985 | 218342468
MCR003123 | HPR006 | 2021-03-01 | Equipment | 46821541 | 53367424 | 56826236
MCR003124 | HPR006 | 2021-03-01 | Subcontract | 160622497 | 183078315 | 198101039
MCR003125 | HPR006 | 2021-03-01 | Overhead | 35257789 | 40187002 | 23088201
MCR003126 | HPR006 | 2021-04-01 | Labor | 72210648 | 41841137 | 42087260
MCR003127 | HPR006 | 2021-04-01 | Material | 183867229 | 106538497 | 116017135
MCR003128 | HPR006 | 2021-04-01 | Equipment | 47505609 | 27526254 | 26529730
MCR003129 | HPR006 | 2021-04-01 | Subcontract | 162969209 | 94429522 | 103082751
MCR003130 | HPR006 | 2021-04-01 | Overhead | 35772909 | 20727957 | 21827950
MCR003131 | HPR006 | 2021-05-01 | Labor | 72364251 | 52505021 | 59883154
MCR003132 | HPR006 | 2021-05-01 | Material | 184258343 | 133691540 | 141541715
MCR003133 | HPR006 | 2021-05-01 | Equipment | 47606661 | 34541761 | 35892959
MCR003134 | HPR006 | 2021-05-01 | Subcontract | 163315870 | 118496398 | 128695026
MCR003135 | HPR006 | 2021-05-01 | Overhead | 35849004 | 26010809 | 22314275
MCR003136 | HPR006 | 2021-06-01 | Labor | 71664108 | 54914080 | 60553942
MCR003137 | HPR006 | 2021-06-01 | Material | 182475595 | 139825636 | 178856702
MCR003138 | HPR006 | 2021-06-01 | Equipment | 47146054 | 36126622 | 43226128
MCR003139 | HPR006 | 2021-06-01 | Subcontract | 161735746 | 123933304 | 126782086
MCR003140 | HPR006 | 2021-06-01 | Overhead | 35502155 | 27204249 | 20479142
MCR003141 | HPR006 | 2021-07-01 | Labor | 70144979 | 48682721 | 50091997
MCR003142 | HPR006 | 2021-07-01 | Material | 178607495 | 123958962 | 141732840
MCR003143 | HPR006 | 2021-07-01 | Equipment | 46146656 | 32027164 | 31425177
MCR003144 | HPR006 | 2021-07-01 | Subcontract | 158307287 | 109870009 | 128515490
MCR003145 | HPR006 | 2021-07-01 | Overhead | 34749584 | 24117254 | 24759746
MCR003146 | HPR006 | 2021-08-01 | Labor | 67844301 | 56838094 | 50862141
MCR003147 | HPR006 | 2021-08-01 | Material | 172749366 | 144724679 | 158770768
MCR003148 | HPR006 | 2021-08-01 | Equipment | 44633096 | 37392384 | 42604359
MCR003149 | HPR006 | 2021-08-01 | Subcontract | 153114982 | 128275531 | 131834947
MCR003150 | HPR006 | 2021-08-01 | Overhead | 33609836 | 28157398 | 21500865
MCR003151 | HPR006 | 2021-09-01 | Labor | 64802666 | 42549272 | 43290258
MCR003152 | HPR006 | 2021-09-01 | Material | 165004567 | 108341595 | 118221031
MCR003153 | HPR006 | 2021-09-01 | Equipment | 42632080 | 27992119 | 23128087
MCR003154 | HPR006 | 2021-09-01 | Subcontract | 146250443 | 96027683 | 103006044
MCR003155 | HPR006 | 2021-09-01 | Overhead | 32103021 | 21078765 | 23588965
MCR003156 | HPR006 | 2021-10-01 | Labor | 61064448 | 58205407 | 69340271
MCR003157 | HPR006 | 2021-10-01 | Material | 155486083 | 148206217 | 191702656
MCR003158 | HPR006 | 2021-10-01 | Equipment | 40172798 | 38291905 | 45613182
MCR003159 | HPR006 | 2021-10-01 | Subcontract | 137813814 | 131361363 | 132619838
MCR003160 | HPR006 | 2021-10-01 | Overhead | 30251120 | 28834761 | 21699729
MCR003161 | HPR006 | 2021-11-01 | Labor | 56678618 | 54060305 | 49300921
MCR003162 | HPR006 | 2021-11-01 | Material | 144318611 | 137651701 | 176314851
MCR003163 | HPR006 | 2021-11-01 | Equipment | 37287468 | 35564945 | 35782216
MCR003164 | HPR006 | 2021-11-01 | Subcontract | 127915616 | 122006455 | 164785105
MCR003165 | HPR006 | 2021-11-01 | Overhead | 28078395 | 26781291 | 22330308
MCR003166 | HPR006 | 2021-12-01 | Labor | 51699863 | 76747538 | 81876335
MCR003167 | HPR006 | 2021-12-01 | Material | 131641398 | 195419339 | 220097010
MCR003168 | HPR006 | 2021-12-01 | Equipment | 34012068 | 50490317 | 52664892
MCR003169 | HPR006 | 2021-12-01 | Subcontract | 116679272 | 173208327 | 183737315
MCR003170 | HPR006 | 2021-12-01 | Overhead | 25611936 | 38020469 | 22426948
MCR003171 | HPR006 | 2022-01-01 | Labor | 46190146 | 53389702 | 51812676
MCR003172 | HPR006 | 2022-01-01 | Material | 117612214 | 135944169 | 191368425
MCR003173 | HPR006 | 2022-01-01 | Equipment | 30387361 | 35123771 | 30948598
MCR003174 | HPR006 | 2022-01-01 | Subcontract | 104244621 | 120492998 | 129131569
MCR003175 | HPR006 | 2022-01-01 | Overhead | 22882441 | 26449077 | 21744420
MCR003176 | HPR006 | 2022-02-01 | Labor | 40220977 | 47465753 | 41421901
MCR003177 | HPR006 | 2022-02-01 | Material | 102413146 | 120860243 | 142240500
MCR003178 | HPR006 | 2022-02-01 | Equipment | 26460391 | 31226551 | 34333646
MCR003179 | HPR006 | 2022-02-01 | Subcontract | 90773051 | 107123484 | 112050440
MCR003180 | HPR006 | 2022-02-01 | Overhead | 19925335 | 23514373 | 23369894
MCR003181 | HPR006 | 2022-03-01 | Labor | 33876898 | 35714639 | 49031520
MCR003182 | HPR006 | 2022-03-01 | Material | 86259457 | 90938828 | 112329272
MCR003183 | HPR006 | 2022-03-01 | Equipment | 22286778 | 23495782 | 21800056
MCR003184 | HPR006 | 2022-03-01 | Subcontract | 76455362 | 80602884 | 83597678
MCR003185 | HPR006 | 2022-03-01 | Overhead | 16782500 | 17692911 | 22927601
MCR003186 | HPR006 | 2022-04-01 | Labor | 27261167 | 37504695 | 35481398
MCR003187 | HPR006 | 2022-04-01 | Material | 69414075 | 95496779 | 112263221
MCR003188 | HPR006 | 2022-04-01 | Equipment | 17934451 | 24673416 | 28624928
MCR003189 | HPR006 | 2022-04-01 | Subcontract | 61524595 | 84642786 | 181946051
MCR003190 | HPR006 | 2022-04-01 | Overhead | 13505090 | 18579698 | 23814158
MCR003191 | HPR006 | 2022-05-01 | Labor | 20505920 | 29024349 | 29365780
MCR003192 | HPR006 | 2022-05-01 | Material | 52213446 | 73903597 | 104151184
MCR003193 | HPR006 | 2022-05-01 | Equipment | 13490341 | 19094405 | 17664080
MCR003194 | HPR006 | 2022-05-01 | Subcontract | 46278959 | 65503846 | 112544742
MCR003195 | HPR006 | 2022-05-01 | Overhead | 10158563 | 14378564 | 23280345
MCR003196 | HPR006 | 2022-06-01 | Labor | 13792813 | 31797239 | 34666728
MCR003197 | HPR006 | 2022-06-01 | Material | 35120116 | 80964100 | 103322404
MCR003198 | HPR006 | 2022-06-01 | Equipment | 9073952 | 20918621 | 23064159
MCR003199 | HPR006 | 2022-06-01 | Subcontract | 31128427 | 71761866 | 113847525
MCR003200 | HPR006 | 2022-06-01 | Overhead | 6832913 | 15752244 | 23836624
MCR003201 | HPR006 | 2022-07-01 | Labor | 7405143 | 22429051 | 27148519
MCR003202 | HPR006 | 2022-07-01 | Material | 18855435 | 57110239 | 65964407
MCR003203 | HPR006 | 2022-07-01 | Equipment | 4871662 | 14755521 | 16910892
MCR003204 | HPR006 | 2022-07-01 | Subcontract | 16712360 | 50619192 | 108283921
MCR003205 | HPR006 | 2022-07-01 | Overhead | 3668483 | 11111275 | 23307355
MCR003206 | HPR006 | 2022-08-01 | Labor | 1949303 | 16762613 | 16055941
MCR003207 | HPR006 | 2022-08-01 | Material | 4963436 | 42682006 | 50066290
MCR003208 | HPR006 | 2022-08-01 | Equipment | 1282399 | 11027711 | 11188434
MCR003209 | HPR006 | 2022-08-01 | Subcontract | 4399301 | 37830845 | 120442841
MCR003210 | HPR006 | 2022-08-01 | Overhead | 965678 | 8304142 | 23345367
MCR003211 | HPR006 | 2022-09-01 | Labor | 0 | 33984443 | 34270313
MCR003212 | HPR006 | 2022-09-01 | Material | 0 | 86533297 | 106045777
MCR003213 | HPR006 | 2022-09-01 | Equipment | 0 | 22357529 | 24856364
MCR003214 | HPR006 | 2022-09-01 | Subcontract | 0 | 76698077 | 159075315
MCR003215 | HPR006 | 2022-09-01 | Overhead | 0 | 16835778 | 22248400
MCR003216 | HPR006 | 2022-10-01 | Labor | 0 | 34703008 | 35420438
MCR003217 | HPR006 | 2022-10-01 | Material | 0 | 88362952 | 112414392
MCR003218 | HPR006 | 2022-10-01 | Equipment | 0 | 22830255 | 25573576
MCR003219 | HPR006 | 2022-10-01 | Subcontract | 0 | 78319777 | 137511359
MCR003220 | HPR006 | 2022-10-01 | Overhead | 0 | 17191752 | 23418507
MCR003221 | HPR006 | 2022-11-01 | Labor | 0 | 16700698 | 17800596
MCR003222 | HPR006 | 2022-11-01 | Material | 0 | 42524352 | 54348791
MCR003223 | HPR006 | 2022-11-01 | Equipment | 0 | 10986978 | 11196569
MCR003224 | HPR006 | 2022-11-01 | Subcontract | 0 | 37691111 | 88006337
MCR003225 | HPR006 | 2022-11-01 | Overhead | 0 | 8273469 | 24254060
MCR003226 | HPR006 | 2022-12-01 | Labor | 0 | 12931769 | 15590097
MCR003227 | HPR006 | 2022-12-01 | Material | 0 | 32927672 | 50926456
MCR003228 | HPR006 | 2022-12-01 | Equipment | 0 | 8507493 | 9292733
MCR003229 | HPR006 | 2022-12-01 | Subcontract | 0 | 29185171 | 71537431
MCR003230 | HPR006 | 2022-12-01 | Overhead | 0 | 6406354 | 22950727
MCR003231 | HPR006 | 2023-01-01 | Labor | 0 | 11370733 | 12881901
MCR003232 | HPR006 | 2023-01-01 | Material | 0 | 28952864 | 35820044
MCR003233 | HPR006 | 2023-01-01 | Equipment | 0 | 7480525 | 7465968
MCR003234 | HPR006 | 2023-01-01 | Subcontract | 0 | 25662133 | 68793033
MCR003235 | HPR006 | 2023-01-01 | Overhead | 0 | 5633022 | 24640380
MCR003236 | HPR006 | 2023-02-01 | Labor | 0 | 5118477 | 5025322
MCR003237 | HPR006 | 2023-02-01 | Material | 0 | 13032984 | 13071511
MCR003238 | HPR006 | 2023-02-01 | Equipment | 0 | 3367320 | 3735442
MCR003239 | HPR006 | 2023-02-01 | Subcontract | 0 | 11551678 | 70896988
MCR003240 | HPR006 | 2023-02-01 | Overhead | 0 | 2535676 | 21289968
MCR003241 | HPR006 | 2023-03-01 | Labor | 0 | 4570422 | 5547135
MCR003242 | HPR006 | 2023-03-01 | Material | 0 | 11637491 | 14862458
MCR003243 | HPR006 | 2023-03-01 | Equipment | 0 | 3006768 | 3692347
MCR003244 | HPR006 | 2023-03-01 | Subcontract | 0 | 10314794 | 38155719
MCR003245 | HPR006 | 2023-03-01 | Overhead | 0 | 2264171 | 25596407
MCR003246 | HPR006 | 2023-04-01 | Labor | 0 | 1850767 | 1964547
MCR003247 | HPR006 | 2023-04-01 | Material | 0 | 4712537 | 5042090
MCR003248 | HPR006 | 2023-04-01 | Equipment | 0 | 1217574 | 1386056
MCR003249 | HPR006 | 2023-04-01 | Subcontract | 0 | 4176918 | 83928159
MCR003250 | HPR006 | 2023-04-01 | Overhead | 0 | 916864 | 23184308
MCR003251 | HPR007 | 2016-03-01 | Labor | 4777490 | 2791798 | 3041917
MCR003252 | HPR007 | 2016-03-01 | Material | 8834570 | 5162614 | 5496793
MCR003253 | HPR007 | 2016-03-01 | Equipment | 1840216 | 1075358 | 1054411
MCR003254 | HPR007 | 2016-03-01 | Subcontract | 7823094 | 4571543 | 4957488
MCR003255 | HPR007 | 2016-03-01 | Overhead | 2074740 | 1212406 | 15927807
MCR003256 | HPR007 | 2016-04-01 | Labor | 13682304 | 12146625 | 13244282
MCR003257 | HPR007 | 2016-04-01 | Material | 25301421 | 22461632 | 23132142
MCR003258 | HPR007 | 2016-04-01 | Equipment | 5270215 | 4678695 | 5351701
MCR003259 | HPR007 | 2016-04-01 | Subcontract | 22404644 | 19889985 | 20012554
MCR003260 | HPR007 | 2016-04-01 | Overhead | 5941871 | 5274965 | 13223406
MCR003261 | HPR007 | 2016-05-01 | Labor | 21625286 | 18454113 | 18750995
MCR003262 | HPR007 | 2016-05-01 | Material | 39989644 | 34125487 | 32552353
MCR003263 | HPR007 | 2016-05-01 | Equipment | 8329731 | 7108243 | 6241693
MCR003264 | HPR007 | 2016-05-01 | Subcontract | 35411202 | 30218437 | 32306168
MCR003265 | HPR007 | 2016-05-01 | Overhead | 9391303 | 8014144 | 15886749
MCR003266 | HPR007 | 2016-06-01 | Labor | 28624889 | 19279229 | 22333755
MCR003267 | HPR007 | 2016-06-01 | Material | 52933365 | 35651299 | 36161312
MCR003268 | HPR007 | 2016-06-01 | Equipment | 11025871 | 7426065 | 6804674
MCR003269 | HPR007 | 2016-06-01 | Subcontract | 46872987 | 31569557 | 28668351
MCR003270 | HPR007 | 2016-06-01 | Overhead | 12431050 | 8372471 | 14574188
MCR003271 | HPR007 | 2016-07-01 | Labor | 34700331 | 13285301 | 11780950
MCR003272 | HPR007 | 2016-07-01 | Material | 64168119 | 24567281 | 26572885
MCR003273 | HPR007 | 2016-07-01 | Equipment | 13366039 | 5117296 | 6046427
MCR003274 | HPR007 | 2016-07-01 | Subcontract | 56821467 | 21754556 | 25441410
MCR003275 | HPR007 | 2016-07-01 | Overhead | 15069457 | 5769463 | 14598616
MCR003276 | HPR007 | 2016-08-01 | Labor | 39871670 | 10457303 | 12238375
MCR003277 | HPR007 | 2016-08-01 | Material | 73730998 | 19337726 | 18360295
MCR003278 | HPR007 | 2016-08-01 | Equipment | 15357960 | 4027994 | 3833744
MCR003279 | HPR007 | 2016-08-01 | Subcontract | 65289485 | 17123736 | 17840515
MCR003280 | HPR007 | 2016-08-01 | Overhead | 17315236 | 4541337 | 15270287
MCR003281 | HPR007 | 2016-09-01 | Labor | 44159888 | 35631402 | 37695872
MCR003282 | HPR007 | 2016-09-01 | Material | 81660804 | 65889863 | 67906441
MCR003283 | HPR007 | 2016-09-01 | Equipment | 17009716 | 13724673 | 10913199
MCR003284 | HPR007 | 2016-09-01 | Subcontract | 72311402 | 58346087 | 62025528
MCR003285 | HPR007 | 2016-09-01 | Overhead | 19177498 | 15473797 | 14512462
MCR003286 | HPR007 | 2016-10-01 | Labor | 47586998 | 44729140 | 43672273
MCR003287 | HPR007 | 2016-10-01 | Material | 87998243 | 82713469 | 80233691
MCR003288 | HPR007 | 2016-10-01 | Equipment | 18329787 | 17228984 | 19747704
MCR003289 | HPR007 | 2016-10-01 | Subcontract | 77923263 | 73243547 | 72188434
MCR003290 | HPR007 | 2016-10-01 | Overhead | 20665804 | 19424710 | 14273775
MCR003291 | HPR007 | 2016-11-01 | Labor | 50176161 | 19031158 | 20231380
MCR003292 | HPR007 | 2016-11-01 | Material | 92786142 | 35192563 | 35647129
MCR003293 | HPR007 | 2016-11-01 | Equipment | 19327093 | 7330512 | 7544981
MCR003294 | HPR007 | 2016-11-01 | Subcontract | 82162992 | 31163342 | 33539059
MCR003295 | HPR007 | 2016-11-01 | Overhead | 21790210 | 8264740 | 14937124
MCR003296 | HPR007 | 2016-12-01 | Labor | 51951825 | 45853983 | 44190315
MCR003297 | HPR007 | 2016-12-01 | Material | 96069713 | 84793537 | 94901157
MCR003298 | HPR007 | 2016-12-01 | Equipment | 20011052 | 17662256 | 17844042
MCR003299 | HPR007 | 2016-12-01 | Subcontract | 85070625 | 75085466 | 76743166
MCR003300 | HPR007 | 2016-12-01 | Overhead | 22561335 | 19913200 | 15218115
MCR003301 | HPR007 | 2017-01-01 | Labor | 52939899 | 52159302 | 91966098
MCR003302 | HPR007 | 2017-01-01 | Material | 97896868 | 96453381 | 139773028
MCR003303 | HPR007 | 2017-01-01 | Equipment | 20391643 | 20090969 | 22355616
MCR003304 | HPR007 | 2017-01-01 | Subcontract | 86688588 | 85410367 | 85810351
MCR003305 | HPR007 | 2017-01-01 | Overhead | 22990430 | 22651437 | 14305592
MCR003306 | HPR007 | 2017-02-01 | Labor | 53167958 | 31975917 | 74576025
MCR003307 | HPR007 | 2017-02-01 | Material | 98318596 | 59130111 | 104807709
MCR003308 | HPR007 | 2017-02-01 | Equipment | 20479488 | 12316636 | 12784956
MCR003309 | HPR007 | 2017-02-01 | Subcontract | 87062032 | 52360263 | 51756942
MCR003310 | HPR007 | 2017-02-01 | Overhead | 23089470 | 13886315 | 16247552
MCR003311 | HPR007 | 2017-03-01 | Labor | 52665493 | 41090227 | 45587585
MCR003312 | HPR007 | 2017-03-01 | Material | 97389434 | 75984364 | 80448005
MCR003313 | HPR007 | 2017-03-01 | Equipment | 20285946 | 15827330 | 15249940
MCR003314 | HPR007 | 2017-03-01 | Subcontract | 86239251 | 67284862 | 72254725
MCR003315 | HPR007 | 2017-03-01 | Overhead | 22871263 | 17844424 | 15475697
MCR003316 | HPR007 | 2017-04-01 | Labor | 51464230 | 74423945 | 75205690
MCR003317 | HPR007 | 2017-04-01 | Material | 95168049 | 137625331 | 121583013
MCR003318 | HPR007 | 2017-04-01 | Equipment | 19823238 | 28666970 | 33145900
MCR003319 | HPR007 | 2017-04-01 | Subcontract | 84272193 | 121868512 | 111460650
MCR003320 | HPR007 | 2017-04-01 | Overhead | 22349585 | 32320397 | 14489824
MCR003321 | HPR007 | 2017-05-01 | Labor | 49598523 | 42984313 | 39836621
MCR003322 | HPR007 | 2017-05-01 | Material | 91717970 | 79486921 | 95063601
MCR003323 | HPR007 | 2017-05-01 | Equipment | 19104596 | 16556903 | 14481199
MCR003324 | HPR007 | 2017-05-01 | Subcontract | 81217116 | 70386408 | 73674213
MCR003325 | HPR007 | 2017-05-01 | Overhead | 21539357 | 18666976 | 14851195
MCR003326 | HPR007 | 2017-06-01 | Labor | 47105873 | 58176605 | 65478313
MCR003327 | HPR007 | 2017-06-01 | Material | 87108542 | 107580624 | 98043966
MCR003328 | HPR007 | 2017-06-01 | Equipment | 18144465 | 22408742 | 23654842
MCR003329 | HPR007 | 2017-06-01 | Subcontract | 77135425 | 95263644 | 98650046
MCR003330 | HPR007 | 2017-06-01 | Overhead | 20456864 | 25264596 | 13914900
MCR003331 | HPR007 | 2017-07-01 | Labor | 44027602 | 22606425 | 19906045
MCR003332 | HPR007 | 2017-07-01 | Material | 81416180 | 41803974 | 46397295
MCR003333 | HPR007 | 2017-07-01 | Equipment | 16958762 | 8707650 | 9372097
MCR003334 | HPR007 | 2017-07-01 | Subcontract | 72094785 | 37017808 | 33866432
MCR003335 | HPR007 | 2017-07-01 | Overhead | 19120050 | 9817386 | 14500081
MCR003336 | HPR007 | 2017-08-01 | Labor | 40409773 | 28606805 | 26849942
MCR003337 | HPR007 | 2017-08-01 | Material | 74726062 | 52899924 | 54620471
MCR003338 | HPR007 | 2017-08-01 | Equipment | 15565229 | 11018906 | 12214194
MCR003339 | HPR007 | 2017-08-01 | Subcontract | 66170623 | 46843375 | 48833230
MCR003340 | HPR007 | 2017-08-01 | Overhead | 17548920 | 12423196 | 15078032
MCR003341 | HPR007 | 2017-09-01 | Labor | 36304473 | 35280839 | 38952186
MCR003342 | HPR007 | 2017-09-01 | Material | 67134510 | 65241598 | 69324666
MCR003343 | HPR007 | 2017-09-01 | Equipment | 13983930 | 13589642 | 12839096
MCR003344 | HPR007 | 2017-09-01 | Subcontract | 59448234 | 57772043 | 55353631
MCR003345 | HPR007 | 2017-09-01 | Overhead | 15766095 | 15321557 | 14580782
MCR003346 | HPR007 | 2017-10-01 | Labor | 31771686 | 37943241 | 40581784
MCR003347 | HPR007 | 2017-10-01 | Material | 58752445 | 70164932 | 68754973
MCR003348 | HPR007 | 2017-10-01 | Equipment | 12237969 | 14615159 | 15944491
MCR003349 | HPR007 | 2017-10-01 | Subcontract | 52025837 | 62131701 | 58621632
MCR003350 | HPR007 | 2017-10-01 | Overhead | 13797622 | 16477769 | 15037214
MCR003351 | HPR007 | 2017-11-01 | Labor | 26882144 | 33722525 | 31711216
MCR003352 | HPR007 | 2017-11-01 | Material | 49710667 | 62359951 | 64188660
MCR003353 | HPR007 | 2017-11-01 | Equipment | 10354592 | 12989403 | 13584796
MCR003354 | HPR007 | 2017-11-01 | Subcontract | 44019258 | 55220317 | 62984690
MCR003355 | HPR007 | 2017-11-01 | Overhead | 11674221 | 14644821 | 14881200
MCR003356 | HPR007 | 2017-12-01 | Labor | 21721994 | 39711922 | 39851906
MCR003357 | HPR007 | 2017-12-01 | Material | 40168478 | 73435591 | 82973437
MCR003358 | HPR007 | 2017-12-01 | Equipment | 8366981 | 15296427 | 15005550
MCR003359 | HPR007 | 2017-12-01 | Subcontract | 35569561 | 65027899 | 63627320
MCR003360 | HPR007 | 2017-12-01 | Overhead | 9433301 | 17245862 | 15013703
MCR003361 | HPR007 | 2018-01-01 | Labor | 16401100 | 22135048 | 21398726
MCR003362 | HPR007 | 2018-01-01 | Material | 30329040 | 40932300 | 37220043
MCR003363 | HPR007 | 2018-01-01 | Equipment | 6317454 | 8526083 | 9294328
MCR003364 | HPR007 | 2018-01-01 | Subcontract | 26856647 | 36245933 | 36174186
MCR003365 | HPR007 | 2018-01-01 | Overhead | 7122574 | 9612679 | 15318602
MCR003366 | HPR007 | 2018-02-01 | Labor | 11069904 | 22219491 | 27158997
MCR003367 | HPR007 | 2018-02-01 | Material | 20470552 | 41088454 | 44841553
MCR003368 | HPR007 | 2018-02-01 | Equipment | 4263958 | 8558610 | 7963283
MCR003369 | HPR007 | 2018-02-01 | Subcontract | 18126864 | 36384208 | 35305190
MCR003370 | HPR007 | 2018-02-01 | Overhead | 4807373 | 9649351 | 15361464
MCR003371 | HPR007 | 2018-03-01 | Labor | 5961887 | 33697008 | 37711578
MCR003372 | HPR007 | 2018-03-01 | Material | 11024767 | 62312766 | 68623374
MCR003373 | HPR007 | 2018-03-01 | Equipment | 2296428 | 12979574 | 13271180
MCR003374 | HPR007 | 2018-03-01 | Subcontract | 9762534 | 55178534 | 49730830
MCR003375 | HPR007 | 2018-03-01 | Overhead | 2589093 | 14633740 | 15234232
MCR003376 | HPR007 | 2018-04-01 | Labor | 1573501 | 26321086 | 29739068
MCR003377 | HPR007 | 2018-04-01 | Material | 2909731 | 48673155 | 51469952
MCR003378 | HPR007 | 2018-04-01 | Equipment | 606089 | 10138482 | 10830674
MCR003379 | HPR007 | 2018-04-01 | Subcontract | 2576593 | 43100532 | 49986774
MCR003380 | HPR007 | 2018-04-01 | Overhead | 683331 | 11430568 | 14407748
MCR003381 | HPR007 | 2018-05-01 | Labor | 0 | 11968567 | 10759605
MCR003382 | HPR007 | 2018-05-01 | Material | 0 | 22132365 | 15337611
MCR003383 | HPR007 | 2018-05-01 | Equipment | 0 | 4610110 | 5909025
MCR003384 | HPR007 | 2018-05-01 | Subcontract | 0 | 19598415 | 22322355
MCR003385 | HPR007 | 2018-05-01 | Overhead | 0 | 5197639 | 15392750
MCR003386 | HPR007 | 2018-06-01 | Labor | 0 | 12807596 | 15284797
MCR003387 | HPR007 | 2018-06-01 | Material | 0 | 23683906 | 27275262
MCR003388 | HPR007 | 2018-06-01 | Equipment | 0 | 4933291 | 4678341
MCR003389 | HPR007 | 2018-06-01 | Subcontract | 0 | 20972319 | 20898898
MCR003390 | HPR007 | 2018-06-01 | Overhead | 0 | 5562008 | 14612304
MCR003391 | HPR007 | 2018-07-01 | Labor | 0 | 9805750 | 11303116
MCR003392 | HPR007 | 2018-07-01 | Material | 0 | 18132868 | 18743254
MCR003393 | HPR007 | 2018-07-01 | Equipment | 0 | 3777026 | 4163844
MCR003394 | HPR007 | 2018-07-01 | Subcontract | 0 | 16056824 | 16231069
MCR003395 | HPR007 | 2018-07-01 | Overhead | 0 | 4258384 | 14550726
MCR003396 | HPR007 | 2018-08-01 | Labor | 0 | 8327376 | 8499411
MCR003397 | HPR007 | 2018-08-01 | Material | 0 | 15399049 | 17397431
MCR003398 | HPR007 | 2018-08-01 | Equipment | 0 | 3207579 | 3285080
MCR003399 | HPR007 | 2018-08-01 | Subcontract | 0 | 13636001 | 14087938
MCR003400 | HPR007 | 2018-08-01 | Overhead | 0 | 3616364 | 15726280
MCR003401 | HPR007 | 2018-09-01 | Labor | 0 | 9019178 | 9712869
MCR003402 | HPR007 | 2018-09-01 | Material | 0 | 16678334 | 15421016
MCR003403 | HPR007 | 2018-09-01 | Equipment | 0 | 3474050 | 4268194
MCR003404 | HPR007 | 2018-09-01 | Subcontract | 0 | 14768820 | 14950220
MCR003405 | HPR007 | 2018-09-01 | Overhead | 0 | 3916796 | 14700575
MCR003406 | HPR007 | 2018-10-01 | Labor | 0 | 2741899 | 3083814
MCR003407 | HPR007 | 2018-10-01 | Material | 0 | 5070340 | 5543613
MCR003408 | HPR007 | 2018-10-01 | Equipment | 0 | 1056138 | 1129247
MCR003409 | HPR007 | 2018-10-01 | Subcontract | 0 | 4489833 | 4069901
MCR003410 | HPR007 | 2018-10-01 | Overhead | 0 | 1190736 | 14782415
MCR003411 | HPR007 | 2018-11-01 | Labor | 0 | 837765 | 693064
MCR003412 | HPR007 | 2018-11-01 | Material | 0 | 1549201 | 1507399
MCR003413 | HPR007 | 2018-11-01 | Equipment | 0 | 322694 | 331684
MCR003414 | HPR007 | 2018-11-01 | Subcontract | 0 | 1371832 | 1703550
MCR003415 | HPR007 | 2018-11-01 | Overhead | 0 | 363820 | 14583170
MCR003416 | HPR008 | 2020-10-01 | Labor | 1851643 | 1821785 | 2137206
MCR003417 | HPR008 | 2020-10-01 | Material | 4490458 | 4418049 | 4405183
MCR003418 | HPR008 | 2020-10-01 | Equipment | 978929 | 963144 | 881634
MCR003419 | HPR008 | 2020-10-01 | Subcontract | 6342130 | 6239862 | 6486634
MCR003420 | HPR008 | 2020-10-01 | Overhead | 1305232 | 1284185 | 10110601
MCR003421 | HPR008 | 2020-11-01 | Labor | 5312457 | 2899832 | 2884143
MCR003422 | HPR008 | 2020-11-01 | Material | 12883353 | 7032443 | 7916828
MCR003423 | HPR008 | 2020-11-01 | Equipment | 2808598 | 1533087 | 1532893
MCR003424 | HPR008 | 2020-11-01 | Subcontract | 18195894 | 9932321 | 9770214
MCR003425 | HPR008 | 2020-11-01 | Overhead | 3744777 | 2044105 | 9949014
MCR003426 | HPR008 | 2020-12-01 | Labor | 8414373 | 4839738 | 5281428
MCR003427 | HPR008 | 2020-12-01 | Material | 20405873 | 11736951 | 11469945
MCR003428 | HPR008 | 2020-12-01 | Equipment | 4448522 | 2558680 | 2679110
MCR003429 | HPR008 | 2020-12-01 | Subcontract | 28820378 | 16576765 | 16132226
MCR003430 | HPR008 | 2020-12-01 | Overhead | 5931332 | 3411555 | 9189064
MCR003431 | HPR008 | 2021-01-01 | Labor | 11163992 | 8514419 | 8696299
MCR003432 | HPR008 | 2021-01-01 | Material | 27074034 | 20648498 | 19359107
MCR003433 | HPR008 | 2021-01-01 | Equipment | 5902195 | 4501415 | 3800635
MCR003434 | HPR008 | 2021-01-01 | Subcontract | 38238201 | 29163051 | 26153607
MCR003435 | HPR008 | 2021-01-01 | Overhead | 7869552 | 6001855 | 9212588
MCR003436 | HPR008 | 2021-02-01 | Labor | 13568182 | 8534201 | 8762623
MCR003437 | HPR008 | 2021-02-01 | Material | 32904486 | 20696471 | 22704718
MCR003438 | HPR008 | 2021-02-01 | Equipment | 7173246 | 4511874 | 4769131
MCR003439 | HPR008 | 2021-02-01 | Subcontract | 46472882 | 29230806 | 26514985
MCR003440 | HPR008 | 2021-02-01 | Overhead | 9564278 | 6015800 | 9282259
MCR003441 | HPR008 | 2021-03-01 | Labor | 15634096 | 14707211 | 19548957
MCR003442 | HPR008 | 2021-03-01 | Material | 37914576 | 35666769 | 36474321
MCR003443 | HPR008 | 2021-03-01 | Equipment | 8265456 | 7775429 | 8194246
MCR003444 | HPR008 | 2021-03-01 | Subcontract | 53548918 | 50374211 | 50127366
MCR003445 | HPR008 | 2021-03-01 | Overhead | 11020550 | 10367185 | 9550499
MCR003446 | HPR008 | 2021-04-01 | Labor | 17369200 | 19422747 | 18832747
MCR003447 | HPR008 | 2021-04-01 | Material | 42122414 | 47102515 | 44765032
MCR003448 | HPR008 | 2021-04-01 | Equipment | 9182773 | 10268446 | 10537295
MCR003449 | HPR008 | 2021-04-01 | Subcontract | 59491887 | 66525567 | 64317624
MCR003450 | HPR008 | 2021-04-01 | Overhead | 12243633 | 13691189 | 10032471
MCR003451 | HPR008 | 2021-05-01 | Labor | 18781309 | 17423154 | 21608675
MCR003452 | HPR008 | 2021-05-01 | Material | 45546951 | 42253258 | 46711142
MCR003453 | HPR008 | 2021-05-01 | Equipment | 9929330 | 9211298 | 9525966
MCR003454 | HPR008 | 2021-05-01 | Subcontract | 64328555 | 59676686 | 61851622
MCR003455 | HPR008 | 2021-05-01 | Overhead | 13239036 | 12281666 | 10769402
MCR003456 | HPR008 | 2021-06-01 | Labor | 19878626 | 11737470 | 11622079
MCR003457 | HPR008 | 2021-06-01 | Material | 48208077 | 28464786 | 26090698
MCR003458 | HPR008 | 2021-06-01 | Equipment | 10509460 | 6205382 | 6116603
MCR003459 | HPR008 | 2021-06-01 | Subcontract | 68087015 | 40202440 | 38203350
MCR003460 | HPR008 | 2021-06-01 | Overhead | 14012540 | 8273799 | 9740354
MCR003461 | HPR008 | 2021-07-01 | Labor | 20669782 | 10451947 | 11645292
MCR003462 | HPR008 | 2021-07-01 | Material | 50126725 | 25347237 | 34254272
MCR003463 | HPR008 | 2021-07-01 | Equipment | 10927730 | 5525750 | 5057077
MCR003464 | HPR008 | 2021-07-01 | Subcontract | 70796832 | 35799348 | 30569071
MCR003465 | HPR008 | 2021-07-01 | Overhead | 14570230 | 7367628 | 9773322
MCR003466 | HPR008 | 2021-08-01 | Labor | 21163894 | 10672773 | 11628361
MCR003467 | HPR008 | 2021-08-01 | Material | 51325007 | 25882767 | 24340644
MCR003468 | HPR008 | 2021-08-01 | Equipment | 11188958 | 5642497 | 7194607
MCR003469 | HPR008 | 2021-08-01 | Subcontract | 72489233 | 36555708 | 40344592
MCR003470 | HPR008 | 2021-08-01 | Overhead | 14918531 | 7523289 | 9525865
MCR003471 | HPR008 | 2021-09-01 | Labor | 21370627 | 15533167 | 17077515
MCR003472 | HPR008 | 2021-09-01 | Material | 51826361 | 37669812 | 41935316
MCR003473 | HPR008 | 2021-09-01 | Equipment | 11298254 | 8212097 | 8269927
MCR003474 | HPR008 | 2021-09-01 | Subcontract | 73197324 | 53203223 | 48515416
MCR003475 | HPR008 | 2021-09-01 | Overhead | 15064259 | 10949405 | 9949069
MCR003476 | HPR008 | 2021-10-01 | Labor | 21300275 | 15649403 | 18510346
MCR003477 | HPR008 | 2021-10-01 | Material | 51655747 | 37951699 | 39455603
MCR003478 | HPR008 | 2021-10-01 | Equipment | 11261060 | 8273549 | 7982465
MCR003479 | HPR008 | 2021-10-01 | Subcontract | 72956356 | 53601348 | 55985569
MCR003480 | HPR008 | 2021-10-01 | Overhead | 15014667 | 11031340 | 9751319
MCR003481 | HPR008 | 2021-11-01 | Labor | 20963850 | 16975941 | 15787295
MCR003482 | HPR008 | 2021-11-01 | Material | 50839876 | 41168713 | 43203745
MCR003483 | HPR008 | 2021-11-01 | Equipment | 11083198 | 8974865 | 9014212
MCR003484 | HPR008 | 2021-11-01 | Subcontract | 71804055 | 58144920 | 50909858
MCR003485 | HPR008 | 2021-11-01 | Overhead | 14777520 | 11966423 | 8867520
MCR003486 | HPR008 | 2021-12-01 | Labor | 20373208 | 23588764 | 26285025
MCR003487 | HPR008 | 2021-12-01 | Material | 49407498 | 57205611 | 54625474
MCR003488 | HPR008 | 2021-12-01 | Equipment | 10770937 | 12470942 | 13673323
MCR003489 | HPR008 | 2021-12-01 | Subcontract | 69781026 | 80794746 | 87400427
MCR003490 | HPR008 | 2021-12-01 | Overhead | 14361173 | 16627834 | 8608861
MCR003491 | HPR008 | 2022-01-01 | Labor | 19541195 | 28264720 | 31788862
MCR003492 | HPR008 | 2022-01-01 | Material | 47389766 | 68545369 | 73009993
MCR003493 | HPR008 | 2022-01-01 | Equipment | 10331067 | 14943032 | 14792735
MCR003494 | HPR008 | 2022-01-01 | Subcontract | 66931268 | 96810533 | 90571860
MCR003495 | HPR008 | 2022-01-01 | Overhead | 13774683 | 19923938 | 10388531
MCR003496 | HPR008 | 2022-02-01 | Labor | 18481844 | 9564665 | 12012499
MCR003497 | HPR008 | 2022-02-01 | Material | 44820711 | 23195472 | 30375580
MCR003498 | HPR008 | 2022-02-01 | Equipment | 9771008 | 5056661 | 5558725
MCR003499 | HPR008 | 2022-02-01 | Subcontract | 63302846 | 32760288 | 35916188
MCR003500 | HPR008 | 2022-02-01 | Overhead | 13027942 | 6742179 | 9287528
MCR003501 | HPR008 | 2022-03-01 | Labor | 17210630 | 16742132 | 17979604
MCR003502 | HPR008 | 2022-03-01 | Material | 41737863 | 40601698 | 38192293
MCR003503 | HPR008 | 2022-03-01 | Equipment | 9098940 | 8851254 | 8640713
MCR003504 | HPR008 | 2022-03-01 | Subcontract | 58948763 | 57344093 | 47922083
MCR003505 | HPR008 | 2022-03-01 | Overhead | 12131857 | 11801610 | 8683897
MCR003506 | HPR008 | 2022-04-01 | Labor | 15744819 | 8843445 | 9927514
MCR003507 | HPR008 | 2022-04-01 | Material | 38183093 | 21446427 | 25224389
MCR003508 | HPR008 | 2022-04-01 | Equipment | 8323993 | 4675365 | 5776618
MCR003509 | HPR008 | 2022-04-01 | Subcontract | 53928159 | 30290011 | 30777875
MCR003510 | HPR008 | 2022-04-01 | Overhead | 11098599 | 6233788 | 9801807
MCR003511 | HPR008 | 2022-05-01 | Labor | 14103954 | 15790580 | 34930671
MCR003512 | HPR008 | 2022-05-01 | Material | 34203798 | 38294069 | 58332517
MCR003513 | HPR008 | 2022-05-01 | Equipment | 7456499 | 8348186 | 7886355
MCR003514 | HPR008 | 2022-05-01 | Subcontract | 48307973 | 54084897 | 54360493
MCR003515 | HPR008 | 2022-05-01 | Overhead | 9941946 | 11130856 | 10070698
MCR003516 | HPR008 | 2022-06-01 | Labor | 12310568 | 20289785 | 34619101
MCR003517 | HPR008 | 2022-06-01 | Material | 29854619 | 49205187 | 71274017
MCR003518 | HPR008 | 2022-06-01 | Equipment | 6508369 | 10726832 | 10489487
MCR003519 | HPR008 | 2022-06-01 | Subcontract | 42165380 | 69495290 | 64741963
MCR003520 | HPR008 | 2022-06-01 | Overhead | 8677779 | 14302368 | 9148800
MCR003521 | HPR008 | 2022-07-01 | Labor | 10391264 | 15763100 | 16918854
MCR003522 | HPR008 | 2022-07-01 | Material | 25200075 | 38227428 | 39756658
MCR003523 | HPR008 | 2022-07-01 | Equipment | 5493668 | 8333658 | 9182155
MCR003524 | HPR008 | 2022-07-01 | Subcontract | 35591502 | 53990776 | 75958002
MCR003525 | HPR008 | 2022-07-01 | Overhead | 7324853 | 11111486 | 9037741
MCR003526 | HPR008 | 2022-08-01 | Labor | 8378491 | 9061725 | 11362378
MCR003527 | HPR008 | 2022-08-01 | Material | 20318857 | 21975780 | 21047504
MCR003528 | HPR008 | 2022-08-01 | Equipment | 4429553 | 4790765 | 4583471
MCR003529 | HPR008 | 2022-08-01 | Subcontract | 28697480 | 31037647 | 60684732
MCR003530 | HPR008 | 2022-08-01 | Overhead | 5906039 | 6387654 | 9440972
MCR003531 | HPR008 | 2022-09-01 | Labor | 6313704 | 17459650 | 21480834
MCR003532 | HPR008 | 2022-09-01 | Material | 15311497 | 42341767 | 42001345
MCR003533 | HPR008 | 2022-09-01 | Equipment | 3337938 | 9230593 | 9756132
MCR003534 | HPR008 | 2022-09-01 | Subcontract | 21625300 | 59801692 | 88508816
MCR003535 | HPR008 | 2022-09-01 | Overhead | 4450560 | 12307392 | 9923857
MCR003536 | HPR008 | 2022-10-01 | Labor | 4253782 | 15934016 | 16892269
MCR003537 | HPR008 | 2022-10-01 | Material | 10315936 | 38641919 | 46289391
MCR003538 | HPR008 | 2022-10-01 | Equipment | 2248895 | 8424018 | 9169338
MCR003539 | HPR008 | 2022-10-01 | Subcontract | 14569784 | 54576186 | 74721933
MCR003540 | HPR008 | 2022-10-01 | Overhead | 2998511 | 11231965 | 8975382
MCR003541 | HPR008 | 2022-11-01 | Labor | 2287221 | 7216785 | 9048578
MCR003542 | HPR008 | 2022-11-01 | Material | 5546788 | 17501578 | 19812948
MCR003543 | HPR008 | 2022-11-01 | Equipment | 1209211 | 3815380 | 4212981
MCR003544 | HPR008 | 2022-11-01 | Subcontract | 7834046 | 24718476 | 44886810
MCR003545 | HPR008 | 2022-11-01 | Overhead | 1612273 | 5087147 | 9825649
MCR003546 | HPR008 | 2022-12-01 | Labor | 602838 | 4484984 | 4881089
MCR003547 | HPR008 | 2022-12-01 | Material | 1461956 | 10876631 | 11501569
MCR003548 | HPR008 | 2022-12-01 | Equipment | 318709 | 2371128 | 2329129
MCR003549 | HPR008 | 2022-12-01 | Subcontract | 2064804 | 15361686 | 35857438
MCR003550 | HPR008 | 2022-12-01 | Overhead | 424944 | 3161487 | 9582278
MCR003551 | HPR008 | 2023-01-01 | Labor | 0 | 6008962 | 6778857
MCR003552 | HPR008 | 2023-01-01 | Material | 0 | 14572461 | 13234634
MCR003553 | HPR008 | 2023-01-01 | Equipment | 0 | 3176827 | 3106510
MCR003554 | HPR008 | 2023-01-01 | Subcontract | 0 | 20581517 | 32057854
MCR003555 | HPR008 | 2023-01-01 | Overhead | 0 | 4235746 | 10653300
MCR003556 | HPR008 | 2023-02-01 | Labor | 0 | 3633751 | 4670677
MCR003557 | HPR008 | 2023-02-01 | Material | 0 | 8812286 | 9692833
MCR003558 | HPR008 | 2023-02-01 | Equipment | 0 | 1921097 | 2194495
MCR003559 | HPR008 | 2023-02-01 | Subcontract | 0 | 12446094 | 29055313
MCR003560 | HPR008 | 2023-02-01 | Overhead | 0 | 2561449 | 9642701
MCR003561 | HPR008 | 2023-03-01 | Labor | 0 | 2985045 | 3474207
MCR003562 | HPR008 | 2023-03-01 | Material | 0 | 7239095 | 7454332
MCR003563 | HPR008 | 2023-03-01 | Equipment | 0 | 1578138 | 1621520
MCR003564 | HPR008 | 2023-03-01 | Subcontract | 0 | 10224187 | 46172296
MCR003565 | HPR008 | 2023-03-01 | Overhead | 0 | 2104173 | 9583208
MCR003566 | HPR008 | 2023-04-01 | Labor | 0 | 2308445 | 2750328
MCR003567 | HPR008 | 2023-04-01 | Material | 0 | 5598258 | 6386403
MCR003568 | HPR008 | 2023-04-01 | Equipment | 0 | 1220432 | 1376595
MCR003569 | HPR008 | 2023-04-01 | Subcontract | 0 | 7906739 | 42895878
MCR003570 | HPR008 | 2023-04-01 | Overhead | 0 | 1627234 | 9857690
MCR003571 | HPR008 | 2023-05-01 | Labor | 0 | 311484 | 522387
MCR003572 | HPR008 | 2023-05-01 | Material | 0 | 755386 | 587283
MCR003573 | HPR008 | 2023-05-01 | Equipment | 0 | 164676 | 235174
MCR003574 | HPR008 | 2023-05-01 | Subcontract | 0 | 1066874 | 36578154
MCR003575 | HPR008 | 2023-05-01 | Overhead | 0 | 219566 | 9394948
MCR003576 | HPR009 | 2022-12-01 | Labor | 3783351 | 3125194 | 3412666
MCR003577 | HPR009 | 2022-12-01 | Material | 10301840 | 8509719 | 9209487
MCR003578 | HPR009 | 2022-12-01 | Equipment | 1791809 | 1480104 | 1477428
MCR003579 | HPR009 | 2022-12-01 | Subcontract | 19009385 | 15702488 | 15135943
MCR003580 | HPR009 | 2022-12-01 | Overhead | 2882050 | 2380685 | 19911027
MCR003581 | HPR009 | 2023-01-01 | Labor | 10791316 | 8287393 | 8639777
MCR003582 | HPR009 | 2023-01-01 | Material | 29384114 | 22566081 | 21447234
MCR003583 | HPR009 | 2023-01-01 | Equipment | 5110808 | 3924941 | 3583157
MCR003584 | HPR009 | 2023-01-01 | Subcontract | 54220793 | 41639873 | 41200588
MCR003585 | HPR009 | 2023-01-01 | Overhead | 8220521 | 6313103 | 18773019
MCR003586 | HPR009 | 2023-02-01 | Labor | 16973729 | 17752690 | 22413251
MCR003587 | HPR009 | 2023-02-01 | Material | 46218458 | 48339522 | 41034377
MCR003588 | HPR009 | 2023-02-01 | Equipment | 8038823 | 8407742 | 9211895
MCR003589 | HPR009 | 2023-02-01 | Subcontract | 85284227 | 89198103 | 91837424
MCR003590 | HPR009 | 2023-02-01 | Overhead | 12930110 | 13523500 | 21135961
MCR003591 | HPR009 | 2023-03-01 | Labor | 22347906 | 19129472 | 20532573
MCR003592 | HPR009 | 2023-03-01 | Material | 60852021 | 52088417 | 50220483
MCR003593 | HPR009 | 2023-03-01 | Equipment | 10584053 | 9059790 | 9325727
MCR003594 | HPR009 | 2023-03-01 | Subcontract | 112286689 | 96115719 | 92578544
MCR003595 | HPR009 | 2023-03-01 | Overhead | 17024006 | 14572294 | 20025400
MCR003596 | HPR009 | 2023-04-01 | Labor | 26931948 | 16383732 | 19546495
MCR003597 | HPR009 | 2023-04-01 | Material | 73334096 | 44611930 | 35864503
MCR003598 | HPR009 | 2023-04-01 | Equipment | 12755073 | 7759398 | 8396169
MCR003599 | HPR009 | 2023-04-01 | Subcontract | 135319135 | 82319794 | 73993835
MCR003600 | HPR009 | 2023-04-01 | Overhead | 20516001 | 12480666 | 19399080
MCR003601 | HPR009 | 2023-05-01 | Labor | 30744831 | 22206873 | 20304967
MCR003602 | HPR009 | 2023-05-01 | Material | 83716351 | 60467999 | 59364048
MCR003603 | HPR009 | 2023-05-01 | Equipment | 14560869 | 10517260 | 8511637
MCR003604 | HPR009 | 2023-05-01 | Subcontract | 154476904 | 111578074 | 135038359
MCR003605 | HPR009 | 2023-05-01 | Overhead | 23420548 | 16916572 | 18443597
MCR003606 | HPR009 | 2023-06-01 | Labor | 33806503 | 26706097 | 35438238
MCR003607 | HPR009 | 2023-06-01 | Material | 92053102 | 72719118 | 66176451
MCR003608 | HPR009 | 2023-06-01 | Equipment | 16010888 | 12648109 | 13456328
MCR003609 | HPR009 | 2023-06-01 | Subcontract | 169860224 | 134184350 | 129874701
MCR003610 | HPR009 | 2023-06-01 | Overhead | 25752843 | 20343954 | 18144613
MCR003611 | HPR009 | 2023-07-01 | Labor | 36138003 | 20624932 | 23933282
MCR003612 | HPR009 | 2023-07-01 | Material | 98401639 | 56160467 | 60924717
MCR003613 | HPR009 | 2023-07-01 | Equipment | 17115096 | 9768046 | 9512922
MCR003614 | HPR009 | 2023-07-01 | Subcontract | 181574809 | 103629638 | 100753015
MCR003615 | HPR009 | 2023-07-01 | Overhead | 27528915 | 15711494 | 17999029
MCR003616 | HPR009 | 2023-08-01 | Labor | 37761605 | 27675156 | 31689269
MCR003617 | HPR009 | 2023-08-01 | Material | 102822612 | 75357810 | 65911281
MCR003618 | HPR009 | 2023-08-01 | Equipment | 17884040 | 13107059 | 12508099
MCR003619 | HPR009 | 2023-08-01 | Subcontract | 189732574 | 139053375 | 141044252
MCR003620 | HPR009 | 2023-08-01 | Overhead | 28765730 | 21082156 | 19720254
MCR003621 | HPR009 | 2023-09-01 | Labor | 38700991 | 36362190 | 36111375
MCR003622 | HPR009 | 2023-09-01 | Material | 105380504 | 99012086 | 93041762
MCR003623 | HPR009 | 2023-09-01 | Equipment | 18328936 | 17221271 | 17034154
MCR003624 | HPR009 | 2023-09-01 | Subcontract | 194452502 | 182701233 | 192671297
MCR003625 | HPR009 | 2023-09-01 | Overhead | 29481327 | 27699694 | 20215370
MCR003626 | HPR009 | 2023-10-01 | Labor | 38981458 | 33935780 | 47788749
MCR003627 | HPR009 | 2023-10-01 | Material | 106144200 | 92405115 | 79683862
MCR003628 | HPR009 | 2023-10-01 | Equipment | 18461767 | 16072114 | 15254147
MCR003629 | HPR009 | 2023-10-01 | Subcontract | 195861706 | 170509774 | 182678017
MCR003630 | HPR009 | 2023-10-01 | Overhead | 29694979 | 25851323 | 18594860
MCR003631 | HPR009 | 2023-11-01 | Labor | 38630187 | 23478748 | 24976479
MCR003632 | HPR009 | 2023-11-01 | Material | 105187709 | 63931238 | 59454036
MCR003633 | HPR009 | 2023-11-01 | Equipment | 18295404 | 11119624 | 12410744
MCR003634 | HPR009 | 2023-11-01 | Subcontract | 194096750 | 117968588 | 106723347
MCR003635 | HPR009 | 2023-11-01 | Overhead | 29427391 | 17885450 | 18850079
MCR003636 | HPR009 | 2023-12-01 | Labor | 37676571 | 32484881 | 31382738
MCR003637 | HPR009 | 2023-12-01 | Material | 102591068 | 88454406 | 87927719
MCR003638 | HPR009 | 2023-12-01 | Equipment | 17843767 | 15384963 | 14075807
MCR003639 | HPR009 | 2023-12-01 | Subcontract | 189305319 | 163219760 | 152886222
MCR003640 | HPR009 | 2023-12-01 | Overhead | 28700953 | 24746070 | 17816392
MCR003641 | HPR009 | 2024-01-01 | Labor | 36152644 | 39519283 | 51969343
MCR003642 | HPR009 | 2024-01-01 | Material | 98441505 | 107608664 | 89972810
MCR003643 | HPR009 | 2024-01-01 | Equipment | 17122029 | 18716483 | 22580944
MCR003644 | HPR009 | 2024-01-01 | Subcontract | 181648371 | 198563996 | 192995714
MCR003645 | HPR009 | 2024-01-01 | Overhead | 27540068 | 30104679 | 20729795
MCR003646 | HPR009 | 2024-02-01 | Labor | 34093646 | 41052844 | 49006775
MCR003647 | HPR009 | 2024-02-01 | Material | 92834977 | 111784459 | 106161376
MCR003648 | HPR009 | 2024-02-01 | Equipment | 16146880 | 19442783 | 18542528
MCR003649 | HPR009 | 2024-02-01 | Subcontract | 171302972 | 206269347 | 207460553
MCR003650 | HPR009 | 2024-02-01 | Overhead | 25971581 | 31272902 | 17275192
MCR003651 | HPR009 | 2024-03-01 | Labor | 31538788 | 27680370 | 33744682
MCR003652 | HPR009 | 2024-03-01 | Material | 85878250 | 75372005 | 75188239
MCR003653 | HPR009 | 2024-03-01 | Equipment | 14936890 | 13109528 | 14056029
MCR003654 | HPR009 | 2024-03-01 | Subcontract | 158466131 | 139079569 | 145580638
MCR003655 | HPR009 | 2024-03-01 | Overhead | 24025363 | 21086128 | 19256874
MCR003656 | HPR009 | 2024-04-01 | Labor | 28532315 | 53373572 | 68753452
MCR003657 | HPR009 | 2024-04-01 | Material | 77691802 | 145333070 | 134258381
MCR003658 | HPR009 | 2024-04-01 | Equipment | 13513013 | 25277926 | 22548886
MCR003659 | HPR009 | 2024-04-01 | Subcontract | 143360155 | 268174645 | 295688948
MCR003660 | HPR009 | 2024-04-01 | Overhead | 21735116 | 40658487 | 19793916
MCR003661 | HPR009 | 2024-05-01 | Labor | 25125056 | 37373202 | 45638340
MCR003662 | HPR009 | 2024-05-01 | Material | 68414037 | 101765013 | 96489318
MCR003663 | HPR009 | 2024-05-01 | Equipment | 11899322 | 17700091 | 18864763
MCR003664 | HPR009 | 2024-05-01 | Subcontract | 126240436 | 187781048 | 231323604
MCR003665 | HPR009 | 2024-05-01 | Overhead | 19139561 | 28469855 | 18713570
MCR003666 | HPR009 | 2024-06-01 | Labor | 21376787 | 28456373 | 35706259
MCR003667 | HPR009 | 2024-06-01 | Material | 58207723 | 77485015 | 72310188
MCR003668 | HPR009 | 2024-06-01 | Equipment | 10124127 | 13477046 | 13913758
MCR003669 | HPR009 | 2024-06-01 | Subcontract | 107407319 | 142978583 | 204312069
MCR003670 | HPR009 | 2024-06-01 | Overhead | 16284235 | 21677265 | 18749516
MCR003671 | HPR009 | 2024-07-01 | Labor | 17360081 | 14981311 | 19360438
MCR003672 | HPR009 | 2024-07-01 | Material | 47270470 | 40793221 | 44805021
MCR003673 | HPR009 | 2024-07-01 | Equipment | 8221800 | 7095206 | 6405773
MCR003674 | HPR009 | 2024-07-01 | Subcontract | 87225444 | 75273353 | 149023123
MCR003675 | HPR009 | 2024-07-01 | Overhead | 13224421 | 11412341 | 17679545
MCR003676 | HPR009 | 2024-08-01 | Labor | 13167152 | 17816881 | 22321080
MCR003677 | HPR009 | 2024-08-01 | Material | 35853373 | 48514310 | 44009425
MCR003678 | HPR009 | 2024-08-01 | Equipment | 6236013 | 8438143 | 8428873
MCR003679 | HPR009 | 2024-08-01 | Subcontract | 66158139 | 89520629 | 138625557
MCR003680 | HPR009 | 2024-08-01 | Overhead | 10030366 | 13572399 | 17635876
MCR003681 | HPR009 | 2024-09-01 | Labor | 8923718 | 9555666 | 12724627
MCR003682 | HPR009 | 2024-09-01 | Material | 24298756 | 26019513 | 25678444
MCR003683 | HPR009 | 2024-09-01 | Equipment | 4226307 | 4525600 | 5092289
MCR003684 | HPR009 | 2024-09-01 | Subcontract | 44837078 | 48012291 | 108635585
MCR003685 | HPR009 | 2024-09-01 | Overhead | 6797838 | 7279238 | 18036058
MCR003686 | HPR009 | 2024-10-01 | Labor | 4823840 | 19396160 | 25950416
MCR003687 | HPR009 | 2024-10-01 | Material | 13135030 | 52814594 | 52935006
MCR003688 | HPR009 | 2024-10-01 | Equipment | 2284589 | 9186095 | 9122618
MCR003689 | HPR009 | 2024-10-01 | Subcontract | 24237306 | 97455693 | 185732716
MCR003690 | HPR009 | 2024-10-01 | Overhead | 3674666 | 14775450 | 16448205
MCR003691 | HPR009 | 2024-11-01 | Labor | 1277064 | 8453824 | 10396621
MCR003692 | HPR009 | 2024-11-01 | Material | 3477370 | 23019261 | 19140873
MCR003693 | HPR009 | 2024-11-01 | Equipment | 604822 | 4003763 | 5039526
MCR003694 | HPR009 | 2024-11-01 | Subcontract | 6416588 | 42476101 | 81700884
MCR003695 | HPR009 | 2024-11-01 | Overhead | 972832 | 6439885 | 19723737
MCR003696 | HPR009 | 2024-12-01 | Labor | 0 | 4305632 | 5097983
MCR003697 | HPR009 | 2024-12-01 | Material | 0 | 11723980 | 12016200
MCR003698 | HPR009 | 2024-12-01 | Equipment | 0 | 2039164 | 1690489
MCR003699 | HPR009 | 2024-12-01 | Subcontract | 0 | 21633576 | 51224818
MCR003700 | HPR009 | 2024-12-01 | Overhead | 0 | 3279909 | 18203285
MCR003701 | HPR009 | 2025-01-01 | Labor | 0 | 4543177 | 5616105
MCR003702 | HPR009 | 2025-01-01 | Material | 0 | 12370802 | 13147683
MCR003703 | HPR009 | 2025-01-01 | Equipment | 0 | 2151666 | 2090889
MCR003704 | HPR009 | 2025-01-01 | Subcontract | 0 | 22827121 | 78190257
MCR003705 | HPR009 | 2025-01-01 | Overhead | 0 | 3460865 | 18406221
MCR003706 | HPR009 | 2025-02-01 | Labor | 0 | 978058 | 1404929
MCR003707 | HPR009 | 2025-02-01 | Material | 0 | 2663193 | 1312406
MCR003708 | HPR009 | 2025-02-01 | Equipment | 0 | 463212 | 671089
MCR003709 | HPR009 | 2025-02-01 | Subcontract | 0 | 4914234 | 34769334
MCR003710 | HPR009 | 2025-02-01 | Overhead | 0 | 745057 | 19107377
MCR003711 | HPR010 | 2016-06-01 | Labor | 938491 | 664631 | 682937
MCR003712 | HPR010 | 2016-06-01 | Material | 2036506 | 1442236 | 1367439
MCR003713 | HPR010 | 2016-06-01 | Equipment | 399058 | 282609 | 285667
MCR003714 | HPR010 | 2016-06-01 | Subcontract | 2626016 | 1859722 | 1667924
MCR003715 | HPR010 | 2016-06-01 | Overhead | 649828 | 460203 | 6466959
MCR003716 | HPR010 | 2016-07-01 | Labor | 2728650 | 1034819 | 998082
MCR003717 | HPR010 | 2016-07-01 | Material | 5921116 | 2245536 | 2477042
MCR003718 | HPR010 | 2016-07-01 | Equipment | 1160256 | 440018 | 441609
MCR003719 | HPR010 | 2016-07-01 | Subcontract | 7635109 | 2895554 | 2740435
MCR003720 | HPR010 | 2016-07-01 | Overhead | 1889367 | 716527 | 6797024
MCR003721 | HPR010 | 2016-08-01 | Labor | 4389781 | 2224390 | 2444937
MCR003722 | HPR010 | 2016-08-01 | Material | 9525734 | 4826881 | 4906463
MCR003723 | HPR010 | 2016-08-01 | Equipment | 1866589 | 945838 | 989215
MCR003724 | HPR010 | 2016-08-01 | Subcontract | 12283161 | 6224125 | 6237591
MCR003725 | HPR010 | 2016-08-01 | Overhead | 3039564 | 1540208 | 6845235
MCR003726 | HPR010 | 2016-09-01 | Labor | 5923519 | 3104244 | 3562252
MCR003727 | HPR010 | 2016-09-01 | Material | 12853915 | 6736147 | 6444374
MCR003728 | HPR010 | 2016-09-01 | Equipment | 2518754 | 1319963 | 1246012
MCR003729 | HPR010 | 2016-09-01 | Subcontract | 16574755 | 8686068 | 8857059
MCR003730 | HPR010 | 2016-09-01 | Overhead | 4101552 | 2149435 | 6841890
MCR003731 | HPR010 | 2016-10-01 | Labor | 7331547 | 4323480 | 4487218
MCR003732 | HPR010 | 2016-10-01 | Material | 15909308 | 9381864 | 8456088
MCR003733 | HPR010 | 2016-10-01 | Equipment | 3117465 | 1838398 | 2002874
MCR003734 | HPR010 | 2016-10-01 | Subcontract | 20514597 | 12097645 | 11752607
MCR003735 | HPR010 | 2016-10-01 | Overhead | 5076497 | 2993656 | 7039477
MCR003736 | HPR010 | 2016-11-01 | Labor | 8615594 | 5402722 | 5077893
MCR003737 | HPR010 | 2016-11-01 | Material | 18695664 | 11723796 | 12112003
MCR003738 | HPR010 | 2016-11-01 | Equipment | 3663458 | 2297305 | 2579925
MCR003739 | HPR010 | 2016-11-01 | Subcontract | 24107523 | 15117499 | 16041558
MCR003740 | HPR010 | 2016-11-01 | Overhead | 5965594 | 3740943 | 6515941
MCR003741 | HPR010 | 2016-12-01 | Labor | 9777440 | 4496881 | 5147002
MCR003742 | HPR010 | 2016-12-01 | Material | 21216844 | 9758141 | 10695448
MCR003743 | HPR010 | 2016-12-01 | Equipment | 4157489 | 1912130 | 1699395
MCR003744 | HPR010 | 2016-12-01 | Subcontract | 27358512 | 12582843 | 12601218
MCR003745 | HPR010 | 2016-12-01 | Overhead | 6770077 | 3113722 | 7299609
MCR003746 | HPR010 | 2017-01-01 | Labor | 10818915 | 7655702 | 7142770
MCR003747 | HPR010 | 2017-01-01 | Material | 23476825 | 16612716 | 17346454
MCR003748 | HPR010 | 2017-01-01 | Equipment | 4600337 | 3255300 | 3439569
MCR003749 | HPR010 | 2017-01-01 | Subcontract | 30272693 | 21421621 | 20924684
MCR003750 | HPR010 | 2017-01-01 | Overhead | 7491214 | 5300947 | 6631170
MCR003751 | HPR010 | 2017-02-01 | Labor | 11741911 | 10361715 | 11280324
MCR003752 | HPR010 | 2017-02-01 | Material | 25479707 | 22484711 | 22488371
MCR003753 | HPR010 | 2017-02-01 | Equipment | 4992807 | 4405930 | 4564335
MCR003754 | HPR010 | 2017-02-01 | Subcontract | 32855352 | 28993390 | 31221489
MCR003755 | HPR010 | 2017-02-01 | Overhead | 8130313 | 7174640 | 6343765
MCR003756 | HPR010 | 2017-03-01 | Labor | 12548378 | 5265324 | 6065801
MCR003757 | HPR010 | 2017-03-01 | Material | 27229725 | 11425645 | 11687670
MCR003758 | HPR010 | 2017-03-01 | Equipment | 5335727 | 2238881 | 2218193
MCR003759 | HPR010 | 2017-03-01 | Subcontract | 35111949 | 14733042 | 13746678
MCR003760 | HPR010 | 2017-03-01 | Overhead | 8688725 | 3645806 | 6759859
MCR003761 | HPR010 | 2017-04-01 | Labor | 13240335 | 15015237 | 15640882
MCR003762 | HPR010 | 2017-04-01 | Material | 28731256 | 32582757 | 35876792
MCR003763 | HPR010 | 2017-04-01 | Equipment | 5629955 | 6384666 | 6218713
MCR003764 | HPR010 | 2017-04-01 | Subcontract | 37048131 | 42014531 | 35781298
MCR003765 | HPR010 | 2017-04-01 | Overhead | 9167848 | 10396823 | 5815644
MCR003766 | HPR010 | 2017-05-01 | Labor | 13819868 | 10539421 | 11552073
MCR003767 | HPR010 | 2017-05-01 | Material | 29988833 | 22870329 | 19237860
MCR003768 | HPR010 | 2017-05-01 | Equipment | 5876380 | 4481493 | 5412005
MCR003769 | HPR010 | 2017-05-01 | Subcontract | 38669740 | 29490634 | 31993803
MCR003770 | HPR010 | 2017-05-01 | Overhead | 9569128 | 7297687 | 6683058
MCR003771 | HPR010 | 2017-06-01 | Labor | 14289146 | 9377191 | 9660533
MCR003772 | HPR010 | 2017-06-01 | Material | 31007155 | 20348313 | 23765235
MCR003773 | HPR010 | 2017-06-01 | Equipment | 6075923 | 3987298 | 3675780
MCR003774 | HPR010 | 2017-06-01 | Subcontract | 39982837 | 26238566 | 30577119
MCR003775 | HPR010 | 2017-06-01 | Overhead | 9894064 | 6492937 | 7122549
MCR003776 | HPR010 | 2017-07-01 | Labor | 14650416 | 5269183 | 5747825
MCR003777 | HPR010 | 2017-07-01 | Material | 31791104 | 11434019 | 11793214
MCR003778 | HPR010 | 2017-07-01 | Equipment | 6229539 | 2240522 | 2457206
MCR003779 | HPR010 | 2017-07-01 | Subcontract | 40993717 | 14743840 | 10010809
MCR003780 | HPR010 | 2017-07-01 | Overhead | 10144215 | 3648478 | 6783433
MCR003781 | HPR010 | 2017-08-01 | Labor | 14906020 | 6872836 | 7342936
MCR003782 | HPR010 | 2017-08-01 | Material | 32345760 | 14913914 | 16123896
MCR003783 | HPR010 | 2017-08-01 | Equipment | 6338225 | 2922416 | 3303979
MCR003784 | HPR010 | 2017-08-01 | Subcontract | 41708930 | 19231065 | 19042739
MCR003785 | HPR010 | 2017-08-01 | Overhead | 10321199 | 4758877 | 6735226
MCR003786 | HPR010 | 2017-09-01 | Labor | 15058398 | 9881966 | 9202426
MCR003787 | HPR010 | 2017-09-01 | Material | 32676417 | 21443665 | 23910326
MCR003788 | HPR010 | 2017-09-01 | Equipment | 6403018 | 4201935 | 3832785
MCR003789 | HPR010 | 2017-09-01 | Subcontract | 42135303 | 27650991 | 24439812
MCR003790 | HPR010 | 2017-09-01 | Overhead | 10426709 | 6842453 | 6763177
MCR003791 | HPR010 | 2017-10-01 | Labor | 15110101 | 6536365 | 8396912
MCR003792 | HPR010 | 2017-10-01 | Material | 32788611 | 14183778 | 11176469
MCR003793 | HPR010 | 2017-10-01 | Equipment | 6425003 | 2779344 | 3092068
MCR003794 | HPR010 | 2017-10-01 | Subcontract | 42279973 | 18289575 | 21005525
MCR003795 | HPR010 | 2017-10-01 | Overhead | 10462509 | 4525898 | 6834175
MCR003796 | HPR010 | 2017-11-01 | Labor | 15063798 | 12548990 | 10947875
MCR003797 | HPR010 | 2017-11-01 | Material | 32688135 | 27231053 | 29018074
MCR003798 | HPR010 | 2017-11-01 | Equipment | 6405315 | 5335987 | 5231969
MCR003799 | HPR010 | 2017-11-01 | Subcontract | 42150413 | 35113663 | 29724720
MCR003800 | HPR010 | 2017-11-01 | Overhead | 10430448 | 8689149 | 6597820
MCR003801 | HPR010 | 2017-12-01 | Labor | 14922296 | 18629136 | 23272419
MCR003802 | HPR010 | 2017-12-01 | Material | 32381077 | 40424845 | 39169327
MCR003803 | HPR010 | 2017-12-01 | Equipment | 6345146 | 7921340 | 8210238
MCR003804 | HPR010 | 2017-12-01 | Subcontract | 41754471 | 52126678 | 52340215
MCR003805 | HPR010 | 2017-12-01 | Overhead | 10332469 | 12899152 | 7268295
MCR003806 | HPR010 | 2018-01-01 | Labor | 14688547 | 17401420 | 17748820
MCR003807 | HPR010 | 2018-01-01 | Material | 31873848 | 37760726 | 37304082
MCR003808 | HPR010 | 2018-01-01 | Equipment | 6245753 | 7399300 | 8108836
MCR003809 | HPR010 | 2018-01-01 | Subcontract | 41100413 | 48691374 | 45628717
MCR003810 | HPR010 | 2018-01-01 | Overhead | 10170617 | 12049060 | 6272801
MCR003811 | HPR010 | 2018-02-01 | Labor | 14365674 | 14908490 | 14503474
MCR003812 | HPR010 | 2018-02-01 | Material | 31173219 | 32351119 | 37892345
MCR003813 | HPR010 | 2018-02-01 | Equipment | 6108463 | 6339275 | 6926506
MCR003814 | HPR010 | 2018-02-01 | Subcontract | 40196973 | 41715840 | 43341225
MCR003815 | HPR010 | 2018-02-01 | Overhead | 9947054 | 10322909 | 6390877
MCR003816 | HPR010 | 2018-03-01 | Labor | 13956987 | 14023225 | 14605807
MCR003817 | HPR010 | 2018-03-01 | Material | 30286377 | 30430113 | 30210539
MCR003818 | HPR010 | 2018-03-01 | Equipment | 5934685 | 5962850 | 5787115
MCR003819 | HPR010 | 2018-03-01 | Subcontract | 39053414 | 39238758 | 39155153
MCR003820 | HPR010 | 2018-03-01 | Overhead | 9664071 | 9709936 | 6819059
MCR003821 | HPR010 | 2018-04-01 | Labor | 13466011 | 11785730 | 12993481
MCR003822 | HPR010 | 2018-04-01 | Material | 29220970 | 25574794 | 25771204
MCR003823 | HPR010 | 2018-04-01 | Equipment | 5725916 | 5011439 | 5000831
MCR003824 | HPR010 | 2018-04-01 | Subcontract | 37679603 | 32977963 | 34565982
MCR003825 | HPR010 | 2018-04-01 | Overhead | 9324111 | 8160654 | 6473385
MCR003826 | HPR010 | 2018-05-01 | Labor | 12896520 | 8495507 | 9624787
MCR003827 | HPR010 | 2018-05-01 | Material | 27985186 | 18435078 | 16575241
MCR003828 | HPR010 | 2018-05-01 | Equipment | 5483761 | 3612395 | 3933835
MCR003829 | HPR010 | 2018-05-01 | Subcontract | 36086095 | 23771504 | 20816350
MCR003830 | HPR010 | 2018-05-01 | Overhead | 8929785 | 5882444 | 6933542
MCR003831 | HPR010 | 2018-06-01 | Labor | 12252571 | 17394192 | 17820780
MCR003832 | HPR010 | 2018-06-01 | Material | 26587830 | 37745041 | 40613803
MCR003833 | HPR010 | 2018-06-01 | Equipment | 5209946 | 7396227 | 7900993
MCR003834 | HPR010 | 2018-06-01 | Subcontract | 34284245 | 48671148 | 44878087
MCR003835 | HPR010 | 2018-06-01 | Overhead | 8483903 | 12044055 | 6423382
MCR003836 | HPR010 | 2018-07-01 | Labor | 11538558 | 4866734 | 4665226
MCR003837 | HPR010 | 2018-07-01 | Material | 25038436 | 10560714 | 9470220
MCR003838 | HPR010 | 2018-07-01 | Equipment | 4906339 | 2069396 | 2132018
MCR003839 | HPR010 | 2018-07-01 | Subcontract | 32286346 | 13617738 | 16072164
MCR003840 | HPR010 | 2018-07-01 | Overhead | 7989508 | 3369815 | 6350114
MCR003841 | HPR010 | 2018-08-01 | Labor | 10759271 | 10010081 | 11675054
MCR003842 | HPR010 | 2018-08-01 | Material | 23347398 | 21721671 | 23065662
MCR003843 | HPR010 | 2018-08-01 | Equipment | 4574976 | 4256411 | 4091964
MCR003844 | HPR010 | 2018-08-01 | Subcontract | 30105800 | 28009472 | 29732792
MCR003845 | HPR010 | 2018-08-01 | Overhead | 7449915 | 6931162 | 6494972
MCR003846 | HPR010 | 2018-09-01 | Labor | 9919977 | 10878308 | 10514002
MCR003847 | HPR010 | 2018-09-01 | Material | 21526147 | 23605707 | 27055141
MCR003848 | HPR010 | 2018-09-01 | Equipment | 4218098 | 4625592 | 4769276
MCR003849 | HPR010 | 2018-09-01 | Subcontract | 27757349 | 30438882 | 29096145
MCR003850 | HPR010 | 2018-09-01 | Overhead | 6868772 | 7532338 | 6386178
MCR003851 | HPR010 | 2018-10-01 | Labor | 9026529 | 13093126 | 13462905
MCR003852 | HPR010 | 2018-10-01 | Material | 19587384 | 28411815 | 25792910
MCR003853 | HPR010 | 2018-10-01 | Equipment | 3838192 | 5567360 | 5713496
MCR003854 | HPR010 | 2018-10-01 | Subcontract | 25257369 | 36636221 | 35290668
MCR003855 | HPR010 | 2018-10-01 | Overhead | 6250133 | 9065918 | 6818372
MCR003856 | HPR010 | 2018-11-01 | Labor | 8085511 | 12205430 | 13787982
MCR003857 | HPR010 | 2018-11-01 | Material | 17545394 | 26485534 | 29126776
MCR003858 | HPR010 | 2018-11-01 | Equipment | 3438060 | 5189901 | 6057170
MCR003859 | HPR010 | 2018-11-01 | Subcontract | 22624283 | 34152336 | 33732729
MCR003860 | HPR010 | 2018-11-01 | Overhead | 5598555 | 8451261 | 6615208
MCR003861 | HPR010 | 2018-12-01 | Labor | 7104444 | 6900045 | 7025411
MCR003862 | HPR010 | 2018-12-01 | Material | 15416499 | 14972957 | 13990384
MCR003863 | HPR010 | 2018-12-01 | Equipment | 3020898 | 2933985 | 2736399
MCR003864 | HPR010 | 2018-12-01 | Subcontract | 19879133 | 19307199 | 18269995
MCR003865 | HPR010 | 2018-12-01 | Overhead | 4919246 | 4777717 | 7158889
MCR003866 | HPR010 | 2019-01-01 | Labor | 6092086 | 10116965 | 10266859
MCR003867 | HPR010 | 2019-01-01 | Material | 13219703 | 21953608 | 22789837
MCR003868 | HPR010 | 2019-01-01 | Equipment | 2590431 | 4301860 | 4057321
MCR003869 | HPR010 | 2019-01-01 | Subcontract | 17046428 | 28308548 | 28508153
MCR003870 | HPR010 | 2019-01-01 | Overhead | 4218271 | 7005171 | 6668762
MCR003871 | HPR010 | 2019-02-01 | Labor | 5058898 | 9023596 | 8864591
MCR003872 | HPR010 | 2019-02-01 | Material | 10977705 | 19581020 | 22208000
MCR003873 | HPR010 | 2019-02-01 | Equipment | 2151106 | 3836946 | 4214813
MCR003874 | HPR010 | 2019-02-01 | Subcontract | 14155436 | 25249164 | 28970513
MCR003875 | HPR010 | 2019-02-01 | Overhead | 3502873 | 6248102 | 6906153
MCR003876 | HPR010 | 2019-03-01 | Labor | 4017803 | 7131719 | 7449436
MCR003877 | HPR010 | 2019-03-01 | Material | 8718550 | 15475684 | 14765186
MCR003878 | HPR010 | 2019-03-01 | Equipment | 1708420 | 3032496 | 2738989
MCR003879 | HPR010 | 2019-03-01 | Subcontract | 11242320 | 19955450 | 16264795
MCR003880 | HPR010 | 2019-03-01 | Overhead | 2782000 | 4938132 | 6992387
MCR003881 | HPR010 | 2019-04-01 | Labor | 2985559 | 5908871 | 7313426
MCR003882 | HPR010 | 2019-04-01 | Material | 6478602 | 12822129 | 14238755
MCR003883 | HPR010 | 2019-04-01 | Equipment | 1269497 | 2512526 | 2943333
MCR003884 | HPR010 | 2019-04-01 | Subcontract | 8353971 | 16533768 | 16595745
MCR003885 | HPR010 | 2019-04-01 | Overhead | 2067255 | 4091410 | 6857272
MCR003886 | HPR010 | 2019-05-01 | Labor | 1985560 | 12148743 | 13574701
MCR003887 | HPR010 | 2019-05-01 | Material | 4308624 | 26362525 | 28608357
MCR003888 | HPR010 | 2019-05-01 | Equipment | 844285 | 5165797 | 5705498
MCR003889 | HPR010 | 2019-05-01 | Subcontract | 5555847 | 33993720 | 31656841
MCR003890 | HPR010 | 2019-05-01 | Overhead | 1374838 | 8412011 | 5837505
MCR003891 | HPR010 | 2019-06-01 | Labor | 1054962 | 6578933 | 6903798
MCR003892 | HPR010 | 2019-06-01 | Material | 2289246 | 14276151 | 12992484
MCR003893 | HPR010 | 2019-06-01 | Equipment | 448583 | 2797444 | 2612809
MCR003894 | HPR010 | 2019-06-01 | Subcontract | 2951917 | 18408687 | 24189986
MCR003895 | HPR010 | 2019-06-01 | Overhead | 730475 | 4555373 | 6918683
MCR003896 | HPR010 | 2019-07-01 | Labor | 275263 | 5279372 | 5336699
MCR003897 | HPR010 | 2019-07-01 | Material | 597314 | 11456129 | 12407526
MCR003898 | HPR010 | 2019-07-01 | Equipment | 117045 | 2244855 | 2287624
MCR003899 | HPR010 | 2019-07-01 | Subcontract | 770219 | 14772350 | 13604679
MCR003900 | HPR010 | 2019-07-01 | Overhead | 190597 | 3655533 | 6636093
MCR003901 | HPR010 | 2019-08-01 | Labor | 0 | 4036102 | 4345269
MCR003902 | HPR010 | 2019-08-01 | Material | 0 | 8758258 | 7834966
MCR003903 | HPR010 | 2019-08-01 | Equipment | 0 | 1716201 | 1798032
MCR003904 | HPR010 | 2019-08-01 | Subcontract | 0 | 11293523 | 10175672
MCR003905 | HPR010 | 2019-08-01 | Overhead | 0 | 2794670 | 6975371
MCR003906 | HPR010 | 2019-09-01 | Labor | 0 | 6367831 | 7001544
MCR003907 | HPR010 | 2019-09-01 | Material | 0 | 13818063 | 15724038
MCR003908 | HPR010 | 2019-09-01 | Equipment | 0 | 2707681 | 2855262
MCR003909 | HPR010 | 2019-09-01 | Subcontract | 0 | 17817996 | 19261619
MCR003910 | HPR010 | 2019-09-01 | Overhead | 0 | 4409202 | 6407481
MCR003911 | HPR010 | 2019-10-01 | Labor | 0 | 3377774 | 3093462
MCR003912 | HPR010 | 2019-10-01 | Material | 0 | 7329702 | 7176627
MCR003913 | HPR010 | 2019-10-01 | Equipment | 0 | 1436272 | 1742997
MCR003914 | HPR010 | 2019-10-01 | Subcontract | 0 | 9451440 | 8052046
MCR003915 | HPR010 | 2019-10-01 | Overhead | 0 | 2338832 | 7102388
MCR003916 | HPR010 | 2019-11-01 | Labor | 0 | 3666800 | 4174168
MCR003917 | HPR010 | 2019-11-01 | Material | 0 | 7956882 | 7370654
MCR003918 | HPR010 | 2019-11-01 | Equipment | 0 | 1559169 | 1689452
MCR003919 | HPR010 | 2019-11-01 | Subcontract | 0 | 10260171 | 9586534
MCR003920 | HPR010 | 2019-11-01 | Overhead | 0 | 2538959 | 6849445
MCR003921 | HPR010 | 2019-12-01 | Labor | 0 | 2828437 | 2851909
MCR003922 | HPR010 | 2019-12-01 | Material | 0 | 6137651 | 7214752
MCR003923 | HPR010 | 2019-12-01 | Equipment | 0 | 1202687 | 1322759
MCR003924 | HPR010 | 2019-12-01 | Subcontract | 0 | 7914324 | 8690219
MCR003925 | HPR010 | 2019-12-01 | Overhead | 0 | 1958461 | 6299859
MCR003926 | HPR010 | 2020-01-01 | Labor | 0 | 4274392 | 4526245
MCR003927 | HPR010 | 2020-01-01 | Material | 0 | 9275343 | 8837574
MCR003928 | HPR010 | 2020-01-01 | Equipment | 0 | 1817525 | 2166448
MCR003929 | HPR010 | 2020-01-01 | Subcontract | 0 | 11960288 | 12651226
MCR003930 | HPR010 | 2020-01-01 | Overhead | 0 | 2959666 | 6237290
MCR003931 | HPR010 | 2020-02-01 | Labor | 0 | 1022314 | 1081984
MCR003932 | HPR010 | 2020-02-01 | Material | 0 | 2218400 | 2678285
MCR003933 | HPR010 | 2020-02-01 | Equipment | 0 | 434701 | 329386
MCR003934 | HPR010 | 2020-02-01 | Subcontract | 0 | 2860563 | 1511450
MCR003935 | HPR010 | 2020-02-01 | Overhead | 0 | 707869 | 6494895
MCR003936 | HPR010 | 2020-03-01 | Labor | 0 | 1663253 | 1493400
MCR003937 | HPR010 | 2020-03-01 | Material | 0 | 3609225 | 4013231
MCR003938 | HPR010 | 2020-03-01 | Equipment | 0 | 707236 | 898709
MCR003939 | HPR010 | 2020-03-01 | Subcontract | 0 | 4653992 | 5048286
MCR003940 | HPR010 | 2020-03-01 | Overhead | 0 | 1151667 | 6793767
MCR003941 | HPR010 | 2020-04-01 | Labor | 0 | 661734 | 877552
MCR003942 | HPR010 | 2020-04-01 | Material | 0 | 1435948 | 1155786
MCR003943 | HPR010 | 2020-04-01 | Equipment | 0 | 281377 | 262960
MCR003944 | HPR010 | 2020-04-01 | Subcontract | 0 | 1851614 | 1732269
MCR003945 | HPR010 | 2020-04-01 | Overhead | 0 | 458196 | 6347018
MCR003946 | HPR010 | 2020-05-01 | Labor | 0 | 151979 | 130993
MCR003947 | HPR010 | 2020-05-01 | Material | 0 | 329792 | 462251
MCR003948 | HPR010 | 2020-05-01 | Equipment | 0 | 64623 | 77695
MCR003949 | HPR010 | 2020-05-01 | Subcontract | 0 | 425257 | 470964
MCR003950 | HPR010 | 2020-05-01 | Overhead | 0 | 105233 | 6467741
MCR003951 | HPR011 | 2022-07-01 | Labor | 6079586 | 2702011 | 2841440
MCR003952 | HPR011 | 2022-07-01 | Material | 14733304 | 6548069 | 6464499
MCR003953 | HPR011 | 2022-07-01 | Equipment | 4016144 | 1784935 | 2206332
MCR003954 | HPR011 | 2022-07-01 | Subcontract | 19476699 | 8656224 | 8445411
MCR003955 | HPR011 | 2022-07-01 | Overhead | 3805427 | 1691284 | 11424710
MCR003956 | HPR011 | 2022-08-01 | Labor | 16015156 | 7768668 | 7850774
MCR003957 | HPR011 | 2022-08-01 | Material | 38811221 | 18826634 | 21037832
MCR003958 | HPR011 | 2022-08-01 | Equipment | 10579532 | 5131943 | 5201845
MCR003959 | HPR011 | 2022-08-01 | Subcontract | 51306515 | 24887879 | 22734605
MCR003960 | HPR011 | 2022-08-01 | Overhead | 10024449 | 4862682 | 11523061
MCR003961 | HPR011 | 2022-09-01 | Labor | 22747408 | 13071309 | 14131303
MCR003962 | HPR011 | 2022-09-01 | Material | 55126200 | 31677085 | 28919842
MCR003963 | HPR011 | 2022-09-01 | Equipment | 15026825 | 8634842 | 7842336
MCR003964 | HPR011 | 2022-09-01 | Subcontract | 72874110 | 41875540 | 43185448
MCR003965 | HPR011 | 2022-09-01 | Overhead | 14238403 | 8181792 | 10314614
MCR003966 | HPR011 | 2022-10-01 | Labor | 26469935 | 14295457 | 15681473
MCR003967 | HPR011 | 2022-10-01 | Material | 64147393 | 34643692 | 36511106
MCR003968 | HPR011 | 2022-10-01 | Equipment | 17485908 | 9443508 | 10900565
MCR003969 | HPR011 | 2022-10-01 | Subcontract | 84799682 | 45797247 | 49096451
MCR003970 | HPR011 | 2022-10-01 | Overhead | 16568464 | 8948029 | 10397892
MCR003971 | HPR011 | 2022-11-01 | Labor | 27404126 | 14752973 | 16436029
MCR003972 | HPR011 | 2022-11-01 | Material | 66411316 | 35752440 | 37612548
MCR003973 | HPR011 | 2022-11-01 | Equipment | 18103029 | 9745741 | 10783349
MCR003974 | HPR011 | 2022-11-01 | Subcontract | 87792476 | 47262958 | 48953253
MCR003975 | HPR011 | 2022-11-01 | Overhead | 17153206 | 9234405 | 11545467
MCR003976 | HPR011 | 2022-12-01 | Labor | 25809931 | 17559913 | 17632157
MCR003977 | HPR011 | 2022-12-01 | Material | 62547935 | 42554793 | 44804751
MCR003978 | HPR011 | 2022-12-01 | Equipment | 17049912 | 11599991 | 11692787
MCR003979 | HPR011 | 2022-12-01 | Subcontract | 82685278 | 56255332 | 49598188
MCR003980 | HPR011 | 2022-12-01 | Overhead | 16155344 | 10991367 | 11750422
MCR003981 | HPR011 | 2023-01-01 | Labor | 22004487 | 45017055 | 47189699
MCR003982 | HPR011 | 2023-01-01 | Material | 53325799 | 109094588 | 98426204
MCR003983 | HPR011 | 2023-01-01 | Equipment | 14536054 | 29738042 | 34734447
MCR003984 | HPR011 | 2023-01-01 | Subcontract | 70494070 | 144217651 | 141260848
MCR003985 | HPR011 | 2023-01-01 | Overhead | 13773382 | 28177758 | 10338283
MCR003986 | HPR011 | 2023-02-01 | Labor | 16398654 | 14195395 | 15385449
MCR003987 | HPR011 | 2023-02-01 | Material | 39740592 | 34401202 | 36954268
MCR003988 | HPR011 | 2023-02-01 | Equipment | 10832869 | 9377407 | 6874826
MCR003989 | HPR011 | 2023-02-01 | Subcontract | 52535097 | 45476688 | 56228160
MCR003990 | HPR011 | 2023-02-01 | Overhead | 10264494 | 8885397 | 10197502
MCR003991 | HPR011 | 2023-03-01 | Labor | 9585531 | 13678070 | 16044883
MCR003992 | HPR011 | 2023-03-01 | Material | 23229631 | 33147514 | 31485468
MCR003993 | HPR011 | 2023-03-01 | Equipment | 6332154 | 9035665 | 10347758
MCR003994 | HPR011 | 2023-03-01 | Subcontract | 30708423 | 43819375 | 46177331
MCR003995 | HPR011 | 2023-03-01 | Overhead | 5999921 | 8561585 | 11112960
MCR003996 | HPR011 | 2023-04-01 | Labor | 2695870 | 8372150 | 14807151
MCR003997 | HPR011 | 2023-04-01 | Material | 6533187 | 20289116 | 28047661
MCR003998 | HPR011 | 2023-04-01 | Equipment | 1780878 | 5530600 | 4429089
MCR003999 | HPR011 | 2023-04-01 | Subcontract | 8636550 | 26821208 | 23635711
MCR004000 | HPR011 | 2023-04-01 | Overhead | 1687440 | 5240423 | 10720364
MCR004001 | HPR011 | 2023-05-01 | Labor | 0 | 15852677 | 29703179
MCR004002 | HPR011 | 2023-05-01 | Material | 0 | 38417468 | 44386175
MCR004003 | HPR011 | 2023-05-01 | Equipment | 0 | 10472199 | 11130079
MCR004004 | HPR011 | 2023-05-01 | Subcontract | 0 | 50785993 | 53384368
MCR004005 | HPR011 | 2023-05-01 | Overhead | 0 | 9922748 | 11249203
MCR004006 | HPR011 | 2023-06-01 | Labor | 0 | 7127029 | 7042390
MCR004007 | HPR011 | 2023-06-01 | Material | 0 | 17271682 | 18745190
MCR004008 | HPR011 | 2023-06-01 | Equipment | 0 | 4708080 | 4374048
MCR004009 | HPR011 | 2023-06-01 | Subcontract | 0 | 22832310 | 25183130
MCR004010 | HPR011 | 2023-06-01 | Overhead | 0 | 4461058 | 11135435
MCR004011 | HPR011 | 2023-07-01 | Labor | 0 | 817979 | 229964
MCR004012 | HPR011 | 2023-07-01 | Material | 0 | 1982295 | 515060
MCR004013 | HPR011 | 2023-07-01 | Equipment | 0 | 540353 | 1223069
MCR004014 | HPR011 | 2023-07-01 | Subcontract | 0 | 2620496 | 1830529
MCR004015 | HPR011 | 2023-07-01 | Overhead | 0 | 512002 | 9865626
MCR004016 | HPR012 | 2018-04-01 | Labor | 3706741 | 2077965 | 2157802
MCR004017 | HPR012 | 2018-04-01 | Material | 9298735 | 5212786 | 5483346
MCR004018 | HPR012 | 2018-04-01 | Equipment | 1931606 | 1082840 | 1137936
MCR004019 | HPR012 | 2018-04-01 | Subcontract | 20783517 | 11651049 | 12014844
MCR004020 | HPR012 | 2018-04-01 | Overhead | 3087585 | 1730872 | 18889055
MCR004021 | HPR012 | 2018-05-01 | Labor | 10548446 | 6993812 | 7601452
MCR004022 | HPR012 | 2018-05-01 | Material | 26461844 | 17544685 | 18326233
MCR004023 | HPR012 | 2018-05-01 | Equipment | 5496860 | 3644518 | 3785651
MCR004024 | HPR012 | 2018-05-01 | Subcontract | 59144624 | 39213963 | 40068475
MCR004025 | HPR012 | 2018-05-01 | Overhead | 8786484 | 5825599 | 19161088
MCR004026 | HPR012 | 2018-06-01 | Labor | 16545926 | 11566059 | 12439557
MCR004027 | HPR012 | 2018-06-01 | Material | 41507131 | 29014629 | 30806827
MCR004028 | HPR012 | 2018-06-01 | Equipment | 8622184 | 6027145 | 5598966
MCR004029 | HPR012 | 2018-06-01 | Subcontract | 92772207 | 64850331 | 66440034
MCR004030 | HPR012 | 2018-06-01 | Overhead | 13782174 | 9634119 | 19384192
MCR004031 | HPR012 | 2018-07-01 | Labor | 21717756 | 12007462 | 14564009
MCR004032 | HPR012 | 2018-07-01 | Material | 54481189 | 30121934 | 31010360
MCR004033 | HPR012 | 2018-07-01 | Equipment | 11317257 | 6257163 | 7040919
MCR004034 | HPR012 | 2018-07-01 | Subcontract | 121770404 | 67325258 | 63018202
MCR004035 | HPR012 | 2018-07-01 | Overhead | 18090125 | 10001793 | 20521583
MCR004036 | HPR012 | 2018-08-01 | Labor | 26083395 | 12923443 | 13476549
MCR004037 | HPR012 | 2018-08-01 | Material | 65432836 | 32419765 | 31712806
MCR004038 | HPR012 | 2018-08-01 | Equipment | 13592218 | 6734486 | 7689051
MCR004039 | HPR012 | 2018-08-01 | Subcontract | 146248329 | 72461118 | 72667774
MCR004040 | HPR012 | 2018-08-01 | Overhead | 21726549 | 10764773 | 18484714
MCR004041 | HPR012 | 2018-09-01 | Labor | 29663292 | 15149366 | 17643833
MCR004042 | HPR012 | 2018-09-01 | Material | 74413372 | 38003719 | 40404156
MCR004043 | HPR012 | 2018-09-01 | Equipment | 15457725 | 7894428 | 7399240
MCR004044 | HPR012 | 2018-09-01 | Subcontract | 166320642 | 84941762 | 85532795
MCR004045 | HPR012 | 2018-09-01 | Overhead | 24708477 | 12618888 | 19231923
MCR004046 | HPR012 | 2018-10-01 | Labor | 32479007 | 25406809 | 27979203
MCR004047 | HPR012 | 2018-10-01 | Material | 81476878 | 63735552 | 60284164
MCR004048 | HPR012 | 2018-10-01 | Equipment | 16925011 | 13239645 | 13348903
MCR004049 | HPR012 | 2018-10-01 | Subcontract | 182108220 | 142454744 | 128374997
MCR004050 | HPR012 | 2018-10-01 | Overhead | 27053869 | 21162977 | 18205277
MCR004051 | HPR012 | 2018-11-01 | Labor | 34553352 | 27989675 | 37929454
MCR004052 | HPR012 | 2018-11-01 | Material | 86680582 | 70214933 | 69944361
MCR004053 | HPR012 | 2018-11-01 | Equipment | 18005965 | 14585592 | 15734724
MCR004054 | HPR012 | 2018-11-01 | Subcontract | 193738970 | 156936749 | 190752931
MCR004055 | HPR012 | 2018-11-01 | Overhead | 28781725 | 23314413 | 20221430
MCR004056 | HPR012 | 2018-12-01 | Labor | 35910566 | 29054876 | 32280985
MCR004057 | HPR012 | 2018-12-01 | Material | 90085289 | 72887097 | 81148969
MCR004058 | HPR012 | 2018-12-01 | Equipment | 18713218 | 15140675 | 13593802
MCR004059 | HPR012 | 2018-12-01 | Subcontract | 201348800 | 162909278 | 137822380
MCR004060 | HPR012 | 2018-12-01 | Overhead | 29912236 | 24201688 | 18187267
MCR004061 | HPR012 | 2019-01-01 | Labor | 36576528 | 28407498 | 32857772
MCR004062 | HPR012 | 2019-01-01 | Material | 91755923 | 71263084 | 81262307
MCR004063 | HPR012 | 2019-01-01 | Equipment | 19060255 | 14803323 | 15744046
MCR004064 | HPR012 | 2019-01-01 | Subcontract | 205082819 | 159279463 | 149730476
MCR004065 | HPR012 | 2019-01-01 | Overhead | 30466959 | 23662445 | 19431894
MCR004066 | HPR012 | 2019-02-01 | Labor | 36579026 | 20138429 | 27401661
MCR004067 | HPR012 | 2019-02-01 | Material | 91762189 | 50519289 | 50404251
MCR004068 | HPR012 | 2019-02-01 | Equipment | 19061556 | 10494260 | 9788228
MCR004069 | HPR012 | 2019-02-01 | Subcontract | 205096823 | 112915196 | 134320189
MCR004070 | HPR012 | 2019-02-01 | Overhead | 30469040 | 16774602 | 18736905
MCR004071 | HPR012 | 2019-03-01 | Labor | 35948086 | 40161526 | 43251342
MCR004072 | HPR012 | 2019-03-01 | Material | 90179412 | 100749254 | 102937059
MCR004073 | HPR012 | 2019-03-01 | Equipment | 18732769 | 20928419 | 21376478
MCR004074 | HPR012 | 2019-03-01 | Subcontract | 201559173 | 225183730 | 235924857
MCR004075 | HPR012 | 2019-03-01 | Overhead | 29943489 | 33453136 | 19501955
MCR004076 | HPR012 | 2019-04-01 | Labor | 34716408 | 39715104 | 47830563
MCR004077 | HPR012 | 2019-04-01 | Material | 87089624 | 99629358 | 107004009
MCR004078 | HPR012 | 2019-04-01 | Equipment | 18090935 | 20695786 | 23080858
MCR004079 | HPR012 | 2019-04-01 | Subcontract | 194653217 | 222680661 | 235356794
MCR004080 | HPR012 | 2019-04-01 | Overhead | 28917545 | 33081282 | 18566972
MCR004081 | HPR012 | 2019-05-01 | Labor | 32919934 | 34943885 | 41125104
MCR004082 | HPR012 | 2019-05-01 | Material | 82582986 | 87660274 | 91972508
MCR004083 | HPR012 | 2019-05-01 | Equipment | 17154781 | 18209475 | 18320329
MCR004084 | HPR012 | 2019-05-01 | Subcontract | 184580472 | 195928671 | 176189050
MCR004085 | HPR012 | 2019-05-01 | Overhead | 27421145 | 29107025 | 20397829
MCR004086 | HPR012 | 2019-06-01 | Labor | 30598611 | 29795603 | 32755203
MCR004087 | HPR012 | 2019-06-01 | Material | 76759714 | 74745286 | 79801880
MCR004088 | HPR012 | 2019-06-01 | Equipment | 15945125 | 15526673 | 16902318
MCR004089 | HPR012 | 2019-06-01 | Subcontract | 171564930 | 167062499 | 174139686
MCR004090 | HPR012 | 2019-06-01 | Overhead | 25487565 | 24818687 | 20175418
MCR004091 | HPR012 | 2019-07-01 | Labor | 27797470 | 23248975 | 26992322
MCR004092 | HPR012 | 2019-07-01 | Material | 69732769 | 58322407 | 60394297
MCR004093 | HPR012 | 2019-07-01 | Equipment | 14485434 | 12115184 | 11302354
MCR004094 | HPR012 | 2019-07-01 | Subcontract | 155859069 | 130355875 | 136311342
MCR004095 | HPR012 | 2019-07-01 | Overhead | 23154314 | 19365577 | 18729937
MCR004096 | HPR012 | 2019-08-01 | Labor | 24568175 | 20959142 | 24166744
MCR004097 | HPR012 | 2019-08-01 | Material | 61631755 | 52578130 | 56737476
MCR004098 | HPR012 | 2019-08-01 | Equipment | 12802628 | 10921938 | 10034706
MCR004099 | HPR012 | 2019-08-01 | Subcontract | 137752568 | 117516893 | 126529412
MCR004100 | HPR012 | 2019-08-01 | Overhead | 20464424 | 17458227 | 19488125
MCR004101 | HPR012 | 2019-09-01 | Labor | 20971397 | 28916141 | 35810218
MCR004102 | HPR012 | 2019-09-01 | Material | 52608873 | 72539067 | 80096618
MCR004103 | HPR012 | 2019-09-01 | Equipment | 10928325 | 15068380 | 15931359
MCR004104 | HPR012 | 2019-09-01 | Subcontract | 117585607 | 162131401 | 129793640
MCR004105 | HPR012 | 2019-09-01 | Overhead | 17468435 | 24086127 | 20271948
MCR004106 | HPR012 | 2019-10-01 | Labor | 17080671 | 16688929 | 20006561
MCR004107 | HPR012 | 2019-10-01 | Material | 42848591 | 41865867 | 39258534
MCR004108 | HPR012 | 2019-10-01 | Equipment | 8900843 | 8696704 | 9141318
MCR004109 | HPR012 | 2019-10-01 | Subcontract | 95770492 | 93574014 | 109992825
MCR004110 | HPR012 | 2019-10-01 | Overhead | 14227597 | 13901290 | 18468536
MCR004111 | HPR012 | 2019-11-01 | Labor | 12989248 | 22531737 | 26353358
MCR004112 | HPR012 | 2019-11-01 | Material | 32584844 | 56523142 | 61890404
MCR004113 | HPR012 | 2019-11-01 | Equipment | 6768777 | 11741427 | 12508852
MCR004114 | HPR012 | 2019-11-01 | Subcontract | 72830085 | 126334355 | 169817262
MCR004115 | HPR012 | 2019-11-01 | Overhead | 10819586 | 18768143 | 19368908
MCR004116 | HPR012 | 2019-12-01 | Labor | 8823963 | 19545418 | 26817234
MCR004117 | HPR012 | 2019-12-01 | Material | 22135804 | 49031659 | 48688333
MCR004118 | HPR012 | 2019-12-01 | Equipment | 4598221 | 10185238 | 10423654
MCR004119 | HPR012 | 2019-12-01 | Subcontract | 49475531 | 109590210 | 162623782
MCR004120 | HPR012 | 2019-12-01 | Overhead | 7350050 | 16280644 | 18635928
MCR004121 | HPR012 | 2020-01-01 | Labor | 4780017 | 17035333 | 15860079
MCR004122 | HPR012 | 2020-01-01 | Material | 11991157 | 42734858 | 46257705
MCR004123 | HPR012 | 2020-01-01 | Equipment | 2490896 | 8877217 | 10135653
MCR004124 | HPR012 | 2020-01-01 | Subcontract | 26801325 | 95516288 | 191577461
MCR004125 | HPR012 | 2020-01-01 | Overhead | 3981586 | 14189832 | 18684355
MCR004126 | HPR012 | 2020-02-01 | Labor | 1267679 | 11746645 | 16700052
MCR004127 | HPR012 | 2020-02-01 | Material | 3180101 | 29467648 | 32995459
MCR004128 | HPR012 | 2020-02-01 | Equipment | 660595 | 6121249 | 5665567
MCR004129 | HPR012 | 2020-02-01 | Subcontract | 7107814 | 65862868 | 141737135
MCR004130 | HPR012 | 2020-02-01 | Overhead | 1055932 | 9784541 | 18158196
MCR004131 | HPR012 | 2020-03-01 | Labor | 0 | 13023686 | 17042420
MCR004132 | HPR012 | 2020-03-01 | Material | 0 | 32671234 | 31818446
MCR004133 | HPR012 | 2020-03-01 | Equipment | 0 | 6786723 | 7525165
MCR004134 | HPR012 | 2020-03-01 | Subcontract | 0 | 73023175 | 137712086
MCR004135 | HPR012 | 2020-03-01 | Overhead | 0 | 10848271 | 18311597
MCR004136 | HPR012 | 2020-04-01 | Labor | 0 | 12540318 | 13331801
MCR004137 | HPR012 | 2020-04-01 | Material | 0 | 31458657 | 36993191
MCR004138 | HPR012 | 2020-04-01 | Equipment | 0 | 6534837 | 6709136
MCR004139 | HPR012 | 2020-04-01 | Subcontract | 0 | 70312954 | 155755089
MCR004140 | HPR012 | 2020-04-01 | Overhead | 0 | 10445643 | 21574008
MCR004141 | HPR012 | 2020-05-01 | Labor | 0 | 7493352 | 10292700
MCR004142 | HPR012 | 2020-05-01 | Material | 0 | 18797831 | 19484129
MCR004143 | HPR012 | 2020-05-01 | Equipment | 0 | 3904832 | 4051318
MCR004144 | HPR012 | 2020-05-01 | Subcontract | 0 | 42014859 | 105334460
MCR004145 | HPR012 | 2020-05-01 | Overhead | 0 | 6241698 | 18446059
MCR004146 | HPR012 | 2020-06-01 | Labor | 0 | 4300242 | 5610526
MCR004147 | HPR012 | 2020-06-01 | Material | 0 | 10787592 | 8687076
MCR004148 | HPR012 | 2020-06-01 | Equipment | 0 | 2240883 | 2980220
MCR004149 | HPR012 | 2020-06-01 | Subcontract | 0 | 24111247 | 78111840
MCR004150 | HPR012 | 2020-06-01 | Overhead | 0 | 3581950 | 17675206
MCR004151 | HPR012 | 2020-07-01 | Labor | 0 | 1821129 | 2096954
MCR004152 | HPR012 | 2020-07-01 | Material | 0 | 4568487 | 5398712
MCR004153 | HPR012 | 2020-07-01 | Equipment | 0 | 949002 | 997600
MCR004154 | HPR012 | 2020-07-01 | Subcontract | 0 | 10210984 | 86722792
MCR004155 | HPR012 | 2020-07-01 | Overhead | 0 | 1516937 | 19776588
MCR004156 | HPR012 | 2020-08-01 | Labor | 0 | 643137 | 885442
MCR004157 | HPR012 | 2020-08-01 | Material | 0 | 1613374 | 1959012
MCR004158 | HPR012 | 2020-08-01 | Equipment | 0 | 335143 | 330145
MCR004159 | HPR012 | 2020-08-01 | Subcontract | 0 | 3606038 | 31494967
MCR004160 | HPR012 | 2020-08-01 | Overhead | 0 | 535710 | 19902347
MCR004161 | HPR013 | 2021-08-01 | Labor | 4262510 | 2629334 | 2840549
MCR004162 | HPR013 | 2021-08-01 | Material | 11627554 | 7172470 | 6594763
MCR004163 | HPR013 | 2021-08-01 | Equipment | 2932507 | 1808920 | 1924877
MCR004164 | HPR013 | 2021-08-01 | Subcontract | 14512095 | 8951802 | 9661349
MCR004165 | HPR013 | 2021-08-01 | Overhead | 3302423 | 2037104 | 13930657
MCR004166 | HPR013 | 2021-09-01 | Labor | 11691005 | 12249235 | 11096405
MCR004167 | HPR013 | 2021-09-01 | Material | 31891493 | 33414270 | 38827646
MCR004168 | HPR013 | 2021-09-01 | Equipment | 8043138 | 8427187 | 8454063
MCR004169 | HPR013 | 2021-09-01 | Subcontract | 39803072 | 41703616 | 43534408
MCR004170 | HPR013 | 2021-09-01 | Overhead | 9057727 | 9490221 | 11724564
MCR004171 | HPR013 | 2021-10-01 | Labor | 17519022 | 17185731 | 19670539
MCR004172 | HPR013 | 2021-10-01 | Material | 47789542 | 46880369 | 51768951
MCR004173 | HPR013 | 2021-10-01 | Equipment | 12052677 | 11823381 | 12964750
MCR004174 | HPR013 | 2021-10-01 | Subcontract | 59645078 | 58510359 | 60281663
MCR004175 | HPR013 | 2021-10-01 | Overhead | 13573043 | 13314823 | 12983863
MCR004176 | HPR013 | 2021-11-01 | Labor | 21809458 | 18135599 | 19644475
MCR004177 | HPR013 | 2021-11-01 | Material | 59493275 | 49471480 | 49808091
MCR004178 | HPR013 | 2021-11-01 | Equipment | 15004396 | 12476867 | 13501655
MCR004179 | HPR013 | 2021-11-01 | Subcontract | 74252249 | 61744267 | 69669187
MCR004180 | HPR013 | 2021-11-01 | Overhead | 16897103 | 14050742 | 12651418
MCR004181 | HPR013 | 2021-12-01 | Labor | 24630789 | 24223245 | 18371832
MCR004182 | HPR013 | 2021-12-01 | Material | 67189486 | 66077762 | 79470123
MCR004183 | HPR013 | 2021-12-01 | Equipment | 16945405 | 16665025 | 16979786
MCR004184 | HPR013 | 2021-12-01 | Subcontract | 83857721 | 82470203 | 81889656
MCR004185 | HPR013 | 2021-12-01 | Overhead | 19082958 | 18767209 | 12891081
MCR004186 | HPR013 | 2022-01-01 | Labor | 26058315 | 24087304 | 27996736
MCR004187 | HPR013 | 2022-01-01 | Material | 71083586 | 65706934 | 70632583
MCR004188 | HPR013 | 2022-01-01 | Equipment | 17927510 | 16571501 | 15774178
MCR004189 | HPR013 | 2022-01-01 | Subcontract | 88717862 | 82007380 | 87861752
MCR004190 | HPR013 | 2022-01-01 | Overhead | 20188948 | 18661888 | 12778065
MCR004191 | HPR013 | 2022-02-01 | Labor | 26175879 | 22329578 | 23581550
MCR004192 | HPR013 | 2022-02-01 | Material | 71404285 | 60912093 | 70738648
MCR004193 | HPR013 | 2022-02-01 | Equipment | 18008391 | 15362227 | 17848054
MCR004194 | HPR013 | 2022-02-01 | Subcontract | 89118119 | 76023045 | 79503413
MCR004195 | HPR013 | 2022-02-01 | Overhead | 20280032 | 17300071 | 14050551
MCR004196 | HPR013 | 2022-03-01 | Labor | 25078330 | 15640389 | 18312549
MCR004197 | HPR013 | 2022-03-01 | Material | 68410318 | 42664883 | 39746608
MCR004198 | HPR013 | 2022-03-01 | Equipment | 17253303 | 10760221 | 8734493
MCR004199 | HPR013 | 2022-03-01 | Subcontract | 85381415 | 53249103 | 51697797
MCR004200 | HPR013 | 2022-03-01 | Overhead | 19429695 | 12117553 | 12581047
MCR004201 | HPR013 | 2022-04-01 | Labor | 22875233 | 15525239 | 14090512
MCR004202 | HPR013 | 2022-04-01 | Material | 62400567 | 42350769 | 56699898
MCR004203 | HPR013 | 2022-04-01 | Equipment | 15737625 | 10681001 | 10323809
MCR004204 | HPR013 | 2022-04-01 | Subcontract | 77880777 | 52857065 | 49255213
MCR004205 | HPR013 | 2022-04-01 | Overhead | 17722823 | 12028339 | 12457718
MCR004206 | HPR013 | 2022-05-01 | Labor | 19696829 | 23041784 | 25144679
MCR004207 | HPR013 | 2022-05-01 | Material | 53730307 | 62854894 | 55226048
MCR004208 | HPR013 | 2022-05-01 | Equipment | 13550957 | 15852207 | 19192910
MCR004209 | HPR013 | 2022-05-01 | Subcontract | 67059616 | 78447813 | 92095220
MCR004210 | HPR013 | 2022-05-01 | Overhead | 15260322 | 17851860 | 13046392
MCR004211 | HPR013 | 2022-06-01 | Labor | 15704456 | 11206583 | 11414159
MCR004212 | HPR013 | 2022-06-01 | Material | 42839650 | 30570053 | 42510204
MCR004213 | HPR013 | 2022-06-01 | Equipment | 10804298 | 7709866 | 6597377
MCR004214 | HPR013 | 2022-06-01 | Subcontract | 53467226 | 38153812 | 39486888
MCR004215 | HPR013 | 2022-06-01 | Overhead | 12167190 | 8682416 | 13640887
MCR004216 | HPR013 | 2022-07-01 | Labor | 11111302 | 15409793 | 16443341
MCR004217 | HPR013 | 2022-07-01 | Material | 30310141 | 42035847 | 53219976
MCR004218 | HPR013 | 2022-07-01 | Equipment | 7644315 | 10601576 | 9779048
MCR004219 | HPR013 | 2022-07-01 | Subcontract | 37829421 | 52464017 | 67242048
MCR004220 | HPR013 | 2022-07-01 | Overhead | 8608596 | 11938896 | 12737211
MCR004221 | HPR013 | 2022-08-01 | Labor | 6233491 | 8909958 | 9990910
MCR004222 | HPR013 | 2022-08-01 | Material | 17004127 | 24305170 | 25830521
MCR004223 | HPR013 | 2022-08-01 | Equipment | 4288496 | 6129842 | 8781095
MCR004224 | HPR013 | 2022-08-01 | Subcontract | 21222478 | 30334749 | 50293480
MCR004225 | HPR013 | 2022-08-01 | Overhead | 4829462 | 6903082 | 12869950
MCR004226 | HPR013 | 2022-09-01 | Labor | 1700088 | 9638109 | 10017033
MCR004227 | HPR013 | 2022-09-01 | Material | 4637611 | 26291467 | 27171128
MCR004228 | HPR013 | 2022-09-01 | Equipment | 1169621 | 6630793 | 6183226
MCR004229 | HPR013 | 2022-09-01 | Subcontract | 5788101 | 32813802 | 47569233
MCR004230 | HPR013 | 2022-09-01 | Overhead | 1317161 | 7467224 | 12302973
MCR004231 | HPR013 | 2022-10-01 | Labor | 0 | 8375826 | 9187096
MCR004232 | HPR013 | 2022-10-01 | Material | 0 | 22848129 | 26243809
MCR004233 | HPR013 | 2022-10-01 | Equipment | 0 | 5762372 | 6370026
MCR004234 | HPR013 | 2022-10-01 | Subcontract | 0 | 28516248 | 52419483
MCR004235 | HPR013 | 2022-10-01 | Overhead | 0 | 6489257 | 12769134
MCR004236 | HPR013 | 2022-11-01 | Labor | 0 | 4641706 | 5238413
MCR004237 | HPR013 | 2022-11-01 | Material | 0 | 12661951 | 16665477
MCR004238 | HPR013 | 2022-11-01 | Equipment | 0 | 3193385 | 3142097
MCR004239 | HPR013 | 2022-11-01 | Subcontract | 0 | 15803103 | 28744291
MCR004240 | HPR013 | 2022-11-01 | Overhead | 0 | 3596210 | 13823759
MCR004241 | HPR013 | 2022-12-01 | Labor | 0 | 1317294 | 1372382
MCR004242 | HPR013 | 2022-12-01 | Material | 0 | 3593402 | 2835018
MCR004243 | HPR013 | 2022-12-01 | Equipment | 0 | 906268 | 907357
MCR004244 | HPR013 | 2022-12-01 | Subcontract | 0 | 4484846 | 26984848
MCR004245 | HPR013 | 2022-12-01 | Overhead | 0 | 1020587 | 12810412
MCR004246 | HPR014 | 2021-03-01 | Labor | 14964033 | 17313594 | 16116756
MCR004247 | HPR014 | 2021-03-01 | Material | 46261861 | 53525613 | 56632492
MCR004248 | HPR014 | 2021-03-01 | Equipment | 11227881 | 12990814 | 14058347
MCR004249 | HPR014 | 2021-03-01 | Subcontract | 45870410 | 53072700 | 59527646
MCR004250 | HPR014 | 2021-03-01 | Overhead | 12188703 | 14102498 | 56800605
MCR004251 | HPR014 | 2021-04-01 | Labor | 41743368 | 29484301 | 29665259
MCR004252 | HPR014 | 2021-04-01 | Material | 129051161 | 91151803 | 96452367
MCR004253 | HPR014 | 2021-04-01 | Equipment | 31321072 | 22122794 | 20190517
MCR004254 | HPR014 | 2021-04-01 | Subcontract | 127959179 | 90380512 | 81621020
MCR004255 | HPR014 | 2021-04-01 | Overhead | 34001363 | 24015945 | 53091404
MCR004256 | HPR014 | 2021-05-01 | Labor | 63902237 | 67915570 | 65335677
MCR004257 | HPR014 | 2021-05-01 | Material | 197556122 | 209963488 | 201883584
MCR004258 | HPR014 | 2021-05-01 | Equipment | 47947415 | 50958717 | 45082468
MCR004259 | HPR014 | 2021-05-01 | Subcontract | 195884478 | 208186857 | 201265915
MCR004260 | HPR014 | 2021-05-01 | Overhead | 52050500 | 55319493 | 61853460
MCR004261 | HPR014 | 2021-06-01 | Labor | 81584507 | 69431419 | 75143498
MCR004262 | HPR014 | 2021-06-01 | Material | 252221510 | 214649789 | 225537496
MCR004263 | HPR014 | 2021-06-01 | Equipment | 61214855 | 52096095 | 56646123
MCR004264 | HPR014 | 2021-06-01 | Subcontract | 250087308 | 212833505 | 220679500
MCR004265 | HPR014 | 2021-06-01 | Overhead | 66453297 | 56554202 | 56504840
MCR004266 | HPR014 | 2021-07-01 | Labor | 94943968 | 68226027 | 67809959
MCR004267 | HPR014 | 2021-07-01 | Material | 293522775 | 210923277 | 233568864
MCR004268 | HPR014 | 2021-07-01 | Equipment | 71238786 | 51191661 | 55304016
MCR004269 | HPR014 | 2021-07-01 | Subcontract | 291039097 | 209138525 | 233906122
MCR004270 | HPR014 | 2021-07-01 | Overhead | 77335022 | 55572370 | 61642371
MCR004271 | HPR014 | 2021-08-01 | Labor | 104146018 | 65016135 | 67800350
MCR004272 | HPR014 | 2021-08-01 | Material | 321971252 | 200999778 | 211393510
MCR004273 | HPR014 | 2021-08-01 | Equipment | 78143310 | 48783200 | 47008518
MCR004274 | HPR014 | 2021-08-01 | Subcontract | 319246854 | 199298995 | 146353003
MCR004275 | HPR014 | 2021-08-01 | Overhead | 84830398 | 52957806 | 58234429
MCR004276 | HPR014 | 2021-09-01 | Labor | 109369815 | 142985520 | 147076996
MCR004277 | HPR014 | 2021-09-01 | Material | 338120815 | 442045006 | 388825377
MCR004278 | HPR014 | 2021-09-01 | Equipment | 82062853 | 107285541 | 97903601
MCR004279 | HPR014 | 2021-09-01 | Subcontract | 335259766 | 438304590 | 403093914
MCR004280 | HPR014 | 2021-09-01 | Overhead | 89085355 | 116466466 | 57579597
MCR004281 | HPR014 | 2021-10-01 | Labor | 110811100 | 105493340 | 114191207
MCR004282 | HPR014 | 2021-10-01 | Material | 342576599 | 326136550 | 430345345
MCR004283 | HPR014 | 2021-10-01 | Equipment | 83144284 | 79154239 | 81450462
MCR004284 | HPR014 | 2021-10-01 | Subcontract | 339677846 | 323376907 | 316705821
MCR004285 | HPR014 | 2021-10-01 | Overhead | 90259329 | 85927837 | 59104812
MCR004286 | HPR014 | 2021-11-01 | Labor | 108685978 | 133036192 | 143336233
MCR004287 | HPR014 | 2021-11-01 | Material | 336006707 | 411286292 | 398518302
MCR004288 | HPR014 | 2021-11-01 | Equipment | 81549754 | 99820316 | 95497969
MCR004289 | HPR014 | 2021-11-01 | Subcontract | 333163547 | 407806145 | 462354013
MCR004290 | HPR014 | 2021-11-01 | Overhead | 88528347 | 108362407 | 59541957
MCR004291 | HPR014 | 2021-12-01 | Labor | 103236181 | 146228154 | 163011963
MCR004292 | HPR014 | 2021-12-01 | Material | 319158460 | 452069727 | 502046481
MCR004293 | HPR014 | 2021-12-01 | Equipment | 77460638 | 109718568 | 111254482
MCR004294 | HPR014 | 2021-12-01 | Subcontract | 316457863 | 448244486 | 449055778
MCR004295 | HPR014 | 2021-12-01 | Overhead | 84089306 | 119107699 | 55017517
MCR004296 | HPR014 | 2022-01-01 | Labor | 94736636 | 63049767 | 56064744
MCR004297 | HPR014 | 2022-01-01 | Material | 292881802 | 194920679 | 167197196
MCR004298 | HPR014 | 2022-01-01 | Equipment | 71083220 | 47307786 | 58205232
MCR004299 | HPR014 | 2022-01-01 | Subcontract | 290403549 | 193271335 | 184351070
MCR004300 | HPR014 | 2022-01-01 | Overhead | 77166144 | 51356134 | 54429877
MCR004301 | HPR014 | 2022-02-01 | Labor | 83506930 | 81243341 | 90297918
MCR004302 | HPR014 | 2022-02-01 | Material | 258164751 | 251166782 | 290441127
MCR004303 | HPR014 | 2022-02-01 | Equipment | 62657296 | 60958870 | 57976435
MCR004304 | HPR014 | 2022-02-01 | Subcontract | 255980259 | 249041505 | 349671218
MCR004305 | HPR014 | 2022-02-01 | Overhead | 68019174 | 66175406 | 56454228
MCR004306 | HPR014 | 2022-03-01 | Labor | 69929811 | 55819343 | 61007776
MCR004307 | HPR014 | 2022-03-01 | Material | 216190589 | 172567556 | 166075756
MCR004308 | HPR014 | 2022-03-01 | Equipment | 52470052 | 41882621 | 44645580
MCR004309 | HPR014 | 2022-03-01 | Subcontract | 214361267 | 171107356 | 204989801
MCR004310 | HPR014 | 2022-03-01 | Overhead | 56960159 | 45466713 | 57670665
MCR004311 | HPR014 | 2022-04-01 | Labor | 54483790 | 50274998 | 48409996
MCR004312 | HPR014 | 2022-04-01 | Material | 168438645 | 155427008 | 185199594
MCR004313 | HPR014 | 2022-04-01 | Equipment | 40880523 | 37722563 | 31688737
MCR004314 | HPR014 | 2022-04-01 | Subcontract | 167013382 | 154111844 | 198328392
MCR004315 | HPR014 | 2022-04-01 | Overhead | 44378861 | 40950659 | 59483941
MCR004316 | HPR014 | 2022-05-01 | Labor | 37808448 | 53812643 | 69171341
MCR004317 | HPR014 | 2022-05-01 | Material | 116886212 | 166363770 | 204661677
MCR004318 | HPR014 | 2022-05-01 | Equipment | 28368606 | 40376945 | 50136873
MCR004319 | HPR014 | 2022-05-01 | Subcontract | 115897165 | 164956064 | 183497724
MCR004320 | HPR014 | 2022-05-01 | Overhead | 30796240 | 43832189 | 59612653
MCR004321 | HPR014 | 2022-06-01 | Labor | 20866602 | 39660312 | 37974324
MCR004322 | HPR014 | 2022-06-01 | Material | 64509868 | 122611317 | 110973106
MCR004323 | HPR014 | 2022-06-01 | Equipment | 15656723 | 29758104 | 29066994
MCR004324 | HPR014 | 2022-06-01 | Subcontract | 63964010 | 121573827 | 233650177
MCR004325 | HPR014 | 2022-06-01 | Overhead | 16996542 | 32304645 | 57583220
MCR004326 | HPR014 | 2022-07-01 | Labor | 5618292 | 8301923 | 9758407
MCR004327 | HPR014 | 2022-07-01 | Material | 17369156 | 25665701 | 23115900
MCR004328 | HPR014 | 2022-07-01 | Equipment | 4215542 | 6229136 | 4087098
MCR004329 | HPR014 | 2022-07-01 | Subcontract | 17222185 | 25448528 | 95633501
MCR004330 | HPR014 | 2022-07-01 | Overhead | 4576286 | 6762193 | 51808455
MCR004331 | HPR014 | 2022-08-01 | Labor | 0 | 3045134 | 3427280
MCR004332 | HPR014 | 2022-08-01 | Material | 0 | 9414143 | 11040040
MCR004333 | HPR014 | 2022-08-01 | Equipment | 0 | 2284839 | 2070843
MCR004334 | HPR014 | 2022-08-01 | Subcontract | 0 | 9334485 | 65614175
MCR004335 | HPR014 | 2022-08-01 | Overhead | 0 | 2480363 | 59243344
MCR004336 | HPR015 | 2019-06-01 | Labor | 13217605 | 6581326 | 5453154
MCR004337 | HPR015 | 2019-06-01 | Material | 26459146 | 13174570 | 13017144
MCR004338 | HPR015 | 2019-06-01 | Equipment | 6605675 | 3289106 | 3373030
MCR004339 | HPR015 | 2019-06-01 | Subcontract | 30899175 | 15385354 | 16204481
MCR004340 | HPR015 | 2019-06-01 | Overhead | 8609617 | 4286911 | 29658767
MCR004341 | HPR015 | 2019-07-01 | Labor | 35279541 | 28337445 | 23739863
MCR004342 | HPR015 | 2019-07-01 | Material | 70622972 | 56726208 | 59441429
MCR004343 | HPR015 | 2019-07-01 | Equipment | 17631423 | 14162018 | 14224292
MCR004344 | HPR015 | 2019-07-01 | Subcontract | 82473998 | 66245261 | 59514093
MCR004345 | HPR015 | 2019-07-01 | Overhead | 22980210 | 18458303 | 27367741
MCR004346 | HPR015 | 2019-08-01 | Labor | 51014015 | 34759842 | 35062727
MCR004347 | HPR015 | 2019-08-01 | Material | 102120414 | 69582632 | 71547911
MCR004348 | HPR015 | 2019-08-01 | Equipment | 25494937 | 17371696 | 16630374
MCR004349 | HPR015 | 2019-08-01 | Subcontract | 119256930 | 81259082 | 82620807
MCR004350 | HPR015 | 2019-08-01 | Overhead | 33229253 | 22641691 | 27153781
MCR004351 | HPR015 | 2019-09-01 | Labor | 60758085 | 41256317 | 40889876
MCR004352 | HPR015 | 2019-09-01 | Material | 121626199 | 82587348 | 86554287
MCR004353 | HPR015 | 2019-09-01 | Equipment | 30364666 | 20618397 | 22776518
MCR004354 | HPR015 | 2019-09-01 | Subcontract | 142035922 | 96446080 | 102857494
MCR004355 | HPR015 | 2019-09-01 | Overhead | 39576296 | 26873333 | 27450704
MCR004356 | HPR015 | 2019-10-01 | Labor | 64890711 | 78305771 | 70897387
MCR004357 | HPR015 | 2019-10-01 | Material | 129898937 | 156753350 | 169828335
MCR004358 | HPR015 | 2019-10-01 | Equipment | 32430001 | 39134357 | 35827771
MCR004359 | HPR015 | 2019-10-01 | Subcontract | 151696882 | 183057652 | 202162792
MCR004360 | HPR015 | 2019-10-01 | Overhead | 42268185 | 51006419 | 28518768
MCR004361 | HPR015 | 2019-11-01 | Labor | 63846455 | 39917674 | 39567057
MCR004362 | HPR015 | 2019-11-01 | Material | 127808532 | 79907637 | 65262183
MCR004363 | HPR015 | 2019-11-01 | Equipment | 31908120 | 19949392 | 23078001
MCR004364 | HPR015 | 2019-11-01 | Subcontract | 149255693 | 93316694 | 71161856
MCR004365 | HPR015 | 2019-11-01 | Overhead | 41587983 | 26001374 | 26119200
MCR004366 | HPR015 | 2019-12-01 | Labor | 58137284 | 55852856 | 56682070
MCR004367 | HPR015 | 2019-12-01 | Material | 116379851 | 111806859 | 111860275
MCR004368 | HPR015 | 2019-12-01 | Equipment | 29054886 | 27913212 | 26544554
MCR004369 | HPR015 | 2019-12-01 | Subcontract | 135909200 | 130568828 | 149684756
MCR004370 | HPR015 | 2019-12-01 | Overhead | 37869172 | 36381153 | 27133271
MCR004371 | HPR015 | 2020-01-01 | Labor | 48390435 | 70028646 | 60865997
MCR004372 | HPR015 | 2020-01-01 | Material | 96868503 | 140184110 | 159682737
MCR004373 | HPR015 | 2020-01-01 | Equipment | 24183768 | 34997753 | 32838699
MCR004374 | HPR015 | 2020-01-01 | Subcontract | 113123712 | 163707979 | 162984681
MCR004375 | HPR015 | 2020-01-01 | Overhead | 31520318 | 45614907 | 26781266
MCR004376 | HPR015 | 2020-02-01 | Labor | 35423017 | 28146047 | 29289533
MCR004377 | HPR015 | 2020-02-01 | Material | 70910184 | 56343066 | 46168957
MCR004378 | HPR015 | 2020-02-01 | Equipment | 17703127 | 14066364 | 16666633
MCR004379 | HPR015 | 2020-02-01 | Subcontract | 82809406 | 65797825 | 64139531
MCR004380 | HPR015 | 2020-02-01 | Overhead | 23073667 | 18333631 | 29209728
MCR004381 | HPR015 | 2020-03-01 | Labor | 20423612 | 33086182 | 29915001
MCR004382 | HPR015 | 2020-03-01 | Material | 40884210 | 66232282 | 71997436
MCR004383 | HPR015 | 2020-03-01 | Equipment | 10206973 | 16535262 | 16852959
MCR004384 | HPR015 | 2020-03-01 | Subcontract | 47744865 | 77346520 | 77831495
MCR004385 | HPR015 | 2020-03-01 | Overhead | 13303430 | 21551511 | 27136779
MCR004386 | HPR015 | 2020-04-01 | Labor | 5686740 | 22076779 | 19647081
MCR004387 | HPR015 | 2020-04-01 | Material | 11383779 | 44193537 | 48217055
MCR004388 | HPR015 | 2020-04-01 | Equipment | 2842025 | 11033166 | 11135853
MCR004389 | HPR015 | 2020-04-01 | Subcontract | 13294056 | 51609521 | 46235991
MCR004390 | HPR015 | 2020-04-01 | Overhead | 3704200 | 14380261 | 26879929
MCR004391 | HPR015 | 2020-05-01 | Labor | 0 | 13925490 | 15412258
MCR004392 | HPR015 | 2020-05-01 | Material | 0 | 27876199 | 28648051
MCR004393 | HPR015 | 2020-05-01 | Equipment | 0 | 6959450 | 6988862
MCR004394 | HPR015 | 2020-05-01 | Subcontract | 0 | 32554019 | 36751797
MCR004395 | HPR015 | 2020-05-01 | Overhead | 0 | 9070716 | 27600294
MCR004396 | HPR015 | 2020-06-01 | Labor | 0 | 4793125 | 3482397
MCR004397 | HPR015 | 2020-06-01 | Material | 0 | 9594930 | 9643194
MCR004398 | HPR015 | 2020-06-01 | Equipment | 0 | 2395428 | 2848230
MCR004399 | HPR015 | 2020-06-01 | Subcontract | 0 | 11205026 | 10627416
MCR004400 | HPR015 | 2020-06-01 | Overhead | 0 | 3122122 | 28016621
MCR004401 | HPR016 | 2021-08-01 | Labor | 2382166 | 1362088 | 1512323
MCR004402 | HPR016 | 2021-08-01 | Material | 4839349 | 2767070 | 3030030
MCR004403 | HPR016 | 2021-08-01 | Equipment | 1007277 | 575947 | 563054
MCR004404 | HPR016 | 2021-08-01 | Subcontract | 4069959 | 2327144 | 2559846
MCR004405 | HPR016 | 2021-08-01 | Overhead | 1431325 | 818411 | 13553821
MCR004406 | HPR016 | 2021-09-01 | Labor | 6892189 | 4243058 | 4289415
MCR004407 | HPR016 | 2021-09-01 | Material | 14001420 | 8619733 | 8555480
MCR004408 | HPR016 | 2021-09-01 | Equipment | 2914299 | 1794138 | 1966073
MCR004409 | HPR016 | 2021-09-01 | Subcontract | 11775387 | 7249314 | 7275144
MCR004410 | HPR016 | 2021-09-01 | Overhead | 4141174 | 2549442 | 11885657
MCR004411 | HPR016 | 2021-10-01 | Labor | 11024830 | 7268949 | 8855034
MCR004412 | HPR016 | 2021-10-01 | Material | 22396842 | 14766804 | 14352680
MCR004413 | HPR016 | 2021-10-01 | Equipment | 4661748 | 3073609 | 3083804
MCR004414 | HPR016 | 2021-10-01 | Subcontract | 18836052 | 12419085 | 13577861
MCR004415 | HPR016 | 2021-10-01 | Overhead | 6624272 | 4367550 | 11974170
MCR004416 | HPR016 | 2021-11-01 | Labor | 14785664 | 9909323 | 10682150
MCR004417 | HPR016 | 2021-11-01 | Material | 30036943 | 20130699 | 22424771
MCR004418 | HPR016 | 2021-11-01 | Equipment | 6251983 | 4190066 | 4122202
MCR004419 | HPR016 | 2021-11-01 | Subcontract | 25261481 | 16930195 | 16423156
MCR004420 | HPR016 | 2021-11-01 | Overhead | 8883970 | 5954019 | 12565951
MCR004421 | HPR016 | 2021-12-01 | Labor | 18180444 | 8305172 | 9744812
MCR004422 | HPR016 | 2021-12-01 | Material | 36933407 | 16871882 | 15398073
MCR004423 | HPR016 | 2021-12-01 | Equipment | 7687434 | 3511766 | 4097690
MCR004424 | HPR016 | 2021-12-01 | Subcontract | 31061503 | 14189484 | 15575789
MCR004425 | HPR016 | 2021-12-01 | Overhead | 10923725 | 4990165 | 12254946
MCR004426 | HPR016 | 2022-01-01 | Labor | 21215112 | 9484878 | 10780885
MCR004427 | HPR016 | 2022-01-01 | Material | 43098307 | 19268444 | 21054377
MCR004428 | HPR016 | 2022-01-01 | Equipment | 8970616 | 4010594 | 3758832
MCR004429 | HPR016 | 2022-01-01 | Subcontract | 36246268 | 16205026 | 18575553
MCR004430 | HPR016 | 2022-01-01 | Overhead | 12747105 | 5698991 | 13114697
MCR004431 | HPR016 | 2022-02-01 | Labor | 23895812 | 18689999 | 19090169
MCR004432 | HPR016 | 2022-02-01 | Material | 48544125 | 37968562 | 36835633
MCR004433 | HPR016 | 2022-02-01 | Equipment | 10104125 | 7902895 | 7724844
MCR004434 | HPR016 | 2022-02-01 | Subcontract | 40826276 | 31932083 | 30446610
MCR004435 | HPR016 | 2022-02-01 | Overhead | 14357805 | 11229890 | 12824825
MCR004436 | HPR016 | 2022-03-01 | Labor | 26228911 | 15773892 | 19167853
MCR004437 | HPR016 | 2022-03-01 | Material | 53283794 | 32044519 | 35944082
MCR004438 | HPR016 | 2022-03-01 | Equipment | 11090655 | 6669846 | 7178774
MCR004439 | HPR016 | 2022-03-01 | Subcontract | 44812402 | 26949881 | 27501680
MCR004440 | HPR016 | 2022-03-01 | Overhead | 15759648 | 9477747 | 12507847
MCR004441 | HPR016 | 2022-04-01 | Labor | 28221012 | 17495874 | 20074192
MCR004442 | HPR016 | 2022-04-01 | Material | 57330730 | 35542708 | 34484164
MCR004443 | HPR016 | 2022-04-01 | Equipment | 11932997 | 7397970 | 8247963
MCR004444 | HPR016 | 2022-04-01 | Subcontract | 48215932 | 29891906 | 30947001
MCR004445 | HPR016 | 2022-04-01 | Overhead | 16956602 | 10512400 | 13051128
MCR004446 | HPR016 | 2022-05-01 | Labor | 29878981 | 27726687 | 31458730
MCR004447 | HPR016 | 2022-05-01 | Material | 60698879 | 56326513 | 68962591
MCR004448 | HPR016 | 2022-05-01 | Equipment | 12634054 | 11723976 | 13255167
MCR004449 | HPR016 | 2022-05-01 | Subcontract | 51048591 | 47371371 | 46341435
MCR004450 | HPR016 | 2022-05-01 | Overhead | 17952794 | 16659587 | 13127843
MCR004451 | HPR016 | 2022-06-01 | Labor | 31209966 | 23370808 | 26347908
MCR004452 | HPR016 | 2022-06-01 | Material | 63402763 | 47477584 | 46216023
MCR004453 | HPR016 | 2022-06-01 | Equipment | 13196848 | 9882132 | 8783371
MCR004454 | HPR016 | 2022-06-01 | Subcontract | 53322594 | 39929300 | 48214429
MCR004455 | HPR016 | 2022-06-01 | Overhead | 18752516 | 14042356 | 12654776
MCR004456 | HPR016 | 2022-07-01 | Labor | 32221426 | 24219646 | 28504116
MCR004457 | HPR016 | 2022-07-01 | Material | 65457534 | 49201992 | 48224059
MCR004458 | HPR016 | 2022-07-01 | Equipment | 13624535 | 10241056 | 11471458
MCR004459 | HPR016 | 2022-07-01 | Subcontract | 55050685 | 41379551 | 37587844
MCR004460 | HPR016 | 2022-07-01 | Overhead | 19360252 | 14552381 | 11742209
MCR004461 | HPR016 | 2022-08-01 | Labor | 32921162 | 15979734 | 17502185
MCR004462 | HPR016 | 2022-08-01 | Material | 66879042 | 32462685 | 34008288
MCR004463 | HPR016 | 2022-08-01 | Equipment | 13920412 | 6756884 | 5433204
MCR004464 | HPR016 | 2022-08-01 | Subcontract | 56246193 | 27301564 | 28374035
MCR004465 | HPR016 | 2022-08-01 | Overhead | 19780689 | 9601427 | 13431163
MCR004466 | HPR016 | 2022-09-01 | Labor | 33317357 | 21786487 | 28058330
MCR004467 | HPR016 | 2022-09-01 | Material | 67683908 | 44259050 | 42978285
MCR004468 | HPR016 | 2022-09-01 | Equipment | 14087939 | 9212216 | 10736669
MCR004469 | HPR016 | 2022-09-01 | Subcontract | 56923097 | 37222469 | 45590440
MCR004470 | HPR016 | 2022-09-01 | Overhead | 20018742 | 13090416 | 12221026
MCR004471 | HPR016 | 2022-10-01 | Labor | 33418613 | 34189448 | 41607705
MCR004472 | HPR016 | 2022-10-01 | Material | 67889609 | 69455552 | 80077794
MCR004473 | HPR016 | 2022-10-01 | Equipment | 14130755 | 14456695 | 15720467
MCR004474 | HPR016 | 2022-10-01 | Subcontract | 57096094 | 58413074 | 58056246
MCR004475 | HPR016 | 2022-10-01 | Overhead | 20079582 | 20542738 | 12763986
MCR004476 | HPR016 | 2022-11-01 | Labor | 33234007 | 25143984 | 27589878
MCR004477 | HPR016 | 2022-11-01 | Material | 67514582 | 51079775 | 50247473
MCR004478 | HPR016 | 2022-11-01 | Equipment | 14052695 | 10631903 | 8445029
MCR004479 | HPR016 | 2022-11-01 | Subcontract | 56780691 | 42958792 | 40015536
MCR004480 | HPR016 | 2022-11-01 | Overhead | 19968661 | 15107769 | 13215652
MCR004481 | HPR016 | 2022-12-01 | Labor | 32773146 | 36275721 | 47439851
MCR004482 | HPR016 | 2022-12-01 | Material | 66578348 | 73693797 | 78529997
MCR004483 | HPR016 | 2022-12-01 | Equipment | 13857825 | 15338857 | 15784186
MCR004484 | HPR016 | 2022-12-01 | Subcontract | 55993305 | 61977496 | 67591348
MCR004485 | HPR016 | 2022-12-01 | Overhead | 19691753 | 21796276 | 12314948
MCR004486 | HPR016 | 2023-01-01 | Labor | 32046244 | 26313239 | 23920199
MCR004487 | HPR016 | 2023-01-01 | Material | 65101653 | 53455106 | 53379298
MCR004488 | HPR016 | 2023-01-01 | Equipment | 13550461 | 11126312 | 10940220
MCR004489 | HPR016 | 2023-01-01 | Subcontract | 54751384 | 44956478 | 47341271
MCR004490 | HPR016 | 2023-01-01 | Overhead | 19254994 | 15810316 | 11618209
MCR004491 | HPR016 | 2023-02-01 | Labor | 31064206 | 45617887 | 52528204
MCR004492 | HPR016 | 2023-02-01 | Material | 63106652 | 92672322 | 106390806
MCR004493 | HPR016 | 2023-02-01 | Equipment | 13135215 | 19289106 | 20521664
MCR004494 | HPR016 | 2023-02-01 | Subcontract | 53073562 | 77938696 | 76548745
MCR004495 | HPR016 | 2023-02-01 | Overhead | 18664936 | 27409519 | 12449324
MCR004496 | HPR016 | 2023-03-01 | Labor | 29838739 | 16241484 | 20568158
MCR004497 | HPR016 | 2023-03-01 | Material | 60617127 | 32994427 | 26579438
MCR004498 | HPR016 | 2023-03-01 | Equipment | 12617038 | 6867563 | 7694462
MCR004499 | HPR016 | 2023-03-01 | Subcontract | 50979837 | 27748766 | 34071299
MCR004500 | HPR016 | 2023-03-01 | Overhead | 17928614 | 9758700 | 11926376
MCR004501 | HPR016 | 2023-04-01 | Labor | 28382484 | 35094358 | 44712847
MCR004502 | HPR016 | 2023-04-01 | Material | 57658758 | 71293869 | 72136092
MCR004503 | HPR016 | 2023-04-01 | Equipment | 12001273 | 14839328 | 16949586
MCR004504 | HPR016 | 2023-04-01 | Subcontract | 48491807 | 59959124 | 53605923
MCR004505 | HPR016 | 2023-04-01 | Overhead | 17053623 | 21086454 | 12478695
MCR004506 | HPR016 | 2023-05-01 | Labor | 26709188 | 43940652 | 47383055
MCR004507 | HPR016 | 2023-05-01 | Material | 54259473 | 89265036 | 89947846
MCR004508 | HPR016 | 2023-05-01 | Equipment | 11293736 | 18579903 | 18073240
MCR004509 | HPR016 | 2023-05-01 | Subcontract | 45632962 | 75073122 | 75361846
MCR004510 | HPR016 | 2023-05-01 | Overhead | 16048223 | 26401752 | 11919602
MCR004511 | HPR016 | 2023-06-01 | Labor | 24833929 | 23884322 | 24025673
MCR004512 | HPR016 | 2023-06-01 | Material | 50449901 | 48520782 | 48043281
MCR004513 | HPR016 | 2023-06-01 | Equipment | 10500800 | 10099267 | 10582296
MCR004514 | HPR016 | 2023-06-01 | Subcontract | 42429060 | 40806645 | 52129620
MCR004515 | HPR016 | 2023-06-01 | Overhead | 14921473 | 14350901 | 12711342
MCR004516 | HPR016 | 2023-07-01 | Labor | 22773405 | 22241661 | 25327405
MCR004517 | HPR016 | 2023-07-01 | Material | 46263966 | 45183731 | 47359932
MCR004518 | HPR016 | 2023-07-01 | Equipment | 9629526 | 9404683 | 9493970
MCR004519 | HPR016 | 2023-07-01 | Subcontract | 38908631 | 38000139 | 32494189
MCR004520 | HPR016 | 2023-07-01 | Overhead | 13683406 | 13363907 | 12982930
MCR004521 | HPR016 | 2023-08-01 | Labor | 20546338 | 15572536 | 18759980
MCR004522 | HPR016 | 2023-08-01 | Material | 41739699 | 31635465 | 31149748
MCR004523 | HPR016 | 2023-08-01 | Equipment | 8687831 | 6584704 | 7580681
MCR004524 | HPR016 | 2023-08-01 | Subcontract | 35103660 | 26605861 | 32325873
MCR004525 | HPR016 | 2023-08-01 | Overhead | 12345272 | 9356762 | 12684259
MCR004526 | HPR016 | 2023-09-01 | Labor | 18174032 | 21876719 | 25773129
MCR004527 | HPR016 | 2023-09-01 | Material | 36920381 | 44442356 | 47365239
MCR004528 | HPR016 | 2023-09-01 | Equipment | 7684723 | 9250370 | 7572483
MCR004529 | HPR016 | 2023-09-01 | Subcontract | 31050548 | 37376632 | 36879386
MCR004530 | HPR016 | 2023-09-01 | Overhead | 10919872 | 13144632 | 11873887
MCR004531 | HPR016 | 2023-10-01 | Labor | 15681196 | 17516338 | 21140129
MCR004532 | HPR016 | 2023-10-01 | Material | 31856207 | 35584281 | 36151400
MCR004533 | HPR016 | 2023-10-01 | Equipment | 6630650 | 7406623 | 8476889
MCR004534 | HPR016 | 2023-10-01 | Subcontract | 26791508 | 29926869 | 51814585
MCR004535 | HPR016 | 2023-10-01 | Overhead | 9422051 | 10524696 | 13660506
MCR004536 | HPR016 | 2023-11-01 | Labor | 13097203 | 15419249 | 17330052
MCR004537 | HPR016 | 2023-11-01 | Material | 26606849 | 31324064 | 30248211
MCR004538 | HPR016 | 2023-11-01 | Equipment | 5538032 | 6519888 | 6336750
MCR004539 | HPR016 | 2023-11-01 | Subcontract | 22376725 | 26343968 | 58771094
MCR004540 | HPR016 | 2023-11-01 | Overhead | 7869458 | 9264660 | 13406083
MCR004541 | HPR016 | 2023-12-01 | Labor | 10458156 | 26471146 | 29697787
MCR004542 | HPR016 | 2023-12-01 | Material | 21245648 | 53775893 | 55587205
MCR004543 | HPR016 | 2023-12-01 | Equipment | 4422135 | 11193082 | 10674387
MCR004544 | HPR016 | 2023-12-01 | Subcontract | 17867882 | 45226265 | 68654292
MCR004545 | HPR016 | 2023-12-01 | Overhead | 6283786 | 15905195 | 13605165
MCR004546 | HPR016 | 2024-01-01 | Labor | 7810588 | 17870385 | 19457284
MCR004547 | HPR016 | 2024-01-01 | Material | 15867139 | 36303524 | 34008819
MCR004548 | HPR016 | 2024-01-01 | Equipment | 3302636 | 7556329 | 7759837
MCR004549 | HPR016 | 2024-01-01 | Subcontract | 13344482 | 30531763 | 50147239
MCR004550 | HPR016 | 2024-01-01 | Overhead | 4692994 | 10737425 | 12834563
MCR004551 | HPR016 | 2024-02-01 | Labor | 5219019 | 14329408 | 14956267
MCR004552 | HPR016 | 2024-02-01 | Material | 10602390 | 29110063 | 30834416
MCR004553 | HPR016 | 2024-02-01 | Equipment | 2206814 | 6059059 | 7112344
MCR004554 | HPR016 | 2024-02-01 | Subcontract | 8916756 | 24481963 | 46924219
MCR004555 | HPR016 | 2024-02-01 | Overhead | 3135849 | 8609829 | 11969991
MCR004556 | HPR016 | 2024-03-01 | Labor | 2785097 | 10515308 | 12009510
MCR004557 | HPR016 | 2024-03-01 | Material | 5657899 | 21361753 | 19220741
MCR004558 | HPR016 | 2024-03-01 | Equipment | 1177653 | 4446302 | 4023204
MCR004559 | HPR016 | 2024-03-01 | Subcontract | 4758371 | 17965528 | 45353686
MCR004560 | HPR016 | 2024-03-01 | Overhead | 1673426 | 6318126 | 12543818
MCR004561 | HPR016 | 2024-04-01 | Labor | 729403 | 15956338 | 17960855
MCR004562 | HPR016 | 2024-04-01 | Material | 1481775 | 32415155 | 32177514
MCR004563 | HPR016 | 2024-04-01 | Equipment | 308421 | 6746991 | 5935581
MCR004564 | HPR016 | 2024-04-01 | Subcontract | 1246193 | 27261591 | 61370282
MCR004565 | HPR016 | 2024-04-01 | Overhead | 438262 | 9587370 | 13806895
MCR004566 | HPR016 | 2024-05-01 | Labor | 0 | 5729878 | 6587565
MCR004567 | HPR016 | 2024-05-01 | Material | 0 | 11640195 | 13128818
MCR004568 | HPR016 | 2024-05-01 | Equipment | 0 | 2422827 | 3078888
MCR004569 | HPR016 | 2024-05-01 | Subcontract | 0 | 9789564 | 23232899
MCR004570 | HPR016 | 2024-05-01 | Overhead | 0 | 3442799 | 13707999
MCR004571 | HPR016 | 2024-06-01 | Labor | 0 | 11702751 | 12471528
MCR004572 | HPR016 | 2024-06-01 | Material | 0 | 23774032 | 23097087
MCR004573 | HPR016 | 2024-06-01 | Equipment | 0 | 4948401 | 5726227
MCR004574 | HPR016 | 2024-06-01 | Subcontract | 0 | 19994287 | 34369850
MCR004575 | HPR016 | 2024-06-01 | Overhead | 0 | 7031601 | 12114241
MCR004576 | HPR016 | 2024-07-01 | Labor | 0 | 4261920 | 5654038
MCR004577 | HPR016 | 2024-07-01 | Material | 0 | 8658052 | 11054938
MCR004578 | HPR016 | 2024-07-01 | Equipment | 0 | 1802114 | 1510278
MCR004579 | HPR016 | 2024-07-01 | Subcontract | 0 | 7281541 | 26925250
MCR004580 | HPR016 | 2024-07-01 | Overhead | 0 | 2560776 | 13619267
MCR004581 | HPR016 | 2024-08-01 | Labor | 0 | 3732055 | 4060925
MCR004582 | HPR016 | 2024-08-01 | Material | 0 | 7581636 | 8023470
MCR004583 | HPR016 | 2024-08-01 | Equipment | 0 | 1578065 | 1974250
MCR004584 | HPR016 | 2024-08-01 | Subcontract | 0 | 6376260 | 30525996
MCR004585 | HPR016 | 2024-08-01 | Overhead | 0 | 2242406 | 12892882
MCR004586 | HPR016 | 2024-09-01 | Labor | 0 | 4188818 | 4471472
MCR004587 | HPR016 | 2024-09-01 | Material | 0 | 8509545 | 7983332
MCR004588 | HPR016 | 2024-09-01 | Equipment | 0 | 1771203 | 1860666
MCR004589 | HPR016 | 2024-09-01 | Subcontract | 0 | 7156644 | 21972740
MCR004590 | HPR016 | 2024-09-01 | Overhead | 0 | 2516852 | 13090235
MCR004591 | HPR016 | 2024-10-01 | Labor | 0 | 1734501 | 2027219
MCR004592 | HPR016 | 2024-10-01 | Material | 0 | 3523623 | 3863583
MCR004593 | HPR016 | 2024-10-01 | Equipment | 0 | 733418 | 745815
MCR004594 | HPR016 | 2024-10-01 | Subcontract | 0 | 2963415 | 39860026
MCR004595 | HPR016 | 2024-10-01 | Overhead | 0 | 1042175 | 13131106
MCR004596 | HPR016 | 2024-11-01 | Labor | 0 | 513328 | 565503
MCR004597 | HPR016 | 2024-11-01 | Material | 0 | 1042820 | 802665
MCR004598 | HPR016 | 2024-11-01 | Equipment | 0 | 217056 | 278294
MCR004599 | HPR016 | 2024-11-01 | Subcontract | 0 | 877026 | 17722699
MCR004600 | HPR016 | 2024-11-01 | Overhead | 0 | 308433 | 11875456
MCR004601 | HPR017 | 2019-12-01 | Labor | 3582047 | 1979716 | 2154642
MCR004602 | HPR017 | 2019-12-01 | Material | 9483387 | 5241253 | 5376224
MCR004603 | HPR017 | 2019-12-01 | Equipment | 3054097 | 1687930 | 1687107
MCR004604 | HPR017 | 2019-12-01 | Subcontract | 6746146 | 3728442 | 4064591
MCR004605 | HPR017 | 2019-12-01 | Overhead | 2577348 | 1424442 | 14027594
MCR004606 | HPR017 | 2020-01-01 | Labor | 10073984 | 5334245 | 5586212
MCR004607 | HPR017 | 2020-01-01 | Material | 26670643 | 14122293 | 13995765
MCR004608 | HPR017 | 2020-01-01 | Equipment | 8589202 | 4548043 | 4146806
MCR004609 | HPR017 | 2020-01-01 | Subcontract | 18972551 | 10046099 | 12702338
MCR004610 | HPR017 | 2020-01-01 | Overhead | 7248416 | 3838087 | 13215459
MCR004611 | HPR017 | 2020-02-01 | Labor | 15577095 | 8840752 | 8720803
MCR004612 | HPR017 | 2020-02-01 | Material | 41240005 | 23405689 | 25107700
MCR004613 | HPR017 | 2020-02-01 | Equipment | 13281222 | 7537733 | 8621509
MCR004614 | HPR017 | 2020-02-01 | Subcontract | 29336678 | 16649978 | 16443617
MCR004615 | HPR017 | 2020-02-01 | Overhead | 11208005 | 6361082 | 14100421
MCR004616 | HPR017 | 2020-03-01 | Labor | 20118425 | 9114205 | 9184083
MCR004617 | HPR017 | 2020-03-01 | Material | 53263073 | 24129651 | 25732085
MCR004618 | HPR017 | 2020-03-01 | Equipment | 17153216 | 7770883 | 7715505
MCR004619 | HPR017 | 2020-03-01 | Subcontract | 37889463 | 17164979 | 21461463
MCR004620 | HPR017 | 2020-03-01 | Overhead | 14475575 | 6557837 | 13254384
MCR004621 | HPR017 | 2020-04-01 | Labor | 23726643 | 19761349 | 22491611
MCR004622 | HPR017 | 2020-04-01 | Material | 62815749 | 52317722 | 44064947
MCR004623 | HPR017 | 2020-04-01 | Equipment | 20229627 | 16848769 | 16803477
MCR004624 | HPR017 | 2020-04-01 | Subcontract | 44684898 | 37216974 | 33400525
MCR004625 | HPR017 | 2020-04-01 | Overhead | 17071754 | 14218652 | 12256876
MCR004626 | HPR017 | 2020-05-01 | Labor | 26432283 | 14971705 | 15478579
MCR004627 | HPR017 | 2020-05-01 | Material | 69978867 | 39637249 | 37968523
MCR004628 | HPR017 | 2020-05-01 | Equipment | 22536488 | 12765059 | 14475910
MCR004629 | HPR017 | 2020-05-01 | Subcontract | 49780487 | 28196534 | 34850726
MCR004630 | HPR017 | 2020-05-01 | Overhead | 19018510 | 10772415 | 12848415
MCR004631 | HPR017 | 2020-06-01 | Labor | 28268032 | 16853181 | 19273685
MCR004632 | HPR017 | 2020-06-01 | Material | 74838971 | 44618413 | 55959791
MCR004633 | HPR017 | 2020-06-01 | Equipment | 24101671 | 14369229 | 14777128
MCR004634 | HPR017 | 2020-06-01 | Subcontract | 53237793 | 31739958 | 38922229
MCR004635 | HPR017 | 2020-06-01 | Overhead | 20339366 | 12126172 | 14142363
MCR004636 | HPR017 | 2020-07-01 | Labor | 29269107 | 14075252 | 18166164
MCR004637 | HPR017 | 2020-07-01 | Material | 77489295 | 37263911 | 26189036
MCR004638 | HPR017 | 2020-07-01 | Equipment | 24955199 | 12000733 | 11658816
MCR004639 | HPR017 | 2020-07-01 | Subcontract | 55123139 | 26508226 | 28776848
MCR004640 | HPR017 | 2020-07-01 | Overhead | 21059657 | 10127401 | 13484337
MCR004641 | HPR017 | 2020-08-01 | Labor | 29473727 | 19859876 | 17893477
MCR004642 | HPR017 | 2020-08-01 | Material | 78031021 | 52578570 | 62240290
MCR004643 | HPR017 | 2020-08-01 | Equipment | 25129661 | 16932774 | 18942618
MCR004644 | HPR017 | 2020-08-01 | Subcontract | 55508504 | 37402531 | 45978507
MCR004645 | HPR017 | 2020-08-01 | Overhead | 21206885 | 14289544 | 13567460
MCR004646 | HPR017 | 2020-09-01 | Labor | 28923736 | 21609141 | 25547769
MCR004647 | HPR017 | 2020-09-01 | Material | 76574933 | 57209710 | 59900045
MCR004648 | HPR017 | 2020-09-01 | Equipment | 24660732 | 18424219 | 20738837
MCR004649 | HPR017 | 2020-09-01 | Subcontract | 54472694 | 40696961 | 40676946
MCR004650 | HPR017 | 2020-09-01 | Overhead | 20811157 | 15548172 | 13989889
MCR004651 | HPR017 | 2020-10-01 | Labor | 27665445 | 22416998 | 23968834
MCR004652 | HPR017 | 2020-10-01 | Material | 73243638 | 59348494 | 64067186
MCR004653 | HPR017 | 2020-10-01 | Equipment | 23587898 | 19113008 | 18649050
MCR004654 | HPR017 | 2020-10-01 | Subcontract | 52102929 | 42218416 | 46534694
MCR004655 | HPR017 | 2020-10-01 | Overhead | 19905794 | 16129440 | 13117611
MCR004656 | HPR017 | 2020-11-01 | Labor | 25750800 | 18098703 | 21791844
MCR004657 | HPR017 | 2020-11-01 | Material | 68174658 | 47915905 | 45546563
MCR004658 | HPR017 | 2020-11-01 | Equipment | 21955448 | 15431176 | 17461449
MCR004659 | HPR017 | 2020-11-01 | Subcontract | 48497036 | 34085677 | 44317255
MCR004660 | HPR017 | 2020-11-01 | Overhead | 18528171 | 13022348 | 12676078
MCR004661 | HPR017 | 2020-12-01 | Labor | 23239067 | 39521124 | 44579780
MCR004662 | HPR017 | 2020-12-01 | Material | 61524901 | 104631277 | 113940001
MCR004663 | HPR017 | 2020-12-01 | Equipment | 19813913 | 33696195 | 36049444
MCR004664 | HPR017 | 2020-12-01 | Subcontract | 43766635 | 74430983 | 84024053
MCR004665 | HPR017 | 2020-12-01 | Overhead | 16720933 | 28436171 | 14501486
MCR004666 | HPR017 | 2021-01-01 | Labor | 20199394 | 15264181 | 16538136
MCR004667 | HPR017 | 2021-01-01 | Material | 53477437 | 40411573 | 34476243
MCR004668 | HPR017 | 2021-01-01 | Equipment | 17222251 | 13014428 | 10145783
MCR004669 | HPR017 | 2021-01-01 | Subcontract | 38041954 | 28747361 | 32110367
MCR004670 | HPR017 | 2021-01-01 | Overhead | 14533833 | 10982858 | 13662842
MCR004671 | HPR017 | 2021-02-01 | Labor | 16714962 | 17674696 | 17979118
MCR004672 | HPR017 | 2021-02-01 | Material | 44252483 | 46793355 | 47672498
MCR004673 | HPR017 | 2021-02-01 | Equipment | 14251382 | 15069662 | 19132894
MCR004674 | HPR017 | 2021-02-01 | Subcontract | 31479649 | 33287135 | 39515463
MCR004675 | HPR017 | 2021-02-01 | Overhead | 12026721 | 12717267 | 13995686
MCR004676 | HPR017 | 2021-03-01 | Labor | 12890310 | 21439120 | 28464286
MCR004677 | HPR017 | 2021-03-01 | Material | 34126804 | 56759584 | 58840609
MCR004678 | HPR017 | 2021-03-01 | Equipment | 10990437 | 18279257 | 15498663
MCR004679 | HPR017 | 2021-03-01 | Subcontract | 24276599 | 40376757 | 48475067
MCR004680 | HPR017 | 2021-03-01 | Overhead | 9274814 | 15425839 | 13311315
MCR004681 | HPR017 | 2021-04-01 | Labor | 8866079 | 11507213 | 10799401
MCR004682 | HPR017 | 2021-04-01 | Material | 23472744 | 30465086 | 33278170
MCR004683 | HPR017 | 2021-04-01 | Equipment | 7559328 | 9811191 | 11437950
MCR004684 | HPR017 | 2021-04-01 | Subcontract | 16697678 | 21671783 | 25437394
MCR004685 | HPR017 | 2021-04-01 | Overhead | 6379306 | 8279650 | 13414423
MCR004686 | HPR017 | 2021-05-01 | Labor | 4855766 | 25112412 | 31592888
MCR004687 | HPR017 | 2021-05-01 | Material | 12855530 | 66484540 | 70440322
MCR004688 | HPR017 | 2021-05-01 | Equipment | 4140086 | 21411151 | 22076239
MCR004689 | HPR017 | 2021-05-01 | Subcontract | 9144968 | 47294746 | 49258126
MCR004690 | HPR017 | 2021-05-01 | Overhead | 3493812 | 18068840 | 13294220
MCR004691 | HPR017 | 2021-06-01 | Labor | 1299357 | 17863027 | 33823386
MCR004692 | HPR017 | 2021-06-01 | Material | 3440019 | 47291957 | 63567581
MCR004693 | HPR017 | 2021-06-01 | Equipment | 1107848 | 15230236 | 17239608
MCR004694 | HPR017 | 2021-06-01 | Subcontract | 2447107 | 33641823 | 36833912
MCR004695 | HPR017 | 2021-06-01 | Overhead | 934911 | 12852774 | 14637447
MCR004696 | HPR017 | 2021-07-01 | Labor | 0 | 9129925 | 30052298
MCR004697 | HPR017 | 2021-07-01 | Material | 0 | 24171269 | 39261443
MCR004698 | HPR017 | 2021-07-01 | Equipment | 0 | 7784286 | 6029527
MCR004699 | HPR017 | 2021-07-01 | Subcontract | 0 | 17194585 | 23161889
MCR004700 | HPR017 | 2021-07-01 | Overhead | 0 | 6569148 | 13378950
MCR004701 | HPR017 | 2021-08-01 | Labor | 0 | 7623503 | 7984051
MCR004702 | HPR017 | 2021-08-01 | Material | 0 | 20183052 | 19989589
MCR004703 | HPR017 | 2021-08-01 | Equipment | 0 | 6499892 | 7932685
MCR004704 | HPR017 | 2021-08-01 | Subcontract | 0 | 14357508 | 13670208
MCR004705 | HPR017 | 2021-08-01 | Overhead | 0 | 5485250 | 13331907
MCR004706 | HPR017 | 2021-09-01 | Labor | 0 | 4807506 | 6781348
MCR004707 | HPR017 | 2021-09-01 | Material | 0 | 12727762 | 14326806
MCR004708 | HPR017 | 2021-09-01 | Equipment | 0 | 4098938 | 4961293
MCR004709 | HPR017 | 2021-09-01 | Subcontract | 0 | 9054079 | 11902543
MCR004710 | HPR017 | 2021-09-01 | Overhead | 0 | 3459088 | 13410651
MCR004711 | HPR017 | 2021-10-01 | Labor | 0 | 5447998 | 5880563
MCR004712 | HPR017 | 2021-10-01 | Material | 0 | 14423452 | 15597868
MCR004713 | HPR017 | 2021-10-01 | Equipment | 0 | 4645030 | 5583633
MCR004714 | HPR017 | 2021-10-01 | Subcontract | 0 | 10260333 | 10045318
MCR004715 | HPR017 | 2021-10-01 | Overhead | 0 | 3919934 | 13658945
MCR004716 | HPR017 | 2021-11-01 | Labor | 0 | 4454565 | 4973478
MCR004717 | HPR017 | 2021-11-01 | Material | 0 | 11793360 | 12768120
MCR004718 | HPR017 | 2021-11-01 | Equipment | 0 | 3798017 | 3609074
MCR004719 | HPR017 | 2021-11-01 | Subcontract | 0 | 8389379 | 10152687
MCR004720 | HPR017 | 2021-11-01 | Overhead | 0 | 3205141 | 12696902
MCR004721 | HPR017 | 2021-12-01 | Labor | 0 | 3223445 | 4506578
MCR004722 | HPR017 | 2021-12-01 | Material | 0 | 8533996 | 7968057
MCR004723 | HPR017 | 2021-12-01 | Equipment | 0 | 2748348 | 3786471
MCR004724 | HPR017 | 2021-12-01 | Subcontract | 0 | 6070783 | 7339126
MCR004725 | HPR017 | 2021-12-01 | Overhead | 0 | 2319327 | 14367162
MCR004726 | HPR017 | 2022-01-01 | Labor | 0 | 942420 | 860271
MCR004727 | HPR017 | 2022-01-01 | Material | 0 | 2495035 | 3076778
MCR004728 | HPR017 | 2022-01-01 | Equipment | 0 | 803519 | 789449
MCR004729 | HPR017 | 2022-01-01 | Subcontract | 0 | 1774879 | 2104793
MCR004730 | HPR017 | 2022-01-01 | Overhead | 0 | 678088 | 15253694
MCR004731 | HPR018 | 2022-02-01 | Labor | 11406016 | 12650208 | 12199552
MCR004732 | HPR018 | 2022-02-01 | Material | 22020166 | 24422172 | 25536226
MCR004733 | HPR018 | 2022-02-01 | Equipment | 5655866 | 6272819 | 6958409
MCR004734 | HPR018 | 2022-02-01 | Subcontract | 53777912 | 59644120 | 53382581
MCR004735 | HPR018 | 2022-02-01 | Overhead | 8552455 | 9485375 | 24833531
MCR004736 | HPR018 | 2022-03-01 | Labor | 30046309 | 19249417 | 20909584
MCR004737 | HPR018 | 2022-03-01 | Material | 58006645 | 37162438 | 37870773
MCR004738 | HPR018 | 2022-03-01 | Equipment | 14898970 | 9545149 | 8999403
MCR004739 | HPR018 | 2022-03-01 | Subcontract | 141664521 | 90758551 | 98220723
MCR004740 | HPR018 | 2022-03-01 | Overhead | 22529314 | 14433592 | 24664185
MCR004741 | HPR018 | 2022-04-01 | Labor | 42676803 | 26332487 | 26239060
MCR004742 | HPR018 | 2022-04-01 | Material | 82390758 | 50836834 | 52660001
MCR004743 | HPR018 | 2022-04-01 | Equipment | 21162014 | 13057409 | 13301345
MCR004744 | HPR018 | 2022-04-01 | Subcontract | 201215694 | 124154323 | 134083175
MCR004745 | HPR018 | 2022-04-01 | Overhead | 31999908 | 19744617 | 23897697
MCR004746 | HPR018 | 2022-05-01 | Labor | 49660700 | 35972725 | 34211687
MCR004747 | HPR018 | 2022-05-01 | Material | 95873694 | 69448034 | 65875890
MCR004748 | HPR018 | 2022-05-01 | Equipment | 24625098 | 17837684 | 18214775
MCR004749 | HPR018 | 2022-05-01 | Subcontract | 234143880 | 169606818 | 162585651
MCR004750 | HPR018 | 2022-05-01 | Overhead | 37236571 | 26973058 | 24958856
MCR004751 | HPR018 | 2022-06-01 | Labor | 51413351 | 33610360 | 33497771
MCR004752 | HPR018 | 2022-06-01 | Material | 99257317 | 64887311 | 76945726
MCR004753 | HPR018 | 2022-06-01 | Equipment | 25494179 | 16666265 | 17415612
MCR004754 | HPR018 | 2022-06-01 | Subcontract | 242407406 | 158468567 | 165234448
MCR004755 | HPR018 | 2022-06-01 | Overhead | 38550744 | 25201710 | 23961122
MCR004756 | HPR018 | 2022-07-01 | Labor | 48422455 | 23217449 | 24247960
MCR004757 | HPR018 | 2022-07-01 | Material | 93483169 | 44823020 | 39670233
MCR004758 | HPR018 | 2022-07-01 | Equipment | 24011093 | 11512764 | 10600934
MCR004759 | HPR018 | 2022-07-01 | Subcontract | 228305711 | 109467315 | 119040634
MCR004760 | HPR018 | 2022-07-01 | Overhead | 36308111 | 17408900 | 26925338
MCR004761 | HPR018 | 2022-08-01 | Labor | 41282995 | 26165701 | 26853220
MCR004762 | HPR018 | 2022-08-01 | Material | 79699908 | 50514841 | 49755979
MCR004763 | HPR018 | 2022-08-01 | Equipment | 20470871 | 12974705 | 14019807
MCR004764 | HPR018 | 2022-08-01 | Subcontract | 194644067 | 123367949 | 127561241
MCR004765 | HPR018 | 2022-08-01 | Overhead | 30954803 | 19619558 | 24245234
MCR004766 | HPR018 | 2022-09-01 | Labor | 30765796 | 47658791 | 45269569
MCR004767 | HPR018 | 2022-09-01 | Material | 59395669 | 92008858 | 101700679
MCR004768 | HPR018 | 2022-09-01 | Equipment | 15255740 | 23632417 | 25093245
MCR004769 | HPR018 | 2022-09-01 | Subcontract | 145056812 | 224705133 | 253157561
MCR004770 | HPR018 | 2022-09-01 | Overhead | 23068800 | 35735500 | 22907935
MCR004771 | HPR018 | 2022-10-01 | Labor | 17983579 | 62128103 | 61273755
MCR004772 | HPR018 | 2022-10-01 | Material | 34718644 | 119942946 | 121223456
MCR004773 | HPR018 | 2022-10-01 | Equipment | 8917462 | 30807270 | 32801757
MCR004774 | HPR018 | 2022-10-01 | Subcontract | 84790287 | 292926095 | 279159326
MCR004775 | HPR018 | 2022-10-01 | Overhead | 13484442 | 46584875 | 25137248
MCR004776 | HPR018 | 2022-11-01 | Labor | 5057768 | 23878506 | 27200240
MCR004777 | HPR018 | 2022-11-01 | Material | 9764399 | 46099240 | 44634789
MCR004778 | HPR018 | 2022-11-01 | Equipment | 2507980 | 11840561 | 11499633
MCR004779 | HPR018 | 2022-11-01 | Subcontract | 23846733 | 112584116 | 181091027
MCR004780 | HPR018 | 2022-11-01 | Overhead | 3792414 | 17904574 | 27412812
MCR004781 | HPR018 | 2022-12-01 | Labor | 0 | 12522638 | 12358930
MCR004782 | HPR018 | 2022-12-01 | Material | 0 | 24175889 | 27010985
MCR004783 | HPR018 | 2022-12-01 | Equipment | 0 | 6209562 | 5777462
MCR004784 | HPR018 | 2022-12-01 | Subcontract | 0 | 59042645 | 77848724
MCR004785 | HPR018 | 2022-12-01 | Overhead | 0 | 9389721 | 23417264
MCR004786 | HPR018 | 2023-01-01 | Labor | 0 | 5329390 | 5329982
MCR004787 | HPR018 | 2023-01-01 | Material | 0 | 10288785 | 7751468
MCR004788 | HPR018 | 2023-01-01 | Equipment | 0 | 2642668 | 2939378
MCR004789 | HPR018 | 2023-01-01 | Subcontract | 0 | 25127393 | 81390608
MCR004790 | HPR018 | 2023-01-01 | Overhead | 0 | 3996081 | 22979701
MCR004791 | HPR019 | 2016-09-01 | Labor | 2334402 | 2039554 | 1661767
MCR004792 | HPR019 | 2016-09-01 | Material | 5610629 | 4901975 | 5062861
MCR004793 | HPR019 | 2016-09-01 | Equipment | 1820772 | 1590798 | 1761599
MCR004794 | HPR019 | 2016-09-01 | Subcontract | 6661952 | 5820510 | 5788889
MCR004795 | HPR019 | 2016-09-01 | Overhead | 1541163 | 1346505 | 11743118
MCR004796 | HPR019 | 2016-10-01 | Labor | 6708644 | 7077907 | 7298389
MCR004797 | HPR019 | 2016-10-01 | Material | 16123919 | 17011425 | 16447044
MCR004798 | HPR019 | 2016-10-01 | Equipment | 5232565 | 5520580 | 5407147
MCR004799 | HPR019 | 2016-10-01 | Subcontract | 19145231 | 20199039 | 21372068
MCR004800 | HPR019 | 2016-10-01 | Overhead | 4429019 | 4672805 | 11378923
MCR004801 | HPR019 | 2016-11-01 | Labor | 10646661 | 5157093 | 5289368
MCR004802 | HPR019 | 2016-11-01 | Material | 25588765 | 12394838 | 13136392
MCR004803 | HPR019 | 2016-11-01 | Equipment | 8304115 | 4022396 | 4062136
MCR004804 | HPR019 | 2016-11-01 | Subcontract | 30383607 | 14717392 | 15141765
MCR004805 | HPR019 | 2016-11-01 | Overhead | 7028882 | 3404692 | 10831717
MCR004806 | HPR019 | 2016-12-01 | Labor | 14156167 | 12783005 | 13089517
MCR004807 | HPR019 | 2016-12-01 | Material | 34023702 | 30723370 | 31560425
MCR004808 | HPR019 | 2016-12-01 | Equipment | 11041436 | 9970406 | 9778847
MCR004809 | HPR019 | 2016-12-01 | Subcontract | 40399088 | 36480338 | 38070683
MCR004810 | HPR019 | 2016-12-01 | Overhead | 9345843 | 8439287 | 11046757
MCR004811 | HPR019 | 2017-01-01 | Labor | 17245166 | 10140579 | 8351646
MCR004812 | HPR019 | 2017-01-01 | Material | 41447968 | 24372418 | 21973767
MCR004813 | HPR019 | 2017-01-01 | Equipment | 13450773 | 7909383 | 9198035
MCR004814 | HPR019 | 2017-01-01 | Subcontract | 49214520 | 28939340 | 25813518
MCR004815 | HPR019 | 2017-01-01 | Overhead | 11385187 | 6694768 | 12059778
MCR004816 | HPR019 | 2017-02-01 | Labor | 19921981 | 19846079 | 20391258
MCR004817 | HPR019 | 2017-02-01 | Material | 47881573 | 47699144 | 47820932
MCR004818 | HPR019 | 2017-02-01 | Equipment | 15538619 | 15479417 | 15859321
MCR004819 | HPR019 | 2017-02-01 | Subcontract | 56853658 | 56637045 | 64878157
MCR004820 | HPR019 | 2017-02-01 | Overhead | 13152410 | 13102299 | 11800025
MCR004821 | HPR019 | 2017-03-01 | Labor | 22195289 | 21818615 | 21028468
MCR004822 | HPR019 | 2017-03-01 | Material | 53345365 | 52440046 | 56093155
MCR004823 | HPR019 | 2017-03-01 | Equipment | 17311739 | 17017943 | 17515361
MCR004824 | HPR019 | 2017-03-01 | Subcontract | 63341260 | 62266301 | 55930786
MCR004825 | HPR019 | 2017-03-01 | Overhead | 14653239 | 14404560 | 11924988
MCR004826 | HPR019 | 2017-04-01 | Labor | 24074149 | 35432777 | 29144800
MCR004827 | HPR019 | 2017-04-01 | Material | 57861119 | 85161063 | 86382752
MCR004828 | HPR019 | 2017-04-01 | Equipment | 18777200 | 27636630 | 29060231
MCR004829 | HPR019 | 2017-04-01 | Subcontract | 68703178 | 101118607 | 78444683
MCR004830 | HPR019 | 2017-04-01 | Overhead | 15893654 | 23392574 | 10828140
MCR004831 | HPR019 | 2017-05-01 | Labor | 25568045 | 21388895 | 21863257
MCR004832 | HPR019 | 2017-05-01 | Material | 61451629 | 51407233 | 53182164
MCR004833 | HPR019 | 2017-05-01 | Equipment | 19942399 | 16682773 | 16212099
MCR004834 | HPR019 | 2017-05-01 | Subcontract | 72966481 | 61039958 | 81993596
MCR004835 | HPR019 | 2017-05-01 | Overhead | 16879918 | 14120860 | 12433948
MCR004836 | HPR019 | 2017-06-01 | Labor | 26686934 | 25094698 | 24476661
MCR004837 | HPR019 | 2017-06-01 | Material | 64140827 | 60313962 | 57895765
MCR004838 | HPR019 | 2017-06-01 | Equipment | 20815103 | 19573202 | 18674791
MCR004839 | HPR019 | 2017-06-01 | Subcontract | 76159583 | 71615638 | 68535775
MCR004840 | HPR019 | 2017-06-01 | Overhead | 17618604 | 16567417 | 11653517
MCR004841 | HPR019 | 2017-07-01 | Labor | 27441299 | 9003399 | 7797633
MCR004842 | HPR019 | 2017-07-01 | Material | 65953911 | 21639258 | 22814922
MCR004843 | HPR019 | 2017-07-01 | Equipment | 21403488 | 7022413 | 8032341
MCR004844 | HPR019 | 2017-07-01 | Subcontract | 78312404 | 25694039 | 23458681
MCR004845 | HPR019 | 2017-07-01 | Overhead | 18116633 | 5944007 | 11806032
MCR004846 | HPR019 | 2017-08-01 | Labor | 27842220 | 24515989 | 43018107
MCR004847 | HPR019 | 2017-08-01 | Material | 66917505 | 58923060 | 73806302
MCR004848 | HPR019 | 2017-08-01 | Equipment | 21716196 | 19121823 | 18944060
MCR004849 | HPR019 | 2017-08-01 | Subcontract | 79456557 | 69964107 | 72537530
MCR004850 | HPR019 | 2017-08-01 | Overhead | 18381319 | 16185355 | 12346747
MCR004851 | HPR019 | 2017-09-01 | Labor | 27901444 | 45778236 | 68662466
MCR004852 | HPR019 | 2017-09-01 | Material | 67059849 | 110025902 | 123729899
MCR004853 | HPR019 | 2017-09-01 | Equipment | 21762389 | 35705815 | 33836624
MCR004854 | HPR019 | 2017-09-01 | Subcontract | 79625573 | 130642637 | 130759307
MCR004855 | HPR019 | 2017-09-01 | Overhead | 18420419 | 30222603 | 11059755
MCR004856 | HPR019 | 2017-10-01 | Labor | 27631491 | 23604644 | 22631564
MCR004857 | HPR019 | 2017-10-01 | Material | 66411027 | 56732684 | 54382127
MCR004858 | HPR019 | 2017-10-01 | Equipment | 21551833 | 18410998 | 17067735
MCR004859 | HPR019 | 2017-10-01 | Subcontract | 78855175 | 67363296 | 68101422
MCR004860 | HPR019 | 2017-10-01 | Overhead | 18242196 | 15583689 | 10934046
MCR004861 | HPR019 | 2017-11-01 | Labor | 27045761 | 16184068 | 13255803
MCR004862 | HPR019 | 2017-11-01 | Material | 65003252 | 38897669 | 38612116
MCR004863 | HPR019 | 2017-11-01 | Equipment | 21094979 | 12623145 | 12675348
MCR004864 | HPR019 | 2017-11-01 | Subcontract | 77183610 | 46186343 | 39715707
MCR004865 | HPR019 | 2017-11-01 | Overhead | 17855500 | 10684655 | 11491842
MCR004866 | HPR019 | 2017-12-01 | Labor | 26158690 | 23558939 | 22775815
MCR004867 | HPR019 | 2017-12-01 | Material | 62871217 | 56622834 | 66995002
MCR004868 | HPR019 | 2017-12-01 | Equipment | 20403087 | 18375350 | 21065788
MCR004869 | HPR019 | 2017-12-01 | Subcontract | 74652073 | 67232863 | 60045327
MCR004870 | HPR019 | 2017-12-01 | Overhead | 17269859 | 15553514 | 10719169
MCR004871 | HPR019 | 2018-01-01 | Labor | 24985928 | 23227939 | 23526058
MCR004872 | HPR019 | 2018-01-01 | Material | 60052539 | 55827291 | 49806789
MCR004873 | HPR019 | 2018-01-01 | Equipment | 19488364 | 18117179 | 17710775
MCR004874 | HPR019 | 2018-01-01 | Subcontract | 71305228 | 66288251 | 67121604
MCR004875 | HPR019 | 2018-01-01 | Overhead | 16495607 | 15334990 | 11725861
MCR004876 | HPR019 | 2018-02-01 | Labor | 23544586 | 18320966 | 15138095
MCR004877 | HPR019 | 2018-02-01 | Material | 56588337 | 44033605 | 43892287
MCR004878 | HPR019 | 2018-02-01 | Equipment | 18364155 | 14289869 | 15298953
MCR004879 | HPR019 | 2018-02-01 | Subcontract | 67191902 | 52284655 | 49921356
MCR004880 | HPR019 | 2018-02-01 | Overhead | 15544038 | 12095426 | 11804567
MCR004881 | HPR019 | 2018-03-01 | Labor | 21853543 | 16731398 | 15309914
MCR004882 | HPR019 | 2018-03-01 | Material | 52523994 | 40213153 | 41331787
MCR004883 | HPR019 | 2018-03-01 | Equipment | 17045186 | 13050049 | 12989879
MCR004884 | HPR019 | 2018-03-01 | Subcontract | 62365980 | 47748323 | 47296741
MCR004885 | HPR019 | 2018-03-01 | Overhead | 14427619 | 11046000 | 12643304
MCR004886 | HPR019 | 2018-04-01 | Labor | 19933888 | 19822552 | 20219337
MCR004887 | HPR019 | 2018-04-01 | Material | 47910190 | 47642600 | 50346911
MCR004888 | HPR019 | 2018-04-01 | Equipment | 15547906 | 15461067 | 13666292
MCR004889 | HPR019 | 2018-04-01 | Subcontract | 56887637 | 56569906 | 50653583
MCR004890 | HPR019 | 2018-04-01 | Overhead | 13160271 | 13086767 | 11831321
MCR004891 | HPR019 | 2018-05-01 | Labor | 17809509 | 14422233 | 11837258
MCR004892 | HPR019 | 2018-05-01 | Material | 42804343 | 34663179 | 35267772
MCR004893 | HPR019 | 2018-05-01 | Equipment | 13890947 | 11248961 | 12540987
MCR004894 | HPR019 | 2018-05-01 | Subcontract | 50825052 | 41158391 | 39568530
MCR004895 | HPR019 | 2018-05-01 | Overhead | 11757765 | 9521499 | 10797743
MCR004896 | HPR019 | 2018-06-01 | Labor | 15507980 | 22778209 | 23472292
MCR004897 | HPR019 | 2018-06-01 | Material | 37272722 | 54746385 | 53920363
MCR004898 | HPR019 | 2018-06-01 | Equipment | 12095815 | 17766401 | 15868368
MCR004899 | HPR019 | 2018-06-01 | Subcontract | 44256913 | 65004803 | 83554195
MCR004900 | HPR019 | 2018-06-01 | Overhead | 10238305 | 15038080 | 12806223
MCR004901 | HPR019 | 2018-07-01 | Labor | 13061897 | 14775504 | 13376632
MCR004902 | HPR019 | 2018-07-01 | Material | 31393673 | 35512248 | 35262862
MCR004903 | HPR019 | 2018-07-01 | Equipment | 10187934 | 11524502 | 13351331
MCR004904 | HPR019 | 2018-07-01 | Subcontract | 37276243 | 42166560 | 63218814
MCR004905 | HPR019 | 2018-07-01 | Overhead | 8623411 | 9754727 | 11920378
MCR004906 | HPR019 | 2018-08-01 | Labor | 10511073 | 17439481 | 16220430
MCR004907 | HPR019 | 2018-08-01 | Material | 25262885 | 41914997 | 45812650
MCR004908 | HPR019 | 2018-08-01 | Equipment | 8198359 | 13602335 | 14368474
MCR004909 | HPR019 | 2018-08-01 | Subcontract | 29996663 | 49769061 | 70271526
MCR004910 | HPR019 | 2018-08-01 | Overhead | 6939367 | 11513474 | 10986492
MCR004911 | HPR019 | 2018-09-01 | Labor | 7906456 | 13901329 | 13190237
MCR004912 | HPR019 | 2018-09-01 | Material | 19002807 | 33411211 | 35614222
MCR004913 | HPR019 | 2018-09-01 | Equipment | 6166827 | 10842670 | 11067888
MCR004914 | HPR019 | 2018-09-01 | Subcontract | 22563567 | 39671828 | 47421784
MCR004915 | HPR019 | 2018-09-01 | Overhead | 5219810 | 9177600 | 11548347
MCR004916 | HPR019 | 2018-10-01 | Labor | 5318087 | 10124737 | 10144115
MCR004917 | HPR019 | 2018-10-01 | Material | 12781780 | 24334344 | 24061143
MCR004918 | HPR019 | 2018-10-01 | Equipment | 4147968 | 7897028 | 8351137
MCR004919 | HPR019 | 2018-10-01 | Subcontract | 15176840 | 28894132 | 53091989
MCR004920 | HPR019 | 2018-10-01 | Overhead | 3510979 | 6684310 | 11670362
MCR004921 | HPR019 | 2018-11-01 | Labor | 2855197 | 9270310 | 9471632
MCR004922 | HPR019 | 2018-11-01 | Material | 6862336 | 22280768 | 23050582
MCR004923 | HPR019 | 2018-11-01 | Equipment | 2226978 | 7230597 | 7008640
MCR004924 | HPR019 | 2018-11-01 | Subcontract | 8148205 | 26455755 | 84160989
MCR004925 | HPR019 | 2018-11-01 | Overhead | 1884989 | 6120221 | 12187288
MCR004926 | HPR019 | 2018-12-01 | Labor | 751592 | 5958554 | 5236223
MCR004927 | HPR019 | 2018-12-01 | Material | 1806416 | 14321114 | 13175292
MCR004928 | HPR019 | 2018-12-01 | Equipment | 586222 | 4647515 | 4527855
MCR004929 | HPR019 | 2018-12-01 | Subcontract | 2144904 | 17004615 | 42615464
MCR004930 | HPR019 | 2018-12-01 | Overhead | 496198 | 3933813 | 12101321
MCR004931 | HPR019 | 2019-01-01 | Labor | 0 | 4065994 | 4339863
MCR004932 | HPR019 | 2019-01-01 | Material | 0 | 9772430 | 10399707
MCR004933 | HPR019 | 2019-01-01 | Equipment | 0 | 3171368 | 2790009
MCR004934 | HPR019 | 2019-01-01 | Subcontract | 0 | 11603595 | 30292658
MCR004935 | HPR019 | 2019-01-01 | Overhead | 0 | 2684352 | 11528551
MCR004936 | HPR019 | 2019-02-01 | Labor | 0 | 3009732 | 2875897
MCR004937 | HPR019 | 2019-02-01 | Material | 0 | 7233753 | 6971473
MCR004938 | HPR019 | 2019-02-01 | Equipment | 0 | 2347511 | 2502482
MCR004939 | HPR019 | 2019-02-01 | Subcontract | 0 | 8589219 | 36554340
MCR004940 | HPR019 | 2019-02-01 | Overhead | 0 | 1987013 | 12620265
MCR004941 | HPR019 | 2019-03-01 | Labor | 0 | 324667 | 289927
MCR004942 | HPR019 | 2019-03-01 | Material | 0 | 780321 | 673248
MCR004943 | HPR019 | 2019-03-01 | Equipment | 0 | 253231 | 367356
MCR004944 | HPR019 | 2019-03-01 | Subcontract | 0 | 926538 | 36516282
MCR004945 | HPR019 | 2019-03-01 | Overhead | 0 | 214344 | 11318021
MCR004946 | HPR020 | 2016-08-01 | Labor | 4168194 | 3843167 | 4067830
MCR004947 | HPR020 | 2016-08-01 | Material | 7738813 | 7135356 | 7143343
MCR004948 | HPR020 | 2016-08-01 | Equipment | 1940855 | 1789511 | 2026511
MCR004949 | HPR020 | 2016-08-01 | Subcontract | 13441906 | 12393734 | 12321196
MCR004950 | HPR020 | 2016-08-01 | Overhead | 2542682 | 2344409 | 18212425
MCR004951 | HPR020 | 2016-09-01 | Labor | 11958761 | 9326560 | 10171211
MCR004952 | HPR020 | 2016-09-01 | Material | 22203048 | 17316012 | 17561169
MCR004953 | HPR020 | 2016-09-01 | Equipment | 5568411 | 4342768 | 4890447
MCR004954 | HPR020 | 2016-09-01 | Subcontract | 38565511 | 30076990 | 29637162
MCR004955 | HPR020 | 2016-09-01 | Overhead | 7295085 | 5689389 | 19310200
MCR004956 | HPR020 | 2016-10-01 | Labor | 18941417 | 8652451 | 9395592
MCR004957 | HPR020 | 2016-10-01 | Material | 35167287 | 16064439 | 17725091
MCR004958 | HPR020 | 2016-10-01 | Equipment | 8819776 | 4028879 | 3509517
MCR004959 | HPR020 | 2016-10-01 | Subcontract | 61083703 | 27903073 | 29865103
MCR004960 | HPR020 | 2016-10-01 | Overhead | 11554645 | 5278169 | 18260080
MCR004961 | HPR020 | 2016-11-01 | Labor | 25131028 | 14156339 | 15789417
MCR004962 | HPR020 | 2016-11-01 | Material | 46659132 | 26283145 | 26915486
MCR004963 | HPR020 | 2016-11-01 | Equipment | 11701872 | 6591679 | 7562040
MCR004964 | HPR020 | 2016-11-01 | Subcontract | 81044425 | 45652422 | 37167568
MCR004965 | HPR020 | 2016-11-01 | Overhead | 15330432 | 8635651 | 18326191
MCR004966 | HPR020 | 2016-12-01 | Labor | 30543050 | 22795522 | 23798348
MCR004967 | HPR020 | 2016-12-01 | Material | 56707278 | 42322950 | 41962597
MCR004968 | HPR020 | 2016-12-01 | Equipment | 14221896 | 10614380 | 11764007
MCR004969 | HPR020 | 2016-12-01 | Subcontract | 98497520 | 73512708 | 69874752
MCR004970 | HPR020 | 2016-12-01 | Overhead | 18631874 | 13905726 | 18511959
MCR004971 | HPR020 | 2017-01-01 | Labor | 35193585 | 27548421 | 32586382
MCR004972 | HPR020 | 2017-01-01 | Material | 65341620 | 51147347 | 60007811
MCR004973 | HPR020 | 2017-01-01 | Equipment | 16387345 | 12827494 | 12999828
MCR004974 | HPR020 | 2017-01-01 | Subcontract | 113494911 | 88840216 | 88555585
MCR004975 | HPR020 | 2017-01-01 | Overhead | 21468793 | 16805090 | 18273539
MCR004976 | HPR020 | 2017-02-01 | Labor | 39099441 | 39471376 | 38806276
MCR004977 | HPR020 | 2017-02-01 | Material | 72593367 | 73283915 | 78959350
MCR004978 | HPR020 | 2017-02-01 | Equipment | 18206046 | 18379232 | 20750235
MCR004979 | HPR020 | 2017-02-01 | Subcontract | 126090809 | 127290253 | 128530171
MCR004980 | HPR020 | 2017-02-01 | Overhead | 23851444 | 24078332 | 18368450
MCR004981 | HPR020 | 2017-03-01 | Labor | 42278211 | 20639705 | 25269624
MCR004982 | HPR020 | 2017-03-01 | Material | 78495182 | 38320387 | 35250462
MCR004983 | HPR020 | 2017-03-01 | Equipment | 19686191 | 9610558 | 6649396
MCR004984 | HPR020 | 2017-03-01 | Subcontract | 136341947 | 66560470 | 63054452
MCR004985 | HPR020 | 2017-03-01 | Overhead | 25790557 | 12590635 | 17575955
MCR004986 | HPR020 | 2017-04-01 | Labor | 44748358 | 29784352 | 30966354
MCR004987 | HPR020 | 2017-04-01 | Material | 83081340 | 55298653 | 51578502
MCR004988 | HPR020 | 2017-04-01 | Equipment | 20836377 | 13868620 | 14038838
MCR004989 | HPR020 | 2017-04-01 | Subcontract | 144307860 | 96050813 | 89874617
MCR004990 | HPR020 | 2017-04-01 | Overhead | 27297396 | 18169053 | 18325557
MCR004991 | HPR020 | 2017-05-01 | Labor | 46529312 | 26817948 | 33286110
MCR004992 | HPR020 | 2017-05-01 | Material | 86387921 | 49791125 | 52405107
MCR004993 | HPR020 | 2017-05-01 | Equipment | 21665650 | 12487360 | 13657398
MCR004994 | HPR020 | 2017-05-01 | Subcontract | 150051214 | 86484530 | 76635059
MCR004995 | HPR020 | 2017-05-01 | Overhead | 28383814 | 16359486 | 19086708
MCR004996 | HPR020 | 2017-06-01 | Labor | 47641597 | 21661456 | 24694179
MCR004997 | HPR020 | 2017-06-01 | Material | 88453028 | 40217404 | 44556848
MCR004998 | HPR020 | 2017-06-01 | Equipment | 22183568 | 10086320 | 11569375
MCR004999 | HPR020 | 2017-06-01 | Subcontract | 153638194 | 69855487 | 69983632
MCR005000 | HPR020 | 2017-06-01 | Overhead | 29062330 | 13213923 | 18132582
MCR005001 | HPR020 | 2017-07-01 | Labor | 48106970 | 36554536 | 92812740
MCR005002 | HPR020 | 2017-07-01 | Material | 89317056 | 67868409 | 89953962
MCR005003 | HPR020 | 2017-07-01 | Equipment | 22400262 | 17021051 | 16452721
MCR005004 | HPR020 | 2017-07-01 | Subcontract | 155138966 | 117883810 | 113739285
MCR005005 | HPR020 | 2017-07-01 | Overhead | 29346218 | 22299001 | 20410222
MCR005006 | HPR020 | 2017-08-01 | Labor | 47948601 | 36970470 | 69859432
MCR005007 | HPR020 | 2017-08-01 | Material | 89023022 | 68640647 | 95480238
MCR005008 | HPR020 | 2017-08-01 | Equipment | 22326520 | 17214724 | 18728878
MCR005009 | HPR020 | 2017-08-01 | Subcontract | 154628245 | 119225146 | 135931921
MCR005010 | HPR020 | 2017-08-01 | Overhead | 29249609 | 22552729 | 17130053
MCR005011 | HPR020 | 2017-09-01 | Labor | 47191282 | 77807514 | 78953860
MCR005012 | HPR020 | 2017-09-01 | Material | 87616959 | 144460107 | 151981313
MCR005013 | HPR020 | 2017-09-01 | Equipment | 21973886 | 36229858 | 38548087
MCR005014 | HPR020 | 2017-09-01 | Subcontract | 152185987 | 250919506 | 251394423
MCR005015 | HPR020 | 2017-09-01 | Overhead | 28787629 | 47464145 | 18590809
MCR005016 | HPR020 | 2017-10-01 | Labor | 45861700 | 27051230 | 37127216
MCR005017 | HPR020 | 2017-10-01 | Material | 85148411 | 50224245 | 53371804
MCR005018 | HPR020 | 2017-10-01 | Equipment | 21354787 | 12595984 | 13797836
MCR005019 | HPR020 | 2017-10-01 | Subcontract | 147898252 | 87236836 | 76576144
MCR005020 | HPR020 | 2017-10-01 | Overhead | 27976558 | 16501793 | 18061806
MCR005021 | HPR020 | 2017-11-01 | Labor | 43988774 | 30975477 | 32860602
MCR005022 | HPR020 | 2017-11-01 | Material | 81671072 | 57510136 | 51038427
MCR005023 | HPR020 | 2017-11-01 | Equipment | 20482688 | 14423249 | 14326778
MCR005024 | HPR020 | 2017-11-01 | Subcontract | 141858298 | 99892041 | 97461509
MCR005025 | HPR020 | 2017-11-01 | Overhead | 26834035 | 18895663 | 17971872
MCR005026 | HPR020 | 2017-12-01 | Labor | 41604091 | 65616439 | 74659762
MCR005027 | HPR020 | 2017-12-01 | Material | 77243587 | 121825739 | 107645522
MCR005028 | HPR020 | 2017-12-01 | Equipment | 19372298 | 30553274 | 33784185
MCR005029 | HPR020 | 2017-12-01 | Subcontract | 134167993 | 211604814 | 217121229
MCR005030 | HPR020 | 2017-12-01 | Overhead | 25379331 | 40027345 | 17362195
MCR005031 | HPR020 | 2018-01-01 | Labor | 38742487 | 35089007 | 50194507
MCR005032 | HPR020 | 2018-01-01 | Material | 71930635 | 65147458 | 77854587
MCR005033 | HPR020 | 2018-01-01 | Equipment | 18039837 | 16338650 | 13834877
MCR005034 | HPR020 | 2018-01-01 | Subcontract | 124939679 | 113157662 | 110885823
MCR005035 | HPR020 | 2018-01-01 | Overhead | 23633695 | 21404999 | 20486191
MCR005036 | HPR020 | 2018-02-01 | Labor | 35442830 | 23427703 | 22834832
MCR005037 | HPR020 | 2018-02-01 | Material | 65804378 | 43496679 | 46242664
MCR005038 | HPR020 | 2018-02-01 | Equipment | 16503403 | 10908745 | 11741288
MCR005039 | HPR020 | 2018-02-01 | Subcontract | 114298698 | 75551413 | 81585309
MCR005040 | HPR020 | 2018-02-01 | Overhead | 21620838 | 14291369 | 18058367
MCR005041 | HPR020 | 2018-03-01 | Labor | 31749115 | 28489463 | 28005851
MCR005042 | HPR020 | 2018-03-01 | Material | 58946499 | 52894517 | 52978213
MCR005043 | HPR020 | 2018-03-01 | Equipment | 14783481 | 13265675 | 15518977
MCR005044 | HPR020 | 2018-03-01 | Subcontract | 102386927 | 91874956 | 93040024
MCR005045 | HPR020 | 2018-03-01 | Overhead | 19367597 | 17379144 | 18012385
MCR005046 | HPR020 | 2018-04-01 | Labor | 27712061 | 24378029 | 35095973
MCR005047 | HPR020 | 2018-04-01 | Material | 51451166 | 45261088 | 49019397
MCR005048 | HPR020 | 2018-04-01 | Equipment | 12903690 | 11351250 | 10286359
MCR005049 | HPR020 | 2018-04-01 | Subcontract | 89367933 | 78616098 | 64139467
MCR005050 | HPR020 | 2018-04-01 | Overhead | 16904913 | 14871087 | 18781770
MCR005051 | HPR020 | 2018-05-01 | Labor | 23391556 | 43295703 | 56273044
MCR005052 | HPR020 | 2018-05-01 | Material | 43429569 | 80384292 | 89501772
MCR005053 | HPR020 | 2018-05-01 | Equipment | 10891914 | 20159971 | 21534091
MCR005054 | HPR020 | 2018-05-01 | Subcontract | 75434846 | 139623230 | 134368060
MCR005055 | HPR020 | 2018-05-01 | Overhead | 14269319 | 26411248 | 19013272
MCR005056 | HPR020 | 2018-06-01 | Labor | 18860646 | 18562071 | 18106614
MCR005057 | HPR020 | 2018-06-01 | Material | 35017324 | 34462980 | 40123727
MCR005058 | HPR020 | 2018-06-01 | Equipment | 8782166 | 8643140 | 8651538
MCR005059 | HPR020 | 2018-06-01 | Subcontract | 60823226 | 59860359 | 68315763
MCR005060 | HPR020 | 2018-06-01 | Overhead | 11505373 | 11323236 | 18313946
MCR005061 | HPR020 | 2018-07-01 | Labor | 14212646 | 32183355 | 32794379
MCR005062 | HPR020 | 2018-07-01 | Material | 26387688 | 59752725 | 64644493
MCR005063 | HPR020 | 2018-07-01 | Equipment | 6617898 | 14985679 | 16925595
MCR005064 | HPR020 | 2018-07-01 | Subcontract | 45834007 | 103787298 | 105098549
MCR005065 | HPR020 | 2018-07-01 | Overhead | 8669999 | 19632493 | 17365232
MCR005066 | HPR020 | 2018-08-01 | Labor | 9575598 | 13221343 | 20651031
MCR005067 | HPR020 | 2018-08-01 | Material | 17778385 | 24547200 | 23265539
MCR005068 | HPR020 | 2018-08-01 | Equipment | 4458728 | 6156313 | 5848641
MCR005069 | HPR020 | 2018-08-01 | Subcontract | 30880108 | 42637179 | 41632667
MCR005070 | HPR020 | 2018-08-01 | Overhead | 5841307 | 8065285 | 19069346
MCR005071 | HPR020 | 2018-09-01 | Labor | 5148716 | 21924129 | 23008731
MCR005072 | HPR020 | 2018-09-01 | Material | 9559282 | 40705093 | 43115788
MCR005073 | HPR020 | 2018-09-01 | Equipment | 2397419 | 10208630 | 10401067
MCR005074 | HPR020 | 2018-09-01 | Subcontract | 16603964 | 70702576 | 66183036
MCR005075 | HPR020 | 2018-09-01 | Overhead | 3140820 | 13374159 | 18305908
MCR005076 | HPR020 | 2018-10-01 | Labor | 1357037 | 26222882 | 35040418
MCR005077 | HPR020 | 2018-10-01 | Material | 2519521 | 48686305 | 46804123
MCR005078 | HPR020 | 2018-10-01 | Equipment | 631883 | 12210277 | 11520350
MCR005079 | HPR020 | 2018-10-01 | Subcontract | 4376273 | 84565517 | 84834612
MCR005080 | HPR020 | 2018-10-01 | Overhead | 827820 | 15996485 | 19030720
MCR005081 | HPR020 | 2018-11-01 | Labor | 0 | 11881110 | 14356543
MCR005082 | HPR020 | 2018-11-01 | Material | 0 | 22058879 | 24793968
MCR005083 | HPR020 | 2018-11-01 | Equipment | 0 | 5532254 | 5724073
MCR005084 | HPR020 | 2018-11-01 | Subcontract | 0 | 38315096 | 34280625
MCR005085 | HPR020 | 2018-11-01 | Overhead | 0 | 7247716 | 18211596
MCR005086 | HPR020 | 2018-12-01 | Labor | 0 | 12684117 | 15580040
MCR005087 | HPR020 | 2018-12-01 | Material | 0 | 23549767 | 22688935
MCR005088 | HPR020 | 2018-12-01 | Equipment | 0 | 5906162 | 6327306
MCR005089 | HPR020 | 2018-12-01 | Subcontract | 0 | 40904691 | 39277087
MCR005090 | HPR020 | 2018-12-01 | Overhead | 0 | 7737566 | 19257088
MCR005091 | HPR020 | 2019-01-01 | Labor | 0 | 15894135 | 18845093
MCR005092 | HPR020 | 2019-01-01 | Material | 0 | 29509599 | 30214404
MCR005093 | HPR020 | 2019-01-01 | Equipment | 0 | 7400857 | 7871870
MCR005094 | HPR020 | 2019-01-01 | Subcontract | 0 | 51256600 | 48739267
MCR005095 | HPR020 | 2019-01-01 | Overhead | 0 | 9695742 | 18699273
MCR005096 | HPR020 | 2019-02-01 | Labor | 0 | 8971080 | 13209533
MCR005097 | HPR020 | 2019-02-01 | Material | 0 | 16656016 | 21650944
MCR005098 | HPR020 | 2019-02-01 | Equipment | 0 | 4177244 | 4456917
MCR005099 | HPR020 | 2019-02-01 | Subcontract | 0 | 28930612 | 27990115
MCR005100 | HPR020 | 2019-02-01 | Overhead | 0 | 5472539 | 20016376
MCR005101 | HPR020 | 2019-03-01 | Labor | 0 | 6391021 | 7058450
MCR005102 | HPR020 | 2019-03-01 | Material | 0 | 11865790 | 11788667
MCR005103 | HPR020 | 2019-03-01 | Equipment | 0 | 2975880 | 3245934
MCR005104 | HPR020 | 2019-03-01 | Subcontract | 0 | 20610244 | 21435289
MCR005105 | HPR020 | 2019-03-01 | Overhead | 0 | 3898651 | 19657177
MCR005106 | HPR020 | 2019-04-01 | Labor | 0 | 3813724 | 4861872
MCR005107 | HPR020 | 2019-04-01 | Material | 0 | 7080691 | 6671680
MCR005108 | HPR020 | 2019-04-01 | Equipment | 0 | 1775801 | 2211467
MCR005109 | HPR020 | 2019-04-01 | Subcontract | 0 | 12298783 | 10397743
MCR005110 | HPR020 | 2019-04-01 | Overhead | 0 | 2326448 | 17689749
MCR005111 | HPR020 | 2019-05-01 | Labor | 0 | 1025229 | 1513462
MCR005112 | HPR020 | 2019-05-01 | Material | 0 | 1903476 | 2769121
MCR005113 | HPR020 | 2019-05-01 | Equipment | 0 | 477382 | 606584
MCR005114 | HPR020 | 2019-05-01 | Subcontract | 0 | 3306236 | 3971855
MCR005115 | HPR020 | 2019-05-01 | Overhead | 0 | 625410 | 18094820
MCR005116 | HPR021 | 2020-03-01 | Labor | 2517055 | 991721 | 1054081
MCR005117 | HPR021 | 2020-03-01 | Material | 11566194 | 4557088 | 4195764
MCR005118 | HPR021 | 2020-03-01 | Equipment | 5037188 | 1984655 | 2120031
MCR005119 | HPR021 | 2020-03-01 | Subcontract | 6316804 | 2488825 | 2295841
MCR005120 | HPR021 | 2020-03-01 | Overhead | 2387932 | 940847 | 9958769
MCR005121 | HPR021 | 2020-04-01 | Labor | 6903657 | 3003359 | 3411857
MCR005122 | HPR021 | 2020-04-01 | Material | 31723199 | 13800823 | 13434163
MCR005123 | HPR021 | 2020-04-01 | Equipment | 13815756 | 6010390 | 6638028
MCR005124 | HPR021 | 2020-04-01 | Subcontract | 17325425 | 7537232 | 8480440
MCR005125 | HPR021 | 2020-04-01 | Overhead | 6549504 | 2849289 | 8745919
MCR005126 | HPR021 | 2020-05-01 | Labor | 10345161 | 4068182 | 4467365
MCR005127 | HPR021 | 2020-05-01 | Material | 47537352 | 18693823 | 18186878
MCR005128 | HPR021 | 2020-05-01 | Equipment | 20702971 | 8141339 | 9934518
MCR005129 | HPR021 | 2020-05-01 | Subcontract | 25962224 | 10209513 | 9506302
MCR005130 | HPR021 | 2020-05-01 | Overhead | 9814461 | 3859487 | 8984068
MCR005131 | HPR021 | 2020-06-01 | Labor | 12878707 | 7977171 | 9999977
MCR005132 | HPR021 | 2020-06-01 | Material | 59179322 | 36656131 | 37924055
MCR005133 | HPR021 | 2020-06-01 | Equipment | 25773161 | 15964096 | 15506116
MCR005134 | HPR021 | 2020-06-01 | Subcontract | 32320413 | 20019515 | 23024500
MCR005135 | HPR021 | 2020-06-01 | Overhead | 12218037 | 7567947 | 9365889
MCR005136 | HPR021 | 2020-07-01 | Labor | 14544731 | 7086185 | 7919965
MCR005137 | HPR021 | 2020-07-01 | Material | 66834920 | 32561936 | 36238331
MCR005138 | HPR021 | 2020-07-01 | Equipment | 29107247 | 14181035 | 14687025
MCR005139 | HPR021 | 2020-07-01 | Subcontract | 36501469 | 17783496 | 16385893
MCR005140 | HPR021 | 2020-07-01 | Overhead | 13798595 | 6722668 | 10179803
MCR005141 | HPR021 | 2020-08-01 | Labor | 15387700 | 6396970 | 6699598
MCR005142 | HPR021 | 2020-08-01 | Material | 70708470 | 29394906 | 27910301
MCR005143 | HPR021 | 2020-08-01 | Equipment | 30794215 | 12801763 | 13455582
MCR005144 | HPR021 | 2020-08-01 | Subcontract | 38616984 | 16053842 | 15029877
MCR005145 | HPR021 | 2020-08-01 | Overhead | 14598320 | 6068810 | 9805170
MCR005146 | HPR021 | 2020-09-01 | Labor | 15457123 | 7876221 | 16604910
MCR005147 | HPR021 | 2020-09-01 | Material | 71027477 | 36192253 | 52500045
MCR005148 | HPR021 | 2020-09-01 | Equipment | 30933145 | 15762072 | 16280632
MCR005149 | HPR021 | 2020-09-01 | Subcontract | 38791208 | 19766170 | 19263193
MCR005150 | HPR021 | 2020-09-01 | Overhead | 14664182 | 7472176 | 9908793
MCR005151 | HPR021 | 2020-10-01 | Labor | 14809009 | 12140892 | 17989327
MCR005152 | HPR021 | 2020-10-01 | Material | 68049309 | 55788966 | 69335495
MCR005153 | HPR021 | 2020-10-01 | Equipment | 29636125 | 24296628 | 26320764
MCR005154 | HPR021 | 2020-10-01 | Subcontract | 37164701 | 30468792 | 31581033
MCR005155 | HPR021 | 2020-10-01 | Overhead | 14049316 | 11518071 | 9515854
MCR005156 | HPR021 | 2020-11-01 | Labor | 13508058 | 7419453 | 9512294
MCR005157 | HPR021 | 2020-11-01 | Material | 62071272 | 34093344 | 30123928
MCR005158 | HPR021 | 2020-11-01 | Equipment | 27032633 | 14847977 | 12177005
MCR005159 | HPR021 | 2020-11-01 | Subcontract | 33899833 | 18619865 | 20455900
MCR005160 | HPR021 | 2020-11-01 | Overhead | 12815103 | 7038839 | 9998983
MCR005161 | HPR021 | 2020-12-01 | Labor | 11631178 | 12401483 | 14123273
MCR005162 | HPR021 | 2020-12-01 | Material | 53446766 | 56986419 | 61668333
MCR005163 | HPR021 | 2020-12-01 | Equipment | 23276578 | 24818130 | 32018927
MCR005164 | HPR021 | 2020-12-01 | Subcontract | 29189614 | 31122773 | 32282400
MCR005165 | HPR021 | 2020-12-01 | Overhead | 11034506 | 11765295 | 8729105
MCR005166 | HPR021 | 2021-01-01 | Labor | 9273641 | 12157681 | 13654387
MCR005167 | HPR021 | 2021-01-01 | Material | 42613580 | 55866116 | 60734107
MCR005168 | HPR021 | 2021-01-01 | Equipment | 18558622 | 24330228 | 22122100
MCR005169 | HPR021 | 2021-01-01 | Subcontract | 23273138 | 30510927 | 31663665
MCR005170 | HPR021 | 2021-01-01 | Overhead | 8797909 | 11534000 | 10806997
MCR005171 | HPR021 | 2021-02-01 | Labor | 6561337 | 13577718 | 14405316
MCR005172 | HPR021 | 2021-02-01 | Material | 30150191 | 62391370 | 71329455
MCR005173 | HPR021 | 2021-02-01 | Equipment | 13130696 | 27172038 | 29797354
MCR005174 | HPR021 | 2021-02-01 | Subcontract | 16466336 | 34074653 | 31975721
MCR005175 | HPR021 | 2021-02-01 | Overhead | 6224744 | 12881190 | 9801030
MCR005176 | HPR021 | 2021-03-01 | Labor | 3680940 | 11275664 | 13728946
MCR005177 | HPR021 | 2021-03-01 | Material | 16914395 | 51813133 | 56074193
MCR005178 | HPR021 | 2021-03-01 | Equipment | 7366381 | 22565115 | 22867344
MCR005179 | HPR021 | 2021-03-01 | Subcontract | 9237690 | 28297416 | 29952558
MCR005180 | HPR021 | 2021-03-01 | Overhead | 3492110 | 10697229 | 9421571
MCR005181 | HPR021 | 2021-04-01 | Labor | 1003919 | 10821529 | 12667008
MCR005182 | HPR021 | 2021-04-01 | Material | 4613138 | 49726325 | 52863804
MCR005183 | HPR021 | 2021-04-01 | Equipment | 2009066 | 21656290 | 23462769
MCR005184 | HPR021 | 2021-04-01 | Subcontract | 2519436 | 27157719 | 25966161
MCR005185 | HPR021 | 2021-04-01 | Overhead | 952419 | 10266391 | 9153485
MCR005186 | HPR021 | 2021-05-01 | Labor | 0 | 4202933 | 4027063
MCR005187 | HPR021 | 2021-05-01 | Material | 0 | 19313021 | 19782964
MCR005188 | HPR021 | 2021-05-01 | Equipment | 0 | 8411005 | 8425137
MCR005189 | HPR021 | 2021-05-01 | Subcontract | 0 | 10547684 | 11072723
MCR005190 | HPR021 | 2021-05-01 | Overhead | 0 | 3987325 | 10000140
MCR005191 | HPR021 | 2021-06-01 | Labor | 0 | 5220439 | 5692177
MCR005192 | HPR021 | 2021-06-01 | Material | 0 | 23988590 | 27275707
MCR005193 | HPR021 | 2021-06-01 | Equipment | 0 | 10447260 | 12033326
MCR005194 | HPR021 | 2021-06-01 | Subcontract | 0 | 13101217 | 15127498
MCR005195 | HPR021 | 2021-06-01 | Overhead | 0 | 4952633 | 8950552
MCR005196 | HPR021 | 2021-07-01 | Labor | 0 | 5600274 | 7413458
MCR005197 | HPR021 | 2021-07-01 | Material | 0 | 25733981 | 32955380
MCR005198 | HPR021 | 2021-07-01 | Equipment | 0 | 11207395 | 13543114
MCR005199 | HPR021 | 2021-07-01 | Subcontract | 0 | 14054451 | 13889848
MCR005200 | HPR021 | 2021-07-01 | Overhead | 0 | 5312983 | 9512593
MCR005201 | HPR021 | 2021-08-01 | Labor | 0 | 3047864 | 2602539
MCR005202 | HPR021 | 2021-08-01 | Material | 0 | 14005331 | 14334761
MCR005203 | HPR021 | 2021-08-01 | Equipment | 0 | 6099456 | 6841397
MCR005204 | HPR021 | 2021-08-01 | Subcontract | 0 | 7648923 | 8309008
MCR005205 | HPR021 | 2021-08-01 | Overhead | 0 | 2891511 | 8930635
MCR005206 | HPR021 | 2021-09-01 | Labor | 0 | 2274947 | 3176785
MCR005207 | HPR021 | 2021-09-01 | Material | 0 | 10453677 | 13254582
MCR005208 | HPR021 | 2021-09-01 | Equipment | 0 | 4552676 | 4826242
MCR005209 | HPR021 | 2021-09-01 | Subcontract | 0 | 5709209 | 5860404
MCR005210 | HPR021 | 2021-09-01 | Overhead | 0 | 2158244 | 9447869
MCR005211 | HPR021 | 2021-10-01 | Labor | 0 | 961530 | 894514
MCR005212 | HPR021 | 2021-10-01 | Material | 0 | 4418353 | 4630347
MCR005213 | HPR021 | 2021-10-01 | Equipment | 0 | 1924235 | 2487388
MCR005214 | HPR021 | 2021-10-01 | Subcontract | 0 | 2413055 | 2249932
MCR005215 | HPR021 | 2021-10-01 | Overhead | 0 | 912204 | 9288855
MCR005216 | HPR022 | 2023-06-01 | Labor | 3777647 | 3331346 | 3455140
MCR005217 | HPR022 | 2023-06-01 | Material | 7187458 | 6338313 | 6968842
MCR005218 | HPR022 | 2023-06-01 | Equipment | 1608531 | 1418495 | 1445015
MCR005219 | HPR022 | 2023-06-01 | Subcontract | 12475263 | 11001403 | 11678362
MCR005220 | HPR022 | 2023-06-01 | Overhead | 2594262 | 2287769 | 10543307
MCR005221 | HPR022 | 2023-07-01 | Labor | 10538047 | 5599598 | 5735463
MCR005222 | HPR022 | 2023-07-01 | Material | 20049988 | 10653954 | 11946780
MCR005223 | HPR022 | 2023-07-01 | Equipment | 4487126 | 2384322 | 2588208
MCR005224 | HPR022 | 2023-07-01 | Subcontract | 34800743 | 18492057 | 18882588
MCR005225 | HPR022 | 2023-07-01 | Overhead | 7236902 | 3845470 | 12178142
MCR005226 | HPR022 | 2023-08-01 | Labor | 16132019 | 10509726 | 13354506
MCR005227 | HPR022 | 2023-08-01 | Material | 30693238 | 19996104 | 19133669
MCR005228 | HPR022 | 2023-08-01 | Equipment | 6869052 | 4475067 | 4029576
MCR005229 | HPR022 | 2023-08-01 | Subcontract | 53274219 | 34707217 | 37960664
MCR005230 | HPR022 | 2023-08-01 | Overhead | 11078508 | 7217453 | 11846660
MCR005231 | HPR022 | 2023-09-01 | Labor | 20595880 | 16503400 | 15683196
MCR005232 | HPR022 | 2023-09-01 | Material | 39186307 | 31399837 | 33731042
MCR005233 | HPR022 | 2023-09-01 | Equipment | 8769775 | 7027187 | 7052886
MCR005234 | HPR022 | 2023-09-01 | Subcontract | 68015630 | 54500664 | 45962710
MCR005235 | HPR022 | 2023-09-01 | Overhead | 14144021 | 11333550 | 12359910
MCR005236 | HPR022 | 2023-10-01 | Labor | 23968455 | 15221351 | 16822275
MCR005237 | HPR022 | 2023-10-01 | Material | 45603063 | 28960574 | 29434884
MCR005238 | HPR022 | 2023-10-01 | Equipment | 10205826 | 6481288 | 6933702
MCR005239 | HPR022 | 2023-10-01 | Subcontract | 79153187 | 50266837 | 55682236
MCR005240 | HPR022 | 2023-10-01 | Overhead | 16460104 | 10453115 | 12379615
MCR005241 | HPR022 | 2023-11-01 | Labor | 26291498 | 22375266 | 26290302
MCR005242 | HPR022 | 2023-11-01 | Material | 50022951 | 42571818 | 43565964
MCR005243 | HPR022 | 2023-11-01 | Equipment | 11194983 | 9527442 | 11338249
MCR005244 | HPR022 | 2023-11-01 | Subcontract | 86824781 | 73891858 | 63962614
MCR005245 | HPR022 | 2023-11-01 | Overhead | 18055432 | 15365998 | 13006478
MCR005246 | HPR022 | 2023-12-01 | Labor | 27610237 | 13301025 | 11467649
MCR005247 | HPR022 | 2023-12-01 | Material | 52532022 | 25306909 | 26056698
MCR005248 | HPR022 | 2023-12-01 | Equipment | 11756505 | 5663609 | 5222466
MCR005249 | HPR022 | 2023-12-01 | Subcontract | 91179774 | 43925174 | 51445179
MCR005250 | HPR022 | 2023-12-01 | Overhead | 18961063 | 9134350 | 11429903
MCR005251 | HPR022 | 2024-01-01 | Labor | 27974087 | 26262618 | 29214504
MCR005252 | HPR022 | 2024-01-01 | Material | 53224293 | 49968004 | 47673411
MCR005253 | HPR022 | 2024-01-01 | Equipment | 11911434 | 11182686 | 13085888
MCR005254 | HPR022 | 2024-01-01 | Subcontract | 92381348 | 86729410 | 80752930
MCR005255 | HPR022 | 2024-01-01 | Overhead | 19210934 | 18035599 | 12053841
MCR005256 | HPR022 | 2024-02-01 | Labor | 27437603 | 21066694 | 20810916
MCR005257 | HPR022 | 2024-02-01 | Material | 52203565 | 40082092 | 44202335
MCR005258 | HPR022 | 2024-02-01 | Equipment | 11682998 | 8970249 | 9465293
MCR005259 | HPR022 | 2024-02-01 | Subcontract | 90609670 | 69570443 | 74774159
MCR005260 | HPR022 | 2024-02-01 | Overhead | 18842509 | 14467348 | 11562609
MCR005261 | HPR022 | 2024-03-01 | Labor | 26061811 | 30366511 | 34089434
MCR005262 | HPR022 | 2024-03-01 | Material | 49585942 | 57776188 | 57148766
MCR005263 | HPR022 | 2024-03-01 | Equipment | 11097182 | 12930134 | 14146470
MCR005264 | HPR022 | 2024-03-01 | Subcontract | 86066266 | 100282066 | 98436306
MCR005265 | HPR022 | 2024-03-01 | Overhead | 17897696 | 20853908 | 12775349
MCR005266 | HPR022 | 2024-04-01 | Labor | 23916114 | 25134977 | 27649595
MCR005267 | HPR022 | 2024-04-01 | Material | 45503479 | 47822523 | 52274026
MCR005268 | HPR022 | 2024-04-01 | Equipment | 10183539 | 10702534 | 10398089
MCR005269 | HPR022 | 2024-04-01 | Subcontract | 78980339 | 83005501 | 78651123
MCR005270 | HPR022 | 2024-04-01 | Overhead | 16424160 | 17261202 | 11813670
MCR005271 | HPR022 | 2024-05-01 | Labor | 21081192 | 31955039 | 34542796
MCR005272 | HPR022 | 2024-05-01 | Material | 40109676 | 60798566 | 59099635
MCR005273 | HPR022 | 2024-05-01 | Equipment | 8976423 | 13606532 | 13114019
MCR005274 | HPR022 | 2024-05-01 | Subcontract | 69618321 | 105528004 | 114042345
MCR005275 | HPR022 | 2024-05-01 | Overhead | 14477305 | 21944814 | 11725534
MCR005276 | HPR022 | 2024-06-01 | Labor | 17653670 | 28112389 | 33577520
MCR005277 | HPR022 | 2024-06-01 | Material | 33588375 | 53487431 | 56294735
MCR005278 | HPR022 | 2024-06-01 | Equipment | 7516975 | 11970323 | 12453426
MCR005279 | HPR022 | 2024-06-01 | Subcontract | 58299307 | 92838076 | 77382361
MCR005280 | HPR022 | 2024-06-01 | Overhead | 12123487 | 19305911 | 12137882
MCR005281 | HPR022 | 2024-07-01 | Labor | 13754347 | 9839132 | 11417531
MCR005282 | HPR022 | 2024-07-01 | Material | 26169411 | 18720211 | 19888076
MCR005283 | HPR022 | 2024-07-01 | Equipment | 5856634 | 4189526 | 4663363
MCR005284 | HPR022 | 2024-07-01 | Subcontract | 45422219 | 32492651 | 36441993
MCR005285 | HPR022 | 2024-07-01 | Overhead | 9445665 | 6756928 | 11673576
MCR005286 | HPR022 | 2024-08-01 | Labor | 9544683 | 11250400 | 12813942
MCR005287 | HPR022 | 2024-08-01 | Material | 18159985 | 21405330 | 20496542
MCR005288 | HPR022 | 2024-08-01 | Equipment | 4064149 | 4790447 | 4031584
MCR005289 | HPR022 | 2024-08-01 | Subcontract | 31520267 | 37153208 | 39114752
MCR005290 | HPR022 | 2024-08-01 | Overhead | 6554719 | 7726103 | 11231502
MCR005291 | HPR022 | 2024-09-01 | Labor | 5267741 | 16833475 | 19926540
MCR005292 | HPR022 | 2024-09-01 | Material | 10022553 | 32027849 | 34220309
MCR005293 | HPR022 | 2024-09-01 | Equipment | 2243017 | 7167734 | 7362583
MCR005294 | HPR022 | 2024-09-01 | Subcontract | 17396135 | 55590702 | 54731796
MCR005295 | HPR022 | 2024-09-01 | Overhead | 3617570 | 11560226 | 12047529
MCR005296 | HPR022 | 2024-10-01 | Labor | 1418329 | 6748062 | 6595648
MCR005297 | HPR022 | 2024-10-01 | Material | 2698553 | 12839054 | 11466708
MCR005298 | HPR022 | 2024-10-01 | Equipment | 603928 | 2873341 | 2930747
MCR005299 | HPR022 | 2024-10-01 | Subcontract | 4683875 | 22284733 | 27279578
MCR005300 | HPR022 | 2024-10-01 | Overhead | 974024 | 4634166 | 12685276
MCR005301 | HPR022 | 2024-11-01 | Labor | 0 | 3907358 | 4791039
MCR005302 | HPR022 | 2024-11-01 | Material | 0 | 7434250 | 7359985
MCR005303 | HPR022 | 2024-11-01 | Equipment | 0 | 1663762 | 1844716
MCR005304 | HPR022 | 2024-11-01 | Subcontract | 0 | 12903620 | 11369205
MCR005305 | HPR022 | 2024-11-01 | Overhead | 0 | 2683340 | 11812353
MCR005306 | HPR022 | 2024-12-01 | Labor | 0 | 3588978 | 4252357
MCR005307 | HPR022 | 2024-12-01 | Material | 0 | 6828491 | 7415536
MCR005308 | HPR022 | 2024-12-01 | Equipment | 0 | 1528195 | 1701047
MCR005309 | HPR022 | 2024-12-01 | Subcontract | 0 | 11852205 | 11766113
MCR005310 | HPR022 | 2024-12-01 | Overhead | 0 | 2464696 | 12183875
MCR005311 | HPR022 | 2025-01-01 | Labor | 0 | 1116015 | 1252918
MCR005312 | HPR022 | 2025-01-01 | Material | 0 | 2123362 | 2445347
MCR005313 | HPR022 | 2025-01-01 | Equipment | 0 | 475202 | 500652
MCR005314 | HPR022 | 2025-01-01 | Subcontract | 0 | 3685518 | 3287688
MCR005315 | HPR022 | 2025-01-01 | Overhead | 0 | 766413 | 12387603
MCR005316 | HPR023 | 2017-07-01 | Labor | 4462592 | 2726638 | 2905402
MCR005317 | HPR023 | 2017-07-01 | Material | 9221079 | 5634068 | 5389926
MCR005318 | HPR023 | 2017-07-01 | Equipment | 2264628 | 1383685 | 1629727
MCR005319 | HPR023 | 2017-07-01 | Subcontract | 11603592 | 7089781 | 6084826
MCR005320 | HPR023 | 2017-07-01 | Overhead | 2744504 | 1676889 | 14610198
MCR005321 | HPR023 | 2017-08-01 | Labor | 12502480 | 7222788 | 8348355
MCR005322 | HPR023 | 2017-08-01 | Material | 25833945 | 14924488 | 15957230
MCR005323 | HPR023 | 2017-08-01 | Equipment | 6344624 | 3665343 | 3562954
MCR005324 | HPR023 | 2017-08-01 | Subcontract | 32508838 | 18780630 | 20164724
MCR005325 | HPR023 | 2017-08-01 | Overhead | 7689053 | 4442031 | 13950420
MCR005326 | HPR023 | 2017-09-01 | Labor | 19241533 | 12051809 | 12018604
MCR005327 | HPR023 | 2017-09-01 | Material | 39758890 | 24902722 | 24081414
MCR005328 | HPR023 | 2017-09-01 | Equipment | 9764486 | 6115923 | 6921460
MCR005329 | HPR023 | 2017-09-01 | Subcontract | 50031665 | 31337009 | 26105012
MCR005330 | HPR023 | 2017-09-01 | Overhead | 11833586 | 7411890 | 13689027
MCR005331 | HPR023 | 2017-10-01 | Labor | 24717633 | 14701548 | 16172078
MCR005332 | HPR023 | 2017-10-01 | Material | 51074186 | 30377893 | 30777609
MCR005333 | HPR023 | 2017-10-01 | Equipment | 12543438 | 7460584 | 9431332
MCR005334 | HPR023 | 2017-10-01 | Subcontract | 64270572 | 38226837 | 42006397
MCR005335 | HPR023 | 2017-10-01 | Overhead | 15201399 | 9041485 | 13480292
MCR005336 | HPR023 | 2017-11-01 | Labor | 28971094 | 28510191 | 30683348
MCR005337 | HPR023 | 2017-11-01 | Material | 59863138 | 58910771 | 67549224
MCR005338 | HPR023 | 2017-11-01 | Equipment | 14701939 | 14468045 | 13239209
MCR005339 | HPR023 | 2017-11-01 | Subcontract | 75330386 | 74131950 | 73293993
MCR005340 | HPR023 | 2017-11-01 | Overhead | 17817288 | 17533831 | 12706509
MCR005341 | HPR023 | 2017-12-01 | Labor | 32045047 | 39651587 | 42195178
MCR005342 | HPR023 | 2017-12-01 | Material | 66214864 | 81932301 | 71400158
MCR005343 | HPR023 | 2017-12-01 | Equipment | 16261876 | 20121961 | 19355423
MCR005344 | HPR023 | 2017-12-01 | Subcontract | 83323250 | 103101709 | 104916202
MCR005345 | HPR023 | 2017-12-01 | Overhead | 19707775 | 24385815 | 13802972
MCR005346 | HPR023 | 2018-01-01 | Labor | 33985915 | 35595000 | 40684334
MCR005347 | HPR023 | 2018-01-01 | Material | 70225291 | 73550153 | 73822954
MCR005348 | HPR023 | 2018-01-01 | Equipment | 17246807 | 18063368 | 21154938
MCR005349 | HPR023 | 2018-01-01 | Subcontract | 88369880 | 92553809 | 88208023
MCR005350 | HPR023 | 2018-01-01 | Overhead | 20901414 | 21891005 | 14359912
MCR005351 | HPR023 | 2018-02-01 | Labor | 34844036 | 16509355 | 14077405
MCR005352 | HPR023 | 2018-02-01 | Material | 71998431 | 34113376 | 38265032
MCR005353 | HPR023 | 2018-02-01 | Equipment | 17682277 | 8377990 | 7219058
MCR005354 | HPR023 | 2018-02-01 | Subcontract | 90601157 | 42927482 | 41178402
MCR005355 | HPR023 | 2018-02-01 | Overhead | 21429160 | 10153291 | 13903381
MCR005356 | HPR023 | 2018-03-01 | Labor | 34674463 | 26728805 | 32024979
MCR005357 | HPR023 | 2018-03-01 | Material | 71648041 | 55229883 | 52738119
MCR005358 | HPR023 | 2018-03-01 | Equipment | 17596224 | 13564047 | 15873028
MCR005359 | HPR023 | 2018-03-01 | Subcontract | 90160235 | 69500006 | 70116008
MCR005360 | HPR023 | 2018-03-01 | Overhead | 21324872 | 16438275 | 12760051
MCR005361 | HPR023 | 2018-04-01 | Labor | 33538054 | 26198569 | 26446545
MCR005362 | HPR023 | 2018-04-01 | Material | 69299873 | 54134253 | 63254502
MCR005363 | HPR023 | 2018-04-01 | Equipment | 17019531 | 13294968 | 13382685
MCR005364 | HPR023 | 2018-04-01 | Subcontract | 87205354 | 68121290 | 69851128
MCR005365 | HPR023 | 2018-04-01 | Overhead | 20625978 | 16112179 | 12847456
MCR005366 | HPR023 | 2018-05-01 | Labor | 31502978 | 21160332 | 24650294
MCR005367 | HPR023 | 2018-05-01 | Material | 65094785 | 43723716 | 39287039
MCR005368 | HPR023 | 2018-05-01 | Equipment | 15986793 | 10738218 | 10410291
MCR005369 | HPR023 | 2018-05-01 | Subcontract | 81913769 | 55020911 | 53306741
MCR005370 | HPR023 | 2018-05-01 | Overhead | 19374402 | 13013652 | 13334366
MCR005371 | HPR023 | 2018-06-01 | Labor | 28646894 | 13758818 | 14288938
MCR005372 | HPR023 | 2018-06-01 | Material | 59193241 | 28429925 | 32586719
MCR005373 | HPR023 | 2018-06-01 | Equipment | 14537418 | 6982177 | 7665763
MCR005374 | HPR023 | 2018-06-01 | Subcontract | 74487403 | 35775559 | 35120752
MCR005375 | HPR023 | 2018-06-01 | Overhead | 17617904 | 8461704 | 13119842
MCR005376 | HPR023 | 2018-07-01 | Labor | 25060243 | 19065001 | 20618820
MCR005377 | HPR023 | 2018-07-01 | Material | 51782125 | 39394121 | 41131236
MCR005378 | HPR023 | 2018-07-01 | Equipment | 12717303 | 9674902 | 10961298
MCR005379 | HPR023 | 2018-07-01 | Subcontract | 65161426 | 49572649 | 48691061
MCR005380 | HPR023 | 2018-07-01 | Overhead | 15412106 | 11725018 | 14240254
MCR005381 | HPR023 | 2018-08-01 | Labor | 20851589 | 18493742 | 19652043
MCR005382 | HPR023 | 2018-08-01 | Material | 43085758 | 38213724 | 40001156
MCR005383 | HPR023 | 2018-08-01 | Equipment | 10581540 | 9385005 | 8583800
MCR005384 | HPR023 | 2018-08-01 | Subcontract | 54218119 | 48087265 | 46392908
MCR005385 | HPR023 | 2018-08-01 | Overhead | 12823774 | 11373692 | 14048204
MCR005386 | HPR023 | 2018-09-01 | Labor | 16157021 | 21374542 | 22336826
MCR005387 | HPR023 | 2018-09-01 | Material | 33385344 | 44166339 | 46876824
MCR005388 | HPR023 | 2018-09-01 | Equipment | 8199191 | 10846923 | 11123706
MCR005389 | HPR023 | 2018-09-01 | Subcontract | 42011344 | 55577897 | 57965652
MCR005390 | HPR023 | 2018-09-01 | Overhead | 9936604 | 13145391 | 13931070
MCR005391 | HPR023 | 2018-10-01 | Labor | 11159051 | 27615869 | 31804664
MCR005392 | HPR023 | 2018-10-01 | Material | 23058012 | 57062828 | 56568706
MCR005393 | HPR023 | 2018-10-01 | Equipment | 5662875 | 14014204 | 14860990
MCR005394 | HPR023 | 2018-10-01 | Subcontract | 29015667 | 71806541 | 74570020
MCR005395 | HPR023 | 2018-10-01 | Overhead | 6862842 | 16983821 | 13367479
MCR005396 | HPR023 | 2018-11-01 | Labor | 6133622 | 38735423 | 43682638
MCR005397 | HPR023 | 2018-11-01 | Material | 12673939 | 80039227 | 86936184
MCR005398 | HPR023 | 2018-11-01 | Equipment | 3112625 | 19657036 | 20459586
MCR005399 | HPR023 | 2018-11-01 | Subcontract | 15948591 | 100719509 | 99411542
MCR005400 | HPR023 | 2018-11-01 | Overhead | 3772191 | 23822372 | 13112562
MCR005401 | HPR023 | 2018-12-01 | Labor | 1646073 | 9370816 | 7250183
MCR005402 | HPR023 | 2018-12-01 | Material | 3401291 | 19362971 | 15644569
MCR005403 | HPR023 | 2018-12-01 | Equipment | 835332 | 4755401 | 4899676
MCR005404 | HPR023 | 2018-12-01 | Subcontract | 4280105 | 24365914 | 21291487
MCR005405 | HPR023 | 2018-12-01 | Overhead | 1012339 | 5763073 | 14067461
MCR005406 | HPR023 | 2019-01-01 | Labor | 0 | 9411079 | 9167466
MCR005407 | HPR023 | 2019-01-01 | Material | 0 | 19446166 | 21505760
MCR005408 | HPR023 | 2019-01-01 | Equipment | 0 | 4775833 | 5049959
MCR005409 | HPR023 | 2019-01-01 | Subcontract | 0 | 24470605 | 26611839
MCR005410 | HPR023 | 2019-01-01 | Overhead | 0 | 5787835 | 13850805
MCR005411 | HPR023 | 2019-02-01 | Labor | 0 | 6974137 | 7291975
MCR005412 | HPR023 | 2019-02-01 | Material | 0 | 14410699 | 13928459
MCR005413 | HPR023 | 2019-02-01 | Equipment | 0 | 3539160 | 3705362
MCR005414 | HPR023 | 2019-02-01 | Subcontract | 0 | 18134090 | 17961654
MCR005415 | HPR023 | 2019-02-01 | Overhead | 0 | 4289110 | 13273527
MCR005416 | HPR023 | 2019-03-01 | Labor | 0 | 3051831 | 2786963
MCR005417 | HPR023 | 2019-03-01 | Material | 0 | 6306016 | 6053218
MCR005418 | HPR023 | 2019-03-01 | Equipment | 0 | 1548711 | 1310503
MCR005419 | HPR023 | 2019-03-01 | Subcontract | 0 | 7935345 | 7864567
MCR005420 | HPR023 | 2019-03-01 | Overhead | 0 | 1876883 | 13802911
MCR005421 | HPR023 | 2019-04-01 | Labor | 0 | 1232435 | 1238433
MCR005422 | HPR023 | 2019-04-01 | Material | 0 | 2546588 | 2955440
MCR005423 | HPR023 | 2019-04-01 | Equipment | 0 | 625423 | 806352
MCR005424 | HPR023 | 2019-04-01 | Subcontract | 0 | 3204567 | 2786414
MCR005425 | HPR023 | 2019-04-01 | Overhead | 0 | 757950 | 12948833
MCR005426 | HPR024 | 2017-08-01 | Labor | 5949443 | 3668784 | 3316549
MCR005427 | HPR024 | 2017-08-01 | Material | 10517193 | 6485532 | 6093380
MCR005428 | HPR024 | 2017-08-01 | Equipment | 2577731 | 1589584 | 1642742
MCR005429 | HPR024 | 2017-08-01 | Subcontract | 19742709 | 12174538 | 12605668
MCR005430 | HPR024 | 2017-08-01 | Overhead | 4460692 | 2750730 | 26436040
MCR005431 | HPR024 | 2017-09-01 | Labor | 16930608 | 13350185 | 13485202
MCR005432 | HPR024 | 2017-09-01 | Material | 29929266 | 23599934 | 26702931
MCR005433 | HPR024 | 2017-09-01 | Equipment | 7335570 | 5784271 | 6215619
MCR005434 | HPR024 | 2017-09-01 | Subcontract | 56182747 | 44301425 | 43186710
MCR005435 | HPR024 | 2017-09-01 | Overhead | 12693998 | 10009518 | 29791773
MCR005436 | HPR024 | 2017-10-01 | Labor | 26556765 | 23810425 | 27274191
MCR005437 | HPR024 | 2017-10-01 | Material | 46946008 | 42091136 | 43666296
MCR005438 | HPR024 | 2017-10-01 | Equipment | 11506321 | 10316407 | 10584225
MCR005439 | HPR024 | 2017-10-01 | Subcontract | 88126308 | 79012819 | 78680290
MCR005440 | HPR024 | 2017-10-01 | Overhead | 19911365 | 17852252 | 28240720
MCR005441 | HPR024 | 2017-11-01 | Labor | 34857724 | 18500531 | 17986127
MCR005442 | HPR024 | 2017-11-01 | Material | 61620119 | 32704514 | 29868192
MCR005443 | HPR024 | 2017-11-01 | Equipment | 15102900 | 8015775 | 7778290
MCR005444 | HPR024 | 2017-11-01 | Subcontract | 115672317 | 61392399 | 59346561
MCR005445 | HPR024 | 2017-11-01 | Overhead | 26135144 | 13871073 | 28456662
MCR005446 | HPR024 | 2017-12-01 | Labor | 41864720 | 24591396 | 28059442
MCR005447 | HPR024 | 2017-12-01 | Material | 74006812 | 43471708 | 47926279
MCR005448 | HPR024 | 2017-12-01 | Equipment | 18138840 | 10654780 | 10855665
MCR005449 | HPR024 | 2017-12-01 | Subcontract | 138924423 | 81604405 | 79824222
MCR005450 | HPR024 | 2017-12-01 | Overhead | 31388753 | 18437798 | 27368470
MCR005451 | HPR024 | 2018-01-01 | Labor | 47610575 | 29840939 | 29851620
MCR005452 | HPR024 | 2018-01-01 | Material | 84164110 | 52751643 | 49339613
MCR005453 | HPR024 | 2018-01-01 | Equipment | 20628362 | 12929264 | 12694333
MCR005454 | HPR024 | 2018-01-01 | Subcontract | 157991543 | 99024554 | 95916714
MCR005455 | HPR024 | 2018-01-01 | Overhead | 35696801 | 22373728 | 28611849
MCR005456 | HPR024 | 2018-02-01 | Labor | 52129892 | 21828933 | 23358289
MCR005457 | HPR024 | 2018-02-01 | Material | 92153182 | 38588333 | 40654235
MCR005458 | HPR024 | 2018-02-01 | Equipment | 22586459 | 9457881 | 8842921
MCR005459 | HPR024 | 2018-02-01 | Subcontract | 172988502 | 72437412 | 73692322
MCR005460 | HPR024 | 2018-02-01 | Overhead | 39085232 | 16366597 | 27644834
MCR005461 | HPR024 | 2018-03-01 | Labor | 55459285 | 44508717 | 52514395
MCR005462 | HPR024 | 2018-03-01 | Material | 98038752 | 78680767 | 72094483
MCR005463 | HPR024 | 2018-03-01 | Equipment | 24028993 | 19284412 | 20386988
MCR005464 | HPR024 | 2018-03-01 | Subcontract | 184036801 | 147698297 | 138822167
MCR005465 | HPR024 | 2018-03-01 | Overhead | 41581498 | 33371132 | 28715867
MCR005466 | HPR024 | 2018-04-01 | Labor | 57637657 | 40990325 | 38512097
MCR005467 | HPR024 | 2018-04-01 | Material | 101889594 | 72461091 | 70679187
MCR005468 | HPR024 | 2018-04-01 | Equipment | 24972823 | 17759988 | 17623539
MCR005469 | HPR024 | 2018-04-01 | Subcontract | 191265542 | 136022819 | 135962262
MCR005470 | HPR024 | 2018-04-01 | Overhead | 43214768 | 30733161 | 28631717
MCR005471 | HPR024 | 2018-05-01 | Labor | 58706549 | 46280336 | 43857309
MCR005472 | HPR024 | 2018-05-01 | Material | 103779139 | 81812566 | 99989063
MCR005473 | HPR024 | 2018-05-01 | Equipment | 25435945 | 20052006 | 19488445
MCR005474 | HPR024 | 2018-05-01 | Subcontract | 194812566 | 153577261 | 166022054
MCR005475 | HPR024 | 2018-05-01 | Overhead | 44016187 | 34699433 | 28837464
MCR005476 | HPR024 | 2018-06-01 | Labor | 58710558 | 56321267 | 64921247
MCR005477 | HPR024 | 2018-06-01 | Material | 103786225 | 99562530 | 80276607
MCR005478 | HPR024 | 2018-06-01 | Equipment | 25437681 | 24402467 | 24080373
MCR005479 | HPR024 | 2018-06-01 | Subcontract | 194825868 | 186897214 | 185438429
MCR005480 | HPR024 | 2018-06-01 | Overhead | 44019193 | 42227783 | 28918157
MCR005481 | HPR024 | 2018-07-01 | Labor | 57697878 | 40276905 | 43360198
MCR005482 | HPR024 | 2018-07-01 | Material | 101996050 | 71199935 | 85965873
MCR005483 | HPR024 | 2018-07-01 | Equipment | 24998915 | 17450883 | 16411907
MCR005484 | HPR024 | 2018-07-01 | Subcontract | 191465379 | 133655398 | 134965872
MCR005485 | HPR024 | 2018-07-01 | Overhead | 43259920 | 30198263 | 25609019
MCR005486 | HPR024 | 2018-08-01 | Labor | 55720995 | 30022533 | 27537861
MCR005487 | HPR024 | 2018-08-01 | Material | 98501393 | 53072659 | 51893713
MCR005488 | HPR024 | 2018-08-01 | Equipment | 24142385 | 13007944 | 14319301
MCR005489 | HPR024 | 2018-08-01 | Subcontract | 184905264 | 99627159 | 94366621
MCR005490 | HPR024 | 2018-08-01 | Overhead | 41777720 | 22509881 | 26504944
MCR005491 | HPR024 | 2018-09-01 | Labor | 52837593 | 46519937 | 50727954
MCR005492 | HPR024 | 2018-09-01 | Material | 93404228 | 82236124 | 83097760
MCR005493 | HPR024 | 2018-09-01 | Equipment | 22893086 | 20155819 | 21102309
MCR005494 | HPR024 | 2018-09-01 | Subcontract | 175336947 | 154372357 | 149942194
MCR005495 | HPR024 | 2018-09-01 | Overhead | 39615843 | 34879078 | 27365582
MCR005496 | HPR024 | 2018-10-01 | Labor | 49111793 | 57398044 | 52142093
MCR005497 | HPR024 | 2018-10-01 | Material | 86817905 | 101466015 | 107434248
MCR005498 | HPR024 | 2018-10-01 | Equipment | 21278799 | 24869005 | 21500838
MCR005499 | HPR024 | 2018-10-01 | Subcontract | 162973205 | 190470407 | 223264826
MCR005500 | HPR024 | 2018-10-01 | Overhead | 36822364 | 43035115 | 27012437
MCR005501 | HPR024 | 2018-11-01 | Labor | 44615869 | 30628198 | 33998343
MCR005502 | HPR024 | 2018-11-01 | Material | 78870186 | 54143329 | 56752573
MCR005503 | HPR024 | 2018-11-01 | Equipment | 19330838 | 13270362 | 16445076
MCR005504 | HPR024 | 2018-11-01 | Subcontract | 148053871 | 101637004 | 89434373
MCR005505 | HPR024 | 2018-11-01 | Overhead | 33451471 | 22963988 | 28863582
MCR005506 | HPR024 | 2018-12-01 | Labor | 39432742 | 59956900 | 65872348
MCR005507 | HPR024 | 2018-12-01 | Material | 69707657 | 105989461 | 116933738
MCR005508 | HPR024 | 2018-12-01 | Equipment | 17085130 | 25977688 | 26061518
MCR005509 | HPR024 | 2018-12-01 | Subcontract | 130854117 | 198961747 | 195540742
MCR005510 | HPR024 | 2018-12-01 | Overhead | 29565338 | 44953658 | 28800500
MCR005511 | HPR024 | 2019-01-01 | Labor | 33659793 | 38890942 | 40078997
MCR005512 | HPR024 | 2019-01-01 | Material | 59502464 | 68749885 | 66728079
MCR005513 | HPR024 | 2019-01-01 | Equipment | 14583869 | 16850383 | 18358837
MCR005514 | HPR024 | 2019-01-01 | Subcontract | 111697088 | 129056202 | 115691292
MCR005515 | HPR024 | 2019-01-01 | Overhead | 25236976 | 29159115 | 28359766
MCR005516 | HPR024 | 2019-02-01 | Labor | 27415047 | 40183994 | 41832498
MCR005517 | HPR024 | 2019-02-01 | Material | 48463246 | 71035690 | 69240369
MCR005518 | HPR024 | 2019-02-01 | Equipment | 11878191 | 17410627 | 17324228
MCR005519 | HPR024 | 2019-02-01 | Subcontract | 90974443 | 133347080 | 139426868
MCR005520 | HPR024 | 2019-02-01 | Overhead | 20554876 | 30128601 | 26391454
MCR005521 | HPR024 | 2019-03-01 | Labor | 20848177 | 36912544 | 35428593
MCR005522 | HPR024 | 2019-03-01 | Material | 36854591 | 65252550 | 64242597
MCR005523 | HPR024 | 2019-03-01 | Equipment | 9032946 | 15993197 | 16599765
MCR005524 | HPR024 | 2019-03-01 | Subcontract | 69182859 | 122491060 | 133469363
MCR005525 | HPR024 | 2019-03-01 | Overhead | 15631259 | 27675779 | 27849381
MCR005526 | HPR024 | 2019-04-01 | Labor | 14162755 | 41894976 | 49308663
MCR005527 | HPR024 | 2019-04-01 | Material | 25036364 | 74060298 | 83971187
MCR005528 | HPR024 | 2019-04-01 | Equipment | 6136335 | 18151949 | 16552746
MCR005529 | HPR024 | 2019-04-01 | Subcontract | 46997868 | 139024826 | 139448714
MCR005530 | HPR024 | 2019-04-01 | Overhead | 10618755 | 31411438 | 25827060
MCR005531 | HPR024 | 2019-05-01 | Labor | 7672087 | 38037506 | 38016579
MCR005532 | HPR024 | 2019-05-01 | Material | 13562415 | 67241213 | 62920685
MCR005533 | HPR024 | 2019-05-01 | Equipment | 3324106 | 16480613 | 18496926
MCR005534 | HPR024 | 2019-05-01 | Subcontract | 25459153 | 126224147 | 113969019
MCR005535 | HPR024 | 2019-05-01 | Overhead | 5752272 | 28519237 | 27903267
MCR005536 | HPR024 | 2019-06-01 | Labor | 2034667 | 31783575 | 38020758
MCR005537 | HPR024 | 2019-06-01 | Material | 3596805 | 56185759 | 61220963
MCR005538 | HPR024 | 2019-06-01 | Equipment | 881566 | 13770955 | 13984632
MCR005539 | HPR024 | 2019-06-01 | Subcontract | 6751865 | 105471023 | 119447857
MCR005540 | HPR024 | 2019-06-01 | Overhead | 1525525 | 23830251 | 26733501
MCR005541 | HPR024 | 2019-07-01 | Labor | 0 | 13079573 | 13448715
MCR005542 | HPR024 | 2019-07-01 | Material | 0 | 23121558 | 23062594
MCR005543 | HPR024 | 2019-07-01 | Equipment | 0 | 5667022 | 5225380
MCR005544 | HPR024 | 2019-07-01 | Subcontract | 0 | 43403424 | 44047038
MCR005545 | HPR024 | 2019-07-01 | Overhead | 0 | 9806622 | 30648979
MCR005546 | HPR024 | 2019-08-01 | Labor | 0 | 14319141 | 14815139
MCR005547 | HPR024 | 2019-08-01 | Material | 0 | 25312817 | 22701031
MCR005548 | HPR024 | 2019-08-01 | Equipment | 0 | 6204093 | 7422724
MCR005549 | HPR024 | 2019-08-01 | Subcontract | 0 | 47516822 | 34418444
MCR005550 | HPR024 | 2019-08-01 | Overhead | 0 | 10736008 | 27868540
MCR005551 | HPR024 | 2019-09-01 | Labor | 0 | 8163598 | 9463691
MCR005552 | HPR024 | 2019-09-01 | Material | 0 | 14431288 | 13814579
MCR005553 | HPR024 | 2019-09-01 | Equipment | 0 | 3537064 | 3858847
MCR005554 | HPR024 | 2019-09-01 | Subcontract | 0 | 27090187 | 32508336
MCR005555 | HPR024 | 2019-09-01 | Overhead | 0 | 6120790 | 27401906
MCR005556 | HPR024 | 2019-10-01 | Labor | 0 | 8463740 | 10294392
MCR005557 | HPR024 | 2019-10-01 | Material | 0 | 14961868 | 15331270
MCR005558 | HPR024 | 2019-10-01 | Equipment | 0 | 3667107 | 3628582
MCR005559 | HPR024 | 2019-10-01 | Subcontract | 0 | 28086182 | 29968301
MCR005560 | HPR024 | 2019-10-01 | Overhead | 0 | 6345826 | 28586889
MCR005561 | HPR024 | 2019-11-01 | Labor | 0 | 1399228 | 1713867
MCR005562 | HPR024 | 2019-11-01 | Material | 0 | 2473501 | 2977336
MCR005563 | HPR024 | 2019-11-01 | Equipment | 0 | 606247 | 721548
MCR005564 | HPR024 | 2019-11-01 | Subcontract | 0 | 4643216 | 3736208
MCR005565 | HPR024 | 2019-11-01 | Overhead | 0 | 1049094 | 30239559
MCR005566 | HPR025 | 2020-09-01 | Labor | 10994322 | 6417686 | 6985650
MCR005567 | HPR025 | 2020-09-01 | Material | 32418128 | 18923346 | 20323251
MCR005568 | HPR025 | 2020-09-01 | Equipment | 7288650 | 4254584 | 3715904
MCR005569 | HPR025 | 2020-09-01 | Subcontract | 23767647 | 13873824 | 12854781
MCR005570 | HPR025 | 2020-09-01 | Overhead | 6183881 | 3609700 | 21979321
MCR005571 | HPR025 | 2020-10-01 | Labor | 30154696 | 18638871 | 19784884
MCR005572 | HPR025 | 2020-10-01 | Material | 88914876 | 54959031 | 63138167
MCR005573 | HPR025 | 2020-10-01 | Equipment | 19990958 | 12356579 | 13090730
MCR005574 | HPR025 | 2020-10-01 | Subcontract | 65188754 | 40293716 | 43366533
MCR005575 | HPR025 | 2020-10-01 | Overhead | 16960850 | 10483644 | 23349262
MCR005576 | HPR025 | 2020-11-01 | Labor | 45186944 | 48789435 | 47747075
MCR005577 | HPR025 | 2020-11-01 | Material | 133239330 | 143861724 | 128128134
MCR005578 | HPR025 | 2020-11-01 | Equipment | 29956537 | 32344797 | 34622658
MCR005579 | HPR025 | 2020-11-01 | Subcontract | 97685633 | 105473539 | 91966691
MCR005580 | HPR025 | 2020-11-01 | Overhead | 25415908 | 27442171 | 23886252
MCR005581 | HPR025 | 2020-12-01 | Labor | 56253296 | 45260686 | 44903629
MCR005582 | HPR025 | 2020-12-01 | Material | 165869847 | 133456768 | 142503998
MCR005583 | HPR025 | 2020-12-01 | Equipment | 37292939 | 30005424 | 31935132
MCR005584 | HPR025 | 2020-12-01 | Subcontract | 121608995 | 97845050 | 96286808
MCR005585 | HPR025 | 2020-12-01 | Overhead | 31640304 | 25457386 | 24344790
MCR005586 | HPR025 | 2021-01-01 | Labor | 63530375 | 31512331 | 32226804
MCR005587 | HPR025 | 2021-01-01 | Material | 187327219 | 92918031 | 84070236
MCR005588 | HPR025 | 2021-01-01 | Equipment | 42117255 | 20890997 | 22452349
MCR005589 | HPR025 | 2021-01-01 | Subcontract | 137340664 | 68123704 | 62239128
MCR005590 | HPR025 | 2021-01-01 | Overhead | 35733379 | 17724468 | 22195187
MCR005591 | HPR025 | 2021-02-01 | Labor | 67212403 | 41743748 | 45075349
MCR005592 | HPR025 | 2021-02-01 | Material | 198184139 | 123086639 | 131915935
MCR005593 | HPR025 | 2021-02-01 | Equipment | 44558244 | 27673882 | 28310326
MCR005594 | HPR025 | 2021-02-01 | Subcontract | 145300514 | 90242095 | 81335263
MCR005595 | HPR025 | 2021-02-01 | Overhead | 37804378 | 23479244 | 25144477
MCR005596 | HPR025 | 2021-03-01 | Labor | 67515637 | 69314511 | 69514604
MCR005597 | HPR025 | 2021-03-01 | Material | 199078263 | 204382467 | 210114777
MCR005598 | HPR025 | 2021-03-01 | Equipment | 44759272 | 45951830 | 41023104
MCR005599 | HPR025 | 2021-03-01 | Subcontract | 145956049 | 149844874 | 141781395
MCR005600 | HPR025 | 2021-03-01 | Overhead | 37974935 | 38986732 | 23877124
MCR005601 | HPR025 | 2021-04-01 | Labor | 64684721 | 56600160 | 58927314
MCR005602 | HPR025 | 2021-04-01 | Material | 190730953 | 166892620 | 167649253
MCR005603 | HPR025 | 2021-04-01 | Equipment | 42882525 | 37522892 | 40642461
MCR005604 | HPR025 | 2021-04-01 | Subcontract | 139836142 | 122358850 | 126556974
MCR005605 | HPR025 | 2021-04-01 | Overhead | 36382654 | 31835401 | 24589614
MCR005606 | HPR025 | 2021-05-01 | Labor | 59002258 | 40590024 | 43171944
MCR005607 | HPR025 | 2021-05-01 | Material | 173975504 | 119684739 | 127235963
MCR005608 | HPR025 | 2021-05-01 | Equipment | 39115355 | 26909024 | 30495216
MCR005609 | HPR025 | 2021-05-01 | Subcontract | 127551732 | 87747961 | 69298155
MCR005610 | HPR025 | 2021-05-01 | Overhead | 33186488 | 22830319 | 25405462
MCR005611 | HPR025 | 2021-06-01 | Labor | 50804177 | 88730063 | 79151677
MCR005612 | HPR025 | 2021-06-01 | Material | 149802441 | 261631638 | 242274926
MCR005613 | HPR025 | 2021-06-01 | Equipment | 33680464 | 58823306 | 57638013
MCR005614 | HPR025 | 2021-06-01 | Subcontract | 109829029 | 191817627 | 188279098
MCR005615 | HPR025 | 2021-06-01 | Overhead | 28575385 | 49907229 | 23649418
MCR005616 | HPR025 | 2021-07-01 | Labor | 40506620 | 27040521 | 29891846
MCR005617 | HPR025 | 2021-07-01 | Material | 119438814 | 79732344 | 91082085
MCR005618 | HPR025 | 2021-07-01 | Equipment | 26853732 | 17926426 | 21369332
MCR005619 | HPR025 | 2021-07-01 | Subcontract | 87567658 | 58456497 | 57753783
MCR005620 | HPR025 | 2021-07-01 | Overhead | 22783408 | 15209248 | 23436684
MCR005621 | HPR025 | 2021-08-01 | Labor | 28659463 | 48596580 | 47333542
MCR005622 | HPR025 | 2021-08-01 | Material | 84505995 | 143293067 | 140198816
MCR005623 | HPR025 | 2021-08-01 | Equipment | 18999698 | 32216945 | 34506980
MCR005624 | HPR025 | 2021-08-01 | Subcontract | 61956343 | 105056622 | 109252039
MCR005625 | HPR025 | 2021-08-01 | Overhead | 16119840 | 27333697 | 25068471
MCR005626 | HPR025 | 2021-09-01 | Labor | 16078090 | 26090422 | 26888208
MCR005627 | HPR025 | 2021-09-01 | Material | 47408249 | 76930858 | 81840307
MCR005628 | HPR025 | 2021-09-01 | Equipment | 10658917 | 17296560 | 16124095
MCR005629 | HPR025 | 2021-09-01 | Subcontract | 34757791 | 56402562 | 47210070
MCR005630 | HPR025 | 2021-09-01 | Overhead | 9043304 | 14674853 | 22889450
MCR005631 | HPR025 | 2021-10-01 | Labor | 4385049 | 25755909 | 28428117
MCR005632 | HPR025 | 2021-10-01 | Material | 12929863 | 75944503 | 86175064
MCR005633 | HPR025 | 2021-10-01 | Equipment | 2907054 | 17074796 | 15981894
MCR005634 | HPR025 | 2021-10-01 | Subcontract | 9479647 | 55679407 | 52597325
MCR005635 | HPR025 | 2021-10-01 | Overhead | 2466420 | 14486703 | 24942496
MCR005636 | HPR025 | 2021-11-01 | Labor | 0 | 19437667 | 18436173
MCR005637 | HPR025 | 2021-11-01 | Material | 0 | 57314381 | 60238182
MCR005638 | HPR025 | 2021-11-01 | Equipment | 0 | 12886138 | 13817953
MCR005639 | HPR025 | 2021-11-01 | Subcontract | 0 | 42020563 | 37444588
MCR005640 | HPR025 | 2021-11-01 | Overhead | 0 | 10932936 | 21581337
MCR005641 | HPR025 | 2021-12-01 | Labor | 0 | 7945549 | 7763763
MCR005642 | HPR025 | 2021-12-01 | Material | 0 | 23428440 | 25654897
MCR005643 | HPR025 | 2021-12-01 | Equipment | 0 | 5267476 | 6060613
MCR005644 | HPR025 | 2021-12-01 | Subcontract | 0 | 17176775 | 14817277
MCR005645 | HPR025 | 2021-12-01 | Overhead | 0 | 4469064 | 25611673
MCR005646 | HPR025 | 2022-01-01 | Labor | 0 | 2503887 | 2044615
MCR005647 | HPR025 | 2022-01-01 | Material | 0 | 7383023 | 5106494
MCR005648 | HPR025 | 2022-01-01 | Equipment | 0 | 1659944 | 1853549
MCR005649 | HPR025 | 2022-01-01 | Subcontract | 0 | 5412930 | 6812186
MCR005650 | HPR025 | 2022-01-01 | Overhead | 0 | 1408340 | 24652466
MCR005651 | HPR026 | 2021-06-01 | Labor | 8828170 | 5840995 | 5270459
MCR005652 | HPR026 | 2021-06-01 | Material | 28285421 | 18714525 | 21723891
MCR005653 | HPR026 | 2021-06-01 | Equipment | 8679256 | 5742469 | 5432448
MCR005654 | HPR026 | 2021-06-01 | Subcontract | 31534487 | 20864209 | 22695640
MCR005655 | HPR026 | 2021-06-01 | Overhead | 7303513 | 4832234 | 26642514
MCR005656 | HPR026 | 2021-07-01 | Labor | 23817909 | 14155869 | 16110799
MCR005657 | HPR026 | 2021-07-01 | Material | 76312480 | 45355345 | 40185342
MCR005658 | HPR026 | 2021-07-01 | Equipment | 23416145 | 13917086 | 14743885
MCR005659 | HPR026 | 2021-07-01 | Subcontract | 85078277 | 50565185 | 49462359
MCR005660 | HPR026 | 2021-07-01 | Overhead | 19704467 | 11711098 | 23507557
MCR005661 | HPR026 | 2021-08-01 | Labor | 34935990 | 7721257 | 8594570
MCR005662 | HPR026 | 2021-08-01 | Material | 111934766 | 24738874 | 28483466
MCR005663 | HPR026 | 2021-08-01 | Equipment | 34346685 | 7591013 | 6384658
MCR005664 | HPR026 | 2021-08-01 | Subcontract | 124792394 | 27580558 | 28941386
MCR005665 | HPR026 | 2021-08-01 | Overhead | 28902415 | 6387767 | 23377604
MCR005666 | HPR026 | 2021-09-01 | Labor | 42366801 | 26710893 | 28554156
MCR005667 | HPR026 | 2021-09-01 | Material | 135743050 | 85581588 | 99242111
MCR005668 | HPR026 | 2021-09-01 | Equipment | 41652152 | 26260330 | 29852032
MCR005669 | HPR026 | 2021-09-01 | Subcontract | 151335469 | 95412101 | 96868092
MCR005670 | HPR026 | 2021-09-01 | Overhead | 35049896 | 22097822 | 25438707
MCR005671 | HPR026 | 2021-10-01 | Labor | 46314940 | 35873636 | 40743338
MCR005672 | HPR026 | 2021-10-01 | Material | 148392872 | 114938978 | 121347895
MCR005673 | HPR026 | 2021-10-01 | Equipment | 45533693 | 35268515 | 35915957
MCR005674 | HPR026 | 2021-10-01 | Subcontract | 165438340 | 128141692 | 143830724
MCR005675 | HPR026 | 2021-10-01 | Overhead | 38316178 | 29678126 | 24166553
MCR005676 | HPR026 | 2021-11-01 | Labor | 47010943 | 43453066 | 44606375
MCR005677 | HPR026 | 2021-11-01 | Material | 150622861 | 139223441 | 148117299
MCR005678 | HPR026 | 2021-11-01 | Equipment | 46217956 | 42720094 | 42192385
MCR005679 | HPR026 | 2021-11-01 | Subcontract | 167924481 | 155215642 | 175682695
MCR005680 | HPR026 | 2021-11-01 | Overhead | 38891978 | 35948560 | 23278154
MCR005681 | HPR026 | 2021-12-01 | Labor | 44719847 | 40929527 | 53489171
MCR005682 | HPR026 | 2021-12-01 | Material | 143282202 | 131138030 | 117417989
MCR005683 | HPR026 | 2021-12-01 | Equipment | 43965507 | 40239122 | 43407324
MCR005684 | HPR026 | 2021-12-01 | Subcontract | 159740621 | 146201483 | 133829139
MCR005685 | HPR026 | 2021-12-01 | Overhead | 36996563 | 33860845 | 26311011
MCR005686 | HPR026 | 2022-01-01 | Labor | 39754892 | 32774905 | 35476383
MCR005687 | HPR026 | 2022-01-01 | Material | 127374506 | 105010658 | 127647550
MCR005688 | HPR026 | 2022-01-01 | Equipment | 39084301 | 32222054 | 26630332
MCR005689 | HPR026 | 2022-01-01 | Subcontract | 142005654 | 117072935 | 122198793
MCR005690 | HPR026 | 2022-01-01 | Overhead | 32889074 | 27114557 | 25400765
MCR005691 | HPR026 | 2022-02-01 | Labor | 32501354 | 34916943 | 40231693
MCR005692 | HPR026 | 2022-02-01 | Material | 104134201 | 111873739 | 113002967
MCR005693 | HPR026 | 2022-02-01 | Equipment | 31953117 | 34327960 | 35763638
MCR005694 | HPR026 | 2022-02-01 | Subcontract | 116095801 | 124724357 | 143565531
MCR005695 | HPR026 | 2022-02-01 | Overhead | 26888249 | 28886657 | 24787319
MCR005696 | HPR026 | 2022-03-01 | Labor | 23463704 | 32810324 | 40705599
MCR005697 | HPR026 | 2022-03-01 | Material | 75177607 | 105124138 | 118412406
MCR005698 | HPR026 | 2022-03-01 | Equipment | 23067915 | 32256875 | 32488417
MCR005699 | HPR026 | 2022-03-01 | Subcontract | 83813045 | 117199450 | 116380303
MCR005700 | HPR026 | 2022-03-01 | Overhead | 19411435 | 27143859 | 24148834
MCR005701 | HPR026 | 2022-04-01 | Labor | 13380886 | 41894929 | 39719117
MCR005702 | HPR026 | 2022-04-01 | Material | 42872303 | 134231175 | 133965752
MCR005703 | HPR026 | 2022-04-01 | Equipment | 13155176 | 41188240 | 45150307
MCR005704 | HPR026 | 2022-04-01 | Subcontract | 47796923 | 149649929 | 148842397
MCR005705 | HPR026 | 2022-04-01 | Overhead | 11069957 | 34659519 | 24220357
MCR005706 | HPR026 | 2022-05-01 | Labor | 3695441 | 28330625 | 46300362
MCR005707 | HPR026 | 2022-05-01 | Material | 11840177 | 90771202 | 96088334
MCR005708 | HPR026 | 2022-05-01 | Equipment | 3633106 | 27852740 | 26471087
MCR005709 | HPR026 | 2022-05-01 | Subcontract | 13200225 | 101197832 | 107155129
MCR005710 | HPR026 | 2022-05-01 | Overhead | 3057225 | 23437820 | 25248137
MCR005711 | HPR026 | 2022-06-01 | Labor | 0 | 13048316 | 10087959
MCR005712 | HPR026 | 2022-06-01 | Material | 0 | 41806749 | 42138673
MCR005713 | HPR026 | 2022-06-01 | Equipment | 0 | 12828215 | 12729760
MCR005714 | HPR026 | 2022-06-01 | Subcontract | 0 | 46608971 | 49507763
MCR005715 | HPR026 | 2022-06-01 | Overhead | 0 | 10794823 | 25202343
MCR005716 | HPR026 | 2022-07-01 | Labor | 0 | 2329592 | 2210127
MCR005717 | HPR026 | 2022-07-01 | Material | 0 | 7464004 | 5771307
MCR005718 | HPR026 | 2022-07-01 | Equipment | 0 | 2290297 | 1982418
MCR005719 | HPR026 | 2022-07-01 | Subcontract | 0 | 8321373 | 11460381
MCR005720 | HPR026 | 2022-07-01 | Overhead | 0 | 1927263 | 23441219
MCR005721 | HPR027 | 2023-04-01 | Labor | 6344591 | 3810399 | 3882322
MCR005722 | HPR027 | 2023-04-01 | Material | 12439142 | 7470630 | 6499818
MCR005723 | HPR027 | 2023-04-01 | Equipment | 2812133 | 1688895 | 1714327
MCR005724 | HPR027 | 2023-04-01 | Subcontract | 15759491 | 9464747 | 9942420
MCR005725 | HPR027 | 2023-04-01 | Overhead | 2792638 | 1677187 | 14938094
MCR005726 | HPR027 | 2023-05-01 | Labor | 17843238 | 11452540 | 12226593
MCR005727 | HPR027 | 2023-05-01 | Material | 34983273 | 22453734 | 21894556
MCR005728 | HPR027 | 2023-05-01 | Equipment | 7908713 | 5076145 | 5090365
MCR005729 | HPR027 | 2023-05-01 | Subcontract | 44321272 | 28447254 | 27404682
MCR005730 | HPR027 | 2023-05-01 | Overhead | 7853886 | 5040954 | 14995814
MCR005731 | HPR027 | 2023-06-01 | Labor | 27590457 | 11355479 | 12581328
MCR005732 | HPR027 | 2023-06-01 | Material | 54093571 | 22263438 | 22024124
MCR005733 | HPR027 | 2023-06-01 | Equipment | 12229003 | 5033124 | 5646787
MCR005734 | HPR027 | 2023-06-01 | Subcontract | 68532636 | 28206163 | 29746477
MCR005735 | HPR027 | 2023-06-01 | Overhead | 12144225 | 4998232 | 14266942
MCR005736 | HPR027 | 2023-07-01 | Labor | 35634150 | 25832109 | 29042907
MCR005737 | HPR027 | 2023-07-01 | Material | 69863954 | 50646172 | 44789218
MCR005738 | HPR027 | 2023-07-01 | Equipment | 15794234 | 11449645 | 11360796
MCR005739 | HPR027 | 2023-07-01 | Subcontract | 88512568 | 64165030 | 60298547
MCR005740 | HPR027 | 2023-07-01 | Overhead | 15684740 | 11370270 | 13765498
MCR005741 | HPR027 | 2023-08-01 | Labor | 42025097 | 22620708 | 23857275
MCR005742 | HPR027 | 2023-08-01 | Material | 82393981 | 44349932 | 38272992
MCR005743 | HPR027 | 2023-08-01 | Equipment | 18626913 | 10026246 | 10308966
MCR005744 | HPR027 | 2023-08-01 | Subcontract | 104387204 | 56188151 | 57775336
MCR005745 | HPR027 | 2023-08-01 | Overhead | 18497782 | 9956739 | 15409844
MCR005746 | HPR027 | 2023-09-01 | Labor | 46817378 | 27996619 | 26459009
MCR005747 | HPR027 | 2023-09-01 | Material | 91789679 | 54889889 | 50942131
MCR005748 | HPR027 | 2023-09-01 | Equipment | 20751011 | 12409028 | 12615374
MCR005749 | HPR027 | 2023-09-01 | Subcontract | 116290873 | 69541512 | 71140711
MCR005750 | HPR027 | 2023-09-01 | Overhead | 20607154 | 12323002 | 13553379
MCR005751 | HPR027 | 2023-10-01 | Labor | 50068893 | 58139000 | 54806780
MCR005752 | HPR027 | 2023-10-01 | Material | 98164567 | 113986737 | 97304084
MCR005753 | HPR027 | 2023-10-01 | Equipment | 22192190 | 25769128 | 22736374
MCR005754 | HPR027 | 2023-10-01 | Subcontract | 124367393 | 144412937 | 162302819
MCR005755 | HPR027 | 2023-10-01 | Overhead | 22038342 | 25590483 | 14378854
MCR005756 | HPR027 | 2023-11-01 | Labor | 51842017 | 49931808 | 57440414
MCR005757 | HPR027 | 2023-11-01 | Material | 101640936 | 97895799 | 97570156
MCR005758 | HPR027 | 2023-11-01 | Equipment | 22978097 | 22131429 | 28835582
MCR005759 | HPR027 | 2023-11-01 | Subcontract | 128771701 | 124026885 | 110680333
MCR005760 | HPR027 | 2023-11-01 | Overhead | 22818801 | 21978003 | 16258123
MCR005761 | HPR027 | 2023-12-01 | Labor | 52204444 | 70453836 | 78841183
MCR005762 | HPR027 | 2023-12-01 | Material | 102351505 | 138131079 | 137935879
MCR005763 | HPR027 | 2023-12-01 | Equipment | 23138736 | 31227470 | 28551548
MCR005764 | HPR027 | 2023-12-01 | Subcontract | 129671942 | 175002069 | 173310957
MCR005765 | HPR027 | 2023-12-01 | Overhead | 22978327 | 31010985 | 14758877
MCR005766 | HPR027 | 2024-01-01 | Labor | 51230289 | 48927021 | 48676348
MCR005767 | HPR027 | 2024-01-01 | Material | 100441588 | 95925823 | 90169981
MCR005768 | HPR027 | 2024-01-01 | Equipment | 22706959 | 21686074 | 24719093
MCR005769 | HPR027 | 2024-01-01 | Subcontract | 127252214 | 121531068 | 139821786
MCR005770 | HPR027 | 2024-01-01 | Overhead | 22549542 | 21535735 | 14100904
MCR005771 | HPR027 | 2024-02-01 | Labor | 49001581 | 46455255 | 63147975
MCR005772 | HPR027 | 2024-02-01 | Material | 96072004 | 91079704 | 90857971
MCR005773 | HPR027 | 2024-02-01 | Equipment | 21719121 | 20590506 | 21084054
MCR005774 | HPR027 | 2024-02-01 | Subcontract | 121716268 | 115391386 | 93890881
MCR005775 | HPR027 | 2024-02-01 | Overhead | 21568553 | 20447761 | 15611502
MCR005776 | HPR027 | 2024-03-01 | Labor | 45610323 | 32944762 | 30496491
MCR005777 | HPR027 | 2024-03-01 | Material | 89423139 | 64591168 | 53454461
MCR005778 | HPR027 | 2024-03-01 | Equipment | 20216004 | 14602208 | 16113176
MCR005779 | HPR027 | 2024-03-01 | Subcontract | 113292639 | 81832330 | 110375540
MCR005780 | HPR027 | 2024-03-01 | Overhead | 20075856 | 14500978 | 15046245
MCR005781 | HPR027 | 2024-04-01 | Labor | 41161492 | 41092160 | 48788381
MCR005782 | HPR027 | 2024-04-01 | Material | 80700805 | 80564873 | 81432747
MCR005783 | HPR027 | 2024-04-01 | Equipment | 18244135 | 18213404 | 15948099
MCR005784 | HPR027 | 2024-04-01 | Subcontract | 102242073 | 102069857 | 90486137
MCR005785 | HPR027 | 2024-04-01 | Overhead | 18117657 | 18087139 | 14619215
MCR005786 | HPR027 | 2024-05-01 | Labor | 35777564 | 52008558 | 55360769
MCR005787 | HPR027 | 2024-05-01 | Material | 70145131 | 101967454 | 96262893
MCR005788 | HPR027 | 2024-05-01 | Equipment | 15857800 | 23051913 | 25165314
MCR005789 | HPR027 | 2024-05-01 | Subcontract | 88868799 | 129185376 | 123282092
MCR005790 | HPR027 | 2024-05-01 | Overhead | 15747865 | 22892105 | 15382846
MCR005791 | HPR027 | 2024-06-01 | Labor | 29605870 | 29197577 | 31630986
MCR005792 | HPR027 | 2024-06-01 | Material | 58044970 | 57244475 | 61911931
MCR005793 | HPR027 | 2024-06-01 | Equipment | 13122301 | 12941332 | 11001441
MCR005794 | HPR027 | 2024-06-01 | Subcontract | 73538771 | 72524603 | 77342019
MCR005795 | HPR027 | 2024-06-01 | Overhead | 13031330 | 12851616 | 14424241
MCR005796 | HPR027 | 2024-07-01 | Labor | 22831571 | 22116770 | 30842089
MCR005797 | HPR027 | 2024-07-01 | Material | 44763348 | 43361917 | 40481677
MCR005798 | HPR027 | 2024-07-01 | Equipment | 10119708 | 9802884 | 12355024
MCR005799 | HPR027 | 2024-07-01 | Subcontract | 56711919 | 54936407 | 57138930
MCR005800 | HPR027 | 2024-07-01 | Overhead | 10049552 | 9734925 | 15025470
MCR005801 | HPR027 | 2024-08-01 | Labor | 15703774 | 14602475 | 12038476
MCR005802 | HPR027 | 2024-08-01 | Material | 30788661 | 28629466 | 22200940
MCR005803 | HPR027 | 2024-08-01 | Equipment | 6960432 | 6472300 | 5710570
MCR005804 | HPR027 | 2024-08-01 | Subcontract | 39007003 | 36271459 | 32772987
MCR005805 | HPR027 | 2024-08-01 | Overhead | 6912179 | 6427431 | 15691271
MCR005806 | HPR027 | 2024-09-01 | Labor | 8600628 | 16460526 | 19981118
MCR005807 | HPR027 | 2024-09-01 | Material | 16862304 | 32272341 | 36928405
MCR005808 | HPR027 | 2024-09-01 | Equipment | 3812083 | 7295850 | 7171841
MCR005809 | HPR027 | 2024-09-01 | Subcontract | 21363318 | 40886718 | 47686959
MCR005810 | HPR027 | 2024-09-01 | Overhead | 3785655 | 7245271 | 14301078
MCR005811 | HPR027 | 2024-10-01 | Labor | 2301447 | 19871699 | 22649784
MCR005812 | HPR027 | 2024-10-01 | Material | 4512194 | 38960252 | 35012317
MCR005813 | HPR027 | 2024-10-01 | Equipment | 1020077 | 8807794 | 9633372
MCR005814 | HPR027 | 2024-10-01 | Subcontract | 5716623 | 49359817 | 48161531
MCR005815 | HPR027 | 2024-10-01 | Overhead | 1013006 | 8746734 | 14313338
MCR005816 | HPR027 | 2024-11-01 | Labor | 0 | 11282774 | 13555893
MCR005817 | HPR027 | 2024-11-01 | Material | 0 | 22120893 | 22407057
MCR005818 | HPR027 | 2024-11-01 | Equipment | 0 | 5000899 | 4844234
MCR005819 | HPR027 | 2024-11-01 | Subcontract | 0 | 28025569 | 29280765
MCR005820 | HPR027 | 2024-11-01 | Overhead | 0 | 4966230 | 14605221
MCR005821 | HPR027 | 2024-12-01 | Labor | 0 | 9111114 | 9477898
MCR005822 | HPR027 | 2024-12-01 | Material | 0 | 17863159 | 17596925
MCR005823 | HPR027 | 2024-12-01 | Equipment | 0 | 4038347 | 4501489
MCR005824 | HPR027 | 2024-12-01 | Subcontract | 0 | 22631328 | 24414101
MCR005825 | HPR027 | 2024-12-01 | Overhead | 0 | 4010351 | 15423005
MCR005826 | HPR027 | 2025-01-01 | Labor | 0 | 3859447 | 5644762
MCR005827 | HPR027 | 2025-01-01 | Material | 0 | 7566792 | 6602482
MCR005828 | HPR027 | 2025-01-01 | Equipment | 0 | 1710634 | 1754013
MCR005829 | HPR027 | 2025-01-01 | Subcontract | 0 | 9586577 | 8922809
MCR005830 | HPR027 | 2025-01-01 | Overhead | 0 | 1698775 | 15373873
MCR005831 | HPR027 | 2025-02-01 | Labor | 0 | 2672167 | 3119555
MCR005832 | HPR027 | 2025-02-01 | Material | 0 | 5239024 | 5192901
MCR005833 | HPR027 | 2025-02-01 | Equipment | 0 | 1184393 | 1444998
MCR005834 | HPR027 | 2025-02-01 | Subcontract | 0 | 6637464 | 7220396
MCR005835 | HPR027 | 2025-02-01 | Overhead | 0 | 1176182 | 14637489
MCR005836 | HPR028 | 2023-05-01 | Labor | 16177114 | 14720036 | 16494179
MCR005837 | HPR028 | 2023-05-01 | Material | 27736870 | 25238603 | 24395981
MCR005838 | HPR028 | 2023-05-01 | Equipment | 6465366 | 5883028 | 5413798
MCR005839 | HPR028 | 2023-05-01 | Subcontract | 24716067 | 22489884 | 23375622
MCR005840 | HPR028 | 2023-05-01 | Overhead | 7278588 | 6623004 | 26439739
MCR005841 | HPR028 | 2023-06-01 | Labor | 44036397 | 44846842 | 46537062
MCR005842 | HPR028 | 2023-06-01 | Material | 75503694 | 76893263 | 72389643
MCR005843 | HPR028 | 2023-06-01 | Equipment | 17599642 | 17923546 | 18072405
MCR005844 | HPR028 | 2023-06-01 | Subcontract | 67280638 | 68518870 | 71405223
MCR005845 | HPR028 | 2023-06-01 | Overhead | 19813349 | 20177994 | 25359698
MCR005846 | HPR028 | 2023-07-01 | Labor | 65350663 | 27591136 | 29362969
MCR005847 | HPR028 | 2023-07-01 | Material | 112048596 | 47307065 | 54711391
MCR005848 | HPR028 | 2023-07-01 | Equipment | 26118129 | 11027109 | 12845512
MCR005849 | HPR028 | 2023-07-01 | Subcontract | 99845460 | 42154885 | 43076026
MCR005850 | HPR028 | 2023-07-01 | Overhead | 29403303 | 12414113 | 28311129
MCR005851 | HPR028 | 2023-08-01 | Labor | 80401756 | 28868870 | 33041762
MCR005852 | HPR028 | 2023-08-01 | Material | 137854821 | 49497836 | 56118220
MCR005853 | HPR028 | 2023-08-01 | Equipment | 32133468 | 11537769 | 9275109
MCR005854 | HPR028 | 2023-08-01 | Subcontract | 122841146 | 44107060 | 49092869
MCR005855 | HPR028 | 2023-08-01 | Overhead | 36175259 | 12989006 | 26679943
MCR005856 | HPR028 | 2023-09-01 | Labor | 89499161 | 109703367 | 119676110
MCR005857 | HPR028 | 2023-09-01 | Material | 153453002 | 188094623 | 193713687
MCR005858 | HPR028 | 2023-09-01 | Equipment | 35769349 | 43844187 | 44397191
MCR005859 | HPR028 | 2023-09-01 | Subcontract | 136740540 | 167609366 | 158093135
MCR005860 | HPR028 | 2023-09-01 | Overhead | 40268466 | 49358968 | 25215120
MCR005861 | HPR028 | 2023-10-01 | Labor | 92986894 | 73844173 | 82095285
MCR005862 | HPR028 | 2023-10-01 | Material | 159432981 | 126611354 | 140912105
MCR005863 | HPR028 | 2023-10-01 | Equipment | 37163260 | 29512656 | 28847286
MCR005864 | HPR028 | 2023-10-01 | Subcontract | 142069244 | 112822198 | 116418983
MCR005865 | HPR028 | 2023-10-01 | Overhead | 41837706 | 33224798 | 26128164
MCR005866 | HPR028 | 2023-11-01 | Labor | 91253370 | 93840698 | 89180890
MCR005867 | HPR028 | 2023-11-01 | Material | 156460724 | 160896892 | 135625300
MCR005868 | HPR028 | 2023-11-01 | Equipment | 36470438 | 37504493 | 35923975
MCR005869 | HPR028 | 2023-11-01 | Subcontract | 139420694 | 143373721 | 152095493
MCR005870 | HPR028 | 2023-11-01 | Overhead | 41057739 | 42221859 | 26435188
MCR005871 | HPR028 | 2023-12-01 | Labor | 84746236 | 49329584 | 59084036
MCR005872 | HPR028 | 2023-12-01 | Material | 145303756 | 84579259 | 99352483
MCR005873 | HPR028 | 2023-12-01 | Equipment | 33869789 | 19715124 | 24479246
MCR005874 | HPR028 | 2023-12-01 | Subcontract | 129478824 | 75367789 | 65088136
MCR005875 | HPR028 | 2023-12-01 | Overhead | 38129976 | 22194919 | 25767726
MCR005876 | HPR028 | 2024-01-01 | Labor | 73996115 | 86658511 | 97113708
MCR005877 | HPR028 | 2024-01-01 | Material | 126871871 | 148582495 | 157276663
MCR005878 | HPR028 | 2024-01-01 | Equipment | 29573382 | 34634051 | 34749674
MCR005879 | HPR028 | 2024-01-01 | Subcontract | 113054342 | 132400477 | 134140969
MCR005880 | HPR028 | 2024-01-01 | Overhead | 33293162 | 38990369 | 26979558
MCR005881 | HPR028 | 2024-02-01 | Labor | 59658076 | 67585850 | 68452821
MCR005882 | HPR028 | 2024-02-01 | Material | 102288231 | 115880991 | 106011811
MCR005883 | HPR028 | 2024-02-01 | Equipment | 23843023 | 27011447 | 29655801
MCR005884 | HPR028 | 2024-02-01 | Subcontract | 91148089 | 103260472 | 99501834
MCR005885 | HPR028 | 2024-02-01 | Overhead | 26842030 | 30408983 | 24828330
MCR005886 | HPR028 | 2024-03-01 | Labor | 42593904 | 72334779 | 73659196
MCR005887 | HPR028 | 2024-03-01 | Material | 73030432 | 124023386 | 128530181
MCR005888 | HPR028 | 2024-03-01 | Equipment | 17023134 | 28909410 | 26012016
MCR005889 | HPR028 | 2024-03-01 | Subcontract | 65076737 | 110516083 | 114414737
MCR005890 | HPR028 | 2024-03-01 | Overhead | 19164327 | 32545674 | 29073945
MCR005891 | HPR028 | 2024-04-01 | Labor | 24074026 | 38870636 | 49009202
MCR005892 | HPR028 | 2024-04-01 | Material | 41276718 | 66646611 | 71069753
MCR005893 | HPR028 | 2024-04-01 | Equipment | 9621456 | 15535088 | 16900908
MCR005894 | HPR028 | 2024-04-01 | Subcontract | 36781299 | 59388175 | 57438695
MCR005895 | HPR028 | 2024-04-01 | Overhead | 10831656 | 17489112 | 28522657
MCR005896 | HPR028 | 2024-05-01 | Labor | 6603586 | 40829003 | 42107688
MCR005897 | HPR028 | 2024-05-01 | Material | 11322341 | 70004377 | 71095132
MCR005898 | HPR028 | 2024-05-01 | Equipment | 2639197 | 16317771 | 17792492
MCR005899 | HPR028 | 2024-05-01 | Subcontract | 10089233 | 62380248 | 62224714
MCR005900 | HPR028 | 2024-05-01 | Overhead | 2971159 | 18370243 | 24020464
MCR005901 | HPR028 | 2024-06-01 | Labor | 0 | 18560806 | 19620241
MCR005902 | HPR028 | 2024-06-01 | Material | 0 | 31823889 | 31142189
MCR005903 | HPR028 | 2024-06-01 | Equipment | 0 | 7418035 | 6109507
MCR005904 | HPR028 | 2024-06-01 | Subcontract | 0 | 28357971 | 31625684
MCR005905 | HPR028 | 2024-06-01 | Overhead | 0 | 8351086 | 25984074
MCR005906 | HPR028 | 2024-07-01 | Labor | 0 | 3793007 | 4237116
MCR005907 | HPR028 | 2024-07-01 | Material | 0 | 6503394 | 8103583
MCR005908 | HPR028 | 2024-07-01 | Equipment | 0 | 1515918 | 1849334
MCR005909 | HPR028 | 2024-07-01 | Subcontract | 0 | 5795114 | 4385364
MCR005910 | HPR028 | 2024-07-01 | Overhead | 0 | 1706592 | 24658209
MCR005911 | HPR029 | 2017-06-01 | Labor | 16140417 | 12915189 | 11679273
MCR005912 | HPR029 | 2017-06-01 | Material | 46312249 | 37057992 | 38596299
MCR005913 | HPR029 | 2017-06-01 | Equipment | 14537723 | 11632750 | 11227778
MCR005914 | HPR029 | 2017-06-01 | Subcontract | 41979883 | 33591333 | 38451889
MCR005915 | HPR029 | 2017-06-01 | Overhead | 12050492 | 9642526 | 35026991
MCR005916 | HPR029 | 2017-07-01 | Labor | 43080914 | 53489452 | 57737075
MCR005917 | HPR029 | 2017-07-01 | Material | 123613537 | 153479108 | 160055139
MCR005918 | HPR029 | 2017-07-01 | Equipment | 38803112 | 48178113 | 50052964
MCR005919 | HPR029 | 2017-07-01 | Subcontract | 112049878 | 139121619 | 155925867
MCR005920 | HPR029 | 2017-07-01 | Overhead | 32164362 | 39935413 | 36929370
MCR005921 | HPR029 | 2017-08-01 | Labor | 62294756 | 47976849 | 42464256
MCR005922 | HPR029 | 2017-08-01 | Material | 178744468 | 137661610 | 123602925
MCR005923 | HPR029 | 2017-08-01 | Equipment | 56109078 | 43212895 | 43784321
MCR005924 | HPR029 | 2017-08-01 | Subcontract | 162023483 | 124783798 | 111459493
MCR005925 | HPR029 | 2017-08-01 | Overhead | 46509484 | 35819685 | 38391288
MCR005926 | HPR029 | 2017-09-01 | Labor | 74193534 | 96042938 | 88584693
MCR005927 | HPR029 | 2017-09-01 | Material | 212886037 | 275579279 | 245452026
MCR005928 | HPR029 | 2017-09-01 | Equipment | 66826343 | 86506169 | 94228865
MCR005929 | HPR029 | 2017-09-01 | Subcontract | 192971215 | 249799701 | 220235106
MCR005930 | HPR029 | 2017-09-01 | Overhead | 55393153 | 71705996 | 38496670
MCR005931 | HPR029 | 2017-10-01 | Labor | 79240009 | 75687999 | 65443462
MCR005932 | HPR029 | 2017-10-01 | Material | 227366061 | 217174157 | 264116647
MCR005933 | HPR029 | 2017-10-01 | Equipment | 71371719 | 68172413 | 59515975
MCR005934 | HPR029 | 2017-10-01 | Subcontract | 206096679 | 196858195 | 226061547
MCR005935 | HPR029 | 2017-10-01 | Overhead | 59160870 | 56508926 | 35631039
MCR005936 | HPR029 | 2017-11-01 | Labor | 77964836 | 84177191 | 81898479
MCR005937 | HPR029 | 2017-11-01 | Material | 223707163 | 241532486 | 223804563
MCR005938 | HPR029 | 2017-11-01 | Equipment | 70223167 | 75818654 | 78322358
MCR005939 | HPR029 | 2017-11-01 | Subcontract | 202780059 | 218937879 | 232671830
MCR005940 | HPR029 | 2017-11-01 | Overhead | 58208821 | 62846987 | 37680443
MCR005941 | HPR029 | 2017-12-01 | Labor | 70993195 | 76092911 | 83331291
MCR005942 | HPR029 | 2017-12-01 | Material | 203703195 | 218335984 | 231802412
MCR005943 | HPR029 | 2017-12-01 | Equipment | 63943788 | 68537118 | 76538723
MCR005944 | HPR029 | 2017-12-01 | Subcontract | 184647399 | 197911337 | 208514638
MCR005945 | HPR029 | 2017-12-01 | Overhead | 53003769 | 56811235 | 39949491
MCR005946 | HPR029 | 2018-01-01 | Labor | 59091023 | 48307352 | 43024269
MCR005947 | HPR029 | 2018-01-01 | Material | 169551889 | 138609933 | 135856972
MCR005948 | HPR029 | 2018-01-01 | Equipment | 53223466 | 43510580 | 37108830
MCR005949 | HPR029 | 2018-01-01 | Subcontract | 153690841 | 125643408 | 113060881
MCR005950 | HPR029 | 2018-01-01 | Overhead | 44117566 | 36066439 | 37243167
MCR005951 | HPR029 | 2018-02-01 | Labor | 43256117 | 32297771 | 32840365
MCR005952 | HPR029 | 2018-02-01 | Material | 124116252 | 92673095 | 103005065
MCR005953 | HPR029 | 2018-02-01 | Equipment | 38960917 | 29090701 | 28963525
MCR005954 | HPR029 | 2018-02-01 | Subcontract | 112505565 | 84003817 | 92024384
MCR005955 | HPR029 | 2018-02-01 | Overhead | 32295169 | 24113629 | 36563924
MCR005956 | HPR029 | 2018-03-01 | Labor | 24939890 | 24540751 | 25237045
MCR005957 | HPR029 | 2018-03-01 | Material | 71560877 | 70415613 | 66542807
MCR005958 | HPR029 | 2018-03-01 | Equipment | 22463435 | 22103929 | 25833684
MCR005959 | HPR029 | 2018-03-01 | Subcontract | 64866581 | 63828453 | 57692866
MCR005960 | HPR029 | 2018-03-01 | Overhead | 18620210 | 18322211 | 40585027
MCR005961 | HPR029 | 2018-04-01 | Labor | 6944251 | 6610539 | 5088546
MCR005962 | HPR029 | 2018-04-01 | Material | 19925375 | 18967845 | 18786323
MCR005963 | HPR029 | 2018-04-01 | Equipment | 6254708 | 5954133 | 4517166
MCR005964 | HPR029 | 2018-04-01 | Subcontract | 18061419 | 17193462 | 18089738
MCR005965 | HPR029 | 2018-04-01 | Overhead | 5184602 | 4935452 | 37780417
MCR005966 | HPR030 | 2019-10-01 | Labor | 5634739 | 3062614 | 3429073
MCR005967 | HPR030 | 2019-10-01 | Material | 11655224 | 6334890 | 6683842
MCR005968 | HPR030 | 2019-10-01 | Equipment | 2806550 | 1525427 | 1404355
MCR005969 | HPR030 | 2019-10-01 | Subcontract | 16912168 | 9192164 | 9632250
MCR005970 | HPR030 | 2019-10-01 | Overhead | 3969023 | 2157258 | 16973007
MCR005971 | HPR030 | 2019-11-01 | Labor | 15554790 | 9648321 | 10053350
MCR005972 | HPR030 | 2019-11-01 | Material | 32174437 | 19957150 | 19143801
MCR005973 | HPR030 | 2019-11-01 | Equipment | 7747528 | 4805634 | 4978396
MCR005974 | HPR030 | 2019-11-01 | Subcontract | 46686314 | 28958573 | 29114486
MCR005975 | HPR030 | 2019-11-01 | Overhead | 10956551 | 6796126 | 16809137
MCR005976 | HPR030 | 2019-12-01 | Labor | 23501190 | 11071456 | 12949018
MCR005977 | HPR030 | 2019-12-01 | Material | 48611234 | 22900847 | 20555184
MCR005978 | HPR030 | 2019-12-01 | Equipment | 11705469 | 5514469 | 6395164
MCR005979 | HPR030 | 2019-12-01 | Subcontract | 70536724 | 33229988 | 36468828
MCR005980 | HPR030 | 2019-12-01 | Overhead | 16553872 | 7798561 | 18853215
MCR005981 | HPR030 | 2020-01-01 | Labor | 29545268 | 18767882 | 21093205
MCR005982 | HPR030 | 2020-01-01 | Material | 61113158 | 38820583 | 42127952
MCR005983 | HPR030 | 2020-01-01 | Equipment | 14715903 | 9347904 | 10106999
MCR005984 | HPR030 | 2020-01-01 | Subcontract | 88677484 | 56330122 | 59899144
MCR005985 | HPR030 | 2020-01-01 | Overhead | 20811226 | 13219803 | 14929299
MCR005986 | HPR030 | 2020-02-01 | Labor | 33764129 | 18145995 | 19413527
MCR005987 | HPR030 | 2020-02-01 | Material | 69839697 | 37534235 | 36649484
MCR005988 | HPR030 | 2020-02-01 | Equipment | 16817233 | 9038154 | 8720386
MCR005989 | HPR030 | 2020-02-01 | Subcontract | 101340020 | 54463583 | 55323709
MCR005990 | HPR030 | 2020-02-01 | Overhead | 23782926 | 12781755 | 18253854
MCR005991 | HPR030 | 2020-03-01 | Labor | 36241823 | 16289813 | 19851995
MCR005992 | HPR030 | 2020-03-01 | Material | 74964703 | 33694800 | 31124431
MCR005993 | HPR030 | 2020-03-01 | Equipment | 18051322 | 8113628 | 10254258
MCR005994 | HPR030 | 2020-03-01 | Subcontract | 108776596 | 48892418 | 48422732
MCR005995 | HPR030 | 2020-03-01 | Overhead | 25528174 | 11474290 | 17838407
MCR005996 | HPR030 | 2020-04-01 | Labor | 37070900 | 35181958 | 41577517
MCR005997 | HPR030 | 2020-04-01 | Material | 76679615 | 72772418 | 82087991
MCR005998 | HPR030 | 2020-04-01 | Equipment | 18464269 | 17523425 | 17312163
MCR005999 | HPR030 | 2020-04-01 | Subcontract | 111264998 | 105595508 | 103036482
MCR006000 | HPR030 | 2020-04-01 | Overhead | 26112163 | 24781622 | 16828942
MCR006001 | HPR030 | 2020-05-01 | Labor | 36354578 | 40529749 | 43408829
MCR006002 | HPR030 | 2020-05-01 | Material | 75197932 | 83834100 | 91802381
MCR006003 | HPR030 | 2020-05-01 | Equipment | 18107483 | 20187052 | 18770087
MCR006004 | HPR030 | 2020-05-01 | Subcontract | 109115019 | 121646424 | 137791496
MCR006005 | HPR030 | 2020-05-01 | Overhead | 25607597 | 28548523 | 16528621
MCR006006 | HPR030 | 2020-06-01 | Labor | 34209838 | 39812577 | 49054277
MCR006007 | HPR030 | 2020-06-01 | Material | 70761627 | 82350659 | 80516593
MCR006008 | HPR030 | 2020-06-01 | Equipment | 17039231 | 19829843 | 22972800
MCR006009 | HPR030 | 2020-06-01 | Subcontract | 102677775 | 119493895 | 102903894
MCR006010 | HPR030 | 2020-06-01 | Overhead | 24096876 | 28043358 | 17907661
MCR006011 | HPR030 | 2020-07-01 | Labor | 30772114 | 21682809 | 23247868
MCR006012 | HPR030 | 2020-07-01 | Material | 63650838 | 44849989 | 39992968
MCR006013 | HPR030 | 2020-07-01 | Equipment | 15326970 | 10799770 | 10356338
MCR006014 | HPR030 | 2020-07-01 | Subcontract | 92359753 | 65079016 | 73400765
MCR006015 | HPR030 | 2020-07-01 | Overhead | 21675397 | 15273032 | 16156608
MCR006016 | HPR030 | 2020-08-01 | Labor | 26202818 | 26650661 | 26794326
MCR006017 | HPR030 | 2020-08-01 | Material | 54199439 | 55125784 | 58271972
MCR006018 | HPR030 | 2020-08-01 | Equipment | 13051096 | 13274158 | 12739723
MCR006019 | HPR030 | 2020-08-01 | Subcontract | 78645418 | 79989580 | 87681722
MCR006020 | HPR030 | 2020-08-01 | Overhead | 18456856 | 18772310 | 16388369
MCR006021 | HPR030 | 2020-09-01 | Labor | 20702554 | 14121510 | 16007607
MCR006022 | HPR030 | 2020-09-01 | Material | 42822371 | 29209755 | 28748445
MCR006023 | HPR030 | 2020-09-01 | Equipment | 10311525 | 7033640 | 8937348
MCR006024 | HPR030 | 2020-09-01 | Subcontract | 62136867 | 42384451 | 40057288
MCR006025 | HPR030 | 2020-09-01 | Overhead | 14582556 | 9946971 | 16271228
MCR006026 | HPR030 | 2020-10-01 | Labor | 14537479 | 18452914 | 22343401
MCR006027 | HPR030 | 2020-10-01 | Material | 30070170 | 38169085 | 37801966
MCR006028 | HPR030 | 2020-10-01 | Equipment | 7240825 | 9191025 | 8523888
MCR006029 | HPR030 | 2020-10-01 | Subcontract | 43632944 | 55384773 | 50355838
MCR006030 | HPR030 | 2020-10-01 | Overhead | 10239973 | 12997944 | 17406796
MCR006031 | HPR030 | 2020-11-01 | Labor | 8104407 | 21009111 | 24020133
MCR006032 | HPR030 | 2020-11-01 | Material | 16763628 | 43456472 | 41700939
MCR006033 | HPR030 | 2020-11-01 | Equipment | 4036642 | 10464215 | 11636790
MCR006034 | HPR030 | 2020-11-01 | Subcontract | 24324654 | 63056970 | 74759169
MCR006035 | HPR030 | 2020-11-01 | Overhead | 5708618 | 14798490 | 14767238
MCR006036 | HPR030 | 2020-12-01 | Labor | 2199530 | 19318340 | 21626113
MCR006037 | HPR030 | 2020-12-01 | Material | 4549636 | 39959183 | 36592030
MCR006038 | HPR030 | 2020-12-01 | Equipment | 1095541 | 9622076 | 10006711
MCR006039 | HPR030 | 2020-12-01 | Subcontract | 6601692 | 57982273 | 76592995
MCR006040 | HPR030 | 2020-12-01 | Overhead | 1549314 | 13607537 | 15649664
MCR006041 | HPR030 | 2021-01-01 | Labor | 0 | 14775989 | 17547379
MCR006042 | HPR030 | 2021-01-01 | Material | 0 | 30563518 | 37625805
MCR006043 | HPR030 | 2021-01-01 | Equipment | 0 | 7359622 | 7756687
MCR006044 | HPR030 | 2021-01-01 | Subcontract | 0 | 44348811 | 75170673
MCR006045 | HPR030 | 2021-01-01 | Overhead | 0 | 10407976 | 16752157
MCR006046 | HPR030 | 2021-02-01 | Labor | 0 | 12154572 | 13605538
MCR006047 | HPR030 | 2021-02-01 | Material | 0 | 25141226 | 24502772
MCR006048 | HPR030 | 2021-02-01 | Equipment | 0 | 6053947 | 6438615
MCR006049 | HPR030 | 2021-02-01 | Subcontract | 0 | 36480861 | 55866516
MCR006050 | HPR030 | 2021-02-01 | Overhead | 0 | 8561490 | 16275273
MCR006051 | HPR030 | 2021-03-01 | Labor | 0 | 6490486 | 8113922
MCR006052 | HPR030 | 2021-03-01 | Material | 0 | 13425301 | 14016318
MCR006053 | HPR030 | 2021-03-01 | Equipment | 0 | 3232781 | 3965145
MCR006054 | HPR030 | 2021-03-01 | Subcontract | 0 | 19480616 | 35319289
MCR006055 | HPR030 | 2021-03-01 | Overhead | 0 | 4571797 | 15492258
MCR006056 | HPR030 | 2021-04-01 | Labor | 0 | 5770435 | 6221290
MCR006057 | HPR030 | 2021-04-01 | Material | 0 | 11935904 | 13079815
MCR006058 | HPR030 | 2021-04-01 | Equipment | 0 | 2874137 | 2817129
MCR006059 | HPR030 | 2021-04-01 | Subcontract | 0 | 17319445 | 46530220
MCR006060 | HPR030 | 2021-04-01 | Overhead | 0 | 4064604 | 16876841
MCR006061 | HPR030 | 2021-05-01 | Labor | 0 | 1458967 | 1955772
MCR006062 | HPR030 | 2021-05-01 | Material | 0 | 3017812 | 2172020
MCR006063 | HPR030 | 2021-05-01 | Equipment | 0 | 726682 | 1268169
MCR006064 | HPR030 | 2021-05-01 | Subcontract | 0 | 4378958 | 23682258
MCR006065 | HPR030 | 2021-05-01 | Overhead | 0 | 1027673 | 16029097
MCR006066 | HPR031 | 2017-07-01 | Labor | 5715351 | 3027894 | 3301102
MCR006067 | HPR031 | 2017-07-01 | Material | 27487738 | 14562528 | 14012602
MCR006068 | HPR031 | 2017-07-01 | Equipment | 13215836 | 7001522 | 8689293
MCR006069 | HPR031 | 2017-07-01 | Subcontract | 12003368 | 6359177 | 6814652
MCR006070 | HPR031 | 2017-07-01 | Overhead | 5981268 | 3168773 | 25488368
MCR006071 | HPR031 | 2017-08-01 | Labor | 15675787 | 6512493 | 6900995
MCR006072 | HPR031 | 2017-08-01 | Material | 75392041 | 31321561 | 26763467
MCR006073 | HPR031 | 2017-08-01 | Equipment | 36247757 | 15059101 | 14023116
MCR006074 | HPR031 | 2017-08-01 | Subcontract | 32922258 | 13677525 | 13156800
MCR006075 | HPR031 | 2017-08-01 | Overhead | 16405134 | 6815499 | 22951691
MCR006076 | HPR031 | 2017-09-01 | Labor | 23490236 | 11255100 | 11612053
MCR006077 | HPR031 | 2017-09-01 | Material | 112975302 | 54130928 | 55381646
MCR006078 | HPR031 | 2017-09-01 | Equipment | 54317423 | 26025622 | 27993309
MCR006079 | HPR031 | 2017-09-01 | Subcontract | 49334147 | 23637938 | 23243989
MCR006080 | HPR031 | 2017-09-01 | Overhead | 24583165 | 11778765 | 22019521
MCR006081 | HPR031 | 2017-10-01 | Labor | 29243031 | 23830082 | 26304487
MCR006082 | HPR031 | 2017-10-01 | Material | 140643128 | 114609777 | 100357296
MCR006083 | HPR031 | 2017-10-01 | Equipment | 67619843 | 55103262 | 45592463
MCR006084 | HPR031 | 2017-10-01 | Subcontract | 61416156 | 50047891 | 52127414
MCR006085 | HPR031 | 2017-10-01 | Overhead | 30603620 | 24938823 | 21877130
MCR006086 | HPR031 | 2017-11-01 | Labor | 33025989 | 13292207 | 13008818
MCR006087 | HPR031 | 2017-11-01 | Material | 158837103 | 63928309 | 72983852
MCR006088 | HPR031 | 2017-11-01 | Equipment | 76367330 | 30736107 | 39810079
MCR006089 | HPR031 | 2017-11-01 | Subcontract | 69361116 | 27916266 | 25976044
MCR006090 | HPR031 | 2017-11-01 | Overhead | 34562587 | 13910653 | 26284498
MCR006091 | HPR031 | 2017-12-01 | Labor | 34940075 | 19154430 | 20810496
MCR006092 | HPR031 | 2017-12-01 | Material | 168042822 | 92122424 | 86864930
MCR006093 | HPR031 | 2017-12-01 | Equipment | 80793349 | 44291562 | 47917423
MCR006094 | HPR031 | 2017-12-01 | Subcontract | 73381077 | 40228095 | 44327732
MCR006095 | HPR031 | 2017-12-01 | Overhead | 36565730 | 20045627 | 23007192
MCR006096 | HPR031 | 2018-01-01 | Labor | 35097710 | 24186090 | 24386323
MCR006097 | HPR031 | 2018-01-01 | Material | 168800961 | 116321983 | 131324502
MCR006098 | HPR031 | 2018-01-01 | Equipment | 81157855 | 55926475 | 46982733
MCR006099 | HPR031 | 2018-01-01 | Subcontract | 73712142 | 50795579 | 45576160
MCR006100 | HPR031 | 2018-01-01 | Overhead | 36730700 | 25311395 | 23728253
MCR006101 | HPR031 | 2018-02-01 | Labor | 33626070 | 33225113 | 34836754
MCR006102 | HPR031 | 2018-02-01 | Material | 161723172 | 159794786 | 160785913
MCR006103 | HPR031 | 2018-02-01 | Equipment | 77754923 | 76827774 | 86485557
MCR006104 | HPR031 | 2018-02-01 | Subcontract | 70621407 | 69779318 | 71294678
MCR006105 | HPR031 | 2018-02-01 | Overhead | 35190589 | 34770977 | 23940101
MCR006106 | HPR031 | 2018-03-01 | Labor | 30672067 | 18763051 | 20807885
MCR006107 | HPR031 | 2018-03-01 | Material | 147516016 | 90240106 | 92393736
MCR006108 | HPR031 | 2018-03-01 | Equipment | 70924261 | 43386562 | 47314009
MCR006109 | HPR031 | 2018-03-01 | Subcontract | 64417415 | 39406123 | 38663067
MCR006110 | HPR031 | 2018-03-01 | Overhead | 32099145 | 19636039 | 24529647
MCR006111 | HPR031 | 2018-04-01 | Labor | 26410330 | 29145252 | 34335241
MCR006112 | HPR031 | 2018-04-01 | Material | 127019372 | 140172862 | 145843896
MCR006113 | HPR031 | 2018-04-01 | Equipment | 61069675 | 67393744 | 74019514
MCR006114 | HPR031 | 2018-04-01 | Subcontract | 55466923 | 61210800 | 50100370
MCR006115 | HPR031 | 2018-04-01 | Overhead | 27639122 | 30501291 | 20975890
MCR006116 | HPR031 | 2018-05-01 | Labor | 21057190 | 13753551 | 10858233
MCR006117 | HPR031 | 2018-05-01 | Material | 101273671 | 66147124 | 67489049
MCR006118 | HPR031 | 2018-05-01 | Equipment | 48691393 | 31802892 | 33948255
MCR006119 | HPR031 | 2018-05-01 | Subcontract | 44224270 | 28885180 | 37049251
MCR006120 | HPR031 | 2018-05-01 | Overhead | 22036917 | 14393462 | 25061235
MCR006121 | HPR031 | 2018-06-01 | Labor | 14898497 | 17766972 | 19437873
MCR006122 | HPR031 | 2018-06-01 | Material | 71653695 | 85449504 | 80671789
MCR006123 | HPR031 | 2018-06-01 | Equipment | 34450397 | 41083288 | 46291983
MCR006124 | HPR031 | 2018-06-01 | Subcontract | 31289794 | 37314159 | 38479704
MCR006125 | HPR031 | 2018-06-01 | Overhead | 15591679 | 18593615 | 22746667
MCR006126 | HPR031 | 2018-07-01 | Labor | 8358125 | 15947618 | 16030976
MCR006127 | HPR031 | 2018-07-01 | Material | 40198050 | 76699398 | 83767360
MCR006128 | HPR031 | 2018-07-01 | Equipment | 19326830 | 36876322 | 36630345
MCR006129 | HPR031 | 2018-07-01 | Subcontract | 17553717 | 33493156 | 29383790
MCR006130 | HPR031 | 2018-07-01 | Overhead | 8747003 | 16689612 | 25139832
MCR006131 | HPR031 | 2018-08-01 | Labor | 2279549 | 17461161 | 21478322
MCR006132 | HPR031 | 2018-08-01 | Material | 10963393 | 83978720 | 90696733
MCR006133 | HPR031 | 2018-08-01 | Equipment | 5271092 | 40376149 | 38868944
MCR006134 | HPR031 | 2018-08-01 | Subcontract | 4787503 | 36671896 | 40677292
MCR006135 | HPR031 | 2018-08-01 | Overhead | 2385609 | 18273576 | 23544205
MCR006136 | HPR031 | 2018-09-01 | Labor | 0 | 32127504 | 33189581
MCR006137 | HPR031 | 2018-09-01 | Material | 0 | 154515882 | 167625008
MCR006138 | HPR031 | 2018-09-01 | Equipment | 0 | 74289729 | 81398068
MCR006139 | HPR031 | 2018-09-01 | Subcontract | 0 | 67474122 | 80912450
MCR006140 | HPR031 | 2018-09-01 | Overhead | 0 | 33622300 | 23192707
MCR006141 | HPR031 | 2018-10-01 | Labor | 0 | 12342677 | 13137314
MCR006142 | HPR031 | 2018-10-01 | Material | 0 | 59361588 | 56216212
MCR006143 | HPR031 | 2018-10-01 | Equipment | 0 | 28540473 | 26184958
MCR006144 | HPR031 | 2018-10-01 | Subcontract | 0 | 25922067 | 45579236
MCR006145 | HPR031 | 2018-10-01 | Overhead | 0 | 12916945 | 23882083
MCR006146 | HPR031 | 2018-11-01 | Labor | 0 | 10696451 | 11167509
MCR006147 | HPR031 | 2018-11-01 | Material | 0 | 51444131 | 55401234
MCR006148 | HPR031 | 2018-11-01 | Equipment | 0 | 24733836 | 34858830
MCR006149 | HPR031 | 2018-11-01 | Subcontract | 0 | 22464665 | 29436025
MCR006150 | HPR031 | 2018-11-01 | Overhead | 0 | 11194124 | 23818455
MCR006151 | HPR031 | 2018-12-01 | Labor | 0 | 7996991 | 8837012
MCR006152 | HPR031 | 2018-12-01 | Material | 0 | 38461192 | 39140611
MCR006153 | HPR031 | 2018-12-01 | Equipment | 0 | 18491766 | 19157429
MCR006154 | HPR031 | 2018-12-01 | Subcontract | 0 | 16795265 | 26262544
MCR006155 | HPR031 | 2018-12-01 | Overhead | 0 | 8369067 | 23792848
MCR006156 | HPR031 | 2019-01-01 | Labor | 0 | 3098735 | 3833652
MCR006157 | HPR031 | 2019-01-01 | Material | 0 | 14903238 | 16149501
MCR006158 | HPR031 | 2019-01-01 | Equipment | 0 | 7165331 | 9063620
MCR006159 | HPR031 | 2019-01-01 | Subcontract | 0 | 6507958 | 17638437
MCR006160 | HPR031 | 2019-01-01 | Overhead | 0 | 3242910 | 23493946
MCR006161 | HPR031 | 2019-02-01 | Labor | 0 | 906635 | 1113319
MCR006162 | HPR031 | 2019-02-01 | Material | 0 | 4360422 | 4750031
MCR006163 | HPR031 | 2019-02-01 | Equipment | 0 | 2096448 | 2031069
MCR006164 | HPR031 | 2019-02-01 | Subcontract | 0 | 1904112 | 9046567
MCR006165 | HPR031 | 2019-02-01 | Overhead | 0 | 948818 | 22217074
MCR006166 | HPR032 | 2018-07-01 | Labor | 2764480 | 853593 | 948434
MCR006167 | HPR032 | 2018-07-01 | Material | 12476179 | 3852290 | 3911325
MCR006168 | HPR032 | 2018-07-01 | Equipment | 5996009 | 1851397 | 2138632
MCR006169 | HPR032 | 2018-07-01 | Subcontract | 5625767 | 1737077 | 1586525
MCR006170 | HPR032 | 2018-07-01 | Overhead | 2782326 | 859103 | 14946256
MCR006171 | HPR032 | 2018-08-01 | Labor | 7774696 | 3062021 | 3146825
MCR006172 | HPR032 | 2018-08-01 | Material | 35087433 | 13818991 | 12997330
MCR006173 | HPR032 | 2018-08-01 | Equipment | 16862902 | 6641360 | 7350709
MCR006174 | HPR032 | 2018-08-01 | Subcontract | 15821648 | 6231268 | 6815570
MCR006175 | HPR032 | 2018-08-01 | Overhead | 7824885 | 3081788 | 13444135
MCR006176 | HPR032 | 2018-09-01 | Labor | 12021776 | 7076984 | 8152439
MCR006177 | HPR032 | 2018-09-01 | Material | 54254632 | 31938637 | 35353518
MCR006178 | HPR032 | 2018-09-01 | Equipment | 26074592 | 15349601 | 16142453
MCR006179 | HPR032 | 2018-09-01 | Subcontract | 24464534 | 14401791 | 13683166
MCR006180 | HPR032 | 2018-09-01 | Overhead | 12099382 | 7122669 | 14959696
MCR006181 | HPR032 | 2018-10-01 | Labor | 15526592 | 6731027 | 6446062
MCR006182 | HPR032 | 2018-10-01 | Material | 70071970 | 30377324 | 29617749
MCR006183 | HPR032 | 2018-10-01 | Equipment | 33676352 | 14599239 | 15611268
MCR006184 | HPR032 | 2018-10-01 | Subcontract | 31596898 | 13697762 | 14748303
MCR006185 | HPR032 | 2018-10-01 | Overhead | 15626823 | 6774479 | 15209190
MCR006186 | HPR032 | 2018-11-01 | Labor | 18311270 | 11156575 | 13960044
MCR006187 | HPR032 | 2018-11-01 | Material | 82639304 | 50349952 | 51913018
MCR006188 | HPR032 | 2018-11-01 | Equipment | 39716170 | 24198017 | 26233069
MCR006189 | HPR032 | 2018-11-01 | Subcontract | 37263768 | 22703833 | 23842103
MCR006190 | HPR032 | 2018-11-01 | Overhead | 18429477 | 11228595 | 15290588
MCR006191 | HPR032 | 2018-12-01 | Labor | 20399374 | 17683440 | 19940492
MCR006192 | HPR032 | 2018-12-01 | Material | 92062978 | 79805889 | 80864380
MCR006193 | HPR032 | 2018-12-01 | Equipment | 44245156 | 38354440 | 39427224
MCR006194 | HPR032 | 2018-12-01 | Subcontract | 41513097 | 35986123 | 33537541
MCR006195 | HPR032 | 2018-12-01 | Overhead | 20531061 | 17797595 | 14564197
MCR006196 | HPR032 | 2019-01-01 | Labor | 21816132 | 12393078 | 14176337
MCR006197 | HPR032 | 2019-01-01 | Material | 98456846 | 55930329 | 52271128
MCR006198 | HPR032 | 2019-01-01 | Equipment | 47318027 | 26879927 | 28949165
MCR006199 | HPR032 | 2019-01-01 | Subcontract | 44396224 | 25220140 | 27960158
MCR006200 | HPR032 | 2019-01-01 | Overhead | 21956964 | 12473081 | 15003958
MCR006201 | HPR032 | 2019-02-01 | Labor | 22588721 | 19391443 | 21969551
MCR006202 | HPR032 | 2019-02-01 | Material | 101943566 | 87514156 | 101124731
MCR006203 | HPR032 | 2019-02-01 | Equipment | 48993733 | 42059007 | 47610844
MCR006204 | HPR032 | 2019-02-01 | Subcontract | 45968458 | 39461939 | 37560808
MCR006205 | HPR032 | 2019-02-01 | Overhead | 22734541 | 19516623 | 14414627
MCR006206 | HPR032 | 2019-03-01 | Labor | 22746639 | 16067677 | 18724827
MCR006207 | HPR032 | 2019-03-01 | Material | 102656251 | 72513900 | 68656335
MCR006208 | HPR032 | 2019-03-01 | Equipment | 49336247 | 34849935 | 29372265
MCR006209 | HPR032 | 2019-03-01 | Subcontract | 46289823 | 32698014 | 31023238
MCR006210 | HPR032 | 2019-03-01 | Overhead | 22893478 | 16171401 | 12742332
MCR006211 | HPR032 | 2019-04-01 | Labor | 22322178 | 18620606 | 21363196
MCR006212 | HPR032 | 2019-04-01 | Material | 100740647 | 84035346 | 96037449
MCR006213 | HPR032 | 2019-04-01 | Equipment | 48415614 | 40387103 | 45189959
MCR006214 | HPR032 | 2019-04-01 | Subcontract | 45426037 | 37893272 | 39338059
MCR006215 | HPR032 | 2019-04-01 | Overhead | 22466277 | 18740810 | 15297837
MCR006216 | HPR032 | 2019-05-01 | Labor | 21351080 | 17135715 | 17164289
MCR006217 | HPR032 | 2019-05-01 | Material | 96358053 | 77333988 | 87784449
MCR006218 | HPR032 | 2019-05-01 | Equipment | 46309354 | 37166453 | 39977217
MCR006219 | HPR032 | 2019-05-01 | Subcontract | 43449835 | 34871492 | 27609109
MCR006220 | HPR032 | 2019-05-01 | Overhead | 21488910 | 17246333 | 13816505
MCR006221 | HPR032 | 2019-06-01 | Labor | 19873433 | 14498607 | 17275248
MCR006222 | HPR032 | 2019-06-01 | Material | 89689392 | 65432642 | 55664399
MCR006223 | HPR032 | 2019-06-01 | Equipment | 43104418 | 31446706 | 29030467
MCR006224 | HPR032 | 2019-06-01 | Subcontract | 40442798 | 29504929 | 33145986
MCR006225 | HPR032 | 2019-06-01 | Overhead | 20001725 | 14592202 | 13669438
MCR006226 | HPR032 | 2019-07-01 | Labor | 17934978 | 12051952 | 12455232
MCR006227 | HPR032 | 2019-07-01 | Material | 80941087 | 54390817 | 62154841
MCR006228 | HPR032 | 2019-07-01 | Equipment | 38900013 | 26140043 | 30177010
MCR006229 | HPR032 | 2019-07-01 | Subcontract | 36498007 | 24525942 | 26759643
MCR006230 | HPR032 | 2019-07-01 | Overhead | 18050756 | 12129753 | 14126823
MCR006231 | HPR032 | 2019-08-01 | Labor | 15589081 | 15047881 | 17149274
MCR006232 | HPR032 | 2019-08-01 | Material | 70353984 | 67911532 | 61816717
MCR006233 | HPR032 | 2019-08-01 | Equipment | 33811887 | 32638053 | 30577192
MCR006234 | HPR032 | 2019-08-01 | Subcontract | 31724064 | 30622712 | 27428120
MCR006235 | HPR032 | 2019-08-01 | Overhead | 15689715 | 15145022 | 14781433
MCR006236 | HPR032 | 2019-09-01 | Labor | 12899937 | 19843225 | 23968215
MCR006237 | HPR032 | 2019-09-01 | Material | 58217795 | 89553059 | 89770539
MCR006238 | HPR032 | 2019-09-01 | Equipment | 27979275 | 43038897 | 49210279
MCR006239 | HPR032 | 2019-09-01 | Subcontract | 26251606 | 40381323 | 38866650
MCR006240 | HPR032 | 2019-09-01 | Overhead | 12983211 | 19971321 | 15183098
MCR006241 | HPR032 | 2019-10-01 | Labor | 9948224 | 13310339 | 14074410
MCR006242 | HPR032 | 2019-10-01 | Material | 44896628 | 60069954 | 63551300
MCR006243 | HPR032 | 2019-10-01 | Equipment | 21577168 | 28869417 | 26869471
MCR006244 | HPR032 | 2019-10-01 | Subcontract | 20244817 | 27086782 | 26578463
MCR006245 | HPR032 | 2019-10-01 | Overhead | 10012444 | 13396263 | 14572347
MCR006246 | HPR032 | 2019-11-01 | Labor | 6842484 | 7711256 | 8024909
MCR006247 | HPR032 | 2019-11-01 | Material | 30880333 | 34801124 | 38569792
MCR006248 | HPR032 | 2019-11-01 | Equipment | 14840983 | 16725303 | 17919155
MCR006249 | HPR032 | 2019-11-01 | Subcontract | 13924580 | 15692545 | 15667927
MCR006250 | HPR032 | 2019-11-01 | Overhead | 6886655 | 7761035 | 14841690
MCR006251 | HPR032 | 2019-12-01 | Labor | 3747485 | 14977108 | 30438992
MCR006252 | HPR032 | 2019-12-01 | Material | 16912511 | 67592130 | 96284236
MCR006253 | HPR032 | 2019-12-01 | Equipment | 8128095 | 32484549 | 36691837
MCR006254 | HPR032 | 2019-12-01 | Subcontract | 7626200 | 30478687 | 45579648
MCR006255 | HPR032 | 2019-12-01 | Overhead | 3771677 | 15073791 | 14742536
MCR006256 | HPR032 | 2020-01-01 | Labor | 1002792 | 9353226 | 23748832
MCR006257 | HPR032 | 2020-01-01 | Material | 4525629 | 42211385 | 49716381
MCR006258 | HPR032 | 2020-01-01 | Equipment | 2175002 | 20286649 | 18887264
MCR006259 | HPR032 | 2020-01-01 | Subcontract | 2040699 | 19033985 | 33686984
MCR006260 | HPR032 | 2020-01-01 | Overhead | 1009265 | 9413605 | 14059607
MCR006261 | HPR032 | 2020-02-01 | Labor | 0 | 12074287 | 12525584
MCR006262 | HPR032 | 2020-02-01 | Material | 0 | 54491612 | 61687052
MCR006263 | HPR032 | 2020-02-01 | Equipment | 0 | 26188485 | 26885923
MCR006264 | HPR032 | 2020-02-01 | Subcontract | 0 | 24571393 | 41684353
MCR006265 | HPR032 | 2020-02-01 | Overhead | 0 | 12152231 | 14918595
MCR006266 | HPR032 | 2020-03-01 | Labor | 0 | 10033173 | 13539670
MCR006267 | HPR032 | 2020-03-01 | Material | 0 | 45280005 | 48868126
MCR006268 | HPR032 | 2020-03-01 | Equipment | 0 | 21761417 | 24309102
MCR006269 | HPR032 | 2020-03-01 | Subcontract | 0 | 20417689 | 38839478
MCR006270 | HPR032 | 2020-03-01 | Overhead | 0 | 10097941 | 14381891
MCR006271 | HPR032 | 2020-04-01 | Labor | 0 | 5147833 | 5272747
MCR006272 | HPR032 | 2020-04-01 | Material | 0 | 23232324 | 22793670
MCR006273 | HPR032 | 2020-04-01 | Equipment | 0 | 11165376 | 13398272
MCR006274 | HPR032 | 2020-04-01 | Subcontract | 0 | 10475935 | 16763221
MCR006275 | HPR032 | 2020-04-01 | Overhead | 0 | 5181065 | 14252564
MCR006276 | HPR032 | 2020-05-01 | Labor | 0 | 4207988 | 4941852
MCR006277 | HPR032 | 2020-05-01 | Material | 0 | 18990772 | 17574670
MCR006278 | HPR032 | 2020-05-01 | Equipment | 0 | 9126901 | 10626031
MCR006279 | HPR032 | 2020-05-01 | Subcontract | 0 | 8563331 | 23579919
MCR006280 | HPR032 | 2020-05-01 | Overhead | 0 | 4235152 | 13464963
MCR006281 | HPR032 | 2020-06-01 | Labor | 0 | 4979231 | 5134212
MCR006282 | HPR032 | 2020-06-01 | Material | 0 | 22471416 | 26542355
MCR006283 | HPR032 | 2020-06-01 | Equipment | 0 | 10799687 | 12603274
MCR006284 | HPR032 | 2020-06-01 | Subcontract | 0 | 10132826 | 15694068
MCR006285 | HPR032 | 2020-06-01 | Overhead | 0 | 5011374 | 13548023
MCR006286 | HPR032 | 2020-07-01 | Labor | 0 | 1830332 | 2751534
MCR006287 | HPR032 | 2020-07-01 | Material | 0 | 8260342 | 6019553
MCR006288 | HPR032 | 2020-07-01 | Equipment | 0 | 3969893 | 4390253
MCR006289 | HPR032 | 2020-07-01 | Subcontract | 0 | 3724759 | 20531665
MCR006290 | HPR032 | 2020-07-01 | Overhead | 0 | 1842148 | 14555597
MCR006291 | HPR032 | 2020-08-01 | Labor | 0 | 222756 | 8103
MCR006292 | HPR032 | 2020-08-01 | Material | 0 | 1005303 | 897119
MCR006293 | HPR032 | 2020-08-01 | Equipment | 0 | 483145 | 421448
MCR006294 | HPR032 | 2020-08-01 | Subcontract | 0 | 453312 | 6605011
MCR006295 | HPR032 | 2020-08-01 | Overhead | 0 | 224194 | 14850573
MCR006296 | HPR033 | 2022-10-01 | Labor | 3868213 | 4022152 | 3801824
MCR006297 | HPR033 | 2022-10-01 | Material | 12417951 | 12912135 | 12204888
MCR006298 | HPR033 | 2022-10-01 | Equipment | 3129480 | 3254021 | 3254739
MCR006299 | HPR033 | 2022-10-01 | Subcontract | 10681743 | 11106833 | 11070895
MCR006300 | HPR033 | 2022-10-01 | Overhead | 2405367 | 2501091 | 14661601
MCR006301 | HPR033 | 2022-11-01 | Labor | 10980172 | 24926908 | 22800889
MCR006302 | HPR033 | 2022-11-01 | Material | 35249154 | 80021736 | 81087980
MCR006303 | HPR033 | 2022-11-01 | Equipment | 8883232 | 20166488 | 17025480
MCR006304 | HPR033 | 2022-11-01 | Subcontract | 30320815 | 68833544 | 80432707
MCR006305 | HPR033 | 2022-11-01 | Overhead | 6827790 | 15500276 | 13453723
MCR006306 | HPR033 | 2022-12-01 | Labor | 17170826 | 14688077 | 12976718
MCR006307 | HPR033 | 2022-12-01 | Material | 55122732 | 47152473 | 44547785
MCR006308 | HPR033 | 2022-12-01 | Equipment | 13891624 | 11883018 | 13940030
MCR006309 | HPR033 | 2022-12-01 | Subcontract | 47415780 | 40559878 | 34737846
MCR006310 | HPR033 | 2022-12-01 | Overhead | 10677319 | 9133473 | 15252020
MCR006311 | HPR033 | 2023-01-01 | Labor | 22461485 | 8959919 | 9445211
MCR006312 | HPR033 | 2023-01-01 | Material | 72107098 | 28763627 | 28330988
MCR006313 | HPR033 | 2023-01-01 | Equipment | 18171899 | 7248797 | 6779611
MCR006314 | HPR033 | 2023-01-01 | Subcontract | 62025487 | 24742057 | 23496789
MCR006315 | HPR033 | 2023-01-01 | Overhead | 13967204 | 5571538 | 14762600
MCR006316 | HPR033 | 2023-02-01 | Labor | 26874534 | 27844003 | 23792922
MCR006317 | HPR033 | 2023-02-01 | Material | 86274112 | 89386354 | 83998175
MCR006318 | HPR033 | 2023-02-01 | Equipment | 21742165 | 22526489 | 23348110
MCR006319 | HPR033 | 2023-02-01 | Subcontract | 74211748 | 76888853 | 82394923
MCR006320 | HPR033 | 2023-02-01 | Overhead | 16711367 | 17314210 | 13536823
MCR006321 | HPR033 | 2023-03-01 | Labor | 30433561 | 31002162 | 32388975
MCR006322 | HPR033 | 2023-03-01 | Material | 97699495 | 99524851 | 120271987
MCR006323 | HPR033 | 2023-03-01 | Equipment | 24621506 | 25081519 | 26384617
MCR006324 | HPR033 | 2023-03-01 | Subcontract | 84039697 | 85609843 | 74644977
MCR006325 | HPR033 | 2023-03-01 | Overhead | 18924473 | 19278046 | 15456815
MCR006326 | HPR033 | 2023-04-01 | Labor | 33163510 | 50679467 | 42063888
MCR006327 | HPR033 | 2023-04-01 | Material | 106463327 | 162694021 | 150450249
MCR006328 | HPR033 | 2023-04-01 | Equipment | 26830102 | 41000947 | 43946149
MCR006329 | HPR033 | 2023-04-01 | Subcontract | 91578220 | 139947052 | 125815592
MCR006330 | HPR033 | 2023-04-01 | Overhead | 20622034 | 31513966 | 14830503
MCR006331 | HPR033 | 2023-05-01 | Labor | 35090873 | 35551046 | 32610048
MCR006332 | HPR033 | 2023-05-01 | Material | 112650655 | 114127928 | 108517333
MCR006333 | HPR033 | 2023-05-01 | Equipment | 28389387 | 28761679 | 24186021
MCR006334 | HPR033 | 2023-05-01 | Subcontract | 96900470 | 98171199 | 115209839
MCR006335 | HPR033 | 2023-05-01 | Overhead | 21820525 | 22106674 | 14550923
MCR006336 | HPR033 | 2023-06-01 | Labor | 36243917 | 40799926 | 37911813
MCR006337 | HPR033 | 2023-06-01 | Material | 116352222 | 130978173 | 132321996
MCR006338 | HPR033 | 2023-06-01 | Equipment | 29322229 | 33008153 | 30641865
MCR006339 | HPR033 | 2023-06-01 | Subcontract | 100084505 | 112665537 | 122528792
MCR006340 | HPR033 | 2023-06-01 | Overhead | 22537521 | 25370580 | 13974807
MCR006341 | HPR033 | 2023-07-01 | Labor | 36652973 | 36199218 | 28561863
MCR006342 | HPR033 | 2023-07-01 | Material | 117665394 | 116208725 | 109931647
MCR006343 | HPR033 | 2023-07-01 | Equipment | 29653165 | 29286066 | 34454827
MCR006344 | HPR033 | 2023-07-01 | Subcontract | 101214076 | 99961071 | 81312127
MCR006345 | HPR033 | 2023-07-01 | Overhead | 22791884 | 22509726 | 14042710
MCR006346 | HPR033 | 2023-08-01 | Labor | 36350789 | 26825668 | 30722224
MCR006347 | HPR033 | 2023-08-01 | Material | 116695309 | 86117238 | 93899512
MCR006348 | HPR033 | 2023-08-01 | Equipment | 29408691 | 21702631 | 22888706
MCR006349 | HPR033 | 2023-08-01 | Subcontract | 100379623 | 74076807 | 70249226
MCR006350 | HPR033 | 2023-08-01 | Overhead | 22603978 | 16680980 | 13215390
MCR006351 | HPR033 | 2023-09-01 | Labor | 35373004 | 30328013 | 28646792
MCR006352 | HPR033 | 2023-09-01 | Material | 113556369 | 97360660 | 93319724
MCR006353 | HPR033 | 2023-09-01 | Equipment | 28617638 | 24536115 | 21970028
MCR006354 | HPR033 | 2023-09-01 | Subcontract | 97679552 | 83748237 | 90136150
MCR006355 | HPR033 | 2023-09-01 | Overhead | 21995962 | 18858840 | 14473011
MCR006356 | HPR033 | 2023-10-01 | Labor | 33758750 | 35737576 | 32733355
MCR006357 | HPR033 | 2023-10-01 | Material | 108374200 | 114726737 | 104651749
MCR006358 | HPR033 | 2023-10-01 | Equipment | 27311666 | 28912586 | 27256686
MCR006359 | HPR033 | 2023-10-01 | Subcontract | 93221925 | 98686286 | 91849304
MCR006360 | HPR033 | 2023-10-01 | Overhead | 20992172 | 22222664 | 13582363
MCR006361 | HPR033 | 2023-11-01 | Labor | 31551479 | 30245339 | 27996146
MCR006362 | HPR033 | 2023-11-01 | Material | 101288296 | 97095255 | 90097250
MCR006363 | HPR033 | 2023-11-01 | Equipment | 25525929 | 24469230 | 25421469
MCR006364 | HPR033 | 2023-11-01 | Subcontract | 87126733 | 83519939 | 77297103
MCR006365 | HPR033 | 2023-11-01 | Overhead | 19619627 | 18807431 | 12361635
MCR006366 | HPR033 | 2023-12-01 | Labor | 28800112 | 25501803 | 26468667
MCR006367 | HPR033 | 2023-12-01 | Material | 92455708 | 81867293 | 98048987
MCR006368 | HPR033 | 2023-12-01 | Equipment | 23300006 | 20631591 | 23326119
MCR006369 | HPR033 | 2023-12-01 | Subcontract | 79529068 | 70421066 | 74914442
MCR006370 | HPR033 | 2023-12-01 | Overhead | 17908747 | 15857762 | 14311947
MCR006371 | HPR033 | 2024-01-01 | Labor | 25560707 | 20181154 | 18511450
MCR006372 | HPR033 | 2024-01-01 | Material | 82056392 | 64786654 | 58253259
MCR006373 | HPR033 | 2024-01-01 | Equipment | 20679246 | 16327055 | 15571859
MCR006374 | HPR033 | 2024-01-01 | Subcontract | 70583726 | 55728546 | 52172543
MCR006375 | HPR033 | 2024-01-01 | Overhead | 15894391 | 12549228 | 15172583
MCR006376 | HPR033 | 2024-02-01 | Labor | 21898993 | 23577721 | 24290042
MCR006377 | HPR033 | 2024-02-01 | Material | 70301355 | 75690500 | 79418296
MCR006378 | HPR033 | 2024-02-01 | Equipment | 17716829 | 19074961 | 20905291
MCR006379 | HPR033 | 2024-02-01 | Subcontract | 60472213 | 65107878 | 63250978
MCR006380 | HPR033 | 2024-02-01 | Overhead | 13617430 | 14661312 | 14386543
MCR006381 | HPR033 | 2024-03-01 | Labor | 17894496 | 22842796 | 20279833
MCR006382 | HPR033 | 2024-03-01 | Material | 57445896 | 73331203 | 56835346
MCR006383 | HPR033 | 2024-03-01 | Equipment | 14477091 | 18480389 | 17211425
MCR006384 | HPR033 | 2024-03-01 | Subcontract | 49414132 | 63078444 | 60313614
MCR006385 | HPR033 | 2024-03-01 | Overhead | 11127318 | 14204315 | 15335359
MCR006386 | HPR033 | 2024-04-01 | Labor | 13647855 | 11544688 | 10067155
MCR006387 | HPR033 | 2024-04-01 | Material | 43813097 | 37061392 | 44863689
MCR006388 | HPR033 | 2024-04-01 | Equipment | 11041453 | 9339939 | 9312640
MCR006389 | HPR033 | 2024-04-01 | Subcontract | 37687394 | 31879676 | 31636316
MCR006390 | HPR033 | 2024-04-01 | Overhead | 8486633 | 7178822 | 15136903
MCR006391 | HPR033 | 2024-05-01 | Labor | 9295611 | 6765510 | 6541755
MCR006392 | HPR033 | 2024-05-01 | Material | 29841282 | 21719015 | 19315111
MCR006393 | HPR033 | 2024-05-01 | Equipment | 7520380 | 5473466 | 4573780
MCR006394 | HPR033 | 2024-05-01 | Subcontract | 25669041 | 18682383 | 20510821
MCR006395 | HPR033 | 2024-05-01 | Overhead | 5780281 | 4206991 | 13987499
MCR006396 | HPR033 | 2024-06-01 | Labor | 5047248 | 3528613 | 2616494
MCR006397 | HPR033 | 2024-06-01 | Material | 16202954 | 11327749 | 13046056
MCR006398 | HPR033 | 2024-06-01 | Equipment | 4083349 | 2854736 | 2887292
MCR006399 | HPR033 | 2024-06-01 | Subcontract | 13937548 | 9743967 | 9925977
MCR006400 | HPR033 | 2024-06-01 | Overhead | 3138526 | 2194194 | 13573087
MCR006401 | HPR033 | 2024-07-01 | Labor | 1341119 | 1708466 | 1878521
MCR006402 | HPR033 | 2024-07-01 | Material | 4305334 | 5484613 | 6195129
MCR006403 | HPR033 | 2024-07-01 | Equipment | 1084998 | 1382192 | 1593684
MCR006404 | HPR033 | 2024-07-01 | Subcontract | 3703386 | 4717785 | 3482362
MCR006405 | HPR033 | 2024-07-01 | Overhead | 833947 | 1062374 | 15007874
MCR006406 | HPR034 | 2016-07-01 | Labor | 8155093 | 6294984 | 5740950
MCR006407 | HPR034 | 2016-07-01 | Material | 23156444 | 17874650 | 19233136
MCR006408 | HPR034 | 2016-07-01 | Equipment | 6403281 | 4942745 | 6049421
MCR006409 | HPR034 | 2016-07-01 | Subcontract | 25920006 | 20007866 | 20649902
MCR006410 | HPR034 | 2016-07-01 | Overhead | 5870488 | 4531478 | 19767874
MCR006411 | HPR034 | 2016-08-01 | Labor | 21767026 | 7573554 | 9144503
MCR006412 | HPR034 | 2016-08-01 | Material | 61807623 | 21505159 | 20933390
MCR006413 | HPR034 | 2016-08-01 | Equipment | 17091206 | 5946663 | 5656925
MCR006414 | HPR034 | 2016-08-01 | Subcontract | 69183935 | 24071651 | 25798237
MCR006415 | HPR034 | 2016-08-01 | Overhead | 15669110 | 5451863 | 18364416
MCR006416 | HPR034 | 2016-09-01 | Labor | 31474995 | 28923258 | 25545153
MCR006417 | HPR034 | 2016-09-01 | Material | 89373469 | 82127794 | 80448469
MCR006418 | HPR034 | 2016-09-01 | Equipment | 24713786 | 22710193 | 24987859
MCR006419 | HPR034 | 2016-09-01 | Subcontract | 100039574 | 91929177 | 89270241
MCR006420 | HPR034 | 2016-09-01 | Overhead | 22657444 | 20820562 | 19121759
MCR006421 | HPR034 | 2016-10-01 | Labor | 37486961 | 26784912 | 27693090
MCR006422 | HPR034 | 2016-10-01 | Material | 106444490 | 76055945 | 78572383
MCR006423 | HPR034 | 2016-10-01 | Equipment | 29434310 | 21031190 | 20996201
MCR006424 | HPR034 | 2016-10-01 | Subcontract | 119147902 | 85132695 | 72741819
MCR006425 | HPR034 | 2016-10-01 | Overhead | 26985190 | 19281263 | 19597878
MCR006426 | HPR034 | 2016-11-01 | Labor | 40036739 | 20550207 | 23450139
MCR006427 | HPR034 | 2016-11-01 | Material | 113684602 | 58352456 | 64535333
MCR006428 | HPR034 | 2016-11-01 | Equipment | 31436365 | 16135774 | 16389615
MCR006429 | HPR034 | 2016-11-01 | Subcontract | 127252072 | 65316418 | 68681205
MCR006430 | HPR034 | 2016-11-01 | Overhead | 28820662 | 14793177 | 17640937
MCR006431 | HPR034 | 2016-12-01 | Labor | 39392446 | 35011241 | 32523345
MCR006432 | HPR034 | 2016-12-01 | Material | 111855127 | 99414664 | 92744095
MCR006433 | HPR034 | 2016-12-01 | Equipment | 30930474 | 27490404 | 28064759
MCR006434 | HPR034 | 2016-12-01 | Subcontract | 125204262 | 111279115 | 110212416
MCR006435 | HPR034 | 2016-12-01 | Overhead | 28356864 | 25203030 | 16599255
MCR006436 | HPR034 | 2017-01-01 | Labor | 35869961 | 20260779 | 22539755
MCR006437 | HPR034 | 2017-01-01 | Material | 101853005 | 57530624 | 61878093
MCR006438 | HPR034 | 2017-01-01 | Equipment | 28164660 | 15908519 | 17344903
MCR006439 | HPR034 | 2017-01-01 | Subcontract | 114008456 | 64396505 | 54129656
MCR006440 | HPR034 | 2017-01-01 | Overhead | 25821184 | 14584830 | 18242865
MCR006441 | HPR034 | 2017-02-01 | Labor | 29856280 | 40050225 | 45233687
MCR006442 | HPR034 | 2017-02-01 | Material | 84777116 | 113722895 | 105116551
MCR006443 | HPR034 | 2017-02-01 | Equipment | 23442791 | 31446953 | 34566452
MCR006444 | HPR034 | 2017-02-01 | Subcontract | 94894678 | 127294935 | 117630348
MCR006445 | HPR034 | 2017-02-01 | Overhead | 21492203 | 28830369 | 17716020
MCR006446 | HPR034 | 2017-03-01 | Labor | 21855549 | 35534981 | 30701045
MCR006447 | HPR034 | 2017-03-01 | Material | 62058984 | 100901826 | 116530761
MCR006448 | HPR034 | 2017-03-01 | Equipment | 17160713 | 27901638 | 24351329
MCR006449 | HPR034 | 2017-03-01 | Subcontract | 69465294 | 112943761 | 115411593
MCR006450 | HPR034 | 2017-03-01 | Overhead | 15732834 | 25580046 | 16741923
MCR006451 | HPR034 | 2017-04-01 | Labor | 12601108 | 21929532 | 25380840
MCR006452 | HPR034 | 2017-04-01 | Material | 35780933 | 62269061 | 60056006
MCR006453 | HPR034 | 2017-04-01 | Equipment | 9894238 | 17218804 | 18699047
MCR006454 | HPR034 | 2017-04-01 | Subcontract | 40051140 | 69700442 | 61824240
MCR006455 | HPR034 | 2017-04-01 | Overhead | 9070975 | 15786091 | 16517512
MCR006456 | HPR034 | 2017-05-01 | Labor | 3508646 | 19708355 | 20971353
MCR006457 | HPR034 | 2017-05-01 | Material | 9962825 | 55962012 | 54390325
MCR006458 | HPR034 | 2017-05-01 | Equipment | 2754947 | 15474762 | 14526066
MCR006459 | HPR034 | 2017-05-01 | Subcontract | 11151819 | 62640691 | 63406604
MCR006460 | HPR034 | 2017-05-01 | Overhead | 2525718 | 14187165 | 19080098
MCR006461 | HPR034 | 2017-06-01 | Labor | 0 | 10824646 | 10857703
MCR006462 | HPR034 | 2017-06-01 | Material | 0 | 30736657 | 29265712
MCR006463 | HPR034 | 2017-06-01 | Equipment | 0 | 8499381 | 9804899
MCR006464 | HPR034 | 2017-06-01 | Subcontract | 0 | 34404864 | 33783990
MCR006465 | HPR034 | 2017-06-01 | Overhead | 0 | 7792179 | 18653108
MCR006466 | HPR034 | 2017-07-01 | Labor | 0 | 7314565 | 7782377
MCR006467 | HPR034 | 2017-07-01 | Material | 0 | 20769758 | 24527598
MCR006468 | HPR034 | 2017-07-01 | Equipment | 0 | 5743308 | 6323451
MCR006469 | HPR034 | 2017-07-01 | Subcontract | 0 | 23248485 | 26912172
MCR006470 | HPR034 | 2017-07-01 | Overhead | 0 | 5265429 | 19121788
MCR006471 | HPR034 | 2017-08-01 | Labor | 0 | 1243567 | 1040521
MCR006472 | HPR034 | 2017-08-01 | Material | 0 | 3531118 | 2663142
MCR006473 | HPR034 | 2017-08-01 | Equipment | 0 | 976434 | 1090211
MCR006474 | HPR034 | 2017-08-01 | Subcontract | 0 | 3952532 | 1177621
MCR006475 | HPR034 | 2017-08-01 | Overhead | 0 | 895188 | 18416600
MCR006476 | HPR035 | 2021-11-01 | Labor | 3050544 | 1921264 | 2140099
MCR006477 | HPR035 | 2021-11-01 | Material | 11631257 | 7325487 | 6791945
MCR006478 | HPR035 | 2021-11-01 | Equipment | 2163429 | 1362550 | 1080748
MCR006479 | HPR035 | 2021-11-01 | Subcontract | 7772332 | 4895096 | 5538487
MCR006480 | HPR035 | 2021-11-01 | Overhead | 2168517 | 1365755 | 10256450
MCR006481 | HPR035 | 2021-12-01 | Labor | 8579209 | 5702317 | 5261405
MCR006482 | HPR035 | 2021-12-01 | Material | 32711213 | 21742062 | 23973552
MCR006483 | HPR035 | 2021-12-01 | Equipment | 6084327 | 4044051 | 4033929
MCR006484 | HPR035 | 2021-12-01 | Subcontract | 21858549 | 14528655 | 15153478
MCR006485 | HPR035 | 2021-12-01 | Overhead | 6098638 | 4053563 | 11119988
MCR006486 | HPR035 | 2022-01-01 | Labor | 13265770 | 16590489 | 16561178
MCR006487 | HPR035 | 2022-01-01 | Material | 50580355 | 63257001 | 62835022
MCR006488 | HPR035 | 2022-01-01 | Equipment | 9408011 | 11765883 | 13069884
MCR006489 | HPR035 | 2022-01-01 | Subcontract | 33799210 | 42270100 | 42000080
MCR006490 | HPR035 | 2022-01-01 | Overhead | 9430139 | 11793557 | 11631701
MCR006491 | HPR035 | 2022-02-01 | Labor | 17133259 | 11341809 | 11414850
MCR006492 | HPR035 | 2022-02-01 | Material | 65326498 | 43244584 | 47064688
MCR006493 | HPR035 | 2022-02-01 | Equipment | 12150812 | 8043548 | 7917619
MCR006494 | HPR035 | 2022-02-01 | Subcontract | 43652996 | 28897242 | 30352955
MCR006495 | HPR035 | 2022-02-01 | Overhead | 12179391 | 8062466 | 10637799
MCR006496 | HPR035 | 2022-03-01 | Labor | 20206091 | 15310475 | 16976351
MCR006497 | HPR035 | 2022-03-01 | Material | 77042737 | 58376503 | 54545148
MCR006498 | HPR035 | 2022-03-01 | Equipment | 14330048 | 10858104 | 10409431
MCR006499 | HPR035 | 2022-03-01 | Subcontract | 51482115 | 39008814 | 40265122
MCR006500 | HPR035 | 2022-03-01 | Overhead | 14363752 | 10883643 | 11099120
MCR006501 | HPR035 | 2022-04-01 | Labor | 22510268 | 17871172 | 18407170
MCR006502 | HPR035 | 2022-04-01 | Material | 85828213 | 68140046 | 68697627
MCR006503 | HPR035 | 2022-04-01 | Equipment | 15964157 | 12674136 | 12120780
MCR006504 | HPR035 | 2022-04-01 | Subcontract | 57352816 | 45533087 | 40258799
MCR006505 | HPR035 | 2022-04-01 | Overhead | 16001705 | 12703945 | 11238845
MCR006506 | HPR035 | 2022-05-01 | Labor | 24073630 | 27984745 | 28769291
MCR006507 | HPR035 | 2022-05-01 | Material | 91789071 | 106701554 | 115608633
MCR006508 | HPR035 | 2022-05-01 | Equipment | 17072884 | 19846625 | 17066526
MCR006509 | HPR035 | 2022-05-01 | Subcontract | 61336028 | 71300967 | 87252193
MCR006510 | HPR035 | 2022-05-01 | Overhead | 17113040 | 19893305 | 11463781
MCR006511 | HPR035 | 2022-06-01 | Labor | 24926166 | 21934644 | 20657723
MCR006512 | HPR035 | 2022-06-01 | Material | 95039660 | 83633445 | 85113804
MCR006513 | HPR035 | 2022-06-01 | Equipment | 17677498 | 15555928 | 20021420
MCR006514 | HPR035 | 2022-06-01 | Subcontract | 63508163 | 55886210 | 54164433
MCR006515 | HPR035 | 2022-06-01 | Overhead | 17719076 | 15592515 | 11273869
MCR006516 | HPR035 | 2022-07-01 | Labor | 25100424 | 11124992 | 10757425
MCR006517 | HPR035 | 2022-07-01 | Material | 95704080 | 42417894 | 44047590
MCR006518 | HPR035 | 2022-07-01 | Equipment | 17801081 | 7889782 | 7089150
MCR006519 | HPR035 | 2022-07-01 | Subcontract | 63952147 | 28344825 | 27532579
MCR006520 | HPR035 | 2022-07-01 | Overhead | 17842950 | 7908339 | 11729139
MCR006521 | HPR035 | 2022-08-01 | Labor | 24632041 | 22029132 | 22943697
MCR006522 | HPR035 | 2022-08-01 | Material | 93918206 | 83993714 | 84341228
MCR006523 | HPR035 | 2022-08-01 | Equipment | 17468906 | 15622938 | 16540137
MCR006524 | HPR035 | 2022-08-01 | Subcontract | 62758776 | 56126952 | 59941513
MCR006525 | HPR035 | 2022-08-01 | Overhead | 17509994 | 15659684 | 10978623
MCR006526 | HPR035 | 2022-09-01 | Labor | 23560455 | 15887281 | 17009205
MCR006527 | HPR035 | 2022-09-01 | Material | 89832414 | 60575774 | 63433946
MCR006528 | HPR035 | 2022-09-01 | Equipment | 16708944 | 11267171 | 11448320
MCR006529 | HPR035 | 2022-09-01 | Subcontract | 60028535 | 40478429 | 39538903
MCR006530 | HPR035 | 2022-09-01 | Overhead | 16748244 | 11293672 | 11594791
MCR006531 | HPR035 | 2022-10-01 | Labor | 21929904 | 17608646 | 15243463
MCR006532 | HPR035 | 2022-10-01 | Material | 83615373 | 67139074 | 72382360
MCR006533 | HPR035 | 2022-10-01 | Equipment | 15552566 | 12487954 | 12852680
MCR006534 | HPR035 | 2022-10-01 | Subcontract | 55874134 | 44864210 | 54516471
MCR006535 | HPR035 | 2022-10-01 | Overhead | 15589146 | 12517326 | 10205627
MCR006536 | HPR035 | 2022-11-01 | Labor | 19790861 | 17892591 | 20234771
MCR006537 | HPR035 | 2022-11-01 | Material | 75459528 | 68221713 | 70490770
MCR006538 | HPR035 | 2022-11-01 | Equipment | 14035569 | 12689326 | 13513262
MCR006539 | HPR035 | 2022-11-01 | Subcontract | 50424170 | 45587660 | 34240934
MCR006540 | HPR035 | 2022-11-01 | Overhead | 14068581 | 12719171 | 10840952
MCR006541 | HPR035 | 2022-12-01 | Labor | 17202214 | 14232027 | 14770760
MCR006542 | HPR035 | 2022-12-01 | Material | 65589414 | 54264543 | 62281030
MCR006543 | HPR035 | 2022-12-01 | Equipment | 12199715 | 10093274 | 10845619
MCR006544 | HPR035 | 2022-12-01 | Subcontract | 43828684 | 36261088 | 43284224
MCR006545 | HPR035 | 2022-12-01 | Overhead | 12228409 | 10117014 | 11097580
MCR006546 | HPR035 | 2023-01-01 | Labor | 14234801 | 14965663 | 12473696
MCR006547 | HPR035 | 2023-01-01 | Material | 54275122 | 57061787 | 61574082
MCR006548 | HPR035 | 2023-01-01 | Equipment | 10095242 | 10613565 | 10083483
MCR006549 | HPR035 | 2023-01-01 | Subcontract | 36268157 | 38130284 | 38447390
MCR006550 | HPR035 | 2023-01-01 | Overhead | 10118986 | 10638529 | 11427161
MCR006551 | HPR035 | 2023-02-01 | Labor | 10977650 | 15946102 | 18279869
MCR006552 | HPR035 | 2023-02-01 | Material | 41856102 | 60800051 | 53925086
MCR006553 | HPR035 | 2023-02-01 | Equipment | 7785288 | 11308887 | 10386728
MCR006554 | HPR035 | 2023-02-01 | Subcontract | 27969420 | 40628297 | 57523998
MCR006555 | HPR035 | 2023-02-01 | Overhead | 7803600 | 11335486 | 12124396
MCR006556 | HPR035 | 2023-03-01 | Labor | 7550533 | 19340974 | 18918280
MCR006557 | HPR035 | 2023-03-01 | Material | 28789029 | 73744179 | 75472585
MCR006558 | HPR035 | 2023-03-01 | Equipment | 5354796 | 13716512 | 12592670
MCR006559 | HPR035 | 2023-03-01 | Subcontract | 19237636 | 49277926 | 64479429
MCR006560 | HPR035 | 2023-03-01 | Overhead | 5367391 | 13748773 | 10185561
MCR006561 | HPR035 | 2023-04-01 | Labor | 4135269 | 11542700 | 9801422
MCR006562 | HPR035 | 2023-04-01 | Material | 15767148 | 44010550 | 38398054
MCR006563 | HPR035 | 2023-04-01 | Equipment | 2932710 | 8186018 | 9946013
MCR006564 | HPR035 | 2023-04-01 | Subcontract | 10536050 | 29409082 | 41641416
MCR006565 | HPR035 | 2023-04-01 | Overhead | 2939607 | 8205272 | 10813634
MCR006566 | HPR035 | 2023-05-01 | Labor | 1106559 | 14479849 | 16258719
MCR006567 | HPR035 | 2023-05-01 | Material | 4219140 | 55209450 | 60955318
MCR006568 | HPR035 | 2023-05-01 | Equipment | 784765 | 10269028 | 11022403
MCR006569 | HPR035 | 2023-05-01 | Subcontract | 2819348 | 36892501 | 53544802
MCR006570 | HPR035 | 2023-05-01 | Overhead | 786611 | 10293181 | 11709568
MCR006571 | HPR035 | 2023-06-01 | Labor | 0 | 4579164 | 4011186
MCR006572 | HPR035 | 2023-06-01 | Material | 0 | 17459654 | 18197342
MCR006573 | HPR035 | 2023-06-01 | Equipment | 0 | 3247518 | 3487071
MCR006574 | HPR035 | 2023-06-01 | Subcontract | 0 | 11667030 | 35028429
MCR006575 | HPR035 | 2023-06-01 | Overhead | 0 | 3255156 | 11213809
MCR006576 | HPR035 | 2023-07-01 | Labor | 0 | 2856586 | 2487930
MCR006577 | HPR035 | 2023-07-01 | Material | 0 | 10891725 | 10348396
MCR006578 | HPR035 | 2023-07-01 | Equipment | 0 | 2025875 | 2239162
MCR006579 | HPR035 | 2023-07-01 | Subcontract | 0 | 7278156 | 18735321
MCR006580 | HPR035 | 2023-07-01 | Overhead | 0 | 2030640 | 10435455
MCR006581 | HPR035 | 2023-08-01 | Labor | 0 | 2020080 | 2294231
MCR006582 | HPR035 | 2023-08-01 | Material | 0 | 7702254 | 8434185
MCR006583 | HPR035 | 2023-08-01 | Equipment | 0 | 1432629 | 1446616
MCR006584 | HPR035 | 2023-08-01 | Subcontract | 0 | 5146862 | 17700882
MCR006585 | HPR035 | 2023-08-01 | Overhead | 0 | 1435999 | 11926661
MCR006586 | HPR035 | 2023-09-01 | Labor | 0 | 802948 | 538533
MCR006587 | HPR035 | 2023-09-01 | Material | 0 | 3061518 | 2746961
MCR006588 | HPR035 | 2023-09-01 | Equipment | 0 | 569446 | 603970
MCR006589 | HPR035 | 2023-09-01 | Subcontract | 0 | 2045792 | 12932066
MCR006590 | HPR035 | 2023-09-01 | Overhead | 0 | 570786 | 11886990
MCR006591 | HPR036 | 2018-03-01 | Labor | 10703198 | 11960613 | 12563910
MCR006592 | HPR036 | 2018-03-01 | Material | 19893308 | 22230382 | 25927353
MCR006593 | HPR036 | 2018-03-01 | Equipment | 4310907 | 4817354 | 4439297
MCR006594 | HPR036 | 2018-03-01 | Subcontract | 20730821 | 23166286 | 20115040
MCR006595 | HPR036 | 2018-03-01 | Overhead | 5823819 | 6508003 | 31737713
MCR006596 | HPR036 | 2018-04-01 | Labor | 30101183 | 21403062 | 21839650
MCR006597 | HPR036 | 2018-04-01 | Material | 55947029 | 39780420 | 40253600
MCR006598 | HPR036 | 2018-04-01 | Equipment | 12123798 | 8620472 | 8351489
MCR006599 | HPR036 | 2018-04-01 | Subcontract | 58302412 | 41455185 | 44667631
MCR006600 | HPR036 | 2018-04-01 | Overhead | 16378642 | 11645824 | 31421784
MCR006601 | HPR036 | 2018-05-01 | Labor | 46544544 | 29331576 | 29877391
MCR006602 | HPR036 | 2018-05-01 | Material | 86509190 | 54516613 | 59815469
MCR006603 | HPR036 | 2018-05-01 | Equipment | 18746660 | 11813825 | 13002430
MCR006604 | HPR036 | 2018-05-01 | Subcontract | 90151247 | 56811775 | 55295901
MCR006605 | HPR036 | 2018-05-01 | Overhead | 25325796 | 15959883 | 30627713
MCR006606 | HPR036 | 2018-06-01 | Labor | 60114092 | 58210518 | 68227091
MCR006607 | HPR036 | 2018-06-01 | Material | 111729988 | 108191944 | 100303543
MCR006608 | HPR036 | 2018-06-01 | Equipment | 24212042 | 23445343 | 24614495
MCR006609 | HPR036 | 2018-06-01 | Subcontract | 116433847 | 112746850 | 116164852
MCR006610 | HPR036 | 2018-06-01 | Overhead | 32709251 | 31673479 | 28797162
MCR006611 | HPR036 | 2018-07-01 | Labor | 70895491 | 36072059 | 38075097
MCR006612 | HPR036 | 2018-07-01 | Material | 131768644 | 67044691 | 67451332
MCR006613 | HPR036 | 2018-07-01 | Equipment | 28554446 | 14528677 | 13162476
MCR006614 | HPR036 | 2018-07-01 | Subcontract | 137316135 | 69867288 | 69020377
MCR006615 | HPR036 | 2018-07-01 | Overhead | 38575621 | 19627512 | 30785167
MCR006616 | HPR036 | 2018-08-01 | Labor | 78979973 | 54418177 | 60523521
MCR006617 | HPR036 | 2018-08-01 | Material | 146794723 | 101143377 | 105813920
MCR006618 | HPR036 | 2018-08-01 | Equipment | 31810618 | 21917909 | 21020087
MCR006619 | HPR036 | 2018-08-01 | Subcontract | 152974815 | 105401537 | 109740441
MCR006620 | HPR036 | 2018-08-01 | Overhead | 42974546 | 29609993 | 32896354
MCR006621 | HPR036 | 2018-09-01 | Labor | 84465213 | 63930031 | 70319159
MCR006622 | HPR036 | 2018-09-01 | Material | 156989767 | 118822416 | 130134205
MCR006623 | HPR036 | 2018-09-01 | Equipment | 34019898 | 25748981 | 24991885
MCR006624 | HPR036 | 2018-09-01 | Subcontract | 163599073 | 123824868 | 113101750
MCR006625 | HPR036 | 2018-09-01 | Overhead | 45959172 | 34785579 | 29832007
MCR006626 | HPR036 | 2018-10-01 | Labor | 87456438 | 42364108 | 53050803
MCR006627 | HPR036 | 2018-10-01 | Material | 162549353 | 78739296 | 80073470
MCR006628 | HPR036 | 2018-10-01 | Equipment | 35224668 | 17062914 | 19312305
MCR006629 | HPR036 | 2018-10-01 | Subcontract | 169392719 | 82054239 | 90267461
MCR006630 | HPR036 | 2018-10-01 | Overhead | 47586756 | 23051139 | 30448330
MCR006631 | HPR036 | 2018-11-01 | Labor | 88067844 | 75136339 | 81511028
MCR006632 | HPR036 | 2018-11-01 | Material | 163685733 | 139650820 | 134638360
MCR006633 | HPR036 | 2018-11-01 | Equipment | 35470923 | 30262525 | 27031650
MCR006634 | HPR036 | 2018-11-01 | Subcontract | 170576940 | 145530152 | 137723899
MCR006635 | HPR036 | 2018-11-01 | Overhead | 47919434 | 40883149 | 31403006
MCR006636 | HPR036 | 2018-12-01 | Labor | 86424465 | 86477187 | 103874535
MCR006637 | HPR036 | 2018-12-01 | Material | 160631295 | 160729286 | 172330086
MCR006638 | HPR036 | 2018-12-01 | Equipment | 34809022 | 34830257 | 38678329
MCR006639 | HPR036 | 2018-12-01 | Subcontract | 167393910 | 167496026 | 183228962
MCR006640 | HPR036 | 2018-12-01 | Overhead | 47025239 | 47053926 | 30407564
MCR006641 | HPR036 | 2019-01-01 | Labor | 82664678 | 78432432 | 80527041
MCR006642 | HPR036 | 2019-01-01 | Material | 153643234 | 145777045 | 154353588
MCR006643 | HPR036 | 2019-01-01 | Equipment | 33294700 | 31590086 | 32267602
MCR006644 | HPR036 | 2019-01-01 | Subcontract | 160111651 | 151914293 | 137712275
MCR006645 | HPR036 | 2019-01-01 | Overhead | 44979466 | 42676618 | 30953120
MCR006646 | HPR036 | 2019-02-01 | Labor | 76943696 | 90246951 | 97130944
MCR006647 | HPR036 | 2019-02-01 | Material | 143010032 | 167735892 | 167480354
MCR006648 | HPR036 | 2019-02-01 | Equipment | 30990470 | 36348598 | 37656444
MCR006649 | HPR036 | 2019-02-01 | Subcontract | 149030788 | 174797612 | 197430154
MCR006650 | HPR036 | 2019-02-01 | Overhead | 41866568 | 49105129 | 28265676
MCR006651 | HPR036 | 2019-03-01 | Labor | 69438606 | 57875298 | 68500054
MCR006652 | HPR036 | 2019-03-01 | Material | 129060831 | 107568894 | 121415353
MCR006653 | HPR036 | 2019-03-01 | Equipment | 27967659 | 23310327 | 23569552
MCR006654 | HPR036 | 2019-03-01 | Subcontract | 134494322 | 112097569 | 102547625
MCR006655 | HPR036 | 2019-03-01 | Overhead | 37782902 | 31491080 | 29344111
MCR006656 | HPR036 | 2019-04-01 | Labor | 60356029 | 81265035 | 93036458
MCR006657 | HPR036 | 2019-04-01 | Material | 112179661 | 151041813 | 157020759
MCR006658 | HPR036 | 2019-04-01 | Equipment | 24309487 | 32730968 | 35357295
MCR006659 | HPR036 | 2019-04-01 | Subcontract | 116902451 | 157400709 | 162924050
MCR006660 | HPR036 | 2019-04-01 | Overhead | 32840894 | 44217893 | 32548657
MCR006661 | HPR036 | 2019-05-01 | Labor | 49944506 | 82198643 | 95970460
MCR006662 | HPR036 | 2019-05-01 | Material | 92828467 | 152777046 | 154848261
MCR006663 | HPR036 | 2019-05-01 | Equipment | 20116056 | 33106996 | 35295342
MCR006664 | HPR036 | 2019-05-01 | Subcontract | 96736568 | 159208996 | 151539861
MCR006665 | HPR036 | 2019-05-01 | Overhead | 27175781 | 44725887 | 31234102
MCR006666 | HPR036 | 2019-06-01 | Labor | 38516400 | 86960834 | 98268972
MCR006667 | HPR036 | 2019-06-01 | Material | 71587823 | 161628207 | 191867169
MCR006668 | HPR036 | 2019-06-01 | Equipment | 15513180 | 35025055 | 31981244
MCR006669 | HPR036 | 2019-06-01 | Subcontract | 74601687 | 168432793 | 183681337
MCR006670 | HPR036 | 2019-06-01 | Overhead | 20957526 | 47317088 | 32000307
MCR006671 | HPR036 | 2019-07-01 | Labor | 26491950 | 36663670 | 47942156
MCR006672 | HPR036 | 2019-07-01 | Material | 49238793 | 68144279 | 61455061
MCR006673 | HPR036 | 2019-07-01 | Equipment | 10670114 | 14766959 | 12719351
MCR006674 | HPR036 | 2019-07-01 | Subcontract | 51311757 | 71013169 | 63662747
MCR006675 | HPR036 | 2019-07-01 | Overhead | 14414788 | 19949419 | 27391029
MCR006676 | HPR036 | 2019-08-01 | Labor | 14509086 | 14184479 | 17592830
MCR006677 | HPR036 | 2019-08-01 | Material | 26967054 | 26363730 | 23392682
MCR006678 | HPR036 | 2019-08-01 | Equipment | 5843798 | 5713056 | 6773288
MCR006679 | HPR036 | 2019-08-01 | Subcontract | 28102374 | 27473649 | 30495656
MCR006680 | HPR036 | 2019-08-01 | Overhead | 7894677 | 7718052 | 30631980
MCR006681 | HPR036 | 2019-09-01 | Labor | 3882495 | 23733089 | 24034128
MCR006682 | HPR036 | 2019-09-01 | Material | 7216130 | 44111083 | 46138118
MCR006683 | HPR036 | 2019-09-01 | Equipment | 1563745 | 9558932 | 10133081
MCR006684 | HPR036 | 2019-09-01 | Subcontract | 7519930 | 45968170 | 44303089
MCR006685 | HPR036 | 2019-09-01 | Overhead | 2112541 | 12913637 | 32091989
MCR006686 | HPR036 | 2019-10-01 | Labor | 0 | 19885365 | 27999724
MCR006687 | HPR036 | 2019-10-01 | Material | 0 | 36959581 | 35350000
MCR006688 | HPR036 | 2019-10-01 | Equipment | 0 | 8009192 | 7629319
MCR006689 | HPR036 | 2019-10-01 | Subcontract | 0 | 38515588 | 39454112
MCR006690 | HPR036 | 2019-10-01 | Overhead | 0 | 10820016 | 33710203
MCR006691 | HPR036 | 2019-11-01 | Labor | 0 | 12727514 | 13989157
MCR006692 | HPR036 | 2019-11-01 | Material | 0 | 23655767 | 27445374
MCR006693 | HPR036 | 2019-11-01 | Equipment | 0 | 5126237 | 5701088
MCR006694 | HPR036 | 2019-11-01 | Subcontract | 0 | 24651680 | 23487442
MCR006695 | HPR036 | 2019-11-01 | Overhead | 0 | 6925289 | 30978692
MCR006696 | HPR036 | 2019-12-01 | Labor | 0 | 3022908 | 3543725
MCR006697 | HPR036 | 2019-12-01 | Material | 0 | 5618474 | 6376985
MCR006698 | HPR036 | 2019-12-01 | Equipment | 0 | 1217531 | 960492
MCR006699 | HPR036 | 2019-12-01 | Subcontract | 0 | 5855013 | 6069003
MCR006700 | HPR036 | 2019-12-01 | Overhead | 0 | 1644823 | 31030540
MCR006701 | HPR037 | 2016-11-01 | Labor | 2491329 | 1365229 | 1457821
MCR006702 | HPR037 | 2016-11-01 | Material | 5736160 | 3143371 | 2884278
MCR006703 | HPR037 | 2016-11-01 | Equipment | 1748225 | 958013 | 1071334
MCR006704 | HPR037 | 2016-11-01 | Subcontract | 9259643 | 5074211 | 5292952
MCR006705 | HPR037 | 2016-11-01 | Overhead | 1443031 | 790770 | 8497609
MCR006706 | HPR037 | 2016-12-01 | Labor | 7071799 | 3820667 | 4105385
MCR006707 | HPR037 | 2016-12-01 | Material | 16282460 | 8796894 | 7809835
MCR006708 | HPR037 | 2016-12-01 | Equipment | 4962448 | 2681053 | 2837151
MCR006709 | HPR037 | 2016-12-01 | Subcontract | 26284092 | 14200457 | 13052155
MCR006710 | HPR037 | 2016-12-01 | Overhead | 4096136 | 2213012 | 9376809
MCR006711 | HPR037 | 2017-01-01 | Labor | 11058900 | 7452472 | 8237070
MCR006712 | HPR037 | 2017-01-01 | Material | 25462559 | 17158941 | 18435386
MCR006713 | HPR037 | 2017-01-01 | Equipment | 7760292 | 5229576 | 5557221
MCR006714 | HPR037 | 2017-01-01 | Subcontract | 41103141 | 27698959 | 24902234
MCR006715 | HPR037 | 2017-01-01 | Overhead | 6405549 | 4316630 | 9341902
MCR006716 | HPR037 | 2017-02-01 | Labor | 14466358 | 8036815 | 8039004
MCR006717 | HPR037 | 2017-02-01 | Material | 33308059 | 18504362 | 17111873
MCR006718 | HPR037 | 2017-02-01 | Equipment | 10151386 | 5639624 | 6429589
MCR006719 | HPR037 | 2017-02-01 | Subcontract | 53767804 | 29870816 | 30815124
MCR006720 | HPR037 | 2017-02-01 | Overhead | 8379221 | 4655094 | 8596117
MCR006721 | HPR037 | 2017-03-01 | Labor | 17308590 | 7548927 | 8470238
MCR006722 | HPR037 | 2017-03-01 | Material | 39852155 | 17381023 | 19381734
MCR006723 | HPR037 | 2017-03-01 | Equipment | 12145847 | 5297260 | 5139185
MCR006724 | HPR037 | 2017-03-01 | Subcontract | 64331663 | 28057456 | 24866231
MCR006725 | HPR037 | 2017-03-01 | Overhead | 10025502 | 4372498 | 9445911
MCR006726 | HPR037 | 2017-04-01 | Labor | 19600787 | 18212090 | 20255860
MCR006727 | HPR037 | 2017-04-01 | Material | 45129823 | 41932418 | 44271718
MCR006728 | HPR037 | 2017-04-01 | Equipment | 13754336 | 12779854 | 13435785
MCR006729 | HPR037 | 2017-04-01 | Subcontract | 72851181 | 67689744 | 68920383
MCR006730 | HPR037 | 2017-04-01 | Overhead | 11353191 | 10548828 | 8949594
MCR006731 | HPR037 | 2017-05-01 | Labor | 21359015 | 10082958 | 8396937
MCR006732 | HPR037 | 2017-05-01 | Material | 49178055 | 23215503 | 20064279
MCR006733 | HPR037 | 2017-05-01 | Equipment | 14988126 | 7075450 | 6744388
MCR006734 | HPR037 | 2017-05-01 | Subcontract | 79386072 | 37475813 | 39070363
MCR006735 | HPR037 | 2017-05-01 | Overhead | 12371594 | 5840263 | 9336633
MCR006736 | HPR037 | 2017-06-01 | Labor | 22600336 | 12284261 | 13085794
MCR006737 | HPR037 | 2017-06-01 | Material | 52036135 | 28283891 | 29348408
MCR006738 | HPR037 | 2017-06-01 | Equipment | 15859191 | 8620157 | 9300467
MCR006739 | HPR037 | 2017-06-01 | Subcontract | 83999751 | 45657499 | 44968222
MCR006740 | HPR037 | 2017-06-01 | Overhead | 13090594 | 7115304 | 8209687
MCR006741 | HPR037 | 2017-07-01 | Labor | 23342957 | 11765598 | 13575954
MCR006742 | HPR037 | 2017-07-01 | Material | 53745981 | 27089695 | 28461662
MCR006743 | HPR037 | 2017-07-01 | Equipment | 16380305 | 8256198 | 8789197
MCR006744 | HPR037 | 2017-07-01 | Subcontract | 86759884 | 43729760 | 42369928
MCR006745 | HPR037 | 2017-07-01 | Overhead | 13520735 | 6814884 | 7942281
MCR006746 | HPR037 | 2017-08-01 | Labor | 23606409 | 11804539 | 11942564
MCR006747 | HPR037 | 2017-08-01 | Material | 54352568 | 27179357 | 28030800
MCR006748 | HPR037 | 2017-08-01 | Equipment | 16565176 | 8283525 | 8030337
MCR006749 | HPR037 | 2017-08-01 | Subcontract | 87739071 | 43874497 | 39184158
MCR006750 | HPR037 | 2017-08-01 | Overhead | 13673333 | 6837440 | 8633057
MCR006751 | HPR037 | 2017-09-01 | Labor | 23411788 | 17322411 | 20022574
MCR006752 | HPR037 | 2017-09-01 | Material | 53904461 | 39883977 | 42388721
MCR006753 | HPR037 | 2017-09-01 | Equipment | 16428606 | 12155545 | 12874137
MCR006754 | HPR037 | 2017-09-01 | Subcontract | 87015712 | 64383032 | 57146386
MCR006755 | HPR037 | 2017-09-01 | Overhead | 13560604 | 10033507 | 9181152
MCR006756 | HPR037 | 2017-10-01 | Labor | 22782044 | 19472174 | 19470272
MCR006757 | HPR037 | 2017-10-01 | Material | 52454507 | 44833698 | 40895233
MCR006758 | HPR037 | 2017-10-01 | Equipment | 15986699 | 13664085 | 14070977
MCR006759 | HPR037 | 2017-10-01 | Subcontract | 84675111 | 72373159 | 78758504
MCR006760 | HPR037 | 2017-10-01 | Overhead | 13195843 | 11278696 | 9423024
MCR006761 | HPR037 | 2017-11-01 | Labor | 21742380 | 13261660 | 14411925
MCR006762 | HPR037 | 2017-11-01 | Material | 50060735 | 30534304 | 36733118
MCR006763 | HPR037 | 2017-11-01 | Equipment | 15257143 | 9306021 | 9522376
MCR006764 | HPR037 | 2017-11-01 | Subcontract | 80810945 | 49290247 | 44673111
MCR006765 | HPR037 | 2017-11-01 | Overhead | 12593648 | 7681435 | 8973859
MCR006766 | HPR037 | 2017-12-01 | Labor | 20320784 | 18556890 | 17934933
MCR006767 | HPR037 | 2017-12-01 | Material | 46787580 | 42726303 | 47347451
MCR006768 | HPR037 | 2017-12-01 | Equipment | 14259575 | 13021809 | 13738643
MCR006769 | HPR037 | 2017-12-01 | Subcontract | 75527228 | 68971280 | 64170007
MCR006770 | HPR037 | 2017-12-01 | Overhead | 11770229 | 10748544 | 8637990
MCR006771 | HPR037 | 2018-01-01 | Labor | 18548761 | 13031503 | 14583084
MCR006772 | HPR037 | 2018-01-01 | Material | 42707588 | 30004379 | 30052145
MCR006773 | HPR037 | 2018-01-01 | Equipment | 13016105 | 9144514 | 10012167
MCR006774 | HPR037 | 2018-01-01 | Subcontract | 68941068 | 48434811 | 48847976
MCR006775 | HPR037 | 2018-01-01 | Overhead | 10743836 | 7548123 | 9113026
MCR006776 | HPR037 | 2018-02-01 | Labor | 16462417 | 19111115 | 35659309
MCR006777 | HPR037 | 2018-02-01 | Material | 37903885 | 44002378 | 63553974
MCR006778 | HPR037 | 2018-02-01 | Equipment | 11552068 | 13410721 | 12771326
MCR006779 | HPR037 | 2018-02-01 | Subcontract | 61186653 | 71031193 | 57550915
MCR006780 | HPR037 | 2018-02-01 | Overhead | 9535381 | 11069563 | 9025548
MCR006781 | HPR037 | 2018-03-01 | Labor | 14104084 | 26501023 | 38367293
MCR006782 | HPR037 | 2018-03-01 | Material | 32473942 | 61017268 | 72244460
MCR006783 | HPR037 | 2018-03-01 | Equipment | 9897169 | 18596395 | 19135676
MCR006784 | HPR037 | 2018-03-01 | Subcontract | 52421323 | 98497618 | 97151578
MCR006785 | HPR037 | 2018-03-01 | Overhead | 8169384 | 15349954 | 8285407
MCR006786 | HPR037 | 2018-04-01 | Labor | 11524980 | 17352138 | 19862829
MCR006787 | HPR037 | 2018-04-01 | Material | 26535686 | 39952424 | 50279070
MCR006788 | HPR037 | 2018-04-01 | Equipment | 8087351 | 12176406 | 13635411
MCR006789 | HPR037 | 2018-04-01 | Subcontract | 42835446 | 64493523 | 64305138
MCR006790 | HPR037 | 2018-04-01 | Overhead | 6675513 | 10050727 | 8483594
MCR006791 | HPR037 | 2018-05-01 | Labor | 8789924 | 8663921 | 8920611
MCR006792 | HPR037 | 2018-05-01 | Material | 20238357 | 19948241 | 20307001
MCR006793 | HPR037 | 2018-05-01 | Equipment | 6168098 | 6079678 | 5909659
MCR006794 | HPR037 | 2018-05-01 | Subcontract | 32669932 | 32201609 | 30197512
MCR006795 | HPR037 | 2018-05-01 | Overhead | 5091310 | 5018327 | 8247750
MCR006796 | HPR037 | 2018-06-01 | Labor | 5986854 | 13848556 | 13548395
MCR006797 | HPR037 | 2018-06-01 | Material | 13784429 | 31885602 | 38690402
MCR006798 | HPR037 | 2018-06-01 | Equipment | 4201117 | 9717859 | 9658409
MCR006799 | HPR037 | 2018-06-01 | Subcontract | 22251626 | 51471590 | 48594526
MCR006800 | HPR037 | 2018-06-01 | Overhead | 3467713 | 8021377 | 8625215
MCR006801 | HPR037 | 2018-07-01 | Labor | 3250689 | 8640091 | 8631339
MCR006802 | HPR037 | 2018-07-01 | Material | 7484547 | 19893374 | 19749425
MCR006803 | HPR037 | 2018-07-01 | Equipment | 2281085 | 6062956 | 6447310
MCR006804 | HPR037 | 2018-07-01 | Subcontract | 12081991 | 32113040 | 66360170
MCR006805 | HPR037 | 2018-07-01 | Overhead | 1882868 | 5004524 | 8336823
MCR006806 | HPR037 | 2018-08-01 | Labor | 863750 | 11021530 | 11989844
MCR006807 | HPR037 | 2018-08-01 | Material | 1988741 | 25376517 | 29217638
MCR006808 | HPR037 | 2018-08-01 | Equipment | 606114 | 7734069 | 8652633
MCR006809 | HPR037 | 2018-08-01 | Subcontract | 3210341 | 40964248 | 69528214
MCR006810 | HPR037 | 2018-08-01 | Overhead | 500302 | 6383904 | 9303294
MCR006811 | HPR037 | 2018-09-01 | Labor | 0 | 13474618 | 11424393
MCR006812 | HPR037 | 2018-09-01 | Material | 0 | 31024629 | 28574810
MCR006813 | HPR037 | 2018-09-01 | Equipment | 0 | 9455459 | 11163300
MCR006814 | HPR037 | 2018-09-01 | Subcontract | 0 | 50081758 | 57993053
MCR006815 | HPR037 | 2018-09-01 | Overhead | 0 | 7804785 | 8738900
MCR006816 | HPR037 | 2018-10-01 | Labor | 0 | 12418918 | 15133022
MCR006817 | HPR037 | 2018-10-01 | Material | 0 | 28593933 | 26859277
MCR006818 | HPR037 | 2018-10-01 | Equipment | 0 | 8714649 | 8246447
MCR006819 | HPR037 | 2018-10-01 | Subcontract | 0 | 46157988 | 70496334
MCR006820 | HPR037 | 2018-10-01 | Overhead | 0 | 7193301 | 9346699
MCR006821 | HPR037 | 2018-11-01 | Labor | 0 | 7320814 | 5935862
MCR006822 | HPR037 | 2018-11-01 | Material | 0 | 16855805 | 20276159
MCR006823 | HPR037 | 2018-11-01 | Equipment | 0 | 5137188 | 6100088
MCR006824 | HPR037 | 2018-11-01 | Subcontract | 0 | 27209619 | 34637198
MCR006825 | HPR037 | 2018-11-01 | Overhead | 0 | 4240371 | 8656110
MCR006826 | HPR037 | 2018-12-01 | Labor | 0 | 6290098 | 6637397
MCR006827 | HPR037 | 2018-12-01 | Material | 0 | 14482634 | 15636184
MCR006828 | HPR037 | 2018-12-01 | Equipment | 0 | 4413911 | 5039048
MCR006829 | HPR037 | 2018-12-01 | Subcontract | 0 | 23378708 | 58719149
MCR006830 | HPR037 | 2018-12-01 | Overhead | 0 | 3643358 | 8884720
MCR006831 | HPR037 | 2019-01-01 | Labor | 0 | 5018790 | 4590574
MCR006832 | HPR037 | 2019-01-01 | Material | 0 | 11555511 | 13323475
MCR006833 | HPR037 | 2019-01-01 | Equipment | 0 | 3521804 | 3874548
MCR006834 | HPR037 | 2019-01-01 | Subcontract | 0 | 18653576 | 55356029
MCR006835 | HPR037 | 2019-01-01 | Overhead | 0 | 2906989 | 9019285
MCR006836 | HPR037 | 2019-02-01 | Labor | 0 | 4729879 | 4768209
MCR006837 | HPR037 | 2019-02-01 | Material | 0 | 10890307 | 10469425
MCR006838 | HPR037 | 2019-02-01 | Equipment | 0 | 3319068 | 3065681
MCR006839 | HPR037 | 2019-02-01 | Subcontract | 0 | 17579766 | 34772743
MCR006840 | HPR037 | 2019-02-01 | Overhead | 0 | 2739646 | 9283495
MCR006841 | HPR037 | 2019-03-01 | Labor | 0 | 1840395 | 1680155
MCR006842 | HPR037 | 2019-03-01 | Material | 0 | 4237417 | 4965302
MCR006843 | HPR037 | 2019-03-01 | Equipment | 0 | 1291449 | 2331196
MCR006844 | HPR037 | 2019-03-01 | Subcontract | 0 | 6840284 | 28869492
MCR006845 | HPR037 | 2019-03-01 | Overhead | 0 | 1065996 | 8734446
MCR006846 | HPR037 | 2019-04-01 | Labor | 0 | 444855 | 415479
MCR006847 | HPR037 | 2019-04-01 | Material | 0 | 1024255 | 778243
MCR006848 | HPR037 | 2019-04-01 | Equipment | 0 | 312165 | 436544
MCR006849 | HPR037 | 2019-04-01 | Subcontract | 0 | 1653412 | 28335649
MCR006850 | HPR037 | 2019-04-01 | Overhead | 0 | 257669 | 8199240
MCR006851 | HPR038 | 2016-04-01 | Labor | 3450282 | 2702164 | 3110654
MCR006852 | HPR038 | 2016-04-01 | Material | 7253380 | 5680645 | 5819851
MCR006853 | HPR038 | 2016-04-01 | Equipment | 1694673 | 1327220 | 1280474
MCR006854 | HPR038 | 2016-04-01 | Subcontract | 10435701 | 8172950 | 7233133
MCR006855 | HPR038 | 2016-04-01 | Overhead | 2693909 | 2109794 | 16178374
MCR006856 | HPR038 | 2016-05-01 | Labor | 9766646 | 6893446 | 7534610
MCR006857 | HPR038 | 2016-05-01 | Material | 20532003 | 14491797 | 14573419
MCR006858 | HPR038 | 2016-05-01 | Equipment | 4797077 | 3385850 | 3616055
MCR006859 | HPR038 | 2016-05-01 | Subcontract | 29540138 | 20849875 | 18038299
MCR006860 | HPR038 | 2016-05-01 | Overhead | 7625597 | 5382261 | 16112901
MCR006861 | HPR038 | 2016-06-01 | Labor | 15221852 | 10854968 | 12175002
MCR006862 | HPR038 | 2016-06-01 | Material | 32000250 | 22819936 | 22617213
MCR006863 | HPR038 | 2016-06-01 | Equipment | 7476508 | 5331628 | 5107539
MCR006864 | HPR038 | 2016-06-01 | Subcontract | 46039922 | 32831871 | 38073915
MCR006865 | HPR038 | 2016-06-01 | Overhead | 11884910 | 8475336 | 15082531
MCR006866 | HPR038 | 2016-07-01 | Labor | 19836900 | 6992933 | 6744871
MCR006867 | HPR038 | 2016-07-01 | Material | 41702268 | 14700944 | 15501298
MCR006868 | HPR038 | 2016-07-01 | Equipment | 9743278 | 3434714 | 3735535
MCR006869 | HPR038 | 2016-07-01 | Subcontract | 59998568 | 21150782 | 16296797
MCR006870 | HPR038 | 2016-07-01 | Overhead | 15488244 | 5459938 | 15890702
MCR006871 | HPR038 | 2016-08-01 | Labor | 23633907 | 16736068 | 18542213
MCR006872 | HPR038 | 2016-08-01 | Material | 49684553 | 35183522 | 34954354
MCR006873 | HPR038 | 2016-08-01 | Equipment | 11608251 | 8220244 | 8608174
MCR006874 | HPR038 | 2016-08-01 | Subcontract | 71482971 | 50619810 | 42887733
MCR006875 | HPR038 | 2016-08-01 | Overhead | 18452869 | 13067178 | 14954921
MCR006876 | HPR038 | 2016-09-01 | Labor | 26636251 | 17133724 | 16883783
MCR006877 | HPR038 | 2016-09-01 | Material | 55996253 | 36019497 | 38002851
MCR006878 | HPR038 | 2016-09-01 | Equipment | 13082911 | 8415561 | 8582330
MCR006879 | HPR038 | 2016-09-01 | Subcontract | 80563844 | 51822559 | 51472079
MCR006880 | HPR038 | 2016-09-01 | Overhead | 20797038 | 13377660 | 16059698
MCR006881 | HPR038 | 2016-10-01 | Labor | 28868746 | 13874714 | 17337762
MCR006882 | HPR038 | 2016-10-01 | Material | 60689532 | 29168220 | 26061486
MCR006883 | HPR038 | 2016-10-01 | Equipment | 14179444 | 6814835 | 7839860
MCR006884 | HPR038 | 2016-10-01 | Subcontract | 87316234 | 41965378 | 48603667
MCR006885 | HPR038 | 2016-10-01 | Overhead | 22540124 | 10833092 | 15382857
MCR006886 | HPR038 | 2016-11-01 | Labor | 30357851 | 16799478 | 18366991
MCR006887 | HPR038 | 2016-11-01 | Material | 63820015 | 35316826 | 39568328
MCR006888 | HPR038 | 2016-11-01 | Equipment | 14910847 | 8251389 | 7646174
MCR006889 | HPR038 | 2016-11-01 | Subcontract | 91820174 | 50811600 | 47330000
MCR006890 | HPR038 | 2016-11-01 | Overhead | 23702787 | 13116688 | 16216067
MCR006891 | HPR038 | 2016-12-01 | Labor | 31131937 | 25411691 | 27343659
MCR006892 | HPR038 | 2016-12-01 | Material | 65447344 | 53421914 | 53135132
MCR006893 | HPR038 | 2016-12-01 | Equipment | 15291054 | 12481445 | 13236615
MCR006894 | HPR038 | 2016-12-01 | Subcontract | 94161470 | 76860048 | 72713665
MCR006895 | HPR038 | 2016-12-01 | Overhead | 24307178 | 19840927 | 15135382
MCR006896 | HPR038 | 2017-01-01 | Labor | 31221616 | 27755265 | 30576456
MCR006897 | HPR038 | 2017-01-01 | Material | 65635872 | 58348709 | 67849260
MCR006898 | HPR038 | 2017-01-01 | Equipment | 15335102 | 13632536 | 14797844
MCR006899 | HPR038 | 2017-01-01 | Subcontract | 94432713 | 83948406 | 84190881
MCR006900 | HPR038 | 2017-01-01 | Overhead | 24377197 | 21670741 | 17095689
MCR006901 | HPR038 | 2017-02-01 | Labor | 30660169 | 19839121 | 21868047
MCR006902 | HPR038 | 2017-02-01 | Material | 64455565 | 41706938 | 41912517
MCR006903 | HPR038 | 2017-02-01 | Equipment | 15059336 | 9744369 | 9819987
MCR006904 | HPR038 | 2017-02-01 | Subcontract | 92734563 | 60005286 | 58109448
MCR006905 | HPR038 | 2017-02-01 | Overhead | 23938831 | 15489979 | 16212038
MCR006906 | HPR038 | 2017-03-01 | Labor | 29484107 | 21127074 | 19473950
MCR006907 | HPR038 | 2017-03-01 | Material | 61983180 | 44414547 | 36347379
MCR006908 | HPR038 | 2017-03-01 | Equipment | 14481691 | 10376972 | 12644863
MCR006909 | HPR038 | 2017-03-01 | Subcontract | 89177453 | 63900822 | 60042162
MCR006910 | HPR038 | 2017-03-01 | Overhead | 23020586 | 16495586 | 14177480
MCR006911 | HPR038 | 2017-04-01 | Labor | 27733930 | 26932909 | 32639225
MCR006912 | HPR038 | 2017-04-01 | Material | 58303857 | 56619905 | 61981206
MCR006913 | HPR038 | 2017-04-01 | Equipment | 13622057 | 13228620 | 13546618
MCR006914 | HPR038 | 2017-04-01 | Subcontract | 83883877 | 81461114 | 78644377
MCR006915 | HPR038 | 2017-04-01 | Overhead | 21654083 | 21028662 | 14809881
MCR006916 | HPR038 | 2017-05-01 | Labor | 25455179 | 19533023 | 23508722
MCR006917 | HPR038 | 2017-05-01 | Material | 53513336 | 41063440 | 39628970
MCR006918 | HPR038 | 2017-05-01 | Equipment | 12502804 | 9594023 | 8714594
MCR006919 | HPR038 | 2017-05-01 | Subcontract | 76991581 | 59079463 | 54604260
MCR006920 | HPR038 | 2017-05-01 | Overhead | 19874881 | 15250983 | 14370495
MCR006921 | HPR038 | 2017-06-01 | Labor | 22699967 | 20526994 | 24356892
MCR006922 | HPR038 | 2017-06-01 | Material | 47721171 | 43153025 | 39598104
MCR006923 | HPR038 | 2017-06-01 | Equipment | 11149529 | 10082231 | 13836702
MCR006924 | HPR038 | 2017-06-01 | Subcontract | 68658183 | 62085824 | 62414608
MCR006925 | HPR038 | 2017-06-01 | Overhead | 17723668 | 16027056 | 14991498
MCR006926 | HPR038 | 2017-07-01 | Labor | 19529302 | 24304502 | 24679199
MCR006927 | HPR038 | 2017-07-01 | Material | 41055617 | 51094318 | 58496594
MCR006928 | HPR038 | 2017-07-01 | Equipment | 9592195 | 11937627 | 8894902
MCR006929 | HPR038 | 2017-07-01 | Subcontract | 59068208 | 73511251 | 74193902
MCR006930 | HPR038 | 2017-07-01 | Overhead | 15248078 | 18976457 | 16404619
MCR006931 | HPR038 | 2017-08-01 | Labor | 16016861 | 12311050 | 13542040
MCR006932 | HPR038 | 2017-08-01 | Material | 33671564 | 25880995 | 23208658
MCR006933 | HPR038 | 2017-08-01 | Equipment | 7866992 | 6046811 | 6996126
MCR006934 | HPR038 | 2017-08-01 | Subcontract | 48444502 | 37235927 | 35635054
MCR006935 | HPR038 | 2017-08-01 | Overhead | 12505636 | 9612215 | 15761189
MCR006936 | HPR038 | 2017-09-01 | Labor | 12255682 | 20978038 | 23377425
MCR006937 | HPR038 | 2017-09-01 | Material | 25764597 | 44101234 | 52836816
MCR006938 | HPR038 | 2017-09-01 | Equipment | 6019616 | 10303770 | 9989711
MCR006939 | HPR038 | 2017-09-01 | Subcontract | 37068461 | 63450047 | 59144287
MCR006940 | HPR038 | 2017-09-01 | Overhead | 9568985 | 16379222 | 15435272
MCR006941 | HPR038 | 2017-10-01 | Labor | 8371653 | 13404630 | 16521843
MCR006942 | HPR038 | 2017-10-01 | Material | 17599369 | 28179981 | 21106912
MCR006943 | HPR038 | 2017-10-01 | Equipment | 4111900 | 6583944 | 8897482
MCR006944 | HPR038 | 2017-10-01 | Subcontract | 25320851 | 40543563 | 37514748
MCR006945 | HPR038 | 2017-10-01 | Overhead | 6536415 | 10466060 | 15094902
MCR006946 | HPR038 | 2017-11-01 | Labor | 4557280 | 16266882 | 17735759
MCR006947 | HPR038 | 2017-11-01 | Material | 9580575 | 34197171 | 40170820
MCR006948 | HPR038 | 2017-11-01 | Equipment | 2238396 | 7989794 | 6567633
MCR006949 | HPR038 | 2017-11-01 | Subcontract | 13783921 | 49200712 | 52397268
MCR006950 | HPR038 | 2017-11-01 | Overhead | 3558231 | 12700847 | 14949409
MCR006951 | HPR038 | 2017-12-01 | Labor | 1213487 | 8348157 | 10525708
MCR006952 | HPR038 | 2017-12-01 | Material | 2551061 | 17549974 | 17722820
MCR006953 | HPR038 | 2017-12-01 | Equipment | 596028 | 4100359 | 5064730
MCR006954 | HPR038 | 2017-12-01 | Subcontract | 3670305 | 25249785 | 24705496
MCR006955 | HPR038 | 2017-12-01 | Overhead | 947466 | 6518070 | 15754299
MCR006956 | HPR038 | 2018-01-01 | Labor | 0 | 18658279 | 24405262
MCR006957 | HPR038 | 2018-01-01 | Material | 0 | 39224504 | 40283156
MCR006958 | HPR038 | 2018-01-01 | Equipment | 0 | 9164375 | 8515609
MCR006959 | HPR038 | 2018-01-01 | Subcontract | 0 | 56433718 | 54990764
MCR006960 | HPR038 | 2018-01-01 | Overhead | 0 | 14568001 | 15129940
MCR006961 | HPR038 | 2018-02-01 | Labor | 0 | 14012189 | 15962075
MCR006962 | HPR038 | 2018-02-01 | Material | 0 | 29457227 | 23013165
MCR006963 | HPR038 | 2018-02-01 | Equipment | 0 | 6882358 | 7510290
MCR006964 | HPR038 | 2018-02-01 | Subcontract | 0 | 42381182 | 37796999
MCR006965 | HPR038 | 2018-02-01 | Overhead | 0 | 10940429 | 15959508
MCR006966 | HPR038 | 2018-03-01 | Labor | 0 | 12967392 | 13373739
MCR006967 | HPR038 | 2018-03-01 | Material | 0 | 27260796 | 29614834
MCR006968 | HPR038 | 2018-03-01 | Equipment | 0 | 6369186 | 6783234
MCR006969 | HPR038 | 2018-03-01 | Subcontract | 0 | 39221097 | 40500547
MCR006970 | HPR038 | 2018-03-01 | Overhead | 0 | 10124674 | 15770719
MCR006971 | HPR038 | 2018-04-01 | Labor | 0 | 13794336 | 16745725
MCR006972 | HPR038 | 2018-04-01 | Material | 0 | 28999245 | 27156368
MCR006973 | HPR038 | 2018-04-01 | Equipment | 0 | 6775356 | 8031367
MCR006974 | HPR038 | 2018-04-01 | Subcontract | 0 | 41722267 | 36997080
MCR006975 | HPR038 | 2018-04-01 | Overhead | 0 | 10770335 | 16284602
MCR006976 | HPR038 | 2018-05-01 | Labor | 0 | 7646776 | 8866699
MCR006977 | HPR038 | 2018-05-01 | Material | 0 | 16075490 | 19692836
MCR006978 | HPR038 | 2018-05-01 | Equipment | 0 | 3755862 | 4228662
MCR006979 | HPR038 | 2018-05-01 | Subcontract | 0 | 23128392 | 21147187
MCR006980 | HPR038 | 2018-05-01 | Overhead | 0 | 5970446 | 15475005
MCR006981 | HPR038 | 2018-06-01 | Labor | 0 | 1992402 | 2074009
MCR006982 | HPR038 | 2018-06-01 | Material | 0 | 4188542 | 4317158
MCR006983 | HPR038 | 2018-06-01 | Equipment | 0 | 978607 | 1093900
MCR006984 | HPR038 | 2018-06-01 | Subcontract | 0 | 6026207 | 7360187
MCR006985 | HPR038 | 2018-06-01 | Overhead | 0 | 1555627 | 15502182
MCR006986 | HPR038 | 2018-07-01 | Labor | 0 | 305397 | 486358
MCR006987 | HPR038 | 2018-07-01 | Material | 0 | 642022 | 435285
MCR006988 | HPR038 | 2018-07-01 | Equipment | 0 | 150001 | 196367
MCR006989 | HPR038 | 2018-07-01 | Subcontract | 0 | 923701 | 748681
MCR006990 | HPR038 | 2018-07-01 | Overhead | 0 | 238447 | 16038849
MCR006991 | HPR039 | 2019-07-01 | Labor | 4955594 | 1977529 | 1912702
MCR006992 | HPR039 | 2019-07-01 | Material | 11562509 | 4614017 | 5099779
MCR006993 | HPR039 | 2019-07-01 | Equipment | 2541271 | 1014094 | 1069649
MCR006994 | HPR039 | 2019-07-01 | Subcontract | 21749584 | 8679167 | 8564849
MCR006995 | HPR039 | 2019-07-01 | Overhead | 4307900 | 1719067 | 25615343
MCR006996 | HPR039 | 2019-08-01 | Labor | 14027705 | 4389241 | 5228494
MCR006997 | HPR039 | 2019-08-01 | Material | 32729771 | 10241079 | 10248074
MCR006998 | HPR039 | 2019-08-01 | Equipment | 7193526 | 2250840 | 2269459
MCR006999 | HPR039 | 2019-08-01 | Subcontract | 61566129 | 19263917 | 20860772
MCR007000 | HPR039 | 2019-08-01 | Overhead | 12194291 | 3815569 | 24749800
MCR007001 | HPR039 | 2019-09-01 | Labor | 21862947 | 16732108 | 20288988
MCR007002 | HPR039 | 2019-09-01 | Material | 51011140 | 39039747 | 37665290
MCR007003 | HPR039 | 2019-09-01 | Equipment | 11211504 | 8580367 | 9189175
MCR007004 | HPR039 | 2019-09-01 | Subcontract | 95954182 | 73435469 | 83658530
MCR007005 | HPR039 | 2019-09-01 | Overhead | 19005470 | 14545230 | 23309183
MCR007006 | HPR039 | 2019-10-01 | Labor | 28491480 | 20675676 | 23264110
MCR007007 | HPR039 | 2019-10-01 | Material | 66476988 | 48240973 | 48998397
MCR007008 | HPR039 | 2019-10-01 | Equipment | 14610672 | 10602662 | 11067002
MCR007009 | HPR039 | 2019-10-01 | Subcontract | 125046117 | 90743377 | 88900108
MCR007010 | HPR039 | 2019-10-01 | Overhead | 24767657 | 17973375 | 24672974
MCR007011 | HPR039 | 2019-11-01 | Labor | 33945071 | 14413715 | 17890464
MCR007012 | HPR039 | 2019-11-01 | Material | 79201435 | 33630418 | 30127527
MCR007013 | HPR039 | 2019-11-01 | Equipment | 17407319 | 7391475 | 8340880
MCR007014 | HPR039 | 2019-11-01 | Subcontract | 148981357 | 63260284 | 63721930
MCR007015 | HPR039 | 2019-11-01 | Overhead | 29508466 | 12529849 | 25923715
MCR007016 | HPR039 | 2019-12-01 | Labor | 38257299 | 15806918 | 15465323
MCR007017 | HPR039 | 2019-12-01 | Material | 89262826 | 36881071 | 39580481
MCR007018 | HPR039 | 2019-12-01 | Equipment | 19618666 | 8105921 | 7946223
MCR007019 | HPR039 | 2019-12-01 | Subcontract | 167907273 | 69374905 | 69446099
MCR007020 | HPR039 | 2019-12-01 | Overhead | 33257088 | 13740961 | 27071483
MCR007021 | HPR039 | 2020-01-01 | Labor | 41463802 | 25443600 | 30002144
MCR007022 | HPR039 | 2020-01-01 | Material | 96744315 | 59365603 | 59051033
MCR007023 | HPR039 | 2020-01-01 | Equipment | 21262988 | 13047693 | 13345240
MCR007024 | HPR039 | 2020-01-01 | Subcontract | 181980279 | 111669291 | 118059599
MCR007025 | HPR039 | 2020-01-01 | Overhead | 36044503 | 22118133 | 25287476
MCR007026 | HPR039 | 2020-02-01 | Labor | 43602585 | 27557419 | 30797526
MCR007027 | HPR039 | 2020-02-01 | Material | 101734573 | 64297616 | 63695425
MCR007028 | HPR039 | 2020-02-01 | Equipment | 22359774 | 14131677 | 14312154
MCR007029 | HPR039 | 2020-02-01 | Subcontract | 191367173 | 120946622 | 128685466
MCR007030 | HPR039 | 2020-02-01 | Overhead | 37903748 | 23955677 | 25061852
MCR007031 | HPR039 | 2020-03-01 | Labor | 44714394 | 24653629 | 30554766
MCR007032 | HPR039 | 2020-03-01 | Material | 104328674 | 57522425 | 66641019
MCR007033 | HPR039 | 2020-03-01 | Equipment | 22929920 | 12642589 | 16207202
MCR007034 | HPR039 | 2020-03-01 | Subcontract | 196246790 | 108202193 | 123581997
MCR007035 | HPR039 | 2020-03-01 | Overhead | 38870244 | 21431411 | 25350794
MCR007036 | HPR039 | 2020-04-01 | Labor | 44843199 | 26130082 | 27604125
MCR007037 | HPR039 | 2020-04-01 | Material | 104629204 | 60967319 | 64321003
MCR007038 | HPR039 | 2020-04-01 | Equipment | 22995972 | 13399727 | 13382803
MCR007039 | HPR039 | 2020-04-01 | Subcontract | 196812100 | 114682189 | 115383104
MCR007040 | HPR039 | 2020-04-01 | Overhead | 38982214 | 22714892 | 24206213
MCR007041 | HPR039 | 2020-05-01 | Labor | 44036800 | 45649439 | 52805464
MCR007042 | HPR039 | 2020-05-01 | Material | 102747694 | 106510340 | 106752382
MCR007043 | HPR039 | 2020-05-01 | Equipment | 22582443 | 23409418 | 24076170
MCR007044 | HPR039 | 2020-05-01 | Subcontract | 193272898 | 200350600 | 206484881
MCR007045 | HPR039 | 2020-05-01 | Overhead | 38281211 | 39683079 | 25868909
MCR007046 | HPR039 | 2020-06-01 | Labor | 42347637 | 25697025 | 29754426
MCR007047 | HPR039 | 2020-06-01 | Material | 98806501 | 59956901 | 59950515
MCR007048 | HPR039 | 2020-06-01 | Equipment | 21716227 | 13177652 | 13821505
MCR007049 | HPR039 | 2020-06-01 | Subcontract | 185859341 | 112781548 | 125421642
MCR007050 | HPR039 | 2020-06-01 | Overhead | 36812821 | 22338436 | 24021392
MCR007051 | HPR039 | 2020-07-01 | Labor | 39833881 | 23122505 | 27451795
MCR007052 | HPR039 | 2020-07-01 | Material | 92941344 | 53949970 | 56290620
MCR007053 | HPR039 | 2020-07-01 | Equipment | 20427151 | 11857416 | 13478944
MCR007054 | HPR039 | 2020-07-01 | Subcontract | 174826726 | 101482249 | 94288609
MCR007055 | HPR039 | 2020-07-01 | Overhead | 34627611 | 20100404 | 25568869
MCR007056 | HPR039 | 2020-08-01 | Labor | 36560940 | 28538382 | 33413488
MCR007057 | HPR039 | 2020-08-01 | Material | 85304844 | 66586422 | 64992736
MCR007058 | HPR039 | 2020-08-01 | Equipment | 18748759 | 14634724 | 15103331
MCR007059 | HPR039 | 2020-08-01 | Subcontract | 160462135 | 125251967 | 156030620
MCR007060 | HPR039 | 2020-08-01 | Overhead | 31782443 | 24808429 | 24590739
MCR007061 | HPR039 | 2020-09-01 | Labor | 32603665 | 35274328 | 41433982
MCR007062 | HPR039 | 2020-09-01 | Material | 76071636 | 82302888 | 81337494
MCR007063 | HPR039 | 2020-09-01 | Equipment | 16719435 | 18088973 | 18431316
MCR007064 | HPR039 | 2020-09-01 | Subcontract | 143094069 | 154815326 | 172178997
MCR007065 | HPR039 | 2020-09-01 | Overhead | 28342382 | 30663990 | 26305995
MCR007066 | HPR039 | 2020-10-01 | Labor | 28049680 | 42270341 | 43456690
MCR007067 | HPR039 | 2020-10-01 | Material | 65446172 | 98626151 | 102491021
MCR007068 | HPR039 | 2020-10-01 | Equipment | 14384113 | 21676588 | 20547317
MCR007069 | HPR039 | 2020-10-01 | Subcontract | 123107106 | 185520095 | 178628843
MCR007070 | HPR039 | 2020-10-01 | Overhead | 24383600 | 36745628 | 23876541
MCR007071 | HPR039 | 2020-11-01 | Labor | 23004808 | 27766321 | 34152432
MCR007072 | HPR039 | 2020-11-01 | Material | 53675358 | 64785031 | 72723503
MCR007073 | HPR039 | 2020-11-01 | Equipment | 11797060 | 14238804 | 18713492
MCR007074 | HPR039 | 2020-11-01 | Subcontract | 100965691 | 121863472 | 134545340
MCR007075 | HPR039 | 2020-11-01 | Overhead | 19998091 | 24137276 | 26291878
MCR007076 | HPR039 | 2020-12-01 | Labor | 17602675 | 31192081 | 41134160
MCR007077 | HPR039 | 2020-12-01 | Material | 41070975 | 72778095 | 69038539
MCR007078 | HPR039 | 2020-12-01 | Equipment | 9026801 | 15995563 | 18656635
MCR007079 | HPR039 | 2020-12-01 | Subcontract | 77256297 | 136898774 | 146308010
MCR007080 | HPR039 | 2020-12-01 | Overhead | 15302014 | 27115291 | 24610099
MCR007081 | HPR039 | 2021-01-01 | Labor | 12024095 | 30779661 | 37086288
MCR007082 | HPR039 | 2021-01-01 | Material | 28054901 | 71815828 | 89668946
MCR007083 | HPR039 | 2021-01-01 | Equipment | 6166058 | 15784071 | 14990695
MCR007084 | HPR039 | 2021-01-01 | Subcontract | 52772494 | 135088707 | 129228417
MCR007085 | HPR039 | 2021-01-01 | Overhead | 10452552 | 26756774 | 26680545
MCR007086 | HPR039 | 2021-02-01 | Labor | 6545561 | 18543620 | 20861179
MCR007087 | HPR039 | 2021-02-01 | Material | 15272257 | 43266410 | 38556117
MCR007088 | HPR039 | 2021-02-01 | Equipment | 3356619 | 9509325 | 11218159
MCR007089 | HPR039 | 2021-02-01 | Subcontract | 28727783 | 81386006 | 128843311
MCR007090 | HPR039 | 2021-02-01 | Overhead | 5690060 | 16119978 | 26470384
MCR007091 | HPR039 | 2021-03-01 | Labor | 1742915 | 31592602 | 37292228
MCR007092 | HPR039 | 2021-03-01 | Material | 4066610 | 73712599 | 76815955
MCR007093 | HPR039 | 2021-03-01 | Equipment | 893782 | 16200953 | 15763127
MCR007094 | HPR039 | 2021-03-01 | Subcontract | 7649472 | 138656617 | 196714837
MCR007095 | HPR039 | 2021-03-01 | Overhead | 1515117 | 27463464 | 24648116
MCR007096 | HPR039 | 2021-04-01 | Labor | 0 | 13227688 | 13639095
MCR007097 | HPR039 | 2021-04-01 | Material | 0 | 30863151 | 39816843
MCR007098 | HPR039 | 2021-04-01 | Equipment | 0 | 6783270 | 8084466
MCR007099 | HPR039 | 2021-04-01 | Subcontract | 0 | 58054935 | 106672042
MCR007100 | HPR039 | 2021-04-01 | Overhead | 0 | 11498835 | 23546396
MCR007101 | HPR039 | 2021-05-01 | Labor | 0 | 28194177 | 31039770
MCR007102 | HPR039 | 2021-05-01 | Material | 0 | 65783314 | 66737080
MCR007103 | HPR039 | 2021-05-01 | Equipment | 0 | 14458212 | 15013824
MCR007104 | HPR039 | 2021-05-01 | Subcontract | 0 | 123741285 | 202005202
MCR007105 | HPR039 | 2021-05-01 | Overhead | 0 | 24509211 | 23311623
MCR007106 | HPR039 | 2021-06-01 | Labor | 0 | 14827553 | 20378663
MCR007107 | HPR039 | 2021-06-01 | Material | 0 | 34595994 | 43575752
MCR007108 | HPR039 | 2021-06-01 | Equipment | 0 | 7603694 | 8047236
MCR007109 | HPR039 | 2021-06-01 | Subcontract | 0 | 65076574 | 76475352
MCR007110 | HPR039 | 2021-06-01 | Overhead | 0 | 12889599 | 24615581
MCR007111 | HPR039 | 2021-07-01 | Labor | 0 | 12315161 | 12820043
MCR007112 | HPR039 | 2021-07-01 | Material | 0 | 28734022 | 32158403
MCR007113 | HPR039 | 2021-07-01 | Equipment | 0 | 6315319 | 7295355
MCR007114 | HPR039 | 2021-07-01 | Subcontract | 0 | 54049951 | 131715700
MCR007115 | HPR039 | 2021-07-01 | Overhead | 0 | 10705575 | 23641535
MCR007116 | HPR039 | 2021-08-01 | Labor | 0 | 5407152 | 6419514
MCR007117 | HPR039 | 2021-08-01 | Material | 0 | 12616093 | 13333623
MCR007118 | HPR039 | 2021-08-01 | Equipment | 0 | 2772833 | 3506777
MCR007119 | HPR039 | 2021-08-01 | Subcontract | 0 | 23731422 | 69324049
MCR007120 | HPR039 | 2021-08-01 | Overhead | 0 | 4700440 | 24415229
MCR007121 | HPR039 | 2021-09-01 | Labor | 0 | 3897548 | 4010506
MCR007122 | HPR039 | 2021-09-01 | Material | 0 | 9093850 | 10718522
MCR007123 | HPR039 | 2021-09-01 | Equipment | 0 | 1998695 | 2438110
MCR007124 | HPR039 | 2021-09-01 | Subcontract | 0 | 17105929 | 47909519
MCR007125 | HPR039 | 2021-09-01 | Overhead | 0 | 3388140 | 24655039
MCR007126 | HPR039 | 2021-10-01 | Labor | 0 | 3873819 | 5020520
MCR007127 | HPR039 | 2021-10-01 | Material | 0 | 9038486 | 11681436
MCR007128 | HPR039 | 2021-10-01 | Equipment | 0 | 1986527 | 2519672
MCR007129 | HPR039 | 2021-10-01 | Subcontract | 0 | 17001786 | 91994984
MCR007130 | HPR039 | 2021-10-01 | Overhead | 0 | 3367513 | 24496822
MCR007131 | HPR039 | 2021-11-01 | Labor | 0 | 567418 | 427234
MCR007132 | HPR039 | 2021-11-01 | Material | 0 | 1323913 | 1453357
MCR007133 | HPR039 | 2021-11-01 | Equipment | 0 | 290977 | 364879
MCR007134 | HPR039 | 2021-11-01 | Subcontract | 0 | 2490339 | 80299089
MCR007135 | HPR039 | 2021-11-01 | Overhead | 0 | 493257 | 27177580
MCR007136 | HPR040 | 2019-05-01 | Labor | 13205129 | 8923082 | 9193965
MCR007137 | HPR040 | 2019-05-01 | Material | 34718685 | 23460405 | 20727272
MCR007138 | HPR040 | 2019-05-01 | Equipment | 14227850 | 9614164 | 10038300
MCR007139 | HPR040 | 2019-05-01 | Subcontract | 26055906 | 17606718 | 17711617
MCR007140 | HPR040 | 2019-05-01 | Overhead | 10977734 | 7417967 | 59153301
MCR007141 | HPR040 | 2019-06-01 | Labor | 37137499 | 18673761 | 20108204
MCR007142 | HPR040 | 2019-06-01 | Material | 97641240 | 49096714 | 47999674
MCR007143 | HPR040 | 2019-06-01 | Equipment | 40013755 | 20120022 | 20113964
MCR007144 | HPR040 | 2019-06-01 | Subcontract | 73278437 | 36846424 | 36144238
MCR007145 | HPR040 | 2019-06-01 | Overhead | 30873275 | 15523936 | 60212567
MCR007146 | HPR040 | 2019-07-01 | Labor | 57424587 | 16028655 | 16060273
MCR007147 | HPR040 | 2019-07-01 | Material | 150979682 | 42142250 | 49464137
MCR007148 | HPR040 | 2019-07-01 | Equipment | 61872053 | 17270056 | 18175808
MCR007149 | HPR040 | 2019-07-01 | Subcontract | 113308220 | 31627192 | 34207019
MCR007150 | HPR040 | 2019-07-01 | Overhead | 47738407 | 13324998 | 55935412
MCR007151 | HPR040 | 2019-08-01 | Labor | 74166090 | 28130892 | 29937839
MCR007152 | HPR040 | 2019-08-01 | Material | 194996139 | 73961230 | 71354646
MCR007153 | HPR040 | 2019-08-01 | Equipment | 79910166 | 30309596 | 31868295
MCR007154 | HPR040 | 2019-08-01 | Subcontract | 146341979 | 55506908 | 53845379
MCR007155 | HPR040 | 2019-08-01 | Overhead | 61656012 | 23385871 | 56064666
MCR007156 | HPR040 | 2019-09-01 | Labor | 87467700 | 54101286 | 59515526
MCR007157 | HPR040 | 2019-09-01 | Material | 229968492 | 142242119 | 138177305
MCR007158 | HPR040 | 2019-09-01 | Equipment | 94241970 | 58291366 | 59471513
MCR007159 | HPR040 | 2019-09-01 | Subcontract | 172588259 | 106750797 | 102728331
MCR007160 | HPR040 | 2019-09-01 | Overhead | 72713953 | 44975669 | 61217793
MCR007161 | HPR040 | 2019-10-01 | Labor | 97441974 | 55051065 | 51868120
MCR007162 | HPR040 | 2019-10-01 | Material | 256192673 | 144739262 | 142354754
MCR007163 | HPR040 | 2019-10-01 | Equipment | 104988740 | 59314705 | 71855182
MCR007164 | HPR040 | 2019-10-01 | Subcontract | 192269154 | 108624869 | 118449958
MCR007165 | HPR040 | 2019-10-01 | Overhead | 81005801 | 45765243 | 59366078
MCR007166 | HPR040 | 2019-11-01 | Labor | 104209419 | 78643722 | 88463198
MCR007167 | HPR040 | 2019-11-01 | Material | 273985517 | 206768650 | 212917878
MCR007168 | HPR040 | 2019-11-01 | Equipment | 112280316 | 84734586 | 74403700
MCR007169 | HPR040 | 2019-11-01 | Subcontract | 205622444 | 155177090 | 162676800
MCR007170 | HPR040 | 2019-11-01 | Overhead | 86631737 | 65378373 | 57065204
MCR007171 | HPR040 | 2019-12-01 | Labor | 107899859 | 78667899 | 81114892
MCR007172 | HPR040 | 2019-12-01 | Material | 283688354 | 206832215 | 238253369
MCR007173 | HPR040 | 2019-12-01 | Equipment | 116256575 | 84760635 | 98016061
MCR007174 | HPR040 | 2019-12-01 | Subcontract | 212904293 | 155224794 | 160757481
MCR007175 | HPR040 | 2019-12-01 | Overhead | 89699686 | 65398472 | 55537964
MCR007176 | HPR040 | 2020-01-01 | Labor | 108654185 | 134401838 | 138628715
MCR007177 | HPR040 | 2020-01-01 | Material | 285671613 | 353366876 | 344581541
MCR007178 | HPR040 | 2020-01-01 | Equipment | 117069323 | 144811101 | 143706999
MCR007179 | HPR040 | 2020-01-01 | Subcontract | 214392703 | 265197086 | 284751215
MCR007180 | HPR040 | 2020-01-01 | Overhead | 90326775 | 111731403 | 56031145
MCR007181 | HPR040 | 2020-02-01 | Labor | 106626657 | 112413606 | 129246771
MCR007182 | HPR040 | 2020-02-01 | Material | 280340873 | 295555816 | 316321437
MCR007183 | HPR040 | 2020-02-01 | Equipment | 114884765 | 121119907 | 126407249
MCR007184 | HPR040 | 2020-02-01 | Subcontract | 210392054 | 221810664 | 206221742
MCR007185 | HPR040 | 2020-02-01 | Overhead | 88641243 | 93452071 | 60879814
MCR007186 | HPR040 | 2020-03-01 | Labor | 101987999 | 71191234 | 67246010
MCR007187 | HPR040 | 2020-03-01 | Material | 268144999 | 187174703 | 183604885
MCR007188 | HPR040 | 2020-03-01 | Equipment | 109886849 | 76704911 | 74284393
MCR007189 | HPR040 | 2020-03-01 | Subcontract | 201239214 | 140472096 | 140762918
MCR007190 | HPR040 | 2020-03-01 | Overhead | 84785019 | 59182945 | 54552212
MCR007191 | HPR040 | 2020-04-01 | Labor | 94929706 | 86438813 | 93791341
MCR007192 | HPR040 | 2020-04-01 | Material | 249587462 | 227263362 | 260693754
MCR007193 | HPR040 | 2020-04-01 | Equipment | 102281899 | 93133397 | 97315285
MCR007194 | HPR040 | 2020-04-01 | Subcontract | 187312033 | 170558095 | 170858876
MCR007195 | HPR040 | 2020-04-01 | Overhead | 78917294 | 71858615 | 55438027
MCR007196 | HPR040 | 2020-05-01 | Labor | 85670261 | 94640162 | 91387635
MCR007197 | HPR040 | 2020-05-01 | Material | 225242697 | 248826200 | 231650829
MCR007198 | HPR040 | 2020-05-01 | Equipment | 92305321 | 101969931 | 93439403
MCR007199 | HPR040 | 2020-05-01 | Subcontract | 169041614 | 186740715 | 187904453
MCR007200 | HPR040 | 2020-05-01 | Overhead | 71219699 | 78676589 | 57427339
MCR007201 | HPR040 | 2020-06-01 | Labor | 74464581 | 66518974 | 88055964
MCR007202 | HPR040 | 2020-06-01 | Material | 195780928 | 174890482 | 163163118
MCR007203 | HPR040 | 2020-06-01 | Equipment | 80231775 | 71670790 | 87919137
MCR007204 | HPR040 | 2020-06-01 | Subcontract | 146930953 | 131252954 | 142122898
MCR007205 | HPR040 | 2020-06-01 | Overhead | 61904155 | 55298785 | 55987289
MCR007206 | HPR040 | 2020-07-01 | Labor | 61619307 | 59898341 | 54177455
MCR007207 | HPR040 | 2020-07-01 | Material | 162008366 | 157483632 | 154601038
MCR007208 | HPR040 | 2020-07-01 | Equipment | 66391650 | 64537396 | 61615475
MCR007209 | HPR040 | 2020-07-01 | Subcontract | 121585099 | 118189347 | 119823217
MCR007210 | HPR040 | 2020-07-01 | Overhead | 51225577 | 49794897 | 56568905
MCR007211 | HPR040 | 2020-08-01 | Labor | 47519820 | 51881894 | 50504023
MCR007212 | HPR040 | 2020-08-01 | Material | 124938249 | 136406934 | 166373541
MCR007213 | HPR040 | 2020-08-01 | Equipment | 51200174 | 55900085 | 61128849
MCR007214 | HPR040 | 2020-08-01 | Subcontract | 93764475 | 102371569 | 110239326
MCR007215 | HPR040 | 2020-08-01 | Overhead | 39504342 | 43130636 | 60880741
MCR007216 | HPR040 | 2020-09-01 | Labor | 32684589 | 56023301 | 63462719
MCR007217 | HPR040 | 2020-09-01 | Material | 85933729 | 147295448 | 161434936
MCR007218 | HPR040 | 2020-09-01 | Equipment | 35215972 | 60362240 | 55954790
MCR007219 | HPR040 | 2020-09-01 | Subcontract | 64492107 | 110543252 | 97575019
MCR007220 | HPR040 | 2020-09-01 | Overhead | 27171466 | 46573486 | 57335329
MCR007221 | HPR040 | 2020-10-01 | Labor | 17900664 | 44459458 | 45971707
MCR007222 | HPR040 | 2020-10-01 | Material | 47064102 | 116892001 | 91466246
MCR007223 | HPR040 | 2020-10-01 | Equipment | 19287049 | 47902790 | 51224220
MCR007224 | HPR040 | 2020-10-01 | Subcontract | 35320975 | 87725874 | 93343102
MCR007225 | HPR040 | 2020-10-01 | Overhead | 14881242 | 36960191 | 55579698
MCR007226 | HPR040 | 2020-11-01 | Labor | 4790049 | 58902118 | 73524721
MCR007227 | HPR040 | 2020-11-01 | Material | 12593910 | 154864381 | 159949093
MCR007228 | HPR040 | 2020-11-01 | Equipment | 5161033 | 63464017 | 63849379
MCR007229 | HPR040 | 2020-11-01 | Subcontract | 9451560 | 116223635 | 111680516
MCR007230 | HPR040 | 2020-11-01 | Overhead | 3982080 | 48966714 | 54737554
MCR007231 | HPR040 | 2020-12-01 | Labor | 0 | 48696404 | 46455644
MCR007232 | HPR040 | 2020-12-01 | Material | 0 | 128031703 | 139563670
MCR007233 | HPR040 | 2020-12-01 | Equipment | 0 | 52467883 | 54402448
MCR007234 | HPR040 | 2020-12-01 | Subcontract | 0 | 96086071 | 101374652
MCR007235 | HPR040 | 2020-12-01 | Overhead | 0 | 40482464 | 61036419
MCR007236 | HPR040 | 2021-01-01 | Labor | 0 | 38292812 | 48031095
MCR007237 | HPR040 | 2021-01-01 | Material | 0 | 100678767 | 101272357
MCR007238 | HPR040 | 2021-01-01 | Equipment | 0 | 41258545 | 50877432
MCR007239 | HPR040 | 2021-01-01 | Subcontract | 0 | 75558060 | 82092698
MCR007240 | HPR040 | 2021-01-01 | Overhead | 0 | 31833714 | 59100873
MCR007241 | HPR040 | 2021-02-01 | Labor | 0 | 15103582 | 11884725
MCR007242 | HPR040 | 2021-02-01 | Material | 0 | 39710063 | 35152821
MCR007243 | HPR040 | 2021-02-01 | Equipment | 0 | 16273336 | 15291993
MCR007244 | HPR040 | 2021-02-01 | Subcontract | 0 | 29801868 | 29379044
MCR007245 | HPR040 | 2021-02-01 | Overhead | 0 | 12555962 | 59832445
MCR007246 | HPR040 | 2021-03-01 | Labor | 0 | 19908157 | 22307787
MCR007247 | HPR040 | 2021-03-01 | Material | 0 | 52342165 | 53269497
MCR007248 | HPR040 | 2021-03-01 | Equipment | 0 | 21450020 | 24478050
MCR007249 | HPR040 | 2021-03-01 | Subcontract | 0 | 39282090 | 40319194
MCR007250 | HPR040 | 2021-03-01 | Overhead | 0 | 16550118 | 57388632
MCR007251 | HPR040 | 2021-04-01 | Labor | 0 | 15002783 | 17360004
MCR007252 | HPR040 | 2021-04-01 | Material | 0 | 39445046 | 42565924
MCR007253 | HPR040 | 2021-04-01 | Equipment | 0 | 16164731 | 22415887
MCR007254 | HPR040 | 2021-04-01 | Subcontract | 0 | 29602976 | 34136435
MCR007255 | HPR040 | 2021-04-01 | Overhead | 0 | 12472166 | 59270746
MCR007256 | HPR040 | 2021-05-01 | Labor | 0 | 3806237 | 3608235
MCR007257 | HPR040 | 2021-05-01 | Material | 0 | 10007289 | 10847548
MCR007258 | HPR040 | 2021-05-01 | Equipment | 0 | 4101025 | 2635462
MCR007259 | HPR040 | 2021-05-01 | Subcontract | 0 | 7510336 | 5048069
MCR007260 | HPR040 | 2021-05-01 | Overhead | 0 | 3164214 | 56692843
MCR007261 | HPR041 | 2018-08-01 | Labor | 3581424 | 1331742 | 1524205
MCR007262 | HPR041 | 2018-08-01 | Material | 6514773 | 2422499 | 2364955
MCR007263 | HPR041 | 2018-08-01 | Equipment | 1495659 | 556156 | 532326
MCR007264 | HPR041 | 2018-08-01 | Subcontract | 5922466 | 2202251 | 2088440
MCR007265 | HPR041 | 2018-08-01 | Overhead | 2078421 | 772854 | 12688798
MCR007266 | HPR041 | 2018-09-01 | Labor | 10137868 | 4699755 | 4289580
MCR007267 | HPR041 | 2018-09-01 | Material | 18441244 | 8549069 | 7582048
MCR007268 | HPR041 | 2018-09-01 | Equipment | 4233732 | 1962691 | 1956482
MCR007269 | HPR041 | 2018-09-01 | Subcontract | 16764612 | 7771809 | 7963340
MCR007270 | HPR041 | 2018-09-01 | Overhead | 5883346 | 2727426 | 12418483
MCR007271 | HPR041 | 2018-10-01 | Labor | 15800422 | 8143635 | 9421936
MCR007272 | HPR041 | 2018-10-01 | Material | 28741688 | 14813643 | 14162723
MCR007273 | HPR041 | 2018-10-01 | Equipment | 6598503 | 3400909 | 3335918
MCR007274 | HPR041 | 2018-10-01 | Subcontract | 26128565 | 13466823 | 13896240
MCR007275 | HPR041 | 2018-10-01 | Overhead | 9169516 | 4726025 | 11701290
MCR007276 | HPR041 | 2018-11-01 | Labor | 20590884 | 14369135 | 16750011
MCR007277 | HPR041 | 2018-11-01 | Material | 37455757 | 26138111 | 30172917
MCR007278 | HPR041 | 2018-11-01 | Equipment | 8599074 | 6000775 | 6603301
MCR007279 | HPR041 | 2018-11-01 | Subcontract | 34050373 | 23761699 | 22520711
MCR007280 | HPR041 | 2018-11-01 | Overhead | 11949582 | 8338892 | 11309542
MCR007281 | HPR041 | 2018-12-01 | Labor | 24532212 | 14204526 | 16712692
MCR007282 | HPR041 | 2018-12-01 | Material | 44625212 | 25838680 | 27907830
MCR007283 | HPR041 | 2018-12-01 | Equipment | 10245034 | 5932032 | 5008817
MCR007284 | HPR041 | 2018-12-01 | Subcontract | 40567999 | 23489491 | 19898481
MCR007285 | HPR041 | 2018-12-01 | Overhead | 14236867 | 8243364 | 12215293
MCR007286 | HPR041 | 2019-01-01 | Labor | 27648673 | 22512362 | 23113696
MCR007287 | HPR041 | 2019-01-01 | Material | 50294197 | 40951013 | 39157198
MCR007288 | HPR041 | 2019-01-01 | Equipment | 11546517 | 9401514 | 10725847
MCR007289 | HPR041 | 2019-01-01 | Subcontract | 45721573 | 37227849 | 39025014
MCR007290 | HPR041 | 2019-01-01 | Overhead | 16045454 | 13064681 | 11398663
MCR007291 | HPR041 | 2019-02-01 | Labor | 29966023 | 24183072 | 26727632
MCR007292 | HPR041 | 2019-02-01 | Material | 54509563 | 43990110 | 47489146
MCR007293 | HPR041 | 2019-02-01 | Equipment | 12514279 | 10099228 | 10527973
MCR007294 | HPR041 | 2019-02-01 | Subcontract | 49553688 | 39990638 | 37404623
MCR007295 | HPR041 | 2019-02-01 | Overhead | 17390291 | 14034250 | 12416351
MCR007296 | HPR041 | 2019-03-01 | Labor | 31511729 | 23747922 | 26890350
MCR007297 | HPR041 | 2019-03-01 | Material | 57321271 | 43198552 | 51024624
MCR007298 | HPR041 | 2019-03-01 | Equipment | 13159789 | 9917503 | 9370566
MCR007299 | HPR041 | 2019-03-01 | Subcontract | 52109763 | 39271047 | 41682197
MCR007300 | HPR041 | 2019-03-01 | Overhead | 18287315 | 13781717 | 12400573
MCR007301 | HPR041 | 2019-04-01 | Labor | 32315237 | 18923967 | 19628686
MCR007302 | HPR041 | 2019-04-01 | Material | 58782890 | 34423558 | 26951615
MCR007303 | HPR041 | 2019-04-01 | Equipment | 13495347 | 7902944 | 9009897
MCR007304 | HPR041 | 2019-04-01 | Subcontract | 53438495 | 31293854 | 28733674
MCR007305 | HPR041 | 2019-04-01 | Overhead | 18753618 | 10982214 | 11061586
MCR007306 | HPR041 | 2019-05-01 | Labor | 32408325 | 26618674 | 30482124
MCR007307 | HPR041 | 2019-05-01 | Material | 58952220 | 48420582 | 53673031
MCR007308 | HPR041 | 2019-05-01 | Equipment | 13534222 | 11116374 | 11561298
MCR007309 | HPR041 | 2019-05-01 | Subcontract | 53592430 | 44018303 | 42835024
MCR007310 | HPR041 | 2019-05-01 | Overhead | 18807640 | 15447712 | 12363158
MCR007311 | HPR041 | 2019-06-01 | Labor | 31825537 | 20931954 | 22288488
MCR007312 | HPR041 | 2019-06-01 | Material | 57892103 | 38076178 | 41998428
MCR007313 | HPR041 | 2019-06-01 | Equipment | 13290841 | 8741510 | 10254833
MCR007314 | HPR041 | 2019-06-01 | Subcontract | 52628697 | 34614386 | 39397983
MCR007315 | HPR041 | 2019-06-01 | Overhead | 18469429 | 12147516 | 11406631
MCR007316 | HPR041 | 2019-07-01 | Labor | 30604774 | 20307540 | 22928478
MCR007317 | HPR041 | 2019-07-01 | Material | 55671480 | 36940342 | 38291345
MCR007318 | HPR041 | 2019-07-01 | Equipment | 12781031 | 8480746 | 7531154
MCR007319 | HPR041 | 2019-07-01 | Subcontract | 50609967 | 33581818 | 33416018
MCR007320 | HPR041 | 2019-07-01 | Overhead | 17760979 | 11785148 | 12174896
MCR007321 | HPR041 | 2019-08-01 | Labor | 28788074 | 19892563 | 23612069
MCR007322 | HPR041 | 2019-08-01 | Material | 52366819 | 36185479 | 35921743
MCR007323 | HPR041 | 2019-08-01 | Equipment | 12022349 | 8307445 | 10062418
MCR007324 | HPR041 | 2019-08-01 | Subcontract | 47605758 | 32895585 | 28584888
MCR007325 | HPR041 | 2019-08-01 | Overhead | 16706687 | 11544323 | 12120789
MCR007326 | HPR041 | 2019-09-01 | Labor | 26422710 | 24393968 | 27523243
MCR007327 | HPR041 | 2019-09-01 | Material | 48064114 | 44373740 | 51281114
MCR007328 | HPR041 | 2019-09-01 | Equipment | 11034536 | 10187302 | 10882398
MCR007329 | HPR041 | 2019-09-01 | Subcontract | 43694243 | 40339390 | 41935845
MCR007330 | HPR041 | 2019-09-01 | Overhead | 15333987 | 14156640 | 12096665
MCR007331 | HPR041 | 2019-10-01 | Labor | 23562774 | 22113372 | 20426918
MCR007332 | HPR041 | 2019-10-01 | Material | 42861760 | 40225232 | 36738196
MCR007333 | HPR041 | 2019-10-01 | Equipment | 9840182 | 9234889 | 7829012
MCR007334 | HPR041 | 2019-10-01 | Subcontract | 38964875 | 36568053 | 35369775
MCR007335 | HPR041 | 2019-10-01 | Overhead | 13674270 | 12833133 | 11366912
MCR007336 | HPR041 | 2019-11-01 | Labor | 20271595 | 27041716 | 35037546
MCR007337 | HPR041 | 2019-11-01 | Material | 36874955 | 49190113 | 52446377
MCR007338 | HPR041 | 2019-11-01 | Equipment | 8465734 | 11293042 | 12398867
MCR007339 | HPR041 | 2019-11-01 | Subcontract | 33522375 | 44717870 | 45312156
MCR007340 | HPR041 | 2019-11-01 | Overhead | 11764288 | 15693217 | 10553881
MCR007341 | HPR041 | 2019-12-01 | Labor | 16625649 | 34820816 | 40792711
MCR007342 | HPR041 | 2019-12-01 | Material | 30242814 | 63340652 | 66925557
MCR007343 | HPR041 | 2019-12-01 | Equipment | 6943130 | 14541716 | 16601483
MCR007344 | HPR041 | 2019-12-01 | Subcontract | 27493212 | 57581877 | 58720105
MCR007345 | HPR041 | 2019-12-01 | Overhead | 9648423 | 20207690 | 11198910
MCR007346 | HPR041 | 2020-01-01 | Labor | 12721510 | 18022561 | 20803340
MCR007347 | HPR041 | 2020-01-01 | Material | 23141007 | 32783859 | 35883234
MCR007348 | HPR041 | 2020-01-01 | Equipment | 5312701 | 7526502 | 6195226
MCR007349 | HPR041 | 2020-01-01 | Subcontract | 21037084 | 29803232 | 26809831
MCR007350 | HPR041 | 2020-01-01 | Overhead | 7382720 | 10459098 | 11763789
MCR007351 | HPR041 | 2020-02-01 | Labor | 8689853 | 17202954 | 21074662
MCR007352 | HPR041 | 2020-02-01 | Material | 15807238 | 31292957 | 26229402
MCR007353 | HPR041 | 2020-02-01 | Equipment | 3629018 | 7184222 | 8900817
MCR007354 | HPR041 | 2020-02-01 | Subcontract | 14370083 | 28447879 | 47703428
MCR007355 | HPR041 | 2020-02-01 | Overhead | 5043014 | 9983452 | 11802356
MCR007356 | HPR041 | 2020-03-01 | Labor | 4730498 | 18894446 | 19052296
MCR007357 | HPR041 | 2020-03-01 | Material | 8604992 | 34369859 | 40540329
MCR007358 | HPR041 | 2020-03-01 | Equipment | 1975530 | 7890615 | 7446314
MCR007359 | HPR041 | 2020-03-01 | Subcontract | 7822648 | 31245036 | 39985941
MCR007360 | HPR041 | 2020-03-01 | Overhead | 2745267 | 10965082 | 12843747
MCR007361 | HPR041 | 2020-04-01 | Labor | 1259610 | 14338907 | 18801971
MCR007362 | HPR041 | 2020-04-01 | Material | 2291289 | 26083126 | 27938575
MCR007363 | HPR041 | 2020-04-01 | Equipment | 526033 | 5988151 | 6243947
MCR007364 | HPR041 | 2020-04-01 | Subcontract | 2082970 | 23711712 | 41322486
MCR007365 | HPR041 | 2020-04-01 | Overhead | 730994 | 8321350 | 11180832
MCR007366 | HPR041 | 2020-05-01 | Labor | 0 | 14426679 | 16668990
MCR007367 | HPR041 | 2020-05-01 | Material | 0 | 26242786 | 27268889
MCR007368 | HPR041 | 2020-05-01 | Equipment | 0 | 6024806 | 6747926
MCR007369 | HPR041 | 2020-05-01 | Subcontract | 0 | 23856857 | 34858195
MCR007370 | HPR041 | 2020-05-01 | Overhead | 0 | 8372287 | 11044850
MCR007371 | HPR041 | 2020-06-01 | Labor | 0 | 12028296 | 13461974
MCR007372 | HPR041 | 2020-06-01 | Material | 0 | 21880019 | 19985641
MCR007373 | HPR041 | 2020-06-01 | Equipment | 0 | 5023204 | 5187281
MCR007374 | HPR041 | 2020-06-01 | Subcontract | 0 | 19890741 | 45943266
MCR007375 | HPR041 | 2020-06-01 | Overhead | 0 | 6980424 | 13232531
MCR007376 | HPR041 | 2020-07-01 | Labor | 0 | 5325581 | 5999167
MCR007377 | HPR041 | 2020-07-01 | Material | 0 | 9687475 | 14352660
MCR007378 | HPR041 | 2020-07-01 | Equipment | 0 | 2224046 | 2359079
MCR007379 | HPR041 | 2020-07-01 | Subcontract | 0 | 8806714 | 20077935
MCR007380 | HPR041 | 2020-07-01 | Overhead | 0 | 3090614 | 11574629
MCR007381 | HPR041 | 2020-08-01 | Labor | 0 | 3215678 | 4546417
MCR007382 | HPR041 | 2020-08-01 | Material | 0 | 5849465 | 6069099
MCR007383 | HPR041 | 2020-08-01 | Equipment | 0 | 1342917 | 1623897
MCR007384 | HPR041 | 2020-08-01 | Subcontract | 0 | 5317646 | 21150368
MCR007385 | HPR041 | 2020-08-01 | Overhead | 0 | 1866166 | 12412955
MCR007386 | HPR041 | 2020-09-01 | Labor | 0 | 1759427 | 1639469
MCR007387 | HPR041 | 2020-09-01 | Material | 0 | 3200477 | 2922928
MCR007388 | HPR041 | 2020-09-01 | Equipment | 0 | 734764 | 770998
MCR007389 | HPR041 | 2020-09-01 | Subcontract | 0 | 2909498 | 13695298
MCR007390 | HPR041 | 2020-09-01 | Overhead | 0 | 1021054 | 11866679
MCR007391 | HPR041 | 2020-10-01 | Labor | 0 | 544137 | 723650
MCR007392 | HPR041 | 2020-10-01 | Material | 0 | 989810 | 1341212
MCR007393 | HPR041 | 2020-10-01 | Equipment | 0 | 227240 | 338059
MCR007394 | HPR041 | 2020-10-01 | Subcontract | 0 | 899819 | 16761896
MCR007395 | HPR041 | 2020-10-01 | Overhead | 0 | 315781 | 11523367
MCR007396 | HPR042 | 2021-02-01 | Labor | 6268771 | 2515580 | 2781413
MCR007397 | HPR042 | 2021-02-01 | Material | 27008568 | 10838202 | 11107698
MCR007398 | HPR042 | 2021-02-01 | Equipment | 4651662 | 1866654 | 1732188
MCR007399 | HPR042 | 2021-02-01 | Subcontract | 22935039 | 9203546 | 8394676
MCR007400 | HPR042 | 2021-02-01 | Overhead | 5046586 | 2025132 | 25004304
MCR007401 | HPR042 | 2021-03-01 | Labor | 17562704 | 15583867 | 17762911
MCR007402 | HPR042 | 2021-03-01 | Material | 75667700 | 67142016 | 57333302
MCR007403 | HPR042 | 2021-03-01 | Equipment | 13032181 | 11563810 | 12151331
MCR007404 | HPR042 | 2021-03-01 | Subcontract | 64255227 | 57015418 | 62509234
MCR007405 | HPR042 | 2021-03-01 | Overhead | 14138609 | 12545574 | 24234505
MCR007406 | HPR042 | 2021-04-01 | Labor | 27029306 | 15343415 | 14025888
MCR007407 | HPR042 | 2021-04-01 | Material | 116453901 | 66106046 | 67830035
MCR007408 | HPR042 | 2021-04-01 | Equipment | 20056753 | 11385386 | 11884900
MCR007409 | HPR042 | 2021-04-01 | Subcontract | 98889908 | 56135696 | 40919098
MCR007410 | HPR042 | 2021-04-01 | Overhead | 21759565 | 12352002 | 26588671
MCR007411 | HPR042 | 2021-05-01 | Labor | 34721790 | 32853726 | 39485645
MCR007412 | HPR042 | 2021-05-01 | Material | 149596438 | 141548015 | 153421176
MCR007413 | HPR042 | 2021-05-01 | Equipment | 25764863 | 24378690 | 23353053
MCR007414 | HPR042 | 2021-05-01 | Subcontract | 127033769 | 120199238 | 122157627
MCR007415 | HPR042 | 2021-05-01 | Overhead | 27952291 | 26448433 | 23924280
MCR007416 | HPR042 | 2021-06-01 | Labor | 40696787 | 27727033 | 25965978
MCR007417 | HPR042 | 2021-06-01 | Material | 175339302 | 119460012 | 106670262
MCR007418 | HPR042 | 2021-06-01 | Equipment | 30198534 | 20574493 | 22759871
MCR007419 | HPR042 | 2021-06-01 | Subcontract | 148894003 | 101442626 | 95669407
MCR007420 | HPR042 | 2021-06-01 | Overhead | 32762380 | 22321261 | 24787501
MCR007421 | HPR042 | 2021-07-01 | Labor | 45014884 | 27264598 | 25895287
MCR007422 | HPR042 | 2021-07-01 | Material | 193943525 | 117467640 | 137598553
MCR007423 | HPR042 | 2021-07-01 | Equipment | 33402723 | 20231348 | 17556624
MCR007424 | HPR042 | 2021-07-01 | Subcontract | 164692270 | 99750751 | 87009707
MCR007425 | HPR042 | 2021-07-01 | Overhead | 36238603 | 21948983 | 24705398
MCR007426 | HPR042 | 2021-08-01 | Labor | 47741296 | 30518442 | 32530461
MCR007427 | HPR042 | 2021-08-01 | Material | 205690080 | 131486602 | 148454896
MCR007428 | HPR042 | 2021-08-01 | Equipment | 35425822 | 22645822 | 21804151
MCR007429 | HPR042 | 2021-08-01 | Subcontract | 174667168 | 111655323 | 115947604
MCR007430 | HPR042 | 2021-08-01 | Overhead | 38433462 | 24568445 | 27483296
MCR007431 | HPR042 | 2021-09-01 | Labor | 48946730 | 27484269 | 25316000
MCR007432 | HPR042 | 2021-09-01 | Material | 210883611 | 118414080 | 126876401
MCR007433 | HPR042 | 2021-09-01 | Equipment | 36320299 | 20394353 | 22454436
MCR007434 | HPR042 | 2021-09-01 | Subcontract | 179077392 | 100554445 | 90379488
MCR007435 | HPR042 | 2021-09-01 | Overhead | 39403880 | 22125827 | 25158817
MCR007436 | HPR042 | 2021-10-01 | Labor | 48708524 | 46074781 | 50466248
MCR007437 | HPR042 | 2021-10-01 | Material | 209857318 | 198510016 | 184386081
MCR007438 | HPR042 | 2021-10-01 | Equipment | 36143541 | 34189205 | 34337044
MCR007439 | HPR042 | 2021-10-01 | Subcontract | 178205888 | 168570027 | 149600930
MCR007440 | HPR042 | 2021-10-01 | Overhead | 39212116 | 37091858 | 27588786
MCR007441 | HPR042 | 2021-11-01 | Labor | 47112168 | 30764933 | 31020408
MCR007442 | HPR042 | 2021-11-01 | Material | 202979526 | 132548594 | 141953829
MCR007443 | HPR042 | 2021-11-01 | Equipment | 34958985 | 22828728 | 23537329
MCR007444 | HPR042 | 2021-11-01 | Subcontract | 172365429 | 112557142 | 116670881
MCR007445 | HPR042 | 2021-11-01 | Overhead | 37926992 | 24766879 | 24590848
MCR007446 | HPR042 | 2021-12-01 | Labor | 44253421 | 50051067 | 48854047
MCR007447 | HPR042 | 2021-12-01 | Material | 190662812 | 215641571 | 236056484
MCR007448 | HPR042 | 2021-12-01 | Equipment | 32837688 | 37139758 | 36633089
MCR007449 | HPR042 | 2021-12-01 | Subcontract | 161906366 | 183117739 | 173998878
MCR007450 | HPR042 | 2021-12-01 | Overhead | 35625597 | 40292912 | 26194045
MCR007451 | HPR042 | 2022-01-01 | Labor | 40241371 | 56164044 | 56203291
MCR007452 | HPR042 | 2022-01-01 | Material | 173377173 | 241978910 | 264246408
MCR007453 | HPR042 | 2022-01-01 | Equipment | 29860598 | 41675815 | 43367365
MCR007454 | HPR042 | 2022-01-01 | Subcontract | 147227809 | 205482787 | 201250966
MCR007455 | HPR042 | 2022-01-01 | Overhead | 32395753 | 45214078 | 23360426
MCR007456 | HPR042 | 2022-02-01 | Labor | 35203068 | 72402036 | 76997910
MCR007457 | HPR042 | 2022-02-01 | Material | 151669992 | 311939182 | 295887497
MCR007458 | HPR042 | 2022-02-01 | Equipment | 26121989 | 53725011 | 57374869
MCR007459 | HPR042 | 2022-02-01 | Subcontract | 128794582 | 264891401 | 246249017
MCR007460 | HPR042 | 2022-02-01 | Overhead | 28339738 | 58286247 | 25719382
MCR007461 | HPR042 | 2022-03-01 | Labor | 29291012 | 35054449 | 29924931
MCR007462 | HPR042 | 2022-03-01 | Material | 126198308 | 151029678 | 174794220
MCR007463 | HPR042 | 2022-03-01 | Equipment | 21735023 | 26011709 | 27615670
MCR007464 | HPR042 | 2022-03-01 | Subcontract | 107164628 | 128250843 | 121464301
MCR007465 | HPR042 | 2022-03-01 | Overhead | 23580320 | 28220094 | 24892217
MCR007466 | HPR042 | 2022-04-01 | Labor | 22696376 | 41408129 | 46687833
MCR007467 | HPR042 | 2022-04-01 | Material | 97785770 | 178404071 | 198245482
MCR007468 | HPR042 | 2022-04-01 | Equipment | 16841557 | 30726376 | 30423904
MCR007469 | HPR042 | 2022-04-01 | Subcontract | 83037371 | 151496531 | 133358046
MCR007470 | HPR042 | 2022-04-01 | Overhead | 18271400 | 33335035 | 25893953
MCR007471 | HPR042 | 2022-05-01 | Labor | 15675540 | 21851324 | 20570432
MCR007472 | HPR042 | 2022-05-01 | Material | 67536982 | 94144921 | 87321107
MCR007473 | HPR042 | 2022-05-01 | Equipment | 11631835 | 16214497 | 17456532
MCR007474 | HPR042 | 2022-05-01 | Subcontract | 57350813 | 79945648 | 69290892
MCR007475 | HPR042 | 2022-05-01 | Overhead | 12619374 | 17591103 | 22951685
MCR007476 | HPR042 | 2022-06-01 | Labor | 8616130 | 13064994 | 12322118
MCR007477 | HPR042 | 2022-06-01 | Material | 37122003 | 56289627 | 49075061
MCR007478 | HPR042 | 2022-06-01 | Equipment | 6393490 | 9694713 | 8588244
MCR007479 | HPR042 | 2022-06-01 | Subcontract | 31523130 | 47799824 | 56006934
MCR007480 | HPR042 | 2022-06-01 | Overhead | 6936295 | 10517791 | 25966075
MCR007481 | HPR042 | 2022-07-01 | Labor | 2312301 | 10016587 | 10136068
MCR007482 | HPR042 | 2022-07-01 | Material | 9962390 | 43155773 | 48639259
MCR007483 | HPR042 | 2022-07-01 | Equipment | 1715814 | 7432681 | 8184519
MCR007484 | HPR042 | 2022-07-01 | Subcontract | 8459827 | 36646865 | 32007491
MCR007485 | HPR042 | 2022-07-01 | Overhead | 1861486 | 8063713 | 22482047
MCR007486 | HPR042 | 2022-08-01 | Labor | 0 | 4312592 | 4639857
MCR007487 | HPR042 | 2022-08-01 | Material | 0 | 18580504 | 22269012
MCR007488 | HPR042 | 2022-08-01 | Equipment | 0 | 3200104 | 3629708
MCR007489 | HPR042 | 2022-08-01 | Subcontract | 0 | 15778126 | 14749583
MCR007490 | HPR042 | 2022-08-01 | Overhead | 0 | 3471792 | 25704703
MCR007491 | HPR042 | 2022-09-01 | Labor | 0 | 1636312 | 1654856
MCR007492 | HPR042 | 2022-09-01 | Material | 0 | 7049937 | 6022877
MCR007493 | HPR042 | 2022-09-01 | Equipment | 0 | 1214205 | 1107938
MCR007494 | HPR042 | 2022-09-01 | Subcontract | 0 | 5986641 | 5150470
MCR007495 | HPR042 | 2022-09-01 | Overhead | 0 | 1317290 | 25763681
MCR007496 | HPR043 | 2017-11-01 | Labor | 5075620 | 3921795 | 4745371
MCR007497 | HPR043 | 2017-11-01 | Material | 10584704 | 8178517 | 8435315
MCR007498 | HPR043 | 2017-11-01 | Equipment | 2232590 | 1725062 | 1895540
MCR007499 | HPR043 | 2017-11-01 | Subcontract | 13387267 | 10343982 | 10787497
MCR007500 | HPR043 | 2017-11-01 | Overhead | 2964167 | 2290332 | 16106258
MCR007501 | HPR043 | 2017-12-01 | Labor | 14323338 | 15470763 | 15981226
MCR007502 | HPR043 | 2017-12-01 | Material | 29869906 | 32262748 | 28666285
MCR007503 | HPR043 | 2017-12-01 | Equipment | 6300342 | 6805055 | 7088630
MCR007504 | HPR043 | 2017-12-01 | Subcontract | 37778705 | 40805111 | 49014355
MCR007505 | HPR043 | 2017-12-01 | Overhead | 8364842 | 9034940 | 15079519
MCR007506 | HPR043 | 2018-01-01 | Labor | 22240453 | 22761821 | 26708390
MCR007507 | HPR043 | 2018-01-01 | Material | 46380267 | 47467528 | 52176046
MCR007508 | HPR043 | 2018-01-01 | Equipment | 9782808 | 10012140 | 9873582
MCR007509 | HPR043 | 2018-01-01 | Subcontract | 58660594 | 60035734 | 66507371
MCR007510 | HPR043 | 2018-01-01 | Overhead | 12988445 | 13292924 | 17662036
MCR007511 | HPR043 | 2018-02-01 | Labor | 28861272 | 27175835 | 23289618
MCR007512 | HPR043 | 2018-02-01 | Material | 60187331 | 56672517 | 56792844
MCR007513 | HPR043 | 2018-02-01 | Equipment | 12695078 | 11953712 | 11625555
MCR007514 | HPR043 | 2018-02-01 | Subcontract | 76123420 | 71677972 | 70559201
MCR007515 | HPR043 | 2018-02-01 | Overhead | 16855009 | 15870712 | 15603460
MCR007516 | HPR043 | 2018-03-01 | Labor | 34222038 | 33285725 | 39738106
MCR007517 | HPR043 | 2018-03-01 | Material | 71366679 | 69414090 | 72269400
MCR007518 | HPR043 | 2018-03-01 | Equipment | 15053094 | 14641242 | 12260190
MCR007519 | HPR043 | 2018-03-01 | Subcontract | 90262778 | 87793193 | 87506205
MCR007520 | HPR043 | 2018-03-01 | Overhead | 19985701 | 19438893 | 17182480
MCR007521 | HPR043 | 2018-04-01 | Labor | 38361196 | 62257633 | 63464912
MCR007522 | HPR043 | 2018-04-01 | Material | 79998483 | 129832141 | 139609597
MCR007523 | HPR043 | 2018-04-01 | Equipment | 16873767 | 27384985 | 27662386
MCR007524 | HPR043 | 2018-04-01 | Subcontract | 101180066 | 164208422 | 159681055
MCR007525 | HPR043 | 2018-04-01 | Overhead | 22402973 | 36358513 | 16704237
MCR007526 | HPR043 | 2018-05-01 | Labor | 41319715 | 29226101 | 37815420
MCR007527 | HPR043 | 2018-05-01 | Material | 86168182 | 60948145 | 55063716
MCR007528 | HPR043 | 2018-05-01 | Equipment | 18175117 | 12855553 | 13826717
MCR007529 | HPR043 | 2018-05-01 | Subcontract | 108983346 | 77085678 | 91701545
MCR007530 | HPR043 | 2018-05-01 | Overhead | 24130750 | 17068069 | 15807864
MCR007531 | HPR043 | 2018-06-01 | Labor | 43141491 | 56226533 | 68800512
MCR007532 | HPR043 | 2018-06-01 | Material | 89967315 | 117254879 | 113032728
MCR007533 | HPR043 | 2018-06-01 | Equipment | 18976453 | 24732112 | 24052514
MCR007534 | HPR043 | 2018-06-01 | Subcontract | 113788394 | 148301017 | 159379505
MCR007535 | HPR043 | 2018-06-01 | Overhead | 25194669 | 32836346 | 15542012
MCR007536 | HPR043 | 2018-07-01 | Labor | 43873851 | 42143255 | 38161000
MCR007537 | HPR043 | 2018-07-01 | Material | 91494579 | 87885592 | 93991251
MCR007538 | HPR043 | 2018-07-01 | Equipment | 19298593 | 18537364 | 19427722
MCR007539 | HPR043 | 2018-07-01 | Subcontract | 115720039 | 111155484 | 122429667
MCR007540 | HPR043 | 2018-07-01 | Overhead | 25622368 | 24611698 | 16893469
MCR007541 | HPR043 | 2018-08-01 | Labor | 43568203 | 23728678 | 31193592
MCR007542 | HPR043 | 2018-08-01 | Material | 90857182 | 49483812 | 59704167
MCR007543 | HPR043 | 2018-08-01 | Equipment | 19164149 | 10437427 | 10816763
MCR007544 | HPR043 | 2018-08-01 | Subcontract | 114913876 | 62585879 | 65379442
MCR007545 | HPR043 | 2018-08-01 | Overhead | 25443870 | 13857569 | 17500626
MCR007546 | HPR043 | 2018-09-01 | Labor | 42280893 | 44283876 | 50103253
MCR007547 | HPR043 | 2018-09-01 | Material | 88172624 | 92349647 | 95214181
MCR007548 | HPR043 | 2018-09-01 | Equipment | 18597906 | 19478949 | 18204892
MCR007549 | HPR043 | 2018-09-01 | Subcontract | 111518514 | 116801508 | 117128421
MCR007550 | HPR043 | 2018-09-01 | Overhead | 24692079 | 25861823 | 16818177
MCR007551 | HPR043 | 2018-10-01 | Labor | 40074348 | 34883808 | 55797500
MCR007552 | HPR043 | 2018-10-01 | Material | 83571092 | 72746734 | 90066757
MCR007553 | HPR043 | 2018-10-01 | Equipment | 17627323 | 15344184 | 17910565
MCR007554 | HPR043 | 2018-10-01 | Subcontract | 105698612 | 92008237 | 107314812
MCR007555 | HPR043 | 2018-10-01 | Overhead | 23403455 | 20372175 | 16466566
MCR007556 | HPR043 | 2018-11-01 | Labor | 37018682 | 37974620 | 77832907
MCR007557 | HPR043 | 2018-11-01 | Material | 77198803 | 79192316 | 93843649
MCR007558 | HPR043 | 2018-11-01 | Equipment | 16283241 | 16703725 | 15189747
MCR007559 | HPR043 | 2018-11-01 | Subcontract | 97639102 | 100160446 | 111721755
MCR007560 | HPR043 | 2018-11-01 | Overhead | 21618943 | 22177212 | 15766084
MCR007561 | HPR043 | 2018-12-01 | Labor | 33194012 | 33707675 | 32519249
MCR007562 | HPR043 | 2018-12-01 | Material | 69222831 | 70294025 | 77328608
MCR007563 | HPR043 | 2018-12-01 | Equipment | 14600900 | 14826843 | 16979916
MCR007564 | HPR043 | 2018-12-01 | Subcontract | 87551293 | 88906113 | 94093164
MCR007565 | HPR043 | 2018-12-01 | Overhead | 19385332 | 19685312 | 16908175
MCR007566 | HPR043 | 2019-01-01 | Labor | 28693973 | 24140104 | 30061018
MCR007567 | HPR043 | 2019-01-01 | Material | 59838445 | 50341801 | 50446485
MCR007568 | HPR043 | 2019-01-01 | Equipment | 12621489 | 10618399 | 12726151
MCR007569 | HPR043 | 2019-01-01 | Subcontract | 75682158 | 63671042 | 57740704
MCR007570 | HPR043 | 2019-01-01 | Overhead | 16757306 | 14097842 | 16345043
MCR007571 | HPR043 | 2019-02-01 | Labor | 23631431 | 14303437 | 15152540
MCR007572 | HPR043 | 2019-02-01 | Material | 49281014 | 29828405 | 31698727
MCR007573 | HPR043 | 2019-02-01 | Equipment | 10394651 | 6291588 | 3865786
MCR007574 | HPR043 | 2019-02-01 | Subcontract | 62329385 | 37726215 | 44950245
MCR007575 | HPR043 | 2019-02-01 | Overhead | 13800777 | 8353220 | 16542157
MCR007576 | HPR043 | 2019-03-01 | Labor | 18148577 | 10741274 | 11509719
MCR007577 | HPR043 | 2019-03-01 | Material | 37847063 | 22399865 | 22127656
MCR007578 | HPR043 | 2019-03-01 | Equipment | 7982933 | 4724716 | 4539529
MCR007579 | HPR043 | 2019-03-01 | Subcontract | 47868012 | 28330786 | 30290069
MCR007580 | HPR043 | 2019-03-01 | Overhead | 10598785 | 6272914 | 16434368
MCR007581 | HPR043 | 2019-04-01 | Labor | 12437275 | 23686728 | 26628110
MCR007582 | HPR043 | 2019-04-01 | Material | 25936707 | 49396330 | 46188810
MCR007583 | HPR043 | 2019-04-01 | Equipment | 5470728 | 10418974 | 9653483
MCR007584 | HPR043 | 2019-04-01 | Subcontract | 32804093 | 62475234 | 63277779
MCR007585 | HPR043 | 2019-04-01 | Overhead | 7263379 | 13833070 | 16038944
MCR007586 | HPR043 | 2019-05-01 | Labor | 6789881 | 12377700 | 13720955
MCR007587 | HPR043 | 2019-05-01 | Material | 14159625 | 25812470 | 30490578
MCR007588 | HPR043 | 2019-05-01 | Equipment | 2986634 | 5444523 | 5845150
MCR007589 | HPR043 | 2019-05-01 | Subcontract | 17908737 | 32646961 | 40312799
MCR007590 | HPR043 | 2019-05-01 | Overhead | 3965296 | 7228588 | 16178033
MCR007591 | HPR043 | 2019-06-01 | Labor | 1812197 | 5879288 | 6727465
MCR007592 | HPR043 | 2019-06-01 | Material | 3779158 | 12260674 | 14785993
MCR007593 | HPR043 | 2019-06-01 | Equipment | 797123 | 2586096 | 2609344
MCR007594 | HPR043 | 2019-06-01 | Subcontract | 4779784 | 15506992 | 13896306
MCR007595 | HPR043 | 2019-06-01 | Overhead | 1058325 | 3433509 | 16225073
MCR007596 | HPR043 | 2019-07-01 | Labor | 0 | 891796 | 977401
MCR007597 | HPR043 | 2019-07-01 | Material | 0 | 1859753 | 1739497
MCR007598 | HPR043 | 2019-07-01 | Equipment | 0 | 392270 | 291152
MCR007599 | HPR043 | 2019-07-01 | Subcontract | 0 | 2352169 | 2250638
MCR007600 | HPR043 | 2019-07-01 | Overhead | 0 | 520810 | 16233822
MCR007601 | HPR044 | 2018-06-01 | Labor | 3619567 | 3928991 | 3926871
MCR007602 | HPR044 | 2018-06-01 | Material | 9344707 | 10143553 | 10795374
MCR007603 | HPR044 | 2018-06-01 | Equipment | 3216666 | 3491647 | 3654454
MCR007604 | HPR044 | 2018-06-01 | Subcontract | 9136165 | 9917184 | 10449233
MCR007605 | HPR044 | 2018-06-01 | Overhead | 2121162 | 2302492 | 12110736
MCR007606 | HPR044 | 2018-07-01 | Labor | 10214375 | 4970877 | 4790933
MCR007607 | HPR044 | 2018-07-01 | Material | 26370649 | 12833408 | 12623879
MCR007608 | HPR044 | 2018-07-01 | Equipment | 9077391 | 4417558 | 4046816
MCR007609 | HPR044 | 2018-07-01 | Subcontract | 25782147 | 12547011 | 11387328
MCR007610 | HPR044 | 2018-07-01 | Overhead | 5985892 | 2913065 | 11452518
MCR007611 | HPR044 | 2018-08-01 | Labor | 15860292 | 10111879 | 9843021
MCR007612 | HPR044 | 2018-08-01 | Material | 40946822 | 26106033 | 28866861
MCR007613 | HPR044 | 2018-08-01 | Equipment | 14094850 | 8986305 | 8047717
MCR007614 | HPR044 | 2018-08-01 | Subcontract | 40033030 | 25523437 | 26367052
MCR007615 | HPR044 | 2018-08-01 | Overhead | 9294549 | 5925827 | 11321977
MCR007616 | HPR044 | 2018-09-01 | Labor | 20581784 | 23675914 | 24572083
MCR007617 | HPR044 | 2018-09-01 | Material | 53136389 | 61124564 | 61954030
MCR007618 | HPR044 | 2018-09-01 | Equipment | 18290783 | 21040498 | 20645165
MCR007619 | HPR044 | 2018-09-01 | Subcontract | 51950568 | 59760475 | 65564114
MCR007620 | HPR044 | 2018-09-01 | Overhead | 12061467 | 13874709 | 12538486
MCR007621 | HPR044 | 2018-10-01 | Labor | 24404697 | 15591258 | 16671522
MCR007622 | HPR044 | 2018-10-01 | Material | 63006077 | 40252251 | 36601303
MCR007623 | HPR044 | 2018-10-01 | Equipment | 21688159 | 13855762 | 14226172
MCR007624 | HPR044 | 2018-10-01 | Subcontract | 61599999 | 39353960 | 29909572
MCR007625 | HPR044 | 2018-10-01 | Overhead | 14301795 | 9136887 | 11389653
MCR007626 | HPR044 | 2018-11-01 | Labor | 27356446 | 16052530 | 15742948
MCR007627 | HPR044 | 2018-11-01 | Material | 70626666 | 41443126 | 42707326
MCR007628 | HPR044 | 2018-11-01 | Equipment | 24311343 | 14265689 | 14252713
MCR007629 | HPR044 | 2018-11-01 | Subcontract | 69050523 | 40518259 | 45626012
MCR007630 | HPR044 | 2018-11-01 | Overhead | 16031598 | 9407205 | 11430262
MCR007631 | HPR044 | 2018-12-01 | Labor | 29466249 | 28995659 | 30361224
MCR007632 | HPR044 | 2018-12-01 | Material | 76073585 | 74858654 | 79211969
MCR007633 | HPR044 | 2018-12-01 | Equipment | 26186300 | 25768092 | 24051179
MCR007634 | HPR044 | 2018-12-01 | Subcontract | 74375885 | 73188067 | 77232431
MCR007635 | HPR044 | 2018-12-01 | Overhead | 17267998 | 16992220 | 11360698
MCR007636 | HPR044 | 2019-01-01 | Labor | 30765409 | 25502958 | 26676152
MCR007637 | HPR044 | 2019-01-01 | Material | 79427650 | 65841479 | 63011114
MCR007638 | HPR044 | 2019-01-01 | Equipment | 27340847 | 22664171 | 23777897
MCR007639 | HPR044 | 2019-01-01 | Subcontract | 77655099 | 64372125 | 61602054
MCR007640 | HPR044 | 2019-01-01 | Overhead | 18029339 | 14945405 | 11536776
MCR007641 | HPR044 | 2019-02-01 | Labor | 31287675 | 33527956 | 33725130
MCR007642 | HPR044 | 2019-02-01 | Material | 80775995 | 86559774 | 91223182
MCR007643 | HPR044 | 2019-02-01 | Equipment | 27804979 | 29795890 | 28510850
MCR007644 | HPR044 | 2019-02-01 | Subcontract | 78973354 | 84628058 | 70916646
MCR007645 | HPR044 | 2019-02-01 | Overhead | 18335401 | 19648265 | 10781521
MCR007646 | HPR044 | 2019-03-01 | Labor | 31069709 | 31271775 | 36293658
MCR007647 | HPR044 | 2019-03-01 | Material | 80213270 | 80734945 | 83118519
MCR007648 | HPR044 | 2019-03-01 | Equipment | 27611276 | 27790848 | 31324746
MCR007649 | HPR044 | 2019-03-01 | Subcontract | 78423186 | 78933220 | 80997720
MCR007650 | HPR044 | 2019-03-01 | Overhead | 18207668 | 18326083 | 10794501
MCR007651 | HPR044 | 2019-04-01 | Labor | 30151692 | 23866165 | 26895237
MCR007652 | HPR044 | 2019-04-01 | Material | 77843207 | 61615739 | 70688782
MCR007653 | HPR044 | 2019-04-01 | Equipment | 26795445 | 21209572 | 20910382
MCR007654 | HPR044 | 2019-04-01 | Subcontract | 76106015 | 60240688 | 62399663
MCR007655 | HPR044 | 2019-04-01 | Overhead | 17669685 | 13986201 | 11937886
MCR007656 | HPR044 | 2019-05-01 | Labor | 28578143 | 32797213 | 34288333
MCR007657 | HPR044 | 2019-05-01 | Material | 73780744 | 84673199 | 91752563
MCR007658 | HPR044 | 2019-05-01 | Equipment | 25397050 | 29146487 | 32250956
MCR007659 | HPR044 | 2019-05-01 | Subcontract | 72134213 | 82783585 | 88848961
MCR007660 | HPR044 | 2019-05-01 | Overhead | 16747544 | 19220030 | 11623790
MCR007661 | HPR044 | 2019-06-01 | Labor | 26399062 | 38913180 | 45828549
MCR007662 | HPR044 | 2019-06-01 | Material | 68154969 | 100462909 | 95653860
MCR007663 | HPR044 | 2019-06-01 | Equipment | 23460527 | 34581673 | 35811423
MCR007664 | HPR044 | 2019-06-01 | Subcontract | 66633985 | 98220924 | 79537606
MCR007665 | HPR044 | 2019-06-01 | Overhead | 15470545 | 22804148 | 12978234
MCR007666 | HPR044 | 2019-07-01 | Labor | 23671582 | 10375291 | 7369316
MCR007667 | HPR044 | 2019-07-01 | Material | 61113381 | 26786089 | 34237772
MCR007668 | HPR044 | 2019-07-01 | Equipment | 21036649 | 9220396 | 8826607
MCR007669 | HPR044 | 2019-07-01 | Subcontract | 59749541 | 26188316 | 34986447
MCR007670 | HPR044 | 2019-07-01 | Overhead | 13872170 | 6080194 | 11193890
MCR007671 | HPR044 | 2019-08-01 | Labor | 20462478 | 22914894 | 23637059
MCR007672 | HPR044 | 2019-08-01 | Material | 52828376 | 59159824 | 65357956
MCR007673 | HPR044 | 2019-08-01 | Equipment | 18184757 | 20364189 | 21312647
MCR007674 | HPR044 | 2019-08-01 | Subcontract | 51649428 | 57839581 | 59030583
MCR007675 | HPR044 | 2019-08-01 | Overhead | 11991551 | 13428731 | 11790483
MCR007676 | HPR044 | 2019-09-01 | Labor | 16852237 | 19482452 | 25087450
MCR007677 | HPR044 | 2019-09-01 | Material | 43507747 | 50298223 | 53387627
MCR007678 | HPR044 | 2019-09-01 | Equipment | 14976380 | 17313820 | 16752962
MCR007679 | HPR044 | 2019-09-01 | Subcontract | 42536804 | 49175740 | 52124630
MCR007680 | HPR044 | 2019-09-01 | Overhead | 9875855 | 11417230 | 13176888
MCR007681 | HPR044 | 2019-10-01 | Labor | 12942260 | 22083915 | 22454619
MCR007682 | HPR044 | 2019-10-01 | Material | 33413282 | 57014469 | 56960287
MCR007683 | HPR044 | 2019-10-01 | Equipment | 11501630 | 19625708 | 19921741
MCR007684 | HPR044 | 2019-10-01 | Subcontract | 32667613 | 55742103 | 49448428
MCR007685 | HPR044 | 2019-10-01 | Overhead | 7584505 | 12941755 | 10655895
MCR007686 | HPR044 | 2019-11-01 | Labor | 8869370 | 11419391 | 14107457
MCR007687 | HPR044 | 2019-11-01 | Material | 22898223 | 29481662 | 31654252
MCR007688 | HPR044 | 2019-11-01 | Equipment | 7882102 | 10148275 | 9807452
MCR007689 | HPR044 | 2019-11-01 | Subcontract | 22387214 | 28823733 | 33397030
MCR007690 | HPR044 | 2019-11-01 | Overhead | 5197684 | 6692064 | 12480776
MCR007691 | HPR044 | 2019-12-01 | Labor | 4842054 | 13528783 | 14077668
MCR007692 | HPR044 | 2019-12-01 | Material | 12500826 | 34927522 | 31923003
MCR007693 | HPR044 | 2019-12-01 | Equipment | 4303075 | 12022866 | 11183252
MCR007694 | HPR044 | 2019-12-01 | Subcontract | 12221850 | 34148060 | 33326897
MCR007695 | HPR044 | 2019-12-01 | Overhead | 2837571 | 7928223 | 12092869
MCR007696 | HPR044 | 2020-01-01 | Labor | 1292329 | 4282774 | 5277517
MCR007697 | HPR044 | 2020-01-01 | Material | 3336430 | 11056921 | 14872872
MCR007698 | HPR044 | 2020-01-01 | Equipment | 1148477 | 3806050 | 4411000
MCR007699 | HPR044 | 2020-01-01 | Subcontract | 3261972 | 10810169 | 7775015
MCR007700 | HPR044 | 2020-01-01 | Overhead | 757339 | 2509818 | 11367820
MCR007701 | HPR044 | 2020-02-01 | Labor | 0 | 4032191 | 3813876
MCR007702 | HPR044 | 2020-02-01 | Material | 0 | 10409985 | 9561744
MCR007703 | HPR044 | 2020-02-01 | Equipment | 0 | 3583359 | 4479665
MCR007704 | HPR044 | 2020-02-01 | Subcontract | 0 | 10177670 | 11405747
MCR007705 | HPR044 | 2020-02-01 | Overhead | 0 | 2362970 | 11623003
MCR007706 | HPR044 | 2020-03-01 | Labor | 0 | 1361366 | 1993322
MCR007707 | HPR044 | 2020-03-01 | Material | 0 | 3514665 | 4627633
MCR007708 | HPR044 | 2020-03-01 | Equipment | 0 | 1209830 | 941072
MCR007709 | HPR044 | 2020-03-01 | Subcontract | 0 | 3436230 | 3159768
MCR007710 | HPR044 | 2020-03-01 | Overhead | 0 | 797796 | 12120577
MCR007711 | HPR045 | 2022-10-01 | Labor | 6617610 | 4471609 | 4837877
MCR007712 | HPR045 | 2022-10-01 | Material | 30318805 | 20486829 | 18499405
MCR007713 | HPR045 | 2022-10-01 | Equipment | 11945115 | 8071476 | 9623688
MCR007714 | HPR045 | 2022-10-01 | Subcontract | 16825555 | 11369256 | 11528087
MCR007715 | HPR045 | 2022-10-01 | Overhead | 6433537 | 4347228 | 29019836
MCR007716 | HPR045 | 2022-11-01 | Labor | 18370397 | 13377233 | 15490582
MCR007717 | HPR045 | 2022-11-01 | Material | 84164598 | 61288248 | 55555602
MCR007718 | HPR045 | 2022-11-01 | Equipment | 33159478 | 24146570 | 27040141
MCR007719 | HPR045 | 2022-11-01 | Subcontract | 46707516 | 34012184 | 32876259
MCR007720 | HPR045 | 2022-11-01 | Overhead | 17859412 | 13005137 | 28179395
MCR007721 | HPR045 | 2022-12-01 | Labor | 27951181 | 19595581 | 16312605
MCR007722 | HPR045 | 2022-12-01 | Material | 128059288 | 89777823 | 89612129
MCR007723 | HPR045 | 2022-12-01 | Equipment | 50453270 | 35370997 | 38091146
MCR007724 | HPR045 | 2022-12-01 | Subcontract | 71067068 | 49822600 | 41124802
MCR007725 | HPR045 | 2022-12-01 | Overhead | 27173701 | 19050517 | 28749190
MCR007726 | HPR045 | 2023-01-01 | Labor | 35432622 | 27632369 | 27569133
MCR007727 | HPR045 | 2023-01-01 | Material | 162335764 | 126598638 | 151639532
MCR007728 | HPR045 | 2023-01-01 | Equipment | 63957642 | 49877798 | 55654449
MCR007729 | HPR045 | 2023-01-01 | Subcontract | 90088950 | 70256474 | 71367262
MCR007730 | HPR045 | 2023-01-01 | Overhead | 34447041 | 26863757 | 30635223
MCR007731 | HPR045 | 2023-02-01 | Labor | 40892792 | 25989322 | 29639334
MCR007732 | HPR045 | 2023-02-01 | Material | 187351717 | 119070964 | 95226970
MCR007733 | HPR045 | 2023-02-01 | Equipment | 73813519 | 46912017 | 50888570
MCR007734 | HPR045 | 2023-02-01 | Subcontract | 103971663 | 66078958 | 53640097
MCR007735 | HPR045 | 2023-02-01 | Overhead | 39755332 | 25266412 | 27698846
MCR007736 | HPR045 | 2023-03-01 | Labor | 44416173 | 32345924 | 23621214
MCR007737 | HPR045 | 2023-03-01 | Material | 203494209 | 148193952 | 125514398
MCR007738 | HPR045 | 2023-03-01 | Equipment | 80173398 | 58385999 | 60238611
MCR007739 | HPR045 | 2023-03-01 | Subcontract | 112930011 | 82240889 | 82736048
MCR007740 | HPR045 | 2023-03-01 | Overhead | 43180708 | 31446201 | 26693806
MCR007741 | HPR045 | 2023-04-01 | Labor | 46094965 | 27116715 | 30476225
MCR007742 | HPR045 | 2023-04-01 | Material | 211185648 | 124236154 | 138182390
MCR007743 | HPR045 | 2023-04-01 | Equipment | 83203699 | 48947017 | 53731323
MCR007744 | HPR045 | 2023-04-01 | Subcontract | 117198409 | 68945403 | 55908296
MCR007745 | HPR045 | 2023-04-01 | Overhead | 44812803 | 26362446 | 31020660
MCR007746 | HPR045 | 2023-05-01 | Labor | 46030827 | 35881871 | 37104862
MCR007747 | HPR045 | 2023-05-01 | Material | 210891799 | 164394010 | 163834521
MCR007748 | HPR045 | 2023-05-01 | Equipment | 83087927 | 64768557 | 71568224
MCR007749 | HPR045 | 2023-05-01 | Subcontract | 117035336 | 91231183 | 87488776
MCR007750 | HPR045 | 2023-05-01 | Overhead | 44750449 | 34883793 | 27528914
MCR007751 | HPR045 | 2023-06-01 | Labor | 44337309 | 26395978 | 25544229
MCR007752 | HPR045 | 2023-06-01 | Material | 203132889 | 120934072 | 126379889
MCR007753 | HPR045 | 2023-06-01 | Equipment | 80031043 | 47646051 | 44051170
MCR007754 | HPR045 | 2023-06-01 | Subcontract | 112729495 | 67112898 | 64191692
MCR007755 | HPR045 | 2023-06-01 | Overhead | 43104038 | 25661757 | 24629549
MCR007756 | HPR045 | 2023-07-01 | Labor | 41143334 | 23701334 | 23457454
MCR007757 | HPR045 | 2023-07-01 | Material | 188499582 | 108588470 | 103968703
MCR007758 | HPR045 | 2023-07-01 | Equipment | 74265759 | 42782085 | 39721306
MCR007759 | HPR045 | 2023-07-01 | Subcontract | 104608676 | 60261651 | 52495645
MCR007760 | HPR045 | 2023-07-01 | Overhead | 39998905 | 23042066 | 30286994
MCR007761 | HPR045 | 2023-08-01 | Labor | 36598469 | 29866496 | 24541456
MCR007762 | HPR045 | 2023-08-01 | Material | 167677129 | 136834367 | 134074486
MCR007763 | HPR045 | 2023-08-01 | Equipment | 66062052 | 53910508 | 59758527
MCR007764 | HPR045 | 2023-08-01 | Subcontract | 93053164 | 75936837 | 77664270
MCR007765 | HPR045 | 2023-08-01 | Overhead | 35580458 | 29035740 | 28376770
MCR007766 | HPR045 | 2023-09-01 | Labor | 30881419 | 44268353 | 46003564
MCR007767 | HPR045 | 2023-09-01 | Material | 141484270 | 202816967 | 215587741
MCR007768 | HPR045 | 2023-09-01 | Equipment | 55742493 | 79906575 | 77742323
MCR007769 | HPR045 | 2023-09-01 | Subcontract | 78517321 | 112554172 | 98532749
MCR007770 | HPR045 | 2023-09-01 | Overhead | 30022432 | 43037000 | 28390548
MCR007771 | HPR045 | 2023-10-01 | Labor | 24214957 | 22003233 | 19457217
MCR007772 | HPR045 | 2023-10-01 | Material | 110941650 | 100808560 | 92567592
MCR007773 | HPR045 | 2023-10-01 | Equipment | 43709200 | 39716927 | 45861129
MCR007774 | HPR045 | 2023-10-01 | Subcontract | 61567559 | 55944156 | 46902591
MCR007775 | HPR045 | 2023-10-01 | Overhead | 23541402 | 21391199 | 28278938
MCR007776 | HPR045 | 2023-11-01 | Labor | 16895785 | 17138146 | 14966292
MCR007777 | HPR045 | 2023-11-01 | Material | 77408613 | 78519001 | 82716090
MCR007778 | HPR045 | 2023-11-01 | Equipment | 30497730 | 30935205 | 40925626
MCR007779 | HPR045 | 2023-11-01 | Subcontract | 42958252 | 43574466 | 37260927
MCR007780 | HPR045 | 2023-11-01 | Overhead | 16425818 | 16661438 | 29519428
MCR007781 | HPR045 | 2023-12-01 | Labor | 9368477 | 27488425 | 24276263
MCR007782 | HPR045 | 2023-12-01 | Material | 42921997 | 125939156 | 118839231
MCR007783 | HPR045 | 2023-12-01 | Equipment | 16910566 | 49617972 | 44257499
MCR007784 | HPR045 | 2023-12-01 | Subcontract | 23819752 | 69890491 | 67547636
MCR007785 | HPR045 | 2023-12-01 | Overhead | 9107887 | 26723817 | 27642276
MCR007786 | HPR045 | 2024-01-01 | Labor | 2531822 | 17379661 | 17775496
MCR007787 | HPR045 | 2024-01-01 | Material | 11599631 | 79625509 | 82570970
MCR007788 | HPR045 | 2024-01-01 | Equipment | 4570065 | 31371151 | 37150843
MCR007789 | HPR045 | 2024-01-01 | Subcontract | 6437266 | 44188528 | 37900362
MCR007790 | HPR045 | 2024-01-01 | Overhead | 2461398 | 16896235 | 29601830
MCR007791 | HPR045 | 2024-02-01 | Labor | 0 | 30240753 | 29297288
MCR007792 | HPR045 | 2024-02-01 | Material | 0 | 138549039 | 129483935
MCR007793 | HPR045 | 2024-02-01 | Equipment | 0 | 54586060 | 56563322
MCR007794 | HPR045 | 2024-02-01 | Subcontract | 0 | 76888401 | 68324090
MCR007795 | HPR045 | 2024-02-01 | Overhead | 0 | 29399587 | 30545459
MCR007796 | HPR045 | 2024-03-01 | Labor | 0 | 17975924 | 17064160
MCR007797 | HPR045 | 2024-03-01 | Material | 0 | 82357306 | 90096933
MCR007798 | HPR045 | 2024-03-01 | Equipment | 0 | 32447434 | 32359088
MCR007799 | HPR045 | 2024-03-01 | Subcontract | 0 | 45704551 | 42452972
MCR007800 | HPR045 | 2024-03-01 | Overhead | 0 | 17475912 | 26733725
MCR007801 | HPR045 | 2024-04-01 | Labor | 0 | 17058135 | 16811820
MCR007802 | HPR045 | 2024-04-01 | Material | 0 | 78152427 | 69721268
MCR007803 | HPR045 | 2024-04-01 | Equipment | 0 | 30790781 | 38108201
MCR007804 | HPR045 | 2024-04-01 | Subcontract | 0 | 43371035 | 34689572
MCR007805 | HPR045 | 2024-04-01 | Overhead | 0 | 16583652 | 28710447
MCR007806 | HPR045 | 2024-05-01 | Labor | 0 | 6864863 | 6128146
MCR007807 | HPR045 | 2024-05-01 | Material | 0 | 31451605 | 30929268
MCR007808 | HPR045 | 2024-05-01 | Equipment | 0 | 12391419 | 12916138
MCR007809 | HPR045 | 2024-05-01 | Subcontract | 0 | 17454207 | 18636249
MCR007810 | HPR045 | 2024-05-01 | Overhead | 0 | 6673913 | 30172128
MCR007811 | HPR045 | 2024-06-01 | Labor | 0 | 4358810 | 4252435
MCR007812 | HPR045 | 2024-06-01 | Material | 0 | 19970038 | 23265977
MCR007813 | HPR045 | 2024-06-01 | Equipment | 0 | 7867869 | 9514953
MCR007814 | HPR045 | 2024-06-01 | Subcontract | 0 | 11082461 | 10830758
MCR007815 | HPR045 | 2024-06-01 | Overhead | 0 | 4237567 | 29209666
MCR007816 | HPR045 | 2024-07-01 | Labor | 0 | 627401 | 230248
MCR007817 | HPR045 | 2024-07-01 | Material | 0 | 2874457 | 2141549
MCR007818 | HPR045 | 2024-07-01 | Equipment | 0 | 1132489 | 1223518
MCR007819 | HPR045 | 2024-07-01 | Subcontract | 0 | 1595193 | 1220912
MCR007820 | HPR045 | 2024-07-01 | Overhead | 0 | 609949 | 31108922
MCR007821 | HPR046 | 2023-03-01 | Labor | 7450911 | 5374638 | 5809261
MCR007822 | HPR046 | 2023-03-01 | Material | 17970001 | 12962476 | 14034675
MCR007823 | HPR046 | 2023-03-01 | Equipment | 6850784 | 4941743 | 5393099
MCR007824 | HPR046 | 2023-03-01 | Subcontract | 14088403 | 10162525 | 10225921
MCR007825 | HPR046 | 2023-03-01 | Overhead | 5071692 | 3658413 | 14317051
MCR007826 | HPR046 | 2023-04-01 | Labor | 19627571 | 15903520 | 18394391
MCR007827 | HPR046 | 2023-04-01 | Material | 47337494 | 38355881 | 31047826
MCR007828 | HPR046 | 2023-04-01 | Equipment | 18046685 | 14622585 | 18756893
MCR007829 | HPR046 | 2023-04-01 | Subcontract | 37112391 | 30070845 | 31675896
MCR007830 | HPR046 | 2023-04-01 | Overhead | 13360111 | 10825221 | 14736952
MCR007831 | HPR046 | 2023-05-01 | Labor | 27878365 | 23982589 | 22122390
MCR007832 | HPR046 | 2023-05-01 | Material | 67236643 | 57840865 | 48894228
MCR007833 | HPR046 | 2023-05-01 | Equipment | 25632927 | 22050933 | 21145761
MCR007834 | HPR046 | 2023-05-01 | Subcontract | 52713238 | 45346989 | 45440603
MCR007835 | HPR046 | 2023-05-01 | Overhead | 18976268 | 16324488 | 13934716
MCR007836 | HPR046 | 2023-06-01 | Labor | 32440554 | 36084418 | 48087681
MCR007837 | HPR046 | 2023-06-01 | Material | 78239665 | 87027884 | 96837457
MCR007838 | HPR046 | 2023-06-01 | Equipment | 29827658 | 33178031 | 31099902
MCR007839 | HPR046 | 2023-06-01 | Subcontract | 61339559 | 68229486 | 74205584
MCR007840 | HPR046 | 2023-06-01 | Overhead | 22081662 | 24561971 | 14454463
MCR007841 | HPR046 | 2023-07-01 | Labor | 33585463 | 19463742 | 26939178
MCR007842 | HPR046 | 2023-07-01 | Material | 81000939 | 46942374 | 53364593
MCR007843 | HPR046 | 2023-07-01 | Equipment | 30880351 | 17896052 | 17759995
MCR007844 | HPR046 | 2023-07-01 | Subcontract | 63504387 | 36802618 | 29314170
MCR007845 | HPR046 | 2023-07-01 | Overhead | 22860980 | 13248595 | 14847350
MCR007846 | HPR046 | 2023-08-01 | Labor | 31631678 | 21025125 | 22098156
MCR007847 | HPR046 | 2023-08-01 | Material | 76288828 | 50708097 | 44225729
MCR007848 | HPR046 | 2023-08-01 | Equipment | 29083932 | 19331675 | 19847734
MCR007849 | HPR046 | 2023-08-01 | Subcontract | 59810112 | 39754929 | 46238108
MCR007850 | HPR046 | 2023-08-01 | Overhead | 21531076 | 14311399 | 14433369
MCR007851 | HPR046 | 2023-09-01 | Labor | 26967868 | 24306204 | 27455375
MCR007852 | HPR046 | 2023-09-01 | Material | 65040720 | 58621356 | 57621933
MCR007853 | HPR046 | 2023-09-01 | Equipment | 24795766 | 22348483 | 25070386
MCR007854 | HPR046 | 2023-09-01 | Subcontract | 50991644 | 45958890 | 46155968
MCR007855 | HPR046 | 2023-09-01 | Overhead | 18356510 | 16544767 | 13195420
MCR007856 | HPR046 | 2023-10-01 | Labor | 20097571 | 22728056 | 21248509
MCR007857 | HPR046 | 2023-10-01 | Material | 48471035 | 54815201 | 53638698
MCR007858 | HPR046 | 2023-10-01 | Equipment | 18478830 | 20897445 | 19844891
MCR007859 | HPR046 | 2023-10-01 | Subcontract | 38001082 | 42974881 | 44977893
MCR007860 | HPR046 | 2023-10-01 | Overhead | 13680031 | 15470552 | 13966453
MCR007861 | HPR046 | 2023-11-01 | Labor | 11747665 | 27460540 | 28947392
MCR007862 | HPR046 | 2023-11-01 | Material | 28332851 | 66228938 | 70580856
MCR007863 | HPR046 | 2023-11-01 | Equipment | 10801460 | 25248755 | 27787020
MCR007864 | HPR046 | 2023-11-01 | Subcontract | 22212833 | 51923201 | 50059205
MCR007865 | HPR046 | 2023-11-01 | Overhead | 7996410 | 18691862 | 14819188
MCR007866 | HPR046 | 2023-12-01 | Labor | 3303957 | 10846002 | 14414580
MCR007867 | HPR046 | 2023-12-01 | Material | 7968435 | 26158233 | 17277578
MCR007868 | HPR046 | 2023-12-01 | Equipment | 3037842 | 9972421 | 9970266
MCR007869 | HPR046 | 2023-12-01 | Subcontract | 6247219 | 20507942 | 21881346
MCR007870 | HPR046 | 2023-12-01 | Overhead | 2248940 | 7382666 | 13889176
MCR007871 | HPR046 | 2024-01-01 | Labor | 0 | 5814240 | 5251902
MCR007872 | HPR046 | 2024-01-01 | Material | 0 | 14022700 | 16193183
MCR007873 | HPR046 | 2024-01-01 | Equipment | 0 | 5345937 | 4670109
MCR007874 | HPR046 | 2024-01-01 | Subcontract | 0 | 10993736 | 11755216
MCR007875 | HPR046 | 2024-01-01 | Overhead | 0 | 3957641 | 13707559
MCR007876 | HPR046 | 2024-02-01 | Labor | 0 | 1742529 | 2055323
MCR007877 | HPR046 | 2024-02-01 | Material | 0 | 4202607 | 3971678
MCR007878 | HPR046 | 2024-02-01 | Equipment | 0 | 1602179 | 1662727
MCR007879 | HPR046 | 2024-02-01 | Subcontract | 0 | 3294826 | 2847932
MCR007880 | HPR046 | 2024-02-01 | Overhead | 0 | 1186106 | 14530320
MCR007881 | HPR047 | 2022-09-01 | Labor | 3877091 | 3851096 | 3803891
MCR007882 | HPR047 | 2022-09-01 | Material | 8159924 | 8105214 | 8703669
MCR007883 | HPR047 | 2022-09-01 | Equipment | 1940079 | 1927071 | 1806807
MCR007884 | HPR047 | 2022-09-01 | Subcontract | 11800370 | 11721252 | 10246279
MCR007885 | HPR047 | 2022-09-01 | Overhead | 2802025 | 2783238 | 11715958
MCR007886 | HPR047 | 2022-10-01 | Labor | 10702773 | 8367065 | 8123746
MCR007887 | HPR047 | 2022-10-01 | Material | 22525604 | 17609752 | 17723058
MCR007888 | HPR047 | 2022-10-01 | Equipment | 5355620 | 4186842 | 4770435
MCR007889 | HPR047 | 2022-10-01 | Subcontract | 32575115 | 25466119 | 28090111
MCR007890 | HPR047 | 2022-10-01 | Overhead | 7735035 | 6046988 | 11394023
MCR007891 | HPR047 | 2022-11-01 | Labor | 16170446 | 14662078 | 15036638
MCR007892 | HPR047 | 2022-11-01 | Material | 34033149 | 30858559 | 28407556
MCR007893 | HPR047 | 2022-11-01 | Equipment | 8091619 | 7336838 | 8251210
MCR007894 | HPR047 | 2022-11-01 | Subcontract | 49216605 | 44625712 | 39358399
MCR007895 | HPR047 | 2022-11-01 | Overhead | 11686595 | 10596477 | 10071644
MCR007896 | HPR047 | 2022-12-01 | Labor | 20329191 | 12388113 | 13175689
MCR007897 | HPR047 | 2022-12-01 | Material | 42785855 | 26072657 | 25553311
MCR007898 | HPR047 | 2022-12-01 | Equipment | 10172636 | 6198957 | 5954793
MCR007899 | HPR047 | 2022-12-01 | Subcontract | 61874218 | 37704641 | 34810763
MCR007900 | HPR047 | 2022-12-01 | Overhead | 14692174 | 8953053 | 11717402
MCR007901 | HPR047 | 2023-01-01 | Labor | 23232060 | 22904654 | 23748308
MCR007902 | HPR047 | 2023-01-01 | Material | 48895381 | 48206307 | 47978252
MCR007903 | HPR047 | 2023-01-01 | Equipment | 11625219 | 11461386 | 10454430
MCR007904 | HPR047 | 2023-01-01 | Subcontract | 70709432 | 69712936 | 70825226
MCR007905 | HPR047 | 2023-01-01 | Overhead | 16790116 | 16553496 | 12314854
MCR007906 | HPR047 | 2023-02-01 | Labor | 24936884 | 33148401 | 35234666
MCR007907 | HPR047 | 2023-02-01 | Material | 52483442 | 69765821 | 56126845
MCR007908 | HPR047 | 2023-02-01 | Equipment | 12478305 | 16587312 | 16154301
MCR007909 | HPR047 | 2023-02-01 | Subcontract | 75898261 | 100890953 | 86452426
MCR007910 | HPR047 | 2023-02-01 | Overhead | 18022215 | 23956787 | 10725318
MCR007911 | HPR047 | 2023-03-01 | Labor | 25507347 | 27014855 | 24270479
MCR007912 | HPR047 | 2023-03-01 | Material | 53684067 | 56856847 | 58241492
MCR007913 | HPR047 | 2023-03-01 | Equipment | 12763762 | 13518113 | 14841457
MCR007914 | HPR047 | 2023-03-01 | Subcontract | 77634529 | 82222804 | 76221830
MCR007915 | HPR047 | 2023-03-01 | Overhead | 18434496 | 19523992 | 12375227
MCR007916 | HPR047 | 2023-04-01 | Labor | 25014467 | 15873883 | 19406498
MCR007917 | HPR047 | 2023-04-01 | Material | 52646727 | 33408987 | 31551277
MCR007918 | HPR047 | 2023-04-01 | Equipment | 12517128 | 7943220 | 7804075
MCR007919 | HPR047 | 2023-04-01 | Subcontract | 76134394 | 48313980 | 53216422
MCR007920 | HPR047 | 2023-04-01 | Overhead | 18078285 | 11472265 | 11381765
MCR007921 | HPR047 | 2023-05-01 | Labor | 23538738 | 28340650 | 25997158
MCR007922 | HPR047 | 2023-05-01 | Material | 49540832 | 59647182 | 54451354
MCR007923 | HPR047 | 2023-05-01 | Equipment | 11778679 | 14181534 | 13968875
MCR007924 | HPR047 | 2023-05-01 | Subcontract | 71642843 | 86258011 | 86519120
MCR007925 | HPR047 | 2023-05-01 | Overhead | 17011756 | 20482162 | 12789537
MCR007926 | HPR047 | 2023-06-01 | Labor | 21173346 | 22824094 | 24946204
MCR007927 | HPR047 | 2023-06-01 | Material | 44562506 | 48036756 | 43836146
MCR007928 | HPR047 | 2023-06-01 | Equipment | 10595047 | 11421075 | 11240606
MCR007929 | HPR047 | 2023-06-01 | Subcontract | 64443501 | 69467743 | 64540578
MCR007930 | HPR047 | 2023-06-01 | Overhead | 15302256 | 16495274 | 12462227
MCR007931 | HPR047 | 2023-07-01 | Labor | 18029353 | 10360269 | 11783378
MCR007932 | HPR047 | 2023-07-01 | Material | 37945499 | 21804751 | 19629555
MCR007933 | HPR047 | 2023-07-01 | Equipment | 9021808 | 5184232 | 5885625
MCR007934 | HPR047 | 2023-07-01 | Subcontract | 54874400 | 31532663 | 29196685
MCR007935 | HPR047 | 2023-07-01 | Overhead | 13030052 | 7487503 | 10637433
MCR007936 | HPR047 | 2023-08-01 | Labor | 14244791 | 9583914 | 9175189
MCR007937 | HPR047 | 2023-08-01 | Material | 29980315 | 20170796 | 18305108
MCR007938 | HPR047 | 2023-08-01 | Equipment | 7128030 | 4795748 | 5186217
MCR007939 | HPR047 | 2023-08-01 | Subcontract | 43355651 | 29169739 | 27982763
MCR007940 | HPR047 | 2023-08-01 | Overhead | 10294898 | 6926421 | 10762200
MCR007941 | HPR047 | 2023-09-01 | Labor | 10002792 | 11398342 | 12735132
MCR007942 | HPR047 | 2023-09-01 | Material | 21052388 | 23989533 | 20570829
MCR007943 | HPR047 | 2023-09-01 | Equipment | 5005352 | 5703679 | 5280894
MCR007944 | HPR047 | 2023-09-01 | Subcontract | 30444642 | 34692158 | 38195204
MCR007945 | HPR047 | 2023-09-01 | Overhead | 7229150 | 8237732 | 12024070
MCR007946 | HPR047 | 2023-10-01 | Labor | 5576393 | 12336418 | 10616560
MCR007947 | HPR047 | 2023-10-01 | Material | 11736362 | 25963857 | 25489235
MCR007948 | HPR047 | 2023-10-01 | Equipment | 2790402 | 6173089 | 5950075
MCR007949 | HPR047 | 2023-10-01 | Subcontract | 16972391 | 37547301 | 35217050
MCR007950 | HPR047 | 2023-10-01 | Overhead | 4030133 | 8915692 | 12441811
MCR007951 | HPR047 | 2023-11-01 | Labor | 1513429 | 3197776 | 4840820
MCR007952 | HPR047 | 2023-11-01 | Material | 3185240 | 6730202 | 5185635
MCR007953 | HPR047 | 2023-11-01 | Equipment | 757313 | 1600153 | 1752708
MCR007954 | HPR047 | 2023-11-01 | Subcontract | 4606294 | 9732796 | 8949623
MCR007955 | HPR047 | 2023-11-01 | Overhead | 1093775 | 2311075 | 11927941
MCR007956 | HPR047 | 2023-12-01 | Labor | 0 | 5968080 | 6227314
MCR007957 | HPR047 | 2023-12-01 | Material | 0 | 12560727 | 12470960
MCR007958 | HPR047 | 2023-12-01 | Equipment | 0 | 2986401 | 3002096
MCR007959 | HPR047 | 2023-12-01 | Subcontract | 0 | 18164536 | 18458524
MCR007960 | HPR047 | 2023-12-01 | Overhead | 0 | 4313210 | 12697749
MCR007961 | HPR047 | 2024-01-01 | Labor | 0 | 1629412 | 1503511
MCR007962 | HPR047 | 2024-01-01 | Material | 0 | 3429343 | 2751822
MCR007963 | HPR047 | 2024-01-01 | Equipment | 0 | 815350 | 834050
MCR007964 | HPR047 | 2024-01-01 | Subcontract | 0 | 4959301 | 4241567
MCR007965 | HPR047 | 2024-01-01 | Overhead | 0 | 1177597 | 11270733
MCR007966 | HPR048 | 2021-10-01 | Labor | 50870056 | 38890703 | 32884226
MCR007967 | HPR048 | 2021-10-01 | Material | 99239267 | 75869485 | 76243905
MCR007968 | HPR048 | 2021-10-01 | Equipment | 21636084 | 16541018 | 17054839
MCR007969 | HPR048 | 2021-10-01 | Subcontract | 109554436 | 83755541 | 76599219
MCR007970 | HPR048 | 2021-10-01 | Overhead | 28036500 | 21434205 | 97031618
MCR007971 | HPR048 | 2021-11-01 | Labor | 137244559 | 78629567 | 85169440
MCR007972 | HPR048 | 2021-11-01 | Material | 267741981 | 153393593 | 162777907
MCR007973 | HPR048 | 2021-11-01 | Equipment | 58372941 | 33442776 | 38247493
MCR007974 | HPR048 | 2021-11-01 | Subcontract | 295571727 | 169337692 | 175713587
MCR007975 | HPR048 | 2021-11-01 | Overhead | 75640905 | 43335864 | 98867311
MCR007976 | HPR048 | 2021-12-01 | Labor | 201309637 | 155901568 | 166115630
MCR007977 | HPR048 | 2021-12-01 | Material | 392722607 | 304138794 | 323542637
MCR007978 | HPR048 | 2021-12-01 | Equipment | 85621139 | 66308151 | 66284381
MCR007979 | HPR048 | 2021-12-01 | Subcontract | 433543140 | 335751713 | 356794935
MCR007980 | HPR048 | 2021-12-01 | Overhead | 110949703 | 85923521 | 101958044
MCR007981 | HPR048 | 2022-01-01 | Labor | 244127765 | 170368785 | 168549414
MCR007982 | HPR048 | 2022-01-01 | Material | 476253862 | 332361998 | 338708527
MCR007983 | HPR048 | 2022-01-01 | Equipment | 103832572 | 72461357 | 72946962
MCR007984 | HPR048 | 2022-01-01 | Subcontract | 525756835 | 366908504 | 394165198
MCR007985 | HPR048 | 2022-01-01 | Overhead | 134548467 | 93896976 | 101065944
MCR007986 | HPR048 | 2022-02-01 | Labor | 266877901 | 181122123 | 181809480
MCR007987 | HPR048 | 2022-02-01 | Material | 520635705 | 353340026 | 346001459
MCR007988 | HPR048 | 2022-02-01 | Equipment | 113508674 | 77034973 | 73470183
MCR007989 | HPR048 | 2022-02-01 | Subcontract | 574751834 | 390067039 | 399854976
MCR007990 | HPR048 | 2022-02-01 | Overhead | 147086967 | 99823566 | 87940502
MCR007991 | HPR048 | 2022-03-01 | Labor | 270888435 | 174561140 | 247841970
MCR007992 | HPR048 | 2022-03-01 | Material | 528459610 | 340540607 | 423759439
MCR007993 | HPR048 | 2022-03-01 | Equipment | 115214437 | 74244452 | 85739609
MCR007994 | HPR048 | 2022-03-01 | Subcontract | 583388974 | 375937218 | 337454226
MCR007995 | HPR048 | 2022-03-01 | Overhead | 149297331 | 96207549 | 106373983
MCR007996 | HPR048 | 2022-04-01 | Labor | 257686590 | 251617152 | 292540813
MCR007997 | HPR048 | 2022-04-01 | Material | 502704941 | 490864447 | 614050830
MCR007998 | HPR048 | 2022-04-01 | Equipment | 109599420 | 107017963 | 107637969
MCR007999 | HPR048 | 2022-04-01 | Subcontract | 554957303 | 541886079 | 612403165
MCR008000 | HPR048 | 2022-04-01 | Overhead | 142021272 | 138676164 | 96355637
MCR008001 | HPR048 | 2022-05-01 | Labor | 229077316 | 174488759 | 210343197
MCR008002 | HPR048 | 2022-05-01 | Material | 446892865 | 340399403 | 330372235
MCR008003 | HPR048 | 2022-05-01 | Equipment | 97431305 | 74213667 | 79173931
MCR008004 | HPR048 | 2022-05-01 | Subcontract | 493343985 | 375781336 | 405993030
MCR008005 | HPR048 | 2022-05-01 | Overhead | 126253569 | 96167657 | 100683328
MCR008006 | HPR048 | 2022-06-01 | Labor | 187280673 | 239842300 | 237053000
MCR008007 | HPR048 | 2022-06-01 | Material | 365354363 | 467893613 | 504007801
MCR008008 | HPR048 | 2022-06-01 | Equipment | 79654332 | 102009875 | 100589245
MCR008009 | HPR048 | 2022-06-01 | Subcontract | 403330175 | 516527601 | 539007828
MCR008010 | HPR048 | 2022-06-01 | Overhead | 103217787 | 132186578 | 96928334
MCR008011 | HPR048 | 2022-07-01 | Labor | 135203542 | 179075869 | 191847591
MCR008012 | HPR048 | 2022-07-01 | Material | 263760285 | 349348114 | 379140113
MCR008013 | HPR048 | 2022-07-01 | Equipment | 57504854 | 76164659 | 87419619
MCR008014 | HPR048 | 2022-07-01 | Subcontract | 291176164 | 385660198 | 412643091
MCR008015 | HPR048 | 2022-07-01 | Overhead | 74516020 | 98695794 | 87963515
MCR008016 | HPR048 | 2022-08-01 | Labor | 77103907 | 168409685 | 155895759
MCR008017 | HPR048 | 2022-08-01 | Material | 150417277 | 328540110 | 345522171
MCR008018 | HPR048 | 2022-08-01 | Equipment | 32793882 | 71628111 | 77699194
MCR008019 | HPR048 | 2022-08-01 | Subcontract | 166052011 | 362689360 | 573226182
MCR008020 | HPR048 | 2022-08-01 | Overhead | 42495013 | 92817238 | 97546660
MCR008021 | HPR048 | 2022-09-01 | Labor | 21294026 | 124970925 | 122636349
MCR008022 | HPR048 | 2022-09-01 | Material | 41541207 | 243798102 | 234330073
MCR008023 | HPR048 | 2022-09-01 | Equipment | 9056788 | 53152711 | 54319401
MCR008024 | HPR048 | 2022-09-01 | Subcontract | 45859100 | 269139064 | 330406328
MCR008025 | HPR048 | 2022-09-01 | Overhead | 11735980 | 68876420 | 93822799
MCR008026 | HPR048 | 2022-10-01 | Labor | 0 | 81205289 | 85967359
MCR008027 | HPR048 | 2022-10-01 | Material | 0 | 158418411 | 158826897
MCR008028 | HPR048 | 2022-10-01 | Equipment | 0 | 34538284 | 31851074
MCR008029 | HPR048 | 2022-10-01 | Subcontract | 0 | 174884803 | 251733658
MCR008030 | HPR048 | 2022-10-01 | Overhead | 0 | 44755447 | 101968341
MCR008031 | HPR048 | 2022-11-01 | Labor | 0 | 46202807 | 49908230
MCR008032 | HPR048 | 2022-11-01 | Material | 0 | 90134219 | 71664245
MCR008033 | HPR048 | 2022-11-01 | Equipment | 0 | 19651007 | 21762102
MCR008034 | HPR048 | 2022-11-01 | Subcontract | 0 | 99502986 | 132597202
MCR008035 | HPR048 | 2022-11-01 | Overhead | 0 | 25464194 | 96185950
MCR008036 | HPR048 | 2022-12-01 | Labor | 0 | 13677733 | 15418468
MCR008037 | HPR048 | 2022-12-01 | Material | 0 | 26683049 | 37957335
MCR008038 | HPR048 | 2022-12-01 | Equipment | 0 | 5817422 | 7240638
MCR008039 | HPR048 | 2022-12-01 | Subcontract | 0 | 29456549 | 116242536
MCR008040 | HPR048 | 2022-12-01 | Overhead | 0 | 7538340 | 89332905
MCR008041 | HPR049 | 2019-07-01 | Labor | 6292477 | 2311923 | 2553575
MCR008042 | HPR049 | 2019-07-01 | Material | 10725945 | 3940827 | 4370777
MCR008043 | HPR049 | 2019-07-01 | Equipment | 2069271 | 760272 | 725698
MCR008044 | HPR049 | 2019-07-01 | Subcontract | 9467503 | 3478462 | 3643282
MCR008045 | HPR049 | 2019-07-01 | Overhead | 3117686 | 1145471 | 17133233
MCR008046 | HPR049 | 2019-08-01 | Labor | 17811994 | 9788182 | 10252051
MCR008047 | HPR049 | 2019-08-01 | Material | 30361726 | 16684605 | 17141901
MCR008048 | HPR049 | 2019-08-01 | Equipment | 5857447 | 3218828 | 3800906
MCR008049 | HPR049 | 2019-08-01 | Subcontract | 26799480 | 14727052 | 16481822
MCR008050 | HPR049 | 2019-08-01 | Overhead | 8825174 | 4849676 | 18809713
MCR008051 | HPR049 | 2019-09-01 | Labor | 27760968 | 24080950 | 26753885
MCR008052 | HPR049 | 2019-09-01 | Material | 47320413 | 41047577 | 44775400
MCR008053 | HPR049 | 2019-09-01 | Equipment | 9129151 | 7918983 | 6974629
MCR008054 | HPR049 | 2019-09-01 | Subcontract | 41768456 | 36231593 | 37655677
MCR008055 | HPR049 | 2019-09-01 | Overhead | 13754516 | 11931205 | 19605500
MCR008056 | HPR049 | 2019-10-01 | Labor | 36177696 | 35924928 | 37905179
MCR008057 | HPR049 | 2019-10-01 | Material | 61667285 | 61236425 | 60243913
MCR008058 | HPR049 | 2019-10-01 | Equipment | 11896980 | 11813857 | 12517912
MCR008059 | HPR049 | 2019-10-01 | Subcontract | 54432054 | 54051746 | 56263511
MCR008060 | HPR049 | 2019-10-01 | Overhead | 17924689 | 17799452 | 18504400
MCR008061 | HPR049 | 2019-11-01 | Labor | 43102516 | 20891265 | 24488006
MCR008062 | HPR049 | 2019-11-01 | Material | 73471100 | 35610549 | 31366692
MCR008063 | HPR049 | 2019-11-01 | Equipment | 14174196 | 6870060 | 6728470
MCR008064 | HPR049 | 2019-11-01 | Subcontract | 64850965 | 31432474 | 32625450
MCR008065 | HPR049 | 2019-11-01 | Overhead | 21355677 | 10350837 | 17080971
MCR008066 | HPR049 | 2019-12-01 | Labor | 48578064 | 45166761 | 46503104
MCR008067 | HPR049 | 2019-12-01 | Material | 82804535 | 76989742 | 80047600
MCR008068 | HPR049 | 2019-12-01 | Equipment | 15974822 | 14853020 | 15162499
MCR008069 | HPR049 | 2019-12-01 | Subcontract | 73089337 | 67956776 | 66949884
MCR008070 | HPR049 | 2019-12-01 | Overhead | 24068605 | 22378432 | 18170381
MCR008071 | HPR049 | 2020-01-01 | Labor | 52649593 | 49990675 | 58153694
MCR008072 | HPR049 | 2020-01-01 | Material | 89744728 | 85212425 | 93275959
MCR008073 | HPR049 | 2020-01-01 | Equipment | 17313738 | 16439357 | 18431474
MCR008074 | HPR049 | 2020-01-01 | Subcontract | 79215258 | 75214717 | 83789355
MCR008075 | HPR049 | 2020-01-01 | Overhead | 26085895 | 24768501 | 17994051
MCR008076 | HPR049 | 2020-02-01 | Labor | 55365361 | 38992061 | 42132786
MCR008077 | HPR049 | 2020-02-01 | Material | 94373934 | 66464556 | 60092230
MCR008078 | HPR049 | 2020-02-01 | Equipment | 18206814 | 12822479 | 13089608
MCR008079 | HPR049 | 2020-02-01 | Subcontract | 83301334 | 58666477 | 53315314
MCR008080 | HPR049 | 2020-02-01 | Overhead | 27431455 | 19319100 | 16990856
MCR008081 | HPR049 | 2020-03-01 | Labor | 56777107 | 58845652 | 57631823
MCR008082 | HPR049 | 2020-03-01 | Material | 96780348 | 100306321 | 104877046
MCR008083 | HPR049 | 2020-03-01 | Equipment | 18671064 | 19351302 | 18018157
MCR008084 | HPR049 | 2020-03-01 | Subcontract | 85425411 | 88537692 | 93424731
MCR008085 | HPR049 | 2020-03-01 | Overhead | 28130922 | 29155809 | 17833542
MCR008086 | HPR049 | 2020-04-01 | Labor | 56940659 | 63962356 | 66048343
MCR008087 | HPR049 | 2020-04-01 | Material | 97059134 | 109028083 | 113221236
MCR008088 | HPR049 | 2020-04-01 | Equipment | 18724848 | 21033922 | 22880730
MCR008089 | HPR049 | 2020-04-01 | Subcontract | 85671488 | 96236158 | 93305872
MCR008090 | HPR049 | 2020-04-01 | Overhead | 28211956 | 31690944 | 17877358
MCR008091 | HPR049 | 2020-05-01 | Labor | 55916715 | 41979683 | 47977675
MCR008092 | HPR049 | 2020-05-01 | Material | 95313754 | 71557156 | 68782920
MCR008093 | HPR049 | 2020-05-01 | Equipment | 18388126 | 13804954 | 12288384
MCR008094 | HPR049 | 2020-05-01 | Subcontract | 84130888 | 63161578 | 74371426
MCR008095 | HPR049 | 2020-05-01 | Overhead | 27704631 | 20799355 | 17725522
MCR008096 | HPR049 | 2020-06-01 | Labor | 53771864 | 47434807 | 57363459
MCR008097 | HPR049 | 2020-06-01 | Material | 91657712 | 80855778 | 80853522
MCR008098 | HPR049 | 2020-06-01 | Equipment | 17682795 | 15598863 | 16678846
MCR008099 | HPR049 | 2020-06-01 | Subcontract | 80903798 | 71369222 | 68705851
MCR008100 | HPR049 | 2020-06-01 | Overhead | 26641937 | 23502164 | 16398466
MCR008101 | HPR049 | 2020-07-01 | Labor | 50579965 | 23400070 | 21323204
MCR008102 | HPR049 | 2020-07-01 | Material | 86216908 | 39886973 | 35713785
MCR008103 | HPR049 | 2020-07-01 | Equipment | 16633143 | 7695077 | 8322446
MCR008104 | HPR049 | 2020-07-01 | Subcontract | 76101346 | 35207159 | 35290356
MCR008105 | HPR049 | 2020-07-01 | Overhead | 25060471 | 11593855 | 19877266
MCR008106 | HPR049 | 2020-08-01 | Labor | 46424075 | 37784477 | 39624605
MCR008107 | HPR049 | 2020-08-01 | Material | 79132918 | 64406149 | 78484625
MCR008108 | HPR049 | 2020-08-01 | Equipment | 15266486 | 12425367 | 12257997
MCR008109 | HPR049 | 2020-08-01 | Subcontract | 69848499 | 56849576 | 63570670
MCR008110 | HPR049 | 2020-08-01 | Overhead | 23001384 | 18720788 | 15729057
MCR008111 | HPR049 | 2020-09-01 | Labor | 41399236 | 57107495 | 62374885
MCR008112 | HPR049 | 2020-09-01 | Material | 70567746 | 97343517 | 93320966
MCR008113 | HPR049 | 2020-09-01 | Equipment | 13614075 | 18779712 | 18895078
MCR008114 | HPR049 | 2020-09-01 | Subcontract | 62288252 | 85922505 | 80943366
MCR008115 | HPR049 | 2020-09-01 | Overhead | 20511765 | 28294617 | 16679822
MCR008116 | HPR049 | 2020-10-01 | Labor | 35616711 | 39359334 | 44014626
MCR008117 | HPR049 | 2020-10-01 | Material | 60711049 | 67090598 | 66955907
MCR008118 | HPR049 | 2020-10-01 | Equipment | 11712501 | 12943256 | 10877079
MCR008119 | HPR049 | 2020-10-01 | Subcontract | 53588011 | 59219067 | 56685383
MCR008120 | HPR049 | 2020-10-01 | Overhead | 17646742 | 19501071 | 18705226
MCR008121 | HPR049 | 2020-11-01 | Labor | 29210872 | 46350022 | 44923799
MCR008122 | HPR049 | 2020-11-01 | Material | 49791870 | 79006690 | 81748763
MCR008123 | HPR049 | 2020-11-01 | Equipment | 9605950 | 15242133 | 17037167
MCR008124 | HPR049 | 2020-11-01 | Subcontract | 43949945 | 69737081 | 69261685
MCR008125 | HPR049 | 2020-11-01 | Overhead | 14472889 | 22964694 | 18701972
MCR008126 | HPR049 | 2020-12-01 | Labor | 22351392 | 50353045 | 53377114
MCR008127 | HPR049 | 2020-12-01 | Material | 38099432 | 85830108 | 91152694
MCR008128 | HPR049 | 2020-12-01 | Equipment | 7350221 | 16558521 | 16034707
MCR008129 | HPR049 | 2020-12-01 | Subcontract | 33629345 | 75759929 | 85777559
MCR008130 | HPR049 | 2020-12-01 | Overhead | 11074275 | 24948041 | 19348407
MCR008131 | HPR049 | 2021-01-01 | Labor | 15267865 | 23700454 | 26061108
MCR008132 | HPR049 | 2021-01-01 | Material | 26025090 | 40398997 | 45396935
MCR008133 | HPR049 | 2021-01-01 | Equipment | 5020814 | 7793858 | 7914809
MCR008134 | HPR049 | 2021-01-01 | Subcontract | 22971647 | 35659109 | 30348838
MCR008135 | HPR049 | 2021-01-01 | Overhead | 7564653 | 11742684 | 18267652
MCR008136 | HPR049 | 2021-02-01 | Labor | 8311374 | 16186729 | 16554870
MCR008137 | HPR049 | 2021-02-01 | Material | 14167288 | 27591354 | 23487607
MCR008138 | HPR049 | 2021-02-01 | Equipment | 2733182 | 5322981 | 5252846
MCR008139 | HPR049 | 2021-02-01 | Subcontract | 12505084 | 24354146 | 27395616
MCR008140 | HPR049 | 2021-02-01 | Overhead | 4117973 | 8019916 | 18136360
MCR008141 | HPR049 | 2021-03-01 | Labor | 2213106 | 12790647 | 11795531
MCR008142 | HPR049 | 2021-03-01 | Material | 3772386 | 21802507 | 24097834
MCR008143 | HPR049 | 2021-03-01 | Equipment | 727776 | 4206185 | 5089110
MCR008144 | HPR049 | 2021-03-01 | Subcontract | 3329783 | 19244486 | 19487369
MCR008145 | HPR049 | 2021-03-01 | Overhead | 1096511 | 6337285 | 16518513
MCR008146 | HPR049 | 2021-04-01 | Labor | 0 | 8562844 | 10076886
MCR008147 | HPR049 | 2021-04-01 | Material | 0 | 14595936 | 14498294
MCR008148 | HPR049 | 2021-04-01 | Equipment | 0 | 2815878 | 2616806
MCR008149 | HPR049 | 2021-04-01 | Subcontract | 0 | 12883440 | 12902483
MCR008150 | HPR049 | 2021-04-01 | Overhead | 0 | 4242567 | 18245043
MCR008151 | HPR049 | 2021-05-01 | Labor | 0 | 5553075 | 5586499
MCR008152 | HPR049 | 2021-05-01 | Material | 0 | 9465585 | 10145585
MCR008153 | HPR049 | 2021-05-01 | Equipment | 0 | 1826120 | 1828723
MCR008154 | HPR049 | 2021-05-01 | Subcontract | 0 | 8355017 | 9526748
MCR008155 | HPR049 | 2021-05-01 | Overhead | 0 | 2751340 | 18069614
MCR008156 | HPR049 | 2021-06-01 | Labor | 0 | 2002175 | 1736584
MCR008157 | HPR049 | 2021-06-01 | Material | 0 | 3412841 | 3572588
MCR008158 | HPR049 | 2021-06-01 | Equipment | 0 | 658412 | 757697
MCR008159 | HPR049 | 2021-06-01 | Subcontract | 0 | 3012423 | 2651633
MCR008160 | HPR049 | 2021-06-01 | Overhead | 0 | 992003 | 17409388
MCR008161 | HPR050 | 2017-09-01 | Labor | 21624883 | 9999994 | 10378381
MCR008162 | HPR050 | 2017-09-01 | Material | 44055136 | 20372415 | 21617310
MCR008163 | HPR050 | 2017-09-01 | Equipment | 9830933 | 4546118 | 4927845
MCR008164 | HPR050 | 2017-09-01 | Subcontract | 46752558 | 21619783 | 22566326
MCR008165 | HPR050 | 2017-09-01 | Overhead | 12009547 | 5553574 | 35597658
MCR008166 | HPR050 | 2017-10-01 | Labor | 57719683 | 58117626 | 58730558
MCR008167 | HPR050 | 2017-10-01 | Material | 117589004 | 118399710 | 115456814
MCR008168 | HPR050 | 2017-10-01 | Equipment | 26240065 | 26420974 | 26011823
MCR008169 | HPR050 | 2017-10-01 | Subcontract | 124788781 | 125649125 | 122762300
MCR008170 | HPR050 | 2017-10-01 | Overhead | 32055075 | 32276076 | 40064122
MCR008171 | HPR050 | 2017-11-01 | Labor | 83462332 | 42738348 | 47018800
MCR008172 | HPR050 | 2017-11-01 | Material | 170033028 | 87068388 | 97853641
MCR008173 | HPR050 | 2017-11-01 | Equipment | 37942983 | 19429369 | 19704221
MCR008174 | HPR050 | 2017-11-01 | Subcontract | 180443863 | 92399439 | 94931706
MCR008175 | HPR050 | 2017-11-01 | Overhead | 46351456 | 23735074 | 34160525
MCR008176 | HPR050 | 2017-12-01 | Labor | 99404280 | 90848492 | 96793364
MCR008177 | HPR050 | 2017-12-01 | Material | 202510645 | 185080427 | 158340334
MCR008178 | HPR050 | 2017-12-01 | Equipment | 45190385 | 41300821 | 40217474
MCR008179 | HPR050 | 2017-12-01 | Subcontract | 214910030 | 196412590 | 185796508
MCR008180 | HPR050 | 2017-12-01 | Overhead | 55204940 | 50453417 | 36645348
MCR008181 | HPR050 | 2018-01-01 | Labor | 106165533 | 71957556 | 71048902
MCR008182 | HPR050 | 2018-01-01 | Material | 216284958 | 146595006 | 171679262
MCR008183 | HPR050 | 2018-01-01 | Equipment | 48264133 | 32712773 | 35840486
MCR008184 | HPR050 | 2018-01-01 | Subcontract | 229527722 | 155570771 | 167065630
MCR008185 | HPR050 | 2018-01-01 | Overhead | 58959855 | 39962188 | 40732239
MCR008186 | HPR050 | 2018-02-01 | Labor | 104457060 | 87492336 | 102440591
MCR008187 | HPR050 | 2018-02-01 | Material | 212804383 | 178243124 | 163177392
MCR008188 | HPR050 | 2018-02-01 | Equipment | 47487440 | 39775072 | 41139400
MCR008189 | HPR050 | 2018-02-01 | Subcontract | 225834037 | 189156650 | 167842842
MCR008190 | HPR050 | 2018-02-01 | Overhead | 58011041 | 48589550 | 37124277
MCR008191 | HPR050 | 2018-03-01 | Labor | 95116475 | 63544852 | 61803057
MCR008192 | HPR050 | 2018-03-01 | Material | 193775345 | 129456286 | 126419329
MCR008193 | HPR050 | 2018-03-01 | Equipment | 43241097 | 28888257 | 26343649
MCR008194 | HPR050 | 2018-03-01 | Subcontract | 205639883 | 137382677 | 136943263
MCR008195 | HPR050 | 2018-03-01 | Overhead | 52823674 | 35290128 | 38751230
MCR008196 | HPR050 | 2018-04-01 | Labor | 79169981 | 63364703 | 65996088
MCR008197 | HPR050 | 2018-04-01 | Material | 161288465 | 129089278 | 141615225
MCR008198 | HPR050 | 2018-04-01 | Equipment | 35991629 | 28806359 | 35408367
MCR008199 | HPR050 | 2018-04-01 | Subcontract | 171163886 | 136993197 | 130182326
MCR008200 | HPR050 | 2018-04-01 | Overhead | 43967665 | 35190081 | 38552490
MCR008201 | HPR050 | 2018-05-01 | Labor | 57954419 | 92972896 | 92916927
MCR008202 | HPR050 | 2018-05-01 | Material | 118067218 | 189408355 | 183652261
MCR008203 | HPR050 | 2018-05-01 | Equipment | 26346778 | 42266601 | 42862236
MCR008204 | HPR050 | 2018-05-01 | Subcontract | 125296275 | 201005509 | 199922720
MCR008205 | HPR050 | 2018-05-01 | Overhead | 32185438 | 51633221 | 36342428
MCR008206 | HPR050 | 2018-06-01 | Labor | 33414392 | 74336920 | 116891424
MCR008207 | HPR050 | 2018-06-01 | Material | 68073226 | 151442347 | 184648041
MCR008208 | HPR050 | 2018-06-01 | Equipment | 15190586 | 33794461 | 31832586
MCR008209 | HPR050 | 2018-06-01 | Subcontract | 72241235 | 160714907 | 174313973
MCR008210 | HPR050 | 2018-06-01 | Overhead | 18556943 | 41283587 | 37745843
MCR008211 | HPR050 | 2018-07-01 | Labor | 9303887 | 20626866 | 63897365
MCR008212 | HPR050 | 2018-07-01 | Material | 18954275 | 42021932 | 69933028
MCR008213 | HPR050 | 2018-07-01 | Equipment | 4229659 | 9377222 | 10642770
MCR008214 | HPR050 | 2018-07-01 | Subcontract | 20114813 | 44594864 | 39032501
MCR008215 | HPR050 | 2018-07-01 | Overhead | 5166986 | 11455290 | 36375503
MCR008216 | HPR050 | 2018-08-01 | Labor | 0 | 47051331 | 48273604
MCR008217 | HPR050 | 2018-08-01 | Material | 0 | 95854980 | 103456271
MCR008218 | HPR050 | 2018-08-01 | Equipment | 0 | 21390103 | 20630910
MCR008219 | HPR050 | 2018-08-01 | Subcontract | 0 | 101724019 | 94076561
MCR008220 | HPR050 | 2018-08-01 | Overhead | 0 | 26130323 | 39884727
MCR008221 | HPR050 | 2018-09-01 | Labor | 0 | 21730857 | 19664836
MCR008222 | HPR050 | 2018-09-01 | Material | 0 | 44271029 | 56574159
MCR008223 | HPR050 | 2018-09-01 | Equipment | 0 | 9879110 | 12005767
MCR008224 | HPR050 | 2018-09-01 | Subcontract | 0 | 46981670 | 47957473
MCR008225 | HPR050 | 2018-09-01 | Overhead | 0 | 12068400 | 39381051
MCR008226 | HPR050 | 2018-10-01 | Labor | 0 | 3010150 | 3487846
MCR008227 | HPR050 | 2018-10-01 | Material | 0 | 6132406 | 912352
MCR008228 | HPR050 | 2018-10-01 | Equipment | 0 | 1368450 | 1909564
MCR008229 | HPR050 | 2018-10-01 | Subcontract | 0 | 6507883 | 7144511
MCR008230 | HPR050 | 2018-10-01 | Overhead | 0 | 1671710 | 36756328
MCR008231 | HPR051 | 2017-12-01 | Labor | 7384207 | 3530699 | 3877647
MCR008232 | HPR051 | 2017-12-01 | Material | 15029873 | 7186413 | 6777455
MCR008233 | HPR051 | 2017-12-01 | Equipment | 3103381 | 1483857 | 1441039
MCR008234 | HPR051 | 2017-12-01 | Subcontract | 17759361 | 8491496 | 8824112
MCR008235 | HPR051 | 2017-12-01 | Overhead | 4295159 | 2053696 | 21219167
MCR008236 | HPR051 | 2018-01-01 | Labor | 20767006 | 18575379 | 19288454
MCR008237 | HPR051 | 2018-01-01 | Material | 42269326 | 37808472 | 43288059
MCR008238 | HPR051 | 2018-01-01 | Equipment | 8727805 | 7806724 | 7938665
MCR008239 | HPR051 | 2018-01-01 | Subcontract | 49945612 | 44674648 | 44677860
MCR008240 | HPR051 | 2018-01-01 | Overhead | 12079510 | 10804710 | 21944280
MCR008241 | HPR051 | 2018-02-01 | Labor | 32111390 | 17236058 | 18837375
MCR008242 | HPR051 | 2018-02-01 | Material | 65359775 | 35082407 | 31982372
MCR008243 | HPR051 | 2018-02-01 | Equipment | 13495540 | 7243844 | 7509544
MCR008244 | HPR051 | 2018-02-01 | Subcontract | 77229382 | 41453518 | 44565677
MCR008245 | HPR051 | 2018-02-01 | Overhead | 18678179 | 10025669 | 21841692
MCR008246 | HPR051 | 2018-03-01 | Labor | 41473111 | 27820335 | 28211851
MCR008247 | HPR051 | 2018-03-01 | Material | 84414694 | 56625727 | 59919173
MCR008248 | HPR051 | 2018-03-01 | Equipment | 17430016 | 11692127 | 12953116
MCR008249 | HPR051 | 2018-03-01 | Subcontract | 99744754 | 66909195 | 75512360
MCR008250 | HPR051 | 2018-03-01 | Overhead | 24123595 | 16182208 | 26056211
MCR008251 | HPR051 | 2018-04-01 | Labor | 48911269 | 48465508 | 51154750
MCR008252 | HPR051 | 2018-04-01 | Material | 99554381 | 98647074 | 102020287
MCR008253 | HPR051 | 2018-04-01 | Equipment | 20556071 | 20368729 | 22366521
MCR008254 | HPR051 | 2018-04-01 | Subcontract | 117633871 | 116561793 | 136555558
MCR008255 | HPR051 | 2018-04-01 | Overhead | 28450137 | 28190851 | 19167553
MCR008256 | HPR051 | 2018-05-01 | Labor | 54488807 | 40427614 | 43759318
MCR008257 | HPR051 | 2018-05-01 | Material | 110906945 | 82286683 | 83363777
MCR008258 | HPR051 | 2018-05-01 | Equipment | 22900157 | 16990622 | 14726496
MCR008259 | HPR051 | 2018-05-01 | Subcontract | 131048108 | 97230286 | 91093358
MCR008260 | HPR051 | 2018-05-01 | Overhead | 31694414 | 23515463 | 25728690
MCR008261 | HPR051 | 2018-06-01 | Labor | 58273111 | 37323140 | 41364345
MCR008262 | HPR051 | 2018-06-01 | Material | 118609547 | 75967811 | 76665354
MCR008263 | HPR051 | 2018-06-01 | Equipment | 24490597 | 15685896 | 18090514
MCR008264 | HPR051 | 2018-06-01 | Subcontract | 140149534 | 89763882 | 96875526
MCR008265 | HPR051 | 2018-06-01 | Overhead | 33895623 | 21709689 | 24020215
MCR008266 | HPR051 | 2018-07-01 | Labor | 60336777 | 39882708 | 39093310
MCR008267 | HPR051 | 2018-07-01 | Material | 122809948 | 81177577 | 79073174
MCR008268 | HPR051 | 2018-07-01 | Equipment | 25357899 | 16761613 | 16543123
MCR008269 | HPR051 | 2018-07-01 | Subcontract | 145112745 | 95919763 | 101931046
MCR008270 | HPR051 | 2018-07-01 | Overhead | 35095992 | 23198509 | 21300832
MCR008271 | HPR051 | 2018-08-01 | Labor | 60758590 | 31880733 | 37260962
MCR008272 | HPR051 | 2018-08-01 | Material | 123668510 | 64890294 | 73259862
MCR008273 | HPR051 | 2018-08-01 | Equipment | 25535176 | 13398601 | 13444139
MCR008274 | HPR051 | 2018-08-01 | Subcontract | 146127225 | 76674641 | 78469558
MCR008275 | HPR051 | 2018-08-01 | Overhead | 35341348 | 18544013 | 22682000
MCR008276 | HPR051 | 2018-09-01 | Labor | 59624812 | 49889069 | 65399639
MCR008277 | HPR051 | 2018-09-01 | Material | 121360809 | 101544603 | 109416605
MCR008278 | HPR051 | 2018-09-01 | Equipment | 25058680 | 20967013 | 24024546
MCR008279 | HPR051 | 2018-09-01 | Subcontract | 143400436 | 119985525 | 115529450
MCR008280 | HPR051 | 2018-09-01 | Overhead | 34681865 | 29018892 | 23795091
MCR008281 | HPR051 | 2018-10-01 | Labor | 57030910 | 61946195 | 62291168
MCR008282 | HPR051 | 2018-10-01 | Material | 116081161 | 126085771 | 139563184
MCR008283 | HPR051 | 2018-10-01 | Equipment | 23968534 | 26034294 | 25407250
MCR008284 | HPR051 | 2018-10-01 | Subcontract | 137161982 | 148983472 | 137674164
MCR008285 | HPR051 | 2018-10-01 | Overhead | 33173074 | 36032140 | 22017682
MCR008286 | HPR051 | 2018-11-01 | Labor | 53083966 | 52938938 | 58684605
MCR008287 | HPR051 | 2018-11-01 | Material | 108047521 | 107752330 | 114322320
MCR008288 | HPR051 | 2018-11-01 | Equipment | 22309741 | 22248790 | 23879696
MCR008289 | HPR051 | 2018-11-01 | Subcontract | 127669400 | 127320601 | 150789511
MCR008290 | HPR051 | 2018-11-01 | Overhead | 30877262 | 30792904 | 22059457
MCR008291 | HPR051 | 2018-12-01 | Labor | 47906155 | 43891879 | 43943416
MCR008292 | HPR051 | 2018-12-01 | Material | 97508563 | 89337875 | 88972543
MCR008293 | HPR051 | 2018-12-01 | Equipment | 20133649 | 18446558 | 14319716
MCR008294 | HPR051 | 2018-12-01 | Subcontract | 115216524 | 105562004 | 113222937
MCR008295 | HPR051 | 2018-12-01 | Overhead | 27865493 | 25530516 | 21810503
MCR008296 | HPR051 | 2019-01-01 | Labor | 41640025 | 54109818 | 61768249
MCR008297 | HPR051 | 2019-01-01 | Material | 84754433 | 110135548 | 124551724
MCR008298 | HPR051 | 2019-01-01 | Equipment | 17500165 | 22740879 | 23679334
MCR008299 | HPR051 | 2019-01-01 | Subcontract | 100146191 | 130136622 | 148399110
MCR008300 | HPR051 | 2019-01-01 | Overhead | 24220684 | 31473968 | 20879615
MCR008301 | HPR051 | 2019-02-01 | Labor | 34457046 | 59966863 | 66350238
MCR008302 | HPR051 | 2019-02-01 | Material | 70134141 | 122057023 | 113585772
MCR008303 | HPR051 | 2019-02-01 | Equipment | 14481355 | 25202435 | 23988232
MCR008304 | HPR051 | 2019-02-01 | Subcontract | 82870793 | 144223087 | 131529276
MCR008305 | HPR051 | 2019-02-01 | Overhead | 20042572 | 34880825 | 21620204
MCR008306 | HPR051 | 2019-03-01 | Labor | 26572720 | 26557555 | 26506748
MCR008307 | HPR051 | 2019-03-01 | Material | 54086323 | 54055455 | 55644822
MCR008308 | HPR051 | 2019-03-01 | Equipment | 11167788 | 11161415 | 12943044
MCR008309 | HPR051 | 2019-03-01 | Subcontract | 63908624 | 63872151 | 132599209
MCR008310 | HPR051 | 2019-03-01 | Overhead | 15456510 | 15447689 | 21190994
MCR008311 | HPR051 | 2019-04-01 | Labor | 18276972 | 34549555 | 32275883
MCR008312 | HPR051 | 2019-04-01 | Material | 37201093 | 70322435 | 87007814
MCR008313 | HPR051 | 2019-04-01 | Equipment | 7681312 | 14520234 | 15204098
MCR008314 | HPR051 | 2019-04-01 | Subcontract | 43956966 | 83093282 | 139940973
MCR008315 | HPR051 | 2019-04-01 | Overhead | 10631136 | 20096382 | 22966375
MCR008316 | HPR051 | 2019-05-01 | Labor | 10009915 | 51926195 | 58501218
MCR008317 | HPR051 | 2019-05-01 | Material | 20374259 | 105690985 | 113239899
MCR008318 | HPR051 | 2019-05-01 | Equipment | 4206894 | 21823162 | 22852897
MCR008319 | HPR051 | 2019-05-01 | Subcontract | 24074309 | 124884908 | 168631222
MCR008320 | HPR051 | 2019-05-01 | Overhead | 5822450 | 30203824 | 21001778
MCR008321 | HPR051 | 2019-06-01 | Labor | 2678559 | 19302523 | 23087853
MCR008322 | HPR051 | 2019-06-01 | Material | 5451960 | 39288507 | 44818232
MCR008323 | HPR051 | 2019-06-01 | Equipment | 1125725 | 8112323 | 7357072
MCR008324 | HPR051 | 2019-06-01 | Subcontract | 6442058 | 46423464 | 81756115
MCR008325 | HPR051 | 2019-06-01 | Overhead | 1558033 | 11227667 | 20686057
MCR008326 | HPR051 | 2019-07-01 | Labor | 0 | 8876681 | 7418931
MCR008327 | HPR051 | 2019-07-01 | Material | 0 | 18067666 | 15458086
MCR008328 | HPR051 | 2019-07-01 | Equipment | 0 | 3730627 | 3433965
MCR008329 | HPR051 | 2019-07-01 | Subcontract | 0 | 21348829 | 70132783
MCR008330 | HPR051 | 2019-07-01 | Overhead | 0 | 5163284 | 24190034
MCR008331 | HPR051 | 2019-08-01 | Labor | 0 | 3923093 | 5241566
MCR008332 | HPR051 | 2019-08-01 | Material | 0 | 7985095 | 9772200
MCR008333 | HPR051 | 2019-08-01 | Equipment | 0 | 1648769 | 1810602
MCR008334 | HPR051 | 2019-08-01 | Subcontract | 0 | 9435221 | 58479375
MCR008335 | HPR051 | 2019-08-01 | Overhead | 0 | 2281939 | 20999800
MCR008336 | HPR051 | 2019-09-01 | Labor | 0 | 2764806 | 2598647
MCR008337 | HPR051 | 2019-09-01 | Material | 0 | 5627507 | 6106927
MCR008338 | HPR051 | 2019-09-01 | Equipment | 0 | 1161972 | 1079911
MCR008339 | HPR051 | 2019-09-01 | Subcontract | 0 | 6649486 | 52548516
MCR008340 | HPR051 | 2019-09-01 | Overhead | 0 | 1608200 | 25426829
MCR008341 | HPR052 | 2016-12-01 | Labor | 2798599 | 1645282 | 1665575
MCR008342 | HPR052 | 2016-12-01 | Material | 6355047 | 3736099 | 4205430
MCR008343 | HPR052 | 2016-12-01 | Equipment | 1609514 | 946225 | 906473
MCR008344 | HPR052 | 2016-12-01 | Subcontract | 7439805 | 4373822 | 4303624
MCR008345 | HPR052 | 2016-12-01 | Overhead | 1846924 | 1085797 | 12123668
MCR008346 | HPR052 | 2017-01-01 | Labor | 7982493 | 7844864 | 7496231
MCR008347 | HPR052 | 2017-01-01 | Material | 18126610 | 17814083 | 19097897
MCR008348 | HPR052 | 2017-01-01 | Equipment | 4590845 | 4511693 | 4766174
MCR008349 | HPR052 | 2017-01-01 | Subcontract | 21220683 | 20854810 | 18208647
MCR008350 | HPR052 | 2017-01-01 | Overhead | 5268014 | 5177186 | 12257145
MCR008351 | HPR052 | 2017-02-01 | Labor | 12555713 | 13824603 | 14197148
MCR008352 | HPR052 | 2017-02-01 | Material | 28511459 | 31392848 | 33985188
MCR008353 | HPR052 | 2017-02-01 | Equipment | 7220969 | 7950725 | 6922744
MCR008354 | HPR052 | 2017-02-01 | Subcontract | 33378146 | 36751366 | 37713696
MCR008355 | HPR052 | 2017-02-01 | Overhead | 8286092 | 9123491 | 11342210
MCR008356 | HPR052 | 2017-03-01 | Labor | 16531069 | 18696527 | 18758792
MCR008357 | HPR052 | 2017-03-01 | Material | 37538680 | 42455990 | 40920883
MCR008358 | HPR052 | 2017-03-01 | Equipment | 9507252 | 10752638 | 11741091
MCR008359 | HPR052 | 2017-03-01 | Subcontract | 43946244 | 49702902 | 52260221
MCR008360 | HPR052 | 2017-03-01 | Overhead | 10909612 | 12338697 | 12165217
MCR008361 | HPR052 | 2017-04-01 | Labor | 19921952 | 15254204 | 16082127
MCR008362 | HPR052 | 2017-04-01 | Material | 45238680 | 34639178 | 39380271
MCR008363 | HPR052 | 2017-04-01 | Equipment | 11457397 | 8772909 | 9785035
MCR008364 | HPR052 | 2017-04-01 | Subcontract | 52960576 | 40551820 | 33419737
MCR008365 | HPR052 | 2017-04-01 | Overhead | 13147411 | 10066950 | 13125729
MCR008366 | HPR052 | 2017-05-01 | Labor | 22742397 | 27184426 | 27736836
MCR008367 | HPR052 | 2017-05-01 | Material | 51643334 | 61730274 | 67885519
MCR008368 | HPR052 | 2017-05-01 | Equipment | 13079475 | 15634149 | 16036519
MCR008369 | HPR052 | 2017-05-01 | Subcontract | 60458455 | 72267158 | 67251316
MCR008370 | HPR052 | 2017-05-01 | Overhead | 15008752 | 17940251 | 11916334
MCR008371 | HPR052 | 2017-06-01 | Labor | 25007160 | 22564384 | 21744688
MCR008372 | HPR052 | 2017-06-01 | Material | 56786148 | 51239104 | 53089572
MCR008373 | HPR052 | 2017-06-01 | Equipment | 14381972 | 12977097 | 14689922
MCR008374 | HPR052 | 2017-06-01 | Subcontract | 66479107 | 59985226 | 55799366
MCR008375 | HPR052 | 2017-06-01 | Overhead | 16503373 | 14891274 | 12626016
MCR008376 | HPR052 | 2017-07-01 | Labor | 26731804 | 13934822 | 17129971
MCR008377 | HPR052 | 2017-07-01 | Material | 60702463 | 31643131 | 32396368
MCR008378 | HPR052 | 2017-07-01 | Equipment | 15373840 | 8014113 | 6392882
MCR008379 | HPR052 | 2017-07-01 | Subcontract | 71063907 | 37044371 | 45485498
MCR008380 | HPR052 | 2017-07-01 | Overhead | 17641546 | 9196229 | 12828788
MCR008381 | HPR052 | 2017-08-01 | Labor | 27932807 | 16131764 | 17859082
MCR008382 | HPR052 | 2017-08-01 | Material | 63429694 | 36631937 | 35334257
MCR008383 | HPR052 | 2017-08-01 | Equipment | 16064553 | 9277606 | 8908420
MCR008384 | HPR052 | 2017-08-01 | Subcontract | 74256656 | 42884728 | 35834765
MCR008385 | HPR052 | 2017-08-01 | Overhead | 18434142 | 10646092 | 12042937
MCR008386 | HPR052 | 2017-09-01 | Labor | 28627684 | 20103796 | 18690762
MCR008387 | HPR052 | 2017-09-01 | Material | 65007618 | 45651611 | 40778329
MCR008388 | HPR052 | 2017-09-01 | Equipment | 16464187 | 11561978 | 13067195
MCR008389 | HPR052 | 2017-09-01 | Subcontract | 76103919 | 53443991 | 51811027
MCR008390 | HPR052 | 2017-09-01 | Overhead | 18892724 | 13267418 | 13047120
MCR008391 | HPR052 | 2017-10-01 | Labor | 28835150 | 25790422 | 24466881
MCR008392 | HPR052 | 2017-10-01 | Material | 65478730 | 58564777 | 63022229
MCR008393 | HPR052 | 2017-10-01 | Equipment | 16583503 | 14832438 | 14795030
MCR008394 | HPR052 | 2017-10-01 | Subcontract | 76655447 | 68561335 | 66944410
MCR008395 | HPR052 | 2017-10-01 | Overhead | 19029640 | 17020284 | 11941720
MCR008396 | HPR052 | 2017-11-01 | Labor | 28575309 | 17094426 | 20899547
MCR008397 | HPR052 | 2017-11-01 | Material | 64888686 | 38817947 | 42555485
MCR008398 | HPR052 | 2017-11-01 | Equipment | 16434066 | 9831247 | 10178449
MCR008399 | HPR052 | 2017-11-01 | Subcontract | 75964687 | 45443873 | 39859520
MCR008400 | HPR052 | 2017-11-01 | Overhead | 18858159 | 11281397 | 12748911
MCR008401 | HPR052 | 2017-12-01 | Labor | 27869905 | 45594649 | 49013121
MCR008402 | HPR052 | 2017-12-01 | Material | 63286858 | 103536128 | 104804606
MCR008403 | HPR052 | 2017-12-01 | Equipment | 16028378 | 26222129 | 25279857
MCR008404 | HPR052 | 2017-12-01 | Subcontract | 74089439 | 121208951 | 113224387
MCR008405 | HPR052 | 2017-12-01 | Overhead | 18392631 | 30090004 | 11926464
MCR008406 | HPR052 | 2018-01-01 | Labor | 26742634 | 28730841 | 27247201
MCR008407 | HPR052 | 2018-01-01 | Material | 60727056 | 65241866 | 70623793
MCR008408 | HPR052 | 2018-01-01 | Equipment | 15380068 | 16523514 | 17425460
MCR008409 | HPR052 | 2018-01-01 | Subcontract | 71092698 | 76378152 | 85842613
MCR008410 | HPR052 | 2018-01-01 | Overhead | 17648693 | 18960802 | 11622999
MCR008411 | HPR052 | 2018-02-01 | Labor | 25219564 | 25904128 | 24515277
MCR008412 | HPR052 | 2018-02-01 | Material | 57268474 | 58822979 | 57116009
MCR008413 | HPR052 | 2018-02-01 | Equipment | 14504129 | 14897831 | 14698786
MCR008414 | HPR052 | 2018-02-01 | Subcontract | 67043764 | 68863610 | 67891419
MCR008415 | HPR052 | 2018-02-01 | Overhead | 16643549 | 17095324 | 12268434
MCR008416 | HPR052 | 2018-03-01 | Labor | 23329699 | 27046738 | 32341155
MCR008417 | HPR052 | 2018-03-01 | Material | 52976977 | 61417614 | 71008661
MCR008418 | HPR052 | 2018-03-01 | Equipment | 13417241 | 15554963 | 14964517
MCR008419 | HPR052 | 2018-03-01 | Subcontract | 62019740 | 71901129 | 68282083
MCR008420 | HPR052 | 2018-03-01 | Overhead | 15396340 | 17849385 | 11875251
MCR008421 | HPR052 | 2018-04-01 | Labor | 21105767 | 18439665 | 16374560
MCR008422 | HPR052 | 2018-04-01 | Material | 47926882 | 41872710 | 42054760
MCR008423 | HPR052 | 2018-04-01 | Equipment | 12138226 | 10604913 | 10382609
MCR008424 | HPR052 | 2018-04-01 | Subcontract | 56107633 | 49020060 | 45274293
MCR008425 | HPR052 | 2018-04-01 | Overhead | 13928665 | 12169182 | 12472235
MCR008426 | HPR052 | 2018-05-01 | Labor | 18585368 | 22038933 | 25479304
MCR008427 | HPR052 | 2018-05-01 | Material | 42203571 | 50045911 | 54050711
MCR008428 | HPR052 | 2018-05-01 | Equipment | 10688709 | 12674903 | 13267078
MCR008429 | HPR052 | 2018-05-01 | Subcontract | 49407397 | 58588364 | 56068167
MCR008430 | HPR052 | 2018-05-01 | Overhead | 12265338 | 14544504 | 11838909
MCR008431 | HPR052 | 2018-06-01 | Labor | 15812719 | 16499101 | 15882646
MCR008432 | HPR052 | 2018-06-01 | Material | 35907452 | 37466085 | 37407174
MCR008433 | HPR052 | 2018-06-01 | Equipment | 9094119 | 9488867 | 9647503
MCR008434 | HPR052 | 2018-06-01 | Subcontract | 42036579 | 43861258 | 45663084
MCR008435 | HPR052 | 2018-06-01 | Overhead | 10435540 | 10888515 | 12836852
MCR008436 | HPR052 | 2018-07-01 | Labor | 12841503 | 7807336 | 8448470
MCR008437 | HPR052 | 2018-07-01 | Material | 29160429 | 17728864 | 17151598
MCR008438 | HPR052 | 2018-07-01 | Equipment | 7385331 | 4490110 | 4321513
MCR008439 | HPR052 | 2018-07-01 | Subcontract | 34137890 | 20755045 | 18467258
MCR008440 | HPR052 | 2018-07-01 | Overhead | 8474698 | 5152420 | 12056714
MCR008441 | HPR052 | 2018-08-01 | Labor | 9739933 | 11979980 | 14788856
MCR008442 | HPR052 | 2018-08-01 | Material | 22117396 | 27204086 | 31897335
MCR008443 | HPR052 | 2018-08-01 | Equipment | 5601573 | 6889856 | 8259329
MCR008444 | HPR052 | 2018-08-01 | Subcontract | 25892666 | 31847615 | 28007128
MCR008445 | HPR052 | 2018-08-01 | Overhead | 6427829 | 7906139 | 11160904
MCR008446 | HPR052 | 2018-09-01 | Labor | 6601004 | 10344532 | 11625314
MCR008447 | HPR052 | 2018-09-01 | Material | 14989530 | 23490318 | 24823416
MCR008448 | HPR052 | 2018-09-01 | Equipment | 3796331 | 5949287 | 5912572
MCR008449 | HPR052 | 2018-09-01 | Subcontract | 17548128 | 27499935 | 29600994
MCR008450 | HPR052 | 2018-09-01 | Overhead | 4356306 | 6826832 | 11972608
MCR008451 | HPR052 | 2018-10-01 | Labor | 3568264 | 7715476 | 7514852
MCR008452 | HPR052 | 2018-10-01 | Material | 8102799 | 17520270 | 21070107
MCR008453 | HPR052 | 2018-10-01 | Equipment | 2052159 | 4437280 | 4540669
MCR008454 | HPR052 | 2018-10-01 | Subcontract | 9485884 | 20510845 | 19897461
MCR008455 | HPR052 | 2018-10-01 | Overhead | 2354862 | 5091797 | 11860551
MCR008456 | HPR052 | 2018-11-01 | Labor | 944663 | 9931093 | 10141882
MCR008457 | HPR052 | 2018-11-01 | Material | 2145136 | 22551482 | 24030327
MCR008458 | HPR052 | 2018-11-01 | Equipment | 543289 | 5711512 | 6039393
MCR008459 | HPR052 | 2018-11-01 | Subcontract | 2511295 | 26400847 | 27633629
MCR008460 | HPR052 | 2018-11-01 | Overhead | 623426 | 6553984 | 11202396
MCR008461 | HPR052 | 2018-12-01 | Labor | 0 | 4615767 | 5887409
MCR008462 | HPR052 | 2018-12-01 | Material | 0 | 10481464 | 9583274
MCR008463 | HPR052 | 2018-12-01 | Equipment | 0 | 2654593 | 2754496
MCR008464 | HPR052 | 2018-12-01 | Subcontract | 0 | 12270570 | 11168156
MCR008465 | HPR052 | 2018-12-01 | Overhead | 0 | 3046157 | 12675546
MCR008466 | HPR052 | 2019-01-01 | Labor | 0 | 3166874 | 3660199
MCR008467 | HPR052 | 2019-01-01 | Material | 0 | 7191323 | 7410704
MCR008468 | HPR052 | 2019-01-01 | Equipment | 0 | 1821314 | 1526504
MCR008469 | HPR052 | 2019-01-01 | Subcontract | 0 | 8418827 | 7441849
MCR008470 | HPR052 | 2019-01-01 | Overhead | 0 | 2089965 | 12206373
MCR008471 | HPR052 | 2019-02-01 | Labor | 0 | 718527 | 861372
MCR008472 | HPR052 | 2019-02-01 | Material | 0 | 1631627 | 1597198
MCR008473 | HPR052 | 2019-02-01 | Equipment | 0 | 413235 | 529312
MCR008474 | HPR052 | 2019-02-01 | Subcontract | 0 | 1910134 | 1851832
MCR008475 | HPR052 | 2019-02-01 | Overhead | 0 | 474189 | 12000931
MCR008476 | HPR053 | 2022-12-01 | Labor | 5195964 | 3000181 | 3482097
MCR008477 | HPR053 | 2022-12-01 | Material | 13326470 | 7694784 | 7588221
MCR008478 | HPR053 | 2022-12-01 | Equipment | 5015497 | 2895978 | 3182349
MCR008479 | HPR053 | 2022-12-01 | Subcontract | 11430831 | 6600230 | 7407559
MCR008480 | HPR053 | 2022-12-01 | Overhead | 4410259 | 2546510 | 35330432
MCR008481 | HPR053 | 2023-01-01 | Labor | 14907484 | 14427628 | 18840656
MCR008482 | HPR053 | 2023-01-01 | Material | 38234321 | 37003599 | 41636219
MCR008483 | HPR053 | 2023-01-01 | Equipment | 14389715 | 13926525 | 16369597
MCR008484 | HPR053 | 2023-01-01 | Subcontract | 32795636 | 31739979 | 33415606
MCR008485 | HPR053 | 2023-01-01 | Overhead | 12653258 | 12245963 | 33155463
MCR008486 | HPR053 | 2023-02-01 | Labor | 23611884 | 19437268 | 22576480
MCR008487 | HPR053 | 2023-02-01 | Material | 60559132 | 49852189 | 49353802
MCR008488 | HPR053 | 2023-02-01 | Equipment | 22791791 | 18762169 | 18916255
MCR008489 | HPR053 | 2023-02-01 | Subcontract | 51944829 | 42760907 | 43007320
MCR008490 | HPR053 | 2023-02-01 | Overhead | 20041427 | 16498073 | 32224369
MCR008491 | HPR053 | 2023-03-01 | Labor | 31327694 | 15513979 | 17406141
MCR008492 | HPR053 | 2023-03-01 | Material | 80348437 | 39789842 | 35478262
MCR008493 | HPR053 | 2023-03-01 | Equipment | 30239614 | 14975145 | 14267032
MCR008494 | HPR053 | 2023-03-01 | Subcontract | 68919181 | 34129891 | 37095766
MCR008495 | HPR053 | 2023-03-01 | Overhead | 26590495 | 13168042 | 31954503
MCR008496 | HPR053 | 2023-04-01 | Labor | 38074181 | 23895372 | 28398331
MCR008497 | HPR053 | 2023-04-01 | Material | 97651649 | 61286216 | 58578138
MCR008498 | HPR053 | 2023-04-01 | Equipment | 36751781 | 23065433 | 22710383
MCR008499 | HPR053 | 2023-04-01 | Subcontract | 83761079 | 52568488 | 57012607
MCR008500 | HPR053 | 2023-04-01 | Overhead | 32316816 | 20282048 | 32612810
MCR008501 | HPR053 | 2023-05-01 | Labor | 43871418 | 22243928 | 24724338
MCR008502 | HPR053 | 2023-05-01 | Material | 112520248 | 57050636 | 58001222
MCR008503 | HPR053 | 2023-05-01 | Equipment | 42347667 | 21471347 | 25164876
MCR008504 | HPR053 | 2023-05-01 | Subcontract | 96514676 | 48935402 | 48713191
MCR008505 | HPR053 | 2023-05-01 | Overhead | 37237427 | 18880325 | 30509176
MCR008506 | HPR053 | 2023-06-01 | Labor | 48740357 | 22931201 | 25368172
MCR008507 | HPR053 | 2023-06-01 | Material | 125007975 | 58813335 | 63670458
MCR008508 | HPR053 | 2023-06-01 | Equipment | 47047498 | 22134750 | 22593278
MCR008509 | HPR053 | 2023-06-01 | Subcontract | 107226072 | 50447364 | 54954934
MCR008510 | HPR053 | 2023-06-01 | Overhead | 41370113 | 19463673 | 31425060
MCR008511 | HPR053 | 2023-07-01 | Labor | 52702931 | 18763045 | 23249429
MCR008512 | HPR053 | 2023-07-01 | Material | 135171079 | 48122960 | 46901322
MCR008513 | HPR053 | 2023-07-01 | Equipment | 50872442 | 18111363 | 19775837
MCR008514 | HPR053 | 2023-07-01 | Subcontract | 115943513 | 41277654 | 40355131
MCR008515 | HPR053 | 2023-07-01 | Overhead | 44733488 | 15925802 | 31591029
MCR008516 | HPR053 | 2023-08-01 | Labor | 55782152 | 29411015 | 32897391
MCR008517 | HPR053 | 2023-08-01 | Material | 143068583 | 75432590 | 83206776
MCR008518 | HPR053 | 2023-08-01 | Equipment | 53844715 | 28389506 | 31491313
MCR008519 | HPR053 | 2023-08-01 | Subcontract | 122717628 | 64702595 | 73667009
MCR008520 | HPR053 | 2023-08-01 | Overhead | 47347087 | 24963646 | 33367825
MCR008521 | HPR053 | 2023-09-01 | Labor | 58002244 | 36937764 | 41878573
MCR008522 | HPR053 | 2023-09-01 | Material | 148762615 | 94736996 | 82590481
MCR008523 | HPR053 | 2023-09-01 | Equipment | 55987698 | 35654834 | 35375555
MCR008524 | HPR053 | 2023-09-01 | Subcontract | 127601706 | 81261024 | 91080088
MCR008525 | HPR053 | 2023-09-01 | Overhead | 49231469 | 31352242 | 30411311
MCR008526 | HPR053 | 2023-10-01 | Labor | 59388789 | 67732757 | 82214285
MCR008527 | HPR053 | 2023-10-01 | Material | 152318791 | 173719177 | 179864897
MCR008528 | HPR053 | 2023-10-01 | Equipment | 57326086 | 65380249 | 74197095
MCR008529 | HPR053 | 2023-10-01 | Subcontract | 130652030 | 149008293 | 152788004
MCR008530 | HPR053 | 2023-10-01 | Overhead | 50408349 | 57490588 | 32634604
MCR008531 | HPR053 | 2023-11-01 | Labor | 59968912 | 51735831 | 58393817
MCR008532 | HPR053 | 2023-11-01 | Material | 153806674 | 132690686 | 135000780
MCR008533 | HPR053 | 2023-11-01 | Equipment | 57886060 | 49938932 | 44012016
MCR008534 | HPR053 | 2023-11-01 | Subcontract | 131928267 | 113815947 | 127263888
MCR008535 | HPR053 | 2023-11-01 | Overhead | 50900749 | 43912628 | 31425793
MCR008536 | HPR053 | 2023-12-01 | Labor | 59771493 | 49432243 | 64997475
MCR008537 | HPR053 | 2023-12-01 | Material | 153300339 | 126782506 | 124910321
MCR008538 | HPR053 | 2023-12-01 | Equipment | 57695498 | 47715353 | 51579623
MCR008539 | HPR053 | 2023-12-01 | Subcontract | 131493957 | 108748183 | 103680193
MCR008540 | HPR053 | 2023-12-01 | Overhead | 50733182 | 41957376 | 33618993
MCR008541 | HPR053 | 2024-01-01 | Labor | 58827439 | 29603535 | 30294971
MCR008542 | HPR053 | 2024-01-01 | Material | 150879054 | 75926360 | 67471274
MCR008543 | HPR053 | 2024-01-01 | Equipment | 56784233 | 28575339 | 33065699
MCR008544 | HPR053 | 2024-01-01 | Subcontract | 129417090 | 65126128 | 70488849
MCR008545 | HPR053 | 2024-01-01 | Overhead | 49931883 | 25127054 | 32837289
MCR008546 | HPR053 | 2024-02-01 | Labor | 57170017 | 31706601 | 39837423
MCR008547 | HPR053 | 2024-02-01 | Material | 146628141 | 81320249 | 78011631
MCR008548 | HPR053 | 2024-02-01 | Equipment | 55184376 | 30605361 | 28174097
MCR008549 | HPR053 | 2024-02-01 | Subcontract | 125770853 | 69752757 | 81677038
MCR008550 | HPR053 | 2024-02-01 | Overhead | 48525086 | 26912106 | 30925330
MCR008551 | HPR053 | 2024-03-01 | Labor | 54835275 | 66621265 | 87022334
MCR008552 | HPR053 | 2024-03-01 | Material | 140640057 | 170868452 | 172754051
MCR008553 | HPR053 | 2024-03-01 | Equipment | 52930725 | 64307362 | 71011997
MCR008554 | HPR053 | 2024-03-01 | Subcontract | 120634551 | 146563073 | 152673958
MCR008555 | HPR053 | 2024-03-01 | Overhead | 46543391 | 56547170 | 34449788
MCR008556 | HPR053 | 2024-04-01 | Labor | 51862590 | 48019769 | 53412215
MCR008557 | HPR053 | 2024-04-01 | Material | 133015795 | 123159829 | 128542205
MCR008558 | HPR053 | 2024-04-01 | Equipment | 50061288 | 46351937 | 49159357
MCR008559 | HPR053 | 2024-04-01 | Subcontract | 114094810 | 105640818 | 105167744
MCR008560 | HPR053 | 2024-04-01 | Overhead | 44020219 | 40758488 | 30952447
MCR008561 | HPR053 | 2024-05-01 | Labor | 48295389 | 64114288 | 77271384
MCR008562 | HPR053 | 2024-05-01 | Material | 123866731 | 164438625 | 160844721
MCR008563 | HPR053 | 2024-05-01 | Equipment | 46617984 | 61887458 | 64813962
MCR008564 | HPR053 | 2024-05-01 | Subcontract | 106247166 | 141047864 | 168776924
MCR008565 | HPR053 | 2024-05-01 | Overhead | 40992430 | 54419284 | 32148744
MCR008566 | HPR053 | 2024-06-01 | Labor | 44182121 | 38134545 | 44986164
MCR008567 | HPR053 | 2024-06-01 | Material | 113317131 | 97806468 | 79755121
MCR008568 | HPR053 | 2024-06-01 | Equipment | 42647579 | 36810048 | 37828395
MCR008569 | HPR053 | 2024-06-01 | Subcontract | 97198206 | 83893875 | 76148705
MCR008570 | HPR053 | 2024-06-01 | Overhead | 37501148 | 32368052 | 33200902
MCR008571 | HPR053 | 2024-07-01 | Labor | 39577630 | 28108298 | 30876552
MCR008572 | HPR053 | 2024-07-01 | Material | 101507656 | 72091416 | 81296329
MCR008573 | HPR053 | 2024-07-01 | Equipment | 38203012 | 27132035 | 27307088
MCR008574 | HPR053 | 2024-07-01 | Subcontract | 87068583 | 61836690 | 73860705
MCR008575 | HPR053 | 2024-07-01 | Overhead | 33592922 | 23857918 | 30859437
MCR008576 | HPR053 | 2024-08-01 | Labor | 34545143 | 30993191 | 40944951
MCR008577 | HPR053 | 2024-08-01 | Material | 88600465 | 79490514 | 88631050
MCR008578 | HPR053 | 2024-08-01 | Equipment | 33345314 | 29916729 | 28897686
MCR008579 | HPR053 | 2024-08-01 | Subcontract | 75997390 | 68183294 | 59658222
MCR008580 | HPR053 | 2024-08-01 | Overhead | 29321419 | 26306574 | 33428912
MCR008581 | HPR053 | 2024-09-01 | Labor | 29159313 | 42786170 | 53007654
MCR008582 | HPR053 | 2024-09-01 | Material | 74787032 | 109736833 | 95194040
MCR008583 | HPR053 | 2024-09-01 | Equipment | 28146546 | 41300112 | 46774349
MCR008584 | HPR053 | 2024-09-01 | Subcontract | 64148865 | 94127192 | 111160335
MCR008585 | HPR053 | 2024-09-01 | Overhead | 24750005 | 36316285 | 32762556
MCR008586 | HPR053 | 2024-10-01 | Labor | 23511196 | 38114060 | 37287200
MCR008587 | HPR053 | 2024-10-01 | Material | 60300893 | 97753928 | 104149774
MCR008588 | HPR053 | 2024-10-01 | Equipment | 22694601 | 36790274 | 31219020
MCR008589 | HPR053 | 2024-10-01 | Subcontract | 51723323 | 83848809 | 89091757
MCR008590 | HPR053 | 2024-10-01 | Overhead | 19955965 | 32350665 | 32879739
MCR008591 | HPR053 | 2024-11-01 | Labor | 17717119 | 33892655 | 40745378
MCR008592 | HPR053 | 2024-11-01 | Material | 45440397 | 86926982 | 90521061
MCR008593 | HPR053 | 2024-11-01 | Equipment | 17101765 | 32715489 | 36230560
MCR008594 | HPR053 | 2024-11-01 | Subcontract | 38976676 | 74561954 | 68383534
MCR008595 | HPR053 | 2024-11-01 | Overhead | 15038035 | 28767597 | 32064145
MCR008596 | HPR053 | 2024-12-01 | Labor | 11936695 | 39653534 | 42962535
MCR008597 | HPR053 | 2024-12-01 | Material | 30614917 | 101702331 | 100581698
MCR008598 | HPR053 | 2024-12-01 | Equipment | 11522107 | 38276279 | 33706024
MCR008599 | HPR053 | 2024-12-01 | Subcontract | 26260063 | 87235566 | 106383699
MCR008600 | HPR053 | 2024-12-01 | Overhead | 10131694 | 33657348 | 33116906
MCR008601 | HPR053 | 2025-01-01 | Labor | 6418256 | 53906952 | 60177815
MCR008602 | HPR053 | 2025-01-01 | Material | 16461374 | 138259121 | 140389395
MCR008603 | HPR053 | 2025-01-01 | Equipment | 6195336 | 52034645 | 54758798
MCR008604 | HPR053 | 2025-01-01 | Subcontract | 14119807 | 118592294 | 137358064
MCR008605 | HPR053 | 2025-01-01 | Overhead | 5447724 | 45755444 | 31229566
MCR008606 | HPR053 | 2025-02-01 | Labor | 1691647 | 35782494 | 47141207
MCR008607 | HPR053 | 2025-02-01 | Material | 4338691 | 91773990 | 89267447
MCR008608 | HPR053 | 2025-02-01 | Equipment | 1632892 | 34539689 | 35336199
MCR008609 | HPR053 | 2025-02-01 | Subcontract | 3721529 | 78719493 | 78425827
MCR008610 | HPR053 | 2025-02-01 | Overhead | 1435845 | 30371665 | 31711332
MCR008611 | HPR053 | 2025-03-01 | Labor | 0 | 27651120 | 31463788
MCR008612 | HPR053 | 2025-03-01 | Material | 0 | 70918858 | 77294593
MCR008613 | HPR053 | 2025-03-01 | Equipment | 0 | 26690735 | 30424973
MCR008614 | HPR053 | 2025-03-01 | Subcontract | 0 | 60830923 | 57233086
MCR008615 | HPR053 | 2025-03-01 | Overhead | 0 | 23469872 | 32469219
MCR008616 | HPR053 | 2025-04-01 | Labor | 0 | 14955044 | 19067026
MCR008617 | HPR053 | 2025-04-01 | Material | 0 | 38356300 | 33369716
MCR008618 | HPR053 | 2025-04-01 | Equipment | 0 | 14435622 | 18092289
MCR008619 | HPR053 | 2025-04-01 | Subcontract | 0 | 32900264 | 41297659
MCR008620 | HPR053 | 2025-04-01 | Overhead | 0 | 12693626 | 29953927
MCR008621 | HPR053 | 2025-05-01 | Labor | 0 | 13485403 | 15682564
MCR008622 | HPR053 | 2025-05-01 | Material | 0 | 34587003 | 37335508
MCR008623 | HPR053 | 2025-05-01 | Equipment | 0 | 13017025 | 12225258
MCR008624 | HPR053 | 2025-05-01 | Subcontract | 0 | 29667135 | 23560669
MCR008625 | HPR053 | 2025-05-01 | Overhead | 0 | 11446216 | 31442152
MCR008626 | HPR053 | 2025-06-01 | Labor | 0 | 9610181 | 10680115
MCR008627 | HPR053 | 2025-06-01 | Material | 0 | 24647937 | 23564260
MCR008628 | HPR053 | 2025-06-01 | Equipment | 0 | 9276398 | 10170463
MCR008629 | HPR053 | 2025-06-01 | Subcontract | 0 | 21141863 | 27790692
MCR008630 | HPR053 | 2025-06-01 | Overhead | 0 | 8156983 | 32360591
MCR008631 | HPR053 | 2025-07-01 | Labor | 0 | 4641287 | 6227343
MCR008632 | HPR053 | 2025-07-01 | Material | 0 | 11903851 | 11287305
MCR008633 | HPR053 | 2025-07-01 | Equipment | 0 | 4480085 | 5098388
MCR008634 | HPR053 | 2025-07-01 | Subcontract | 0 | 10210574 | 10852370
MCR008635 | HPR053 | 2025-07-01 | Overhead | 0 | 3939458 | 29605355
MCR008636 | HPR053 | 2025-08-01 | Labor | 0 | 2637844 | 2742397
MCR008637 | HPR053 | 2025-08-01 | Material | 0 | 6765472 | 7500467
MCR008638 | HPR053 | 2025-08-01 | Equipment | 0 | 2546226 | 2935535
MCR008639 | HPR053 | 2025-08-01 | Subcontract | 0 | 5803110 | 5860578
MCR008640 | HPR053 | 2025-08-01 | Overhead | 0 | 2238964 | 33523599
MCR008641 | HPR053 | 2025-09-01 | Labor | 0 | 1194886 | 1386870
MCR008642 | HPR053 | 2025-09-01 | Material | 0 | 3064613 | 2262240
MCR008643 | HPR053 | 2025-09-01 | Equipment | 0 | 1153385 | 1285716
MCR008644 | HPR053 | 2025-09-01 | Subcontract | 0 | 2628683 | 2653524
MCR008645 | HPR053 | 2025-09-01 | Overhead | 0 | 1014202 | 32544053
MCR008646 | HPR054 | 2021-05-01 | Labor | 3360915 | 1580457 | 1731278
MCR008647 | HPR054 | 2021-05-01 | Material | 6484872 | 3049486 | 3340242
MCR008648 | HPR054 | 2021-05-01 | Equipment | 1407215 | 661737 | 656322
MCR008649 | HPR054 | 2021-05-01 | Subcontract | 10362345 | 4872852 | 4653560
MCR008650 | HPR054 | 2021-05-01 | Overhead | 2123382 | 998512 | 15241518
MCR008651 | HPR054 | 2021-06-01 | Labor | 9606674 | 3932232 | 4550454
MCR008652 | HPR054 | 2021-06-01 | Material | 18536040 | 7587226 | 8128172
MCR008653 | HPR054 | 2021-06-01 | Equipment | 4022315 | 1646426 | 1427913
MCR008654 | HPR054 | 2021-06-01 | Subcontract | 29619217 | 12123825 | 12272442
MCR008655 | HPR054 | 2021-06-01 | Overhead | 6069369 | 2484332 | 14322085
MCR008656 | HPR054 | 2021-07-01 | Labor | 15148567 | 9494787 | 10166982
MCR008657 | HPR054 | 2021-07-01 | Material | 29229100 | 18320155 | 18476628
MCR008658 | HPR054 | 2021-07-01 | Equipment | 6342706 | 3975468 | 3665711
MCR008659 | HPR054 | 2021-07-01 | Subcontract | 46705935 | 29274249 | 30251045
MCR008660 | HPR054 | 2021-07-01 | Overhead | 9570664 | 5998681 | 13997990
MCR008661 | HPR054 | 2021-08-01 | Labor | 20000699 | 7684310 | 7355880
MCR008662 | HPR054 | 2021-08-01 | Material | 38591270 | 14826846 | 18217131
MCR008663 | HPR054 | 2021-08-01 | Equipment | 8374294 | 3217421 | 3585856
MCR008664 | HPR054 | 2021-08-01 | Subcontract | 61665988 | 23692200 | 25934999
MCR008665 | HPR054 | 2021-08-01 | Overhead | 12636176 | 4854845 | 13911118
MCR008666 | HPR054 | 2021-09-01 | Labor | 24177787 | 15512377 | 16660372
MCR008667 | HPR054 | 2021-09-01 | Material | 46650946 | 29931070 | 37158447
MCR008668 | HPR054 | 2021-09-01 | Equipment | 10123241 | 6495033 | 6374677
MCR008669 | HPR054 | 2021-09-01 | Subcontract | 74544752 | 47827631 | 53983491
MCR008670 | HPR054 | 2021-09-01 | Overhead | 15275205 | 9800514 | 14444151
MCR008671 | HPR054 | 2021-10-01 | Labor | 27695223 | 14579220 | 17993173
MCR008672 | HPR054 | 2021-10-01 | Material | 53437825 | 28130547 | 32921776
MCR008673 | HPR054 | 2021-10-01 | Equipment | 11595992 | 6104320 | 6947808
MCR008674 | HPR054 | 2021-10-01 | Subcontract | 85389683 | 44950529 | 42311935
MCR008675 | HPR054 | 2021-10-01 | Overhead | 17497475 | 9210958 | 14742256
MCR008676 | HPR054 | 2021-11-01 | Labor | 30569147 | 13725344 | 12650452
MCR008677 | HPR054 | 2021-11-01 | Material | 58983050 | 26482997 | 33465216
MCR008678 | HPR054 | 2021-11-01 | Equipment | 12799304 | 5746802 | 5994708
MCR008679 | HPR054 | 2021-11-01 | Subcontract | 94250541 | 42317866 | 49964211
MCR008680 | HPR054 | 2021-11-01 | Overhead | 19313182 | 8671490 | 13930015
MCR008681 | HPR054 | 2021-12-01 | Labor | 32816533 | 22758235 | 24007173
MCR008682 | HPR054 | 2021-12-01 | Material | 63319371 | 43911925 | 53783059
MCR008683 | HPR054 | 2021-12-01 | Equipment | 13740284 | 9528874 | 10110009
MCR008684 | HPR054 | 2021-12-01 | Subcontract | 101179660 | 70168000 | 76436048
MCR008685 | HPR054 | 2021-12-01 | Overhead | 20733050 | 14378351 | 13382552
MCR008686 | HPR054 | 2022-01-01 | Labor | 34455291 | 18336850 | 21241772
MCR008687 | HPR054 | 2022-01-01 | Material | 66481349 | 35380880 | 37461308
MCR008688 | HPR054 | 2022-01-01 | Equipment | 14426432 | 7677640 | 6750569
MCR008689 | HPR054 | 2022-01-01 | Subcontract | 106232266 | 56536023 | 58178199
MCR008690 | HPR054 | 2022-01-01 | Overhead | 21768396 | 11584979 | 14168377
MCR008691 | HPR054 | 2022-02-01 | Labor | 35504393 | 23727266 | 24135167
MCR008692 | HPR054 | 2022-02-01 | Material | 68505588 | 45781668 | 53030432
MCR008693 | HPR054 | 2022-02-01 | Equipment | 14865691 | 9934608 | 13736534
MCR008694 | HPR054 | 2022-02-01 | Subcontract | 109466849 | 73155710 | 68229662
MCR008695 | HPR054 | 2022-02-01 | Overhead | 22431205 | 14990572 | 15193574
MCR008696 | HPR054 | 2022-03-01 | Labor | 35984020 | 28849710 | 29577107
MCR008697 | HPR054 | 2022-03-01 | Material | 69431026 | 55665403 | 71183812
MCR008698 | HPR054 | 2022-03-01 | Equipment | 15066511 | 12079375 | 11948619
MCR008699 | HPR054 | 2022-03-01 | Subcontract | 110945631 | 88949187 | 97917146
MCR008700 | HPR054 | 2022-03-01 | Overhead | 22734227 | 18226864 | 14941576
MCR008701 | HPR054 | 2022-04-01 | Labor | 35915743 | 24633319 | 25730600
MCR008702 | HPR054 | 2022-04-01 | Material | 69299285 | 47529892 | 58166287
MCR008703 | HPR054 | 2022-04-01 | Equipment | 15037923 | 10313972 | 10249653
MCR008704 | HPR054 | 2022-04-01 | Subcontract | 110735119 | 75949244 | 84871938
MCR008705 | HPR054 | 2022-04-01 | Overhead | 22691090 | 15563004 | 14185184
MCR008706 | HPR054 | 2022-05-01 | Labor | 35322752 | 24388937 | 26140911
MCR008707 | HPR054 | 2022-05-01 | Material | 68155112 | 47058359 | 43063757
MCR008708 | HPR054 | 2022-05-01 | Equipment | 14789638 | 10211649 | 11554212
MCR008709 | HPR054 | 2022-05-01 | Subcontract | 108906815 | 75195768 | 69690682
MCR008710 | HPR054 | 2022-05-01 | Overhead | 22316446 | 15408607 | 15325415
MCR008711 | HPR054 | 2022-06-01 | Labor | 34230144 | 33882226 | 39573168
MCR008712 | HPR054 | 2022-06-01 | Material | 66046929 | 65375622 | 84807661
MCR008713 | HPR054 | 2022-06-01 | Equipment | 14332163 | 14186490 | 13379368
MCR008714 | HPR054 | 2022-06-01 | Subcontract | 105538096 | 104465396 | 105031853
MCR008715 | HPR054 | 2022-06-01 | Overhead | 21626151 | 21406341 | 14701668
MCR008716 | HPR054 | 2022-07-01 | Labor | 32665292 | 20138930 | 21459560
MCR008717 | HPR054 | 2022-07-01 | Material | 63027553 | 38857987 | 48403133
MCR008718 | HPR054 | 2022-07-01 | Equipment | 13676960 | 8432171 | 10618808
MCR008719 | HPR054 | 2022-07-01 | Subcontract | 100713356 | 62092182 | 75711388
MCR008720 | HPR054 | 2022-07-01 | Overhead | 20637498 | 12723509 | 14887017
MCR008721 | HPR054 | 2022-08-01 | Labor | 30658333 | 27916514 | 28242892
MCR008722 | HPR054 | 2022-08-01 | Material | 59155134 | 53864805 | 69162596
MCR008723 | HPR054 | 2022-08-01 | Equipment | 12836646 | 11688646 | 11988637
MCR008724 | HPR054 | 2022-08-01 | Subcontract | 94525518 | 86071965 | 84680699
MCR008725 | HPR054 | 2022-08-01 | Overhead | 19369528 | 17637284 | 13950532
MCR008726 | HPR054 | 2022-09-01 | Labor | 28242833 | 17793607 | 19020171
MCR008727 | HPR054 | 2022-09-01 | Material | 54494435 | 34332695 | 39385656
MCR008728 | HPR054 | 2022-09-01 | Equipment | 11825276 | 7450184 | 7136914
MCR008729 | HPR054 | 2022-09-01 | Subcontract | 87078067 | 54861101 | 55554134
MCR008730 | HPR054 | 2022-09-01 | Overhead | 17843447 | 11241765 | 14416028
MCR008731 | HPR054 | 2022-10-01 | Labor | 25456706 | 21790363 | 24909745
MCR008732 | HPR054 | 2022-10-01 | Material | 49118614 | 42044420 | 59879263
MCR008733 | HPR054 | 2022-10-01 | Equipment | 10658724 | 9123626 | 10123186
MCR008734 | HPR054 | 2022-10-01 | Subcontract | 78487903 | 67183866 | 67502783
MCR008735 | HPR054 | 2022-10-01 | Overhead | 16083209 | 13766862 | 14731930
MCR008736 | HPR054 | 2022-11-01 | Labor | 22343563 | 45407102 | 57780634
MCR008737 | HPR054 | 2022-11-01 | Material | 43111818 | 87612825 | 100305912
MCR008738 | HPR054 | 2022-11-01 | Equipment | 9355251 | 19011956 | 19240063
MCR008739 | HPR054 | 2022-11-01 | Subcontract | 68889488 | 139998799 | 140992888
MCR008740 | HPR054 | 2022-11-01 | Overhead | 14116367 | 28687605 | 14153428
MCR008741 | HPR054 | 2022-12-01 | Labor | 18954764 | 13198908 | 10331934
MCR008742 | HPR054 | 2022-12-01 | Material | 36573143 | 25467242 | 35826351
MCR008743 | HPR054 | 2022-12-01 | Equipment | 7936361 | 5526384 | 6598579
MCR008744 | HPR054 | 2022-12-01 | Subcontract | 58441170 | 40694764 | 49111537
MCR008745 | HPR054 | 2022-12-01 | Overhead | 11975368 | 8338895 | 13599893
MCR008746 | HPR054 | 2023-01-01 | Labor | 15352761 | 28869486 | 36990253
MCR008747 | HPR054 | 2023-01-01 | Material | 29623093 | 55703561 | 69726758
MCR008748 | HPR054 | 2023-01-01 | Equipment | 6428202 | 12087656 | 11684619
MCR008749 | HPR054 | 2023-01-01 | Subcontract | 47335505 | 89010161 | 90378824
MCR008750 | HPR054 | 2023-01-01 | Overhead | 9699671 | 18239359 | 14079330
MCR008751 | HPR054 | 2023-02-01 | Labor | 11617061 | 25912311 | 25927808
MCR008752 | HPR054 | 2023-02-01 | Material | 22415074 | 49997704 | 52177802
MCR008753 | HPR054 | 2023-02-01 | Equipment | 4864064 | 10849486 | 13417189
MCR008754 | HPR054 | 2023-02-01 | Subcontract | 35817626 | 79892623 | 91619458
MCR008755 | HPR054 | 2023-02-01 | Overhead | 7339505 | 16371055 | 15004967
MCR008756 | HPR054 | 2023-03-01 | Labor | 7856301 | 31469418 | 33911281
MCR008757 | HPR054 | 2023-03-01 | Material | 15158702 | 60720119 | 70249736
MCR008758 | HPR054 | 2023-03-01 | Equipment | 3289434 | 13176247 | 12802193
MCR008759 | HPR054 | 2023-03-01 | Subcontract | 24222481 | 97026247 | 102358728
MCR008760 | HPR054 | 2023-03-01 | Overhead | 4963507 | 19881961 | 15170632
MCR008761 | HPR054 | 2023-04-01 | Labor | 4238640 | 19910592 | 25231503
MCR008762 | HPR054 | 2023-04-01 | Material | 8178439 | 38417410 | 43922064
MCR008763 | HPR054 | 2023-04-01 | Equipment | 1774719 | 8336566 | 9817761
MCR008764 | HPR054 | 2023-04-01 | Subcontract | 13068539 | 61388173 | 68961246
MCR008765 | HPR054 | 2023-04-01 | Overhead | 2677916 | 12579248 | 15031073
MCR008766 | HPR054 | 2023-05-01 | Labor | 1120341 | 13979140 | 13946199
MCR008767 | HPR054 | 2023-05-01 | Material | 2161693 | 26972697 | 26599888
MCR008768 | HPR054 | 2023-05-01 | Equipment | 469087 | 5853067 | 5882848
MCR008769 | HPR054 | 2023-05-01 | Subcontract | 3454225 | 43100369 | 34279527
MCR008770 | HPR054 | 2023-05-01 | Overhead | 707816 | 8831835 | 14674813
MCR008771 | HPR054 | 2023-06-01 | Labor | 0 | 9456516 | 11756165
MCR008772 | HPR054 | 2023-06-01 | Material | 0 | 18246310 | 22366134
MCR008773 | HPR054 | 2023-06-01 | Equipment | 0 | 3959444 | 4053515
MCR008774 | HPR054 | 2023-06-01 | Subcontract | 0 | 29156250 | 32762938
MCR008775 | HPR054 | 2023-06-01 | Overhead | 0 | 5974501 | 14967159
MCR008776 | HPR054 | 2023-07-01 | Labor | 0 | 9756591 | 11062907
MCR008777 | HPR054 | 2023-07-01 | Material | 0 | 18825304 | 17605475
MCR008778 | HPR054 | 2023-07-01 | Equipment | 0 | 4085085 | 4267806
MCR008779 | HPR054 | 2023-07-01 | Subcontract | 0 | 30081440 | 35036193
MCR008780 | HPR054 | 2023-07-01 | Overhead | 0 | 6164085 | 15542888
MCR008781 | HPR054 | 2023-08-01 | Labor | 0 | 8909160 | 10296589
MCR008782 | HPR054 | 2023-08-01 | Material | 0 | 17190190 | 19330835
MCR008783 | HPR054 | 2023-08-01 | Equipment | 0 | 3730266 | 3499493
MCR008784 | HPR054 | 2023-08-01 | Subcontract | 0 | 27468648 | 25642582
MCR008785 | HPR054 | 2023-08-01 | Overhead | 0 | 5628689 | 14440111
MCR008786 | HPR054 | 2023-09-01 | Labor | 0 | 10248131 | 12914902
MCR008787 | HPR054 | 2023-09-01 | Material | 0 | 19773729 | 21220749
MCR008788 | HPR054 | 2023-09-01 | Equipment | 0 | 4290893 | 5572480
MCR008789 | HPR054 | 2023-09-01 | Subcontract | 0 | 31596952 | 31045280
MCR008790 | HPR054 | 2023-09-01 | Overhead | 0 | 6474633 | 14542622
MCR008791 | HPR054 | 2023-10-01 | Labor | 0 | 11994736 | 13312204
MCR008792 | HPR054 | 2023-10-01 | Material | 0 | 23143796 | 27350203
MCR008793 | HPR054 | 2023-10-01 | Equipment | 0 | 5022197 | 6522638
MCR008794 | HPR054 | 2023-10-01 | Subcontract | 0 | 36982070 | 39654525
MCR008795 | HPR054 | 2023-10-01 | Overhead | 0 | 7578115 | 13677569
MCR008796 | HPR054 | 2023-11-01 | Labor | 0 | 4662877 | 6117251
MCR008797 | HPR054 | 2023-11-01 | Material | 0 | 8997002 | 9581232
MCR008798 | HPR054 | 2023-11-01 | Equipment | 0 | 1952347 | 1716574
MCR008799 | HPR054 | 2023-11-01 | Subcontract | 0 | 14376542 | 14980693
MCR008800 | HPR054 | 2023-11-01 | Overhead | 0 | 2945944 | 14420084
MCR008801 | HPR054 | 2023-12-01 | Labor | 0 | 2702105 | 2889574
MCR008802 | HPR054 | 2023-12-01 | Material | 0 | 5213700 | 5691781
MCR008803 | HPR054 | 2023-12-01 | Equipment | 0 | 1131371 | 1415546
MCR008804 | HPR054 | 2023-12-01 | Subcontract | 0 | 8331106 | 7975049
MCR008805 | HPR054 | 2023-12-01 | Overhead | 0 | 1707154 | 15354951
MCR008806 | HPR054 | 2024-01-01 | Labor | 0 | 5351785 | 6879152
MCR008807 | HPR054 | 2024-01-01 | Material | 0 | 10326248 | 12294506
MCR008808 | HPR054 | 2024-01-01 | Equipment | 0 | 2240793 | 2460699
MCR008809 | HPR054 | 2024-01-01 | Subcontract | 0 | 16500579 | 19177197
MCR008810 | HPR054 | 2024-01-01 | Overhead | 0 | 3381187 | 14192727
MCR008811 | HPR054 | 2024-02-01 | Labor | 0 | 740940 | 881251
MCR008812 | HPR054 | 2024-02-01 | Material | 0 | 1429641 | 1326971
MCR008813 | HPR054 | 2024-02-01 | Equipment | 0 | 310232 | 575926
MCR008814 | HPR054 | 2024-02-01 | Subcontract | 0 | 2284460 | 1375629
MCR008815 | HPR054 | 2024-02-01 | Overhead | 0 | 468116 | 14112502
MCR008816 | HPR055 | 2021-08-01 | Labor | 8250767 | 2776046 | 2980252
MCR008817 | HPR055 | 2021-08-01 | Material | 25276479 | 8504502 | 9224484
MCR008818 | HPR055 | 2021-08-01 | Equipment | 5738269 | 1930693 | 1848000
MCR008819 | HPR055 | 2021-08-01 | Subcontract | 25101148 | 8445511 | 8761601
MCR008820 | HPR055 | 2021-08-01 | Overhead | 5513378 | 1855027 | 22505321
MCR008821 | HPR055 | 2021-09-01 | Labor | 22629804 | 16385840 | 16610269
MCR008822 | HPR055 | 2021-09-01 | Material | 69327105 | 50198526 | 46895840
MCR008823 | HPR055 | 2021-09-01 | Equipment | 15738648 | 11396076 | 11585886
MCR008824 | HPR055 | 2021-09-01 | Subcontract | 68846216 | 49850324 | 47182926
MCR008825 | HPR055 | 2021-09-01 | Overhead | 15121827 | 10949447 | 24130256
MCR008826 | HPR055 | 2021-10-01 | Labor | 33910860 | 23544878 | 21085874
MCR008827 | HPR055 | 2021-10-01 | Material | 103886970 | 72130462 | 68650491
MCR008828 | HPR055 | 2021-10-01 | Equipment | 23584433 | 16375066 | 18443264
MCR008829 | HPR055 | 2021-10-01 | Subcontract | 103166356 | 71630128 | 82882992
MCR008830 | HPR055 | 2021-10-01 | Overhead | 22660124 | 15733304 | 20504376
MCR008831 | HPR055 | 2021-11-01 | Labor | 42215682 | 24711342 | 28335488
MCR008832 | HPR055 | 2021-11-01 | Material | 129329048 | 75703960 | 91645340
MCR008833 | HPR055 | 2021-11-01 | Equipment | 29360296 | 17186322 | 16990678
MCR008834 | HPR055 | 2021-11-01 | Subcontract | 128431955 | 75178838 | 72797135
MCR008835 | HPR055 | 2021-11-01 | Overhead | 28209624 | 16512765 | 23040858
MCR008836 | HPR055 | 2021-12-01 | Labor | 47676817 | 70082522 | 69553539
MCR008837 | HPR055 | 2021-12-01 | Material | 146059404 | 214699975 | 213494675
MCR008838 | HPR055 | 2021-12-01 | Equipment | 33158424 | 48741215 | 45227315
MCR008839 | HPR055 | 2021-12-01 | Subcontract | 145046261 | 213210705 | 228071594
MCR008840 | HPR055 | 2021-12-01 | Overhead | 31858897 | 46830976 | 21646975
MCR008841 | HPR055 | 2022-01-01 | Labor | 50440022 | 31036601 | 37653969
MCR008842 | HPR055 | 2022-01-01 | Material | 154524566 | 95081588 | 90637517
MCR008843 | HPR055 | 2022-01-01 | Equipment | 35080186 | 21585434 | 27925240
MCR008844 | HPR055 | 2022-01-01 | Subcontract | 153452704 | 94422053 | 99695723
MCR008845 | HPR055 | 2022-01-01 | Overhead | 33705343 | 20739469 | 20093790
MCR008846 | HPR055 | 2022-02-01 | Labor | 50667586 | 44728130 | 44910263
MCR008847 | HPR055 | 2022-02-01 | Material | 155221716 | 137026010 | 141952610
MCR008848 | HPR055 | 2022-02-01 | Equipment | 35238453 | 31107662 | 30227109
MCR008849 | HPR055 | 2022-02-01 | Subcontract | 154145018 | 136075527 | 115797680
MCR008850 | HPR055 | 2022-02-01 | Overhead | 33857407 | 29888507 | 22574836
MCR008851 | HPR055 | 2022-03-01 | Labor | 48543104 | 47228184 | 52047967
MCR008852 | HPR055 | 2022-03-01 | Material | 148713302 | 144685003 | 161177887
MCR008853 | HPR055 | 2022-03-01 | Equipment | 33760912 | 32846407 | 33626562
MCR008854 | HPR055 | 2022-03-01 | Subcontract | 147681750 | 143681393 | 161065530
MCR008855 | HPR055 | 2022-03-01 | Overhead | 32437773 | 31559109 | 20711638
MCR008856 | HPR055 | 2022-04-01 | Labor | 44278660 | 29686924 | 31542517
MCR008857 | HPR055 | 2022-04-01 | Material | 135649046 | 90946811 | 85724177
MCR008858 | HPR055 | 2022-04-01 | Equipment | 30795063 | 20646756 | 19152462
MCR008859 | HPR055 | 2022-04-01 | Subcontract | 134708114 | 90315957 | 96106409
MCR008860 | HPR055 | 2022-04-01 | Overhead | 29588160 | 19837580 | 22242210
MCR008861 | HPR055 | 2022-05-01 | Labor | 38126352 | 48608955 | 54687674
MCR008862 | HPR055 | 2022-05-01 | Material | 116801260 | 148915039 | 183774573
MCR008863 | HPR055 | 2022-05-01 | Equipment | 26516236 | 33806710 | 36645086
MCR008864 | HPR055 | 2022-05-01 | Subcontract | 115991066 | 147882087 | 146688105
MCR008865 | HPR055 | 2022-05-01 | Overhead | 25477027 | 32481776 | 22935199
MCR008866 | HPR055 | 2022-06-01 | Labor | 30398479 | 38511069 | 38972886
MCR008867 | HPR055 | 2022-06-01 | Material | 93126680 | 117979850 | 121415093
MCR008868 | HPR055 | 2022-06-01 | Equipment | 21141630 | 26783800 | 26069537
MCR008869 | HPR055 | 2022-06-01 | Subcontract | 92480705 | 117161481 | 133967921
MCR008870 | HPR055 | 2022-06-01 | Overhead | 20313059 | 25734104 | 21674717
MCR008871 | HPR055 | 2022-07-01 | Labor | 21507696 | 28012012 | 28725082
MCR008872 | HPR055 | 2022-07-01 | Material | 65889492 | 85815665 | 76461136
MCR008873 | HPR055 | 2022-07-01 | Equipment | 14958240 | 19481883 | 21471985
MCR008874 | HPR055 | 2022-07-01 | Subcontract | 65432448 | 85220403 | 73509115
MCR008875 | HPR055 | 2022-07-01 | Overhead | 14372005 | 18718359 | 21586682
MCR008876 | HPR055 | 2022-08-01 | Labor | 12065916 | 10733445 | 12654471
MCR008877 | HPR055 | 2022-08-01 | Material | 36964306 | 32882241 | 34842595
MCR008878 | HPR055 | 2022-08-01 | Equipment | 8391641 | 7464930 | 6834508
MCR008879 | HPR055 | 2022-08-01 | Subcontract | 36707902 | 32654153 | 43504215
MCR008880 | HPR055 | 2022-08-01 | Overhead | 8062761 | 7172369 | 21288163
MCR008881 | HPR055 | 2022-09-01 | Labor | 3290791 | 15094717 | 16937905
MCR008882 | HPR055 | 2022-09-01 | Material | 10081440 | 46243131 | 51105992
MCR008883 | HPR055 | 2022-09-01 | Equipment | 2288690 | 10498121 | 10568176
MCR008884 | HPR055 | 2022-09-01 | Subcontract | 10011509 | 45922365 | 43858551
MCR008885 | HPR055 | 2022-09-01 | Overhead | 2198993 | 10086685 | 21018843
MCR008886 | HPR055 | 2022-10-01 | Labor | 0 | 14162670 | 13904361
MCR008887 | HPR055 | 2022-10-01 | Material | 0 | 43387777 | 42654963
MCR008888 | HPR055 | 2022-10-01 | Equipment | 0 | 9849898 | 9540481
MCR008889 | HPR055 | 2022-10-01 | Subcontract | 0 | 43086817 | 45730008
MCR008890 | HPR055 | 2022-10-01 | Overhead | 0 | 9463867 | 20698834
MCR008891 | HPR055 | 2022-11-01 | Labor | 0 | 6369733 | 7809021
MCR008892 | HPR055 | 2022-11-01 | Material | 0 | 19513874 | 18668723
MCR008893 | HPR055 | 2022-11-01 | Equipment | 0 | 4430042 | 4470827
MCR008894 | HPR055 | 2022-11-01 | Subcontract | 0 | 19378516 | 19582234
MCR008895 | HPR055 | 2022-11-01 | Overhead | 0 | 4256422 | 20763297
MCR008896 | HPR055 | 2022-12-01 | Labor | 0 | 2329468 | 2176171
MCR008897 | HPR055 | 2022-12-01 | Material | 0 | 7136398 | 9447631
MCR008898 | HPR055 | 2022-12-01 | Equipment | 0 | 1620106 | 2323495
MCR008899 | HPR055 | 2022-12-01 | Subcontract | 0 | 7086896 | 6873224
MCR008900 | HPR055 | 2022-12-01 | Overhead | 0 | 1556612 | 21998694
MCR008901 | HPR056 | 2023-05-01 | Labor | 4859275 | 2784854 | 3052604
MCR008902 | HPR056 | 2023-05-01 | Material | 12726388 | 7293504 | 8668248
MCR008903 | HPR056 | 2023-05-01 | Equipment | 4992644 | 2861288 | 2842323
MCR008904 | HPR056 | 2023-05-01 | Subcontract | 10622932 | 6088011 | 5714240
MCR008905 | HPR056 | 2023-05-01 | Overhead | 4474355 | 2564257 | 26924524
MCR008906 | HPR056 | 2023-06-01 | Labor | 13793364 | 8276403 | 9088725
MCR008907 | HPR056 | 2023-06-01 | Material | 36124672 | 21675811 | 20315729
MCR008908 | HPR056 | 2023-06-01 | Equipment | 14171942 | 8503560 | 8929814
MCR008909 | HPR056 | 2023-06-01 | Subcontract | 30153876 | 18093167 | 19418759
MCR008910 | HPR056 | 2023-06-01 | Overhead | 12700744 | 7620801 | 26356213
MCR008911 | HPR056 | 2023-07-01 | Labor | 21570103 | 9044420 | 8591362
MCR008912 | HPR056 | 2023-07-01 | Material | 56491869 | 23687239 | 25820085
MCR008913 | HPR056 | 2023-07-01 | Equipment | 22162124 | 9292656 | 8308897
MCR008914 | HPR056 | 2023-07-01 | Subcontract | 47154720 | 19772140 | 16809517
MCR008915 | HPR056 | 2023-07-01 | Overhead | 19861462 | 8327981 | 29950385
MCR008916 | HPR056 | 2023-08-01 | Labor | 28216264 | 8767523 | 10016083
MCR008917 | HPR056 | 2023-08-01 | Material | 73898092 | 22962050 | 21604747
MCR008918 | HPR056 | 2023-08-01 | Equipment | 28990698 | 9008160 | 10046761
MCR008919 | HPR056 | 2023-08-01 | Subcontract | 61683990 | 19166812 | 23367896
MCR008920 | HPR056 | 2023-08-01 | Overhead | 25981157 | 8073018 | 25391390
MCR008921 | HPR056 | 2023-09-01 | Labor | 33759965 | 15661601 | 16156394
MCR008922 | HPR056 | 2023-09-01 | Material | 88416986 | 41017565 | 44132580
MCR008923 | HPR056 | 2023-09-01 | Equipment | 34686554 | 16091455 | 15778067
MCR008924 | HPR056 | 2023-09-01 | Subcontract | 73803156 | 34238057 | 36632501
MCR008925 | HPR056 | 2023-09-01 | Overhead | 31085723 | 14420992 | 26980333
MCR008926 | HPR056 | 2023-10-01 | Labor | 38230838 | 11623732 | 12583367
MCR008927 | HPR056 | 2023-10-01 | Material | 100126152 | 30442428 | 30770714
MCR008928 | HPR056 | 2023-10-01 | Equipment | 39280135 | 11942761 | 12472582
MCR008929 | HPR056 | 2023-10-01 | Subcontract | 83576996 | 25410811 | 23284486
MCR008930 | HPR056 | 2023-10-01 | Overhead | 35202442 | 10702976 | 26276161
MCR008931 | HPR056 | 2023-11-01 | Labor | 41660217 | 20320494 | 21445771
MCR008932 | HPR056 | 2023-11-01 | Material | 109107660 | 53219154 | 53562393
MCR008933 | HPR056 | 2023-11-01 | Equipment | 42803639 | 20878217 | 22182062
MCR008934 | HPR056 | 2023-11-01 | Subcontract | 91074013 | 44422929 | 48333821
MCR008935 | HPR056 | 2023-11-01 | Overhead | 38360169 | 18710838 | 27088824
MCR008936 | HPR056 | 2023-12-01 | Labor | 44081383 | 22704924 | 25549390
MCR008937 | HPR056 | 2023-12-01 | Material | 115448668 | 59463952 | 64835033
MCR008938 | HPR056 | 2023-12-01 | Equipment | 45291257 | 23328092 | 25491606
MCR008939 | HPR056 | 2023-12-01 | Subcontract | 96366960 | 49635569 | 48850136
MCR008940 | HPR056 | 2023-12-01 | Overhead | 40589546 | 20906390 | 25834978
MCR008941 | HPR056 | 2024-01-01 | Labor | 45529846 | 25033499 | 21899483
MCR008942 | HPR056 | 2024-01-01 | Material | 119242175 | 65562465 | 61046903
MCR008943 | HPR056 | 2024-01-01 | Equipment | 46779474 | 25720578 | 31238503
MCR008944 | HPR056 | 2024-01-01 | Subcontract | 99533464 | 54726101 | 64241321
MCR008945 | HPR056 | 2024-01-01 | Overhead | 41923271 | 23050510 | 28447973
MCR008946 | HPR056 | 2024-02-01 | Labor | 46043704 | 36999855 | 41064263
MCR008947 | HPR056 | 2024-02-01 | Material | 120587964 | 96902222 | 104428213
MCR008948 | HPR056 | 2024-02-01 | Equipment | 47307436 | 38015366 | 43044178
MCR008949 | HPR056 | 2024-02-01 | Subcontract | 100656817 | 80885927 | 83006332
MCR008950 | HPR056 | 2024-02-01 | Overhead | 42396424 | 34068970 | 27632612
MCR008951 | HPR056 | 2024-03-01 | Labor | 45664099 | 56305661 | 65700432
MCR008952 | HPR056 | 2024-03-01 | Material | 119593783 | 147463921 | 140583961
MCR008953 | HPR056 | 2024-03-01 | Equipment | 46917412 | 57851047 | 51644958
MCR008954 | HPR056 | 2024-03-01 | Subcontract | 99826958 | 123090633 | 123038922
MCR008955 | HPR056 | 2024-03-01 | Overhead | 42046890 | 51845497 | 25795857
MCR008956 | HPR056 | 2024-04-01 | Labor | 44435799 | 61036128 | 64616302
MCR008957 | HPR056 | 2024-04-01 | Material | 116376879 | 159852963 | 152341093
MCR008958 | HPR056 | 2024-04-01 | Equipment | 45655400 | 62711348 | 67015913
MCR008959 | HPR056 | 2024-04-01 | Subcontract | 97141753 | 133431977 | 135688046
MCR008960 | HPR056 | 2024-04-01 | Overhead | 40915887 | 56201248 | 26843755
MCR008961 | HPR056 | 2024-05-01 | Labor | 42407962 | 36909027 | 42934956
MCR008962 | HPR056 | 2024-05-01 | Material | 111065995 | 96664344 | 112939858
MCR008963 | HPR056 | 2024-05-01 | Equipment | 43571906 | 37922045 | 44958491
MCR008964 | HPR056 | 2024-05-01 | Subcontract | 92708669 | 80687366 | 82057088
MCR008965 | HPR056 | 2024-05-01 | Overhead | 39048682 | 33985337 | 27489480
MCR008966 | HPR056 | 2024-06-01 | Labor | 39635173 | 49959577 | 51870246
MCR008967 | HPR056 | 2024-06-01 | Material | 103804092 | 130843593 | 126524004
MCR008968 | HPR056 | 2024-06-01 | Equipment | 40723015 | 51330785 | 49305458
MCR008969 | HPR056 | 2024-06-01 | Subcontract | 86647035 | 109217364 | 124856971
MCR008970 | HPR056 | 2024-06-01 | Overhead | 36495536 | 46002108 | 26267366
MCR008971 | HPR056 | 2024-07-01 | Labor | 36178889 | 21471451 | 21399202
MCR008972 | HPR056 | 2024-07-01 | Material | 94752120 | 56233500 | 53696143
MCR008973 | HPR056 | 2024-07-01 | Equipment | 37171868 | 22060765 | 27443720
MCR008974 | HPR056 | 2024-07-01 | Subcontract | 79091201 | 46939055 | 49018515
MCR008975 | HPR056 | 2024-07-01 | Overhead | 33313035 | 19770624 | 29668044
MCR008976 | HPR056 | 2024-08-01 | Labor | 32109527 | 12338685 | 11648326
MCR008977 | HPR056 | 2024-08-01 | Material | 84094506 | 32314884 | 36820304
MCR008978 | HPR056 | 2024-08-01 | Equipment | 32990817 | 12677337 | 11686047
MCR008979 | HPR056 | 2024-08-01 | Subcontract | 70195109 | 26973781 | 20661487
MCR008980 | HPR056 | 2024-08-01 | Overhead | 29566022 | 11361296 | 27995167
MCR008981 | HPR056 | 2024-09-01 | Labor | 27509658 | 36324751 | 41849179
MCR008982 | HPR056 | 2024-09-01 | Material | 72047498 | 95134131 | 96633001
MCR008983 | HPR056 | 2024-09-01 | Equipment | 28264698 | 37321733 | 44211798
MCR008984 | HPR056 | 2024-09-01 | Subcontract | 60139268 | 79410072 | 91767622
MCR008985 | HPR056 | 2024-09-01 | Overhead | 25330524 | 33447343 | 26638085
MCR008986 | HPR056 | 2024-10-01 | Labor | 22479182 | 39700765 | 44248271
MCR008987 | HPR056 | 2024-10-01 | Material | 58872736 | 103975876 | 106541774
MCR008988 | HPR056 | 2024-10-01 | Equipment | 23096154 | 40790407 | 37603093
MCR008989 | HPR056 | 2024-10-01 | Subcontract | 49142070 | 86790426 | 82965808
MCR008990 | HPR056 | 2024-10-01 | Overhead | 20698529 | 36555932 | 27671005
MCR008991 | HPR056 | 2024-11-01 | Labor | 17144525 | 24125771 | 27337627
MCR008992 | HPR056 | 2024-11-01 | Material | 44901325 | 63185134 | 50080599
MCR008993 | HPR056 | 2024-11-01 | Equipment | 17615079 | 24787936 | 27367678
MCR008994 | HPR056 | 2024-11-01 | Subcontract | 37479897 | 52741702 | 57444671
MCR008995 | HPR056 | 2024-11-01 | Overhead | 15786448 | 22214686 | 28301829
MCR008996 | HPR056 | 2024-12-01 | Labor | 11677207 | 24214656 | 28537648
MCR008997 | HPR056 | 2024-12-01 | Material | 30582479 | 63417924 | 78882435
MCR008998 | HPR056 | 2024-12-01 | Equipment | 11997704 | 24879260 | 24903144
MCR008999 | HPR056 | 2024-12-01 | Subcontract | 25527713 | 52936016 | 72034847
MCR009000 | HPR056 | 2024-12-01 | Overhead | 10752215 | 22296531 | 26086773
MCR009001 | HPR056 | 2025-01-01 | Labor | 6340386 | 18240321 | 17927702
MCR009002 | HPR056 | 2025-01-01 | Material | 16605403 | 47771205 | 46919682
MCR009003 | HPR056 | 2025-01-01 | Equipment | 6514407 | 18740952 | 17812691
MCR009004 | HPR056 | 2025-01-01 | Subcontract | 13860811 | 39875435 | 60196569
MCR009005 | HPR056 | 2025-01-01 | Overhead | 5838142 | 16795443 | 25970357
MCR009006 | HPR056 | 2025-02-01 | Labor | 1684722 | 18072940 | 19090332
MCR009007 | HPR056 | 2025-02-01 | Material | 4412270 | 47332836 | 51758413
MCR009008 | HPR056 | 2025-02-01 | Equipment | 1730962 | 18568977 | 18005477
MCR009009 | HPR056 | 2025-02-01 | Subcontract | 3682996 | 39509520 | 57085946
MCR009010 | HPR056 | 2025-02-01 | Overhead | 1551270 | 16641321 | 25189714
MCR009011 | HPR056 | 2025-03-01 | Labor | 0 | 15268498 | 15012358
MCR009012 | HPR056 | 2025-03-01 | Material | 0 | 39988031 | 38157241
MCR009013 | HPR056 | 2025-03-01 | Equipment | 0 | 15687562 | 18624055
MCR009014 | HPR056 | 2025-03-01 | Subcontract | 0 | 33378687 | 67351864
MCR009015 | HPR056 | 2025-03-01 | Overhead | 0 | 14059028 | 28480347
MCR009016 | HPR056 | 2025-04-01 | Labor | 0 | 19001904 | 22792479
MCR009017 | HPR056 | 2025-04-01 | Material | 0 | 49765782 | 46512942
MCR009018 | HPR056 | 2025-04-01 | Equipment | 0 | 19523437 | 22456630
MCR009019 | HPR056 | 2025-04-01 | Subcontract | 0 | 41540342 | 62740632
MCR009020 | HPR056 | 2025-04-01 | Overhead | 0 | 17496698 | 27742877
MCR009021 | HPR056 | 2025-05-01 | Labor | 0 | 17285764 | 17804993
MCR009022 | HPR056 | 2025-05-01 | Material | 0 | 45271230 | 49988940
MCR009023 | HPR056 | 2025-05-01 | Equipment | 0 | 17760196 | 18043514
MCR009024 | HPR056 | 2025-05-01 | Subcontract | 0 | 37788663 | 78106828
MCR009025 | HPR056 | 2025-05-01 | Overhead | 0 | 15916500 | 23492582
MCR009026 | HPR056 | 2025-06-01 | Labor | 0 | 10749474 | 13071824
MCR009027 | HPR056 | 2025-06-01 | Material | 0 | 28152758 | 26587402
MCR009028 | HPR056 | 2025-06-01 | Equipment | 0 | 11044508 | 13650535
MCR009029 | HPR056 | 2025-06-01 | Subcontract | 0 | 23499584 | 56847391
MCR009030 | HPR056 | 2025-06-01 | Overhead | 0 | 9897972 | 26314668
MCR009031 | HPR056 | 2025-07-01 | Labor | 0 | 9771367 | 9529173
MCR009032 | HPR056 | 2025-07-01 | Material | 0 | 25591104 | 29152226
MCR009033 | HPR056 | 2025-07-01 | Equipment | 0 | 10039555 | 10858910
MCR009034 | HPR056 | 2025-07-01 | Subcontract | 0 | 21361328 | 61259319
MCR009035 | HPR056 | 2025-07-01 | Overhead | 0 | 8997343 | 26388324
MCR009036 | HPR056 | 2025-08-01 | Labor | 0 | 4161376 | 4785101
MCR009037 | HPR056 | 2025-08-01 | Material | 0 | 10898600 | 8754151
MCR009038 | HPR056 | 2025-08-01 | Equipment | 0 | 4275591 | 5653129
MCR009039 | HPR056 | 2025-08-01 | Subcontract | 0 | 9097246 | 25934656
MCR009040 | HPR056 | 2025-08-01 | Overhead | 0 | 3831740 | 30660001
MCR009041 | HPR056 | 2025-09-01 | Labor | 0 | 7747759 | 9345294
MCR009042 | HPR056 | 2025-09-01 | Material | 0 | 20291297 | 20869629
MCR009043 | HPR056 | 2025-09-01 | Equipment | 0 | 7960407 | 10132719
MCR009044 | HPR056 | 2025-09-01 | Subcontract | 0 | 16937490 | 58067345
MCR009045 | HPR056 | 2025-09-01 | Overhead | 0 | 7134032 | 27184842
MCR009046 | HPR056 | 2025-10-01 | Labor | 0 | 1108904 | 784438
MCR009047 | HPR056 | 2025-10-01 | Material | 0 | 2904209 | 2923584
MCR009048 | HPR056 | 2025-10-01 | Equipment | 0 | 1139340 | 930850
MCR009049 | HPR056 | 2025-10-01 | Subcontract | 0 | 2424192 | 17433979
MCR009050 | HPR056 | 2025-10-01 | Overhead | 0 | 1021064 | 28365612
MCR009051 | HPR057 | 2016-07-01 | Labor | 8309839 | 2650929 | 2786228
MCR009052 | HPR057 | 2016-07-01 | Material | 27038929 | 8625712 | 9882896
MCR009053 | HPR057 | 2016-07-01 | Equipment | 7010164 | 2236319 | 2273160
MCR009054 | HPR057 | 2016-07-01 | Subcontract | 22409716 | 7148943 | 7696647
MCR009055 | HPR057 | 2016-07-01 | Overhead | 5121644 | 1633860 | 17092897
MCR009056 | HPR057 | 2016-08-01 | Labor | 22419479 | 7396329 | 7734726
MCR009057 | HPR057 | 2016-08-01 | Material | 72949514 | 24066511 | 25137014
MCR009058 | HPR057 | 2016-08-01 | Equipment | 18913030 | 6239530 | 6797103
MCR009059 | HPR057 | 2016-08-01 | Subcontract | 60460158 | 19946193 | 22988629
MCR009060 | HPR057 | 2016-08-01 | Overhead | 13817908 | 4558616 | 17459327
MCR009061 | HPR057 | 2016-09-01 | Labor | 32884780 | 17118796 | 16992509
MCR009062 | HPR057 | 2016-09-01 | Material | 107001985 | 55701915 | 58552774
MCR009063 | HPR057 | 2016-09-01 | Equipment | 27741539 | 14441385 | 13680961
MCR009064 | HPR057 | 2016-09-01 | Subcontract | 88682659 | 46165442 | 38379914
MCR009065 | HPR057 | 2016-09-01 | Overhead | 20268038 | 10550912 | 18554483
MCR009066 | HPR057 | 2016-10-01 | Labor | 39879302 | 17869084 | 18121153
MCR009067 | HPR057 | 2016-10-01 | Material | 129761078 | 58143234 | 61041372
MCR009068 | HPR057 | 2016-10-01 | Equipment | 33642104 | 15074326 | 17215995
MCR009069 | HPR057 | 2016-10-01 | Subcontract | 107545270 | 48188794 | 64054625
MCR009070 | HPR057 | 2016-10-01 | Overhead | 24579007 | 11013340 | 16371998
MCR009071 | HPR057 | 2016-11-01 | Labor | 43595633 | 29735365 | 34666566
MCR009072 | HPR057 | 2016-11-01 | Material | 141853443 | 96754277 | 107977621
MCR009073 | HPR057 | 2016-11-01 | Equipment | 36777194 | 25084698 | 24779804
MCR009074 | HPR057 | 2016-11-01 | Subcontract | 117567356 | 80189415 | 89776431
MCR009075 | HPR057 | 2016-11-01 | Overhead | 26869511 | 18326944 | 17541470
MCR009076 | HPR057 | 2016-12-01 | Labor | 44250770 | 48894642 | 49434401
MCR009077 | HPR057 | 2016-12-01 | Material | 143985160 | 159095601 | 162942886
MCR009078 | HPR057 | 2016-12-01 | Equipment | 37329867 | 41247429 | 42715981
MCR009079 | HPR057 | 2016-12-01 | Subcontract | 119334112 | 131857562 | 138515818
MCR009080 | HPR057 | 2016-12-01 | Overhead | 27273295 | 30135476 | 17448069
MCR009081 | HPR057 | 2017-01-01 | Labor | 42094193 | 35011440 | 38376863
MCR009082 | HPR057 | 2017-01-01 | Material | 136967991 | 113921810 | 137070863
MCR009083 | HPR057 | 2017-01-01 | Equipment | 35510583 | 29535586 | 30501700
MCR009084 | HPR057 | 2017-01-01 | Subcontract | 113518321 | 94417772 | 111305570
MCR009085 | HPR057 | 2017-01-01 | Overhead | 25944122 | 21578774 | 16892288
MCR009086 | HPR057 | 2017-02-01 | Labor | 37420747 | 29963213 | 32106134
MCR009087 | HPR057 | 2017-02-01 | Material | 121761322 | 97495659 | 82710489
MCR009088 | HPR057 | 2017-02-01 | Equipment | 31568072 | 25276910 | 28867332
MCR009089 | HPR057 | 2017-02-01 | Subcontract | 100915116 | 80803868 | 78448466
MCR009090 | HPR057 | 2017-02-01 | Overhead | 23063714 | 18467375 | 17694930
MCR009091 | HPR057 | 2017-03-01 | Labor | 30593089 | 23476221 | 25932461
MCR009092 | HPR057 | 2017-03-01 | Material | 99545179 | 76387990 | 84964818
MCR009093 | HPR057 | 2017-03-01 | Equipment | 25808273 | 19804496 | 18614748
MCR009094 | HPR057 | 2017-03-01 | Subcontract | 82502499 | 63309948 | 67207355
MCR009095 | HPR057 | 2017-03-01 | Overhead | 18855589 | 14469215 | 16386616
MCR009096 | HPR057 | 2017-04-01 | Labor | 22086070 | 30607851 | 34795783
MCR009097 | HPR057 | 2017-04-01 | Material | 71864654 | 99593212 | 92466041
MCR009098 | HPR057 | 2017-04-01 | Equipment | 18631767 | 25820726 | 30072238
MCR009099 | HPR057 | 2017-04-01 | Subcontract | 59561031 | 82542308 | 83490815
MCR009100 | HPR057 | 2017-04-01 | Overhead | 13612416 | 18864688 | 16844128
MCR009101 | HPR057 | 2017-05-01 | Labor | 12595249 | 23653918 | 24927785
MCR009102 | HPR057 | 2017-05-01 | Material | 40982992 | 76966190 | 86700763
MCR009103 | HPR057 | 2017-05-01 | Equipment | 10625329 | 19954401 | 19160426
MCR009104 | HPR057 | 2017-05-01 | Subcontract | 33966479 | 63789156 | 77868961
MCR009105 | HPR057 | 2017-05-01 | Overhead | 7762892 | 14578736 | 17755433
MCR009106 | HPR057 | 2017-06-01 | Labor | 3478469 | 44348684 | 43967257
MCR009107 | HPR057 | 2017-06-01 | Material | 11318400 | 144303756 | 161710270
MCR009108 | HPR057 | 2017-06-01 | Equipment | 2934430 | 37412467 | 42555177
MCR009109 | HPR057 | 2017-06-01 | Subcontract | 9380628 | 119598162 | 115925520
MCR009110 | HPR057 | 2017-06-01 | Overhead | 2143902 | 27333643 | 17322280
MCR009111 | HPR057 | 2017-07-01 | Labor | 0 | 11064350 | 14983886
MCR009112 | HPR057 | 2017-07-01 | Material | 0 | 36001683 | 31180039
MCR009113 | HPR057 | 2017-07-01 | Equipment | 0 | 9333865 | 6761914
MCR009114 | HPR057 | 2017-07-01 | Subcontract | 0 | 29837997 | 42447996
MCR009115 | HPR057 | 2017-07-01 | Overhead | 0 | 6819345 | 17971961
MCR009116 | HPR057 | 2017-08-01 | Labor | 0 | 9606548 | 13039091
MCR009117 | HPR057 | 2017-08-01 | Material | 0 | 31258221 | 32228019
MCR009118 | HPR057 | 2017-08-01 | Equipment | 0 | 8104066 | 8681712
MCR009119 | HPR057 | 2017-08-01 | Subcontract | 0 | 25906642 | 30092555
MCR009120 | HPR057 | 2017-08-01 | Overhead | 0 | 5920851 | 18335165
MCR009121 | HPR057 | 2017-09-01 | Labor | 0 | 6076532 | 5847095
MCR009122 | HPR057 | 2017-09-01 | Material | 0 | 19772096 | 21433629
MCR009123 | HPR057 | 2017-09-01 | Equipment | 0 | 5126151 | 5287078
MCR009124 | HPR057 | 2017-09-01 | Subcontract | 0 | 16387005 | 16521955
MCR009125 | HPR057 | 2017-09-01 | Overhead | 0 | 3745179 | 18055570
MCR009126 | HPR057 | 2017-10-01 | Labor | 0 | 2133716 | 2771127
MCR009127 | HPR057 | 2017-10-01 | Material | 0 | 6942780 | 7308572
MCR009128 | HPR057 | 2017-10-01 | Equipment | 0 | 1799998 | 2724062
MCR009129 | HPR057 | 2017-10-01 | Subcontract | 0 | 5754138 | 6357656
MCR009130 | HPR057 | 2017-10-01 | Overhead | 0 | 1315083 | 17057237
MCR009131 | HPR058 | 2018-01-01 | Labor | 1846958 | 1572399 | 1633840
MCR009132 | HPR058 | 2018-01-01 | Material | 3641214 | 3099930 | 3111005
MCR009133 | HPR058 | 2018-01-01 | Equipment | 713640 | 607554 | 667121
MCR009134 | HPR058 | 2018-01-01 | Subcontract | 3285865 | 2797405 | 2900705
MCR009135 | HPR058 | 2018-01-01 | Overhead | 938762 | 799210 | 6588295
MCR009136 | HPR058 | 2018-02-01 | Labor | 5307820 | 1479053 | 1401745
MCR009137 | HPR058 | 2018-02-01 | Material | 10464181 | 2915902 | 2799954
MCR009138 | HPR058 | 2018-02-01 | Equipment | 2050870 | 571486 | 593161
MCR009139 | HPR058 | 2018-02-01 | Subcontract | 9442973 | 2631337 | 2554062
MCR009140 | HPR058 | 2018-02-01 | Overhead | 2697830 | 751765 | 7750737
MCR009141 | HPR058 | 2018-03-01 | Labor | 8423545 | 5036488 | 5012981
MCR009142 | HPR058 | 2018-03-01 | Material | 16606724 | 9929259 | 8648351
MCR009143 | HPR058 | 2018-03-01 | Equipment | 3254745 | 1946031 | 2240375
MCR009144 | HPR058 | 2018-03-01 | Subcontract | 14986060 | 8960254 | 7495437
MCR009145 | HPR058 | 2018-03-01 | Overhead | 4281473 | 2559918 | 7040133
MCR009146 | HPR058 | 2018-04-01 | Labor | 11200235 | 5404694 | 6162027
MCR009147 | HPR058 | 2018-04-01 | Material | 22080871 | 10655164 | 11925281
MCR009148 | HPR058 | 2018-04-01 | Equipment | 4327620 | 2088301 | 2386037
MCR009149 | HPR058 | 2018-04-01 | Subcontract | 19925980 | 9615317 | 10600075
MCR009150 | HPR058 | 2018-04-01 | Overhead | 5692794 | 2747068 | 7746645
MCR009151 | HPR058 | 2018-05-01 | Labor | 13644224 | 5988806 | 6303427
MCR009152 | HPR058 | 2018-05-01 | Material | 26899109 | 11806722 | 11930651
MCR009153 | HPR058 | 2018-05-01 | Equipment | 5271945 | 2313994 | 2169777
MCR009154 | HPR058 | 2018-05-01 | Subcontract | 24274002 | 10654494 | 10688179
MCR009155 | HPR058 | 2018-05-01 | Overhead | 6935011 | 3043958 | 7281205
MCR009156 | HPR058 | 2018-06-01 | Labor | 15762097 | 16008925 | 17818703
MCR009157 | HPR058 | 2018-06-01 | Material | 31074422 | 31561035 | 28632744
MCR009158 | HPR058 | 2018-06-01 | Equipment | 6090263 | 6185634 | 6164471
MCR009159 | HPR058 | 2018-06-01 | Subcontract | 28041843 | 28480967 | 29758624
MCR009160 | HPR058 | 2018-06-01 | Overhead | 8011472 | 8136928 | 7299713
MCR009161 | HPR058 | 2018-07-01 | Labor | 17560718 | 5524926 | 5508927
MCR009162 | HPR058 | 2018-07-01 | Material | 34620341 | 10892199 | 14091828
MCR009163 | HPR058 | 2018-07-01 | Equipment | 6785226 | 2134757 | 2702701
MCR009164 | HPR058 | 2018-07-01 | Subcontract | 31241712 | 9829220 | 9333523
MCR009165 | HPR058 | 2018-07-01 | Overhead | 8925665 | 2808179 | 6878118
MCR009166 | HPR058 | 2018-08-01 | Labor | 19047256 | 8224023 | 10526013
MCR009167 | HPR058 | 2018-08-01 | Material | 37550997 | 16213373 | 14502024
MCR009168 | HPR058 | 2018-08-01 | Equipment | 7359604 | 3177652 | 3104441
MCR009169 | HPR058 | 2018-08-01 | Subcontract | 33886363 | 14631097 | 11630891
MCR009170 | HPR058 | 2018-08-01 | Overhead | 9681234 | 4180061 | 7343140
MCR009171 | HPR058 | 2018-09-01 | Labor | 20229213 | 13319499 | 13521723
MCR009172 | HPR058 | 2018-09-01 | Material | 39881184 | 26258926 | 31303572
MCR009173 | HPR058 | 2018-09-01 | Equipment | 7816296 | 5146476 | 5897456
MCR009174 | HPR058 | 2018-09-01 | Subcontract | 35989146 | 23696295 | 26618860
MCR009175 | HPR058 | 2018-09-01 | Overhead | 10281993 | 6769962 | 6403813
MCR009176 | HPR058 | 2018-10-01 | Labor | 21114468 | 9883165 | 11816363
MCR009177 | HPR058 | 2018-10-01 | Material | 41626433 | 19484313 | 17243525
MCR009178 | HPR058 | 2018-10-01 | Equipment | 8158347 | 3818722 | 3621362
MCR009179 | HPR058 | 2018-10-01 | Subcontract | 37564074 | 17582822 | 18072770
MCR009180 | HPR058 | 2018-10-01 | Overhead | 10731946 | 5023361 | 6766011
MCR009181 | HPR058 | 2018-11-01 | Labor | 21711315 | 13622354 | 15837332
MCR009182 | HPR058 | 2018-11-01 | Material | 42803097 | 26855993 | 24805190
MCR009183 | HPR058 | 2018-11-01 | Equipment | 8388961 | 5263495 | 5890232
MCR009184 | HPR058 | 2018-11-01 | Subcontract | 38625907 | 24235094 | 20791025
MCR009185 | HPR058 | 2018-11-01 | Overhead | 11035308 | 6923895 | 6939196
MCR009186 | HPR058 | 2018-12-01 | Labor | 22028520 | 21380517 | 22893932
MCR009187 | HPR058 | 2018-12-01 | Material | 43428455 | 42150941 | 44179854
MCR009188 | HPR058 | 2018-12-01 | Equipment | 8511524 | 8261145 | 7849010
MCR009189 | HPR058 | 2018-12-01 | Subcontract | 39190236 | 38037395 | 43796677
MCR009190 | HPR058 | 2018-12-01 | Overhead | 11196535 | 10867172 | 7420777
MCR009191 | HPR058 | 2019-01-01 | Labor | 22075378 | 16247043 | 17811926
MCR009192 | HPR058 | 2019-01-01 | Material | 43520834 | 32030475 | 36812975
MCR009193 | HPR058 | 2019-01-01 | Equipment | 8529630 | 6277639 | 6000326
MCR009194 | HPR058 | 2019-01-01 | Subcontract | 39273599 | 28904594 | 26042347
MCR009195 | HPR058 | 2019-01-01 | Overhead | 11220352 | 8257958 | 7596787
MCR009196 | HPR058 | 2019-02-01 | Labor | 21861793 | 14808504 | 16444362
MCR009197 | HPR058 | 2019-02-01 | Material | 43099759 | 29194447 | 28543380
MCR009198 | HPR058 | 2019-02-01 | Equipment | 8447103 | 5721807 | 6651742
MCR009199 | HPR058 | 2019-02-01 | Subcontract | 38893617 | 26345336 | 26453909
MCR009200 | HPR058 | 2019-02-01 | Overhead | 11111792 | 7526785 | 7220481
MCR009201 | HPR058 | 2019-03-01 | Labor | 21398369 | 16302108 | 18072682
MCR009202 | HPR058 | 2019-03-01 | Material | 42186134 | 32139035 | 34671957
MCR009203 | HPR058 | 2019-03-01 | Equipment | 8268042 | 6298916 | 7083168
MCR009204 | HPR058 | 2019-03-01 | Subcontract | 38069154 | 29002560 | 29968248
MCR009205 | HPR058 | 2019-03-01 | Overhead | 10876245 | 8285946 | 7411884
MCR009206 | HPR058 | 2019-04-01 | Labor | 20696526 | 18193697 | 19601638
MCR009207 | HPR058 | 2019-04-01 | Material | 40802475 | 35868236 | 40801077
MCR009208 | HPR058 | 2019-04-01 | Equipment | 7996860 | 7029800 | 7626012
MCR009209 | HPR058 | 2019-04-01 | Subcontract | 36820527 | 32367825 | 31517748
MCR009210 | HPR058 | 2019-04-01 | Overhead | 10519516 | 9247392 | 7085632
MCR009211 | HPR058 | 2019-05-01 | Labor | 19768647 | 12432938 | 15775740
MCR009212 | HPR058 | 2019-05-01 | Material | 38973195 | 24511102 | 22323012
MCR009213 | HPR058 | 2019-05-01 | Equipment | 7638340 | 4803920 | 4076093
MCR009214 | HPR058 | 2019-05-01 | Subcontract | 35169768 | 22119043 | 21142300
MCR009215 | HPR058 | 2019-05-01 | Overhead | 10047899 | 6319346 | 6759233
MCR009216 | HPR058 | 2019-06-01 | Labor | 18628270 | 16013749 | 16891910
MCR009217 | HPR058 | 2019-06-01 | Material | 36724980 | 31570545 | 31230120
MCR009218 | HPR058 | 2019-06-01 | Equipment | 7197713 | 6187498 | 7347625
MCR009219 | HPR058 | 2019-06-01 | Subcontract | 33140959 | 28489549 | 31363793
MCR009220 | HPR058 | 2019-06-01 | Overhead | 9468274 | 8139380 | 6810192
MCR009221 | HPR058 | 2019-07-01 | Labor | 17290332 | 9453349 | 10572902
MCR009222 | HPR058 | 2019-07-01 | Material | 34087283 | 18636946 | 21424914
MCR009223 | HPR058 | 2019-07-01 | Equipment | 6680752 | 3652647 | 3466790
MCR009224 | HPR058 | 2019-07-01 | Subcontract | 30760677 | 16818151 | 16409280
MCR009225 | HPR058 | 2019-07-01 | Overhead | 8788235 | 4804896 | 6949362
MCR009226 | HPR058 | 2019-08-01 | Labor | 15771517 | 8736750 | 8969176
MCR009227 | HPR058 | 2019-08-01 | Material | 31092993 | 17224197 | 16568557
MCR009228 | HPR058 | 2019-08-01 | Equipment | 6093902 | 3375763 | 3594855
MCR009229 | HPR058 | 2019-08-01 | Subcontract | 28058602 | 15543273 | 15372940
MCR009230 | HPR058 | 2019-08-01 | Overhead | 8016260 | 4440667 | 6380876
MCR009231 | HPR058 | 2019-09-01 | Labor | 14090728 | 40731077 | 40685460
MCR009232 | HPR058 | 2019-09-01 | Material | 27779375 | 80299891 | 72103221
MCR009233 | HPR058 | 2019-09-01 | Equipment | 5444468 | 15737941 | 15615364
MCR009234 | HPR058 | 2019-09-01 | Subcontract | 25068363 | 72463357 | 66424106
MCR009235 | HPR058 | 2019-09-01 | Overhead | 7161957 | 20702568 | 7004683
MCR009236 | HPR058 | 2019-10-01 | Labor | 12269778 | 15963659 | 21788671
MCR009237 | HPR058 | 2019-10-01 | Material | 24189437 | 31471793 | 39072554
MCR009238 | HPR058 | 2019-10-01 | Equipment | 4740877 | 6168143 | 6370140
MCR009239 | HPR058 | 2019-10-01 | Subcontract | 21828769 | 28400435 | 29755116
MCR009240 | HPR058 | 2019-10-01 | Overhead | 6236415 | 8113921 | 7224977
MCR009241 | HPR058 | 2019-11-01 | Labor | 10334458 | 8878491 | 10302965
MCR009242 | HPR058 | 2019-11-01 | Material | 20374022 | 17503635 | 19409294
MCR009243 | HPR058 | 2019-11-01 | Equipment | 3993096 | 3430530 | 4163554
MCR009244 | HPR058 | 2019-11-01 | Subcontract | 18385704 | 15795440 | 14403849
MCR009245 | HPR058 | 2019-11-01 | Overhead | 5252742 | 4512711 | 6545756
MCR009246 | HPR058 | 2019-12-01 | Labor | 8316269 | 14960805 | 16804349
MCR009247 | HPR058 | 2019-12-01 | Material | 16395233 | 29494703 | 27677767
MCR009248 | HPR058 | 2019-12-01 | Equipment | 3213295 | 5780654 | 6173691
MCR009249 | HPR058 | 2019-12-01 | Subcontract | 14795208 | 26616291 | 29241195
MCR009250 | HPR058 | 2019-12-01 | Overhead | 4226947 | 7604196 | 7562161
MCR009251 | HPR058 | 2020-01-01 | Labor | 6255519 | 14139579 | 18139685
MCR009252 | HPR058 | 2020-01-01 | Material | 12332536 | 27875685 | 29435497
MCR009253 | HPR058 | 2020-01-01 | Equipment | 2417049 | 5463344 | 6243670
MCR009254 | HPR058 | 2020-01-01 | Subcontract | 11128994 | 25155274 | 21566288
MCR009255 | HPR058 | 2020-01-01 | Overhead | 3179521 | 7186788 | 6504849
MCR009256 | HPR058 | 2020-02-01 | Labor | 4207624 | 16314152 | 18530400
MCR009257 | HPR058 | 2020-02-01 | Material | 8295183 | 32162779 | 32744687
MCR009258 | HPR058 | 2020-02-01 | Equipment | 1625769 | 6303569 | 7975122
MCR009259 | HPR058 | 2020-02-01 | Subcontract | 7485649 | 29023987 | 28271161
MCR009260 | HPR058 | 2020-02-01 | Overhead | 2138628 | 8292068 | 6802182
MCR009261 | HPR058 | 2020-03-01 | Labor | 2259007 | 10310137 | 10446457
MCR009262 | HPR058 | 2020-03-01 | Material | 4453553 | 20326074 | 22296108
MCR009263 | HPR058 | 2020-03-01 | Equipment | 872850 | 3983699 | 3738441
MCR009264 | HPR058 | 2020-03-01 | Subcontract | 4018927 | 18342436 | 20368209
MCR009265 | HPR058 | 2020-03-01 | Overhead | 1148196 | 5240380 | 7942481
MCR009266 | HPR058 | 2020-04-01 | Labor | 594653 | 10254579 | 11560721
MCR009267 | HPR058 | 2020-04-01 | Material | 1172337 | 20216543 | 20029016
MCR009268 | HPR058 | 2020-04-01 | Equipment | 229766 | 3962232 | 3597883
MCR009269 | HPR058 | 2020-04-01 | Subcontract | 1057928 | 18243594 | 18129378
MCR009270 | HPR058 | 2020-04-01 | Overhead | 302247 | 5212141 | 7304085
MCR009271 | HPR058 | 2020-05-01 | Labor | 0 | 10051250 | 13765079
MCR009272 | HPR058 | 2020-05-01 | Material | 0 | 19815688 | 20866028
MCR009273 | HPR058 | 2020-05-01 | Equipment | 0 | 3883668 | 4533324
MCR009274 | HPR058 | 2020-05-01 | Subcontract | 0 | 17881858 | 16977239
MCR009275 | HPR058 | 2020-05-01 | Overhead | 0 | 5108794 | 7431286
MCR009276 | HPR058 | 2020-06-01 | Labor | 0 | 8729511 | 9090729
MCR009277 | HPR058 | 2020-06-01 | Material | 0 | 17209924 | 18404141
MCR009278 | HPR058 | 2020-06-01 | Equipment | 0 | 3372966 | 3780348
MCR009279 | HPR058 | 2020-06-01 | Subcontract | 0 | 15530393 | 16664622
MCR009280 | HPR058 | 2020-06-01 | Overhead | 0 | 4436988 | 7073069
MCR009281 | HPR058 | 2020-07-01 | Labor | 0 | 6712253 | 7166447
MCR009282 | HPR058 | 2020-07-01 | Material | 0 | 13232972 | 13343653
MCR009283 | HPR058 | 2020-07-01 | Equipment | 0 | 2593524 | 2965668
MCR009284 | HPR058 | 2020-07-01 | Subcontract | 0 | 11941555 | 10990163
MCR009285 | HPR058 | 2020-07-01 | Overhead | 0 | 3411667 | 6911786
MCR009286 | HPR058 | 2020-08-01 | Labor | 0 | 3221479 | 3397661
MCR009287 | HPR058 | 2020-08-01 | Material | 0 | 6351032 | 6688010
MCR009288 | HPR058 | 2020-08-01 | Equipment | 0 | 1244736 | 1069663
MCR009289 | HPR058 | 2020-08-01 | Subcontract | 0 | 5731230 | 5241940
MCR009290 | HPR058 | 2020-08-01 | Overhead | 0 | 1637395 | 7015995
MCR009291 | HPR058 | 2020-09-01 | Labor | 0 | 5184284 | 6586856
MCR009292 | HPR058 | 2020-09-01 | Material | 0 | 10220633 | 9673304
MCR009293 | HPR058 | 2020-09-01 | Equipment | 0 | 2003138 | 2546756
MCR009294 | HPR058 | 2020-09-01 | Subcontract | 0 | 9223193 | 9619392
MCR009295 | HPR058 | 2020-09-01 | Overhead | 0 | 2635039 | 6996767
MCR009296 | HPR058 | 2020-10-01 | Labor | 0 | 3183595 | 3247357
MCR009297 | HPR058 | 2020-10-01 | Material | 0 | 6276345 | 7236837
MCR009298 | HPR058 | 2020-10-01 | Equipment | 0 | 1230098 | 1185114
MCR009299 | HPR058 | 2020-10-01 | Subcontract | 0 | 5663832 | 5941276
MCR009300 | HPR058 | 2020-10-01 | Overhead | 0 | 1618140 | 7182669
MCR009301 | HPR058 | 2020-11-01 | Labor | 0 | 2309857 | 2876889
MCR009302 | HPR058 | 2020-11-01 | Material | 0 | 4553802 | 4620996
MCR009303 | HPR058 | 2020-11-01 | Equipment | 0 | 892498 | 1072976
MCR009304 | HPR058 | 2020-11-01 | Subcontract | 0 | 4109392 | 3673607
MCR009305 | HPR058 | 2020-11-01 | Overhead | 0 | 1174041 | 7506894
MCR009306 | HPR058 | 2020-12-01 | Labor | 0 | 1333608 | 1407923
MCR009307 | HPR058 | 2020-12-01 | Material | 0 | 2629162 | 2699981
MCR009308 | HPR058 | 2020-12-01 | Equipment | 0 | 515288 | 599563
MCR009309 | HPR058 | 2020-12-01 | Subcontract | 0 | 2372580 | 2499180
MCR009310 | HPR058 | 2020-12-01 | Overhead | 0 | 677839 | 6921898
MCR009311 | HPR058 | 2021-01-01 | Labor | 0 | 1278490 | 1487770
MCR009312 | HPR058 | 2021-01-01 | Material | 0 | 2520499 | 2268935
MCR009313 | HPR058 | 2021-01-01 | Equipment | 0 | 493992 | 531074
MCR009314 | HPR058 | 2021-01-01 | Subcontract | 0 | 2274522 | 1922333
MCR009315 | HPR058 | 2021-01-01 | Overhead | 0 | 649824 | 7448950
MCR009316 | HPR058 | 2021-02-01 | Labor | 0 | 505440 | 569325
MCR009317 | HPR058 | 2021-02-01 | Material | 0 | 996458 | 1217303
MCR009318 | HPR058 | 2021-02-01 | Equipment | 0 | 195295 | 358289
MCR009319 | HPR058 | 2021-02-01 | Subcontract | 0 | 899213 | 1178793
MCR009320 | HPR058 | 2021-02-01 | Overhead | 0 | 256902 | 7258948
MCR009321 | HPR059 | 2017-10-01 | Labor | 8273698 | 3297983 | 4131312
MCR009322 | HPR059 | 2017-10-01 | Material | 16925600 | 6746722 | 6605053
MCR009323 | HPR059 | 2017-10-01 | Equipment | 4187356 | 1669124 | 1781773
MCR009324 | HPR059 | 2017-10-01 | Subcontract | 34572916 | 13781129 | 16184181
MCR009325 | HPR059 | 2017-10-01 | Overhead | 5458997 | 2176014 | 15622987
MCR009326 | HPR059 | 2017-11-01 | Labor | 21794998 | 7894940 | 8665562
MCR009327 | HPR059 | 2017-11-01 | Material | 44586279 | 16150770 | 17586147
MCR009328 | HPR059 | 2017-11-01 | Equipment | 11030547 | 3995665 | 4732495
MCR009329 | HPR059 | 2017-11-01 | Subcontract | 91073739 | 32990217 | 32256219
MCR009330 | HPR059 | 2017-11-01 | Overhead | 14380368 | 5209092 | 16077594
MCR009331 | HPR059 | 2017-12-01 | Labor | 30956909 | 22199749 | 26018591
MCR009332 | HPR059 | 2017-12-01 | Material | 63328905 | 45414282 | 43355747
MCR009333 | HPR059 | 2017-12-01 | Equipment | 15667431 | 11235393 | 12620279
MCR009334 | HPR059 | 2017-12-01 | Subcontract | 129358187 | 92765052 | 87027951
MCR009335 | HPR059 | 2017-12-01 | Overhead | 20425409 | 14647423 | 16142678
MCR009336 | HPR059 | 2018-01-01 | Labor | 36022890 | 16577063 | 21492836
MCR009337 | HPR059 | 2018-01-01 | Material | 73692440 | 33911888 | 34574369
MCR009338 | HPR059 | 2018-01-01 | Equipment | 18231347 | 8389726 | 9302314
MCR009339 | HPR059 | 2018-01-01 | Subcontract | 150527165 | 69269796 | 89236695
MCR009340 | HPR059 | 2018-01-01 | Overhead | 23767949 | 10937567 | 16762402
MCR009341 | HPR059 | 2018-02-01 | Labor | 37294228 | 21934471 | 26133449
MCR009342 | HPR059 | 2018-02-01 | Material | 76293232 | 44871599 | 44029206
MCR009343 | HPR059 | 2018-02-01 | Equipment | 18874777 | 11101134 | 10907711
MCR009344 | HPR059 | 2018-02-01 | Subcontract | 155839647 | 91656546 | 87079994
MCR009345 | HPR059 | 2018-02-01 | Overhead | 24606780 | 14472392 | 15154454
MCR009346 | HPR059 | 2018-03-01 | Labor | 35124691 | 20997726 | 23059742
MCR009347 | HPR059 | 2018-03-01 | Material | 71854985 | 42955289 | 48306731
MCR009348 | HPR059 | 2018-03-01 | Equipment | 17776764 | 10627043 | 11874516
MCR009349 | HPR059 | 2018-03-01 | Subcontract | 146773904 | 87742214 | 103367774
MCR009350 | HPR059 | 2018-03-01 | Overhead | 23175317 | 13854327 | 15087695
MCR009351 | HPR059 | 2018-04-01 | Labor | 29945868 | 17298793 | 20643464
MCR009352 | HPR059 | 2018-04-01 | Material | 61260607 | 35388341 | 34437503
MCR009353 | HPR059 | 2018-04-01 | Equipment | 15155739 | 8754997 | 9128089
MCR009354 | HPR059 | 2018-04-01 | Subcontract | 125133399 | 72285659 | 72981258
MCR009355 | HPR059 | 2018-04-01 | Overhead | 19758323 | 11413766 | 13973156
MCR009356 | HPR059 | 2018-05-01 | Labor | 22316900 | 45066384 | 53273834
MCR009357 | HPR059 | 2018-05-01 | Material | 45653939 | 92192820 | 101831038
MCR009358 | HPR059 | 2018-05-01 | Equipment | 11294684 | 22808300 | 19722975
MCR009359 | HPR059 | 2018-05-01 | Subcontract | 93254586 | 188316791 | 193748670
MCR009360 | HPR059 | 2018-05-01 | Overhead | 14724720 | 29734859 | 15270213
MCR009361 | HPR059 | 2018-06-01 | Labor | 13044933 | 27070230 | 31449750
MCR009362 | HPR059 | 2018-06-01 | Material | 26686169 | 55377881 | 52064567
MCR009363 | HPR059 | 2018-06-01 | Equipment | 6602099 | 13700365 | 19054787
MCR009364 | HPR059 | 2018-06-01 | Subcontract | 54510250 | 113117104 | 106914131
MCR009365 | HPR059 | 2018-06-01 | Overhead | 8607064 | 17860973 | 15697541
MCR009366 | HPR059 | 2018-07-01 | Labor | 3668805 | 10792740 | 10855260
MCR009367 | HPR059 | 2018-07-01 | Material | 7505317 | 22078832 | 24998842
MCR009368 | HPR059 | 2018-07-01 | Equipment | 1856799 | 5462254 | 4440377
MCR009369 | HPR059 | 2018-07-01 | Subcontract | 15330664 | 45099117 | 54516514
MCR009370 | HPR059 | 2018-07-01 | Overhead | 2420682 | 7121064 | 16167613
MCR009371 | HPR059 | 2018-08-01 | Labor | 0 | 13395136 | 32376930
MCR009372 | HPR059 | 2018-08-01 | Material | 0 | 27402585 | 33445281
MCR009373 | HPR059 | 2018-08-01 | Equipment | 0 | 6779339 | 6707898
MCR009374 | HPR059 | 2018-08-01 | Subcontract | 0 | 55973630 | 55346036
MCR009375 | HPR059 | 2018-08-01 | Overhead | 0 | 8838128 | 15124438
MCR009376 | HPR059 | 2018-09-01 | Labor | 0 | 12874468 | 22978009
MCR009377 | HPR059 | 2018-09-01 | Material | 0 | 26337448 | 36149605
MCR009378 | HPR059 | 2018-09-01 | Equipment | 0 | 6515826 | 8075274
MCR009379 | HPR059 | 2018-09-01 | Subcontract | 0 | 53797939 | 58255897
MCR009380 | HPR059 | 2018-09-01 | Overhead | 0 | 8494591 | 13713761
MCR009381 | HPR059 | 2018-10-01 | Labor | 0 | 11721696 | 13436166
MCR009382 | HPR059 | 2018-10-01 | Material | 0 | 23979207 | 28602853
MCR009383 | HPR059 | 2018-10-01 | Equipment | 0 | 5932403 | 7508540
MCR009384 | HPR059 | 2018-10-01 | Subcontract | 0 | 48980901 | 56288289
MCR009385 | HPR059 | 2018-10-01 | Overhead | 0 | 7733990 | 15375872
MCR009386 | HPR059 | 2018-11-01 | Labor | 0 | 6133782 | 6399842
MCR009387 | HPR059 | 2018-11-01 | Material | 0 | 12547948 | 13750923
MCR009388 | HPR059 | 2018-11-01 | Equipment | 0 | 3104334 | 3190118
MCR009389 | HPR059 | 2018-11-01 | Subcontract | 0 | 25630946 | 25145204
MCR009390 | HPR059 | 2018-11-01 | Overhead | 0 | 4047077 | 14890213
MCR009391 | HPR059 | 2018-12-01 | Labor | 0 | 1188760 | 1864281
MCR009392 | HPR059 | 2018-12-01 | Material | 0 | 2431861 | 1097434
MCR009393 | HPR059 | 2018-12-01 | Equipment | 0 | 601637 | 871672
MCR009394 | HPR059 | 2018-12-01 | Subcontract | 0 | 4967418 | 4425713
MCR009395 | HPR059 | 2018-12-01 | Overhead | 0 | 784346 | 16229354
MCR009396 | HPR060 | 2019-03-01 | Labor | 4472926 | 2333364 | 2569324
MCR009397 | HPR060 | 2019-03-01 | Material | 13468864 | 7026218 | 7284619
MCR009398 | HPR060 | 2019-03-01 | Equipment | 3503837 | 1827825 | 2048186
MCR009399 | HPR060 | 2019-03-01 | Subcontract | 10814904 | 5641744 | 5677565
MCR009400 | HPR060 | 2019-03-01 | Overhead | 2940473 | 1533938 | 13944724
MCR009401 | HPR060 | 2019-04-01 | Labor | 12531433 | 8582311 | 9276916
MCR009402 | HPR060 | 2019-04-01 | Material | 37734618 | 25843031 | 26388951
MCR009403 | HPR060 | 2019-04-01 | Equipment | 9816414 | 6722896 | 7014566
MCR009404 | HPR060 | 2019-04-01 | Subcontract | 30299234 | 20750814 | 19144801
MCR009405 | HPR060 | 2019-04-01 | Overhead | 8238085 | 5641957 | 14930793
MCR009406 | HPR060 | 2019-05-01 | Labor | 19286093 | 15783385 | 18757090
MCR009407 | HPR060 | 2019-05-01 | Material | 58074230 | 47526885 | 49266273
MCR009408 | HPR060 | 2019-05-01 | Equipment | 15107631 | 12363809 | 12523920
MCR009409 | HPR060 | 2019-05-01 | Subcontract | 46631047 | 38161994 | 45914250
MCR009410 | HPR060 | 2019-05-01 | Overhead | 12678555 | 10375897 | 14545424
MCR009411 | HPR060 | 2019-06-01 | Labor | 24774874 | 22364151 | 22515336
MCR009412 | HPR060 | 2019-06-01 | Material | 74602034 | 67342870 | 55367016
MCR009413 | HPR060 | 2019-06-01 | Equipment | 19407232 | 17518808 | 18173663
MCR009414 | HPR060 | 2019-06-01 | Subcontract | 59902145 | 54073356 | 53677754
MCR009415 | HPR060 | 2019-06-01 | Overhead | 16286845 | 14702051 | 16345773
MCR009416 | HPR060 | 2019-07-01 | Labor | 29038186 | 13613121 | 15648134
MCR009417 | HPR060 | 2019-07-01 | Material | 87439707 | 40991795 | 42183001
MCR009418 | HPR060 | 2019-07-01 | Equipment | 22746868 | 10663748 | 10793999
MCR009419 | HPR060 | 2019-07-01 | Subcontract | 70210230 | 32914604 | 29778628
MCR009420 | HPR060 | 2019-07-01 | Overhead | 19089519 | 8949180 | 14630090
MCR009421 | HPR060 | 2019-08-01 | Labor | 32119257 | 21469917 | 24933522
MCR009422 | HPR060 | 2019-08-01 | Material | 96717420 | 64650156 | 68637880
MCR009423 | HPR060 | 2019-08-01 | Equipment | 25160405 | 16818316 | 18777397
MCR009424 | HPR060 | 2019-08-01 | Subcontract | 77659825 | 51911225 | 53124440
MCR009425 | HPR060 | 2019-08-01 | Overhead | 21114996 | 14114187 | 14188815
MCR009426 | HPR060 | 2019-09-01 | Labor | 34064620 | 28545977 | 25523318
MCR009427 | HPR060 | 2019-09-01 | Material | 102575293 | 85957568 | 94343119
MCR009428 | HPR060 | 2019-09-01 | Equipment | 26684292 | 22361300 | 24660970
MCR009429 | HPR060 | 2019-09-01 | Subcontract | 82363438 | 69020138 | 63635636
MCR009430 | HPR060 | 2019-09-01 | Overhead | 22393865 | 18765944 | 13624818
MCR009431 | HPR060 | 2019-10-01 | Labor | 34924728 | 33176542 | 33686678
MCR009432 | HPR060 | 2019-10-01 | Material | 105165247 | 99901115 | 98955504
MCR009433 | HPR060 | 2019-10-01 | Equipment | 27358052 | 25988622 | 23389475
MCR009434 | HPR060 | 2019-10-01 | Subcontract | 84443058 | 80216192 | 84987294
MCR009435 | HPR060 | 2019-10-01 | Overhead | 22959295 | 21810048 | 15147303
MCR009436 | HPR060 | 2019-11-01 | Labor | 34754762 | 25628443 | 30095858
MCR009437 | HPR060 | 2019-11-01 | Material | 104653447 | 77172300 | 79388166
MCR009438 | HPR060 | 2019-11-01 | Equipment | 27224910 | 20075870 | 23501577
MCR009439 | HPR060 | 2019-11-01 | Subcontract | 84032104 | 61965955 | 61082693
MCR009440 | HPR060 | 2019-11-01 | Overhead | 22847560 | 16847976 | 16053623
MCR009441 | HPR060 | 2019-12-01 | Labor | 33615722 | 21902682 | 23505426
MCR009442 | HPR060 | 2019-12-01 | Material | 101223570 | 65953296 | 58012073
MCR009443 | HPR060 | 2019-12-01 | Equipment | 26332650 | 17157319 | 15241899
MCR009444 | HPR060 | 2019-12-01 | Subcontract | 81278065 | 52957589 | 42284651
MCR009445 | HPR060 | 2019-12-01 | Overhead | 22098762 | 14398684 | 14485383
MCR009446 | HPR060 | 2020-01-01 | Labor | 31575934 | 38351802 | 36654100
MCR009447 | HPR060 | 2020-01-01 | Material | 95081366 | 115484843 | 137121881
MCR009448 | HPR060 | 2020-01-01 | Equipment | 24734796 | 30042627 | 35942654
MCR009449 | HPR060 | 2020-01-01 | Subcontract | 76346145 | 92729238 | 103675722
MCR009450 | HPR060 | 2020-01-01 | Overhead | 20757818 | 25212231 | 14327641
MCR009451 | HPR060 | 2020-02-01 | Labor | 28713235 | 19454228 | 18181816
MCR009452 | HPR060 | 2020-02-01 | Material | 86461215 | 58580517 | 52070011
MCR009453 | HPR060 | 2020-02-01 | Equipment | 22492320 | 15239339 | 12425331
MCR009454 | HPR060 | 2020-02-01 | Subcontract | 69424545 | 47037573 | 38085139
MCR009455 | HPR060 | 2020-02-01 | Overhead | 18875898 | 12789086 | 15029947
MCR009456 | HPR060 | 2020-03-01 | Labor | 25118278 | 24354490 | 23988659
MCR009457 | HPR060 | 2020-03-01 | Material | 75636092 | 73336175 | 74867235
MCR009458 | HPR060 | 2020-03-01 | Equipment | 19676235 | 19077927 | 19166400
MCR009459 | HPR060 | 2020-03-01 | Subcontract | 60732448 | 58885716 | 64187312
MCR009460 | HPR060 | 2020-03-01 | Overhead | 16512597 | 16010487 | 14753370
MCR009461 | HPR060 | 2020-04-01 | Labor | 20899877 | 39996833 | 39954753
MCR009462 | HPR060 | 2020-04-01 | Material | 62933654 | 120438356 | 127151269
MCR009463 | HPR060 | 2020-04-01 | Equipment | 16371779 | 31331251 | 34253850
MCR009464 | HPR060 | 2020-04-01 | Subcontract | 50532950 | 96706690 | 101405400
MCR009465 | HPR060 | 2020-04-01 | Overhead | 13739447 | 26293664 | 15006901
MCR009466 | HPR060 | 2020-05-01 | Labor | 16194437 | 16339634 | 19175463
MCR009467 | HPR060 | 2020-05-01 | Material | 48764646 | 49201861 | 42573806
MCR009468 | HPR060 | 2020-05-01 | Equipment | 12685804 | 12799543 | 13660999
MCR009469 | HPR060 | 2020-05-01 | Subcontract | 39155861 | 39506925 | 27032491
MCR009470 | HPR060 | 2020-05-01 | Overhead | 10646120 | 10741571 | 14980581
MCR009471 | HPR060 | 2020-06-01 | Labor | 11184894 | 20242847 | 19878822
MCR009472 | HPR060 | 2020-06-01 | Material | 33679921 | 60955206 | 59927218
MCR009473 | HPR060 | 2020-06-01 | Equipment | 8761611 | 15857099 | 17419914
MCR009474 | HPR060 | 2020-06-01 | Subcontract | 27043492 | 48944343 | 56072319
MCR009475 | HPR060 | 2020-06-01 | Overhead | 7352878 | 13307519 | 14644183
MCR009476 | HPR060 | 2020-07-01 | Labor | 6147827 | 12943653 | 12977166
MCR009477 | HPR060 | 2020-07-01 | Material | 18512319 | 38975894 | 42013279
MCR009478 | HPR060 | 2020-07-01 | Equipment | 4815859 | 10139324 | 11607345
MCR009479 | HPR060 | 2020-07-01 | Subcontract | 14864576 | 31295925 | 23590863
MCR009480 | HPR060 | 2020-07-01 | Overhead | 4041542 | 8509076 | 14305512
MCR009481 | HPR060 | 2020-08-01 | Labor | 1649885 | 10770288 | 10393230
MCR009482 | HPR060 | 2020-08-01 | Material | 4968130 | 32431461 | 30498276
MCR009483 | HPR060 | 2020-08-01 | Equipment | 1292427 | 8436833 | 7464926
MCR009484 | HPR060 | 2020-08-01 | Subcontract | 3989189 | 26041033 | 27087697
MCR009485 | HPR060 | 2020-08-01 | Overhead | 1084624 | 7080319 | 13403656
MCR009486 | HPR060 | 2020-09-01 | Labor | 0 | 12445917 | 12877724
MCR009487 | HPR060 | 2020-09-01 | Material | 0 | 37477110 | 39276666
MCR009488 | HPR060 | 2020-09-01 | Equipment | 0 | 9749425 | 10080972
MCR009489 | HPR060 | 2020-09-01 | Subcontract | 0 | 30092468 | 33072703
MCR009490 | HPR060 | 2020-09-01 | Overhead | 0 | 8181866 | 14797524
MCR009491 | HPR060 | 2020-10-01 | Labor | 0 | 8951639 | 9636716
MCR009492 | HPR060 | 2020-10-01 | Material | 0 | 26955152 | 28644294
MCR009493 | HPR060 | 2020-10-01 | Equipment | 0 | 7012207 | 7086905
MCR009494 | HPR060 | 2020-10-01 | Subcontract | 0 | 21643799 | 20604405
MCR009495 | HPR060 | 2020-10-01 | Overhead | 0 | 5884751 | 14596550
MCR009496 | HPR060 | 2020-11-01 | Labor | 0 | 2658493 | 2681564
MCR009497 | HPR060 | 2020-11-01 | Material | 0 | 8005248 | 7848789
MCR009498 | HPR060 | 2020-11-01 | Equipment | 0 | 2082513 | 2248747
MCR009499 | HPR060 | 2020-11-01 | Subcontract | 0 | 6427861 | 6983704
MCR009500 | HPR060 | 2020-11-01 | Overhead | 0 | 1747677 | 15705634
MCR009501 | HPR060 | 2020-12-01 | Labor | 0 | 1157253 | 1320798
MCR009502 | HPR060 | 2020-12-01 | Material | 0 | 3484717 | 3191869
MCR009503 | HPR060 | 2020-12-01 | Equipment | 0 | 906526 | 985545
MCR009504 | HPR060 | 2020-12-01 | Subcontract | 0 | 2798074 | 2655811
MCR009505 | HPR060 | 2020-12-01 | Overhead | 0 | 760771 | 14128614
MCR009506 | HPR061 | 2017-06-01 | Labor | 3276557 | 2044452 | 2067047
MCR009507 | HPR061 | 2017-06-01 | Material | 7525865 | 4695865 | 5262896
MCR009508 | HPR061 | 2017-06-01 | Equipment | 2281420 | 1423523 | 1500974
MCR009509 | HPR061 | 2017-06-01 | Subcontract | 11082591 | 6915133 | 7398019
MCR009510 | HPR061 | 2017-06-01 | Overhead | 2335808 | 1457459 | 14505346
MCR009511 | HPR061 | 2017-07-01 | Labor | 9324250 | 5691603 | 6359097
MCR009512 | HPR061 | 2017-07-01 | Material | 21416704 | 13072941 | 11993005
MCR009513 | HPR061 | 2017-07-01 | Equipment | 6492344 | 3962983 | 3724544
MCR009514 | HPR061 | 2017-07-01 | Subcontract | 31538245 | 19251217 | 21975981
MCR009515 | HPR061 | 2017-07-01 | Overhead | 6647119 | 4057459 | 14421520
MCR009516 | HPR061 | 2017-08-01 | Labor | 14625696 | 7200659 | 7926845
MCR009517 | HPR061 | 2017-08-01 | Material | 33593499 | 16539066 | 17023978
MCR009518 | HPR061 | 2017-08-01 | Equipment | 10183666 | 5013718 | 5674829
MCR009519 | HPR061 | 2017-08-01 | Subcontract | 49469798 | 24355434 | 22171361
MCR009520 | HPR061 | 2017-08-01 | Overhead | 10426440 | 5133242 | 14871118
MCR009521 | HPR061 | 2017-09-01 | Labor | 19197310 | 14618669 | 15396021
MCR009522 | HPR061 | 2017-09-01 | Material | 44093959 | 33577360 | 32635693
MCR009523 | HPR061 | 2017-09-01 | Equipment | 13366817 | 10178773 | 9816188
MCR009524 | HPR061 | 2017-09-01 | Subcontract | 64932780 | 49446032 | 59989678
MCR009525 | HPR061 | 2017-09-01 | Overhead | 13685476 | 10421431 | 15280701
MCR009526 | HPR061 | 2017-10-01 | Labor | 23056297 | 21556597 | 23053293
MCR009527 | HPR061 | 2017-10-01 | Material | 52957596 | 49512963 | 48624730
MCR009528 | HPR061 | 2017-10-01 | Equipment | 16053775 | 15009555 | 16171226
MCR009529 | HPR061 | 2017-10-01 | Subcontract | 77985375 | 72912807 | 79016964
MCR009530 | HPR061 | 2017-10-01 | Overhead | 16436489 | 15367376 | 14588316
MCR009531 | HPR061 | 2017-11-01 | Labor | 26220731 | 12186608 | 15641501
MCR009532 | HPR061 | 2017-11-01 | Material | 60225928 | 27991203 | 31485470
MCR009533 | HPR061 | 2017-11-01 | Equipment | 18257126 | 8485364 | 8858024
MCR009534 | HPR061 | 2017-11-01 | Subcontract | 88688723 | 41219856 | 45995137
MCR009535 | HPR061 | 2017-11-01 | Overhead | 18692367 | 8687651 | 14988090
MCR009536 | HPR061 | 2017-12-01 | Labor | 28709669 | 28131686 | 29524202
MCR009537 | HPR061 | 2017-12-01 | Material | 65942727 | 64615168 | 61460037
MCR009538 | HPR061 | 2017-12-01 | Equipment | 19990138 | 19587697 | 19143660
MCR009539 | HPR061 | 2017-12-01 | Subcontract | 97107283 | 95152319 | 101717431
MCR009540 | HPR061 | 2017-12-01 | Overhead | 20466694 | 20054659 | 14877203
MCR009541 | HPR061 | 2018-01-01 | Labor | 30543277 | 21626303 | 24081621
MCR009542 | HPR061 | 2018-01-01 | Material | 70154307 | 49673068 | 59458516
MCR009543 | HPR061 | 2018-01-01 | Equipment | 21266853 | 15058090 | 18898598
MCR009544 | HPR061 | 2018-01-01 | Subcontract | 103309257 | 73148578 | 73848371
MCR009545 | HPR061 | 2018-01-01 | Overhead | 21773846 | 15417068 | 15236932
MCR009546 | HPR061 | 2018-02-01 | Labor | 31742979 | 28952912 | 32371616
MCR009547 | HPR061 | 2018-02-01 | Material | 72909882 | 66501425 | 53037844
MCR009548 | HPR061 | 2018-02-01 | Equipment | 22102189 | 20159505 | 20597509
MCR009549 | HPR061 | 2018-02-01 | Subcontract | 107367118 | 97930022 | 119263204
MCR009550 | HPR061 | 2018-02-01 | Overhead | 22629096 | 20640098 | 14426102
MCR009551 | HPR061 | 2018-03-01 | Labor | 32331654 | 30435956 | 35761388
MCR009552 | HPR061 | 2018-03-01 | Material | 74261998 | 69907803 | 76260708
MCR009553 | HPR061 | 2018-03-01 | Equipment | 22512075 | 21192127 | 21601737
MCR009554 | HPR061 | 2018-03-01 | Subcontract | 109358244 | 102946256 | 108781055
MCR009555 | HPR061 | 2018-03-01 | Overhead | 23048753 | 21697338 | 14824188
MCR009556 | HPR061 | 2018-04-01 | Labor | 32333862 | 19180236 | 21875537
MCR009557 | HPR061 | 2018-04-01 | Material | 74267069 | 44054742 | 45929961
MCR009558 | HPR061 | 2018-04-01 | Equipment | 22513612 | 13354928 | 13928717
MCR009559 | HPR061 | 2018-04-01 | Subcontract | 109365712 | 64875029 | 74245234
MCR009560 | HPR061 | 2018-04-01 | Overhead | 23050327 | 13673304 | 13876756
MCR009561 | HPR061 | 2018-05-01 | Labor | 31776145 | 26614019 | 30797535
MCR009562 | HPR061 | 2018-05-01 | Material | 72986060 | 61129264 | 61664891
MCR009563 | HPR061 | 2018-05-01 | Equipment | 22125282 | 18530966 | 18811023
MCR009564 | HPR061 | 2018-05-01 | Subcontract | 107479297 | 90018976 | 86901578
MCR009565 | HPR061 | 2018-05-01 | Overhead | 22652739 | 18972736 | 14690698
MCR009566 | HPR061 | 2018-06-01 | Labor | 30687409 | 22412760 | 27490176
MCR009567 | HPR061 | 2018-06-01 | Material | 70485362 | 51479468 | 45962839
MCR009568 | HPR061 | 2018-06-01 | Equipment | 21367211 | 15605689 | 16039681
MCR009569 | HPR061 | 2018-06-01 | Subcontract | 103796769 | 75808683 | 87398101
MCR009570 | HPR061 | 2018-06-01 | Overhead | 21876595 | 15977722 | 14150638
MCR009571 | HPR061 | 2018-07-01 | Labor | 29099424 | 22855258 | 27040140
MCR009572 | HPR061 | 2018-07-01 | Material | 66837947 | 52495833 | 55835073
MCR009573 | HPR061 | 2018-07-01 | Equipment | 20261519 | 15913794 | 15672634
MCR009574 | HPR061 | 2018-07-01 | Subcontract | 98425585 | 77305382 | 73231296
MCR009575 | HPR061 | 2018-07-01 | Overhead | 20744544 | 16293172 | 14636291
MCR009576 | HPR061 | 2018-08-01 | Labor | 27047502 | 18768082 | 22553147
MCR009577 | HPR061 | 2018-08-01 | Material | 62124924 | 43108072 | 46576533
MCR009578 | HPR061 | 2018-08-01 | Equipment | 18832795 | 13067951 | 15902608
MCR009579 | HPR061 | 2018-08-01 | Subcontract | 91485185 | 63480962 | 78089191
MCR009580 | HPR061 | 2018-08-01 | Overhead | 19281760 | 13379485 | 14481670
MCR009581 | HPR061 | 2018-09-01 | Labor | 24571446 | 21491730 | 19413007
MCR009582 | HPR061 | 2018-09-01 | Material | 56437716 | 49363971 | 52116896
MCR009583 | HPR061 | 2018-09-01 | Equipment | 17108752 | 14964389 | 13308164
MCR009584 | HPR061 | 2018-09-01 | Subcontract | 83110200 | 72693400 | 84154910
MCR009585 | HPR061 | 2018-09-01 | Overhead | 17516617 | 15321133 | 14589291
MCR009586 | HPR061 | 2018-10-01 | Labor | 21716926 | 18098942 | 21554288
MCR009587 | HPR061 | 2018-10-01 | Material | 49881219 | 41571137 | 36532411
MCR009588 | HPR061 | 2018-10-01 | Equipment | 15121189 | 12602039 | 14842159
MCR009589 | HPR061 | 2018-10-01 | Subcontract | 73455100 | 61217672 | 75756966
MCR009590 | HPR061 | 2018-10-01 | Overhead | 15481672 | 12902465 | 15534240
MCR009591 | HPR061 | 2018-11-01 | Labor | 18537570 | 23878355 | 29090516
MCR009592 | HPR061 | 2018-11-01 | Material | 42578613 | 54845767 | 61494447
MCR009593 | HPR061 | 2018-11-01 | Equipment | 12907449 | 16626162 | 17952085
MCR009594 | HPR061 | 2018-11-01 | Subcontract | 62701281 | 80765895 | 90518551
MCR009595 | HPR061 | 2018-11-01 | Overhead | 13215157 | 17022522 | 15460322
MCR009596 | HPR061 | 2018-12-01 | Labor | 15098380 | 17435732 | 16587009
MCR009597 | HPR061 | 2018-12-01 | Material | 34679200 | 40047821 | 42960536
MCR009598 | HPR061 | 2018-12-01 | Equipment | 10512790 | 12140254 | 10995967
MCR009599 | HPR061 | 2018-12-01 | Subcontract | 51068602 | 58974435 | 64691014
MCR009600 | HPR061 | 2018-12-01 | Overhead | 10763410 | 12429673 | 14454108
MCR009601 | HPR061 | 2019-01-01 | Labor | 11481786 | 30366303 | 33086496
MCR009602 | HPR061 | 2019-01-01 | Material | 26372310 | 69747819 | 66984330
MCR009603 | HPR061 | 2019-01-01 | Equipment | 7994606 | 21143629 | 23267343
MCR009604 | HPR061 | 2019-01-01 | Subcontract | 38835872 | 102710663 | 155712932
MCR009605 | HPR061 | 2019-01-01 | Overhead | 8185194 | 21647684 | 14525967
MCR009606 | HPR061 | 2019-02-01 | Labor | 7799901 | 21611642 | 24276828
MCR009607 | HPR061 | 2019-02-01 | Material | 17915454 | 49639395 | 56306321
MCR009608 | HPR061 | 2019-02-01 | Equipment | 5430961 | 15047882 | 14264847
MCR009609 | HPR061 | 2019-02-01 | Subcontract | 26382304 | 73098990 | 98142572
MCR009610 | HPR061 | 2019-02-01 | Overhead | 5560433 | 15406617 | 13494265
MCR009611 | HPR061 | 2019-03-01 | Labor | 4225274 | 19422297 | 26523262
MCR009612 | HPR061 | 2019-03-01 | Material | 9704957 | 44610728 | 45087019
MCR009613 | HPR061 | 2019-03-01 | Equipment | 2941999 | 13523472 | 12444599
MCR009614 | HPR061 | 2019-03-01 | Subcontract | 14291523 | 65693774 | 89752829
MCR009615 | HPR061 | 2019-03-01 | Overhead | 3012135 | 13845866 | 16274843
MCR009616 | HPR061 | 2019-04-01 | Labor | 1120559 | 10730197 | 8965729
MCR009617 | HPR061 | 2019-04-01 | Material | 2573792 | 24645997 | 23739285
MCR009618 | HPR061 | 2019-04-01 | Equipment | 780229 | 7471285 | 8587311
MCR009619 | HPR061 | 2019-04-01 | Subcontract | 3790167 | 36293704 | 71657824
MCR009620 | HPR061 | 2019-04-01 | Overhead | 798830 | 7649397 | 14969308
MCR009621 | HPR061 | 2019-05-01 | Labor | 0 | 10391266 | 11351174
MCR009622 | HPR061 | 2019-05-01 | Material | 0 | 23867514 | 24079898
MCR009623 | HPR061 | 2019-05-01 | Equipment | 0 | 7235292 | 7722543
MCR009624 | HPR061 | 2019-05-01 | Subcontract | 0 | 35147309 | 68231649
MCR009625 | HPR061 | 2019-05-01 | Overhead | 0 | 7407778 | 13804099
MCR009626 | HPR061 | 2019-06-01 | Labor | 0 | 7627509 | 8396063
MCR009627 | HPR061 | 2019-06-01 | Material | 0 | 17519490 | 19139475
MCR009628 | HPR061 | 2019-06-01 | Equipment | 0 | 5310927 | 4845358
MCR009629 | HPR061 | 2019-06-01 | Subcontract | 0 | 25799207 | 58654395
MCR009630 | HPR061 | 2019-06-01 | Overhead | 0 | 5437537 | 14406292
MCR009631 | HPR061 | 2019-07-01 | Labor | 0 | 3748569 | 3945951
MCR009632 | HPR061 | 2019-07-01 | Material | 0 | 8610022 | 8457986
MCR009633 | HPR061 | 2019-07-01 | Equipment | 0 | 2610076 | 2743120
MCR009634 | HPR061 | 2019-07-01 | Subcontract | 0 | 12679121 | 55336963
MCR009635 | HPR061 | 2019-07-01 | Overhead | 0 | 2672299 | 13297460
MCR009636 | HPR061 | 2019-08-01 | Labor | 0 | 4069987 | 4837856
MCR009637 | HPR061 | 2019-08-01 | Material | 0 | 9348279 | 10177164
MCR009638 | HPR061 | 2019-08-01 | Equipment | 0 | 2833874 | 3415188
MCR009639 | HPR061 | 2019-08-01 | Subcontract | 0 | 13766280 | 57095919
MCR009640 | HPR061 | 2019-08-01 | Overhead | 0 | 2901433 | 14859916
MCR009641 | HPR061 | 2019-09-01 | Labor | 0 | 2122938 | 1921009
MCR009642 | HPR061 | 2019-09-01 | Material | 0 | 4876139 | 5020964
MCR009643 | HPR061 | 2019-09-01 | Equipment | 0 | 1478172 | 1567350
MCR009644 | HPR061 | 2019-09-01 | Subcontract | 0 | 7180604 | 34942965
MCR009645 | HPR061 | 2019-09-01 | Overhead | 0 | 1513411 | 14271614
MCR009646 | HPR061 | 2019-10-01 | Labor | 0 | 1253336 | 1558765
MCR009647 | HPR061 | 2019-10-01 | Material | 0 | 2878766 | 2478895
MCR009648 | HPR061 | 2019-10-01 | Equipment | 0 | 872680 | 970724
MCR009649 | HPR061 | 2019-10-01 | Subcontract | 0 | 4239271 | 30755878
MCR009650 | HPR061 | 2019-10-01 | Overhead | 0 | 893485 | 13916723
MCR009651 | HPR062 | 2017-10-01 | Labor | 3411227 | 2639442 | 2377144
MCR009652 | HPR062 | 2017-10-01 | Material | 7910193 | 6120523 | 5933378
MCR009653 | HPR062 | 2017-10-01 | Equipment | 1934150 | 1496551 | 1537443
MCR009654 | HPR062 | 2017-10-01 | Subcontract | 8594309 | 6649859 | 6392380
MCR009655 | HPR062 | 2017-10-01 | Overhead | 2211101 | 1710843 | 12116712
MCR009656 | HPR062 | 2017-11-01 | Labor | 9656095 | 6578251 | 6952757
MCR009657 | HPR062 | 2017-11-01 | Material | 22391230 | 15254110 | 14493821
MCR009658 | HPR062 | 2017-11-01 | Equipment | 5474961 | 3729838 | 3799849
MCR009659 | HPR062 | 2017-11-01 | Subcontract | 24327747 | 16573369 | 16054084
MCR009660 | HPR062 | 2017-11-01 | Overhead | 6258922 | 4263914 | 12773740
MCR009661 | HPR062 | 2017-12-01 | Labor | 15049552 | 11435319 | 10988605
MCR009662 | HPR062 | 2017-12-01 | Material | 34897958 | 26517020 | 24687516
MCR009663 | HPR062 | 2017-12-01 | Equipment | 8533026 | 6483773 | 6658244
MCR009664 | HPR062 | 2017-12-01 | Subcontract | 37916125 | 28810357 | 29483801
MCR009665 | HPR062 | 2017-12-01 | Overhead | 9754873 | 7412186 | 11755324
MCR009666 | HPR062 | 2018-01-01 | Labor | 19612361 | 16919654 | 16863942
MCR009667 | HPR062 | 2018-01-01 | Material | 45478520 | 39234482 | 40981241
MCR009668 | HPR062 | 2018-01-01 | Equipment | 11120118 | 9593365 | 9636147
MCR009669 | HPR062 | 2018-01-01 | Subcontract | 49411751 | 42627695 | 29903067
MCR009670 | HPR062 | 2018-01-01 | Overhead | 12712411 | 10967042 | 12842657
MCR009671 | HPR062 | 2018-02-01 | Labor | 23366388 | 31154040 | 29572264
MCR009672 | HPR062 | 2018-02-01 | Material | 54183622 | 72242176 | 71090071
MCR009673 | HPR062 | 2018-02-01 | Equipment | 13248634 | 17664197 | 17404725
MCR009674 | HPR062 | 2018-02-01 | Subcontract | 58869719 | 78490076 | 82442185
MCR009675 | HPR062 | 2018-02-01 | Overhead | 15145710 | 20193538 | 13068814
MCR009676 | HPR062 | 2018-03-01 | Labor | 26334748 | 26693099 | 22402571
MCR009677 | HPR062 | 2018-03-01 | Material | 61066863 | 61897833 | 68470770
MCR009678 | HPR062 | 2018-03-01 | Equipment | 14931680 | 15134864 | 15542774
MCR009679 | HPR062 | 2018-03-01 | Subcontract | 66348261 | 67251097 | 72118179
MCR009680 | HPR062 | 2018-03-01 | Overhead | 17069752 | 17302029 | 12873530
MCR009681 | HPR062 | 2018-04-01 | Labor | 28541973 | 28322938 | 29793899
MCR009682 | HPR062 | 2018-04-01 | Material | 66185131 | 65677217 | 70040502
MCR009683 | HPR062 | 2018-04-01 | Equipment | 16183167 | 16058975 | 15826311
MCR009684 | HPR062 | 2018-04-01 | Subcontract | 71909184 | 71357343 | 61785700
MCR009685 | HPR062 | 2018-04-01 | Overhead | 18500439 | 18358464 | 12810040
MCR009686 | HPR062 | 2018-05-01 | Labor | 30014223 | 26942911 | 22116511
MCR009687 | HPR062 | 2018-05-01 | Material | 69599088 | 62477113 | 56926399
MCR009688 | HPR062 | 2018-05-01 | Equipment | 17017926 | 15276506 | 14039503
MCR009689 | HPR062 | 2018-05-01 | Subcontract | 75618399 | 67880477 | 73669243
MCR009690 | HPR062 | 2018-05-01 | Overhead | 19454727 | 17463953 | 11611281
MCR009691 | HPR062 | 2018-06-01 | Labor | 30779547 | 21083026 | 19249884
MCR009692 | HPR062 | 2018-06-01 | Material | 71373775 | 48888801 | 55879501
MCR009693 | HPR062 | 2018-06-01 | Equipment | 17451861 | 11953978 | 13495129
MCR009694 | HPR062 | 2018-06-01 | Subcontract | 77546571 | 53116972 | 47209099
MCR009695 | HPR062 | 2018-06-01 | Overhead | 19950798 | 13665672 | 11657222
MCR009696 | HPR062 | 2018-07-01 | Labor | 30868211 | 33407224 | 32335773
MCR009697 | HPR062 | 2018-07-01 | Material | 71579375 | 77467017 | 77894128
MCR009698 | HPR062 | 2018-07-01 | Equipment | 17502133 | 18941741 | 22151289
MCR009699 | HPR062 | 2018-07-01 | Subcontract | 77769952 | 84166790 | 81576275
MCR009700 | HPR062 | 2018-07-01 | Overhead | 20008268 | 21654015 | 12915108
MCR009701 | HPR062 | 2018-08-01 | Labor | 30313119 | 24908911 | 23877528
MCR009702 | HPR062 | 2018-08-01 | Material | 70292188 | 57760532 | 56899762
MCR009703 | HPR062 | 2018-08-01 | Equipment | 17187398 | 14123237 | 13306532
MCR009704 | HPR062 | 2018-08-01 | Subcontract | 76371443 | 62755980 | 68334885
MCR009705 | HPR062 | 2018-08-01 | Overhead | 19648467 | 16145548 | 13105843
MCR009706 | HPR062 | 2018-09-01 | Labor | 29150369 | 35301033 | 31605859
MCR009707 | HPR062 | 2018-09-01 | Material | 67595923 | 81858515 | 90824353
MCR009708 | HPR062 | 2018-09-01 | Equipment | 16528124 | 20015522 | 17635778
MCR009709 | HPR062 | 2018-09-01 | Subcontract | 73441989 | 88938088 | 87220956
MCR009710 | HPR062 | 2018-09-01 | Overhead | 18894791 | 22881551 | 11421585
MCR009711 | HPR062 | 2018-10-01 | Labor | 27420002 | 25486723 | 20475648
MCR009712 | HPR062 | 2018-10-01 | Material | 63583427 | 59100404 | 59784832
MCR009713 | HPR062 | 2018-10-01 | Equipment | 15547014 | 14450854 | 13516224
MCR009714 | HPR062 | 2018-10-01 | Subcontract | 69082471 | 64211731 | 66874793
MCR009715 | HPR062 | 2018-10-01 | Overhead | 17773196 | 16520076 | 14373730
MCR009716 | HPR062 | 2018-11-01 | Labor | 25167045 | 22880222 | 20834088
MCR009717 | HPR062 | 2018-11-01 | Material | 58359112 | 53056266 | 54214142
MCR009718 | HPR062 | 2018-11-01 | Equipment | 14269598 | 12972980 | 12777939
MCR009719 | HPR062 | 2018-11-01 | Subcontract | 63406328 | 57644863 | 50897876
MCR009720 | HPR062 | 2018-11-01 | Overhead | 16312866 | 14830585 | 12064117
MCR009721 | HPR062 | 2018-12-01 | Labor | 22443020 | 24784132 | 22068852
MCR009722 | HPR062 | 2018-12-01 | Material | 52042451 | 57471185 | 60969529
MCR009723 | HPR062 | 2018-12-01 | Equipment | 12725088 | 14052488 | 16211811
MCR009724 | HPR062 | 2018-12-01 | Subcontract | 56543367 | 62441608 | 64693663
MCR009725 | HPR062 | 2018-12-01 | Overhead | 14547198 | 16064668 | 11969410
MCR009726 | HPR062 | 2019-01-01 | Labor | 19308244 | 22390177 | 19116135
MCR009727 | HPR062 | 2019-01-01 | Material | 44773313 | 51919916 | 64072252
MCR009728 | HPR062 | 2019-01-01 | Equipment | 10947685 | 12695127 | 11871418
MCR009729 | HPR062 | 2019-01-01 | Subcontract | 48645555 | 56410235 | 53499664
MCR009730 | HPR062 | 2019-01-01 | Overhead | 12515287 | 14512946 | 12398843
MCR009731 | HPR062 | 2019-02-01 | Labor | 15835562 | 24255441 | 20494760
MCR009732 | HPR062 | 2019-02-01 | Material | 36720614 | 56245221 | 53087163
MCR009733 | HPR062 | 2019-02-01 | Equipment | 8978690 | 13752723 | 11288458
MCR009734 | HPR062 | 2019-02-01 | Subcontract | 39896414 | 61109616 | 68587809
MCR009735 | HPR062 | 2019-02-01 | Overhead | 10264352 | 15721979 | 14118865
MCR009736 | HPR062 | 2019-03-01 | Labor | 12116957 | 13657083 | 13590742
MCR009737 | HPR062 | 2019-03-01 | Material | 28097650 | 31669002 | 32006069
MCR009738 | HPR062 | 2019-03-01 | Equipment | 6870258 | 7743503 | 9083518
MCR009739 | HPR062 | 2019-03-01 | Subcontract | 30527689 | 34407911 | 28822416
MCR009740 | HPR062 | 2019-03-01 | Overhead | 7854013 | 8852297 | 13706658
MCR009741 | HPR062 | 2019-04-01 | Labor | 8276892 | 9284334 | 7554033
MCR009742 | HPR062 | 2019-04-01 | Material | 19193038 | 21529165 | 21097594
MCR009743 | HPR062 | 2019-04-01 | Equipment | 4692959 | 5264174 | 6007184
MCR009744 | HPR062 | 2019-04-01 | Subcontract | 20852958 | 23391125 | 23469664
MCR009745 | HPR062 | 2019-04-01 | Overhead | 5364946 | 6017953 | 12992726
MCR009746 | HPR062 | 2019-05-01 | Labor | 4505695 | 3610899 | 2702786
MCR009747 | HPR062 | 2019-05-01 | Material | 10448122 | 8373206 | 9349393
MCR009748 | HPR062 | 2019-05-01 | Equipment | 2554708 | 2047363 | 1538585
MCR009749 | HPR062 | 2019-05-01 | Subcontract | 11351732 | 9097366 | 10405096
MCR009750 | HPR062 | 2019-05-01 | Overhead | 2920517 | 2340525 | 13546705
MCR009751 | HPR062 | 2019-06-01 | Labor | 1199751 | 1636123 | 1288715
MCR009752 | HPR062 | 2019-06-01 | Material | 2782067 | 3793956 | 4161984
MCR009753 | HPR062 | 2019-06-01 | Equipment | 680253 | 927674 | 993447
MCR009754 | HPR062 | 2019-06-01 | Subcontract | 3022675 | 4122078 | 3598983
MCR009755 | HPR062 | 2019-06-01 | Overhead | 777659 | 1060508 | 12340818
MCR009756 | HPR063 | 2021-05-01 | Labor | 4424049 | 2762026 | 2826839
MCR009757 | HPR063 | 2021-05-01 | Material | 14395325 | 8987301 | 9448161
MCR009758 | HPR063 | 2021-05-01 | Equipment | 3079261 | 1922447 | 2018030
MCR009759 | HPR063 | 2021-05-01 | Subcontract | 9874799 | 6165043 | 6877378
MCR009760 | HPR063 | 2021-05-01 | Overhead | 3129927 | 1954078 | 13183496
MCR009761 | HPR063 | 2021-06-01 | Labor | 12212660 | 8091648 | 7305526
MCR009762 | HPR063 | 2021-06-01 | Material | 39738528 | 26329251 | 27647825
MCR009763 | HPR063 | 2021-06-01 | Equipment | 8500349 | 5632011 | 5275877
MCR009764 | HPR063 | 2021-06-01 | Subcontract | 27259545 | 18061147 | 17256580
MCR009765 | HPR063 | 2021-06-01 | Overhead | 8640214 | 5724680 | 13260622
MCR009766 | HPR063 | 2021-07-01 | Labor | 18451682 | 11863551 | 12920176
MCR009767 | HPR063 | 2021-07-01 | Material | 60039556 | 38602568 | 39293699
MCR009768 | HPR063 | 2021-07-01 | Equipment | 12842881 | 8257360 | 7814396
MCR009769 | HPR063 | 2021-07-01 | Subcontract | 41185495 | 26480307 | 24756575
MCR009770 | HPR063 | 2021-07-01 | Overhead | 13054197 | 8393226 | 13435060
MCR009771 | HPR063 | 2021-08-01 | Labor | 23197118 | 10193775 | 9663711
MCR009772 | HPR063 | 2021-08-01 | Material | 75480636 | 33169318 | 34136949
MCR009773 | HPR063 | 2021-08-01 | Equipment | 16145837 | 7095149 | 7591784
MCR009774 | HPR063 | 2021-08-01 | Subcontract | 51777654 | 22753246 | 24470982
MCR009775 | HPR063 | 2021-08-01 | Overhead | 16411499 | 7211892 | 14074386
MCR009776 | HPR063 | 2021-09-01 | Labor | 26509508 | 18691966 | 20071366
MCR009777 | HPR063 | 2021-09-01 | Material | 86258753 | 60821413 | 67338734
MCR009778 | HPR063 | 2021-09-01 | Equipment | 18451351 | 13010126 | 13311768
MCR009779 | HPR063 | 2021-09-01 | Subcontract | 59171148 | 41721827 | 39663892
MCR009780 | HPR063 | 2021-09-01 | Overhead | 18754948 | 13224194 | 12411041
MCR009781 | HPR063 | 2021-10-01 | Labor | 28454839 | 27497688 | 26537847
MCR009782 | HPR063 | 2021-10-01 | Material | 92588628 | 89474173 | 94062813
MCR009783 | HPR063 | 2021-10-01 | Equipment | 19805356 | 19139152 | 19311557
MCR009784 | HPR063 | 2021-10-01 | Subcontract | 63513270 | 61376838 | 64128849
MCR009785 | HPR063 | 2021-10-01 | Overhead | 20131232 | 19454066 | 12695909
MCR009786 | HPR063 | 2021-11-01 | Labor | 29105780 | 27796986 | 31386633
MCR009787 | HPR063 | 2021-11-01 | Material | 94706710 | 90448053 | 94064233
MCR009788 | HPR063 | 2021-11-01 | Equipment | 20258428 | 19347472 | 21935502
MCR009789 | HPR063 | 2021-11-01 | Subcontract | 64966216 | 62044893 | 66184487
MCR009790 | HPR063 | 2021-11-01 | Overhead | 20591759 | 19665814 | 12713876
MCR009791 | HPR063 | 2021-12-01 | Labor | 28543367 | 20247241 | 36182451
MCR009792 | HPR063 | 2021-12-01 | Material | 92876688 | 65882088 | 89042304
MCR009793 | HPR063 | 2021-12-01 | Equipment | 19866974 | 14092640 | 13508599
MCR009794 | HPR063 | 2021-12-01 | Subcontract | 63710871 | 45193313 | 37626723
MCR009795 | HPR063 | 2021-12-01 | Overhead | 20193864 | 14324519 | 13808414
MCR009796 | HPR063 | 2022-01-01 | Labor | 26859450 | 26025129 | 32007635
MCR009797 | HPR063 | 2022-01-01 | Material | 87397425 | 84682642 | 117359642
MCR009798 | HPR063 | 2022-01-01 | Equipment | 18694921 | 18114210 | 18166773
MCR009799 | HPR063 | 2022-01-01 | Subcontract | 59952246 | 58089979 | 58206953
MCR009800 | HPR063 | 2022-01-01 | Overhead | 19002526 | 18412260 | 11568179
MCR009801 | HPR063 | 2022-02-01 | Labor | 24160362 | 25160915 | 29800737
MCR009802 | HPR063 | 2022-02-01 | Material | 78614915 | 81870596 | 73181838
MCR009803 | HPR063 | 2022-02-01 | Equipment | 16816281 | 17512694 | 14265556
MCR009804 | HPR063 | 2022-02-01 | Subcontract | 53927684 | 56160992 | 54333323
MCR009805 | HPR063 | 2022-02-01 | Overhead | 17092975 | 17800846 | 12604720
MCR009806 | HPR063 | 2022-03-01 | Labor | 20572833 | 23849223 | 21821479
MCR009807 | HPR063 | 2022-03-01 | Material | 66941527 | 77602505 | 73744369
MCR009808 | HPR063 | 2022-03-01 | Equipment | 14319261 | 16599719 | 19611728
MCR009809 | HPR063 | 2022-03-01 | Subcontract | 45920059 | 53233198 | 62183615
MCR009810 | HPR063 | 2022-03-01 | Overhead | 14554869 | 16872850 | 11781822
MCR009811 | HPR063 | 2022-04-01 | Labor | 16254366 | 27534741 | 30218881
MCR009812 | HPR063 | 2022-04-01 | Material | 52889753 | 89594738 | 96872468
MCR009813 | HPR063 | 2022-04-01 | Equipment | 11313488 | 19164942 | 19283693
MCR009814 | HPR063 | 2022-04-01 | Subcontract | 36280926 | 61459543 | 56200900
MCR009815 | HPR063 | 2022-04-01 | Overhead | 11499640 | 19480280 | 13425533
MCR009816 | HPR063 | 2022-05-01 | Labor | 11413930 | 19617060 | 19061834
MCR009817 | HPR063 | 2022-05-01 | Material | 37139556 | 63831557 | 76978264
MCR009818 | HPR063 | 2022-05-01 | Equipment | 7944411 | 13654017 | 12702890
MCR009819 | HPR063 | 2022-05-01 | Subcontract | 25476721 | 43786704 | 42462140
MCR009820 | HPR063 | 2022-05-01 | Overhead | 8075128 | 13878679 | 12730338
MCR009821 | HPR063 | 2022-06-01 | Labor | 6363079 | 17151944 | 19291217
MCR009822 | HPR063 | 2022-06-01 | Material | 20704696 | 55810366 | 45167967
MCR009823 | HPR063 | 2022-06-01 | Equipment | 4428879 | 11938228 | 11253323
MCR009824 | HPR063 | 2022-06-01 | Subcontract | 14202856 | 38284387 | 38023218
MCR009825 | HPR063 | 2022-06-01 | Overhead | 4501752 | 12134659 | 12612653
MCR009826 | HPR063 | 2022-07-01 | Labor | 1726935 | 6673066 | 5427216
MCR009827 | HPR063 | 2022-07-01 | Material | 5619238 | 21713356 | 26903961
MCR009828 | HPR063 | 2022-07-01 | Equipment | 1201994 | 4644639 | 4917201
MCR009829 | HPR063 | 2022-07-01 | Subcontract | 3854644 | 14894769 | 14355148
MCR009830 | HPR063 | 2022-07-01 | Overhead | 1221772 | 4721061 | 13404831
MCR009831 | HPR063 | 2022-08-01 | Labor | 0 | 2933503 | 2778247
MCR009832 | HPR063 | 2022-08-01 | Material | 0 | 9545266 | 11606574
MCR009833 | HPR063 | 2022-08-01 | Equipment | 0 | 2041799 | 2228036
MCR009834 | HPR063 | 2022-08-01 | Subcontract | 0 | 6547791 | 6848322
MCR009835 | HPR063 | 2022-08-01 | Overhead | 0 | 2075395 | 13949852
MCR009836 | HPR063 | 2022-09-01 | Labor | 0 | 2159497 | 2324693
MCR009837 | HPR063 | 2022-09-01 | Material | 0 | 7026744 | 6618621
MCR009838 | HPR063 | 2022-09-01 | Equipment | 0 | 1503070 | 1653542
MCR009839 | HPR063 | 2022-09-01 | Subcontract | 0 | 4820154 | 4758124
MCR009840 | HPR063 | 2022-09-01 | Overhead | 0 | 1527801 | 11980174
MCR009841 | HPR065 | 2016-10-01 | Labor | 2505432 | 1340695 | 1454543
MCR009842 | HPR065 | 2016-10-01 | Material | 6952058 | 3720152 | 3828415
MCR009843 | HPR065 | 2016-10-01 | Equipment | 2380634 | 1273913 | 1343502
MCR009844 | HPR065 | 2016-10-01 | Subcontract | 6368035 | 3407633 | 3266782
MCR009845 | HPR065 | 2016-10-01 | Overhead | 2420873 | 1295446 | 21270520
MCR009846 | HPR065 | 2016-11-01 | Labor | 7221602 | 2127151 | 2386963
MCR009847 | HPR065 | 2016-11-01 | Material | 20038464 | 5902408 | 5263853
MCR009848 | HPR065 | 2016-11-01 | Equipment | 6861888 | 2021196 | 2200303
MCR009849 | HPR065 | 2016-11-01 | Subcontract | 18355089 | 5406563 | 5451545
MCR009850 | HPR065 | 2016-11-01 | Overhead | 6977873 | 2055360 | 18808591
MCR009851 | HPR065 | 2016-12-01 | Labor | 11500963 | 7930054 | 8374469
MCR009852 | HPR065 | 2016-12-01 | Material | 31912811 | 22004272 | 24209627
MCR009853 | HPR065 | 2016-12-01 | Equipment | 10928090 | 7535051 | 6877662
MCR009854 | HPR065 | 2016-12-01 | Subcontract | 29231906 | 20155755 | 21368451
MCR009855 | HPR065 | 2016-12-01 | Overhead | 11112804 | 7662414 | 20003106
MCR009856 | HPR065 | 2017-01-01 | Labor | 15350673 | 4839364 | 5434333
MCR009857 | HPR065 | 2017-01-01 | Material | 42594966 | 13428241 | 12091201
MCR009858 | HPR065 | 2017-01-01 | Equipment | 14586042 | 4598311 | 6035092
MCR009859 | HPR065 | 2017-01-01 | Subcontract | 39016683 | 12300172 | 13507861
MCR009860 | HPR065 | 2017-01-01 | Overhead | 14832586 | 4676035 | 19898387
MCR009861 | HPR065 | 2017-02-01 | Labor | 18778143 | 11959412 | 11109861
MCR009862 | HPR065 | 2017-02-01 | Material | 52105492 | 33184914 | 34941576
MCR009863 | HPR065 | 2017-02-01 | Equipment | 17842787 | 11363703 | 12311313
MCR009864 | HPR065 | 2017-02-01 | Subcontract | 47728256 | 30397142 | 33040725
MCR009865 | HPR065 | 2017-02-01 | Overhead | 18144379 | 11555781 | 21423125
MCR009866 | HPR065 | 2017-03-01 | Labor | 21791057 | 13304595 | 14040015
MCR009867 | HPR065 | 2017-03-01 | Material | 60465711 | 36917521 | 37855159
MCR009868 | HPR065 | 2017-03-01 | Equipment | 20705625 | 12641882 | 14400830
MCR009869 | HPR065 | 2017-03-01 | Subcontract | 55386156 | 33816184 | 34876784
MCR009870 | HPR065 | 2017-03-01 | Overhead | 21055607 | 12855564 | 20467075
MCR009871 | HPR065 | 2017-04-01 | Labor | 24397396 | 14285864 | 13029012
MCR009872 | HPR065 | 2017-04-01 | Material | 67697766 | 39640339 | 36328375
MCR009873 | HPR065 | 2017-04-01 | Equipment | 23182140 | 13574272 | 15952972
MCR009874 | HPR065 | 2017-04-01 | Subcontract | 62010667 | 36310266 | 39769488
MCR009875 | HPR065 | 2017-04-01 | Overhead | 23573982 | 13803714 | 20736959
MCR009876 | HPR065 | 2017-05-01 | Labor | 26605463 | 17655127 | 21440363
MCR009877 | HPR065 | 2017-05-01 | Material | 73824698 | 48989352 | 53789123
MCR009878 | HPR065 | 2017-05-01 | Equipment | 25280221 | 16775709 | 15538661
MCR009879 | HPR065 | 2017-05-01 | Subcontract | 67622893 | 44873895 | 42953199
MCR009880 | HPR065 | 2017-05-01 | Overhead | 25707526 | 17059265 | 19024542
MCR009881 | HPR065 | 2017-06-01 | Labor | 28423916 | 13696570 | 13490038
MCR009882 | HPR065 | 2017-06-01 | Material | 78870531 | 38005170 | 33136740
MCR009883 | HPR065 | 2017-06-01 | Equipment | 27008095 | 13014332 | 15630314
MCR009884 | HPR065 | 2017-06-01 | Subcontract | 72244840 | 34812463 | 34405068
MCR009885 | HPR065 | 2017-06-01 | Overhead | 27464606 | 13234310 | 19700855
MCR009886 | HPR065 | 2017-07-01 | Labor | 29861802 | 8353202 | 9696697
MCR009887 | HPR065 | 2017-07-01 | Material | 82860370 | 23178422 | 26880384
MCR009888 | HPR065 | 2017-07-01 | Equipment | 28374359 | 7937122 | 8557175
MCR009889 | HPR065 | 2017-07-01 | Subcontract | 75899503 | 21231268 | 25477693
MCR009890 | HPR065 | 2017-07-01 | Overhead | 28853963 | 8071281 | 19092732
MCR009891 | HPR065 | 2017-08-01 | Labor | 30928599 | 13974190 | 14032343
MCR009892 | HPR065 | 2017-08-01 | Material | 85820513 | 38775510 | 39291580
MCR009893 | HPR065 | 2017-08-01 | Equipment | 29388018 | 13278124 | 15485046
MCR009894 | HPR065 | 2017-08-01 | Subcontract | 78610973 | 35518088 | 38436346
MCR009895 | HPR065 | 2017-08-01 | Overhead | 29884756 | 13502560 | 19403656
MCR009896 | HPR065 | 2017-09-01 | Labor | 31634265 | 16748867 | 19263134
MCR009897 | HPR065 | 2017-09-01 | Material | 87778591 | 46474669 | 45049406
MCR009898 | HPR065 | 2017-09-01 | Equipment | 30058534 | 15914592 | 16251984
MCR009899 | HPR065 | 2017-09-01 | Subcontract | 80404559 | 42570463 | 40495824
MCR009900 | HPR065 | 2017-09-01 | Overhead | 30566606 | 16183592 | 19348858
MCR009901 | HPR065 | 2017-10-01 | Labor | 31989292 | 15070155 | 15784959
MCR009902 | HPR065 | 2017-10-01 | Material | 88763719 | 41816587 | 43671674
MCR009903 | HPR065 | 2017-10-01 | Equipment | 30395877 | 14319498 | 15293142
MCR009904 | HPR065 | 2017-10-01 | Subcontract | 81306929 | 38303693 | 43383177
MCR009905 | HPR065 | 2017-10-01 | Overhead | 30909651 | 14561536 | 19867026
MCR009906 | HPR065 | 2017-11-01 | Labor | 32004776 | 27243677 | 29618743
MCR009907 | HPR065 | 2017-11-01 | Material | 88806684 | 75595610 | 68715692
MCR009908 | HPR065 | 2017-11-01 | Equipment | 30410590 | 25886645 | 27617293
MCR009909 | HPR065 | 2017-11-01 | Subcontract | 81346284 | 69245035 | 76584888
MCR009910 | HPR065 | 2017-11-01 | Overhead | 30924612 | 26324200 | 16655355
MCR009911 | HPR065 | 2017-12-01 | Labor | 31692496 | 17588931 | 17256016
MCR009912 | HPR065 | 2017-12-01 | Material | 87940171 | 48805672 | 56120653
MCR009913 | HPR065 | 2017-12-01 | Equipment | 30113865 | 16712811 | 19484800
MCR009914 | HPR065 | 2017-12-01 | Subcontract | 80552564 | 44705645 | 48053244
MCR009915 | HPR065 | 2017-12-01 | Overhead | 30622871 | 16995303 | 20186044
MCR009916 | HPR065 | 2018-01-01 | Labor | 31065012 | 19233400 | 20723815
MCR009917 | HPR065 | 2018-01-01 | Material | 86199032 | 53368738 | 45285683
MCR009918 | HPR065 | 2018-01-01 | Equipment | 29517637 | 18275368 | 18049602
MCR009919 | HPR065 | 2018-01-01 | Subcontract | 78957694 | 48885380 | 50341584
MCR009920 | HPR065 | 2018-01-01 | Overhead | 30016565 | 18584271 | 19327936
MCR009921 | HPR065 | 2018-02-01 | Labor | 30135788 | 15563121 | 18862059
MCR009922 | HPR065 | 2018-02-01 | Material | 83620625 | 43184467 | 45693301
MCR009923 | HPR065 | 2018-02-01 | Equipment | 28634698 | 14787909 | 15515624
MCR009924 | HPR065 | 2018-02-01 | Subcontract | 76595892 | 39556662 | 42348966
MCR009925 | HPR065 | 2018-02-01 | Overhead | 29118702 | 15037865 | 19383842
MCR009926 | HPR065 | 2018-03-01 | Labor | 28919339 | 22079960 | 25809400
MCR009927 | HPR065 | 2018-03-01 | Material | 80245229 | 61267356 | 69243018
MCR009928 | HPR065 | 2018-03-01 | Equipment | 27478841 | 20980138 | 23968407
MCR009929 | HPR065 | 2018-03-01 | Subcontract | 73504053 | 56120458 | 48793108
MCR009930 | HPR065 | 2018-03-01 | Overhead | 27943308 | 21334759 | 20747028
MCR009931 | HPR065 | 2018-04-01 | Labor | 27431424 | 15292767 | 16024090
MCR009932 | HPR065 | 2018-04-01 | Material | 76116570 | 42434288 | 40343959
MCR009933 | HPR065 | 2018-04-01 | Equipment | 26065040 | 14531020 | 16692184
MCR009934 | HPR065 | 2018-04-01 | Subcontract | 69722231 | 38869503 | 45138738
MCR009935 | HPR065 | 2018-04-01 | Overhead | 26505611 | 14776634 | 19268412
MCR009936 | HPR065 | 2018-05-01 | Labor | 25689292 | 21863300 | 23049308
MCR009937 | HPR065 | 2018-05-01 | Material | 71282513 | 60666169 | 56218236
MCR009938 | HPR065 | 2018-05-01 | Equipment | 24409686 | 20774270 | 19690794
MCR009939 | HPR065 | 2018-05-01 | Subcontract | 65294269 | 55569775 | 59788696
MCR009940 | HPR065 | 2018-05-01 | Overhead | 24822276 | 21125411 | 18369625
MCR009941 | HPR065 | 2018-06-01 | Labor | 23712011 | 27377293 | 32524033
MCR009942 | HPR065 | 2018-06-01 | Material | 65795962 | 75966369 | 81146328
MCR009943 | HPR065 | 2018-06-01 | Equipment | 22530895 | 26013606 | 27017687
MCR009944 | HPR065 | 2018-06-01 | Subcontract | 60268629 | 69584648 | 71916509
MCR009945 | HPR065 | 2018-06-01 | Overhead | 22911728 | 26453307 | 20420140
MCR009946 | HPR065 | 2018-07-01 | Labor | 21520905 | 11565391 | 10516103
MCR009947 | HPR065 | 2018-07-01 | Material | 59716094 | 32091587 | 36515259
MCR009948 | HPR065 | 2018-07-01 | Equipment | 20448930 | 10989309 | 14417421
MCR009949 | HPR065 | 2018-07-01 | Subcontract | 54699513 | 29395663 | 32283854
MCR009950 | HPR065 | 2018-07-01 | Overhead | 20794573 | 11175058 | 18916512
MCR009951 | HPR065 | 2018-08-01 | Labor | 19140183 | 16769441 | 19699873
MCR009952 | HPR065 | 2018-08-01 | Material | 53110078 | 46531757 | 52475577
MCR009953 | HPR065 | 2018-08-01 | Equipment | 18186793 | 15934141 | 17124105
MCR009954 | HPR065 | 2018-08-01 | Subcontract | 48648449 | 42622755 | 40859350
MCR009955 | HPR065 | 2018-08-01 | Overhead | 18494200 | 16203471 | 18587388
MCR009956 | HPR065 | 2018-09-01 | Labor | 16597839 | 25558457 | 28835136
MCR009957 | HPR065 | 2018-09-01 | Material | 46055597 | 70919473 | 80905465
MCR009958 | HPR065 | 2018-09-01 | Equipment | 15771086 | 24285368 | 24857554
MCR009959 | HPR065 | 2018-09-01 | Subcontract | 42186596 | 64961727 | 66855532
MCR009960 | HPR065 | 2018-09-01 | Overhead | 16037661 | 24695857 | 21955915
MCR009961 | HPR065 | 2018-10-01 | Labor | 13927049 | 25926205 | 29358291
MCR009962 | HPR065 | 2018-10-01 | Material | 38644703 | 71939897 | 62682526
MCR009963 | HPR065 | 2018-10-01 | Equipment | 13233331 | 24634798 | 27568479
MCR009964 | HPR065 | 2018-10-01 | Subcontract | 35398270 | 65896429 | 71538374
MCR009965 | HPR065 | 2018-10-01 | Overhead | 13457010 | 25051193 | 20193838
MCR009966 | HPR065 | 2018-11-01 | Labor | 11168440 | 19047896 | 21480910
MCR009967 | HPR065 | 2018-11-01 | Material | 30990130 | 52854002 | 52194458
MCR009968 | HPR065 | 2018-11-01 | Equipment | 10612131 | 18099104 | 20406005
MCR009969 | HPR065 | 2018-11-01 | Subcontract | 28386736 | 48413886 | 46338702
MCR009970 | HPR065 | 2018-11-01 | Overhead | 10791505 | 18405028 | 19704938
MCR009971 | HPR065 | 2018-12-01 | Labor | 8374161 | 14626582 | 15290696
MCR009972 | HPR065 | 2018-12-01 | Material | 23236578 | 40585763 | 39905864
MCR009973 | HPR065 | 2018-12-01 | Equipment | 7957037 | 13898019 | 13711174
MCR009974 | HPR065 | 2018-12-01 | Subcontract | 21284539 | 37176267 | 40026378
MCR009975 | HPR065 | 2018-12-01 | Overhead | 8091532 | 14132934 | 20988184
MCR009976 | HPR065 | 2019-01-01 | Labor | 5616164 | 21215684 | 23490586
MCR009977 | HPR065 | 2019-01-01 | Material | 15583703 | 58869168 | 67952386
MCR009978 | HPR065 | 2019-01-01 | Equipment | 5336418 | 20158912 | 21889255
MCR009979 | HPR065 | 2019-01-01 | Subcontract | 14274560 | 53923735 | 55848307
MCR009980 | HPR065 | 2019-01-01 | Overhead | 5426618 | 20499653 | 19830303
MCR009981 | HPR065 | 2019-02-01 | Labor | 3007155 | 15417110 | 17180784
MCR009982 | HPR065 | 2019-02-01 | Material | 8344238 | 42779317 | 42972197
MCR009983 | HPR065 | 2019-02-01 | Equipment | 2857366 | 14649171 | 17952736
MCR009984 | HPR065 | 2019-02-01 | Subcontract | 7643262 | 39185546 | 41326764
MCR009985 | HPR065 | 2019-02-01 | Overhead | 2905663 | 14896781 | 20767475
MCR009986 | HPR065 | 2019-03-01 | Labor | 789809 | 20168844 | 21053416
MCR009987 | HPR065 | 2019-03-01 | Material | 2191557 | 55964401 | 51975364
MCR009988 | HPR065 | 2019-03-01 | Equipment | 750468 | 19164216 | 19235265
MCR009989 | HPR065 | 2019-03-01 | Subcontract | 2007451 | 51262989 | 48045649
MCR009990 | HPR065 | 2019-03-01 | Overhead | 763153 | 19488143 | 21088460
MCR009991 | HPR065 | 2019-04-01 | Labor | 0 | 30261086 | 38203379
MCR009992 | HPR065 | 2019-04-01 | Material | 0 | 83968301 | 79860951
MCR009993 | HPR065 | 2019-04-01 | Equipment | 0 | 28753754 | 33127752
MCR009994 | HPR065 | 2019-04-01 | Subcontract | 0 | 76914360 | 107933027
MCR009995 | HPR065 | 2019-04-01 | Overhead | 0 | 29239771 | 18732313
MCR009996 | HPR065 | 2019-05-01 | Labor | 0 | 15651470 | 17579101
MCR009997 | HPR065 | 2019-05-01 | Material | 0 | 43429616 | 54031206
MCR009998 | HPR065 | 2019-05-01 | Equipment | 0 | 14871856 | 14968922
MCR009999 | HPR065 | 2019-05-01 | Subcontract | 0 | 39781216 | 83185625
MCR010000 | HPR065 | 2019-05-01 | Overhead | 0 | 15123231 | 19761681
MCR010001 | HPR065 | 2019-06-01 | Labor | 0 | 7931873 | 8739196
MCR010002 | HPR065 | 2019-06-01 | Material | 0 | 22009321 | 20011515
MCR010003 | HPR065 | 2019-06-01 | Equipment | 0 | 7536780 | 7871453
MCR010004 | HPR065 | 2019-06-01 | Subcontract | 0 | 20160379 | 71753537
MCR010005 | HPR065 | 2019-06-01 | Overhead | 0 | 7664172 | 19194376
MCR010006 | HPR065 | 2019-07-01 | Labor | 0 | 14394488 | 16296392
MCR010007 | HPR065 | 2019-07-01 | Material | 0 | 39941751 | 37450159
MCR010008 | HPR065 | 2019-07-01 | Equipment | 0 | 13677486 | 16380462
MCR010009 | HPR065 | 2019-07-01 | Subcontract | 0 | 36586356 | 68710689
MCR010010 | HPR065 | 2019-07-01 | Overhead | 0 | 13908673 | 20427010
MCR010011 | HPR065 | 2019-08-01 | Labor | 0 | 7806534 | 11631515
MCR010012 | HPR065 | 2019-08-01 | Material | 0 | 21661528 | 23685151
MCR010013 | HPR065 | 2019-08-01 | Equipment | 0 | 7417683 | 9019073
MCR010014 | HPR065 | 2019-08-01 | Subcontract | 0 | 19841804 | 54659605
MCR010015 | HPR065 | 2019-08-01 | Overhead | 0 | 7543062 | 19191705
MCR010016 | HPR065 | 2019-09-01 | Labor | 0 | 11351319 | 15461977
MCR010017 | HPR065 | 2019-09-01 | Material | 0 | 31497581 | 36179938
MCR010018 | HPR065 | 2019-09-01 | Equipment | 0 | 10785900 | 13451576
MCR010019 | HPR065 | 2019-09-01 | Subcontract | 0 | 28851558 | 52361068
MCR010020 | HPR065 | 2019-09-01 | Overhead | 0 | 10968211 | 19418558
MCR010021 | HPR065 | 2019-10-01 | Labor | 0 | 7883239 | 7611733
MCR010022 | HPR065 | 2019-10-01 | Material | 0 | 21874370 | 22025284
MCR010023 | HPR065 | 2019-10-01 | Equipment | 0 | 7490568 | 8167393
MCR010024 | HPR065 | 2019-10-01 | Subcontract | 0 | 20036766 | 65140512
MCR010025 | HPR065 | 2019-10-01 | Overhead | 0 | 7617179 | 19991783
MCR010026 | HPR065 | 2019-11-01 | Labor | 0 | 5611244 | 6241918
MCR010027 | HPR065 | 2019-11-01 | Material | 0 | 15570050 | 15843612
MCR010028 | HPR065 | 2019-11-01 | Equipment | 0 | 5331743 | 6502649
MCR010029 | HPR065 | 2019-11-01 | Subcontract | 0 | 14262053 | 37017519
MCR010030 | HPR065 | 2019-11-01 | Overhead | 0 | 5421864 | 20643331
MCR010031 | HPR065 | 2019-12-01 | Labor | 0 | 9829135 | 13391000
MCR010032 | HPR065 | 2019-12-01 | Material | 0 | 27273831 | 28905823
MCR010033 | HPR065 | 2019-12-01 | Equipment | 0 | 9339537 | 12874299
MCR010034 | HPR065 | 2019-12-01 | Subcontract | 0 | 24982633 | 59505969
MCR010035 | HPR065 | 2019-12-01 | Overhead | 0 | 9497401 | 19558818
MCR010036 | HPR065 | 2020-01-01 | Labor | 0 | 7892364 | 8750857
MCR010037 | HPR065 | 2020-01-01 | Material | 0 | 21899691 | 21836972
MCR010038 | HPR065 | 2020-01-01 | Equipment | 0 | 7499239 | 8814987
MCR010039 | HPR065 | 2020-01-01 | Subcontract | 0 | 20059959 | 54580632
MCR010040 | HPR065 | 2020-01-01 | Overhead | 0 | 7625996 | 19074845
MCR010041 | HPR065 | 2020-02-01 | Labor | 0 | 4406769 | 4659862
MCR010042 | HPR065 | 2020-02-01 | Material | 0 | 12227880 | 13309643
MCR010043 | HPR065 | 2020-02-01 | Equipment | 0 | 4187264 | 5260034
MCR010044 | HPR065 | 2020-02-01 | Subcontract | 0 | 11200650 | 26905552
MCR010045 | HPR065 | 2020-02-01 | Overhead | 0 | 4258040 | 19766272
MCR010046 | HPR065 | 2020-03-01 | Labor | 0 | 4350644 | 6415092
MCR010047 | HPR065 | 2020-03-01 | Material | 0 | 12072145 | 12296783
MCR010048 | HPR065 | 2020-03-01 | Equipment | 0 | 4133935 | 4821009
MCR010049 | HPR065 | 2020-03-01 | Subcontract | 0 | 11057998 | 56356646
MCR010050 | HPR065 | 2020-03-01 | Overhead | 0 | 4203810 | 20123237
MCR010051 | HPR065 | 2020-04-01 | Labor | 0 | 2868608 | 2946633
MCR010052 | HPR065 | 2020-04-01 | Material | 0 | 7959797 | 8434768
MCR010053 | HPR065 | 2020-04-01 | Equipment | 0 | 2725720 | 3987731
MCR010054 | HPR065 | 2020-04-01 | Subcontract | 0 | 7291117 | 44418595
MCR010055 | HPR065 | 2020-04-01 | Overhead | 0 | 2771792 | 21175813
MCR010056 | HPR065 | 2020-05-01 | Labor | 0 | 2357302 | 2824555
MCR010057 | HPR065 | 2020-05-01 | Material | 0 | 6541030 | 6583843
MCR010058 | HPR065 | 2020-05-01 | Equipment | 0 | 2239883 | 3145063
MCR010059 | HPR065 | 2020-05-01 | Subcontract | 0 | 5991536 | 46678449
MCR010060 | HPR065 | 2020-05-01 | Overhead | 0 | 2277743 | 18775508
MCR010061 | HPR065 | 2020-06-01 | Labor | 0 | 1064501 | 1280497
MCR010062 | HPR065 | 2020-06-01 | Material | 0 | 2953771 | 2903656
MCR010063 | HPR065 | 2020-06-01 | Equipment | 0 | 1011477 | 1356533
MCR010064 | HPR065 | 2020-06-01 | Subcontract | 0 | 2705633 | 25790615
MCR010065 | HPR065 | 2020-06-01 | Overhead | 0 | 1028574 | 18190737
MCR010066 | HPR065 | 2020-07-01 | Labor | 0 | 296562 | 326855
MCR010067 | HPR065 | 2020-07-01 | Material | 0 | 822900 | 837900
MCR010068 | HPR065 | 2020-07-01 | Equipment | 0 | 281790 | 300058
MCR010069 | HPR065 | 2020-07-01 | Subcontract | 0 | 753770 | 27035216
MCR010070 | HPR065 | 2020-07-01 | Overhead | 0 | 286553 | 20784216
MCR010071 | HPR066 | 2019-08-01 | Labor | 2740445 | 1340711 | 1480882
MCR010072 | HPR066 | 2019-08-01 | Material | 11291044 | 5523929 | 6274804
MCR010073 | HPR066 | 2019-08-01 | Equipment | 5119862 | 2504795 | 2478305
MCR010074 | HPR066 | 2019-08-01 | Subcontract | 6498956 | 3179491 | 3413015
MCR010075 | HPR066 | 2019-08-01 | Overhead | 2348903 | 1149156 | 13938108
MCR010076 | HPR066 | 2019-09-01 | Labor | 7778931 | 5417619 | 5801976
MCR010077 | HPR066 | 2019-09-01 | Material | 32050355 | 22321397 | 21156296
MCR010078 | HPR066 | 2019-09-01 | Equipment | 14533059 | 10121516 | 9861079
MCR010079 | HPR066 | 2019-09-01 | Subcontract | 18447706 | 12847863 | 12367551
MCR010080 | HPR066 | 2019-09-01 | Overhead | 6667513 | 4643575 | 13702141
MCR010081 | HPR066 | 2019-10-01 | Labor | 12164715 | 8259013 | 8792752
MCR010082 | HPR066 | 2019-10-01 | Material | 50120440 | 34028363 | 32740851
MCR010083 | HPR066 | 2019-10-01 | Equipment | 22726840 | 15429976 | 15529794
MCR010084 | HPR066 | 2019-10-01 | Subcontract | 28848577 | 19586218 | 20459686
MCR010085 | HPR066 | 2019-10-01 | Overhead | 10426677 | 7079003 | 13709335
MCR010086 | HPR066 | 2019-11-01 | Labor | 15912896 | 5483630 | 7158276
MCR010087 | HPR066 | 2019-11-01 | Material | 65563504 | 22593373 | 26423461
MCR010088 | HPR066 | 2019-11-01 | Equipment | 29729414 | 10244842 | 10294297
MCR010089 | HPR066 | 2019-11-01 | Subcontract | 37737374 | 13004408 | 11822690
MCR010090 | HPR066 | 2019-11-01 | Overhead | 13639335 | 4700154 | 14877897
MCR010091 | HPR066 | 2019-12-01 | Labor | 19039332 | 41037308 | 42597351
MCR010092 | HPR066 | 2019-12-01 | Material | 78444886 | 169079823 | 160286616
MCR010093 | HPR066 | 2019-12-01 | Equipment | 35570406 | 76668325 | 90677087
MCR010094 | HPR066 | 2019-12-01 | Subcontract | 45151705 | 97319822 | 85147130
MCR010095 | HPR066 | 2019-12-01 | Overhead | 16319080 | 35174087 | 13209608
MCR010096 | HPR066 | 2020-01-01 | Labor | 21560733 | 15105949 | 16247451
MCR010097 | HPR066 | 2020-01-01 | Material | 88833435 | 62238759 | 67331362
MCR010098 | HPR066 | 2020-01-01 | Equipment | 40281037 | 28221826 | 19988299
MCR010099 | HPR066 | 2020-01-01 | Subcontract | 51131199 | 35823701 | 42158769
MCR010100 | HPR066 | 2020-01-01 | Overhead | 18480236 | 12947680 | 13968498
MCR010101 | HPR066 | 2020-02-01 | Labor | 23494773 | 17846650 | 18691972
MCR010102 | HPR066 | 2020-02-01 | Material | 96801965 | 73530856 | 76382099
MCR010103 | HPR066 | 2020-02-01 | Equipment | 43894324 | 33342166 | 36717082
MCR010104 | HPR066 | 2020-02-01 | Subcontract | 55717766 | 42323263 | 47871856
MCR010105 | HPR066 | 2020-02-01 | Overhead | 20137948 | 15296803 | 14010682
MCR010106 | HPR066 | 2020-03-01 | Labor | 24860218 | 16298947 | 18915288
MCR010107 | HPR066 | 2020-03-01 | Material | 102427803 | 67154089 | 66474842
MCR010108 | HPR066 | 2020-03-01 | Equipment | 46445329 | 30450656 | 29757279
MCR010109 | HPR066 | 2020-03-01 | Subcontract | 58955914 | 38652891 | 40068130
MCR010110 | HPR066 | 2020-03-01 | Overhead | 21308305 | 13970228 | 14438075
MCR010111 | HPR066 | 2020-04-01 | Labor | 25677096 | 20274117 | 25077863
MCR010112 | HPR066 | 2020-04-01 | Material | 105793460 | 83532384 | 79038443
MCR010113 | HPR066 | 2020-04-01 | Equipment | 47971468 | 37877304 | 37762460
MCR010114 | HPR066 | 2020-04-01 | Subcontract | 60893136 | 48079993 | 47195268
MCR010115 | HPR066 | 2020-04-01 | Overhead | 22008471 | 17377445 | 15241623
MCR010116 | HPR066 | 2020-05-01 | Labor | 25966892 | 17628909 | 21172454
MCR010117 | HPR066 | 2020-05-01 | Material | 106987464 | 72633734 | 77223897
MCR010118 | HPR066 | 2020-05-01 | Equipment | 48512883 | 32935371 | 37046566
MCR010119 | HPR066 | 2020-05-01 | Subcontract | 61580387 | 41806893 | 40652765
MCR010120 | HPR066 | 2020-05-01 | Overhead | 22256862 | 15110172 | 14696098
MCR010121 | HPR066 | 2020-06-01 | Labor | 25752809 | 22514766 | 23985676
MCR010122 | HPR066 | 2020-06-01 | Material | 106105412 | 92764189 | 91341102
MCR010123 | HPR066 | 2020-06-01 | Equipment | 48112921 | 42063416 | 42133003
MCR010124 | HPR066 | 2020-06-01 | Subcontract | 61072691 | 53393682 | 53486489
MCR010125 | HPR066 | 2020-06-01 | Overhead | 22073367 | 19297960 | 13872879
MCR010126 | HPR066 | 2020-07-01 | Labor | 25060095 | 16026936 | 17905166
MCR010127 | HPR066 | 2020-07-01 | Material | 103251325 | 66033366 | 69028267
MCR010128 | HPR066 | 2020-07-01 | Equipment | 46818751 | 29942470 | 30614986
MCR010129 | HPR066 | 2020-07-01 | Subcontract | 59429921 | 38007820 | 39640633
MCR010130 | HPR066 | 2020-07-01 | Overhead | 21479624 | 13737082 | 13777801
MCR010131 | HPR066 | 2020-08-01 | Labor | 23916472 | 12373983 | 14006303
MCR010132 | HPR066 | 2020-08-01 | Material | 98539430 | 50982654 | 50436392
MCR010133 | HPR066 | 2020-08-01 | Equipment | 44682168 | 23117807 | 25085947
MCR010134 | HPR066 | 2020-08-01 | Subcontract | 56717824 | 29344855 | 29026570
MCR010135 | HPR066 | 2020-08-01 | Overhead | 20499397 | 10606046 | 14595452
MCR010136 | HPR066 | 2020-09-01 | Labor | 22352725 | 17736858 | 31459134
MCR010137 | HPR066 | 2020-09-01 | Material | 92096559 | 73078497 | 100585627
MCR010138 | HPR066 | 2020-09-01 | Equipment | 41760683 | 33137046 | 35567960
MCR010139 | HPR066 | 2020-09-01 | Subcontract | 53009404 | 42062892 | 36413119
MCR010140 | HPR066 | 2020-09-01 | Overhead | 19159071 | 15202698 | 13716858
MCR010141 | HPR066 | 2020-10-01 | Labor | 20403513 | 27847637 | 57104654
MCR010142 | HPR066 | 2020-10-01 | Material | 84065513 | 114736413 | 157099754
MCR010143 | HPR066 | 2020-10-01 | Equipment | 38119049 | 52026601 | 51772299
MCR010144 | HPR066 | 2020-10-01 | Subcontract | 48386854 | 66040566 | 66503022
MCR010145 | HPR066 | 2020-10-01 | Overhead | 17488353 | 23868895 | 12999084
MCR010146 | HPR066 | 2020-11-01 | Labor | 18108548 | 11572909 | 11822229
MCR010147 | HPR066 | 2020-11-01 | Material | 74609916 | 47682108 | 53167459
MCR010148 | HPR066 | 2020-11-01 | Equipment | 33831460 | 21621192 | 20705827
MCR010149 | HPR066 | 2020-11-01 | Subcontract | 42944354 | 27445110 | 31590651
MCR010150 | HPR066 | 2020-11-01 | Overhead | 15521282 | 9919425 | 15379857
MCR010151 | HPR066 | 2020-12-01 | Labor | 15514397 | 17685166 | 17259648
MCR010152 | HPR066 | 2020-12-01 | Material | 63921629 | 72865519 | 81730698
MCR010153 | HPR066 | 2020-12-01 | Equipment | 28984915 | 33040473 | 33085529
MCR010154 | HPR066 | 2020-12-01 | Subcontract | 36792335 | 41940305 | 37470717
MCR010155 | HPR066 | 2020-12-01 | Overhead | 13297772 | 15158391 | 14714412
MCR010156 | HPR066 | 2021-01-01 | Labor | 12677401 | 20216324 | 23570986
MCR010157 | HPR066 | 2021-01-01 | Material | 52232781 | 83294266 | 83074217
MCR010158 | HPR066 | 2021-01-01 | Equipment | 23684670 | 37769331 | 36086689
MCR010159 | HPR066 | 2021-01-01 | Subcontract | 30064409 | 47942936 | 46612051
MCR010160 | HPR066 | 2021-01-01 | Overhead | 10866112 | 17327909 | 14157887
MCR010161 | HPR066 | 2021-02-01 | Labor | 9668858 | 16798915 | 18367031
MCR010162 | HPR066 | 2021-02-01 | Material | 39837134 | 69214034 | 65514867
MCR010163 | HPR066 | 2021-02-01 | Equipment | 18063931 | 31384727 | 34853865
MCR010164 | HPR066 | 2021-02-01 | Subcontract | 22929660 | 39838565 | 41679820
MCR010165 | HPR066 | 2021-02-01 | Overhead | 8287416 | 14398764 | 14577026
MCR010166 | HPR066 | 2021-03-01 | Labor | 6585499 | 16440688 | 18663505
MCR010167 | HPR066 | 2021-03-01 | Material | 27133237 | 67738083 | 78363806
MCR010168 | HPR066 | 2021-03-01 | Equipment | 12303419 | 30715465 | 31130520
MCR010169 | HPR066 | 2021-03-01 | Subcontract | 15617486 | 38989029 | 38143278
MCR010170 | HPR066 | 2021-03-01 | Overhead | 5644593 | 14091718 | 14895086
MCR010171 | HPR066 | 2021-04-01 | Labor | 3575736 | 7819748 | 8074372
MCR010172 | HPR066 | 2021-04-01 | Material | 14732564 | 32218528 | 32152659
MCR010173 | HPR066 | 2021-04-01 | Equipment | 6680401 | 14609316 | 16550379
MCR010174 | HPR066 | 2021-04-01 | Subcontract | 8479844 | 18544504 | 16859621
MCR010175 | HPR066 | 2021-04-01 | Overhead | 3064851 | 6702499 | 14175712
MCR010176 | HPR066 | 2021-05-01 | Labor | 950119 | 12268818 | 13536340
MCR010177 | HPR066 | 2021-05-01 | Material | 3914632 | 50549359 | 51132512
MCR010178 | HPR066 | 2021-05-01 | Equipment | 1775069 | 22921332 | 21187433
MCR010179 | HPR066 | 2021-05-01 | Subcontract | 2253204 | 29095456 | 24665793
MCR010180 | HPR066 | 2021-05-01 | Overhead | 814370 | 10515906 | 13859937
MCR010181 | HPR066 | 2021-06-01 | Labor | 0 | 4050523 | 3872997
MCR010182 | HPR066 | 2021-06-01 | Material | 0 | 16688760 | 16497456
MCR010183 | HPR066 | 2021-06-01 | Equipment | 0 | 7567427 | 7445839
MCR010184 | HPR066 | 2021-06-01 | Subcontract | 0 | 9605801 | 12915233
MCR010185 | HPR066 | 2021-06-01 | Overhead | 0 | 3471803 | 14096478
MCR010186 | HPR066 | 2021-07-01 | Labor | 0 | 5148105 | 6649605
MCR010187 | HPR066 | 2021-07-01 | Material | 0 | 21210959 | 23660319
MCR010188 | HPR066 | 2021-07-01 | Equipment | 0 | 9617994 | 11611607
MCR010189 | HPR066 | 2021-07-01 | Subcontract | 0 | 12208711 | 10830931
MCR010190 | HPR066 | 2021-07-01 | Overhead | 0 | 4412567 | 14096461
MCR010191 | HPR066 | 2021-08-01 | Labor | 0 | 3838791 | 3629568
MCR010192 | HPR066 | 2021-08-01 | Material | 0 | 15816391 | 15591438
MCR010193 | HPR066 | 2021-08-01 | Equipment | 0 | 7171856 | 6803823
MCR010194 | HPR066 | 2021-08-01 | Subcontract | 0 | 9103678 | 9255410
MCR010195 | HPR066 | 2021-08-01 | Overhead | 0 | 3290322 | 14237984
MCR010196 | HPR066 | 2021-09-01 | Labor | 0 | 2275177 | 2535226
MCR010197 | HPR066 | 2021-09-01 | Material | 0 | 9374069 | 9684617
MCR010198 | HPR066 | 2021-09-01 | Equipment | 0 | 4250621 | 5081818
MCR010199 | HPR066 | 2021-09-01 | Subcontract | 0 | 5395574 | 5401771
MCR010200 | HPR066 | 2021-09-01 | Overhead | 0 | 1950110 | 13509942
MCR010201 | HPR066 | 2021-10-01 | Labor | 0 | 454010 | 475078
MCR010202 | HPR066 | 2021-10-01 | Material | 0 | 1870587 | 2176266
MCR010203 | HPR066 | 2021-10-01 | Equipment | 0 | 848207 | 957672
MCR010204 | HPR066 | 2021-10-01 | Subcontract | 0 | 1076682 | 1267591
MCR010205 | HPR066 | 2021-10-01 | Overhead | 0 | 389143 | 13246145
MCR010206 | HPR067 | 2018-11-01 | Labor | 5874262 | 3180903 | 3363007
MCR010207 | HPR067 | 2018-11-01 | Material | 21214571 | 11487657 | 10555987
MCR010208 | HPR067 | 2018-11-01 | Equipment | 5741430 | 3108976 | 2733885
MCR010209 | HPR067 | 2018-11-01 | Subcontract | 19753842 | 10696674 | 10709185
MCR010210 | HPR067 | 2018-11-01 | Overhead | 3997383 | 2164577 | 28430786
MCR010211 | HPR067 | 2018-12-01 | Labor | 16716660 | 13850512 | 14369402
MCR010212 | HPR067 | 2018-12-01 | Material | 60371295 | 50020357 | 54862584
MCR010213 | HPR067 | 2018-12-01 | Equipment | 16338656 | 13537318 | 15526160
MCR010214 | HPR067 | 2018-12-01 | Subcontract | 56214428 | 46576204 | 48607219
MCR010215 | HPR067 | 2018-12-01 | Overhead | 11375539 | 9425150 | 24285107
MCR010216 | HPR067 | 2019-01-01 | Labor | 26221174 | 18913377 | 20411175
MCR010217 | HPR067 | 2019-01-01 | Material | 94696320 | 68304615 | 66143413
MCR010218 | HPR067 | 2019-01-01 | Equipment | 25628250 | 18485700 | 20337553
MCR010219 | HPR067 | 2019-01-01 | Subcontract | 88176003 | 63601499 | 64958858
MCR010220 | HPR067 | 2019-01-01 | Overhead | 17843276 | 12870385 | 25369170
MCR010221 | HPR067 | 2019-02-01 | Labor | 34417236 | 39681318 | 40242691
MCR010222 | HPR067 | 2019-02-01 | Material | 124295945 | 143306886 | 154508606
MCR010223 | HPR067 | 2019-02-01 | Equipment | 33638979 | 38784027 | 36821593
MCR010224 | HPR067 | 2019-02-01 | Subcontract | 115737545 | 133439487 | 130377460
MCR010225 | HPR067 | 2019-02-01 | Overhead | 23420623 | 27002784 | 25072614
MCR010226 | HPR067 | 2019-03-01 | Labor | 41335686 | 41279254 | 36279714
MCR010227 | HPR067 | 2019-03-01 | Material | 149281547 | 149077744 | 142906667
MCR010228 | HPR067 | 2019-03-01 | Equipment | 40400986 | 40345830 | 37358613
MCR010229 | HPR067 | 2019-03-01 | Subcontract | 139002762 | 138812992 | 136025799
MCR010230 | HPR067 | 2019-03-01 | Overhead | 28128567 | 28090165 | 26177573
MCR010231 | HPR067 | 2019-04-01 | Labor | 47008933 | 27874704 | 34734530
MCR010232 | HPR067 | 2019-04-01 | Material | 169770163 | 100667953 | 109716465
MCR010233 | HPR067 | 2019-04-01 | Equipment | 45945947 | 27244389 | 27902507
MCR010234 | HPR067 | 2019-04-01 | Subcontract | 158080635 | 93736459 | 86261488
MCR010235 | HPR067 | 2019-04-01 | Overhead | 31989161 | 18968488 | 23052641
MCR010236 | HPR067 | 2019-05-01 | Labor | 51471141 | 39172775 | 41076656
MCR010237 | HPR067 | 2019-05-01 | Material | 185885179 | 141470310 | 139134680
MCR010238 | HPR067 | 2019-05-01 | Equipment | 50307253 | 38286983 | 45812007
MCR010239 | HPR067 | 2019-05-01 | Subcontract | 173086051 | 131729369 | 142064692
MCR010240 | HPR067 | 2019-05-01 | Overhead | 35025653 | 26656725 | 22056105
MCR010241 | HPR067 | 2019-06-01 | Labor | 54758460 | 78194787 | 73961736
MCR010242 | HPR067 | 2019-06-01 | Material | 197757153 | 282396153 | 280269006
MCR010243 | HPR067 | 2019-06-01 | Equipment | 53520239 | 76426614 | 77970345
MCR010244 | HPR067 | 2019-06-01 | Subcontract | 184140580 | 262951759 | 233294046
MCR010245 | HPR067 | 2019-06-01 | Overhead | 37262645 | 53210857 | 25280841
MCR010246 | HPR067 | 2019-07-01 | Labor | 56909306 | 34985410 | 42697934
MCR010247 | HPR067 | 2019-07-01 | Material | 205524812 | 126347874 | 133566110
MCR010248 | HPR067 | 2019-07-01 | Equipment | 55622448 | 34194305 | 37318508
MCR010249 | HPR067 | 2019-07-01 | Subcontract | 191373396 | 117648188 | 123098900
MCR010250 | HPR067 | 2019-07-01 | Overhead | 38726276 | 23807260 | 23216081
MCR010251 | HPR067 | 2019-08-01 | Labor | 57964690 | 29144188 | 33013019
MCR010252 | HPR067 | 2019-08-01 | Material | 209336276 | 105252625 | 91332575
MCR010253 | HPR067 | 2019-08-01 | Equipment | 56653968 | 28485168 | 23033172
MCR010254 | HPR067 | 2019-08-01 | Subcontract | 194922421 | 98005453 | 100222463
MCR010255 | HPR067 | 2019-08-01 | Overhead | 39444456 | 19832361 | 26840152
MCR010256 | HPR067 | 2019-09-01 | Labor | 57968648 | 74473770 | 73936657
MCR010257 | HPR067 | 2019-09-01 | Material | 209350570 | 268957903 | 305993965
MCR010258 | HPR067 | 2019-09-01 | Equipment | 56657837 | 72789737 | 76222553
MCR010259 | HPR067 | 2019-09-01 | Subcontract | 194935731 | 250438800 | 230558508
MCR010260 | HPR067 | 2019-09-01 | Overhead | 39447150 | 50678738 | 24017689
MCR010261 | HPR067 | 2019-10-01 | Labor | 56968766 | 39254814 | 45877788
MCR010262 | HPR067 | 2019-10-01 | Material | 205739549 | 141766592 | 131024290
MCR010263 | HPR067 | 2019-10-01 | Equipment | 55680564 | 38367168 | 45314807
MCR010264 | HPR067 | 2019-10-01 | Subcontract | 191573347 | 132005250 | 144187384
MCR010265 | HPR067 | 2019-10-01 | Overhead | 38766738 | 26712552 | 24457109
MCR010266 | HPR067 | 2019-11-01 | Labor | 55016863 | 28542032 | 28636451
MCR010267 | HPR067 | 2019-11-01 | Material | 198690362 | 103077970 | 105845179
MCR010268 | HPR067 | 2019-11-01 | Equipment | 53772799 | 27896627 | 21639955
MCR010269 | HPR067 | 2019-11-01 | Subcontract | 185009532 | 95980534 | 86510278
MCR010270 | HPR067 | 2019-11-01 | Overhead | 37438486 | 19422599 | 25590908
MCR010271 | HPR067 | 2019-12-01 | Labor | 52169899 | 74282542 | 82012120
MCR010272 | HPR067 | 2019-12-01 | Material | 188408706 | 268267294 | 280802878
MCR010273 | HPR067 | 2019-12-01 | Equipment | 50990211 | 72602833 | 76990978
MCR010274 | HPR067 | 2019-12-01 | Subcontract | 175435820 | 249795743 | 215503700
MCR010275 | HPR067 | 2019-12-01 | Overhead | 35501152 | 50548609 | 24972178
MCR010276 | HPR067 | 2020-01-01 | Labor | 48491181 | 71264187 | 77789859
MCR010277 | HPR067 | 2020-01-01 | Material | 175123220 | 257366672 | 240000825
MCR010278 | HPR067 | 2020-01-01 | Equipment | 47394678 | 69652731 | 72017600
MCR010279 | HPR067 | 2020-01-01 | Subcontract | 163065106 | 239645683 | 272495314
MCR010280 | HPR067 | 2020-01-01 | Overhead | 32997817 | 48494645 | 26364722
MCR010281 | HPR067 | 2020-02-01 | Labor | 44052070 | 40983517 | 41967569
MCR010282 | HPR067 | 2020-02-01 | Material | 159091616 | 148009706 | 155550271
MCR010283 | HPR067 | 2020-02-01 | Equipment | 43055946 | 40056780 | 46012251
MCR010284 | HPR067 | 2020-02-01 | Subcontract | 148137358 | 137818494 | 122146041
MCR010285 | HPR067 | 2020-02-01 | Overhead | 29977042 | 27888919 | 27637445
MCR010286 | HPR067 | 2020-03-01 | Labor | 38934441 | 62702173 | 68196111
MCR010287 | HPR067 | 2020-03-01 | Material | 140609582 | 226445432 | 236212115
MCR010288 | HPR067 | 2020-03-01 | Equipment | 38054039 | 61284325 | 58094192
MCR010289 | HPR067 | 2020-03-01 | Subcontract | 130927906 | 210853526 | 240262348
MCR010290 | HPR067 | 2020-03-01 | Overhead | 26494541 | 42668271 | 23548990
MCR010291 | HPR067 | 2020-04-01 | Labor | 33234443 | 26928136 | 31038515
MCR010292 | HPR067 | 2020-04-01 | Material | 120024354 | 97249475 | 100688555
MCR010293 | HPR067 | 2020-04-01 | Equipment | 32482932 | 26319226 | 25105513
MCR010294 | HPR067 | 2020-04-01 | Subcontract | 111760075 | 90553360 | 72443333
MCR010295 | HPR067 | 2020-04-01 | Overhead | 22615743 | 18324357 | 23716753
MCR010296 | HPR067 | 2020-05-01 | Labor | 27068610 | 38322469 | 46886527
MCR010297 | HPR067 | 2020-05-01 | Material | 97756790 | 138399478 | 139159769
MCR010298 | HPR067 | 2020-05-01 | Equipment | 26456523 | 37455905 | 38977772
MCR010299 | HPR067 | 2020-05-01 | Subcontract | 91025744 | 128869979 | 109338292
MCR010300 | HPR067 | 2020-05-01 | Overhead | 18419949 | 26078099 | 24540082
MCR010301 | HPR067 | 2020-06-01 | Labor | 20584724 | 21382542 | 20412007
MCR010302 | HPR067 | 2020-06-01 | Material | 74340594 | 77221870 | 89082314
MCR010303 | HPR067 | 2020-06-01 | Equipment | 20119254 | 20899031 | 19995559
MCR010304 | HPR067 | 2020-06-01 | Subcontract | 69221871 | 71904756 | 75918201
MCR010305 | HPR067 | 2020-06-01 | Overhead | 14007722 | 14550630 | 23348721
MCR010306 | HPR067 | 2020-07-01 | Labor | 13983784 | 12337502 | 14047481
MCR010307 | HPR067 | 2020-07-01 | Material | 50501663 | 44556208 | 41728296
MCR010308 | HPR067 | 2020-07-01 | Equipment | 13667577 | 12058522 | 12080470
MCR010309 | HPR067 | 2020-07-01 | Subcontract | 47024370 | 41488289 | 38498228
MCR010310 | HPR067 | 2020-07-01 | Overhead | 9515841 | 8395561 | 24697035
MCR010311 | HPR067 | 2020-08-01 | Labor | 7575137 | 17338890 | 17186311
MCR010312 | HPR067 | 2020-08-01 | Material | 27357189 | 62618444 | 66602527
MCR010313 | HPR067 | 2020-08-01 | Equipment | 7403845 | 16946816 | 18314130
MCR010314 | HPR067 | 2020-08-01 | Subcontract | 25473509 | 58306849 | 57966119
MCR010315 | HPR067 | 2020-08-01 | Overhead | 5154813 | 11798961 | 26960732
MCR010316 | HPR067 | 2020-09-01 | Labor | 2008955 | 8750215 | 11003928
MCR010317 | HPR067 | 2020-09-01 | Material | 7255231 | 31600918 | 27519818
MCR010318 | HPR067 | 2020-09-01 | Equipment | 1963528 | 8552351 | 8383018
MCR010319 | HPR067 | 2020-09-01 | Subcontract | 6755672 | 29425036 | 29670202
MCR010320 | HPR067 | 2020-09-01 | Overhead | 1367076 | 5954443 | 26162873
MCR010321 | HPR067 | 2020-10-01 | Labor | 0 | 6252921 | 6593422
MCR010322 | HPR067 | 2020-10-01 | Material | 0 | 22582078 | 24533318
MCR010323 | HPR067 | 2020-10-01 | Equipment | 0 | 6111527 | 6775709
MCR010324 | HPR067 | 2020-10-01 | Subcontract | 0 | 21027188 | 19938507
MCR010325 | HPR067 | 2020-10-01 | Overhead | 0 | 4255057 | 24989760
MCR010326 | HPR067 | 2020-11-01 | Labor | 0 | 1642133 | 1919593
MCR010327 | HPR067 | 2020-11-01 | Material | 0 | 5930474 | 6241882
MCR010328 | HPR067 | 2020-11-01 | Equipment | 0 | 1605001 | 1009754
MCR010329 | HPR067 | 2020-11-01 | Subcontract | 0 | 5522131 | 4733869
MCR010330 | HPR067 | 2020-11-01 | Overhead | 0 | 1117457 | 24353842
MCR010331 | HPR068 | 2022-04-01 | Labor | 10680820 | 7472366 | 8237970
MCR010332 | HPR068 | 2022-04-01 | Material | 31376846 | 21951431 | 20363243
MCR010333 | HPR068 | 2022-04-01 | Equipment | 11577146 | 8099441 | 7451762
MCR010334 | HPR068 | 2022-04-01 | Subcontract | 23103101 | 16163069 | 18492941
MCR010335 | HPR068 | 2022-04-01 | Overhead | 10419208 | 7289341 | 40570609
MCR010336 | HPR068 | 2022-05-01 | Labor | 29484577 | 18755241 | 22355053
MCR010337 | HPR068 | 2022-05-01 | Material | 86616296 | 55096924 | 53692613
MCR010338 | HPR068 | 2022-05-01 | Equipment | 31958899 | 20329166 | 20637689
MCR010339 | HPR068 | 2022-05-01 | Subcontract | 63776488 | 40568444 | 44893610
MCR010340 | HPR068 | 2022-05-01 | Overhead | 28762394 | 18295858 | 48269390
MCR010341 | HPR068 | 2022-06-01 | Labor | 44547219 | 25622302 | 27575500
MCR010342 | HPR068 | 2022-06-01 | Material | 130865541 | 75270162 | 84080882
MCR010343 | HPR068 | 2022-06-01 | Equipment | 48285586 | 27772505 | 26810415
MCR010344 | HPR068 | 2022-06-01 | Subcontract | 96357672 | 55422211 | 55645595
MCR010345 | HPR068 | 2022-06-01 | Overhead | 43456098 | 24994720 | 44355446
MCR010346 | HPR068 | 2022-07-01 | Labor | 56003952 | 28020200 | 32945053
MCR010347 | HPR068 | 2022-07-01 | Material | 164521773 | 82314424 | 88523996
MCR010348 | HPR068 | 2022-07-01 | Equipment | 60703759 | 30371633 | 32216623
MCR010349 | HPR068 | 2022-07-01 | Subcontract | 121139109 | 60608974 | 57333683
MCR010350 | HPR068 | 2022-07-01 | Overhead | 54632215 | 27333885 | 40079045
MCR010351 | HPR068 | 2022-08-01 | Labor | 64000932 | 19087959 | 24287889
MCR010352 | HPR068 | 2022-08-01 | Material | 188014353 | 56074343 | 59230341
MCR010353 | HPR068 | 2022-08-01 | Equipment | 69371839 | 20689805 | 20455298
MCR010354 | HPR068 | 2022-08-01 | Subcontract | 138436942 | 41288127 | 47933389
MCR010355 | HPR068 | 2022-08-01 | Overhead | 62433320 | 18620426 | 42736043
MCR010356 | HPR068 | 2022-09-01 | Labor | 68697475 | 51150152 | 64928293
MCR010357 | HPR068 | 2022-09-01 | Material | 201811300 | 150262854 | 163065086
MCR010358 | HPR068 | 2022-09-01 | Equipment | 74462512 | 55442632 | 58763370
MCR010359 | HPR068 | 2022-09-01 | Subcontract | 148595779 | 110640118 | 108705656
MCR010360 | HPR068 | 2022-09-01 | Overhead | 67014828 | 49897302 | 41024501
MCR010361 | HPR068 | 2022-10-01 | Labor | 70269016 | 48563644 | 56328533
MCR010362 | HPR068 | 2022-10-01 | Material | 206427988 | 142664517 | 129509602
MCR010363 | HPR068 | 2022-10-01 | Equipment | 76165936 | 52639066 | 57019969
MCR010364 | HPR068 | 2022-10-01 | Subcontract | 151995095 | 105045382 | 115942163
MCR010365 | HPR068 | 2022-10-01 | Overhead | 68547876 | 47374146 | 43409700
MCR010366 | HPR068 | 2022-11-01 | Labor | 68911205 | 58622505 | 69527510
MCR010367 | HPR068 | 2022-11-01 | Material | 202439171 | 172214249 | 197873827
MCR010368 | HPR068 | 2022-11-01 | Equipment | 74694178 | 63542060 | 66361986
MCR010369 | HPR068 | 2022-11-01 | Subcontract | 149058087 | 126803160 | 124822769
MCR010370 | HPR068 | 2022-11-01 | Overhead | 67223323 | 57186630 | 43693259
MCR010371 | HPR068 | 2022-12-01 | Labor | 64845786 | 77214893 | 97373527
MCR010372 | HPR068 | 2022-12-01 | Material | 190496265 | 226832761 | 228182825
MCR010373 | HPR068 | 2022-12-01 | Equipment | 70287593 | 83694705 | 83169511
MCR010374 | HPR068 | 2022-12-01 | Subcontract | 140264400 | 167019344 | 195205735
MCR010375 | HPR068 | 2022-12-01 | Overhead | 63257480 | 75323624 | 43899701
MCR010376 | HPR068 | 2023-01-01 | Labor | 58329476 | 70088912 | 71981680
MCR010377 | HPR068 | 2023-01-01 | Material | 171353421 | 205898900 | 197305783
MCR010378 | HPR068 | 2023-01-01 | Equipment | 63224439 | 75970718 | 78197182
MCR010379 | HPR068 | 2023-01-01 | Subcontract | 126169323 | 151605522 | 168619780
MCR010380 | HPR068 | 2023-01-01 | Overhead | 56900778 | 68372184 | 42461389
MCR010381 | HPR068 | 2023-02-01 | Labor | 49668236 | 66305714 | 97543848
MCR010382 | HPR068 | 2023-02-01 | Material | 145909457 | 194785070 | 185604399
MCR010383 | HPR068 | 2023-02-01 | Equipment | 53836355 | 71870037 | 63980982
MCR010384 | HPR068 | 2023-02-01 | Subcontract | 107434666 | 143422292 | 118567227
MCR010385 | HPR068 | 2023-02-01 | Overhead | 48451683 | 64681650 | 44244313
MCR010386 | HPR068 | 2023-03-01 | Labor | 39242319 | 24253359 | 21909447
MCR010387 | HPR068 | 2023-03-01 | Material | 115281433 | 71248643 | 75077704
MCR010388 | HPR068 | 2023-03-01 | Equipment | 42535503 | 26288681 | 30436597
MCR010389 | HPR068 | 2023-03-01 | Subcontract | 84882930 | 52461124 | 71574628
MCR010390 | HPR068 | 2023-03-01 | Overhead | 38281134 | 23659307 | 44228363
MCR010391 | HPR068 | 2023-04-01 | Labor | 27556232 | 32204389 | 38239787
MCR010392 | HPR068 | 2023-04-01 | Material | 80951432 | 94606238 | 85055190
MCR010393 | HPR068 | 2023-04-01 | Equipment | 29868729 | 34906956 | 40217853
MCR010394 | HPR068 | 2023-04-01 | Subcontract | 59605389 | 69659566 | 61906794
MCR010395 | HPR068 | 2023-04-01 | Overhead | 26881281 | 31415588 | 43789928
MCR010396 | HPR068 | 2023-05-01 | Labor | 15362149 | 68592402 | 119666121
MCR010397 | HPR068 | 2023-05-01 | Material | 45129101 | 201502629 | 255483580
MCR010398 | HPR068 | 2023-05-01 | Equipment | 16651328 | 74348622 | 77102096
MCR010399 | HPR068 | 2023-05-01 | Subcontract | 33229031 | 148368501 | 163304121
MCR010400 | HPR068 | 2023-05-01 | Overhead | 14985875 | 66912328 | 45116439
MCR010401 | HPR068 | 2023-06-01 | Labor | 4169275 | 28946284 | 67234148
MCR010402 | HPR068 | 2023-06-01 | Material | 12248003 | 85034963 | 105628758
MCR010403 | HPR068 | 2023-06-01 | Equipment | 4519158 | 31375433 | 29369570
MCR010404 | HPR068 | 2023-06-01 | Subcontract | 9018333 | 62612137 | 66043466
MCR010405 | HPR068 | 2023-06-01 | Overhead | 4067155 | 28237286 | 39821895
MCR010406 | HPR068 | 2023-07-01 | Labor | 0 | 27692376 | 39279628
MCR010407 | HPR068 | 2023-07-01 | Material | 0 | 81351381 | 81720985
MCR010408 | HPR068 | 2023-07-01 | Equipment | 0 | 30016298 | 30373800
MCR010409 | HPR068 | 2023-07-01 | Subcontract | 0 | 59899876 | 60789772
MCR010410 | HPR068 | 2023-07-01 | Overhead | 0 | 27014091 | 46848669
MCR010411 | HPR068 | 2023-08-01 | Labor | 0 | 9514842 | 7817606
MCR010412 | HPR068 | 2023-08-01 | Material | 0 | 27951574 | 24575483
MCR010413 | HPR068 | 2023-08-01 | Equipment | 0 | 10313320 | 11559424
MCR010414 | HPR068 | 2023-08-01 | Subcontract | 0 | 20581038 | 21203824
MCR010415 | HPR068 | 2023-08-01 | Overhead | 0 | 9281789 | 46864812
MCR010416 | HPR068 | 2023-09-01 | Labor | 0 | 6980377 | 10581357
MCR010417 | HPR068 | 2023-09-01 | Material | 0 | 20506125 | 19163660
MCR010418 | HPR068 | 2023-09-01 | Equipment | 0 | 7566165 | 7834478
MCR010419 | HPR068 | 2023-09-01 | Subcontract | 0 | 15098875 | 14485628
MCR010420 | HPR068 | 2023-09-01 | Overhead | 0 | 6809403 | 43220266
MCR010421 | HPR068 | 2023-10-01 | Labor | 0 | 2680750 | 1427553
MCR010422 | HPR068 | 2023-10-01 | Material | 0 | 7875191 | 9213406
MCR010423 | HPR068 | 2023-10-01 | Equipment | 0 | 2905717 | 3123595
MCR010424 | HPR068 | 2023-10-01 | Subcontract | 0 | 5798586 | 5950609
MCR010425 | HPR068 | 2023-10-01 | Overhead | 0 | 2615089 | 37614415
MCR010426 | HPR069 | 2017-09-01 | Labor | 2422472 | 1939507 | 2084304
MCR010427 | HPR069 | 2017-09-01 | Material | 4086501 | 3271782 | 3276854
MCR010428 | HPR069 | 2017-09-01 | Equipment | 898404 | 719291 | 726285
MCR010429 | HPR069 | 2017-09-01 | Subcontract | 3816896 | 3055927 | 3075632
MCR010430 | HPR069 | 2017-09-01 | Overhead | 1015032 | 812667 | 7959643
MCR010431 | HPR069 | 2017-10-01 | Labor | 6972475 | 4410107 | 4711736
MCR010432 | HPR069 | 2017-10-01 | Material | 11761964 | 7439470 | 7304243
MCR010433 | HPR069 | 2017-10-01 | Equipment | 2585830 | 1635544 | 1628395
MCR010434 | HPR069 | 2017-10-01 | Subcontract | 10985974 | 6948655 | 6840905
MCR010435 | HPR069 | 2017-10-01 | Overhead | 2921515 | 1847865 | 7563447
MCR010436 | HPR069 | 2017-11-01 | Labor | 11085489 | 11255711 | 11199680
MCR010437 | HPR069 | 2017-11-01 | Material | 18700265 | 18987415 | 16184563
MCR010438 | HPR069 | 2017-11-01 | Equipment | 4111193 | 4174322 | 4676734
MCR010439 | HPR069 | 2017-11-01 | Subcontract | 17466523 | 17734729 | 18459288
MCR010440 | HPR069 | 2017-11-01 | Overhead | 4644896 | 4716220 | 8329108
MCR010441 | HPR069 | 2017-12-01 | Labor | 14768948 | 18770738 | 21477480
MCR010442 | HPR069 | 2017-12-01 | Material | 24913943 | 31664617 | 36797319
MCR010443 | HPR069 | 2017-12-01 | Equipment | 5477250 | 6961364 | 7878724
MCR010444 | HPR069 | 2017-12-01 | Subcontract | 23270257 | 29575558 | 27538914
MCR010445 | HPR069 | 2017-12-01 | Overhead | 6188291 | 7865068 | 8853220
MCR010446 | HPR069 | 2018-01-01 | Labor | 18030557 | 27071068 | 22848801
MCR010447 | HPR069 | 2018-01-01 | Material | 30415995 | 45666558 | 51075580
MCR010448 | HPR069 | 2018-01-01 | Equipment | 6686859 | 10039646 | 9734591
MCR010449 | HPR069 | 2018-01-01 | Subcontract | 28409314 | 42653728 | 42559343
MCR010450 | HPR069 | 2018-01-01 | Overhead | 7554927 | 11342963 | 8105546
MCR010451 | HPR069 | 2018-02-01 | Labor | 20878314 | 15511479 | 19477330
MCR010452 | HPR069 | 2018-02-01 | Material | 35219917 | 26166528 | 20266974
MCR010453 | HPR069 | 2018-02-01 | Equipment | 7742985 | 5752627 | 5869844
MCR010454 | HPR069 | 2018-02-01 | Subcontract | 32896299 | 24440204 | 25020159
MCR010455 | HPR069 | 2018-02-01 | Overhead | 8748157 | 6499416 | 7487343
MCR010456 | HPR069 | 2018-03-01 | Labor | 23320543 | 22198199 | 25809981
MCR010457 | HPR069 | 2018-03-01 | Material | 39339746 | 37446448 | 40452943
MCR010458 | HPR069 | 2018-03-01 | Equipment | 8648717 | 8232481 | 7268779
MCR010459 | HPR069 | 2018-03-01 | Subcontract | 36744325 | 34975936 | 34051068
MCR010460 | HPR069 | 2018-03-01 | Overhead | 9771468 | 9301198 | 7542789
MCR010461 | HPR069 | 2018-04-01 | Labor | 25365917 | 19382454 | 20315972
MCR010462 | HPR069 | 2018-04-01 | Material | 42790115 | 32696529 | 32637225
MCR010463 | HPR069 | 2018-04-01 | Equipment | 9407269 | 7188227 | 8006667
MCR010464 | HPR069 | 2018-04-01 | Subcontract | 39967057 | 30539390 | 28883836
MCR010465 | HPR069 | 2018-04-01 | Overhead | 10628493 | 8121381 | 8508471
MCR010466 | HPR069 | 2018-05-01 | Labor | 27023497 | 31857480 | 32747085
MCR010467 | HPR069 | 2018-05-01 | Material | 45586311 | 53740824 | 52080135
MCR010468 | HPR069 | 2018-05-01 | Equipment | 10022004 | 11814747 | 10345014
MCR010469 | HPR069 | 2018-05-01 | Subcontract | 42578775 | 50195298 | 52644939
MCR010470 | HPR069 | 2018-05-01 | Overhead | 11323031 | 13348503 | 7338580
MCR010471 | HPR069 | 2018-06-01 | Labor | 28302775 | 16937856 | 17325175
MCR010472 | HPR069 | 2018-06-01 | Material | 47744342 | 28572703 | 30798891
MCR010473 | HPR069 | 2018-06-01 | Equipment | 10496440 | 6281617 | 6833450
MCR010474 | HPR069 | 2018-06-01 | Subcontract | 44594431 | 26687633 | 25103855
MCR010475 | HPR069 | 2018-06-01 | Overhead | 11859057 | 7097078 | 7977934
MCR010476 | HPR069 | 2018-07-01 | Labor | 29213716 | 17773443 | 18797864
MCR010477 | HPR069 | 2018-07-01 | Material | 49281021 | 29982267 | 28752020
MCR010478 | HPR069 | 2018-07-01 | Equipment | 10834274 | 6591505 | 6612806
MCR010479 | HPR069 | 2018-07-01 | Subcontract | 46029728 | 28004201 | 27428487
MCR010480 | HPR069 | 2018-07-01 | Overhead | 12240747 | 7447195 | 7986223
MCR010481 | HPR069 | 2018-08-01 | Labor | 29766818 | 20552549 | 21884536
MCR010482 | HPR069 | 2018-08-01 | Material | 50214057 | 34670379 | 40565612
MCR010483 | HPR069 | 2018-08-01 | Equipment | 11039399 | 7622171 | 7916499
MCR010484 | HPR069 | 2018-08-01 | Subcontract | 46901208 | 32383017 | 28799758
MCR010485 | HPR069 | 2018-08-01 | Overhead | 12472501 | 8611659 | 7895495
MCR010486 | HPR069 | 2018-09-01 | Labor | 29973178 | 25849846 | 29466990
MCR010487 | HPR069 | 2018-09-01 | Material | 50562169 | 43606462 | 38911806
MCR010488 | HPR069 | 2018-09-01 | Equipment | 11115930 | 9586740 | 9742110
MCR010489 | HPR069 | 2018-09-01 | Subcontract | 47226353 | 40729546 | 39467343
MCR010490 | HPR069 | 2018-09-01 | Overhead | 12558967 | 10831263 | 8545343
MCR010491 | HPR069 | 2018-10-01 | Labor | 29844572 | 23351935 | 24510611
MCR010492 | HPR069 | 2018-10-01 | Material | 50345222 | 39392702 | 51182647
MCR010493 | HPR069 | 2018-10-01 | Equipment | 11068235 | 8660359 | 9437269
MCR010494 | HPR069 | 2018-10-01 | Subcontract | 47023719 | 36793787 | 36372586
MCR010495 | HPR069 | 2018-10-01 | Overhead | 12505081 | 9784621 | 8160019
MCR010496 | HPR069 | 2018-11-01 | Labor | 29393551 | 20600938 | 21782278
MCR010497 | HPR069 | 2018-11-01 | Material | 49584387 | 34752006 | 30573728
MCR010498 | HPR069 | 2018-11-01 | Equipment | 10900968 | 7640117 | 6625428
MCR010499 | HPR069 | 2018-11-01 | Subcontract | 46313080 | 32459259 | 30838472
MCR010500 | HPR069 | 2018-11-01 | Overhead | 12316100 | 8631934 | 7671264
MCR010501 | HPR069 | 2018-12-01 | Labor | 28633559 | 52956495 | 57363697
MCR010502 | HPR069 | 2018-12-01 | Material | 48302347 | 89333044 | 95948576
MCR010503 | HPR069 | 2018-12-01 | Equipment | 10619116 | 19639582 | 22190688
MCR010504 | HPR069 | 2018-12-01 | Subcontract | 45115622 | 83439338 | 85435026
MCR010505 | HPR069 | 2018-12-01 | Overhead | 11997658 | 22189135 | 8559639
MCR010506 | HPR069 | 2019-01-01 | Labor | 27579087 | 27457965 | 22426373
MCR010507 | HPR069 | 2019-01-01 | Material | 46523542 | 46319221 | 48295012
MCR010508 | HPR069 | 2019-01-01 | Equipment | 10228051 | 10183132 | 9644710
MCR010509 | HPR069 | 2019-01-01 | Subcontract | 43454173 | 43263332 | 41722613
MCR010510 | HPR069 | 2019-01-01 | Overhead | 11555827 | 11505076 | 7798027
MCR010511 | HPR069 | 2019-02-01 | Labor | 26245853 | 27267775 | 31328164
MCR010512 | HPR069 | 2019-02-01 | Material | 44274492 | 45998387 | 47051215
MCR010513 | HPR069 | 2019-02-01 | Equipment | 9733605 | 10112597 | 10969764
MCR010514 | HPR069 | 2019-02-01 | Subcontract | 41353503 | 42963665 | 44173528
MCR010515 | HPR069 | 2019-02-01 | Overhead | 10997193 | 11425385 | 7800221
MCR010516 | HPR069 | 2019-03-01 | Labor | 24651054 | 22013783 | 23227515
MCR010517 | HPR069 | 2019-03-01 | Material | 41584204 | 37135354 | 39190440
MCR010518 | HPR069 | 2019-03-01 | Equipment | 9142153 | 8164088 | 6978899
MCR010519 | HPR069 | 2019-03-01 | Subcontract | 38840706 | 34685367 | 31814525
MCR010520 | HPR069 | 2019-03-01 | Overhead | 10328961 | 9223926 | 7527135
MCR010521 | HPR069 | 2019-04-01 | Labor | 22813683 | 35644441 | 41258185
MCR010522 | HPR069 | 2019-04-01 | Material | 38484717 | 60129100 | 51431271
MCR010523 | HPR069 | 2019-04-01 | Equipment | 8460741 | 13219189 | 12858879
MCR010524 | HPR069 | 2019-04-01 | Subcontract | 35945706 | 56162111 | 55065646
MCR010525 | HPR069 | 2019-04-01 | Overhead | 9559090 | 14935265 | 7897065
MCR010526 | HPR069 | 2019-05-01 | Labor | 20754966 | 13809454 | 10594468
MCR010527 | HPR069 | 2019-05-01 | Material | 35011840 | 23295359 | 27308972
MCR010528 | HPR069 | 2019-05-01 | Equipment | 7697240 | 5121410 | 6056444
MCR010529 | HPR069 | 2019-05-01 | Subcontract | 32701950 | 21758459 | 24817509
MCR010530 | HPR069 | 2019-05-01 | Overhead | 8696473 | 5786256 | 7881263
MCR010531 | HPR069 | 2019-06-01 | Labor | 18498977 | 27174422 | 28347491
MCR010532 | HPR069 | 2019-06-01 | Material | 31206180 | 45840908 | 46421632
MCR010533 | HPR069 | 2019-06-01 | Equipment | 6860578 | 10077976 | 9789345
MCR010534 | HPR069 | 2019-06-01 | Subcontract | 29147367 | 42816575 | 39181642
MCR010535 | HPR069 | 2019-06-01 | Overhead | 7751198 | 11386269 | 7143340
MCR010536 | HPR069 | 2019-07-01 | Labor | 16073527 | 10011928 | 10580024
MCR010537 | HPR069 | 2019-07-01 | Material | 27114655 | 16889260 | 16756951
MCR010538 | HPR069 | 2019-07-01 | Equipment | 5961070 | 3713050 | 3967524
MCR010539 | HPR069 | 2019-07-01 | Subcontract | 25325778 | 15774999 | 16539533
MCR010540 | HPR069 | 2019-07-01 | Overhead | 6734918 | 4195067 | 7968518
MCR010541 | HPR069 | 2019-08-01 | Labor | 13511535 | 11931342 | 14621891
MCR010542 | HPR069 | 2019-08-01 | Material | 22792795 | 20127145 | 21725582
MCR010543 | HPR069 | 2019-08-01 | Equipment | 5010923 | 4424888 | 4656710
MCR010544 | HPR069 | 2019-08-01 | Subcontract | 21289051 | 18799266 | 17221420
MCR010545 | HPR069 | 2019-08-01 | Overhead | 5661426 | 4999314 | 7175435
MCR010546 | HPR069 | 2019-09-01 | Labor | 10853264 | 18281072 | 17526979
MCR010547 | HPR069 | 2019-09-01 | Material | 18308521 | 30838594 | 31898126
MCR010548 | HPR069 | 2019-09-01 | Equipment | 4025069 | 6779766 | 7237922
MCR010549 | HPR069 | 2019-09-01 | Subcontract | 17100625 | 28804032 | 29945423
MCR010550 | HPR069 | 2019-09-01 | Overhead | 4547592 | 7659895 | 8760218
MCR010551 | HPR069 | 2019-10-01 | Labor | 8150315 | 8485075 | 10935893
MCR010552 | HPR069 | 2019-10-01 | Material | 13748879 | 14313590 | 13971721
MCR010553 | HPR069 | 2019-10-01 | Equipment | 3022647 | 3146797 | 2694373
MCR010554 | HPR069 | 2019-10-01 | Subcontract | 12841803 | 13369258 | 14125617
MCR010555 | HPR069 | 2019-10-01 | Overhead | 3415038 | 3555305 | 7734419
MCR010556 | HPR069 | 2019-11-01 | Labor | 5473762 | 7015378 | 6295948
MCR010557 | HPR069 | 2019-11-01 | Material | 9233764 | 11834338 | 10683602
MCR010558 | HPR069 | 2019-11-01 | Equipment | 2030013 | 2601741 | 2496715
MCR010559 | HPR069 | 2019-11-01 | Subcontract | 8624571 | 11053573 | 9923202
MCR010560 | HPR069 | 2019-11-01 | Overhead | 2293544 | 2939491 | 7485202
MCR010561 | HPR069 | 2019-12-01 | Labor | 2934692 | 7622877 | 7606489
MCR010562 | HPR069 | 2019-12-01 | Material | 4950573 | 12859136 | 14474336
MCR010563 | HPR069 | 2019-12-01 | Equipment | 1088368 | 2827040 | 2994314
MCR010564 | HPR069 | 2019-12-01 | Subcontract | 4623961 | 12010761 | 12397044
MCR010565 | HPR069 | 2019-12-01 | Overhead | 1229656 | 3194038 | 7887175
MCR010566 | HPR069 | 2020-01-01 | Labor | 771616 | 3680450 | 4906661
MCR010567 | HPR069 | 2020-01-01 | Material | 1301649 | 6208603 | 5424149
MCR010568 | HPR069 | 2020-01-01 | Equipment | 286163 | 1364941 | 1353454
MCR010569 | HPR069 | 2020-01-01 | Subcontract | 1215773 | 5798993 | 5760502
MCR010570 | HPR069 | 2020-01-01 | Overhead | 323312 | 1542134 | 7892826
MCR010571 | HPR069 | 2020-02-01 | Labor | 0 | 1919028 | 2568111
MCR010572 | HPR069 | 2020-02-01 | Material | 0 | 3237235 | 3554655
MCR010573 | HPR069 | 2020-02-01 | Equipment | 0 | 711696 | 696908
MCR010574 | HPR069 | 2020-02-01 | Subcontract | 0 | 3023660 | 2252998
MCR010575 | HPR069 | 2020-02-01 | Overhead | 0 | 804086 | 7523110
MCR010576 | HPR069 | 2020-03-01 | Labor | 0 | 573917 | 525797
MCR010577 | HPR069 | 2020-03-01 | Material | 0 | 968148 | 889507
MCR010578 | HPR069 | 2020-03-01 | Equipment | 0 | 212844 | 219064
MCR010579 | HPR069 | 2020-03-01 | Subcontract | 0 | 904275 | 1338955
MCR010580 | HPR069 | 2020-03-01 | Overhead | 0 | 240475 | 7576015
MCR010581 | HPR070 | 2016-02-01 | Labor | 3177166 | 3927412 | 3707271
MCR010582 | HPR070 | 2016-02-01 | Material | 7085611 | 8758785 | 9605420
MCR010583 | HPR070 | 2016-02-01 | Equipment | 1302870 | 1610525 | 1494175
MCR010584 | HPR070 | 2016-02-01 | Subcontract | 5755756 | 7114902 | 6197978
MCR010585 | HPR070 | 2016-02-01 | Overhead | 1741627 | 2152889 | 9017899
MCR010586 | HPR070 | 2016-03-01 | Labor | 8965924 | 8109203 | 8312924
MCR010587 | HPR070 | 2016-03-01 | Material | 19995508 | 18084876 | 17411617
MCR010588 | HPR070 | 2016-03-01 | Equipment | 3676683 | 3325364 | 3078047
MCR010589 | HPR070 | 2016-03-01 | Subcontract | 16242672 | 14690635 | 14985432
MCR010590 | HPR070 | 2016-03-01 | Overhead | 4914851 | 4445222 | 9587057
MCR010591 | HPR070 | 2016-04-01 | Labor | 13921770 | 14769902 | 15693012
MCR010592 | HPR070 | 2016-04-01 | Material | 31047871 | 32939346 | 34952403
MCR010593 | HPR070 | 2016-04-01 | Equipment | 5708941 | 6056736 | 7143668
MCR010594 | HPR070 | 2016-04-01 | Subcontract | 25220685 | 26757160 | 24692426
MCR010595 | HPR070 | 2016-04-01 | Overhead | 7631497 | 8096417 | 8832243
MCR010596 | HPR070 | 2016-05-01 | Labor | 18066179 | 14443792 | 12994292
MCR010597 | HPR070 | 2016-05-01 | Material | 40290593 | 32212067 | 33207552
MCR010598 | HPR070 | 2016-05-01 | Equipment | 7408450 | 5923008 | 5504890
MCR010599 | HPR070 | 2016-05-01 | Subcontract | 32728696 | 26166379 | 26737533
MCR010600 | HPR070 | 2016-05-01 | Overhead | 9903337 | 7917653 | 9799107
MCR010601 | HPR070 | 2016-06-01 | Labor | 21421836 | 21276364 | 23658552
MCR010602 | HPR070 | 2016-06-01 | Material | 47774271 | 47449842 | 49604797
MCR010603 | HPR070 | 2016-06-01 | Equipment | 8784515 | 8724860 | 8342348
MCR010604 | HPR070 | 2016-06-01 | Subcontract | 38807808 | 38544269 | 38696080
MCR010605 | HPR070 | 2016-06-01 | Overhead | 11742808 | 11663064 | 8654309
MCR010606 | HPR070 | 2016-07-01 | Labor | 24012809 | 13013778 | 11634030
MCR010607 | HPR070 | 2016-07-01 | Material | 53552572 | 29022896 | 32926958
MCR010608 | HPR070 | 2016-07-01 | Equipment | 9847002 | 5336598 | 6085780
MCR010609 | HPR070 | 2016-07-01 | Subcontract | 43501615 | 23575765 | 20303072
MCR010610 | HPR070 | 2016-07-01 | Overhead | 13163101 | 7133762 | 10473840
MCR010611 | HPR070 | 2016-08-01 | Labor | 25864742 | 14619874 | 13833620
MCR010612 | HPR070 | 2016-08-01 | Material | 57682691 | 32604760 | 30637644
MCR010613 | HPR070 | 2016-08-01 | Equipment | 10606430 | 5995214 | 6287477
MCR010614 | HPR070 | 2016-08-01 | Subcontract | 46856577 | 26485371 | 24461370
MCR010615 | HPR070 | 2016-08-01 | Overhead | 14178275 | 8014176 | 8997359
MCR010616 | HPR070 | 2016-09-01 | Labor | 27005112 | 26603068 | 27751045
MCR010617 | HPR070 | 2016-09-01 | Material | 60225906 | 59329283 | 56342842
MCR010618 | HPR070 | 2016-09-01 | Equipment | 11074064 | 10909197 | 10340534
MCR010619 | HPR070 | 2016-09-01 | Subcontract | 48922471 | 48194130 | 48887347
MCR010620 | HPR070 | 2016-09-01 | Overhead | 14803392 | 14583004 | 9168570
MCR010621 | HPR070 | 2016-10-01 | Labor | 27463544 | 19641740 | 20108274
MCR010622 | HPR070 | 2016-10-01 | Material | 61248287 | 43804358 | 46230000
MCR010623 | HPR070 | 2016-10-01 | Equipment | 11262055 | 8054545 | 8180000
MCR010624 | HPR070 | 2016-10-01 | Subcontract | 49752967 | 35582984 | 32704034
MCR010625 | HPR070 | 2016-10-01 | Overhead | 15054691 | 10767012 | 10182685
MCR010626 | HPR070 | 2016-11-01 | Labor | 27272219 | 24048141 | 21223139
MCR010627 | HPR070 | 2016-11-01 | Material | 60821601 | 53631369 | 53105572
MCR010628 | HPR070 | 2016-11-01 | Equipment | 11183598 | 9861491 | 10090636
MCR010629 | HPR070 | 2016-11-01 | Subcontract | 49406363 | 43565623 | 42800795
MCR010630 | HPR070 | 2016-11-01 | Overhead | 14949812 | 13182469 | 9787705
MCR010631 | HPR070 | 2016-12-01 | Labor | 26466407 | 19039677 | 21372580
MCR010632 | HPR070 | 2016-12-01 | Material | 59024504 | 42461657 | 44662965
MCR010633 | HPR070 | 2016-12-01 | Equipment | 10853156 | 7807656 | 9026769
MCR010634 | HPR070 | 2016-12-01 | Subcontract | 47946553 | 34492287 | 35144788
MCR010635 | HPR070 | 2016-12-01 | Overhead | 14508090 | 10436980 | 9884467
MCR010636 | HPR070 | 2017-01-01 | Labor | 25085184 | 21000664 | 24011529
MCR010637 | HPR070 | 2017-01-01 | Material | 55944147 | 46834986 | 45955543
MCR010638 | HPR070 | 2017-01-01 | Equipment | 10286754 | 8611803 | 7754927
MCR010639 | HPR070 | 2017-01-01 | Subcontract | 45444330 | 38044812 | 38487894
MCR010640 | HPR070 | 2017-01-01 | Overhead | 13750945 | 11511934 | 9707697
MCR010641 | HPR070 | 2017-02-01 | Labor | 23172441 | 22445070 | 21970958
MCR010642 | HPR070 | 2017-02-01 | Material | 51678411 | 50056251 | 58287617
MCR010643 | HPR070 | 2017-02-01 | Equipment | 9502390 | 9204115 | 9492872
MCR010644 | HPR070 | 2017-02-01 | Subcontract | 41979203 | 40661497 | 37733417
MCR010645 | HPR070 | 2017-02-01 | Overhead | 12702437 | 12303714 | 10105838
MCR010646 | HPR070 | 2017-03-01 | Labor | 20778327 | 31431793 | 32565685
MCR010647 | HPR070 | 2017-03-01 | Material | 46339136 | 70098145 | 56878267
MCR010648 | HPR070 | 2017-03-01 | Equipment | 8520629 | 12889327 | 13115758
MCR010649 | HPR070 | 2017-03-01 | Subcontract | 37642025 | 56941850 | 53767369
MCR010650 | HPR070 | 2017-03-01 | Overhead | 11390055 | 17229966 | 9429972
MCR010651 | HPR070 | 2017-04-01 | Labor | 17961455 | 20437632 | 19935140
MCR010652 | HPR070 | 2017-04-01 | Material | 40057043 | 45579329 | 50772530
MCR010653 | HPR070 | 2017-04-01 | Equipment | 7365506 | 8380919 | 8854663
MCR010654 | HPR070 | 2017-04-01 | Subcontract | 32538979 | 37024822 | 41856069
MCR010655 | HPR070 | 2017-04-01 | Overhead | 9845931 | 11203296 | 9786346
MCR010656 | HPR070 | 2017-05-01 | Labor | 14792475 | 18702174 | 23711425
MCR010657 | HPR070 | 2017-05-01 | Material | 32989689 | 41708968 | 40135754
MCR010658 | HPR070 | 2017-05-01 | Equipment | 6065993 | 7669255 | 8010885
MCR010659 | HPR070 | 2017-05-01 | Subcontract | 26798054 | 33880865 | 33286398
MCR010660 | HPR070 | 2017-05-01 | Overhead | 8108791 | 10251970 | 8921284
MCR010661 | HPR070 | 2017-06-01 | Labor | 11360394 | 16635218 | 16937389
MCR010662 | HPR070 | 2017-06-01 | Material | 25335575 | 37099312 | 35105601
MCR010663 | HPR070 | 2017-06-01 | Equipment | 4658590 | 6821652 | 6396346
MCR010664 | HPR070 | 2017-06-01 | Subcontract | 20580495 | 30136367 | 29733168
MCR010665 | HPR070 | 2017-06-01 | Overhead | 6227427 | 9118927 | 9526741
MCR010666 | HPR070 | 2017-07-01 | Labor | 7785312 | 11591649 | 12405939
MCR010667 | HPR070 | 2017-07-01 | Material | 17362546 | 25851313 | 29495579
MCR010668 | HPR070 | 2017-07-01 | Equipment | 3192546 | 4753421 | 5264313
MCR010669 | HPR070 | 2017-07-01 | Subcontract | 14103875 | 20999437 | 17272106
MCR010670 | HPR070 | 2017-07-01 | Overhead | 4267675 | 6354194 | 9116327
MCR010671 | HPR070 | 2017-08-01 | Labor | 4250235 | 8508179 | 10206289
MCR010672 | HPR070 | 2017-08-01 | Material | 9478734 | 18974660 | 20125928
MCR010673 | HPR070 | 2017-08-01 | Equipment | 1742906 | 3488974 | 3596914
MCR010674 | HPR070 | 2017-08-01 | Subcontract | 7699728 | 15413421 | 17813072
MCR010675 | HPR070 | 2017-08-01 | Overhead | 2329851 | 4663929 | 10025054
MCR010676 | HPR070 | 2017-09-01 | Labor | 1134374 | 9518634 | 10293414
MCR010677 | HPR070 | 2017-09-01 | Material | 2529843 | 21228143 | 21650403
MCR010678 | HPR070 | 2017-09-01 | Equipment | 465176 | 3903334 | 3534276
MCR010679 | HPR070 | 2017-09-01 | Subcontract | 2055032 | 17243962 | 14209627
MCR010680 | HPR070 | 2017-09-01 | Overhead | 621830 | 5217830 | 9523865
MCR010681 | HPR070 | 2017-10-01 | Labor | 0 | 6215384 | 6094524
MCR010682 | HPR070 | 2017-10-01 | Material | 0 | 13861344 | 15337390
MCR010683 | HPR070 | 2017-10-01 | Equipment | 0 | 2548761 | 2707980
MCR010684 | HPR070 | 2017-10-01 | Subcontract | 0 | 11259793 | 11135182
MCR010685 | HPR070 | 2017-10-01 | Overhead | 0 | 3407087 | 9482097
MCR010686 | HPR070 | 2017-11-01 | Labor | 0 | 3460819 | 3871024
MCR010687 | HPR070 | 2017-11-01 | Material | 0 | 7718204 | 6626685
MCR010688 | HPR070 | 2017-11-01 | Equipment | 0 | 1419188 | 1664244
MCR010689 | HPR070 | 2017-11-01 | Subcontract | 0 | 6269621 | 7077541
MCR010690 | HPR070 | 2017-11-01 | Overhead | 0 | 1897117 | 9436350
MCR010691 | HPR070 | 2017-12-01 | Labor | 0 | 517738 | 476824
MCR010692 | HPR070 | 2017-12-01 | Material | 0 | 1154642 | 1249087
MCR010693 | HPR070 | 2017-12-01 | Equipment | 0 | 212310 | 146066
MCR010694 | HPR070 | 2017-12-01 | Subcontract | 0 | 937934 | 1024094
MCR010695 | HPR070 | 2017-12-01 | Overhead | 0 | 283808 | 9887537
MCR010696 | HPR071 | 2019-03-01 | Labor | 9413658 | 11321699 | 11045855
MCR010697 | HPR071 | 2019-03-01 | Material | 26367053 | 31711352 | 33372917
MCR010698 | HPR071 | 2019-03-01 | Equipment | 8667899 | 10424782 | 10884982
MCR010699 | HPR071 | 2019-03-01 | Subcontract | 25480189 | 30644731 | 30557610
MCR010700 | HPR071 | 2019-03-01 | Overhead | 6528170 | 7851355 | 34567963
MCR010701 | HPR071 | 2019-04-01 | Labor | 26565230 | 18127855 | 18244634
MCR010702 | HPR071 | 2019-04-01 | Material | 74407504 | 50774958 | 44179731
MCR010703 | HPR071 | 2019-04-01 | Equipment | 24460704 | 16691747 | 15706410
MCR010704 | HPR071 | 2019-04-01 | Subcontract | 71904784 | 49067127 | 50957536
MCR010705 | HPR071 | 2019-04-01 | Overhead | 18422418 | 12571279 | 37597508
MCR010706 | HPR071 | 2019-05-01 | Labor | 41248956 | 45365813 | 46170858
MCR010707 | HPR071 | 2019-05-01 | Material | 115535681 | 127066733 | 125444510
MCR010708 | HPR071 | 2019-05-01 | Equipment | 37981171 | 41771886 | 44548586
MCR010709 | HPR071 | 2019-05-01 | Subcontract | 111649602 | 122792804 | 114282038
MCR010710 | HPR071 | 2019-05-01 | Overhead | 28605268 | 31460220 | 37089029
MCR010711 | HPR071 | 2019-06-01 | Labor | 53528467 | 33468237 | 35448814
MCR010712 | HPR071 | 2019-06-01 | Material | 149929801 | 93742384 | 103356514
MCR010713 | HPR071 | 2019-06-01 | Equipment | 49287885 | 30816848 | 30120405
MCR010714 | HPR071 | 2019-06-01 | Subcontract | 144886866 | 90589330 | 102182449
MCR010715 | HPR071 | 2019-06-01 | Overhead | 37120845 | 23209505 | 33822039
MCR010716 | HPR071 | 2019-07-01 | Labor | 63470980 | 30498756 | 33809568
MCR010717 | HPR071 | 2019-07-01 | Material | 177778143 | 85425058 | 76674028
MCR010718 | HPR071 | 2019-07-01 | Equipment | 58442743 | 28082612 | 31367796
MCR010719 | HPR071 | 2019-07-01 | Subcontract | 171798520 | 82551760 | 80501496
MCR010720 | HPR071 | 2019-07-01 | Overhead | 44015765 | 21150234 | 32696723
MCR010721 | HPR071 | 2019-08-01 | Labor | 71147799 | 58785945 | 61643920
MCR010722 | HPR071 | 2019-08-01 | Material | 199280421 | 164655661 | 165575087
MCR010723 | HPR071 | 2019-08-01 | Equipment | 65511396 | 54128861 | 52510491
MCR010724 | HPR071 | 2019-08-01 | Subcontract | 192577562 | 159117417 | 166367889
MCR010725 | HPR071 | 2019-08-01 | Overhead | 49339475 | 40766794 | 36288757
MCR010726 | HPR071 | 2019-09-01 | Labor | 76634909 | 49668346 | 47086019
MCR010727 | HPR071 | 2019-09-01 | Material | 214649465 | 139117850 | 141461715
MCR010728 | HPR071 | 2019-09-01 | Equipment | 70563812 | 45733567 | 42633383
MCR010729 | HPR071 | 2019-09-01 | Subcontract | 207429664 | 134438578 | 149374449
MCR010730 | HPR071 | 2019-09-01 | Overhead | 53144668 | 34443934 | 34844481
MCR010731 | HPR071 | 2019-10-01 | Labor | 80013723 | 81260732 | 90209325
MCR010732 | HPR071 | 2019-10-01 | Material | 224113305 | 227606098 | 235184904
MCR010733 | HPR071 | 2019-10-01 | Equipment | 73674952 | 74823172 | 66971237
MCR010734 | HPR071 | 2019-10-01 | Subcontract | 216575185 | 219950497 | 202514196
MCR010735 | HPR071 | 2019-10-01 | Overhead | 55487803 | 56352577 | 33823987
MCR010736 | HPR071 | 2019-11-01 | Labor | 81372017 | 58192717 | 65749296
MCR010737 | HPR071 | 2019-11-01 | Material | 227917800 | 162994068 | 164995669
MCR010738 | HPR071 | 2019-11-01 | Equipment | 74925641 | 53582629 | 55315978
MCR010739 | HPR071 | 2019-11-01 | Subcontract | 220251714 | 157511712 | 152376172
MCR010740 | HPR071 | 2019-11-01 | Overhead | 56429751 | 40355403 | 35418758
MCR010741 | HPR071 | 2019-12-01 | Labor | 80805139 | 50865980 | 55588423
MCR010742 | HPR071 | 2019-12-01 | Material | 226330011 | 142472348 | 139951471
MCR010743 | HPR071 | 2019-12-01 | Equipment | 74403672 | 46836324 | 51702976
MCR010744 | HPR071 | 2019-12-01 | Subcontract | 218717331 | 137680246 | 141541551
MCR010745 | HPR071 | 2019-12-01 | Overhead | 56036633 | 35274468 | 39756641
MCR010746 | HPR071 | 2020-01-01 | Labor | 78417588 | 105198833 | 100616639
MCR010747 | HPR071 | 2020-01-01 | Material | 219642635 | 294655182 | 311833585
MCR010748 | HPR071 | 2020-01-01 | Equipment | 72205265 | 96864871 | 104163895
MCR010749 | HPR071 | 2020-01-01 | Subcontract | 212254887 | 284744364 | 296287864
MCR010750 | HPR071 | 2020-01-01 | Overhead | 54380918 | 72953137 | 35771624
MCR010751 | HPR071 | 2020-02-01 | Labor | 74325150 | 78084478 | 88440558
MCR010752 | HPR071 | 2020-02-01 | Material | 208179977 | 218709614 | 219727370
MCR010753 | HPR071 | 2020-02-01 | Equipment | 68437034 | 71898544 | 68854382
MCR010754 | HPR071 | 2020-02-01 | Subcontract | 201177779 | 211353248 | 197233267
MCR010755 | HPR071 | 2020-02-01 | Overhead | 51542899 | 54149913 | 39026151
MCR010756 | HPR071 | 2020-03-01 | Labor | 68657864 | 94673925 | 105726745
MCR010757 | HPR071 | 2020-03-01 | Material | 192306272 | 265175589 | 299235083
MCR010758 | HPR071 | 2020-03-01 | Equipment | 63218716 | 87173757 | 84111099
MCR010759 | HPR071 | 2020-03-01 | Subcontract | 185837991 | 256256326 | 276129010
MCR010760 | HPR071 | 2020-03-01 | Overhead | 47612758 | 65654339 | 35623222
MCR010761 | HPR071 | 2020-04-01 | Labor | 61564318 | 77687627 | 74801908
MCR010762 | HPR071 | 2020-04-01 | Material | 172437706 | 217598060 | 185977494
MCR010763 | HPR071 | 2020-04-01 | Equipment | 56687128 | 71533132 | 66290025
MCR010764 | HPR071 | 2020-04-01 | Subcontract | 166637710 | 210279082 | 228893368
MCR010765 | HPR071 | 2020-04-01 | Overhead | 42693536 | 53874705 | 36450437
MCR010766 | HPR071 | 2020-05-01 | Labor | 53218180 | 57572203 | 63951927
MCR010767 | HPR071 | 2020-05-01 | Material | 149060709 | 161256048 | 209488057
MCR010768 | HPR071 | 2020-05-01 | Equipment | 49002180 | 53011273 | 59628993
MCR010769 | HPR071 | 2020-05-01 | Subcontract | 144047006 | 155832151 | 133148169
MCR010770 | HPR071 | 2020-05-01 | Overhead | 36905668 | 39925090 | 36435198
MCR010771 | HPR071 | 2020-06-01 | Labor | 43828777 | 51007738 | 47718614
MCR010772 | HPR071 | 2020-06-01 | Material | 122761593 | 142869402 | 118372964
MCR010773 | HPR071 | 2020-06-01 | Equipment | 40356616 | 46966852 | 45327589
MCR010774 | HPR071 | 2020-06-01 | Subcontract | 118632469 | 138063945 | 131335877
MCR010775 | HPR071 | 2020-06-01 | Overhead | 30394318 | 35372774 | 33744791
MCR010776 | HPR071 | 2020-07-01 | Labor | 33659829 | 20994382 | 25478281
MCR010777 | HPR071 | 2020-07-01 | Material | 94279021 | 58803918 | 56655032
MCR010778 | HPR071 | 2020-07-01 | Equipment | 30993262 | 19331185 | 21812061
MCR010779 | HPR071 | 2020-07-01 | Subcontract | 91107917 | 56826030 | 66318964
MCR010780 | HPR071 | 2020-07-01 | Overhead | 23342370 | 14559154 | 39365366
MCR010781 | HPR071 | 2020-08-01 | Labor | 23067182 | 28408002 | 27133477
MCR010782 | HPR071 | 2020-08-01 | Material | 64609698 | 79568990 | 88140008
MCR010783 | HPR071 | 2020-08-01 | Equipment | 21239776 | 26157490 | 25685097
MCR010784 | HPR071 | 2020-08-01 | Subcontract | 62436531 | 76892663 | 82379708
MCR010785 | HPR071 | 2020-08-01 | Overhead | 15996597 | 19700341 | 34207250
MCR010786 | HPR071 | 2020-09-01 | Labor | 12593066 | 29512260 | 36497411
MCR010787 | HPR071 | 2020-09-01 | Material | 35272369 | 82661948 | 86369242
MCR010788 | HPR071 | 2020-09-01 | Equipment | 11595430 | 27174268 | 27618598
MCR010789 | HPR071 | 2020-09-01 | Subcontract | 34085972 | 79881588 | 83972870
MCR010790 | HPR071 | 2020-09-01 | Overhead | 8733021 | 20466120 | 38323416
MCR010791 | HPR071 | 2020-10-01 | Labor | 3361048 | 28587441 | 21448162
MCR010792 | HPR071 | 2020-10-01 | Material | 9414081 | 80071589 | 83265407
MCR010793 | HPR071 | 2020-10-01 | Equipment | 3094783 | 26322714 | 30091402
MCR010794 | HPR071 | 2020-10-01 | Subcontract | 9097435 | 77378356 | 69623017
MCR010795 | HPR071 | 2020-10-01 | Overhead | 2330815 | 19824778 | 33433603
MCR010796 | HPR071 | 2020-11-01 | Labor | 0 | 12991106 | 17752557
MCR010797 | HPR071 | 2020-11-01 | Material | 0 | 36387255 | 40251264
MCR010798 | HPR071 | 2020-11-01 | Equipment | 0 | 11961937 | 9670873
MCR010799 | HPR071 | 2020-11-01 | Subcontract | 0 | 35163358 | 42305850
MCR010800 | HPR071 | 2020-11-01 | Overhead | 0 | 9009054 | 39385360
MCR010801 | HPR071 | 2020-12-01 | Labor | 0 | 11936430 | 11598859
MCR010802 | HPR071 | 2020-12-01 | Material | 0 | 33433176 | 35546324
MCR010803 | HPR071 | 2020-12-01 | Equipment | 0 | 10990814 | 10692489
MCR010804 | HPR071 | 2020-12-01 | Subcontract | 0 | 32308641 | 31376998
MCR010805 | HPR071 | 2020-12-01 | Overhead | 0 | 8277659 | 37970541
MCR010806 | HPR071 | 2021-01-01 | Labor | 0 | 2683376 | 3015268
MCR010807 | HPR071 | 2021-01-01 | Material | 0 | 7515963 | 5600256
MCR010808 | HPR071 | 2021-01-01 | Equipment | 0 | 2470796 | 3650523
MCR010809 | HPR071 | 2021-01-01 | Subcontract | 0 | 7263162 | 8514605
MCR010810 | HPR071 | 2021-01-01 | Overhead | 0 | 1860864 | 39443209
MCR010811 | HPR072 | 2018-08-01 | Labor | 2086886 | 711674 | 749803
MCR010812 | HPR072 | 2018-08-01 | Material | 4431259 | 1511157 | 1460132
MCR010813 | HPR072 | 2018-08-01 | Equipment | 1018935 | 347479 | 349265
MCR010814 | HPR072 | 2018-08-01 | Subcontract | 5656539 | 1929005 | 2162695
MCR010815 | HPR072 | 2018-08-01 | Overhead | 1103852 | 376438 | 6244576
MCR010816 | HPR072 | 2018-09-01 | Labor | 5889167 | 4513959 | 4548444
MCR010817 | HPR072 | 2018-09-01 | Material | 12504958 | 9584865 | 10233167
MCR010818 | HPR072 | 2018-09-01 | Equipment | 2875421 | 2203968 | 1958576
MCR010819 | HPR072 | 2018-09-01 | Subcontract | 15962683 | 12235160 | 12083093
MCR010820 | HPR072 | 2018-09-01 | Overhead | 3115056 | 2387644 | 6317865
MCR010821 | HPR072 | 2018-10-01 | Labor | 9144358 | 5413207 | 6522252
MCR010822 | HPR072 | 2018-10-01 | Material | 19416977 | 11494314 | 9815969
MCR010823 | HPR072 | 2018-10-01 | Equipment | 4464788 | 2643031 | 3081196
MCR010824 | HPR072 | 2018-10-01 | Subcontract | 24785934 | 14672588 | 12914949
MCR010825 | HPR072 | 2018-10-01 | Overhead | 4836880 | 2863299 | 5583785
MCR010826 | HPR072 | 2018-11-01 | Labor | 11866566 | 7228544 | 6489447
MCR010827 | HPR072 | 2018-11-01 | Material | 25197269 | 15348969 | 15341826
MCR010828 | HPR072 | 2018-11-01 | Equipment | 5793923 | 3529380 | 3368944
MCR010829 | HPR072 | 2018-11-01 | Subcontract | 32164523 | 19593087 | 21645377
MCR010830 | HPR072 | 2018-11-01 | Overhead | 6276784 | 3823516 | 6053875
MCR010831 | HPR072 | 2018-12-01 | Labor | 14070692 | 19005607 | 19711509
MCR010832 | HPR072 | 2018-12-01 | Material | 29877473 | 40356189 | 40990719
MCR010833 | HPR072 | 2018-12-01 | Equipment | 6870101 | 9279603 | 9665727
MCR010834 | HPR072 | 2018-12-01 | Subcontract | 38138844 | 51515012 | 50778781
MCR010835 | HPR072 | 2018-12-01 | Overhead | 7442649 | 10052957 | 6937075
MCR010836 | HPR072 | 2019-01-01 | Labor | 15772544 | 10740992 | 12925763
MCR010837 | HPR072 | 2019-01-01 | Material | 33491156 | 22807243 | 25118848
MCR010838 | HPR072 | 2019-01-01 | Equipment | 7701040 | 5244354 | 5410272
MCR010839 | HPR072 | 2019-01-01 | Subcontract | 42751739 | 29113636 | 30077892
MCR010840 | HPR072 | 2019-01-01 | Overhead | 8342838 | 5681414 | 6030933
MCR010841 | HPR072 | 2019-02-01 | Labor | 16988965 | 13448820 | 13862962
MCR010842 | HPR072 | 2019-02-01 | Material | 36074084 | 28557001 | 25778687
MCR010843 | HPR072 | 2019-02-01 | Equipment | 8294965 | 6566468 | 7130071
MCR010844 | HPR072 | 2019-02-01 | Subcontract | 46048869 | 36453250 | 37231589
MCR010845 | HPR072 | 2019-02-01 | Overhead | 8986260 | 7113712 | 6288905
MCR010846 | HPR072 | 2019-03-01 | Labor | 17738004 | 16527078 | 17040652
MCR010847 | HPR072 | 2019-03-01 | Material | 37664581 | 35093322 | 39942252
MCR010848 | HPR072 | 2019-03-01 | Equipment | 8660688 | 8069446 | 7150226
MCR010849 | HPR072 | 2019-03-01 | Subcontract | 48079152 | 44796919 | 50698922
MCR010850 | HPR072 | 2019-03-01 | Overhead | 9382462 | 8741947 | 6082978
MCR010851 | HPR072 | 2019-04-01 | Labor | 18039120 | 11207969 | 15331166
MCR010852 | HPR072 | 2019-04-01 | Material | 38303966 | 23798815 | 22814647
MCR010853 | HPR072 | 2019-04-01 | Equipment | 8807710 | 5472359 | 6552950
MCR010854 | HPR072 | 2019-04-01 | Subcontract | 48895332 | 30379386 | 28208273
MCR010855 | HPR072 | 2019-04-01 | Overhead | 9541737 | 5928421 | 5674488
MCR010856 | HPR072 | 2019-05-01 | Labor | 17913450 | 13990530 | 14051636
MCR010857 | HPR072 | 2019-05-01 | Material | 38037122 | 29707258 | 31927499
MCR010858 | HPR072 | 2019-05-01 | Equipment | 8746351 | 6830961 | 6299286
MCR010859 | HPR072 | 2019-05-01 | Subcontract | 48554703 | 37921562 | 38187759
MCR010860 | HPR072 | 2019-05-01 | Overhead | 9475264 | 7400248 | 5598278
MCR010861 | HPR072 | 2019-06-01 | Labor | 17384161 | 27740165 | 30026362
MCR010862 | HPR072 | 2019-06-01 | Material | 36913238 | 58903002 | 56972128
MCR010863 | HPR072 | 2019-06-01 | Equipment | 8487922 | 13544304 | 13759168
MCR010864 | HPR072 | 2019-06-01 | Subcontract | 47120056 | 75190174 | 70011051
MCR010865 | HPR072 | 2019-06-01 | Overhead | 9195298 | 14673074 | 5804210
MCR010866 | HPR072 | 2019-07-01 | Labor | 16476921 | 13984754 | 15126101
MCR010867 | HPR072 | 2019-07-01 | Material | 34986819 | 29694993 | 37988071
MCR010868 | HPR072 | 2019-07-01 | Equipment | 8044957 | 6828141 | 8433956
MCR010869 | HPR072 | 2019-07-01 | Subcontract | 44660966 | 37905906 | 38189691
MCR010870 | HPR072 | 2019-07-01 | Overhead | 8715416 | 7397192 | 5667845
MCR010871 | HPR072 | 2019-08-01 | Labor | 15220557 | 8226425 | 9422382
MCR010872 | HPR072 | 2019-08-01 | Material | 32319077 | 17467853 | 16774704
MCR010873 | HPR072 | 2019-08-01 | Equipment | 7431529 | 4016602 | 3504787
MCR010874 | HPR072 | 2019-08-01 | Subcontract | 41255571 | 22297860 | 22549866
MCR010875 | HPR072 | 2019-08-01 | Overhead | 8050867 | 4351342 | 6102011
MCR010876 | HPR072 | 2019-09-01 | Labor | 13648010 | 17950761 | 19669181
MCR010877 | HPR072 | 2019-09-01 | Material | 28979957 | 38116347 | 40406977
MCR010878 | HPR072 | 2019-09-01 | Equipment | 6663724 | 8764568 | 10625861
MCR010879 | HPR072 | 2019-09-01 | Subcontract | 36993157 | 48655835 | 49130634
MCR010880 | HPR072 | 2019-09-01 | Overhead | 7219073 | 9495000 | 6131243
MCR010881 | HPR072 | 2019-10-01 | Labor | 11797780 | 6241328 | 7558339
MCR010882 | HPR072 | 2019-10-01 | Material | 25051209 | 13252731 | 13890506
MCR010883 | HPR072 | 2019-10-01 | Equipment | 5760338 | 3047366 | 1772792
MCR010884 | HPR072 | 2019-10-01 | Subcontract | 31978077 | 16917222 | 14985639
MCR010885 | HPR072 | 2019-10-01 | Overhead | 6240399 | 3301331 | 5355164
MCR010886 | HPR072 | 2019-11-01 | Labor | 9716271 | 7237163 | 8174872
MCR010887 | HPR072 | 2019-11-01 | Material | 20631368 | 15367272 | 16802301
MCR010888 | HPR072 | 2019-11-01 | Equipment | 4744028 | 3533589 | 3706182
MCR010889 | HPR072 | 2019-11-01 | Subcontract | 26336113 | 19616451 | 35617234
MCR010890 | HPR072 | 2019-11-01 | Overhead | 5139391 | 3828075 | 6231679
MCR010891 | HPR072 | 2019-12-01 | Labor | 7461947 | 16053377 | 16336127
MCR010892 | HPR072 | 2019-12-01 | Material | 15844574 | 34087472 | 35232898
MCR010893 | HPR072 | 2019-12-01 | Equipment | 3643341 | 7838159 | 6919686
MCR010894 | HPR072 | 2019-12-01 | Subcontract | 20225731 | 43512942 | 48809468
MCR010895 | HPR072 | 2019-12-01 | Overhead | 3946974 | 8491384 | 6446552
MCR010896 | HPR072 | 2020-01-01 | Labor | 5113695 | 10241376 | 13381335
MCR010897 | HPR072 | 2020-01-01 | Material | 10858334 | 21746368 | 20307791
MCR010898 | HPR072 | 2020-01-01 | Equipment | 2496793 | 5000414 | 5389832
MCR010899 | HPR072 | 2020-01-01 | Subcontract | 13860754 | 27759420 | 41653433
MCR010900 | HPR072 | 2020-01-01 | Overhead | 2704873 | 5417144 | 6187439
MCR010901 | HPR072 | 2020-02-01 | Labor | 2791719 | 6785442 | 6135090
MCR010902 | HPR072 | 2020-02-01 | Material | 5927890 | 14408095 | 17044734
MCR010903 | HPR072 | 2020-02-01 | Equipment | 1363074 | 3313033 | 3224598
MCR010904 | HPR072 | 2020-02-01 | Subcontract | 7567001 | 18392054 | 35625233
MCR010905 | HPR072 | 2020-02-01 | Overhead | 1476671 | 3589139 | 5996453
MCR010906 | HPR072 | 2020-03-01 | Labor | 745101 | 5121355 | 6681188
MCR010907 | HPR072 | 2020-03-01 | Material | 1582135 | 10874599 | 10727463
MCR010908 | HPR072 | 2020-03-01 | Equipment | 363800 | 2500532 | 2955993
MCR010909 | HPR072 | 2020-03-01 | Subcontract | 2019608 | 13881516 | 22688265
MCR010910 | HPR072 | 2020-03-01 | Overhead | 394119 | 2708925 | 6385576
MCR010911 | HPR072 | 2020-04-01 | Labor | 0 | 4985721 | 5160192
MCR010912 | HPR072 | 2020-04-01 | Material | 0 | 10586597 | 10660951
MCR010913 | HPR072 | 2020-04-01 | Equipment | 0 | 2434309 | 2072385
MCR010914 | HPR072 | 2020-04-01 | Subcontract | 0 | 13513879 | 36602855
MCR010915 | HPR072 | 2020-04-01 | Overhead | 0 | 2637182 | 5826922
MCR010916 | HPR072 | 2020-05-01 | Labor | 0 | 1998143 | 2474517
MCR010917 | HPR072 | 2020-05-01 | Material | 0 | 4242824 | 4844202
MCR010918 | HPR072 | 2020-05-01 | Equipment | 0 | 975606 | 1182070
MCR010919 | HPR072 | 2020-05-01 | Subcontract | 0 | 5416000 | 20514526
MCR010920 | HPR072 | 2020-05-01 | Overhead | 0 | 1056912 | 5877119
MCR010921 | HPR072 | 2020-06-01 | Labor | 0 | 511522 | 656679
MCR010922 | HPR072 | 2020-06-01 | Material | 0 | 1086158 | 1158112
MCR010923 | HPR072 | 2020-06-01 | Equipment | 0 | 249754 | 267035
MCR010924 | HPR072 | 2020-06-01 | Subcontract | 0 | 1386490 | 17974364
MCR010925 | HPR072 | 2020-06-01 | Overhead | 0 | 270568 | 6767024
MCR010926 | HPR073 | 2021-07-01 | Labor | 4186329 | 1698411 | 1737252
MCR010927 | HPR073 | 2021-07-01 | Material | 7883362 | 3198313 | 2837399
MCR010928 | HPR073 | 2021-07-01 | Equipment | 1785370 | 724332 | 714208
MCR010929 | HPR073 | 2021-07-01 | Subcontract | 13223720 | 5364918 | 5336054
MCR010930 | HPR073 | 2021-07-01 | Overhead | 2214822 | 898562 | 16210707
MCR010931 | HPR073 | 2021-08-01 | Labor | 11965997 | 5504354 | 5304125
MCR010932 | HPR073 | 2021-08-01 | Material | 22533414 | 10365362 | 9492087
MCR010933 | HPR073 | 2021-08-01 | Equipment | 5103213 | 2347476 | 2072618
MCR010934 | HPR073 | 2021-08-01 | Subcontract | 37798028 | 17387079 | 18790807
MCR010935 | HPR073 | 2021-08-01 | Overhead | 6330738 | 2912137 | 15607339
MCR010936 | HPR073 | 2021-09-01 | Labor | 18868935 | 13570270 | 15640564
MCR010937 | HPR073 | 2021-09-01 | Material | 35532476 | 25554453 | 30354593
MCR010938 | HPR073 | 2021-09-01 | Equipment | 8047152 | 5787397 | 6643423
MCR010939 | HPR073 | 2021-09-01 | Subcontract | 59602934 | 42865584 | 47733244
MCR010940 | HPR073 | 2021-09-01 | Overhead | 9982811 | 7179496 | 15488448
MCR010941 | HPR073 | 2021-10-01 | Labor | 24912712 | 23142961 | 26079073
MCR010942 | HPR073 | 2021-10-01 | Material | 46913637 | 43580982 | 42536084
MCR010943 | HPR073 | 2021-10-01 | Equipment | 10624679 | 9869922 | 8712678
MCR010944 | HPR073 | 2021-10-01 | Subcontract | 78693935 | 73103668 | 74317988
MCR010945 | HPR073 | 2021-10-01 | Overhead | 13180335 | 12244030 | 15375952
MCR010946 | HPR073 | 2021-11-01 | Labor | 30115660 | 27907229 | 27357485
MCR010947 | HPR073 | 2021-11-01 | Material | 56711415 | 52552674 | 48594305
MCR010948 | HPR073 | 2021-11-01 | Equipment | 12843612 | 11901769 | 12881031
MCR010949 | HPR073 | 2021-11-01 | Subcontract | 95128937 | 88152976 | 82418364
MCR010950 | HPR073 | 2021-11-01 | Overhead | 15933011 | 14764617 | 15166333
MCR010951 | HPR073 | 2021-12-01 | Labor | 34496951 | 17563488 | 21532455
MCR010952 | HPR073 | 2021-12-01 | Material | 64961914 | 33074164 | 39879590
MCR010953 | HPR073 | 2021-12-01 | Equipment | 14712129 | 7490410 | 7249242
MCR010954 | HPR073 | 2021-12-01 | Subcontract | 108968499 | 55479307 | 60913639
MCR010955 | HPR073 | 2021-12-01 | Overhead | 18250979 | 9292150 | 15548862
MCR010956 | HPR073 | 2022-01-01 | Labor | 38076688 | 27328096 | 27546785
MCR010957 | HPR073 | 2022-01-01 | Material | 71702989 | 51462096 | 52290010
MCR010958 | HPR073 | 2022-01-01 | Equipment | 16238801 | 11654783 | 11787686
MCR010959 | HPR073 | 2022-01-01 | Subcontract | 120276122 | 86323617 | 86383486
MCR010960 | HPR073 | 2022-01-01 | Overhead | 20144877 | 14458220 | 15849970
MCR010961 | HPR073 | 2022-02-01 | Labor | 40876013 | 20479537 | 24758528
MCR010962 | HPR073 | 2022-02-01 | Material | 76974456 | 38565435 | 45137290
MCR010963 | HPR073 | 2022-02-01 | Equipment | 17432647 | 8734035 | 9237074
MCR010964 | HPR073 | 2022-02-01 | Subcontract | 129118593 | 64690483 | 70699112
MCR010965 | HPR073 | 2022-02-01 | Overhead | 21625890 | 10834917 | 14973567
MCR010966 | HPR073 | 2022-03-01 | Labor | 42917237 | 22219282 | 23575613
MCR010967 | HPR073 | 2022-03-01 | Material | 80818327 | 41841585 | 42202488
MCR010968 | HPR073 | 2022-03-01 | Equipment | 18303180 | 9475995 | 10522185
MCR010969 | HPR073 | 2022-03-01 | Subcontract | 135566384 | 70185966 | 69642470
MCR010970 | HPR073 | 2022-03-01 | Overhead | 22705821 | 11755348 | 16471077
MCR010971 | HPR073 | 2022-04-01 | Labor | 44223991 | 44703474 | 50835240
MCR010972 | HPR073 | 2022-04-01 | Material | 83279101 | 84182026 | 84496284
MCR010973 | HPR073 | 2022-04-01 | Equipment | 18860480 | 19064968 | 19300216
MCR010974 | HPR073 | 2022-04-01 | Subcontract | 139694140 | 141208724 | 145167449
MCR010975 | HPR073 | 2022-04-01 | Overhead | 23397173 | 23650849 | 14230869
MCR010976 | HPR073 | 2022-05-01 | Labor | 44821410 | 40192480 | 45531848
MCR010977 | HPR073 | 2022-05-01 | Material | 84404114 | 75687281 | 78083609
MCR010978 | HPR073 | 2022-05-01 | Equipment | 19115265 | 17141137 | 16555218
MCR010979 | HPR073 | 2022-05-01 | Subcontract | 141581259 | 126959460 | 119881494
MCR010980 | HPR073 | 2022-05-01 | Overhead | 23713244 | 21264260 | 14480071
MCR010981 | HPR073 | 2022-06-01 | Labor | 44736365 | 30771817 | 34984321
MCR010982 | HPR073 | 2022-06-01 | Material | 84243963 | 57947038 | 57948930
MCR010983 | HPR073 | 2022-06-01 | Equipment | 19078995 | 13123448 | 12895342
MCR010984 | HPR073 | 2022-06-01 | Subcontract | 141312619 | 97201597 | 106829572
MCR010985 | HPR073 | 2022-06-01 | Overhead | 23668250 | 16280157 | 15858495
MCR010986 | HPR073 | 2022-07-01 | Labor | 43997740 | 18483665 | 17491196
MCR010987 | HPR073 | 2022-07-01 | Material | 82853044 | 34806967 | 40668133
MCR010988 | HPR073 | 2022-07-01 | Equipment | 18763989 | 7882843 | 8882661
MCR010989 | HPR073 | 2022-07-01 | Subcontract | 138979462 | 58385948 | 58351104
MCR010990 | HPR073 | 2022-07-01 | Overhead | 23277473 | 9778980 | 16009102
MCR010991 | HPR073 | 2022-08-01 | Labor | 42636796 | 29999235 | 32787096
MCR010992 | HPR073 | 2022-08-01 | Material | 80290223 | 56492173 | 60215129
MCR010993 | HPR073 | 2022-08-01 | Equipment | 18183579 | 12793960 | 14198346
MCR010994 | HPR073 | 2022-08-01 | Subcontract | 134680532 | 94761175 | 89342735
MCR010995 | HPR073 | 2022-08-01 | Overhead | 22557451 | 15871415 | 14424100
MCR010996 | HPR073 | 2022-09-01 | Labor | 40687629 | 49100933 | 50384226
MCR010997 | HPR073 | 2022-09-01 | Material | 76619706 | 92462971 | 100289900
MCR010998 | HPR073 | 2022-09-01 | Equipment | 17352306 | 20940380 | 20225065
MCR010999 | HPR073 | 2022-09-01 | Subcontract | 128523528 | 155099358 | 166499763
MCR011000 | HPR073 | 2022-09-01 | Overhead | 21526223 | 25977371 | 14946692
MCR011001 | HPR073 | 2022-10-01 | Labor | 38187777 | 39040366 | 45038573
MCR011002 | HPR073 | 2022-10-01 | Material | 71912183 | 73517711 | 74005764
MCR011003 | HPR073 | 2022-10-01 | Equipment | 16286178 | 16649787 | 16365602
MCR011004 | HPR073 | 2022-10-01 | Subcontract | 120627030 | 123320175 | 134352313
MCR011005 | HPR073 | 2022-10-01 | Overhead | 20203650 | 20654721 | 15193285
MCR011006 | HPR073 | 2022-11-01 | Labor | 35179049 | 25451088 | 33521973
MCR011007 | HPR073 | 2022-11-01 | Material | 66246386 | 47927464 | 45443732
MCR011008 | HPR073 | 2022-11-01 | Equipment | 15003027 | 10854283 | 12194431
MCR011009 | HPR073 | 2022-11-01 | Subcontract | 111123099 | 80394549 | 75755462
MCR011010 | HPR073 | 2022-11-01 | Overhead | 18611850 | 13465169 | 15296172
MCR011011 | HPR073 | 2022-12-01 | Labor | 31708671 | 31677640 | 35075799
MCR011012 | HPR073 | 2022-12-01 | Material | 59711246 | 59652811 | 64457614
MCR011013 | HPR073 | 2022-12-01 | Equipment | 13522994 | 13509760 | 13939995
MCR011014 | HPR073 | 2022-12-01 | Subcontract | 100160918 | 100062897 | 105187543
MCR011015 | HPR073 | 2022-12-01 | Overhead | 16775810 | 16759393 | 16775807
MCR011016 | HPR073 | 2023-01-01 | Labor | 27830965 | 35086396 | 38276051
MCR011017 | HPR073 | 2023-01-01 | Material | 52409059 | 66071910 | 68402366
MCR011018 | HPR073 | 2023-01-01 | Equipment | 11869244 | 14963513 | 14801881
MCR011019 | HPR073 | 2023-01-01 | Subcontract | 87912074 | 110830430 | 108070321
MCR011020 | HPR073 | 2023-01-01 | Overhead | 14724268 | 18562831 | 14040714
MCR011021 | HPR073 | 2023-02-01 | Labor | 23609904 | 46192979 | 55033131
MCR011022 | HPR073 | 2023-02-01 | Material | 44460292 | 86986943 | 96897877
MCR011023 | HPR073 | 2023-02-01 | Equipment | 10069062 | 19700206 | 18268636
MCR011024 | HPR073 | 2023-02-01 | Subcontract | 74578642 | 145913753 | 139502856
MCR011025 | HPR073 | 2023-02-01 | Overhead | 12491071 | 24438887 | 14637954
MCR011026 | HPR073 | 2023-03-01 | Labor | 19123278 | 22539499 | 27344000
MCR011027 | HPR073 | 2023-03-01 | Material | 36011435 | 42444591 | 36405349
MCR011028 | HPR073 | 2023-03-01 | Equipment | 8155623 | 9612560 | 11769515
MCR011029 | HPR073 | 2023-03-01 | Subcontract | 60406349 | 71197461 | 93195054
MCR011030 | HPR073 | 2023-03-01 | Overhead | 10117374 | 11924762 | 15242085
MCR011031 | HPR073 | 2023-04-01 | Labor | 14470119 | 38354894 | 41944854
MCR011032 | HPR073 | 2023-04-01 | Material | 27248977 | 72226885 | 77146303
MCR011033 | HPR073 | 2023-04-01 | Equipment | 6171162 | 16357450 | 17188573
MCR011034 | HPR073 | 2023-04-01 | Subcontract | 45708015 | 121154916 | 123967645
MCR011035 | HPR073 | 2023-04-01 | Overhead | 7655571 | 20292065 | 16764787
MCR011036 | HPR073 | 2023-05-01 | Labor | 9785746 | 21693158 | 22214611
MCR011037 | HPR073 | 2023-05-01 | Material | 18427738 | 40850829 | 39209672
MCR011038 | HPR073 | 2023-05-01 | Equipment | 4173388 | 9251616 | 9312315
MCR011039 | HPR073 | 2023-05-01 | Subcontract | 30911081 | 68524051 | 74033710
MCR011040 | HPR073 | 2023-05-01 | Overhead | 5177253 | 11476996 | 14175018
MCR011041 | HPR073 | 2023-06-01 | Labor | 5279616 | 19500847 | 23524348
MCR011042 | HPR073 | 2023-06-01 | Material | 9942153 | 36722443 | 38246745
MCR011043 | HPR073 | 2023-06-01 | Equipment | 2251631 | 8316647 | 7973884
MCR011044 | HPR073 | 2023-06-01 | Subcontract | 16677180 | 61599009 | 58086761
MCR011045 | HPR073 | 2023-06-01 | Overhead | 2793237 | 10317131 | 14904172
MCR011046 | HPR073 | 2023-07-01 | Labor | 1395487 | 12205315 | 12382667
MCR011047 | HPR073 | 2023-07-01 | Material | 2627871 | 22984079 | 22511640
MCR011048 | HPR073 | 2023-07-01 | Equipment | 595142 | 5205277 | 6028633
MCR011049 | HPR073 | 2023-07-01 | Subcontract | 4408047 | 38553984 | 34334181
MCR011050 | HPR073 | 2023-07-01 | Overhead | 738297 | 6457352 | 15726401
MCR011051 | HPR073 | 2023-08-01 | Labor | 0 | 18447115 | 22088599
MCR011052 | HPR073 | 2023-08-01 | Material | 0 | 34738138 | 34510361
MCR011053 | HPR073 | 2023-08-01 | Equipment | 0 | 7867255 | 8564749
MCR011054 | HPR073 | 2023-08-01 | Subcontract | 0 | 58270494 | 67109227
MCR011055 | HPR073 | 2023-08-01 | Overhead | 0 | 9759642 | 15389023
MCR011056 | HPR073 | 2023-09-01 | Labor | 0 | 13145132 | 13694973
MCR011057 | HPR073 | 2023-09-01 | Material | 0 | 24753867 | 26926237
MCR011058 | HPR073 | 2023-09-01 | Equipment | 0 | 5606086 | 5153432
MCR011059 | HPR073 | 2023-09-01 | Subcontract | 0 | 41522664 | 44087978
MCR011060 | HPR073 | 2023-09-01 | Overhead | 0 | 6954572 | 14596358
MCR011061 | HPR073 | 2023-10-01 | Labor | 0 | 9160772 | 8974583
MCR011062 | HPR073 | 2023-10-01 | Material | 0 | 17250836 | 18698060
MCR011063 | HPR073 | 2023-10-01 | Equipment | 0 | 3906851 | 4713521
MCR011064 | HPR073 | 2023-10-01 | Subcontract | 0 | 28936920 | 25054164
MCR011065 | HPR073 | 2023-10-01 | Overhead | 0 | 4846604 | 16402618
MCR011066 | HPR073 | 2023-11-01 | Labor | 0 | 4787253 | 6831787
MCR011067 | HPR073 | 2023-11-01 | Material | 0 | 9014975 | 7183636
MCR011068 | HPR073 | 2023-11-01 | Equipment | 0 | 2041650 | 2235716
MCR011069 | HPR073 | 2023-11-01 | Subcontract | 0 | 15121911 | 17176824
MCR011070 | HPR073 | 2023-11-01 | Overhead | 0 | 2532747 | 15863492
MCR011071 | HPR073 | 2023-12-01 | Labor | 0 | 3487580 | 4020997
MCR011072 | HPR073 | 2023-12-01 | Material | 0 | 6567533 | 6960078
MCR011073 | HPR073 | 2023-12-01 | Equipment | 0 | 1487370 | 1528827
MCR011074 | HPR073 | 2023-12-01 | Subcontract | 0 | 11016520 | 12674105
MCR011075 | HPR073 | 2023-12-01 | Overhead | 0 | 1845141 | 15047733
MCR011076 | HPR073 | 2024-01-01 | Labor | 0 | 655800 | 564004
MCR011077 | HPR073 | 2024-01-01 | Material | 0 | 1234950 | 1339176
MCR011078 | HPR073 | 2024-01-01 | Equipment | 0 | 279683 | 317820
MCR011079 | HPR073 | 2024-01-01 | Subcontract | 0 | 2071532 | 1255609
MCR011080 | HPR073 | 2024-01-01 | Overhead | 0 | 346958 | 15175497
MCR011081 | HPR074 | 2019-05-01 | Labor | 2780159 | 1879674 | 1863998
MCR011082 | HPR074 | 2019-05-01 | Material | 9159278 | 6192616 | 6541254
MCR011083 | HPR074 | 2019-05-01 | Equipment | 3786681 | 2560186 | 2515392
MCR011084 | HPR074 | 2019-05-01 | Subcontract | 7342075 | 4963999 | 5303920
MCR011085 | HPR074 | 2019-05-01 | Overhead | 2960716 | 2001749 | 18345590
MCR011086 | HPR074 | 2019-06-01 | Labor | 7911629 | 3592716 | 3366199
MCR011087 | HPR074 | 2019-06-01 | Material | 26064984 | 11836257 | 12531805
MCR011088 | HPR074 | 2019-06-01 | Equipment | 10775934 | 4893413 | 5032178
MCR011089 | HPR074 | 2019-06-01 | Subcontract | 20893684 | 9487941 | 10685922
MCR011090 | HPR074 | 2019-06-01 | Overhead | 8425447 | 3826044 | 18726618
MCR011091 | HPR074 | 2019-07-01 | Labor | 12409907 | 9391679 | 11457719
MCR011092 | HPR074 | 2019-07-01 | Material | 40884629 | 30941031 | 34993411
MCR011093 | HPR074 | 2019-07-01 | Equipment | 16902756 | 12791817 | 12762517
MCR011094 | HPR074 | 2019-07-01 | Subcontract | 32773108 | 24802322 | 23304021
MCR011095 | HPR074 | 2019-07-01 | Overhead | 13215865 | 10001619 | 19094346
MCR011096 | HPR074 | 2019-08-01 | Labor | 16288923 | 6167736 | 6380250
MCR011097 | HPR074 | 2019-08-01 | Material | 53664109 | 20319700 | 16593795
MCR011098 | HPR074 | 2019-08-01 | Equipment | 22186122 | 8400686 | 8822075
MCR011099 | HPR074 | 2019-08-01 | Subcontract | 43017135 | 16288266 | 17853643
MCR011100 | HPR074 | 2019-08-01 | Overhead | 17346803 | 6568297 | 19032069
MCR011101 | HPR074 | 2019-09-01 | Labor | 19563274 | 10689398 | 11650152
MCR011102 | HPR074 | 2019-09-01 | Material | 64451509 | 35216386 | 37889039
MCR011103 | HPR074 | 2019-09-01 | Equipment | 26645910 | 14559359 | 13420814
MCR011104 | HPR074 | 2019-09-01 | Subcontract | 51664312 | 28229445 | 29284496
MCR011105 | HPR074 | 2019-09-01 | Overhead | 20833805 | 11383617 | 16256406
MCR011106 | HPR074 | 2019-10-01 | Labor | 22248297 | 24471387 | 28348504
MCR011107 | HPR074 | 2019-10-01 | Material | 73297360 | 80621363 | 90063124
MCR011108 | HPR074 | 2019-10-01 | Equipment | 30303012 | 33330943 | 34874178
MCR011109 | HPR074 | 2019-10-01 | Subcontract | 58755143 | 64626063 | 71073316
MCR011110 | HPR074 | 2019-10-01 | Overhead | 23693207 | 26060674 | 18611799
MCR011111 | HPR074 | 2019-11-01 | Labor | 24360162 | 12346905 | 12416551
MCR011112 | HPR074 | 2019-11-01 | Material | 80254931 | 40677069 | 33650475
MCR011113 | HPR074 | 2019-11-01 | Equipment | 33179451 | 16816946 | 16359255
MCR011114 | HPR074 | 2019-11-01 | Subcontract | 64332331 | 32606728 | 31670802
MCR011115 | HPR074 | 2019-11-01 | Overhead | 25942226 | 13148771 | 18488581
MCR011116 | HPR074 | 2019-12-01 | Labor | 25915979 | 16957405 | 16144949
MCR011117 | HPR074 | 2019-12-01 | Material | 85380593 | 55866432 | 63766405
MCR011118 | HPR074 | 2019-12-01 | Equipment | 35298531 | 23096618 | 24710728
MCR011119 | HPR074 | 2019-12-01 | Subcontract | 68441060 | 44782516 | 48126316
MCR011120 | HPR074 | 2019-12-01 | Overhead | 27599085 | 18058698 | 18175977
MCR011121 | HPR074 | 2020-01-01 | Labor | 26933927 | 19264535 | 23363767
MCR011122 | HPR074 | 2020-01-01 | Material | 88734238 | 63467307 | 64331600
MCR011123 | HPR074 | 2020-01-01 | Equipment | 36685014 | 26239015 | 30859519
MCR011124 | HPR074 | 2020-01-01 | Subcontract | 71129341 | 50875376 | 51159246
MCR011125 | HPR074 | 2020-01-01 | Overhead | 28683143 | 20515664 | 19210465
MCR011126 | HPR074 | 2020-02-01 | Labor | 27433417 | 26540965 | 27508736
MCR011127 | HPR074 | 2020-02-01 | Material | 90379817 | 87439618 | 84448783
MCR011128 | HPR074 | 2020-02-01 | Equipment | 37365338 | 36149785 | 39717264
MCR011129 | HPR074 | 2020-02-01 | Subcontract | 72448436 | 70091574 | 69385992
MCR011130 | HPR074 | 2020-02-01 | Overhead | 29215073 | 28264660 | 18089063
MCR011131 | HPR074 | 2020-03-01 | Labor | 27435290 | 41347805 | 46545868
MCR011132 | HPR074 | 2020-03-01 | Material | 90385988 | 136220982 | 152199553
MCR011133 | HPR074 | 2020-03-01 | Equipment | 37367890 | 56317254 | 68523187
MCR011134 | HPR074 | 2020-03-01 | Subcontract | 72453383 | 109194702 | 96376204
MCR011135 | HPR074 | 2020-03-01 | Overhead | 29217067 | 44033126 | 19449925
MCR011136 | HPR074 | 2020-04-01 | Labor | 26962068 | 20254483 | 19243834
MCR011137 | HPR074 | 2020-04-01 | Material | 88826949 | 66728706 | 65496067
MCR011138 | HPR074 | 2020-04-01 | Equipment | 36723343 | 27587361 | 22685819
MCR011139 | HPR074 | 2020-04-01 | Subcontract | 71203658 | 53489712 | 58635943
MCR011140 | HPR074 | 2020-04-01 | Overhead | 28713112 | 21569904 | 19585983
MCR011141 | HPR074 | 2020-05-01 | Labor | 26038275 | 19141088 | 20585135
MCR011142 | HPR074 | 2020-05-01 | Material | 85783500 | 63060610 | 65165020
MCR011143 | HPR074 | 2020-05-01 | Equipment | 35465103 | 26070876 | 25279422
MCR011144 | HPR074 | 2020-05-01 | Subcontract | 68764031 | 50549368 | 59601378
MCR011145 | HPR074 | 2020-05-01 | Overhead | 27729324 | 20384200 | 19585192
MCR011146 | HPR074 | 2020-06-01 | Labor | 24690869 | 17423126 | 18866015
MCR011147 | HPR074 | 2020-06-01 | Material | 81344451 | 57400759 | 51264063
MCR011148 | HPR074 | 2020-06-01 | Equipment | 33629886 | 23730949 | 26008415
MCR011149 | HPR074 | 2020-06-01 | Subcontract | 65205689 | 46012433 | 49406831
MCR011150 | HPR074 | 2020-06-01 | Overhead | 26294411 | 18554666 | 18858605
MCR011151 | HPR074 | 2020-07-01 | Labor | 22949813 | 11249419 | 12450131
MCR011152 | HPR074 | 2020-07-01 | Material | 75608513 | 37061385 | 38882079
MCR011153 | HPR074 | 2020-07-01 | Equipment | 31258502 | 15322129 | 14860714
MCR011154 | HPR074 | 2020-07-01 | Subcontract | 60607763 | 29708396 | 20726813
MCR011155 | HPR074 | 2020-07-01 | Overhead | 24440282 | 11980009 | 20769231
MCR011156 | HPR074 | 2020-08-01 | Labor | 20848879 | 14370896 | 16220112
MCR011157 | HPR074 | 2020-08-01 | Material | 68686954 | 47345138 | 49146282
MCR011158 | HPR074 | 2020-08-01 | Equipment | 28396952 | 19573697 | 19381318
MCR011159 | HPR074 | 2020-08-01 | Subcontract | 55059443 | 37951850 | 47748308
MCR011160 | HPR074 | 2020-08-01 | Overhead | 22202903 | 15304209 | 19109996
MCR011161 | HPR074 | 2020-09-01 | Labor | 18426817 | 20373835 | 19381020
MCR011162 | HPR074 | 2020-09-01 | Material | 60707435 | 67121913 | 68901977
MCR011163 | HPR074 | 2020-09-01 | Equipment | 25098013 | 27749924 | 32257128
MCR011164 | HPR074 | 2020-09-01 | Subcontract | 48663063 | 53804907 | 48306665
MCR011165 | HPR074 | 2020-09-01 | Overhead | 19623542 | 21697008 | 19417828
MCR011166 | HPR074 | 2020-10-01 | Labor | 15729133 | 20426481 | 22252952
MCR011167 | HPR074 | 2020-10-01 | Material | 51819873 | 67295358 | 62805107
MCR011168 | HPR074 | 2020-10-01 | Equipment | 21423667 | 27821630 | 30788647
MCR011169 | HPR074 | 2020-10-01 | Subcontract | 41538796 | 53943941 | 55070599
MCR011170 | HPR074 | 2020-10-01 | Overhead | 16750657 | 21753073 | 17691667
MCR011171 | HPR074 | 2020-11-01 | Labor | 12810980 | 14595216 | 14470154
MCR011172 | HPR074 | 2020-11-01 | Material | 42205971 | 48084164 | 53040212
MCR011173 | HPR074 | 2020-11-01 | Equipment | 17449033 | 19879229 | 18088857
MCR011174 | HPR074 | 2020-11-01 | Subcontract | 33832295 | 38544253 | 40803652
MCR011175 | HPR074 | 2020-11-01 | Overhead | 13642985 | 15543098 | 20019381
MCR011176 | HPR074 | 2020-12-01 | Labor | 9742299 | 13367177 | 13583103
MCR011177 | HPR074 | 2020-12-01 | Material | 32096154 | 44038370 | 44532518
MCR011178 | HPR074 | 2020-12-01 | Equipment | 13269375 | 18206594 | 20887954
MCR011179 | HPR074 | 2020-12-01 | Subcontract | 25728268 | 35301146 | 65984185
MCR011180 | HPR074 | 2020-12-01 | Overhead | 10375010 | 14235304 | 17885975
MCR011181 | HPR074 | 2021-01-01 | Labor | 6618218 | 18919590 | 22925678
MCR011182 | HPR074 | 2021-01-01 | Material | 21803823 | 62330881 | 58286666
MCR011183 | HPR074 | 2021-01-01 | Equipment | 9014261 | 25769188 | 26358030
MCR011184 | HPR074 | 2021-01-01 | Subcontract | 17477938 | 49964417 | 79483486
MCR011185 | HPR074 | 2021-01-01 | Overhead | 7048037 | 20148317 | 19220520
MCR011186 | HPR074 | 2021-02-01 | Labor | 3585146 | 18494176 | 17755993
MCR011187 | HPR074 | 2021-02-01 | Material | 11811320 | 60929349 | 67587481
MCR011188 | HPR074 | 2021-02-01 | Equipment | 4883103 | 25189759 | 22749703
MCR011189 | HPR074 | 2021-02-01 | Subcontract | 9467951 | 48840950 | 73183639
MCR011190 | HPR074 | 2021-02-01 | Overhead | 3817983 | 19695275 | 19961620
MCR011191 | HPR074 | 2021-03-01 | Labor | 950795 | 10888976 | 12562675
MCR011192 | HPR074 | 2021-03-01 | Material | 3132407 | 35873899 | 38143235
MCR011193 | HPR074 | 2021-03-01 | Equipment | 1295018 | 14831192 | 16009461
MCR011194 | HPR074 | 2021-03-01 | Subcontract | 2510937 | 28756508 | 47509020
MCR011195 | HPR074 | 2021-03-01 | Overhead | 1012544 | 11596157 | 19764994
MCR011196 | HPR074 | 2021-04-01 | Labor | 0 | 8348260 | 9136019
MCR011197 | HPR074 | 2021-04-01 | Material | 0 | 27503473 | 27771319
MCR011198 | HPR074 | 2021-04-01 | Equipment | 0 | 11370642 | 12800304
MCR011199 | HPR074 | 2021-04-01 | Subcontract | 0 | 22046776 | 52958456
MCR011200 | HPR074 | 2021-04-01 | Overhead | 0 | 8890436 | 19284958
MCR011201 | HPR074 | 2021-05-01 | Labor | 0 | 10627804 | 11375131
MCR011202 | HPR074 | 2021-05-01 | Material | 0 | 35013465 | 34928689
MCR011203 | HPR074 | 2021-05-01 | Equipment | 0 | 14475466 | 16765106
MCR011204 | HPR074 | 2021-05-01 | Subcontract | 0 | 28066784 | 48799596
MCR011205 | HPR074 | 2021-05-01 | Overhead | 0 | 11318024 | 18085981
MCR011206 | HPR074 | 2021-06-01 | Labor | 0 | 6589478 | 7352003
MCR011207 | HPR074 | 2021-06-01 | Material | 0 | 21709136 | 22820038
MCR011208 | HPR074 | 2021-06-01 | Equipment | 0 | 8975115 | 8109664
MCR011209 | HPR074 | 2021-06-01 | Subcontract | 0 | 17402037 | 31068039
MCR011210 | HPR074 | 2021-06-01 | Overhead | 0 | 7017429 | 16176658
MCR011211 | HPR074 | 2021-07-01 | Labor | 0 | 2325625 | 1963948
MCR011212 | HPR074 | 2021-07-01 | Material | 0 | 7661809 | 8574549
MCR011213 | HPR074 | 2021-07-01 | Equipment | 0 | 3167589 | 4510818
MCR011214 | HPR074 | 2021-07-01 | Subcontract | 0 | 6141704 | 25067858
MCR011215 | HPR074 | 2021-07-01 | Overhead | 0 | 2476663 | 18198252
MCR011216 | HPR074 | 2021-08-01 | Labor | 0 | 2150048 | 2647220
MCR011217 | HPR074 | 2021-08-01 | Material | 0 | 7083366 | 7460402
MCR011218 | HPR074 | 2021-08-01 | Equipment | 0 | 2928446 | 2978114
MCR011219 | HPR074 | 2021-08-01 | Subcontract | 0 | 5678024 | 32461910
MCR011220 | HPR074 | 2021-08-01 | Overhead | 0 | 2289682 | 18590365
MCR011221 | HPR074 | 2021-09-01 | Labor | 0 | 438377 | 481848
MCR011222 | HPR074 | 2021-09-01 | Material | 0 | 1444241 | 1815012
MCR011223 | HPR074 | 2021-09-01 | Equipment | 0 | 597086 | 719445
MCR011224 | HPR074 | 2021-09-01 | Subcontract | 0 | 1157703 | 26251300
MCR011225 | HPR074 | 2021-09-01 | Overhead | 0 | 466848 | 18575645
MCR011226 | HPR075 | 2019-10-01 | Labor | 31768827 | 22335135 | 24855809
MCR011227 | HPR075 | 2019-10-01 | Material | 84265264 | 59242857 | 66538584
MCR011228 | HPR075 | 2019-10-01 | Equipment | 15125767 | 10634200 | 11444213
MCR011229 | HPR075 | 2019-10-01 | Subcontract | 87090302 | 61229006 | 62791264
MCR011230 | HPR075 | 2019-10-01 | Overhead | 16522154 | 11615932 | 53315094
MCR011231 | HPR075 | 2019-11-01 | Labor | 84795215 | 24891825 | 24081646
MCR011232 | HPR075 | 2019-11-01 | Material | 224915171 | 66024351 | 54710341
MCR011233 | HPR075 | 2019-11-01 | Equipment | 40372678 | 11851490 | 13186905
MCR011234 | HPR075 | 2019-11-01 | Subcontract | 232455574 | 68237854 | 69337807
MCR011235 | HPR075 | 2019-11-01 | Overhead | 44099822 | 12945601 | 48952781
MCR011236 | HPR075 | 2019-12-01 | Labor | 122613397 | 63677301 | 65220191
MCR011237 | HPR075 | 2019-12-01 | Material | 325226051 | 168900934 | 146911211
MCR011238 | HPR075 | 2019-12-01 | Equipment | 58378662 | 30318022 | 28484964
MCR011239 | HPR075 | 2019-12-01 | Subcontract | 336129430 | 174563429 | 185532082
MCR011240 | HPR075 | 2019-12-01 | Overhead | 63768090 | 33116935 | 51477944
MCR011241 | HPR075 | 2020-01-01 | Labor | 146033499 | 88591766 | 104807513
MCR011242 | HPR075 | 2020-01-01 | Material | 387346730 | 234985337 | 250587503
MCR011243 | HPR075 | 2020-01-01 | Equipment | 69529436 | 42180291 | 44724781
MCR011244 | HPR075 | 2020-01-01 | Subcontract | 400332739 | 242863347 | 223037877
MCR011245 | HPR075 | 2020-01-01 | Overhead | 75948286 | 46074311 | 52361530
MCR011246 | HPR075 | 2020-02-01 | Labor | 155966366 | 118623625 | 111964846
MCR011247 | HPR075 | 2020-02-01 | Material | 413693174 | 314643377 | 327041188
MCR011248 | HPR075 | 2020-02-01 | Equipment | 74258670 | 56479053 | 67721887
MCR011249 | HPR075 | 2020-02-01 | Subcontract | 427562461 | 325191966 | 362750509
MCR011250 | HPR075 | 2020-02-01 | Overhead | 81114116 | 61693112 | 47331695
MCR011251 | HPR075 | 2020-03-01 | Labor | 153456470 | 94211908 | 103334074
MCR011252 | HPR075 | 2020-03-01 | Material | 407035799 | 249892488 | 251089300
MCR011253 | HPR075 | 2020-03-01 | Equipment | 73063659 | 44856152 | 41780099
MCR011254 | HPR075 | 2020-03-01 | Subcontract | 420681894 | 258270269 | 246651315
MCR011255 | HPR075 | 2020-03-01 | Overhead | 79808783 | 48997202 | 51613760
MCR011256 | HPR075 | 2020-04-01 | Labor | 139734342 | 116443601 | 129019239
MCR011257 | HPR075 | 2020-04-01 | Material | 370638523 | 308860970 | 315872447
MCR011258 | HPR075 | 2020-04-01 | Equipment | 66530282 | 55441100 | 53874798
MCR011259 | HPR075 | 2020-04-01 | Subcontract | 383064380 | 319215701 | 298143323
MCR011260 | HPR075 | 2020-04-01 | Overhead | 72672256 | 60559337 | 53238316
MCR011261 | HPR075 | 2020-05-01 | Labor | 116307560 | 154191100 | 153173980
MCR011262 | HPR075 | 2020-05-01 | Material | 308500128 | 408984370 | 445852387
MCR011263 | HPR075 | 2020-05-01 | Equipment | 55376328 | 73413431 | 85471839
MCR011264 | HPR075 | 2020-05-01 | Subcontract | 318842761 | 422695792 | 472105578
MCR011265 | HPR075 | 2020-05-01 | Overhead | 60488586 | 80190846 | 51853084
MCR011266 | HPR075 | 2020-06-01 | Labor | 85140063 | 97858006 | 121576325
MCR011267 | HPR075 | 2020-06-01 | Material | 225829862 | 259563586 | 232328542
MCR011268 | HPR075 | 2020-06-01 | Equipment | 40536867 | 46592131 | 45314059
MCR011269 | HPR075 | 2020-06-01 | Subcontract | 233400930 | 268265596 | 268572070
MCR011270 | HPR075 | 2020-06-01 | Overhead | 44279168 | 50893445 | 52577855
MCR011271 | HPR075 | 2020-07-01 | Labor | 49088637 | 37775956 | 77258799
MCR011272 | HPR075 | 2020-07-01 | Material | 130205213 | 100198879 | 170460697
MCR011273 | HPR075 | 2020-07-01 | Equipment | 23372070 | 17985879 | 19393267
MCR011274 | HPR075 | 2020-07-01 | Subcontract | 134570413 | 103558101 | 112286806
MCR011275 | HPR075 | 2020-07-01 | Overhead | 25529744 | 19646308 | 49659324
MCR011276 | HPR075 | 2020-08-01 | Labor | 13668215 | 47250122 | 119948994
MCR011277 | HPR075 | 2020-08-01 | Material | 36254274 | 125328642 | 240435103
MCR011278 | HPR075 | 2020-08-01 | Equipment | 6507708 | 22496717 | 24943915
MCR011279 | HPR075 | 2020-08-01 | Subcontract | 37469719 | 129530353 | 149196744
MCR011280 | HPR075 | 2020-08-01 | Overhead | 7108489 | 24573579 | 55973496
MCR011281 | HPR075 | 2020-09-01 | Labor | 0 | 69619500 | 64196653
MCR011282 | HPR075 | 2020-09-01 | Material | 0 | 184662326 | 162127905
MCR011283 | HPR075 | 2020-09-01 | Equipment | 0 | 33147220 | 33622418
MCR011284 | HPR075 | 2020-09-01 | Subcontract | 0 | 190853230 | 185495121
MCR011285 | HPR075 | 2020-09-01 | Overhead | 0 | 36207320 | 50772230
MCR011286 | HPR075 | 2020-10-01 | Labor | 0 | 92888796 | 105124087
MCR011287 | HPR075 | 2020-10-01 | Material | 0 | 246382999 | 242410742
MCR011288 | HPR075 | 2020-10-01 | Equipment | 0 | 44226192 | 48919260
MCR011289 | HPR075 | 2020-10-01 | Subcontract | 0 | 254643122 | 296693480
MCR011290 | HPR075 | 2020-10-01 | Overhead | 0 | 48309086 | 53659745
MCR011291 | HPR075 | 2020-11-01 | Labor | 0 | 41387095 | 43843079
MCR011292 | HPR075 | 2020-11-01 | Material | 0 | 109777249 | 120826022
MCR011293 | HPR075 | 2020-11-01 | Equipment | 0 | 19705214 | 23258225
MCR011294 | HPR075 | 2020-11-01 | Subcontract | 0 | 113457591 | 80363151
MCR011295 | HPR075 | 2020-11-01 | Overhead | 0 | 21524369 | 56976881
MCR011296 | HPR075 | 2020-12-01 | Labor | 0 | 22597931 | 29278248
MCR011297 | HPR075 | 2020-12-01 | Material | 0 | 59939910 | 57473197
MCR011298 | HPR075 | 2020-12-01 | Equipment | 0 | 10759322 | 12655252
MCR011299 | HPR075 | 2020-12-01 | Subcontract | 0 | 61949428 | 73736847
MCR011300 | HPR075 | 2020-12-01 | Overhead | 0 | 11752606 | 54490825
MCR011301 | HPR075 | 2021-01-01 | Labor | 0 | 6228922 | 4245335
MCR011302 | HPR075 | 2021-01-01 | Material | 0 | 16521912 | 20907774
MCR011303 | HPR075 | 2021-01-01 | Equipment | 0 | 2965713 | 3951142
MCR011304 | HPR075 | 2021-01-01 | Subcontract | 0 | 17075818 | 19054513
MCR011305 | HPR075 | 2021-01-01 | Overhead | 0 | 3239503 | 54015554
MCR011306 | HPR076 | 2019-01-01 | Labor | 2735369 | 4007200 | 3745526
MCR011307 | HPR076 | 2019-01-01 | Material | 9936281 | 14556228 | 13305612
MCR011308 | HPR076 | 2019-01-01 | Equipment | 1985666 | 2908916 | 3093402
MCR011309 | HPR076 | 2019-01-01 | Subcontract | 7970811 | 11676899 | 11295437
MCR011310 | HPR076 | 2019-01-01 | Overhead | 2002561 | 2933667 | 11554356
MCR011311 | HPR076 | 2019-02-01 | Labor | 7742958 | 4787607 | 5346281
MCR011312 | HPR076 | 2019-02-01 | Material | 28126439 | 17391074 | 18566032
MCR011313 | HPR076 | 2019-02-01 | Equipment | 5620786 | 3475431 | 3567553
MCR011314 | HPR076 | 2019-02-01 | Subcontract | 22562822 | 13950991 | 15411177
MCR011315 | HPR076 | 2019-02-01 | Overhead | 5668612 | 3505003 | 10899061
MCR011316 | HPR076 | 2019-03-01 | Labor | 12067823 | 14519769 | 14155749
MCR011317 | HPR076 | 2019-03-01 | Material | 43836595 | 52743334 | 47909284
MCR011318 | HPR076 | 2019-03-01 | Equipment | 8760302 | 10540224 | 10860828
MCR011319 | HPR076 | 2019-03-01 | Subcontract | 35165394 | 42310315 | 42859473
MCR011320 | HPR076 | 2019-03-01 | Overhead | 8834842 | 10629909 | 12571458
MCR011321 | HPR076 | 2019-04-01 | Labor | 15726615 | 14685350 | 13995991
MCR011322 | HPR076 | 2019-04-01 | Material | 57127223 | 53344808 | 61626117
MCR011323 | HPR076 | 2019-04-01 | Equipment | 11416300 | 10660423 | 10751005
MCR011324 | HPR076 | 2019-04-01 | Subcontract | 45827038 | 42792813 | 43376831
MCR011325 | HPR076 | 2019-04-01 | Overhead | 11513439 | 10751130 | 10887959
MCR011326 | HPR076 | 2019-05-01 | Labor | 18736867 | 18313919 | 17081374
MCR011327 | HPR076 | 2019-05-01 | Material | 68062019 | 66525655 | 62694576
MCR011328 | HPR076 | 2019-05-01 | Equipment | 13601509 | 13294482 | 15798393
MCR011329 | HPR076 | 2019-05-01 | Subcontract | 54598851 | 53366391 | 54104585
MCR011330 | HPR076 | 2019-05-01 | Overhead | 13717242 | 13407602 | 11706741
MCR011331 | HPR076 | 2019-06-01 | Labor | 21117113 | 24164565 | 23273934
MCR011332 | HPR076 | 2019-06-01 | Material | 76708309 | 87778236 | 83025081
MCR011333 | HPR076 | 2019-06-01 | Equipment | 15329383 | 17541597 | 17149384
MCR011334 | HPR076 | 2019-06-01 | Subcontract | 61534842 | 70415056 | 67497738
MCR011335 | HPR076 | 2019-06-01 | Overhead | 15459818 | 17690855 | 11479472
MCR011336 | HPR076 | 2019-07-01 | Labor | 22887026 | 13542997 | 15694877
MCR011337 | HPR076 | 2019-07-01 | Material | 83137552 | 49195190 | 58560423
MCR011338 | HPR076 | 2019-07-01 | Equipment | 16614203 | 9831163 | 8882755
MCR011339 | HPR076 | 2019-07-01 | Subcontract | 66692333 | 39464019 | 47971299
MCR011340 | HPR076 | 2019-07-01 | Overhead | 16755569 | 9914815 | 11960392
MCR011341 | HPR076 | 2019-08-01 | Labor | 24067583 | 8183723 | 8392340
MCR011342 | HPR076 | 2019-08-01 | Material | 87425947 | 29727528 | 29349938
MCR011343 | HPR076 | 2019-08-01 | Equipment | 17471195 | 5940747 | 6232005
MCR011344 | HPR076 | 2019-08-01 | Subcontract | 70132452 | 23847205 | 21693173
MCR011345 | HPR076 | 2019-08-01 | Overhead | 17619854 | 5991296 | 11816383
MCR011346 | HPR076 | 2019-09-01 | Labor | 24681276 | 26252208 | 30106517
MCR011347 | HPR076 | 2019-09-01 | Material | 89655196 | 95361637 | 96417233
MCR011348 | HPR076 | 2019-09-01 | Equipment | 17916688 | 19057063 | 19990246
MCR011349 | HPR076 | 2019-09-01 | Subcontract | 71920739 | 76498404 | 77273576
MCR011350 | HPR076 | 2019-09-01 | Overhead | 18069138 | 19219216 | 11042797
MCR011351 | HPR076 | 2019-10-01 | Labor | 24752373 | 17622342 | 15052464
MCR011352 | HPR076 | 2019-10-01 | Material | 89913458 | 64013487 | 63761490
MCR011353 | HPR076 | 2019-10-01 | Equipment | 17968299 | 12792451 | 12434928
MCR011354 | HPR076 | 2019-10-01 | Subcontract | 72127915 | 51351148 | 56217413
MCR011355 | HPR076 | 2019-10-01 | Overhead | 18121188 | 12901299 | 11463626
MCR011356 | HPR076 | 2019-11-01 | Labor | 24307260 | 32898371 | 31255406
MCR011357 | HPR076 | 2019-11-01 | Material | 88296576 | 119503949 | 131638462
MCR011358 | HPR076 | 2019-11-01 | Equipment | 17645182 | 23881661 | 23249309
MCR011359 | HPR076 | 2019-11-01 | Subcontract | 70830864 | 95865189 | 91606456
MCR011360 | HPR076 | 2019-11-01 | Overhead | 17795321 | 24084865 | 12112331
MCR011361 | HPR076 | 2019-12-01 | Labor | 23374882 | 12780058 | 13296973
MCR011362 | HPR076 | 2019-12-01 | Material | 84909698 | 46423802 | 47452515
MCR011363 | HPR076 | 2019-12-01 | Equipment | 16968348 | 9277329 | 9321246
MCR011364 | HPR076 | 2019-12-01 | Subcontract | 68113936 | 37240832 | 40909926
MCR011365 | HPR076 | 2019-12-01 | Overhead | 17112728 | 9356268 | 11781605
MCR011366 | HPR076 | 2020-01-01 | Labor | 21987349 | 25138272 | 24139302
MCR011367 | HPR076 | 2020-01-01 | Material | 79869457 | 91315243 | 104581990
MCR011368 | HPR076 | 2020-01-01 | Equipment | 15961107 | 18248432 | 18825641
MCR011369 | HPR076 | 2020-01-01 | Subcontract | 64070691 | 73252416 | 75383558
MCR011370 | HPR076 | 2020-01-01 | Overhead | 16096917 | 18403704 | 11419471
MCR011371 | HPR076 | 2020-02-01 | Labor | 20180764 | 15596454 | 15030596
MCR011372 | HPR076 | 2020-02-01 | Material | 73307004 | 56654412 | 46560832
MCR011373 | HPR076 | 2020-02-01 | Equipment | 14649667 | 11321814 | 12368537
MCR011374 | HPR076 | 2020-02-01 | Subcontract | 58806339 | 45447753 | 51196220
MCR011375 | HPR076 | 2020-02-01 | Overhead | 14774318 | 11418149 | 10614014
MCR011376 | HPR076 | 2020-03-01 | Labor | 17996443 | 15384498 | 16626797
MCR011377 | HPR076 | 2020-03-01 | Material | 65372416 | 55884476 | 61785705
MCR011378 | HPR076 | 2020-03-01 | Equipment | 13064019 | 11167950 | 11275170
MCR011379 | HPR076 | 2020-03-01 | Subcontract | 52441271 | 44830115 | 44597813
MCR011380 | HPR076 | 2020-03-01 | Overhead | 13175178 | 11262976 | 10944536
MCR011381 | HPR076 | 2020-04-01 | Labor | 15482752 | 14503126 | 13566683
MCR011382 | HPR076 | 2020-04-01 | Material | 56241388 | 52682877 | 56429898
MCR011383 | HPR076 | 2020-04-01 | Equipment | 11239275 | 10528143 | 10642789
MCR011384 | HPR076 | 2020-04-01 | Subcontract | 45116428 | 42261817 | 39638191
MCR011385 | HPR076 | 2020-04-01 | Overhead | 11334908 | 10617724 | 12081520
MCR011386 | HPR076 | 2020-05-01 | Labor | 12698104 | 22239764 | 21947675
MCR011387 | HPR076 | 2020-05-01 | Material | 46126099 | 80786359 | 80274404
MCR011388 | HPR076 | 2020-05-01 | Equipment | 9217837 | 16144341 | 16347204
MCR011389 | HPR076 | 2020-05-01 | Subcontract | 37002017 | 64806223 | 63542688
MCR011390 | HPR076 | 2020-05-01 | Overhead | 9296269 | 16281709 | 11511304
MCR011391 | HPR076 | 2020-06-01 | Labor | 9716256 | 14418812 | 15590596
MCR011392 | HPR076 | 2020-06-01 | Material | 35294480 | 52376605 | 53203234
MCR011393 | HPR076 | 2020-06-01 | Equipment | 7053247 | 10466937 | 10256174
MCR011394 | HPR076 | 2020-06-01 | Subcontract | 28312973 | 42016128 | 43135609
MCR011395 | HPR076 | 2020-06-01 | Overhead | 7113261 | 10555998 | 12577543
MCR011396 | HPR076 | 2020-07-01 | Labor | 6637013 | 7875399 | 8614237
MCR011397 | HPR076 | 2020-07-01 | Material | 24109074 | 28607536 | 33125481
MCR011398 | HPR076 | 2020-07-01 | Equipment | 4817956 | 5716928 | 6309667
MCR011399 | HPR076 | 2020-07-01 | Subcontract | 19340122 | 22948755 | 22544319
MCR011400 | HPR076 | 2020-07-01 | Overhead | 4858951 | 5765572 | 12179132
MCR011401 | HPR076 | 2020-08-01 | Labor | 3612993 | 8661270 | 7810141
MCR011402 | HPR076 | 2020-08-01 | Material | 13124266 | 31462227 | 34265861
MCR011403 | HPR076 | 2020-08-01 | Equipment | 2622752 | 6287409 | 6223972
MCR011404 | HPR076 | 2020-08-01 | Subcontract | 10528189 | 25238767 | 24723737
MCR011405 | HPR076 | 2020-08-01 | Overhead | 2645069 | 6340908 | 11807250
MCR011406 | HPR076 | 2020-09-01 | Labor | 962047 | 4874097 | 4595618
MCR011407 | HPR076 | 2020-09-01 | Material | 3494655 | 17705248 | 17707162
MCR011408 | HPR076 | 2020-09-01 | Equipment | 698372 | 3538216 | 2997299
MCR011409 | HPR076 | 2020-09-01 | Subcontract | 2803387 | 14203020 | 17396552
MCR011410 | HPR076 | 2020-09-01 | Overhead | 704314 | 3568321 | 11364769
MCR011411 | HPR076 | 2020-10-01 | Labor | 0 | 6565397 | 6654382
MCR011412 | HPR076 | 2020-10-01 | Material | 0 | 23848928 | 25034934
MCR011413 | HPR076 | 2020-10-01 | Equipment | 0 | 4765968 | 5079410
MCR011414 | HPR076 | 2020-10-01 | Subcontract | 0 | 19131435 | 19426643
MCR011415 | HPR076 | 2020-10-01 | Overhead | 0 | 4806521 | 11236800
MCR011416 | HPR076 | 2020-11-01 | Labor | 0 | 3931786 | 3965969
MCR011417 | HPR076 | 2020-11-01 | Material | 0 | 14282288 | 14610702
MCR011418 | HPR076 | 2020-11-01 | Equipment | 0 | 2854172 | 3104799
MCR011419 | HPR076 | 2020-11-01 | Subcontract | 0 | 11457146 | 11850897
MCR011420 | HPR076 | 2020-11-01 | Overhead | 0 | 2878457 | 11218986
MCR011421 | HPR076 | 2020-12-01 | Labor | 0 | 523880 | 487304
MCR011422 | HPR076 | 2020-12-01 | Material | 0 | 1903004 | 1990777
MCR011423 | HPR076 | 2020-12-01 | Equipment | 0 | 380296 | 342192
MCR011424 | HPR076 | 2020-12-01 | Subcontract | 0 | 1526576 | 804339
MCR011425 | HPR076 | 2020-12-01 | Overhead | 0 | 383532 | 11893098
MCR011426 | HPR077 | 2020-09-01 | Labor | 3882236 | 2510512 | 2623379
MCR011427 | HPR077 | 2020-09-01 | Material | 17973443 | 11622824 | 12831690
MCR011428 | HPR077 | 2020-09-01 | Equipment | 8823942 | 5706148 | 5159741
MCR011429 | HPR077 | 2020-09-01 | Subcontract | 8951784 | 5788819 | 5871732
MCR011430 | HPR077 | 2020-09-01 | Overhead | 4195027 | 2712783 | 18287281
MCR011431 | HPR077 | 2020-10-01 | Labor | 10777036 | 6143033 | 6841229
MCR011432 | HPR077 | 2020-10-01 | Material | 49894036 | 28440171 | 26490275
MCR011433 | HPR077 | 2020-10-01 | Equipment | 24495144 | 13962512 | 15615946
MCR011434 | HPR077 | 2020-10-01 | Subcontract | 24850032 | 14164802 | 13985876
MCR011435 | HPR077 | 2020-10-01 | Overhead | 11645338 | 6637976 | 19634916
MCR011436 | HPR077 | 2020-11-01 | Labor | 16397625 | 14018306 | 13455381
MCR011437 | HPR077 | 2020-11-01 | Material | 75915467 | 64900022 | 57959812
MCR011438 | HPR077 | 2020-11-01 | Equipment | 37270191 | 31862232 | 36172412
MCR011439 | HPR077 | 2020-11-01 | Subcontract | 37810166 | 32323856 | 37431873
MCR011440 | HPR077 | 2020-11-01 | Overhead | 17718776 | 15147756 | 18315660
MCR011441 | HPR077 | 2020-12-01 | Labor | 20786629 | 12208989 | 12672759
MCR011442 | HPR077 | 2020-12-01 | Material | 96235076 | 56523499 | 56676454
MCR011443 | HPR077 | 2020-12-01 | Equipment | 47245967 | 27749834 | 25116327
MCR011444 | HPR077 | 2020-12-01 | Subcontract | 47930472 | 28151877 | 33204628
MCR011445 | HPR077 | 2020-12-01 | Overhead | 22461402 | 13192664 | 16257147
MCR011446 | HPR077 | 2021-01-01 | Labor | 23989851 | 16891261 | 16199346
MCR011447 | HPR077 | 2021-01-01 | Material | 111064908 | 78200835 | 81708376
MCR011448 | HPR077 | 2021-01-01 | Equipment | 54526574 | 38392177 | 46727234
MCR011449 | HPR077 | 2021-01-01 | Subcontract | 55316561 | 38948407 | 38940107
MCR011450 | HPR077 | 2021-01-01 | Overhead | 25922705 | 18252184 | 19271119
MCR011451 | HPR077 | 2021-02-01 | Labor | 26056850 | 28735556 | 31154871
MCR011452 | HPR077 | 2021-02-01 | Material | 120634420 | 133035920 | 127742970
MCR011453 | HPR077 | 2021-02-01 | Equipment | 59224662 | 65313096 | 70800181
MCR011454 | HPR077 | 2021-02-01 | Subcontract | 60082715 | 66259359 | 69284732
MCR011455 | HPR077 | 2021-02-01 | Overhead | 28156243 | 31050770 | 17805840
MCR011456 | HPR077 | 2021-03-01 | Labor | 27041717 | 30795991 | 28413661
MCR011457 | HPR077 | 2021-03-01 | Material | 125194020 | 142575038 | 157713658
MCR011458 | HPR077 | 2021-03-01 | Equipment | 61463167 | 69996262 | 77934523
MCR011459 | HPR077 | 2021-03-01 | Subcontract | 62353652 | 71010376 | 83011352
MCR011460 | HPR077 | 2021-03-01 | Overhead | 29220460 | 33277214 | 17702630
MCR011461 | HPR077 | 2021-04-01 | Labor | 27004091 | 21466844 | 22250644
MCR011462 | HPR077 | 2021-04-01 | Material | 125019822 | 99384238 | 91881553
MCR011463 | HPR077 | 2021-04-01 | Equipment | 61377646 | 48792028 | 44137499
MCR011464 | HPR077 | 2021-04-01 | Subcontract | 62266892 | 49498932 | 45074384
MCR011465 | HPR077 | 2021-04-01 | Overhead | 29179801 | 23196420 | 18555465
MCR011466 | HPR077 | 2021-05-01 | Labor | 26010584 | 24050464 | 22030339
MCR011467 | HPR077 | 2021-05-01 | Material | 120420223 | 111345527 | 114733178
MCR011468 | HPR077 | 2021-05-01 | Equipment | 59119504 | 54664342 | 55197550
MCR011469 | HPR077 | 2021-05-01 | Subcontract | 59976034 | 55456325 | 60067118
MCR011470 | HPR077 | 2021-05-01 | Overhead | 28106249 | 25988202 | 18873148
MCR011471 | HPR077 | 2021-06-01 | Labor | 24136831 | 25182930 | 26279993
MCR011472 | HPR077 | 2021-06-01 | Material | 111745380 | 116588464 | 131569029
MCR011473 | HPR077 | 2021-06-01 | Equipment | 54860647 | 57238327 | 57682783
MCR011474 | HPR077 | 2021-06-01 | Subcontract | 55655474 | 58067602 | 64707000
MCR011475 | HPR077 | 2021-06-01 | Overhead | 26081528 | 27211911 | 18705665
MCR011476 | HPR077 | 2021-07-01 | Labor | 21470576 | 11311410 | 9295199
MCR011477 | HPR077 | 2021-07-01 | Material | 99401517 | 52368007 | 48322461
MCR011478 | HPR077 | 2021-07-01 | Equipment | 48800510 | 25709723 | 26935740
MCR011479 | HPR077 | 2021-07-01 | Subcontract | 49507538 | 26082208 | 21760177
MCR011480 | HPR077 | 2021-07-01 | Overhead | 23200453 | 12222766 | 19265237
MCR011481 | HPR077 | 2021-08-01 | Labor | 18116655 | 11797352 | 11262789
MCR011482 | HPR077 | 2021-08-01 | Material | 83873997 | 54617755 | 65274905
MCR011483 | HPR077 | 2021-08-01 | Equipment | 41177378 | 26814222 | 27515425
MCR011484 | HPR077 | 2021-08-01 | Subcontract | 41773961 | 27202709 | 35353835
MCR011485 | HPR077 | 2021-08-01 | Overhead | 19576308 | 12747861 | 18614056
MCR011486 | HPR077 | 2021-09-01 | Labor | 14205760 | 21763836 | 21871479
MCR011487 | HPR077 | 2021-09-01 | Material | 65767874 | 100759211 | 88097532
MCR011488 | HPR077 | 2021-09-01 | Equipment | 32288298 | 49467061 | 49675331
MCR011489 | HPR077 | 2021-09-01 | Subcontract | 32756095 | 50183745 | 47845291
MCR011490 | HPR077 | 2021-09-01 | Overhead | 15350314 | 23517341 | 18939255
MCR011491 | HPR077 | 2021-10-01 | Labor | 9911951 | 16764801 | 15925351
MCR011492 | HPR077 | 2021-10-01 | Material | 45888987 | 77615367 | 89562436
MCR011493 | HPR077 | 2021-10-01 | Equipment | 22528892 | 38104746 | 32259479
MCR011494 | HPR077 | 2021-10-01 | Subcontract | 22855293 | 38656812 | 44194698
MCR011495 | HPR077 | 2021-10-01 | Overhead | 10710554 | 18115535 | 18643084
MCR011496 | HPR077 | 2021-11-01 | Labor | 5496039 | 11570014 | 11233394
MCR011497 | HPR077 | 2021-11-01 | Material | 25444804 | 53565257 | 54679088
MCR011498 | HPR077 | 2021-11-01 | Equipment | 12491956 | 26297505 | 33559668
MCR011499 | HPR077 | 2021-11-01 | Subcontract | 12672941 | 26678506 | 23747044
MCR011500 | HPR077 | 2021-11-01 | Overhead | 5938853 | 12502206 | 18443311
MCR011501 | HPR077 | 2021-12-01 | Labor | 1485299 | 8834359 | 9004806
MCR011502 | HPR077 | 2021-12-01 | Material | 6876435 | 40900100 | 43932998
MCR011503 | HPR077 | 2021-12-01 | Equipment | 3375940 | 20079631 | 21081264
MCR011504 | HPR077 | 2021-12-01 | Subcontract | 3424851 | 20370547 | 27601737
MCR011505 | HPR077 | 2021-12-01 | Overhead | 1604970 | 9546141 | 19513013
MCR011506 | HPR077 | 2022-01-01 | Labor | 0 | 5875582 | 5475228
MCR011507 | HPR077 | 2022-01-01 | Material | 0 | 27201962 | 28011852
MCR011508 | HPR077 | 2022-01-01 | Equipment | 0 | 13354621 | 14402391
MCR011509 | HPR077 | 2022-01-01 | Subcontract | 0 | 13548105 | 11991602
MCR011510 | HPR077 | 2022-01-01 | Overhead | 0 | 6348976 | 18249827
MCR011511 | HPR077 | 2022-02-01 | Labor | 0 | 5681560 | 6127884
MCR011512 | HPR077 | 2022-02-01 | Material | 0 | 26303704 | 25482512
MCR011513 | HPR077 | 2022-02-01 | Equipment | 0 | 12913628 | 13108081
MCR011514 | HPR077 | 2022-02-01 | Subcontract | 0 | 13100722 | 13131880
MCR011515 | HPR077 | 2022-02-01 | Overhead | 0 | 6139321 | 19485759
MCR011516 | HPR077 | 2022-03-01 | Labor | 0 | 1166933 | 1110876
MCR011517 | HPR077 | 2022-03-01 | Material | 0 | 5402506 | 7670903
MCR011518 | HPR077 | 2022-03-01 | Equipment | 0 | 2652324 | 2334552
MCR011519 | HPR077 | 2022-03-01 | Subcontract | 0 | 2690751 | 2738550
MCR011520 | HPR077 | 2022-03-01 | Overhead | 0 | 1260952 | 19649053
MCR011521 | HPR078 | 2020-11-01 | Labor | 2452222 | 1090313 | 1181696
MCR011522 | HPR078 | 2020-11-01 | Material | 5038369 | 2240171 | 2082962
MCR011523 | HPR078 | 2020-11-01 | Equipment | 1228273 | 546118 | 565196
MCR011524 | HPR078 | 2020-11-01 | Subcontract | 7704376 | 3425538 | 3568130
MCR011525 | HPR078 | 2020-11-01 | Overhead | 1546095 | 687428 | 12076229
MCR011526 | HPR078 | 2020-12-01 | Labor | 7058103 | 4300181 | 4290570
MCR011527 | HPR078 | 2020-12-01 | Material | 14501676 | 8835210 | 9632627
MCR011528 | HPR078 | 2020-12-01 | Equipment | 3535274 | 2153882 | 2316452
MCR011529 | HPR078 | 2020-12-01 | Subcontract | 22175105 | 13510281 | 13904940
MCR011530 | HPR078 | 2020-12-01 | Overhead | 4450045 | 2711210 | 11905837
MCR011531 | HPR078 | 2021-01-01 | Labor | 11221629 | 10788481 | 12503885
MCR011532 | HPR078 | 2021-01-01 | Material | 23056114 | 22166162 | 20327005
MCR011533 | HPR078 | 2021-01-01 | Equipment | 5620708 | 5403752 | 5356989
MCR011534 | HPR078 | 2021-01-01 | Subcontract | 35256046 | 33895184 | 31243116
MCR011535 | HPR078 | 2021-01-01 | Overhead | 7075096 | 6802002 | 11294796
MCR011536 | HPR078 | 2021-02-01 | Labor | 14950325 | 9088680 | 10685625
MCR011537 | HPR078 | 2021-02-01 | Material | 30717143 | 18673726 | 22238401
MCR011538 | HPR078 | 2021-02-01 | Equipment | 7488343 | 4552353 | 5040316
MCR011539 | HPR078 | 2021-02-01 | Subcontract | 46970838 | 28554758 | 31107957
MCR011540 | HPR078 | 2021-02-01 | Overhead | 9425992 | 5730298 | 11571846
MCR011541 | HPR078 | 2021-03-01 | Labor | 18251989 | 21229721 | 20683013
MCR011542 | HPR078 | 2021-03-01 | Material | 37500787 | 43618876 | 43926537
MCR011543 | HPR078 | 2021-03-01 | Equipment | 9142086 | 10633578 | 10589848
MCR011544 | HPR078 | 2021-03-01 | Subcontract | 57343985 | 66699405 | 64265364
MCR011545 | HPR078 | 2021-03-01 | Overhead | 11507649 | 13385072 | 12480269
MCR011546 | HPR078 | 2021-04-01 | Labor | 21134720 | 18974097 | 18725279
MCR011547 | HPR078 | 2021-04-01 | Material | 43423685 | 38984440 | 41124613
MCR011548 | HPR078 | 2021-04-01 | Equipment | 10585993 | 9503777 | 9956287
MCR011549 | HPR078 | 2021-04-01 | Subcontract | 66400931 | 59612700 | 64601868
MCR011550 | HPR078 | 2021-04-01 | Overhead | 13325175 | 11962929 | 13230308
MCR011551 | HPR078 | 2021-05-01 | Labor | 23606941 | 17533788 | 22137774
MCR011552 | HPR078 | 2021-05-01 | Material | 48503146 | 36025162 | 37494118
MCR011553 | HPR078 | 2021-05-01 | Equipment | 11824284 | 8782353 | 9862758
MCR011554 | HPR078 | 2021-05-01 | Subcontract | 74168142 | 55087547 | 61604338
MCR011555 | HPR078 | 2021-05-01 | Overhead | 14883879 | 11054833 | 10553535
MCR011556 | HPR078 | 2021-06-01 | Labor | 25677434 | 23060052 | 26469363
MCR011557 | HPR078 | 2021-06-01 | Material | 52757209 | 47379499 | 56557123
MCR011558 | HPR078 | 2021-06-01 | Equipment | 12861356 | 11550357 | 11304024
MCR011559 | HPR078 | 2021-06-01 | Subcontract | 80673203 | 72449927 | 75749848
MCR011560 | HPR078 | 2021-06-01 | Overhead | 16189299 | 14539072 | 11960670
MCR011561 | HPR078 | 2021-07-01 | Labor | 27355371 | 7659037 | 6105582
MCR011562 | HPR078 | 2021-07-01 | Material | 56204722 | 15736363 | 12127776
MCR011563 | HPR078 | 2021-07-01 | Equipment | 13701804 | 3836271 | 3557133
MCR011564 | HPR078 | 2021-07-01 | Subcontract | 85944936 | 24063116 | 22902071
MCR011565 | HPR078 | 2021-07-01 | Overhead | 17247217 | 4828927 | 13077497
MCR011566 | HPR078 | 2021-08-01 | Labor | 28650360 | 19359155 | 20261098
MCR011567 | HPR078 | 2021-08-01 | Material | 58865423 | 39775586 | 43043254
MCR011568 | HPR078 | 2021-08-01 | Equipment | 14350440 | 9696646 | 10908986
MCR011569 | HPR078 | 2021-08-01 | Subcontract | 90013523 | 60822473 | 72018489
MCR011570 | HPR078 | 2021-08-01 | Overhead | 18063691 | 12205704 | 12158720
MCR011571 | HPR078 | 2021-09-01 | Labor | 29572488 | 16821182 | 18463717
MCR011572 | HPR078 | 2021-09-01 | Material | 60760040 | 34561031 | 35670270
MCR011573 | HPR078 | 2021-09-01 | Equipment | 14812317 | 8425421 | 7258943
MCR011574 | HPR078 | 2021-09-01 | Subcontract | 92910659 | 52848684 | 48260380
MCR011575 | HPR078 | 2021-09-01 | Overhead | 18645081 | 10605543 | 11886048
MCR011576 | HPR078 | 2021-10-01 | Labor | 30132383 | 17399720 | 18742241
MCR011577 | HPR078 | 2021-10-01 | Material | 61910407 | 35749704 | 39240710
MCR011578 | HPR078 | 2021-10-01 | Equipment | 15092758 | 8715201 | 10275250
MCR011579 | HPR078 | 2021-10-01 | Subcontract | 94669733 | 54666333 | 50865442
MCR011580 | HPR078 | 2021-10-01 | Overhead | 18998088 | 10970305 | 12067191
MCR011581 | HPR078 | 2021-11-01 | Labor | 30341277 | 29123957 | 35182346
MCR011582 | HPR078 | 2021-11-01 | Material | 62339605 | 59838482 | 68116779
MCR011583 | HPR078 | 2021-11-01 | Equipment | 15197389 | 14587656 | 14923847
MCR011584 | HPR078 | 2021-11-01 | Subcontract | 95326037 | 91501467 | 100940422
MCR011585 | HPR078 | 2021-11-01 | Overhead | 19129793 | 18362288 | 12858036
MCR011586 | HPR078 | 2021-12-01 | Labor | 30211092 | 20943869 | 23376936
MCR011587 | HPR078 | 2021-12-01 | Material | 62072124 | 43031561 | 39584960
MCR011588 | HPR078 | 2021-12-01 | Equipment | 15132182 | 10490400 | 10341443
MCR011589 | HPR078 | 2021-12-01 | Subcontract | 94917021 | 65801318 | 72027983
MCR011590 | HPR078 | 2021-12-01 | Overhead | 19047713 | 13204846 | 12152874
MCR011591 | HPR078 | 2022-01-01 | Labor | 29754531 | 41903303 | 49970377
MCR011592 | HPR078 | 2022-01-01 | Material | 61134069 | 86095102 | 99060641
MCR011593 | HPR078 | 2022-01-01 | Equipment | 14903499 | 20988596 | 21864472
MCR011594 | HPR078 | 2022-01-01 | Subcontract | 93482602 | 131651538 | 131904364
MCR011595 | HPR078 | 2022-01-01 | Overhead | 18759858 | 26419505 | 11203754
MCR011596 | HPR078 | 2022-02-01 | Labor | 28985206 | 23293635 | 24215642
MCR011597 | HPR078 | 2022-02-01 | Material | 59553403 | 47859423 | 49159144
MCR011598 | HPR078 | 2022-02-01 | Equipment | 14518158 | 11667354 | 13892291
MCR011599 | HPR078 | 2022-02-01 | Subcontract | 91065542 | 73183798 | 62101819
MCR011600 | HPR078 | 2022-02-01 | Overhead | 18274808 | 14686344 | 13182904
MCR011601 | HPR078 | 2022-03-01 | Labor | 27917784 | 29766269 | 31375271
MCR011602 | HPR078 | 2022-03-01 | Material | 57360262 | 61158185 | 58033189
MCR011603 | HPR078 | 2022-03-01 | Equipment | 13983506 | 14909378 | 16049260
MCR011604 | HPR078 | 2022-03-01 | Subcontract | 87711920 | 93519480 | 108595089
MCR011605 | HPR078 | 2022-03-01 | Overhead | 17601811 | 18767258 | 13116847
MCR011606 | HPR078 | 2022-04-01 | Labor | 26568177 | 24646961 | 29196283
MCR011607 | HPR078 | 2022-04-01 | Material | 54587341 | 50639985 | 63063313
MCR011608 | HPR078 | 2022-04-01 | Equipment | 13307512 | 12345211 | 14078865
MCR011609 | HPR078 | 2022-04-01 | Subcontract | 83471733 | 77435669 | 67469170
MCR011610 | HPR078 | 2022-04-01 | Overhead | 16750901 | 15539599 | 11808446
MCR011611 | HPR078 | 2022-05-01 | Labor | 24953792 | 14967691 | 17957209
MCR011612 | HPR078 | 2022-05-01 | Material | 51270405 | 30752824 | 26481161
MCR011613 | HPR078 | 2022-05-01 | Equipment | 12498897 | 7497042 | 5767954
MCR011614 | HPR078 | 2022-05-01 | Subcontract | 78399670 | 47025400 | 58605899
MCR011615 | HPR078 | 2022-05-01 | Overhead | 15733052 | 9436941 | 11756309
MCR011616 | HPR078 | 2022-06-01 | Labor | 23093857 | 16530498 | 17117991
MCR011617 | HPR078 | 2022-06-01 | Material | 47448955 | 33963788 | 43529525
MCR011618 | HPR078 | 2022-06-01 | Equipment | 11567289 | 8279823 | 9285998
MCR011619 | HPR078 | 2022-06-01 | Subcontract | 72556136 | 51935415 | 55382665
MCR011620 | HPR078 | 2022-06-01 | Overhead | 14560386 | 10422271 | 12683216
MCR011621 | HPR078 | 2022-07-01 | Labor | 21009857 | 16393321 | 16549653
MCR011622 | HPR078 | 2022-07-01 | Material | 43167141 | 33681942 | 30273779
MCR011623 | HPR078 | 2022-07-01 | Equipment | 10523452 | 8211114 | 8244048
MCR011624 | HPR078 | 2022-07-01 | Subcontract | 66008638 | 51504434 | 53821904
MCR011625 | HPR078 | 2022-07-01 | Overhead | 13246450 | 10335782 | 11938207
MCR011626 | HPR078 | 2022-08-01 | Labor | 18726162 | 9325735 | 31403441
MCR011627 | HPR078 | 2022-08-01 | Material | 38475029 | 19160783 | 35107100
MCR011628 | HPR078 | 2022-08-01 | Equipment | 9379591 | 4671090 | 5424125
MCR011629 | HPR078 | 2022-08-01 | Subcontract | 58833739 | 29299536 | 30350555
MCR011630 | HPR078 | 2022-08-01 | Overhead | 11806609 | 5879759 | 11898728
MCR011631 | HPR078 | 2022-09-01 | Labor | 16270925 | 24452272 | 56927246
MCR011632 | HPR078 | 2022-09-01 | Material | 33430466 | 50239974 | 84953293
MCR011633 | HPR078 | 2022-09-01 | Equipment | 8149808 | 12247694 | 11255200
MCR011634 | HPR078 | 2022-09-01 | Subcontract | 51119891 | 76823997 | 71980599
MCR011635 | HPR078 | 2022-09-01 | Overhead | 10258613 | 15416850 | 12067228
MCR011636 | HPR078 | 2022-10-01 | Labor | 13677470 | 18083780 | 19573352
MCR011637 | HPR078 | 2022-10-01 | Material | 28101917 | 37155182 | 38292487
MCR011638 | HPR078 | 2022-10-01 | Equipment | 6850794 | 9057833 | 10174656
MCR011639 | HPR078 | 2022-10-01 | Subcontract | 42971789 | 56815507 | 68493595
MCR011640 | HPR078 | 2022-10-01 | Overhead | 8623472 | 11401595 | 12224236
MCR011641 | HPR078 | 2022-11-01 | Labor | 10986552 | 21640396 | 25009547
MCR011642 | HPR078 | 2022-11-01 | Material | 22573121 | 44462654 | 46559040
MCR011643 | HPR078 | 2022-11-01 | Equipment | 5502962 | 10839277 | 11526326
MCR011644 | HPR078 | 2022-11-01 | Subcontract | 34517482 | 67989661 | 63084014
MCR011645 | HPR078 | 2022-11-01 | Overhead | 6926883 | 13643997 | 11737672
MCR011646 | HPR078 | 2022-12-01 | Labor | 8250409 | 21464279 | 20088001
MCR011647 | HPR078 | 2022-12-01 | Material | 16951403 | 44100802 | 45110040
MCR011648 | HPR078 | 2022-12-01 | Equipment | 4132478 | 10751063 | 11248400
MCR011649 | HPR078 | 2022-12-01 | Subcontract | 25921083 | 67436338 | 71751459
MCR011650 | HPR078 | 2022-12-01 | Overhead | 5201779 | 13532958 | 11850821
MCR011651 | HPR078 | 2023-01-01 | Labor | 5540985 | 11264176 | 15706139
MCR011652 | HPR078 | 2023-01-01 | Material | 11384583 | 23143531 | 24714632
MCR011653 | HPR078 | 2023-01-01 | Equipment | 2775378 | 5642019 | 6005336
MCR011654 | HPR078 | 2023-01-01 | Subcontract | 17408631 | 35389718 | 37629488
MCR011655 | HPR078 | 2023-01-01 | Overhead | 3493521 | 7101921 | 12662526
MCR011656 | HPR078 | 2023-02-01 | Labor | 2970733 | 14227701 | 16616839
MCR011657 | HPR078 | 2023-02-01 | Material | 6103709 | 29232429 | 33281570
MCR011658 | HPR078 | 2023-02-01 | Equipment | 1487986 | 7126394 | 6303777
MCR011659 | HPR078 | 2023-02-01 | Subcontract | 9333431 | 44700502 | 39556747
MCR011660 | HPR078 | 2023-02-01 | Overhead | 1873010 | 8970386 | 11990166
MCR011661 | HPR078 | 2023-03-01 | Labor | 781092 | 19866894 | 24794346
MCR011662 | HPR078 | 2023-03-01 | Material | 1604842 | 40818794 | 39679053
MCR011663 | HPR078 | 2023-03-01 | Equipment | 391235 | 9950963 | 11146410
MCR011664 | HPR078 | 2023-03-01 | Subcontract | 2454029 | 62417685 | 69820265
MCR011665 | HPR078 | 2023-03-01 | Overhead | 492469 | 12525827 | 12179238
MCR011666 | HPR078 | 2023-04-01 | Labor | 0 | 8923443 | 8657120
MCR011667 | HPR078 | 2023-04-01 | Material | 0 | 18334229 | 20440696
MCR011668 | HPR078 | 2023-04-01 | Equipment | 0 | 4469589 | 4230495
MCR011669 | HPR078 | 2023-04-01 | Subcontract | 0 | 28035618 | 23932449
MCR011670 | HPR078 | 2023-04-01 | Overhead | 0 | 5626119 | 12254900
MCR011671 | HPR078 | 2023-05-01 | Labor | 0 | 5385727 | 6743122
MCR011672 | HPR078 | 2023-05-01 | Material | 0 | 11065590 | 11296577
MCR011673 | HPR078 | 2023-05-01 | Equipment | 0 | 2697612 | 2933557
MCR011674 | HPR078 | 2023-05-01 | Subcontract | 0 | 16920845 | 17695658
MCR011675 | HPR078 | 2023-05-01 | Overhead | 0 | 3395633 | 12683880
MCR011676 | HPR078 | 2023-06-01 | Labor | 0 | 6594570 | 7988305
MCR011677 | HPR078 | 2023-06-01 | Material | 0 | 13549294 | 15154783
MCR011678 | HPR078 | 2023-06-01 | Equipment | 0 | 3303099 | 3928318
MCR011679 | HPR078 | 2023-06-01 | Subcontract | 0 | 20718779 | 21455985
MCR011680 | HPR078 | 2023-06-01 | Overhead | 0 | 4157793 | 12091157
MCR011681 | HPR078 | 2023-07-01 | Labor | 0 | 5467411 | 6090025
MCR011682 | HPR078 | 2023-07-01 | Material | 0 | 11233417 | 12910848
MCR011683 | HPR078 | 2023-07-01 | Equipment | 0 | 2738526 | 2724579
MCR011684 | HPR078 | 2023-07-01 | Subcontract | 0 | 17177477 | 16991491
MCR011685 | HPR078 | 2023-07-01 | Overhead | 0 | 3447134 | 13513130
MCR011686 | HPR078 | 2023-08-01 | Labor | 0 | 3452198 | 3364495
MCR011687 | HPR078 | 2023-08-01 | Material | 0 | 7092933 | 6328765
MCR011688 | HPR078 | 2023-08-01 | Equipment | 0 | 1729142 | 1901217
MCR011689 | HPR078 | 2023-08-01 | Subcontract | 0 | 10846093 | 12738038
MCR011690 | HPR078 | 2023-08-01 | Overhead | 0 | 2176567 | 13132515
MCR011691 | HPR078 | 2023-09-01 | Labor | 0 | 2849236 | 3411174
MCR011692 | HPR078 | 2023-09-01 | Material | 0 | 5854079 | 6417727
MCR011693 | HPR078 | 2023-09-01 | Equipment | 0 | 1427130 | 1792070
MCR011694 | HPR078 | 2023-09-01 | Subcontract | 0 | 8951711 | 8734094
MCR011695 | HPR078 | 2023-09-01 | Overhead | 0 | 1796407 | 12253346
MCR011696 | HPR078 | 2023-10-01 | Labor | 0 | 1914543 | 2363725
MCR011697 | HPR078 | 2023-10-01 | Material | 0 | 3933646 | 4373883
MCR011698 | HPR078 | 2023-10-01 | Equipment | 0 | 958959 | 1240823
MCR011699 | HPR078 | 2023-10-01 | Subcontract | 0 | 6015099 | 4849793
MCR011700 | HPR078 | 2023-10-01 | Overhead | 0 | 1207095 | 11488234
MCR011701 | HPR078 | 2023-11-01 | Labor | 0 | 317596 | 292853
MCR011702 | HPR078 | 2023-11-01 | Material | 0 | 652537 | 577027
MCR011703 | HPR078 | 2023-11-01 | Equipment | 0 | 159078 | 97217
MCR011704 | HPR078 | 2023-11-01 | Subcontract | 0 | 997822 | 1519644
MCR011705 | HPR078 | 2023-11-01 | Overhead | 0 | 200240 | 12999292
MCR011706 | HPR079 | 2017-12-01 | Labor | 1796584 | 1265920 | 1180452
MCR011707 | HPR079 | 2017-12-01 | Material | 4889602 | 3445342 | 3561919
MCR011708 | HPR079 | 2017-12-01 | Equipment | 1417680 | 998935 | 931447
MCR011709 | HPR079 | 2017-12-01 | Subcontract | 5381028 | 3791614 | 4165329
MCR011710 | HPR079 | 2017-12-01 | Overhead | 1066108 | 751208 | 6690145
MCR011711 | HPR079 | 2018-01-01 | Labor | 5099719 | 4808528 | 5305222
MCR011712 | HPR079 | 2018-01-01 | Material | 13879449 | 13086939 | 12329950
MCR011713 | HPR079 | 2018-01-01 | Equipment | 4024176 | 3794397 | 4051933
MCR011714 | HPR079 | 2018-01-01 | Subcontract | 15274396 | 14402235 | 13297338
MCR011715 | HPR079 | 2018-01-01 | Overhead | 3026217 | 2853421 | 6677682
MCR011716 | HPR079 | 2018-02-01 | Labor | 7974956 | 5905790 | 5878338
MCR011717 | HPR079 | 2018-02-01 | Material | 21704724 | 16073258 | 18886164
MCR011718 | HPR079 | 2018-02-01 | Equipment | 6293018 | 4660244 | 4887637
MCR011719 | HPR079 | 2018-02-01 | Subcontract | 23886145 | 17688692 | 19565033
MCR011720 | HPR079 | 2018-02-01 | Overhead | 4732407 | 3504546 | 6189627
MCR011721 | HPR079 | 2018-03-01 | Labor | 10432193 | 7851514 | 8439630
MCR011722 | HPR079 | 2018-03-01 | Material | 28392363 | 21368761 | 22608001
MCR011723 | HPR079 | 2018-03-01 | Equipment | 8232017 | 6195610 | 6250846
MCR011724 | HPR079 | 2018-03-01 | Subcontract | 31245923 | 23516417 | 23718366
MCR011725 | HPR079 | 2018-03-01 | Overhead | 6190552 | 4659155 | 6046056
MCR011726 | HPR079 | 2018-04-01 | Labor | 12481825 | 10511902 | 10458799
MCR011727 | HPR079 | 2018-04-01 | Material | 33970663 | 28609300 | 26505435
MCR011728 | HPR079 | 2018-04-01 | Equipment | 9849377 | 8294915 | 8679426
MCR011729 | HPR079 | 2018-04-01 | Subcontract | 37384867 | 31484662 | 27362086
MCR011730 | HPR079 | 2018-04-01 | Overhead | 7406821 | 6237852 | 6485017
MCR011731 | HPR079 | 2018-05-01 | Labor | 14134808 | 10660288 | 11692730
MCR011732 | HPR079 | 2018-05-01 | Material | 38469438 | 29013149 | 29976652
MCR011733 | HPR079 | 2018-05-01 | Equipment | 11153741 | 8412006 | 9000406
MCR011734 | HPR079 | 2018-05-01 | Subcontract | 42335789 | 31929100 | 39079099
MCR011735 | HPR079 | 2018-05-01 | Overhead | 8387715 | 6325905 | 6110369
MCR011736 | HPR079 | 2018-06-01 | Labor | 15402727 | 7465085 | 8488904
MCR011737 | HPR079 | 2018-06-01 | Material | 41920221 | 20317052 | 21567497
MCR011738 | HPR079 | 2018-06-01 | Equipment | 12154253 | 5890680 | 5835639
MCR011739 | HPR079 | 2018-06-01 | Subcontract | 46133390 | 22359006 | 19212518
MCR011740 | HPR079 | 2018-06-01 | Overhead | 9140109 | 4429845 | 6228925
MCR011741 | HPR079 | 2018-07-01 | Labor | 16297887 | 11208802 | 11807943
MCR011742 | HPR079 | 2018-07-01 | Material | 44356497 | 30505991 | 30795087
MCR011743 | HPR079 | 2018-07-01 | Equipment | 12860622 | 8844837 | 9977021
MCR011744 | HPR079 | 2018-07-01 | Subcontract | 48814524 | 33571980 | 30558932
MCR011745 | HPR079 | 2018-07-01 | Overhead | 9671305 | 6651398 | 6695818
MCR011746 | HPR079 | 2018-08-01 | Labor | 16833416 | 17140057 | 19748182
MCR011747 | HPR079 | 2018-08-01 | Material | 45814000 | 46648556 | 50143132
MCR011748 | HPR079 | 2018-08-01 | Equipment | 13283206 | 13525176 | 12226249
MCR011749 | HPR079 | 2018-08-01 | Subcontract | 50418512 | 51336945 | 59812050
MCR011750 | HPR079 | 2018-08-01 | Overhead | 9989092 | 10171055 | 6408172
MCR011751 | HPR079 | 2018-09-01 | Labor | 17023401 | 13190808 | 13755438
MCR011752 | HPR079 | 2018-09-01 | Material | 46331065 | 35900240 | 35805589
MCR011753 | HPR079 | 2018-09-01 | Equipment | 13433123 | 10408834 | 11206406
MCR011754 | HPR079 | 2018-09-01 | Subcontract | 50987544 | 39508374 | 31382602
MCR011755 | HPR079 | 2018-09-01 | Overhead | 10101831 | 7827538 | 6277264
MCR011756 | HPR079 | 2018-10-01 | Labor | 16883053 | 12214421 | 11191485
MCR011757 | HPR079 | 2018-10-01 | Material | 45949091 | 33242893 | 34361938
MCR011758 | HPR079 | 2018-10-01 | Equipment | 13322375 | 9638369 | 10555052
MCR011759 | HPR079 | 2018-10-01 | Subcontract | 50567180 | 36583952 | 37396342
MCR011760 | HPR079 | 2018-10-01 | Overhead | 10018547 | 7248141 | 6362601
MCR011761 | HPR079 | 2018-11-01 | Labor | 16428923 | 11727272 | 13398919
MCR011762 | HPR079 | 2018-11-01 | Material | 44713125 | 31917065 | 38331029
MCR011763 | HPR079 | 2018-11-01 | Equipment | 12964021 | 9253961 | 8995210
MCR011764 | HPR079 | 2018-11-01 | Subcontract | 49206994 | 35124873 | 41360739
MCR011765 | HPR079 | 2018-11-01 | Overhead | 9749062 | 6959063 | 7265751
MCR011766 | HPR079 | 2018-12-01 | Labor | 15679185 | 16249844 | 15582294
MCR011767 | HPR079 | 2018-12-01 | Material | 42672632 | 44225742 | 43453867
MCR011768 | HPR079 | 2018-12-01 | Equipment | 12372406 | 12822711 | 12936568
MCR011769 | HPR079 | 2018-12-01 | Subcontract | 46961422 | 48670627 | 46605707
MCR011770 | HPR079 | 2018-12-01 | Overhead | 9304162 | 9642795 | 6820261
MCR011771 | HPR079 | 2019-01-01 | Labor | 14654022 | 27946498 | 29218048
MCR011772 | HPR079 | 2019-01-01 | Material | 39882538 | 76059477 | 81705273
MCR011773 | HPR079 | 2019-01-01 | Equipment | 11563452 | 22052511 | 19763155
MCR011774 | HPR079 | 2019-01-01 | Subcontract | 43890912 | 83703794 | 88112852
MCR011775 | HPR079 | 2019-01-01 | Overhead | 8695821 | 16583689 | 5945114
MCR011776 | HPR079 | 2019-02-01 | Labor | 13376156 | 11651821 | 13467364
MCR011777 | HPR079 | 2019-02-01 | Material | 36404683 | 31711716 | 31853946
MCR011778 | HPR079 | 2019-02-01 | Equipment | 10555091 | 9194423 | 10292322
MCR011779 | HPR079 | 2019-02-01 | Subcontract | 40063517 | 34898885 | 35846403
MCR011780 | HPR079 | 2019-02-01 | Overhead | 7937524 | 6914290 | 5892788
MCR011781 | HPR079 | 2019-03-01 | Labor | 11871620 | 12687203 | 12182287
MCR011782 | HPR079 | 2019-03-01 | Material | 32309924 | 34529623 | 31218920
MCR011783 | HPR079 | 2019-03-01 | Equipment | 9367866 | 10011440 | 10628506
MCR011784 | HPR079 | 2019-03-01 | Subcontract | 35557216 | 38000005 | 39239588
MCR011785 | HPR079 | 2019-03-01 | Overhead | 7044720 | 7528694 | 6618494
MCR011786 | HPR079 | 2019-04-01 | Labor | 10170944 | 9516213 | 10349645
MCR011787 | HPR079 | 2019-04-01 | Material | 27681347 | 25899424 | 30886238
MCR011788 | HPR079 | 2019-04-01 | Equipment | 8025867 | 7509220 | 7869993
MCR011789 | HPR079 | 2019-04-01 | Subcontract | 30463446 | 28502432 | 25008941
MCR011790 | HPR079 | 2019-04-01 | Overhead | 6035525 | 5647002 | 6185241
MCR011791 | HPR079 | 2019-05-01 | Labor | 8311063 | 12529343 | 12144929
MCR011792 | HPR079 | 2019-05-01 | Material | 22619476 | 34099988 | 36941833
MCR011793 | HPR079 | 2019-05-01 | Equipment | 6558239 | 9886873 | 9866959
MCR011794 | HPR079 | 2019-05-01 | Subcontract | 24892834 | 37527189 | 44458160
MCR011795 | HPR079 | 2019-05-01 | Overhead | 4931856 | 7435018 | 6182686
MCR011796 | HPR079 | 2019-06-01 | Labor | 6338720 | 7063624 | 6473716
MCR011797 | HPR079 | 2019-06-01 | Material | 17251524 | 19224431 | 18495063
MCR011798 | HPR079 | 2019-06-01 | Equipment | 5001868 | 5573888 | 6320772
MCR011799 | HPR079 | 2019-06-01 | Subcontract | 18985380 | 21156572 | 18375192
MCR011800 | HPR079 | 2019-06-01 | Overhead | 3761450 | 4191614 | 6588120
MCR011801 | HPR079 | 2019-07-01 | Labor | 4317328 | 6029977 | 6625017
MCR011802 | HPR079 | 2019-07-01 | Material | 11750085 | 16411247 | 16862386
MCR011803 | HPR079 | 2019-07-01 | Equipment | 3406793 | 4758240 | 5563917
MCR011804 | HPR079 | 2019-07-01 | Subcontract | 12931021 | 18060651 | 18608999
MCR011805 | HPR079 | 2019-07-01 | Overhead | 2561939 | 3578239 | 6392857
MCR011806 | HPR079 | 2019-08-01 | Labor | 2344185 | 7463237 | 7612312
MCR011807 | HPR079 | 2019-08-01 | Material | 6379957 | 20312022 | 25047815
MCR011808 | HPR079 | 2019-08-01 | Equipment | 1849790 | 5889221 | 5757258
MCR011809 | HPR079 | 2019-08-01 | Subcontract | 7021171 | 22353471 | 22187997
MCR011810 | HPR079 | 2019-08-01 | Overhead | 1391059 | 4428748 | 6242800
MCR011811 | HPR079 | 2019-09-01 | Labor | 622880 | 5312692 | 5880228
MCR011812 | HPR079 | 2019-09-01 | Material | 1695237 | 14459078 | 15290727
MCR011813 | HPR079 | 2019-09-01 | Equipment | 491513 | 4192232 | 4034532
MCR011814 | HPR079 | 2019-09-01 | Subcontract | 1865616 | 15912280 | 17378786
MCR011815 | HPR079 | 2019-09-01 | Overhead | 369622 | 3152597 | 6580274
MCR011816 | HPR079 | 2019-10-01 | Labor | 0 | 4938541 | 5178719
MCR011817 | HPR079 | 2019-10-01 | Material | 0 | 13440784 | 12609881
MCR011818 | HPR079 | 2019-10-01 | Equipment | 0 | 3896990 | 4340216
MCR011819 | HPR079 | 2019-10-01 | Subcontract | 0 | 14791643 | 15298174
MCR011820 | HPR079 | 2019-10-01 | Overhead | 0 | 2930572 | 5925038
MCR011821 | HPR079 | 2019-11-01 | Labor | 0 | 2450546 | 2237468
MCR011822 | HPR079 | 2019-11-01 | Material | 0 | 6669431 | 7496610
MCR011823 | HPR079 | 2019-11-01 | Equipment | 0 | 1933720 | 1896671
MCR011824 | HPR079 | 2019-11-01 | Subcontract | 0 | 7339739 | 6887668
MCR011825 | HPR079 | 2019-11-01 | Overhead | 0 | 1454175 | 6798826
MCR011826 | HPR079 | 2019-12-01 | Labor | 0 | 685672 | 855708
MCR011827 | HPR079 | 2019-12-01 | Material | 0 | 1866133 | 2109052
MCR011828 | HPR079 | 2019-12-01 | Equipment | 0 | 541062 | 502875
MCR011829 | HPR079 | 2019-12-01 | Subcontract | 0 | 2053688 | 2155754
MCR011830 | HPR079 | 2019-12-01 | Overhead | 0 | 406884 | 6830823
MCR011831 | HPR080 | 2019-03-01 | Labor | 8121770 | 7836934 | 7300946
MCR011832 | HPR080 | 2019-03-01 | Material | 21663375 | 20903626 | 21817434
MCR011833 | HPR080 | 2019-03-01 | Equipment | 5702301 | 5502318 | 5130616
MCR011834 | HPR080 | 2019-03-01 | Subcontract | 20283546 | 19572189 | 19250720
MCR011835 | HPR080 | 2019-03-01 | Overhead | 4442641 | 4286834 | 15561941
MCR011836 | HPR080 | 2019-04-01 | Labor | 21912080 | 20482270 | 20521592
MCR011837 | HPR080 | 2019-04-01 | Material | 58446571 | 54632808 | 68773141
MCR011838 | HPR080 | 2019-04-01 | Equipment | 15384489 | 14380619 | 13558071
MCR011839 | HPR080 | 2019-04-01 | Subcontract | 54723871 | 51153022 | 53310297
MCR011840 | HPR080 | 2019-04-01 | Overhead | 11985995 | 11203884 | 15575396
MCR011841 | HPR080 | 2019-05-01 | Labor | 32140530 | 31302101 | 35044547
MCR011842 | HPR080 | 2019-05-01 | Material | 85729140 | 83492780 | 78163510
MCR011843 | HPR080 | 2019-05-01 | Equipment | 22565892 | 21977231 | 24849856
MCR011844 | HPR080 | 2019-05-01 | Subcontract | 80268702 | 78174785 | 72235301
MCR011845 | HPR080 | 2019-05-01 | Overhead | 17580998 | 17122374 | 14260980
MCR011846 | HPR080 | 2019-06-01 | Labor | 38976752 | 51106539 | 46998439
MCR011847 | HPR080 | 2019-06-01 | Material | 103963544 | 136317592 | 136324852
MCR011848 | HPR080 | 2019-06-01 | Equipment | 27365609 | 35881943 | 36207929
MCR011849 | HPR080 | 2019-06-01 | Subcontract | 97341683 | 127634969 | 127777715
MCR011850 | HPR080 | 2019-06-01 | Overhead | 21320439 | 27955481 | 15349787
MCR011851 | HPR080 | 2019-07-01 | Labor | 42608975 | 27349205 | 46188251
MCR011852 | HPR080 | 2019-07-01 | Material | 113651851 | 72949134 | 93036656
MCR011853 | HPR080 | 2019-07-01 | Equipment | 29915795 | 19201899 | 16624394
MCR011854 | HPR080 | 2019-07-01 | Subcontract | 106412902 | 68302707 | 74677742
MCR011855 | HPR080 | 2019-07-01 | Overhead | 23307279 | 14960124 | 15659636
MCR011856 | HPR080 | 2019-08-01 | Labor | 43249285 | 25781847 | 45956577
MCR011857 | HPR080 | 2019-08-01 | Material | 115359766 | 68768486 | 76836791
MCR011858 | HPR080 | 2019-08-01 | Equipment | 30365358 | 18101456 | 19023942
MCR011859 | HPR080 | 2019-08-01 | Subcontract | 108012033 | 64388341 | 51062617
MCR011860 | HPR080 | 2019-08-01 | Overhead | 23657532 | 14102773 | 16084359
MCR011861 | HPR080 | 2019-09-01 | Labor | 41141516 | 46036586 | 51877316
MCR011862 | HPR080 | 2019-09-01 | Material | 109737666 | 122794393 | 134841160
MCR011863 | HPR080 | 2019-09-01 | Equipment | 28885491 | 32322324 | 31650875
MCR011864 | HPR080 | 2019-09-01 | Subcontract | 102748027 | 114973119 | 123947769
MCR011865 | HPR080 | 2019-09-01 | Overhead | 22504574 | 25182196 | 15482859
MCR011866 | HPR080 | 2019-10-01 | Labor | 36573840 | 42205974 | 49570167
MCR011867 | HPR080 | 2019-10-01 | Material | 97554203 | 112576918 | 106679739
MCR011868 | HPR080 | 2019-10-01 | Equipment | 25678522 | 29632848 | 25908516
MCR011869 | HPR080 | 2019-10-01 | Subcontract | 91340579 | 105406436 | 92949612
MCR011870 | HPR080 | 2019-10-01 | Overhead | 20006036 | 23086836 | 13449529
MCR011871 | HPR080 | 2019-11-01 | Labor | 29900705 | 20164956 | 21779734
MCR011872 | HPR080 | 2019-11-01 | Material | 79754806 | 53786428 | 58222354
MCR011873 | HPR080 | 2019-11-01 | Equipment | 20993309 | 14157832 | 15368822
MCR011874 | HPR080 | 2019-11-01 | Subcontract | 74674898 | 50360551 | 56124063
MCR011875 | HPR080 | 2019-11-01 | Overhead | 16355805 | 11030311 | 15944768
MCR011876 | HPR080 | 2019-12-01 | Labor | 21586217 | 23841405 | 26495232
MCR011877 | HPR080 | 2019-12-01 | Material | 57577389 | 63592701 | 62691337
MCR011878 | HPR080 | 2019-12-01 | Equipment | 15155700 | 16739070 | 18790668
MCR011879 | HPR080 | 2019-12-01 | Subcontract | 53910051 | 59542223 | 54797569
MCR011880 | HPR080 | 2019-12-01 | Overhead | 11807747 | 13041344 | 14710481
MCR011881 | HPR080 | 2020-01-01 | Labor | 12310193 | 21236740 | 24947129
MCR011882 | HPR080 | 2020-01-01 | Material | 32835247 | 56645222 | 62496954
MCR011883 | HPR080 | 2020-01-01 | Equipment | 8642996 | 14910332 | 14875014
MCR011884 | HPR080 | 2020-01-01 | Subcontract | 30743837 | 53037257 | 45046116
MCR011885 | HPR080 | 2020-01-01 | Overhead | 6733725 | 11616582 | 14443167
MCR011886 | HPR080 | 2020-02-01 | Labor | 3399744 | 10927203 | 11981072
MCR011887 | HPR080 | 2020-02-01 | Material | 9068212 | 29146368 | 31857002
MCR011888 | HPR080 | 2020-02-01 | Equipment | 2386963 | 7671998 | 8377195
MCR011889 | HPR080 | 2020-02-01 | Subcontract | 8490621 | 27289917 | 30958474
MCR011890 | HPR080 | 2020-02-01 | Overhead | 1859674 | 5977224 | 15129445
MCR011891 | HPR080 | 2020-03-01 | Labor | 0 | 3649846 | 5311050
MCR011892 | HPR080 | 2020-03-01 | Material | 0 | 9735315 | 8623851
MCR011893 | HPR080 | 2020-03-01 | Equipment | 0 | 2562560 | 1798957
MCR011894 | HPR080 | 2020-03-01 | Subcontract | 0 | 9115233 | 9081999
MCR011895 | HPR080 | 2020-03-01 | Overhead | 0 | 1996480 | 14814546
MCR011896 | HPR081 | 2022-09-01 | Labor | 6166700 | 6585537 | 6420102
MCR011897 | HPR081 | 2022-09-01 | Material | 26632683 | 28441554 | 29123863
MCR011898 | HPR081 | 2022-09-01 | Equipment | 12980264 | 13861874 | 14289712
MCR011899 | HPR081 | 2022-09-01 | Subcontract | 12079109 | 12899512 | 13547356
MCR011900 | HPR081 | 2022-09-01 | Overhead | 6060618 | 6472250 | 30044355
MCR011901 | HPR081 | 2022-10-01 | Labor | 17342944 | 11213905 | 13049542
MCR011902 | HPR081 | 2022-10-01 | Material | 74900538 | 48430505 | 47756125
MCR011903 | HPR081 | 2022-10-01 | Equipment | 36505100 | 23604108 | 22846869
MCR011904 | HPR081 | 2022-10-01 | Subcontract | 33970732 | 21965392 | 26076970
MCR011905 | HPR081 | 2022-10-01 | Overhead | 17044604 | 11020999 | 30794962
MCR011906 | HPR081 | 2022-11-01 | Labor | 26816867 | 17769968 | 20525516
MCR011907 | HPR081 | 2022-11-01 | Material | 115816426 | 76744767 | 73099537
MCR011908 | HPR081 | 2022-11-01 | Equipment | 56446727 | 37403942 | 41539673
MCR011909 | HPR081 | 2022-11-01 | Subcontract | 52527910 | 34807172 | 34439400
MCR011910 | HPR081 | 2022-11-01 | Overhead | 26355552 | 17464282 | 29248317
MCR011911 | HPR081 | 2022-12-01 | Labor | 34635028 | 26021198 | 25365131
MCR011912 | HPR081 | 2022-12-01 | Material | 149581424 | 112380100 | 116353628
MCR011913 | HPR081 | 2022-12-01 | Equipment | 72903146 | 54771927 | 54492778
MCR011914 | HPR081 | 2022-12-01 | Subcontract | 67841842 | 50969383 | 45281064
MCR011915 | HPR081 | 2022-12-01 | Overhead | 34039222 | 25573571 | 31755308
MCR011916 | HPR081 | 2023-01-01 | Labor | 40846784 | 37746593 | 40623822
MCR011917 | HPR081 | 2023-01-01 | Material | 176408695 | 163019621 | 174268727
MCR011918 | HPR081 | 2023-01-01 | Equipment | 85978248 | 79452668 | 100280941
MCR011919 | HPR081 | 2023-01-01 | Subcontract | 80009205 | 73936663 | 74787051
MCR011920 | HPR081 | 2023-01-01 | Overhead | 40144121 | 37097261 | 31073984
MCR011921 | HPR081 | 2023-02-01 | Labor | 45504698 | 41605240 | 46171502
MCR011922 | HPR081 | 2023-02-01 | Material | 196525248 | 179684307 | 147720979
MCR011923 | HPR081 | 2023-02-01 | Equipment | 95782674 | 87574719 | 77052022
MCR011924 | HPR081 | 2023-02-01 | Subcontract | 89132958 | 81494840 | 82390355
MCR011925 | HPR081 | 2023-02-01 | Overhead | 44721908 | 40889530 | 33808790
MCR011926 | HPR081 | 2023-03-01 | Labor | 48665046 | 69702804 | 78378370
MCR011927 | HPR081 | 2023-03-01 | Material | 210174129 | 301031797 | 328134555
MCR011928 | HPR081 | 2023-03-01 | Equipment | 102434879 | 146717182 | 166864070
MCR011929 | HPR081 | 2023-03-01 | Subcontract | 95323333 | 136531335 | 123172469
MCR011930 | HPR081 | 2023-03-01 | Overhead | 47827890 | 68503749 | 34331762
MCR011931 | HPR081 | 2023-04-01 | Labor | 50388454 | 42521956 | 41584468
MCR011932 | HPR081 | 2023-04-01 | Material | 217617169 | 183643411 | 184953301
MCR011933 | HPR081 | 2023-04-01 | Equipment | 106062476 | 89504311 | 82700896
MCR011934 | HPR081 | 2023-04-01 | Subcontract | 98699084 | 83290471 | 99893102
MCR011935 | HPR081 | 2023-04-01 | Overhead | 49521652 | 41790476 | 33444121
MCR011936 | HPR081 | 2023-05-01 | Labor | 50740719 | 52729995 | 57716571
MCR011937 | HPR081 | 2023-05-01 | Material | 219138527 | 227729792 | 202462633
MCR011938 | HPR081 | 2023-05-01 | Equipment | 106803957 | 110991176 | 107070014
MCR011939 | HPR081 | 2023-05-01 | Subcontract | 99389087 | 103285609 | 106317247
MCR011940 | HPR081 | 2023-05-01 | Overhead | 49867857 | 51822912 | 29416801
MCR011941 | HPR081 | 2023-06-01 | Labor | 49793878 | 39188642 | 46109353
MCR011942 | HPR081 | 2023-06-01 | Material | 215049319 | 169247530 | 158570695
MCR011943 | HPR081 | 2023-06-01 | Equipment | 104810955 | 82488032 | 90020142
MCR011944 | HPR081 | 2023-06-01 | Subcontract | 97534450 | 76761297 | 78356580
MCR011945 | HPR081 | 2023-06-01 | Overhead | 48937304 | 38514504 | 31401984
MCR011946 | HPR081 | 2023-07-01 | Labor | 47627659 | 34796604 | 40375766
MCR011947 | HPR081 | 2023-07-01 | Material | 205693871 | 150279239 | 154648153
MCR011948 | HPR081 | 2023-07-01 | Equipment | 100251287 | 73243247 | 84974610
MCR011949 | HPR081 | 2023-07-01 | Subcontract | 93291337 | 68158332 | 65351827
MCR011950 | HPR081 | 2023-07-01 | Overhead | 46808348 | 34198019 | 30185196
MCR011951 | HPR081 | 2023-08-01 | Labor | 44331487 | 27364068 | 23725172
MCR011952 | HPR081 | 2023-08-01 | Material | 191458396 | 118179671 | 120546730
MCR011953 | HPR081 | 2023-08-01 | Equipment | 93313186 | 57598527 | 55928493
MCR011954 | HPR081 | 2023-08-01 | Subcontract | 86834914 | 53599747 | 51188675
MCR011955 | HPR081 | 2023-08-01 | Overhead | 43568879 | 26893340 | 30812926
MCR011956 | HPR081 | 2023-09-01 | Labor | 40007393 | 25557253 | 31791115
MCR011957 | HPR081 | 2023-09-01 | Material | 172783540 | 110376417 | 112425137
MCR011958 | HPR081 | 2023-09-01 | Equipment | 84211417 | 53795370 | 54247771
MCR011959 | HPR081 | 2023-09-01 | Subcontract | 78365035 | 50060624 | 53290790
MCR011960 | HPR081 | 2023-09-01 | Overhead | 39319169 | 25117607 | 31239904
MCR011961 | HPR081 | 2023-10-01 | Labor | 34774421 | 31781519 | 37015341
MCR011962 | HPR081 | 2023-10-01 | Material | 150183435 | 137257718 | 138286230
MCR011963 | HPR081 | 2023-10-01 | Equipment | 73196554 | 66896805 | 59443056
MCR011964 | HPR081 | 2023-10-01 | Subcontract | 68114880 | 62252492 | 56342976
MCR011965 | HPR081 | 2023-10-01 | Overhead | 34176218 | 31234801 | 29938847
MCR011966 | HPR081 | 2023-11-01 | Labor | 28775771 | 26223587 | 26027581
MCR011967 | HPR081 | 2023-11-01 | Material | 124276522 | 113254173 | 113440064
MCR011968 | HPR081 | 2023-11-01 | Equipment | 60570017 | 55197933 | 64852476
MCR011969 | HPR081 | 2023-11-01 | Subcontract | 56364941 | 51365814 | 54216520
MCR011970 | HPR081 | 2023-11-01 | Overhead | 28280759 | 25772478 | 31761236
MCR011971 | HPR081 | 2023-12-01 | Labor | 22191412 | 35375980 | 40048469
MCR011972 | HPR081 | 2023-12-01 | Material | 95840057 | 152781442 | 155897811
MCR011973 | HPR081 | 2023-12-01 | Equipment | 46710624 | 74462773 | 86161644
MCR011974 | HPR081 | 2023-12-01 | Subcontract | 43467737 | 69293192 | 94529338
MCR011975 | HPR081 | 2023-12-01 | Overhead | 21809667 | 34767428 | 31864859
MCR011976 | HPR081 | 2024-01-01 | Labor | 15263467 | 27490772 | 28272764
MCR011977 | HPR081 | 2024-01-01 | Material | 65919713 | 118726879 | 102896089
MCR011978 | HPR081 | 2024-01-01 | Equipment | 32128016 | 57865226 | 58550851
MCR011979 | HPR081 | 2024-01-01 | Subcontract | 29897527 | 53847931 | 82006417
MCR011980 | HPR081 | 2024-01-01 | Overhead | 15000899 | 27017864 | 29634071
MCR011981 | HPR081 | 2024-02-01 | Labor | 8359481 | 21608968 | 20333220
MCR011982 | HPR081 | 2024-02-01 | Material | 36102845 | 93324604 | 98320433
MCR011983 | HPR081 | 2024-02-01 | Equipment | 17595841 | 45484640 | 44667102
MCR011984 | HPR081 | 2024-02-01 | Subcontract | 16374249 | 42326867 | 78641085
MCR011985 | HPR081 | 2024-02-01 | Overhead | 8215678 | 21237242 | 32476896
MCR011986 | HPR081 | 2024-03-01 | Labor | 2236918 | 20935983 | 22374228
MCR011987 | HPR081 | 2024-03-01 | Material | 9660781 | 90418119 | 105887854
MCR011988 | HPR081 | 2024-03-01 | Equipment | 4708481 | 44068074 | 43030903
MCR011989 | HPR081 | 2024-03-01 | Subcontract | 4381595 | 41008646 | 67864652
MCR011990 | HPR081 | 2024-03-01 | Overhead | 2198438 | 20575833 | 31304243
MCR011991 | HPR081 | 2024-04-01 | Labor | 0 | 10360574 | 13575921
MCR011992 | HPR081 | 2024-04-01 | Material | 0 | 44745145 | 36575611
MCR011993 | HPR081 | 2024-04-01 | Equipment | 0 | 21807934 | 20714406
MCR011994 | HPR081 | 2024-04-01 | Subcontract | 0 | 20293917 | 37780079
MCR011995 | HPR081 | 2024-04-01 | Overhead | 0 | 10182347 | 32836219
MCR011996 | HPR081 | 2024-05-01 | Labor | 0 | 6325854 | 6438664
MCR011997 | HPR081 | 2024-05-01 | Material | 0 | 27320038 | 28975614
MCR011998 | HPR081 | 2024-05-01 | Equipment | 0 | 13315268 | 14151464
MCR011999 | HPR081 | 2024-05-01 | Subcontract | 0 | 12390854 | 26176281
MCR012000 | HPR081 | 2024-05-01 | Overhead | 0 | 6217034 | 32254145
MCR012001 | HPR081 | 2024-06-01 | Labor | 0 | 1562125 | 2040969
MCR012002 | HPR081 | 2024-06-01 | Material | 0 | 6746491 | 4136353
MCR012003 | HPR081 | 2024-06-01 | Equipment | 0 | 3288112 | 3964406
MCR012004 | HPR081 | 2024-06-01 | Subcontract | 0 | 3059834 | 36244805
MCR012005 | HPR081 | 2024-06-01 | Overhead | 0 | 1535253 | 33102034
MCR012006 | HPR082 | 2016-09-01 | Labor | 4230084 | 2759247 | 2980349
MCR012007 | HPR082 | 2016-09-01 | Material | 14201278 | 9263372 | 9511270
MCR012008 | HPR082 | 2016-09-01 | Equipment | 2932334 | 1912736 | 1927505
MCR012009 | HPR082 | 2016-09-01 | Subcontract | 12262690 | 7998847 | 6934689
MCR012010 | HPR082 | 2016-09-01 | Overhead | 2989679 | 1950142 | 17316550
MCR012011 | HPR082 | 2016-10-01 | Labor | 12007365 | 7964251 | 6790585
MCR012012 | HPR082 | 2016-10-01 | Material | 40311243 | 26737661 | 25426576
MCR012013 | HPR082 | 2016-10-01 | Equipment | 8323619 | 5520894 | 5314013
MCR012014 | HPR082 | 2016-10-01 | Subcontract | 34808435 | 23087756 | 19547383
MCR012015 | HPR082 | 2016-10-01 | Overhead | 8486397 | 5628862 | 18347905
MCR012016 | HPR082 | 2016-11-01 | Labor | 18777152 | 21254355 | 22124396
MCR012017 | HPR082 | 2016-11-01 | Material | 63038841 | 71355329 | 77447271
MCR012018 | HPR082 | 2016-11-01 | Equipment | 13016500 | 14733720 | 14885555
MCR012019 | HPR082 | 2016-11-01 | Subcontract | 54433534 | 61614756 | 53448835
MCR012020 | HPR082 | 2016-11-01 | Overhead | 13271053 | 15021856 | 18655782
MCR012021 | HPR082 | 2016-12-01 | Labor | 24562751 | 16089968 | 13945996
MCR012022 | HPR082 | 2016-12-01 | Material | 82462311 | 54017399 | 46261990
MCR012023 | HPR082 | 2016-12-01 | Equipment | 17027132 | 11153718 | 11102126
MCR012024 | HPR082 | 2016-12-01 | Subcontract | 71205546 | 46643591 | 50018016
MCR012025 | HPR082 | 2016-12-01 | Overhead | 17360118 | 11371842 | 18717002
MCR012026 | HPR082 | 2017-01-01 | Labor | 29388640 | 22316523 | 24244004
MCR012027 | HPR082 | 2017-01-01 | Material | 98663833 | 74921252 | 72312379
MCR012028 | HPR082 | 2017-01-01 | Equipment | 20372484 | 15470026 | 16851181
MCR012029 | HPR082 | 2017-01-01 | Subcontract | 85195430 | 64693901 | 58466804
MCR012030 | HPR082 | 2017-01-01 | Overhead | 20770892 | 15772560 | 16709638
MCR012031 | HPR082 | 2017-02-01 | Labor | 33280613 | 33376097 | 32323685
MCR012032 | HPR082 | 2017-02-01 | Material | 111730001 | 112050562 | 114770329
MCR012033 | HPR082 | 2017-02-01 | Equipment | 23070436 | 23136627 | 22494795
MCR012034 | HPR082 | 2017-02-01 | Subcontract | 96477961 | 96754763 | 86850227
MCR012035 | HPR082 | 2017-02-01 | Overhead | 23521606 | 23589091 | 18245277
MCR012036 | HPR082 | 2017-03-01 | Labor | 36265948 | 32018875 | 35611255
MCR012037 | HPR082 | 2017-03-01 | Material | 121752397 | 107494083 | 110039377
MCR012038 | HPR082 | 2017-03-01 | Equipment | 25139899 | 22195788 | 23737011
MCR012039 | HPR082 | 2017-03-01 | Subcontract | 105132220 | 92820280 | 103547610
MCR012040 | HPR082 | 2017-03-01 | Overhead | 25631539 | 22629853 | 18734213
MCR012041 | HPR082 | 2017-04-01 | Labor | 38373615 | 23119409 | 18069605
MCR012042 | HPR082 | 2017-04-01 | Material | 128828279 | 77616707 | 79104764
MCR012043 | HPR082 | 2017-04-01 | Equipment | 26600954 | 16026593 | 17728506
MCR012044 | HPR082 | 2017-04-01 | Subcontract | 111242187 | 67021405 | 61327713
MCR012045 | HPR082 | 2017-04-01 | Overhead | 27121167 | 16340012 | 17839057
MCR012046 | HPR082 | 2017-05-01 | Labor | 39634527 | 32941714 | 33293175
MCR012047 | HPR082 | 2017-05-01 | Material | 133061425 | 110592247 | 110746791
MCR012048 | HPR082 | 2017-05-01 | Equipment | 27475030 | 22835509 | 23136440
MCR012049 | HPR082 | 2017-05-01 | Subcontract | 114897475 | 95495520 | 91263324
MCR012050 | HPR082 | 2017-05-01 | Overhead | 28012337 | 23282084 | 16942822
MCR012051 | HPR082 | 2017-06-01 | Labor | 40081849 | 35574135 | 33996904
MCR012052 | HPR082 | 2017-06-01 | Material | 134563179 | 119429836 | 129108086
MCR012053 | HPR082 | 2017-06-01 | Equipment | 27785118 | 24660328 | 23700280
MCR012054 | HPR082 | 2017-06-01 | Subcontract | 116194228 | 103126707 | 95810389
MCR012055 | HPR082 | 2017-06-01 | Overhead | 28328489 | 25142589 | 17067374
MCR012056 | HPR082 | 2017-07-01 | Labor | 39751397 | 27675616 | 27655938
MCR012057 | HPR082 | 2017-07-01 | Material | 133453781 | 92912850 | 95297844
MCR012058 | HPR082 | 2017-07-01 | Equipment | 27556045 | 19184999 | 21405449
MCR012059 | HPR082 | 2017-07-01 | Subcontract | 115236271 | 80229502 | 76251250
MCR012060 | HPR082 | 2017-07-01 | Overhead | 28094936 | 19560185 | 18872738
MCR012061 | HPR082 | 2017-08-01 | Labor | 38682140 | 34836197 | 26197869
MCR012062 | HPR082 | 2017-08-01 | Material | 129864062 | 116952425 | 112158643
MCR012063 | HPR082 | 2017-08-01 | Equipment | 26814827 | 24148782 | 21501472
MCR012064 | HPR082 | 2017-08-01 | Subcontract | 112136578 | 100987482 | 89309241
MCR012065 | HPR082 | 2017-08-01 | Overhead | 27339222 | 24621040 | 16336516
MCR012066 | HPR082 | 2017-09-01 | Labor | 36916872 | 34202577 | 34107973
MCR012067 | HPR082 | 2017-09-01 | Material | 123937688 | 114825230 | 122105532
MCR012068 | HPR082 | 2017-09-01 | Equipment | 25591126 | 23709551 | 24660373
MCR012069 | HPR082 | 2017-09-01 | Subcontract | 107019201 | 99150666 | 116957351
MCR012070 | HPR082 | 2017-09-01 | Overhead | 26091591 | 24173219 | 17947153
MCR012071 | HPR082 | 2017-10-01 | Labor | 34503111 | 36281133 | 32587150
MCR012072 | HPR082 | 2017-10-01 | Material | 115834186 | 121803376 | 127531799
MCR012073 | HPR082 | 2017-10-01 | Equipment | 23917884 | 25150425 | 24195028
MCR012074 | HPR082 | 2017-10-01 | Subcontract | 100021892 | 105176240 | 92267896
MCR012075 | HPR082 | 2017-10-01 | Overhead | 24385627 | 25642271 | 18929536
MCR012076 | HPR082 | 2017-11-01 | Labor | 31494355 | 33613476 | 34234933
MCR012077 | HPR082 | 2017-11-01 | Material | 105733161 | 112847494 | 117698637
MCR012078 | HPR082 | 2017-11-01 | Equipment | 21832186 | 23301181 | 27770275
MCR012079 | HPR082 | 2017-11-01 | Subcontract | 91299738 | 97442907 | 90746569
MCR012080 | HPR082 | 2017-11-01 | Overhead | 22259140 | 23756863 | 17048719
MCR012081 | HPR082 | 2017-12-01 | Labor | 27951905 | 25390018 | 23918729
MCR012082 | HPR082 | 2017-12-01 | Material | 93840411 | 85239619 | 82087636
MCR012083 | HPR082 | 2017-12-01 | Equipment | 19376526 | 17600601 | 18757732
MCR012084 | HPR082 | 2017-12-01 | Subcontract | 81030444 | 73603728 | 73339288
MCR012085 | HPR082 | 2017-12-01 | Overhead | 19755456 | 17944802 | 18564694
MCR012086 | HPR082 | 2018-01-01 | Labor | 23947638 | 41865922 | 42357995
MCR012087 | HPR082 | 2018-01-01 | Material | 80397248 | 140552687 | 153252396
MCR012088 | HPR082 | 2018-01-01 | Equipment | 16600730 | 29021855 | 28362567
MCR012089 | HPR082 | 2018-01-01 | Subcontract | 69422380 | 121366120 | 157317754
MCR012090 | HPR082 | 2018-01-01 | Overhead | 16925377 | 29589411 | 16809413
MCR012091 | HPR082 | 2018-02-01 | Labor | 19568521 | 20190999 | 17143668
MCR012092 | HPR082 | 2018-02-01 | Material | 65695632 | 67785423 | 63947616
MCR012093 | HPR082 | 2018-02-01 | Equipment | 13565085 | 13996592 | 12563362
MCR012094 | HPR082 | 2018-02-01 | Subcontract | 56727652 | 58532170 | 76539187
MCR012095 | HPR082 | 2018-02-01 | Overhead | 13830366 | 14270312 | 20098676
MCR012096 | HPR082 | 2018-03-01 | Labor | 14924608 | 14819217 | 10332680
MCR012097 | HPR082 | 2018-03-01 | Material | 50105043 | 49751221 | 57753679
MCR012098 | HPR082 | 2018-03-01 | Equipment | 10345880 | 10272822 | 10903550
MCR012099 | HPR082 | 2018-03-01 | Subcontract | 43265303 | 42959781 | 61146787
MCR012100 | HPR082 | 2018-03-01 | Overhead | 10548206 | 10473719 | 19140513
MCR012101 | HPR082 | 2018-04-01 | Labor | 10165213 | 12069451 | 10709624
MCR012102 | HPR082 | 2018-04-01 | Material | 34126752 | 40519681 | 37844605
MCR012103 | HPR082 | 2018-04-01 | Equipment | 7046622 | 8366658 | 9004734
MCR012104 | HPR082 | 2018-04-01 | Subcontract | 29468177 | 34988420 | 63063468
MCR012105 | HPR082 | 2018-04-01 | Overhead | 7184427 | 8530278 | 18371677
MCR012106 | HPR082 | 2018-05-01 | Labor | 5519417 | 35168640 | 30679435
MCR012107 | HPR082 | 2018-05-01 | Material | 18529841 | 118068506 | 129439149
MCR012108 | HPR082 | 2018-05-01 | Equipment | 3826112 | 24379235 | 22758926
MCR012109 | HPR082 | 2018-05-01 | Subcontract | 16000369 | 101951209 | 113194655
MCR012110 | HPR082 | 2018-05-01 | Overhead | 3900936 | 24856000 | 18279764
MCR012111 | HPR082 | 2018-06-01 | Labor | 1466580 | 6094136 | 6848777
MCR012112 | HPR082 | 2018-06-01 | Material | 4923618 | 20459295 | 19074847
MCR012113 | HPR082 | 2018-06-01 | Equipment | 1016647 | 4224513 | 5121805
MCR012114 | HPR082 | 2018-06-01 | Subcontract | 4251504 | 17666437 | 51246991
MCR012115 | HPR082 | 2018-06-01 | Overhead | 1036529 | 4307129 | 18209976
MCR012116 | HPR082 | 2018-07-01 | Labor | 0 | 8007202 | 7645641
MCR012117 | HPR082 | 2018-07-01 | Material | 0 | 26881859 | 27592708
MCR012118 | HPR082 | 2018-07-01 | Equipment | 0 | 5550669 | 5324167
MCR012119 | HPR082 | 2018-07-01 | Subcontract | 0 | 23212270 | 68000726
MCR012120 | HPR082 | 2018-07-01 | Overhead | 0 | 5659219 | 18173704
MCR012121 | HPR082 | 2018-08-01 | Labor | 0 | 3354380 | 2723542
MCR012122 | HPR082 | 2018-08-01 | Material | 0 | 11261357 | 13515057
MCR012123 | HPR082 | 2018-08-01 | Equipment | 0 | 2325288 | 2664084
MCR012124 | HPR082 | 2018-08-01 | Subcontract | 0 | 9724092 | 30759680
MCR012125 | HPR082 | 2018-08-01 | Overhead | 0 | 2370762 | 17879856
MCR012126 | HPR082 | 2018-09-01 | Labor | 0 | 510764 | 748412
MCR012127 | HPR082 | 2018-09-01 | Material | 0 | 1714741 | 1764811
MCR012128 | HPR082 | 2018-09-01 | Equipment | 0 | 354066 | 375232
MCR012129 | HPR082 | 2018-09-01 | Subcontract | 0 | 1480665 | 25884593
MCR012130 | HPR082 | 2018-09-01 | Overhead | 0 | 360990 | 17361077
MCR012131 | HPR083 | 2021-07-01 | Labor | 18701747 | 7947436 | 8874868
MCR012132 | HPR083 | 2021-07-01 | Material | 36236129 | 15398793 | 14412835
MCR012133 | HPR083 | 2021-07-01 | Equipment | 8897961 | 3781250 | 3815079
MCR012134 | HPR083 | 2021-07-01 | Subcontract | 45058725 | 19148016 | 19153371
MCR012135 | HPR083 | 2021-07-01 | Overhead | 10297880 | 4376155 | 33709020
MCR012136 | HPR083 | 2021-08-01 | Labor | 50456264 | 29800776 | 32226797
MCR012137 | HPR083 | 2021-08-01 | Material | 97763044 | 57741385 | 58568723
MCR012138 | HPR083 | 2021-08-01 | Equipment | 24006199 | 14178683 | 15136441
MCR012139 | HPR083 | 2021-08-01 | Subcontract | 121565915 | 71799976 | 68262485
MCR012140 | HPR083 | 2021-08-01 | Overhead | 27783102 | 16409419 | 37358788
MCR012141 | HPR083 | 2021-09-01 | Labor | 74008997 | 79768785 | 88354859
MCR012142 | HPR083 | 2021-09-01 | Material | 143398348 | 154558396 | 159531459
MCR012143 | HPR083 | 2021-09-01 | Equipment | 35212174 | 37952579 | 33921921
MCR012144 | HPR083 | 2021-09-01 | Subcontract | 178312280 | 192189523 | 198870762
MCR012145 | HPR083 | 2021-09-01 | Overhead | 40752116 | 43923670 | 35828465
MCR012146 | HPR083 | 2021-10-01 | Labor | 89750552 | 133558793 | 147794499
MCR012147 | HPR083 | 2021-10-01 | Material | 173898868 | 258780836 | 275557220
MCR012148 | HPR083 | 2021-10-01 | Equipment | 42701727 | 63544914 | 63646754
MCR012149 | HPR083 | 2021-10-01 | Subcontract | 216238919 | 321787536 | 344906567
MCR012150 | HPR083 | 2021-10-01 | Overhead | 49420004 | 73542456 | 35519335
MCR012151 | HPR083 | 2021-11-01 | Labor | 98114358 | 93766615 | 107771491
MCR012152 | HPR083 | 2021-11-01 | Material | 190104411 | 181680312 | 254609644
MCR012153 | HPR083 | 2021-11-01 | Equipment | 46681078 | 44612499 | 48673527
MCR012154 | HPR083 | 2021-11-01 | Subcontract | 236390109 | 225914951 | 218821837
MCR012155 | HPR083 | 2021-11-01 | Overhead | 54025427 | 51631398 | 34708469
MCR012156 | HPR083 | 2021-12-01 | Labor | 99588781 | 55758920 | 61187475
MCR012157 | HPR083 | 2021-12-01 | Material | 192961224 | 108037365 | 89729589
MCR012158 | HPR083 | 2021-12-01 | Equipment | 47382583 | 26529109 | 22621982
MCR012159 | HPR083 | 2021-12-01 | Subcontract | 239942484 | 134341777 | 119358984
MCR012160 | HPR083 | 2021-12-01 | Overhead | 54837300 | 30702943 | 35488861
MCR012161 | HPR083 | 2022-01-01 | Labor | 94735286 | 89984842 | 91970787
MCR012162 | HPR083 | 2022-01-01 | Material | 183557189 | 174352823 | 198406239
MCR012163 | HPR083 | 2022-01-01 | Equipment | 45073376 | 42813198 | 45494895
MCR012164 | HPR083 | 2022-01-01 | Subcontract | 228248801 | 216803401 | 196639928
MCR012165 | HPR083 | 2022-01-01 | Overhead | 52164784 | 49549012 | 34472646
MCR012166 | HPR083 | 2022-02-01 | Labor | 84217441 | 117493556 | 139890443
MCR012167 | HPR083 | 2022-02-01 | Material | 163178022 | 227653156 | 270298954
MCR012168 | HPR083 | 2022-02-01 | Equipment | 40069171 | 55901359 | 51864282
MCR012169 | HPR083 | 2022-02-01 | Subcontract | 202907814 | 283081040 | 289734328
MCR012170 | HPR083 | 2022-02-01 | Overhead | 46373266 | 64696337 | 35710287
MCR012171 | HPR083 | 2022-03-01 | Labor | 68851422 | 83598107 | 124622036
MCR012172 | HPR083 | 2022-03-01 | Material | 133405134 | 161978014 | 199285563
MCR012173 | HPR083 | 2022-03-01 | Equipment | 32758291 | 39774503 | 38009866
MCR012174 | HPR083 | 2022-03-01 | Subcontract | 165885967 | 201415634 | 218369949
MCR012175 | HPR083 | 2022-03-01 | Overhead | 37912163 | 46032238 | 35963050
MCR012176 | HPR083 | 2022-04-01 | Labor | 49705909 | 47232468 | 89145589
MCR012177 | HPR083 | 2022-04-01 | Material | 96309172 | 91516682 | 126797501
MCR012178 | HPR083 | 2022-04-01 | Equipment | 23649194 | 22472374 | 25304665
MCR012179 | HPR083 | 2022-04-01 | Subcontract | 119758061 | 113798719 | 115711937
MCR012180 | HPR083 | 2022-04-01 | Overhead | 27369929 | 26007960 | 38476302
MCR012181 | HPR083 | 2022-05-01 | Labor | 28346298 | 19815351 | 13459430
MCR012182 | HPR083 | 2022-05-01 | Material | 54923217 | 38393827 | 45802802
MCR012183 | HPR083 | 2022-05-01 | Equipment | 13486668 | 9427794 | 9541224
MCR012184 | HPR083 | 2022-05-01 | Subcontract | 68295655 | 47741769 | 40951235
MCR012185 | HPR083 | 2022-05-01 | Overhead | 15608529 | 10911072 | 33592984
MCR012186 | HPR083 | 2022-06-01 | Labor | 7828485 | 5579891 | 5049883
MCR012187 | HPR083 | 2022-06-01 | Material | 15168316 | 10811486 | 11468002
MCR012188 | HPR083 | 2022-06-01 | Equipment | 3724655 | 2654814 | 2510615
MCR012189 | HPR083 | 2022-06-01 | Subcontract | 18861423 | 13443814 | 16325372
MCR012190 | HPR083 | 2022-06-01 | Overhead | 4310656 | 3072496 | 33632097
MCR012191 | HPR084 | 2022-03-01 | Labor | 1707256 | 1462627 | 1784315
MCR012192 | HPR084 | 2022-03-01 | Material | 5120303 | 4386623 | 4301352
MCR012193 | HPR084 | 2022-03-01 | Equipment | 1316626 | 1127969 | 1188505
MCR012194 | HPR084 | 2022-03-01 | Subcontract | 4860714 | 4164230 | 4853908
MCR012195 | HPR084 | 2022-03-01 | Overhead | 1167536 | 1000242 | 7914825
MCR012196 | HPR084 | 2022-04-01 | Labor | 4879938 | 2266078 | 2069141
MCR012197 | HPR084 | 2022-04-01 | Material | 14635622 | 6796287 | 7132779
MCR012198 | HPR084 | 2022-04-01 | Equipment | 3763378 | 1747585 | 1950383
MCR012199 | HPR084 | 2022-04-01 | Subcontract | 13893624 | 6451729 | 7309338
MCR012200 | HPR084 | 2022-04-01 | Overhead | 3337227 | 1549695 | 7848033
MCR012201 | HPR084 | 2022-05-01 | Labor | 7695074 | 7588546 | 7170010
MCR012202 | HPR084 | 2022-05-01 | Material | 23078611 | 22759118 | 25889244
MCR012203 | HPR084 | 2022-05-01 | Equipment | 5934394 | 5852240 | 6492082
MCR012204 | HPR084 | 2022-05-01 | Subcontract | 21908570 | 21605275 | 25447733
MCR012205 | HPR084 | 2022-05-01 | Overhead | 5262405 | 5189554 | 7513248
MCR012206 | HPR084 | 2022-06-01 | Labor | 10159829 | 13456413 | 14139478
MCR012207 | HPR084 | 2022-06-01 | Material | 30470760 | 40357679 | 34357795
MCR012208 | HPR084 | 2022-06-01 | Equipment | 7835198 | 10377503 | 10075615
MCR012209 | HPR084 | 2022-06-01 | Subcontract | 28925952 | 38311623 | 35790824
MCR012210 | HPR084 | 2022-06-01 | Overhead | 6947969 | 9202393 | 8388089
MCR012211 | HPR084 | 2022-07-01 | Labor | 12281680 | 7115661 | 6855936
MCR012212 | HPR084 | 2022-07-01 | Material | 36834491 | 21340872 | 24152301
MCR012213 | HPR084 | 2022-07-01 | Equipment | 9471556 | 5487554 | 5672264
MCR012214 | HPR084 | 2022-07-01 | Subcontract | 34967053 | 20258931 | 23643950
MCR012215 | HPR084 | 2022-07-01 | Overhead | 8399033 | 4866164 | 8053028
MCR012216 | HPR084 | 2022-08-01 | Labor | 14068445 | 9159083 | 9687679
MCR012217 | HPR084 | 2022-08-01 | Material | 42193251 | 27469383 | 27150920
MCR012218 | HPR084 | 2022-08-01 | Equipment | 10849499 | 7063429 | 7254799
MCR012219 | HPR084 | 2022-08-01 | Subcontract | 40054136 | 26076738 | 24786709
MCR012220 | HPR084 | 2022-08-01 | Overhead | 9620942 | 6263593 | 8043429
MCR012221 | HPR084 | 2022-09-01 | Labor | 15528323 | 7333112 | 7306580
MCR012222 | HPR084 | 2022-09-01 | Material | 46571631 | 21993036 | 26037632
MCR012223 | HPR084 | 2022-09-01 | Equipment | 11975347 | 5655251 | 5499180
MCR012224 | HPR084 | 2022-09-01 | Subcontract | 44210539 | 20878032 | 27581692
MCR012225 | HPR084 | 2022-09-01 | Overhead | 10619304 | 5014871 | 8278635
MCR012226 | HPR084 | 2022-10-01 | Labor | 16669936 | 13812190 | 14772219
MCR012227 | HPR084 | 2022-10-01 | Material | 49995488 | 41424706 | 39126351
MCR012228 | HPR084 | 2022-10-01 | Equipment | 12855752 | 10651876 | 12129483
MCR012229 | HPR084 | 2022-10-01 | Subcontract | 47460814 | 39324554 | 38548197
MCR012230 | HPR084 | 2022-10-01 | Overhead | 11400015 | 9445698 | 8096571
MCR012231 | HPR084 | 2022-11-01 | Labor | 17502382 | 16962014 | 17549332
MCR012232 | HPR084 | 2022-11-01 | Material | 52492111 | 50871470 | 47180296
MCR012233 | HPR084 | 2022-11-01 | Equipment | 13497729 | 13081001 | 13702294
MCR012234 | HPR084 | 2022-11-01 | Subcontract | 49830863 | 48292385 | 56578456
MCR012235 | HPR084 | 2022-11-01 | Overhead | 11969297 | 11599757 | 7961400
MCR012236 | HPR084 | 2022-12-01 | Labor | 18035298 | 11875328 | 11547831
MCR012237 | HPR084 | 2022-12-01 | Material | 54090402 | 35615783 | 42572280
MCR012238 | HPR084 | 2022-12-01 | Equipment | 13908711 | 9158180 | 9046897
MCR012239 | HPR084 | 2022-12-01 | Subcontract | 51348124 | 33810132 | 32478763
MCR012240 | HPR084 | 2022-12-01 | Overhead | 12333741 | 8121142 | 7824857
MCR012241 | HPR084 | 2023-01-01 | Labor | 18278936 | 19369916 | 17033201
MCR012242 | HPR084 | 2023-01-01 | Material | 54821106 | 58093110 | 56000612
MCR012243 | HPR084 | 2023-01-01 | Equipment | 14096603 | 14937961 | 14952289
MCR012244 | HPR084 | 2023-01-01 | Subcontract | 52041783 | 55147902 | 57239461
MCR012245 | HPR084 | 2023-01-01 | Overhead | 12500357 | 13246442 | 7491826
MCR012246 | HPR084 | 2023-02-01 | Labor | 18244253 | 15389367 | 15651553
MCR012247 | HPR084 | 2023-02-01 | Material | 54717087 | 46154880 | 44340513
MCR012248 | HPR084 | 2023-02-01 | Equipment | 14069856 | 11868185 | 13420675
MCR012249 | HPR084 | 2023-02-01 | Subcontract | 51943037 | 43814917 | 43245369
MCR012250 | HPR084 | 2023-02-01 | Overhead | 12476638 | 10524276 | 8045833
MCR012251 | HPR084 | 2023-03-01 | Labor | 17943029 | 15864685 | 16623935
MCR012252 | HPR084 | 2023-03-01 | Material | 53813675 | 47580428 | 49018573
MCR012253 | HPR084 | 2023-03-01 | Equipment | 13837554 | 12234748 | 14308122
MCR012254 | HPR084 | 2023-03-01 | Subcontract | 51085426 | 45168193 | 52663453
MCR012255 | HPR084 | 2023-03-01 | Overhead | 12270641 | 10849331 | 7742022
MCR012256 | HPR084 | 2023-04-01 | Labor | 17388013 | 16319059 | 15919445
MCR012257 | HPR084 | 2023-04-01 | Material | 52149104 | 48943158 | 43405746
MCR012258 | HPR084 | 2023-04-01 | Equipment | 13409529 | 12585158 | 10377512
MCR012259 | HPR084 | 2023-04-01 | Subcontract | 49505245 | 46461835 | 45480375
MCR012260 | HPR084 | 2023-04-01 | Overhead | 11891084 | 11160062 | 8159290
MCR012261 | HPR084 | 2023-05-01 | Labor | 16593110 | 11069855 | 9700311
MCR012262 | HPR084 | 2023-05-01 | Material | 49765075 | 33200055 | 31311713
MCR012263 | HPR084 | 2023-05-01 | Equipment | 12796504 | 8537004 | 8638945
MCR012264 | HPR084 | 2023-05-01 | Subcontract | 47242082 | 31516876 | 33925544
MCR012265 | HPR084 | 2023-05-01 | Overhead | 11347476 | 7570305 | 7109229
MCR012266 | HPR084 | 2023-06-01 | Labor | 15573627 | 11222126 | 13300803
MCR012267 | HPR084 | 2023-06-01 | Material | 46707504 | 33656738 | 31735398
MCR012268 | HPR084 | 2023-06-01 | Equipment | 12010286 | 8654435 | 8502679
MCR012269 | HPR084 | 2023-06-01 | Subcontract | 44339524 | 31950406 | 32427246
MCR012270 | HPR084 | 2023-06-01 | Overhead | 10650286 | 7674439 | 8781374
MCR012271 | HPR084 | 2023-07-01 | Labor | 14346616 | 7809703 | 6905440
MCR012272 | HPR084 | 2023-07-01 | Material | 43027526 | 23422401 | 22660930
MCR012273 | HPR084 | 2023-07-01 | Equipment | 11064023 | 6022795 | 6345236
MCR012274 | HPR084 | 2023-07-01 | Subcontract | 40846114 | 22234931 | 21068269
MCR012275 | HPR084 | 2023-07-01 | Overhead | 9811174 | 5340796 | 7267954
MCR012276 | HPR084 | 2023-08-01 | Labor | 12931337 | 8541727 | 7943285
MCR012277 | HPR084 | 2023-08-01 | Material | 38782904 | 25617844 | 21229485
MCR012278 | HPR084 | 2023-08-01 | Equipment | 9972568 | 6587328 | 6712803
MCR012279 | HPR084 | 2023-08-01 | Subcontract | 36816686 | 24319069 | 29141487
MCR012280 | HPR084 | 2023-08-01 | Overhead | 8843312 | 5841403 | 8087362
MCR012281 | HPR084 | 2023-09-01 | Labor | 11349943 | 14054542 | 15527230
MCR012282 | HPR084 | 2023-09-01 | Material | 34040078 | 42151552 | 42433177
MCR012283 | HPR084 | 2023-09-01 | Equipment | 8753006 | 10838776 | 12427300
MCR012284 | HPR084 | 2023-09-01 | Subcontract | 32314312 | 40014550 | 44773044
MCR012285 | HPR084 | 2023-09-01 | Overhead | 7761848 | 9611434 | 7934886
MCR012286 | HPR084 | 2023-10-01 | Labor | 9628522 | 14513892 | 14452527
MCR012287 | HPR084 | 2023-10-01 | Material | 28877294 | 43529209 | 40998867
MCR012288 | HPR084 | 2023-10-01 | Equipment | 7425457 | 11193025 | 12950678
MCR012289 | HPR084 | 2023-10-01 | Subcontract | 27413271 | 41322363 | 39156260
MCR012290 | HPR084 | 2023-10-01 | Overhead | 6584626 | 9925568 | 8354982
MCR012291 | HPR084 | 2023-11-01 | Labor | 7798799 | 9885791 | 9179745
MCR012292 | HPR084 | 2023-11-01 | Material | 23389698 | 29648881 | 31321290
MCR012293 | HPR084 | 2023-11-01 | Equipment | 6014386 | 7623861 | 7072615
MCR012294 | HPR084 | 2023-11-01 | Subcontract | 22203886 | 28145740 | 45455051
MCR012295 | HPR084 | 2023-11-01 | Overhead | 5333339 | 6760564 | 7719854
MCR012296 | HPR084 | 2023-12-01 | Labor | 5901162 | 16390943 | 18598139
MCR012297 | HPR084 | 2023-12-01 | Material | 17698416 | 49158750 | 47127448
MCR012298 | HPR084 | 2023-12-01 | Equipment | 4550940 | 12640595 | 14457847
MCR012299 | HPR084 | 2023-12-01 | Subcontract | 16801140 | 46666497 | 67922603
MCR012300 | HPR084 | 2023-12-01 | Overhead | 4035608 | 11209221 | 7463001
MCR012301 | HPR084 | 2024-01-01 | Labor | 3990794 | 9690586 | 9328549
MCR012302 | HPR084 | 2024-01-01 | Material | 11968955 | 29063434 | 27024785
MCR012303 | HPR084 | 2024-01-01 | Equipment | 3077676 | 7473321 | 7643410
MCR012304 | HPR084 | 2024-01-01 | Subcontract | 11362152 | 27589975 | 38427781
MCR012305 | HPR084 | 2024-01-01 | Overhead | 2729172 | 6627070 | 7842857
MCR012306 | HPR084 | 2024-02-01 | Labor | 2153118 | 6989358 | 6461465
MCR012307 | HPR084 | 2024-02-01 | Material | 6457503 | 20962069 | 17933375
MCR012308 | HPR084 | 2024-02-01 | Equipment | 1660471 | 5390150 | 5487002
MCR012309 | HPR084 | 2024-02-01 | Subcontract | 6130120 | 19899333 | 30723946
MCR012310 | HPR084 | 2024-02-01 | Overhead | 1472446 | 4779789 | 8197393
MCR012311 | HPR084 | 2024-03-01 | Labor | 569104 | 8590328 | 8451893
MCR012312 | HPR084 | 2024-03-01 | Material | 1706822 | 25763606 | 27255832
MCR012313 | HPR084 | 2024-03-01 | Equipment | 438889 | 6624809 | 6043462
MCR012314 | HPR084 | 2024-03-01 | Subcontract | 1620289 | 24457441 | 37255227
MCR012315 | HPR084 | 2024-03-01 | Overhead | 389191 | 5874640 | 7974110
MCR012316 | HPR084 | 2024-04-01 | Labor | 0 | 5821351 | 5268356
MCR012317 | HPR084 | 2024-04-01 | Material | 0 | 17459051 | 13739306
MCR012318 | HPR084 | 2024-04-01 | Equipment | 0 | 4489390 | 4684112
MCR012319 | HPR084 | 2024-04-01 | Subcontract | 0 | 16573911 | 32446487
MCR012320 | HPR084 | 2024-04-01 | Overhead | 0 | 3981028 | 7767560
MCR012321 | HPR084 | 2024-05-01 | Labor | 0 | 4573245 | 4843385
MCR012322 | HPR084 | 2024-05-01 | Material | 0 | 13715806 | 14674559
MCR012323 | HPR084 | 2024-05-01 | Equipment | 0 | 3526858 | 4112947
MCR012324 | HPR084 | 2024-05-01 | Subcontract | 0 | 13020441 | 28219173
MCR012325 | HPR084 | 2024-05-01 | Overhead | 0 | 3127490 | 8285039
MCR012326 | HPR084 | 2024-06-01 | Labor | 0 | 2616715 | 2816150
MCR012327 | HPR084 | 2024-06-01 | Material | 0 | 7847896 | 7114544
MCR012328 | HPR084 | 2024-06-01 | Equipment | 0 | 2017994 | 2237308
MCR012329 | HPR084 | 2024-06-01 | Subcontract | 0 | 7450023 | 23553563
MCR012330 | HPR084 | 2024-06-01 | Overhead | 0 | 1789484 | 8032297
MCR012331 | HPR084 | 2024-07-01 | Labor | 0 | 1249366 | 851582
MCR012332 | HPR084 | 2024-07-01 | Material | 0 | 3747024 | 3644058
MCR012333 | HPR084 | 2024-07-01 | Equipment | 0 | 963503 | 955345
MCR012334 | HPR084 | 2024-07-01 | Subcontract | 0 | 3557057 | 21621339
MCR012335 | HPR084 | 2024-07-01 | Overhead | 0 | 854400 | 8464530
MCR012336 | HPR084 | 2024-08-01 | Labor | 0 | 224919 | 311737
MCR012337 | HPR084 | 2024-08-01 | Material | 0 | 674564 | 752146
MCR012338 | HPR084 | 2024-08-01 | Equipment | 0 | 173456 | 118238
MCR012339 | HPR084 | 2024-08-01 | Subcontract | 0 | 640365 | 17535776
MCR012340 | HPR084 | 2024-08-01 | Overhead | 0 | 153815 | 8049288
MCR012341 | HPR085 | 2020-07-01 | Labor | 11778742 | 2841983 | 3318803
MCR012342 | HPR085 | 2020-07-01 | Material | 24303903 | 5864062 | 6884729
MCR012343 | HPR085 | 2020-07-01 | Equipment | 6329359 | 1527152 | 1733200
MCR012344 | HPR085 | 2020-07-01 | Subcontract | 41767266 | 10077633 | 10307993
MCR012345 | HPR085 | 2020-07-01 | Overhead | 8437620 | 2035835 | 31736190
MCR012346 | HPR085 | 2020-08-01 | Labor | 32063406 | 11789085 | 12893918
MCR012347 | HPR085 | 2020-08-01 | Material | 66158670 | 24325243 | 22774698
MCR012348 | HPR085 | 2020-08-01 | Equipment | 17229412 | 6334916 | 6755865
MCR012349 | HPR085 | 2020-08-01 | Subcontract | 113696419 | 41803940 | 45302787
MCR012350 | HPR085 | 2020-08-01 | Overhead | 22968398 | 8445029 | 36126041
MCR012351 | HPR085 | 2020-09-01 | Labor | 47582568 | 27681975 | 31733169
MCR012352 | HPR085 | 2020-09-01 | Material | 98180442 | 57118157 | 61085522
MCR012353 | HPR085 | 2020-09-01 | Equipment | 25568702 | 14875031 | 15708155
MCR012354 | HPR085 | 2020-09-01 | Subcontract | 168727163 | 98159922 | 97485829
MCR012355 | HPR085 | 2020-09-01 | Overhead | 34085442 | 19829791 | 29855859
MCR012356 | HPR085 | 2020-10-01 | Labor | 58541442 | 42123886 | 51151242
MCR012357 | HPR085 | 2020-10-01 | Material | 120792654 | 86917162 | 73316043
MCR012358 | HPR085 | 2020-10-01 | Equipment | 31457501 | 22635455 | 23929229
MCR012359 | HPR085 | 2020-10-01 | Subcontract | 207587186 | 149370749 | 131844618
MCR012360 | HPR085 | 2020-10-01 | Overhead | 41935755 | 30175153 | 31086302
MCR012361 | HPR085 | 2020-11-01 | Labor | 65165367 | 48962552 | 51910525
MCR012362 | HPR085 | 2020-11-01 | Material | 134460263 | 101027859 | 112695877
MCR012363 | HPR085 | 2020-11-01 | Equipment | 35016896 | 26310242 | 24212127
MCR012364 | HPR085 | 2020-11-01 | Subcontract | 231075539 | 173620567 | 203636836
MCR012365 | HPR085 | 2020-11-01 | Overhead | 46680758 | 35073984 | 27416781
MCR012366 | HPR085 | 2020-12-01 | Labor | 67704825 | 46619369 | 49977792
MCR012367 | HPR085 | 2020-12-01 | Material | 139700105 | 96193006 | 92303912
MCR012368 | HPR085 | 2020-12-01 | Equipment | 36381485 | 25051122 | 26953115
MCR012369 | HPR085 | 2020-12-01 | Subcontract | 240080425 | 165311672 | 153314716
MCR012370 | HPR085 | 2020-12-01 | Overhead | 48499881 | 33395461 | 32191840
MCR012371 | HPR085 | 2021-01-01 | Labor | 66442627 | 44038469 | 47784225
MCR012372 | HPR085 | 2021-01-01 | Material | 137095722 | 90867654 | 91947137
MCR012373 | HPR085 | 2021-01-01 | Equipment | 35703237 | 23664264 | 24171337
MCR012374 | HPR085 | 2021-01-01 | Subcontract | 235604684 | 156159833 | 174281410
MCR012375 | HPR085 | 2021-01-01 | Overhead | 47595714 | 31546651 | 29318092
MCR012376 | HPR085 | 2021-02-01 | Labor | 61704708 | 43170023 | 41784984
MCR012377 | HPR085 | 2021-02-01 | Material | 127319642 | 89075729 | 96523742
MCR012378 | HPR085 | 2021-02-01 | Equipment | 33157295 | 23197601 | 25111455
MCR012379 | HPR085 | 2021-02-01 | Subcontract | 218804086 | 153080335 | 167072739
MCR012380 | HPR085 | 2021-02-01 | Overhead | 44201739 | 30924546 | 28885448
MCR012381 | HPR085 | 2021-03-01 | Labor | 53877421 | 76262163 | 84738404
MCR012382 | HPR085 | 2021-03-01 | Material | 111169054 | 157357059 | 167513856
MCR012383 | HPR085 | 2021-03-01 | Equipment | 28951269 | 40979808 | 42424280
MCR012384 | HPR085 | 2021-03-01 | Subcontract | 191048631 | 270424632 | 266721598
MCR012385 | HPR085 | 2021-03-01 | Overhead | 38594717 | 54629871 | 32252330
MCR012386 | HPR085 | 2021-04-01 | Labor | 43437730 | 37944908 | 34340070
MCR012387 | HPR085 | 2021-04-01 | Material | 89628109 | 78294384 | 77806003
MCR012388 | HPR085 | 2021-04-01 | Equipment | 23341455 | 20389863 | 22089870
MCR012389 | HPR085 | 2021-04-01 | Subcontract | 154029623 | 134552146 | 133763438
MCR012390 | HPR085 | 2021-04-01 | Overhead | 31116316 | 27181571 | 29236317
MCR012391 | HPR085 | 2021-05-01 | Labor | 31013110 | 44392311 | 52273758
MCR012392 | HPR085 | 2021-05-01 | Material | 63991521 | 91597761 | 92751474
MCR012393 | HPR085 | 2021-05-01 | Equipment | 16665031 | 23854403 | 22685085
MCR012394 | HPR085 | 2021-05-01 | Subcontract | 109972084 | 157414553 | 155337737
MCR012395 | HPR085 | 2021-05-01 | Overhead | 22216026 | 31800123 | 31358653
MCR012396 | HPR085 | 2021-06-01 | Labor | 17528575 | 66083043 | 68125873
MCR012397 | HPR085 | 2021-06-01 | Material | 36167936 | 136353768 | 157206973
MCR012398 | HPR085 | 2021-06-01 | Equipment | 9419057 | 35510013 | 39064627
MCR012399 | HPR085 | 2021-06-01 | Subcontract | 62156098 | 234329607 | 261055488
MCR012400 | HPR085 | 2021-06-01 | Overhead | 12556473 | 47338129 | 29793966
MCR012401 | HPR085 | 2021-07-01 | Labor | 4808147 | 16393280 | 16440607
MCR012402 | HPR085 | 2021-07-01 | Material | 9920985 | 33825403 | 31368947
MCR012403 | HPR085 | 2021-07-01 | Equipment | 2583679 | 8809001 | 8259119
MCR012404 | HPR085 | 2021-07-01 | Subcontract | 17049625 | 58130358 | 51938565
MCR012405 | HPR085 | 2021-07-01 | Overhead | 3444282 | 11743213 | 31123255
MCR012406 | HPR085 | 2021-08-01 | Labor | 0 | 12067988 | 12430675
MCR012407 | HPR085 | 2021-08-01 | Material | 0 | 24900724 | 24647229
MCR012408 | HPR085 | 2021-08-01 | Equipment | 0 | 6484786 | 7309951
MCR012409 | HPR085 | 2021-08-01 | Subcontract | 0 | 42792927 | 34160832
MCR012410 | HPR085 | 2021-08-01 | Overhead | 0 | 8644819 | 30882241
MCR012411 | HPR085 | 2021-09-01 | Labor | 0 | 28756988 | 33016604
MCR012412 | HPR085 | 2021-09-01 | Material | 0 | 59336305 | 54006490
MCR012413 | HPR085 | 2021-09-01 | Equipment | 0 | 15452693 | 16351683
MCR012414 | HPR085 | 2021-09-01 | Subcontract | 0 | 101971901 | 118098700
MCR012415 | HPR085 | 2021-09-01 | Overhead | 0 | 20599868 | 31142183
MCR012416 | HPR085 | 2021-10-01 | Labor | 0 | 10864252 | 10802734
MCR012417 | HPR085 | 2021-10-01 | Material | 0 | 22416972 | 30603455
MCR012418 | HPR085 | 2021-10-01 | Equipment | 0 | 5837954 | 6228465
MCR012419 | HPR085 | 2021-10-01 | Subcontract | 0 | 38524496 | 30061659
MCR012420 | HPR085 | 2021-10-01 | Overhead | 0 | 7782532 | 30747696
MCR012421 | HPR085 | 2021-11-01 | Labor | 0 | 1656395 | 1047584
MCR012422 | HPR085 | 2021-11-01 | Material | 0 | 3417756 | 1698570
MCR012423 | HPR085 | 2021-11-01 | Equipment | 0 | 890071 | 1178709
MCR012424 | HPR085 | 2021-11-01 | Subcontract | 0 | 5873555 | 5734943
MCR012425 | HPR085 | 2021-11-01 | Overhead | 0 | 1186547 | 31015545
MCR012426 | HPR086 | 2023-06-01 | Labor | 15789190 | 10775327 | 10834081
MCR012427 | HPR086 | 2023-06-01 | Material | 36856618 | 25152784 | 26016371
MCR012428 | HPR086 | 2023-06-01 | Equipment | 6568369 | 4482581 | 4690012
MCR012429 | HPR086 | 2023-06-01 | Subcontract | 29773395 | 20318841 | 19631255
MCR012430 | HPR086 | 2023-06-01 | Overhead | 8603161 | 5871223 | 25392001
MCR012431 | HPR086 | 2023-07-01 | Labor | 41592691 | 20835647 | 22556110
MCR012432 | HPR086 | 2023-07-01 | Material | 97089583 | 48636534 | 47655721
MCR012433 | HPR086 | 2023-07-01 | Equipment | 17302734 | 8667717 | 8963294
MCR012434 | HPR086 | 2023-07-01 | Subcontract | 78430597 | 39289409 | 45596366
MCR012435 | HPR086 | 2023-07-01 | Overhead | 22662884 | 11352857 | 24161289
MCR012436 | HPR086 | 2023-08-01 | Labor | 59076910 | 30936369 | 30882883
MCR012437 | HPR086 | 2023-08-01 | Material | 137902897 | 72214590 | 75620925
MCR012438 | HPR086 | 2023-08-01 | Equipment | 24576242 | 12869659 | 13855201
MCR012439 | HPR086 | 2023-08-01 | Subcontract | 111400277 | 58336159 | 58447620
MCR012440 | HPR086 | 2023-08-01 | Overhead | 32189626 | 16856504 | 24735772
MCR012441 | HPR086 | 2023-09-01 | Labor | 68744623 | 38934049 | 49997496
MCR012442 | HPR086 | 2023-09-01 | Material | 160470184 | 90883531 | 85773421
MCR012443 | HPR086 | 2023-09-01 | Equipment | 28598051 | 16196728 | 19571685
MCR012444 | HPR086 | 2023-09-01 | Subcontract | 129630510 | 73417243 | 81679313
MCR012445 | HPR086 | 2023-09-01 | Overhead | 37457337 | 21214253 | 24029812
MCR012446 | HPR086 | 2023-10-01 | Labor | 71170794 | 56521969 | 62427800
MCR012447 | HPR086 | 2023-10-01 | Material | 166133580 | 131938912 | 146770084
MCR012448 | HPR086 | 2023-10-01 | Equipment | 29607348 | 23513376 | 24468593
MCR012449 | HPR086 | 2023-10-01 | Subcontract | 134205497 | 106582469 | 119277330
MCR012450 | HPR086 | 2023-10-01 | Overhead | 38779300 | 30797499 | 25230089
MCR012451 | HPR086 | 2023-11-01 | Labor | 67030537 | 63180352 | 73249362
MCR012452 | HPR086 | 2023-11-01 | Material | 156469003 | 147481538 | 137537927
MCR012453 | HPR086 | 2023-11-01 | Equipment | 27884984 | 26283291 | 25013647
MCR012454 | HPR086 | 2023-11-01 | Subcontract | 126398289 | 119138064 | 125416236
MCR012455 | HPR086 | 2023-11-01 | Overhead | 36523372 | 34425496 | 25467417
MCR012456 | HPR086 | 2023-12-01 | Labor | 57147481 | 43370751 | 46981509
MCR012457 | HPR086 | 2023-12-01 | Material | 133399042 | 101240098 | 107806992
MCR012458 | HPR086 | 2023-12-01 | Equipment | 23773592 | 18042414 | 18583009
MCR012459 | HPR086 | 2023-12-01 | Subcontract | 107761987 | 81783452 | 90969473
MCR012460 | HPR086 | 2023-12-01 | Overhead | 31138326 | 23631708 | 25239683
MCR012461 | HPR086 | 2024-01-01 | Labor | 42588667 | 36426406 | 43454038
MCR012462 | HPR086 | 2024-01-01 | Material | 99414485 | 85029953 | 91278898
MCR012463 | HPR086 | 2024-01-01 | Equipment | 17717064 | 15153538 | 17229200
MCR012464 | HPR086 | 2024-01-01 | Subcontract | 80308691 | 68688624 | 76335023
MCR012465 | HPR086 | 2024-01-01 | Overhead | 23205569 | 19847896 | 25253647
MCR012466 | HPR086 | 2024-02-01 | Labor | 24894421 | 39261198 | 40663812
MCR012467 | HPR086 | 2024-02-01 | Material | 58110906 | 91647191 | 88336631
MCR012468 | HPR086 | 2024-02-01 | Equipment | 10356183 | 16332823 | 19225825
MCR012469 | HPR086 | 2024-02-01 | Subcontract | 46942966 | 74034141 | 65083734
MCR012470 | HPR086 | 2024-02-01 | Overhead | 13564388 | 21392508 | 22969158
MCR012471 | HPR086 | 2024-03-01 | Labor | 7001399 | 45743919 | 71523211
MCR012472 | HPR086 | 2024-03-01 | Material | 16343325 | 106779770 | 115139293
MCR012473 | HPR086 | 2024-03-01 | Equipment | 2912611 | 19029662 | 19058950
MCR012474 | HPR086 | 2024-03-01 | Subcontract | 13202413 | 86258492 | 115336147
MCR012475 | HPR086 | 2024-03-01 | Overhead | 3814898 | 24924791 | 24020898
MCR012476 | HPR086 | 2024-04-01 | Labor | 0 | 18263767 | 41624541
MCR012477 | HPR086 | 2024-04-01 | Material | 0 | 42633007 | 63718651
MCR012478 | HPR086 | 2024-04-01 | Equipment | 0 | 7597803 | 7928762
MCR012479 | HPR086 | 2024-04-01 | Subcontract | 0 | 34439659 | 41876331
MCR012480 | HPR086 | 2024-04-01 | Overhead | 0 | 9951499 | 24448418
MCR012481 | HPR086 | 2024-05-01 | Labor | 0 | 33682234 | 34682844
MCR012482 | HPR086 | 2024-05-01 | Material | 0 | 78624248 | 70968623
MCR012483 | HPR086 | 2024-05-01 | Equipment | 0 | 14011950 | 16275523
MCR012484 | HPR086 | 2024-05-01 | Subcontract | 0 | 63513988 | 66529585
MCR012485 | HPR086 | 2024-05-01 | Overhead | 0 | 18352661 | 25860215
MCR012486 | HPR086 | 2024-06-01 | Labor | 0 | 13694701 | 17829209
MCR012487 | HPR086 | 2024-06-01 | Material | 0 | 31967462 | 39942826
MCR012488 | HPR086 | 2024-06-01 | Equipment | 0 | 5697053 | 6537875
MCR012489 | HPR086 | 2024-06-01 | Subcontract | 0 | 25823853 | 60055403
MCR012490 | HPR086 | 2024-06-01 | Overhead | 0 | 7461922 | 21752173
MCR012491 | HPR086 | 2024-07-01 | Labor | 0 | 3410027 | 4760958
MCR012492 | HPR086 | 2024-07-01 | Material | 0 | 7960006 | 5198940
MCR012493 | HPR086 | 2024-07-01 | Equipment | 0 | 1418585 | 1680027
MCR012494 | HPR086 | 2024-07-01 | Subcontract | 0 | 6430226 | 24578367
MCR012495 | HPR086 | 2024-07-01 | Overhead | 0 | 1858044 | 25631919
MCR012496 | HPR087 | 2017-03-01 | Labor | 1804657 | 1855282 | 1970287
MCR012497 | HPR087 | 2017-03-01 | Material | 7149631 | 7350198 | 6637490
MCR012498 | HPR087 | 2017-03-01 | Equipment | 3515243 | 3613855 | 3762699
MCR012499 | HPR087 | 2017-03-01 | Subcontract | 3531954 | 3631035 | 3672062
MCR012500 | HPR087 | 2017-03-01 | Overhead | 1373580 | 1412113 | 7326861
MCR012501 | HPR087 | 2017-04-01 | Labor | 5055959 | 3630125 | 4052706
MCR012502 | HPR087 | 2017-04-01 | Material | 20030538 | 14381712 | 15404374
MCR012503 | HPR087 | 2017-04-01 | Equipment | 9848368 | 7071023 | 8232887
MCR012504 | HPR087 | 2017-04-01 | Subcontract | 9895187 | 7104639 | 6208526
MCR012505 | HPR087 | 2017-04-01 | Overhead | 3848248 | 2763001 | 6348773
MCR012506 | HPR087 | 2017-05-01 | Labor | 7781209 | 5011835 | 5799679
MCR012507 | HPR087 | 2017-05-01 | Material | 30827344 | 19855728 | 21264934
MCR012508 | HPR087 | 2017-05-01 | Equipment | 15156810 | 9762420 | 10258363
MCR012509 | HPR087 | 2017-05-01 | Subcontract | 15228864 | 9808830 | 8654769
MCR012510 | HPR087 | 2017-05-01 | Overhead | 5922520 | 3814664 | 6188992
MCR012511 | HPR087 | 2017-06-01 | Labor | 9995725 | 7648455 | 8035488
MCR012512 | HPR087 | 2017-06-01 | Material | 39600742 | 30301404 | 27543651
MCR012513 | HPR087 | 2017-06-01 | Equipment | 19470406 | 14898222 | 14425737
MCR012514 | HPR087 | 2017-06-01 | Subcontract | 19562967 | 14969047 | 15375070
MCR012515 | HPR087 | 2017-06-01 | Overhead | 7608057 | 5821477 | 6445359
MCR012516 | HPR087 | 2017-07-01 | Labor | 11715810 | 4144435 | 4806439
MCR012517 | HPR087 | 2017-07-01 | Material | 46415320 | 16419291 | 20507764
MCR012518 | HPR087 | 2017-07-01 | Equipment | 22820914 | 8072835 | 8074449
MCR012519 | HPR087 | 2017-07-01 | Subcontract | 22929403 | 8111213 | 7643277
MCR012520 | HPR087 | 2017-07-01 | Overhead | 8917267 | 3154459 | 6893137
MCR012521 | HPR087 | 2017-08-01 | Labor | 12958906 | 6812485 | 6615673
MCR012522 | HPR087 | 2017-08-01 | Material | 51340177 | 26989485 | 27567788
MCR012523 | HPR087 | 2017-08-01 | Equipment | 25242307 | 13269858 | 14075215
MCR012524 | HPR087 | 2017-08-01 | Subcontract | 25362308 | 13332942 | 14002863
MCR012525 | HPR087 | 2017-08-01 | Overhead | 9863426 | 5185194 | 6808865
MCR012526 | HPR087 | 2017-09-01 | Labor | 13743786 | 6885337 | 8144081
MCR012527 | HPR087 | 2017-09-01 | Material | 54449691 | 27278106 | 24550008
MCR012528 | HPR087 | 2017-09-01 | Equipment | 26771155 | 13411764 | 13217839
MCR012529 | HPR087 | 2017-09-01 | Subcontract | 26898423 | 13475523 | 12275097
MCR012530 | HPR087 | 2017-09-01 | Overhead | 10460823 | 5240644 | 7288447
MCR012531 | HPR087 | 2017-10-01 | Labor | 14090807 | 8493241 | 8443862
MCR012532 | HPR087 | 2017-10-01 | Material | 55824508 | 33648251 | 30491896
MCR012533 | HPR087 | 2017-10-01 | Equipment | 27447108 | 16543758 | 17034422
MCR012534 | HPR087 | 2017-10-01 | Subcontract | 27577590 | 16622407 | 15527057
MCR012535 | HPR087 | 2017-10-01 | Overhead | 10724952 | 6464470 | 6715096
MCR012536 | HPR087 | 2017-11-01 | Labor | 14022232 | 11149078 | 12264500
MCR012537 | HPR087 | 2017-11-01 | Material | 55552830 | 44170060 | 44309832
MCR012538 | HPR087 | 2017-11-01 | Equipment | 27313533 | 21716992 | 23414845
MCR012539 | HPR087 | 2017-11-01 | Subcontract | 27443380 | 21820234 | 21028964
MCR012540 | HPR087 | 2017-11-01 | Overhead | 10672757 | 8485910 | 6304723
MCR012541 | HPR087 | 2017-12-01 | Labor | 13562672 | 13235784 | 11780855
MCR012542 | HPR087 | 2017-12-01 | Material | 53732161 | 52437103 | 55264700
MCR012543 | HPR087 | 2017-12-01 | Equipment | 26418368 | 25781630 | 29475105
MCR012544 | HPR087 | 2017-12-01 | Subcontract | 26543960 | 25904195 | 21060193
MCR012545 | HPR087 | 2017-12-01 | Overhead | 10322972 | 10074167 | 6990183
MCR012546 | HPR087 | 2018-01-01 | Labor | 12739695 | 15369420 | 18828968
MCR012547 | HPR087 | 2018-01-01 | Material | 50471715 | 60890076 | 63785616
MCR012548 | HPR087 | 2018-01-01 | Equipment | 24815312 | 29937684 | 28199751
MCR012549 | HPR087 | 2018-01-01 | Subcontract | 24933283 | 30080006 | 26538042
MCR012550 | HPR087 | 2018-01-01 | Overhead | 9696578 | 11698144 | 6756904
MCR012551 | HPR087 | 2018-02-01 | Labor | 11584704 | 11586828 | 13664459
MCR012552 | HPR087 | 2018-02-01 | Material | 45895911 | 45904322 | 39487456
MCR012553 | HPR087 | 2018-02-01 | Equipment | 22565537 | 22569673 | 25108504
MCR012554 | HPR087 | 2018-02-01 | Subcontract | 22672813 | 22676968 | 25046635
MCR012555 | HPR087 | 2018-02-01 | Overhead | 8817479 | 8819095 | 6094360
MCR012556 | HPR087 | 2018-03-01 | Labor | 10134275 | 7560370 | 6821255
MCR012557 | HPR087 | 2018-03-01 | Material | 40149647 | 29952432 | 33003302
MCR012558 | HPR087 | 2018-03-01 | Equipment | 19740285 | 14726643 | 15549881
MCR012559 | HPR087 | 2018-03-01 | Subcontract | 19834129 | 14796653 | 13692716
MCR012560 | HPR087 | 2018-03-01 | Overhead | 7713512 | 5754433 | 6922566
MCR012561 | HPR087 | 2018-04-01 | Labor | 8432310 | 18315473 | 24978938
MCR012562 | HPR087 | 2018-04-01 | Material | 33406856 | 72561651 | 74533148
MCR012563 | HPR087 | 2018-04-01 | Equipment | 16425072 | 35676221 | 42146706
MCR012564 | HPR087 | 2018-04-01 | Subcontract | 16503156 | 35845824 | 32765905
MCR012565 | HPR087 | 2018-04-01 | Overhead | 6418094 | 13940476 | 6637712
MCR012566 | HPR087 | 2018-05-01 | Labor | 6533843 | 10872499 | 8924110
MCR012567 | HPR087 | 2018-05-01 | Material | 25885570 | 43074317 | 50321789
MCR012568 | HPR087 | 2018-05-01 | Equipment | 12727099 | 21178251 | 18868004
MCR012569 | HPR087 | 2018-05-01 | Subcontract | 12787603 | 21278931 | 20043968
MCR012570 | HPR087 | 2018-05-01 | Overhead | 4973111 | 8275397 | 6738753
MCR012571 | HPR087 | 2018-06-01 | Labor | 4512682 | 10656736 | 10877383
MCR012572 | HPR087 | 2018-06-01 | Material | 17878197 | 42219517 | 39075123
MCR012573 | HPR087 | 2018-06-01 | Equipment | 8790132 | 20757973 | 21239581
MCR012574 | HPR087 | 2018-06-01 | Subcontract | 8831920 | 20856655 | 19894598
MCR012575 | HPR087 | 2018-06-01 | Overhead | 3434742 | 8111174 | 6691434
MCR012576 | HPR087 | 2018-07-01 | Labor | 2480416 | 4877221 | 6144791
MCR012577 | HPR087 | 2018-07-01 | Material | 9826831 | 19322417 | 17327296
MCR012578 | HPR087 | 2018-07-01 | Equipment | 4831535 | 9500208 | 10004211
MCR012579 | HPR087 | 2018-07-01 | Subcontract | 4854504 | 9545372 | 8456602
MCR012580 | HPR087 | 2018-07-01 | Overhead | 1887921 | 3712204 | 6633459
MCR012581 | HPR087 | 2018-08-01 | Labor | 665666 | 4341643 | 4487010
MCR012582 | HPR087 | 2018-08-01 | Material | 2637215 | 17200584 | 18077389
MCR012583 | HPR087 | 2018-08-01 | Equipment | 1296634 | 8456972 | 10106863
MCR012584 | HPR087 | 2018-08-01 | Subcontract | 1302798 | 8497176 | 7703551
MCR012585 | HPR087 | 2018-08-01 | Overhead | 506659 | 3304560 | 6483397
MCR012586 | HPR087 | 2018-09-01 | Labor | 0 | 3527792 | 3192093
MCR012587 | HPR087 | 2018-09-01 | Material | 0 | 13976293 | 15805869
MCR012588 | HPR087 | 2018-09-01 | Equipment | 0 | 6871692 | 5947704
MCR012589 | HPR087 | 2018-09-01 | Subcontract | 0 | 6904360 | 6724780
MCR012590 | HPR087 | 2018-09-01 | Overhead | 0 | 2685112 | 6868405
MCR012591 | HPR087 | 2018-10-01 | Labor | 0 | 3765272 | 4119914
MCR012592 | HPR087 | 2018-10-01 | Material | 0 | 14917135 | 13793340
MCR012593 | HPR087 | 2018-10-01 | Equipment | 0 | 7334274 | 7305807
MCR012594 | HPR087 | 2018-10-01 | Subcontract | 0 | 7369140 | 6572468
MCR012595 | HPR087 | 2018-10-01 | Overhead | 0 | 2865866 | 7207671
MCR012596 | HPR087 | 2018-11-01 | Labor | 0 | 1697282 | 2046815
MCR012597 | HPR087 | 2018-11-01 | Material | 0 | 6724237 | 7328639
MCR012598 | HPR087 | 2018-11-01 | Equipment | 0 | 3306090 | 4159376
MCR012599 | HPR087 | 2018-11-01 | Subcontract | 0 | 3321807 | 3351590
MCR012600 | HPR087 | 2018-11-01 | Overhead | 0 | 1291854 | 6744881
MCR012601 | HPR087 | 2018-12-01 | Labor | 0 | 378761 | 352331
MCR012602 | HPR087 | 2018-12-01 | Material | 0 | 1500564 | 1641437
MCR012603 | HPR087 | 2018-12-01 | Equipment | 0 | 737779 | 447089
MCR012604 | HPR087 | 2018-12-01 | Subcontract | 0 | 741286 | 715878
MCR012605 | HPR087 | 2018-12-01 | Overhead | 0 | 288287 | 6899680
MCR012606 | HPR088 | 2018-08-01 | Labor | 2438899 | 1615751 | 1642121
MCR012607 | HPR088 | 2018-08-01 | Material | 4324736 | 2865103 | 2763913
MCR012608 | HPR088 | 2018-08-01 | Equipment | 1037497 | 687334 | 645709
MCR012609 | HPR088 | 2018-08-01 | Subcontract | 6778673 | 4490817 | 3860144
MCR012610 | HPR088 | 2018-08-01 | Overhead | 1462781 | 969081 | 9196213
MCR012611 | HPR088 | 2018-09-01 | Labor | 6956514 | 4188338 | 4131883
MCR012612 | HPR088 | 2018-09-01 | Material | 12335518 | 7426898 | 6457911
MCR012613 | HPR088 | 2018-09-01 | Equipment | 2959271 | 1781701 | 1718419
MCR012614 | HPR088 | 2018-09-01 | Subcontract | 19334924 | 11641060 | 12019211
MCR012615 | HPR088 | 2018-09-01 | Overhead | 4172316 | 2512044 | 9425854
MCR012616 | HPR088 | 2018-10-01 | Labor | 10941945 | 12781238 | 13352575
MCR012617 | HPR088 | 2018-10-01 | Material | 19402613 | 22664109 | 24422854
MCR012618 | HPR088 | 2018-10-01 | Equipment | 4654657 | 5437084 | 6882228
MCR012619 | HPR088 | 2018-10-01 | Subcontract | 30412024 | 35524153 | 33555173
MCR012620 | HPR088 | 2018-10-01 | Overhead | 6562662 | 7665817 | 9304789
MCR012621 | HPR088 | 2018-11-01 | Labor | 14406353 | 11572390 | 10378529
MCR012622 | HPR088 | 2018-11-01 | Material | 25545816 | 20520539 | 19481659
MCR012623 | HPR088 | 2018-11-01 | Equipment | 6128401 | 4922845 | 4055393
MCR012624 | HPR088 | 2018-11-01 | Subcontract | 40040997 | 32164282 | 33665358
MCR012625 | HPR088 | 2018-11-01 | Overhead | 8640514 | 6940784 | 10048246
MCR012626 | HPR088 | 2018-12-01 | Labor | 17361410 | 10137636 | 11602186
MCR012627 | HPR088 | 2018-12-01 | Material | 30785820 | 17976387 | 19722733
MCR012628 | HPR088 | 2018-12-01 | Equipment | 7385470 | 4312507 | 4761325
MCR012629 | HPR088 | 2018-12-01 | Subcontract | 48254277 | 28176529 | 26132923
MCR012630 | HPR088 | 2018-12-01 | Overhead | 10412871 | 6080260 | 9426093
MCR012631 | HPR088 | 2019-01-01 | Labor | 19819347 | 15707418 | 15979355
MCR012632 | HPR088 | 2019-01-01 | Material | 35144314 | 27852906 | 31987977
MCR012633 | HPR088 | 2019-01-01 | Equipment | 8431066 | 6681869 | 7367666
MCR012634 | HPR088 | 2019-01-01 | Subcontract | 55085863 | 43657172 | 43439565
MCR012635 | HPR088 | 2019-01-01 | Overhead | 11887071 | 9420854 | 9456423
MCR012636 | HPR088 | 2019-02-01 | Labor | 21793023 | 19208456 | 20199834
MCR012637 | HPR088 | 2019-02-01 | Material | 38644101 | 34061061 | 32616914
MCR012638 | HPR088 | 2019-02-01 | Equipment | 9270659 | 8171195 | 6873539
MCR012639 | HPR088 | 2019-02-01 | Subcontract | 60571495 | 53387953 | 51473540
MCR012640 | HPR088 | 2019-02-01 | Overhead | 13070824 | 11520676 | 10024541
MCR012641 | HPR088 | 2019-03-01 | Labor | 23296002 | 21511158 | 20973139
MCR012642 | HPR088 | 2019-03-01 | Material | 41309231 | 38144288 | 40021867
MCR012643 | HPR088 | 2019-03-01 | Equipment | 9910020 | 9150755 | 10377590
MCR012644 | HPR088 | 2019-03-01 | Subcontract | 64748871 | 59788080 | 56944416
MCR012645 | HPR088 | 2019-03-01 | Overhead | 13972267 | 12901770 | 9141908
MCR012646 | HPR088 | 2019-04-01 | Labor | 24342641 | 16798515 | 19313066
MCR012647 | HPR088 | 2019-04-01 | Material | 43165166 | 29787676 | 28037568
MCR012648 | HPR088 | 2019-04-01 | Equipment | 10355256 | 7146017 | 7824596
MCR012649 | HPR088 | 2019-04-01 | Subcontract | 67657898 | 46689768 | 44618530
MCR012650 | HPR088 | 2019-04-01 | Overhead | 14600011 | 10075263 | 10110141
MCR012651 | HPR088 | 2019-05-01 | Labor | 24948206 | 23253482 | 22234623
MCR012652 | HPR088 | 2019-05-01 | Material | 44238974 | 41233833 | 45412429
MCR012653 | HPR088 | 2019-05-01 | Equipment | 10612861 | 9891932 | 11030705
MCR012654 | HPR088 | 2019-05-01 | Subcontract | 69341006 | 64630691 | 58467339
MCR012655 | HPR088 | 2019-05-01 | Overhead | 14963212 | 13946765 | 8791706
MCR012656 | HPR088 | 2019-06-01 | Labor | 25129007 | 17852451 | 19433544
MCR012657 | HPR088 | 2019-06-01 | Material | 44559575 | 31656549 | 26207499
MCR012658 | HPR088 | 2019-06-01 | Equipment | 10689772 | 7594357 | 8093378
MCR012659 | HPR088 | 2019-06-01 | Subcontract | 69843523 | 49619075 | 49293900
MCR012660 | HPR088 | 2019-06-01 | Overhead | 15071651 | 10707383 | 9459769
MCR012661 | HPR088 | 2019-07-01 | Labor | 24902563 | 23506396 | 25613808
MCR012662 | HPR088 | 2019-07-01 | Material | 44158039 | 41682309 | 47107752
MCR012663 | HPR088 | 2019-07-01 | Equipment | 10593444 | 9999521 | 9171180
MCR012664 | HPR088 | 2019-07-01 | Subcontract | 69214146 | 65333640 | 67362825
MCR012665 | HPR088 | 2019-07-01 | Overhead | 14935837 | 14098456 | 8831248
MCR012666 | HPR088 | 2019-08-01 | Labor | 24287824 | 14701585 | 15176936
MCR012667 | HPR088 | 2019-08-01 | Material | 43067963 | 26069330 | 22286254
MCR012668 | HPR088 | 2019-08-01 | Equipment | 10331937 | 6253992 | 6539652
MCR012669 | HPR088 | 2019-08-01 | Subcontract | 67505541 | 40861562 | 34919398
MCR012670 | HPR088 | 2019-08-01 | Overhead | 14567134 | 8817585 | 8983689
MCR012671 | HPR088 | 2019-09-01 | Labor | 23305440 | 15496124 | 16897810
MCR012672 | HPR088 | 2019-09-01 | Material | 41325967 | 27478233 | 30493938
MCR012673 | HPR088 | 2019-09-01 | Equipment | 9914035 | 6591985 | 7737480
MCR012674 | HPR088 | 2019-09-01 | Subcontract | 64775103 | 43069902 | 42508517
MCR012675 | HPR088 | 2019-09-01 | Overhead | 13977928 | 9294126 | 9746951
MCR012676 | HPR088 | 2019-10-01 | Labor | 21978127 | 18767295 | 19685010
MCR012677 | HPR088 | 2019-10-01 | Material | 38972333 | 33278780 | 34754391
MCR012678 | HPR088 | 2019-10-01 | Equipment | 9349402 | 7983527 | 8784278
MCR012679 | HPR088 | 2019-10-01 | Subcontract | 61085974 | 52161790 | 48221675
MCR012680 | HPR088 | 2019-10-01 | Overhead | 13181845 | 11256080 | 8909885
MCR012681 | HPR088 | 2019-11-01 | Labor | 20331164 | 18842414 | 18686355
MCR012682 | HPR088 | 2019-11-01 | Material | 36051884 | 33411985 | 32261934
MCR012683 | HPR088 | 2019-11-01 | Equipment | 8648791 | 8015483 | 7148283
MCR012684 | HPR088 | 2019-11-01 | Subcontract | 56508406 | 52370578 | 50217625
MCR012685 | HPR088 | 2019-11-01 | Overhead | 12194044 | 11301135 | 10492592
MCR012686 | HPR088 | 2019-12-01 | Labor | 18393071 | 16087262 | 18584806
MCR012687 | HPR088 | 2019-12-01 | Material | 32615195 | 28526459 | 30139416
MCR012688 | HPR088 | 2019-12-01 | Equipment | 7824334 | 6843453 | 7891882
MCR012689 | HPR088 | 2019-12-01 | Subcontract | 51121674 | 44712912 | 38220869
MCR012690 | HPR088 | 2019-12-01 | Overhead | 11031632 | 9648674 | 9568881
MCR012691 | HPR088 | 2020-01-01 | Labor | 16196616 | 17663930 | 17477096
MCR012692 | HPR088 | 2020-01-01 | Material | 28720368 | 31322258 | 27764394
MCR012693 | HPR088 | 2020-01-01 | Equipment | 6889971 | 7514161 | 7863741
MCR012694 | HPR088 | 2020-01-01 | Subcontract | 45016848 | 49095101 | 52839136
MCR012695 | HPR088 | 2020-01-01 | Overhead | 9714261 | 10594314 | 8767735
MCR012696 | HPR088 | 2020-02-01 | Labor | 13780331 | 22245738 | 26790021
MCR012697 | HPR088 | 2020-02-01 | Material | 24435734 | 39446870 | 41533742
MCR012698 | HPR088 | 2020-02-01 | Equipment | 5862094 | 9463242 | 8614526
MCR012699 | HPR088 | 2020-02-01 | Subcontract | 38301032 | 61829771 | 59902955
MCR012700 | HPR088 | 2020-02-01 | Overhead | 8265044 | 13342350 | 9316275
MCR012701 | HPR088 | 2020-03-01 | Labor | 11191002 | 13213291 | 14528831
MCR012702 | HPR088 | 2020-03-01 | Material | 19844250 | 23430240 | 21905701
MCR012703 | HPR088 | 2020-03-01 | Equipment | 4760605 | 5620878 | 6574648
MCR012704 | HPR088 | 2020-03-01 | Subcontract | 31104254 | 36725001 | 34767283
MCR012705 | HPR088 | 2020-03-01 | Overhead | 6712039 | 7924950 | 9326108
MCR012706 | HPR088 | 2020-04-01 | Labor | 8488072 | 23807987 | 24355179
MCR012707 | HPR088 | 2020-04-01 | Material | 15051327 | 42217100 | 44253854
MCR012708 | HPR088 | 2020-04-01 | Equipment | 3610790 | 10127816 | 9618609
MCR012709 | HPR088 | 2020-04-01 | Subcontract | 23591735 | 66171882 | 68689937
MCR012710 | HPR088 | 2020-04-01 | Overhead | 5090900 | 14279341 | 10017678
MCR012711 | HPR088 | 2020-05-01 | Labor | 5752586 | 10127289 | 12302279
MCR012712 | HPR088 | 2020-05-01 | Material | 10200673 | 17958040 | 19069280
MCR012713 | HPR088 | 2020-05-01 | Equipment | 2447125 | 4308106 | 5377969
MCR012714 | HPR088 | 2020-05-01 | Subcontract | 15988728 | 28147771 | 26269211
MCR012715 | HPR088 | 2020-05-01 | Overhead | 3450234 | 6074055 | 9033591
MCR012716 | HPR088 | 2020-06-01 | Labor | 3109640 | 9333935 | 11417861
MCR012717 | HPR088 | 2020-06-01 | Material | 5514115 | 16551239 | 15395479
MCR012718 | HPR088 | 2020-06-01 | Equipment | 1322828 | 3970616 | 4208787
MCR012719 | HPR088 | 2020-06-01 | Subcontract | 8642929 | 25942725 | 22847571
MCR012720 | HPR088 | 2020-06-01 | Overhead | 1865072 | 5598224 | 9409531
MCR012721 | HPR088 | 2020-07-01 | Labor | 823247 | 4255937 | 4303211
MCR012722 | HPR088 | 2020-07-01 | Material | 1459808 | 7546766 | 8948096
MCR012723 | HPR088 | 2020-07-01 | Equipment | 350206 | 1810457 | 1689192
MCR012724 | HPR088 | 2020-07-01 | Subcontract | 2288130 | 11828943 | 12455999
MCR012725 | HPR088 | 2020-07-01 | Overhead | 493759 | 2552588 | 9998999
MCR012726 | HPR088 | 2020-08-01 | Labor | 0 | 5459143 | 6697251
MCR012727 | HPR088 | 2020-08-01 | Material | 0 | 9680331 | 10640079
MCR012728 | HPR088 | 2020-08-01 | Equipment | 0 | 2322296 | 1911438
MCR012729 | HPR088 | 2020-08-01 | Subcontract | 0 | 15173134 | 14846628
MCR012730 | HPR088 | 2020-08-01 | Overhead | 0 | 3274236 | 10284986
MCR012731 | HPR088 | 2020-09-01 | Labor | 0 | 5611331 | 5587763
MCR012732 | HPR088 | 2020-09-01 | Material | 0 | 9950196 | 10391512
MCR012733 | HPR088 | 2020-09-01 | Equipment | 0 | 2387036 | 2468116
MCR012734 | HPR088 | 2020-09-01 | Subcontract | 0 | 15596125 | 14605847
MCR012735 | HPR088 | 2020-09-01 | Overhead | 0 | 3365514 | 9981135
MCR012736 | HPR088 | 2020-10-01 | Labor | 0 | 5485040 | 6445465
MCR012737 | HPR088 | 2020-10-01 | Material | 0 | 9726252 | 10742660
MCR012738 | HPR088 | 2020-10-01 | Equipment | 0 | 2333313 | 2887931
MCR012739 | HPR088 | 2020-10-01 | Subcontract | 0 | 15245112 | 15461929
MCR012740 | HPR088 | 2020-10-01 | Overhead | 0 | 3289768 | 9952722
MCR012741 | HPR088 | 2020-11-01 | Labor | 0 | 1930385 | 2214540
MCR012742 | HPR088 | 2020-11-01 | Material | 0 | 3423021 | 2992782
MCR012743 | HPR088 | 2020-11-01 | Equipment | 0 | 821177 | 728035
MCR012744 | HPR088 | 2020-11-01 | Subcontract | 0 | 5365308 | 4743144
MCR012745 | HPR088 | 2020-11-01 | Overhead | 0 | 1157789 | 9296643
MCR012746 | HPR088 | 2020-12-01 | Labor | 0 | 2381525 | 2682204
MCR012747 | HPR088 | 2020-12-01 | Material | 0 | 4222997 | 4181316
MCR012748 | HPR088 | 2020-12-01 | Equipment | 0 | 1013090 | 1127510
MCR012749 | HPR088 | 2020-12-01 | Subcontract | 0 | 6619206 | 6865950
MCR012750 | HPR088 | 2020-12-01 | Overhead | 0 | 1428370 | 10378939
MCR012751 | HPR088 | 2021-01-01 | Labor | 0 | 429591 | 500786
MCR012752 | HPR088 | 2021-01-01 | Material | 0 | 761765 | 885380
MCR012753 | HPR088 | 2021-01-01 | Equipment | 0 | 182746 | 209377
MCR012754 | HPR088 | 2021-01-01 | Subcontract | 0 | 1194005 | 1177244
MCR012755 | HPR088 | 2021-01-01 | Overhead | 0 | 257656 | 10566806
MCR012756 | HPR089 | 2022-03-01 | Labor | 1595690 | 1340089 | 1395241
MCR012757 | HPR089 | 2022-03-01 | Material | 5217774 | 4381980 | 4546839
MCR012758 | HPR089 | 2022-03-01 | Equipment | 1534356 | 1288579 | 1418936
MCR012759 | HPR089 | 2022-03-01 | Subcontract | 6194898 | 5202586 | 4433418
MCR012760 | HPR089 | 2022-03-01 | Overhead | 1425683 | 1197314 | 10361266
MCR012761 | HPR089 | 2022-04-01 | Labor | 4569915 | 2394804 | 2573596
MCR012762 | HPR089 | 2022-04-01 | Material | 14943238 | 7830809 | 7390740
MCR012763 | HPR089 | 2022-04-01 | Equipment | 4394258 | 2302754 | 2361969
MCR012764 | HPR089 | 2022-04-01 | Subcontract | 17741635 | 9297273 | 9780498
MCR012765 | HPR089 | 2022-04-01 | Overhead | 4083029 | 2139658 | 9484489
MCR012766 | HPR089 | 2022-05-01 | Labor | 7222885 | 5529129 | 6583704
MCR012767 | HPR089 | 2022-05-01 | Material | 23618230 | 18079787 | 20164450
MCR012768 | HPR089 | 2022-05-01 | Equipment | 6945255 | 5316602 | 5964337
MCR012769 | HPR089 | 2022-05-01 | Subcontract | 28041179 | 21465560 | 19608939
MCR012770 | HPR089 | 2022-05-01 | Overhead | 6453348 | 4940046 | 9729340
MCR012771 | HPR089 | 2022-06-01 | Labor | 9560766 | 8313034 | 8189431
MCR012772 | HPR089 | 2022-06-01 | Material | 31262903 | 27182925 | 24897881
MCR012773 | HPR089 | 2022-06-01 | Equipment | 9193272 | 7993501 | 7646990
MCR012774 | HPR089 | 2022-06-01 | Subcontract | 37117458 | 32273429 | 34954524
MCR012775 | HPR089 | 2022-06-01 | Overhead | 8542146 | 7427350 | 9564598
MCR012776 | HPR089 | 2022-07-01 | Labor | 11589975 | 5956306 | 7749528
MCR012777 | HPR089 | 2022-07-01 | Material | 37898246 | 19476622 | 21749884
MCR012778 | HPR089 | 2022-07-01 | Equipment | 11144483 | 5727360 | 5476284
MCR012779 | HPR089 | 2022-07-01 | Subcontract | 44995391 | 23123978 | 20467507
MCR012780 | HPR089 | 2022-07-01 | Overhead | 10355160 | 5321712 | 10634019
MCR012781 | HPR089 | 2022-08-01 | Labor | 13317211 | 5106299 | 5969250
MCR012782 | HPR089 | 2022-08-01 | Material | 43546165 | 16697171 | 19639940
MCR012783 | HPR089 | 2022-08-01 | Equipment | 12805329 | 4910025 | 4761157
MCR012784 | HPR089 | 2022-08-01 | Subcontract | 51700987 | 19824024 | 14927574
MCR012785 | HPR089 | 2022-08-01 | Overhead | 11898374 | 4562266 | 9987880
MCR012786 | HPR089 | 2022-09-01 | Labor | 14749484 | 14170816 | 13979395
MCR012787 | HPR089 | 2022-09-01 | Material | 48229578 | 46337382 | 44518297
MCR012788 | HPR089 | 2022-09-01 | Equipment | 14182549 | 13626123 | 14087854
MCR012789 | HPR089 | 2022-09-01 | Subcontract | 57261455 | 55014910 | 60348343
MCR012790 | HPR089 | 2022-09-01 | Overhead | 13178050 | 12661035 | 10276736
MCR012791 | HPR089 | 2022-10-01 | Labor | 15894145 | 7790050 | 10055773
MCR012792 | HPR089 | 2022-10-01 | Material | 51972524 | 25472810 | 27181973
MCR012793 | HPR089 | 2022-10-01 | Equipment | 15283212 | 7490618 | 7861722
MCR012794 | HPR089 | 2022-10-01 | Subcontract | 61705337 | 30243063 | 29063625
MCR012795 | HPR089 | 2022-10-01 | Overhead | 14200757 | 6960085 | 10228388
MCR012796 | HPR089 | 2022-11-01 | Labor | 16758930 | 11645086 | 12848035
MCR012797 | HPR089 | 2022-11-01 | Material | 54800299 | 38078454 | 38766449
MCR012798 | HPR089 | 2022-11-01 | Equipment | 16114756 | 11197476 | 11536151
MCR012799 | HPR089 | 2022-11-01 | Subcontract | 65062664 | 45209347 | 45223807
MCR012800 | HPR089 | 2022-11-01 | Overhead | 14973407 | 10404399 | 10834113
MCR012801 | HPR089 | 2022-12-01 | Labor | 17352005 | 10159772 | 12528746
MCR012802 | HPR089 | 2022-12-01 | Material | 56739604 | 33221602 | 34689858
MCR012803 | HPR089 | 2022-12-01 | Equipment | 16685035 | 9769254 | 9893461
MCR012804 | HPR089 | 2022-12-01 | Subcontract | 67365141 | 39442960 | 35025402
MCR012805 | HPR089 | 2022-12-01 | Overhead | 15503295 | 9077333 | 10190069
MCR012806 | HPR089 | 2023-01-01 | Labor | 17682024 | 15033016 | 17510662
MCR012807 | HPR089 | 2023-01-01 | Material | 57818737 | 49156702 | 55668457
MCR012808 | HPR089 | 2023-01-01 | Equipment | 17002369 | 14455182 | 15514848
MCR012809 | HPR089 | 2023-01-01 | Subcontract | 68646361 | 58362200 | 49434819
MCR012810 | HPR089 | 2023-01-01 | Overhead | 15798153 | 13431374 | 11410093
MCR012811 | HPR089 | 2023-02-01 | Labor | 17758196 | 12616280 | 13740183
MCR012812 | HPR089 | 2023-02-01 | Material | 58067814 | 41254178 | 34566815
MCR012813 | HPR089 | 2023-02-01 | Equipment | 17075613 | 12131339 | 10150222
MCR012814 | HPR089 | 2023-02-01 | Subcontract | 68942082 | 48979783 | 51952331
MCR012815 | HPR089 | 2023-02-01 | Overhead | 15866209 | 11272121 | 10496462
MCR012816 | HPR089 | 2023-03-01 | Labor | 17590372 | 20767166 | 26974902
MCR012817 | HPR089 | 2023-03-01 | Material | 57519043 | 67906893 | 63018472
MCR012818 | HPR089 | 2023-03-01 | Equipment | 16914239 | 19968925 | 23429082
MCR012819 | HPR089 | 2023-03-01 | Subcontract | 68290544 | 80623710 | 77099620
MCR012820 | HPR089 | 2023-03-01 | Overhead | 15716265 | 18554598 | 9984305
MCR012821 | HPR089 | 2023-04-01 | Labor | 17189148 | 17334731 | 17344699
MCR012822 | HPR089 | 2023-04-01 | Material | 56207073 | 56683117 | 51508920
MCR012823 | HPR089 | 2023-04-01 | Equipment | 16528437 | 16668424 | 15140442
MCR012824 | HPR089 | 2023-04-01 | Subcontract | 66732884 | 67298075 | 59842595
MCR012825 | HPR089 | 2023-04-01 | Overhead | 15357788 | 15487860 | 10686600
MCR012826 | HPR089 | 2023-05-01 | Labor | 16565998 | 9794374 | 12225031
MCR012827 | HPR089 | 2023-05-01 | Material | 54169427 | 32026783 | 30467383
MCR012828 | HPR089 | 2023-05-01 | Equipment | 15929240 | 9417901 | 10453604
MCR012829 | HPR089 | 2023-05-01 | Subcontract | 64313650 | 38024389 | 35259764
MCR012830 | HPR089 | 2023-05-01 | Overhead | 14801030 | 8750866 | 9513037
MCR012831 | HPR089 | 2023-06-01 | Labor | 15733449 | 21166879 | 21699057
MCR012832 | HPR089 | 2023-06-01 | Material | 51447059 | 69213922 | 67424281
MCR012833 | HPR089 | 2023-06-01 | Equipment | 15128692 | 20353274 | 20923495
MCR012834 | HPR089 | 2023-06-01 | Subcontract | 61081469 | 82175505 | 86300929
MCR012835 | HPR089 | 2023-06-01 | Overhead | 14057182 | 18911726 | 9547497
MCR012836 | HPR089 | 2023-07-01 | Labor | 14705300 | 11235083 | 13741075
MCR012837 | HPR089 | 2023-07-01 | Material | 48085101 | 36737779 | 39113509
MCR012838 | HPR089 | 2023-07-01 | Equipment | 14140063 | 10803232 | 9038433
MCR012839 | HPR089 | 2023-07-01 | Subcontract | 57089922 | 43617605 | 39364705
MCR012840 | HPR089 | 2023-07-01 | Overhead | 13138574 | 10038079 | 10416663
MCR012841 | HPR089 | 2023-08-01 | Labor | 13496939 | 6335301 | 6786550
MCR012842 | HPR089 | 2023-08-01 | Material | 44133859 | 20715903 | 15032647
MCR012843 | HPR089 | 2023-08-01 | Equipment | 12978148 | 6091787 | 7177015
MCR012844 | HPR089 | 2023-08-01 | Subcontract | 52398737 | 24595338 | 22767098
MCR012845 | HPR089 | 2023-08-01 | Overhead | 12058953 | 5660328 | 10316322
MCR012846 | HPR089 | 2023-09-01 | Labor | 12125761 | 15270028 | 18003257
MCR012847 | HPR089 | 2023-09-01 | Material | 39650223 | 49931711 | 47823032
MCR012848 | HPR089 | 2023-09-01 | Equipment | 11659675 | 14683084 | 15953202
MCR012849 | HPR089 | 2023-09-01 | Subcontract | 47075458 | 59282344 | 50008649
MCR012850 | HPR089 | 2023-09-01 | Overhead | 10833863 | 13643134 | 10008528
MCR012851 | HPR089 | 2023-10-01 | Labor | 10611802 | 12711638 | 13856031
MCR012852 | HPR089 | 2023-10-01 | Material | 34699703 | 41565992 | 44260996
MCR012853 | HPR089 | 2023-10-01 | Equipment | 10203909 | 12223033 | 10260149
MCR012854 | HPR089 | 2023-10-01 | Subcontract | 41197861 | 49349990 | 55793855
MCR012855 | HPR089 | 2023-10-01 | Overhead | 9481203 | 11357320 | 9818962
MCR012856 | HPR089 | 2023-11-01 | Labor | 8978686 | 15824731 | 18370901
MCR012857 | HPR089 | 2023-11-01 | Material | 29359550 | 51745546 | 47850287
MCR012858 | HPR089 | 2023-11-01 | Equipment | 8633566 | 15216466 | 18014298
MCR012859 | HPR089 | 2023-11-01 | Subcontract | 34857667 | 61435853 | 59478369
MCR012860 | HPR089 | 2023-11-01 | Overhead | 8022082 | 14138739 | 9623690
MCR012861 | HPR089 | 2023-12-01 | Labor | 7255186 | 12766793 | 15444740
MCR012862 | HPR089 | 2023-12-01 | Material | 23723851 | 41746342 | 42917790
MCR012863 | HPR089 | 2023-12-01 | Equipment | 6976314 | 12276067 | 12734775
MCR012864 | HPR089 | 2023-12-01 | Subcontract | 28166579 | 49564114 | 77983896
MCR012865 | HPR089 | 2023-12-01 | Overhead | 6482207 | 11406598 | 10037870
MCR012866 | HPR089 | 2024-01-01 | Labor | 5477998 | 4462107 | 5268871
MCR012867 | HPR089 | 2024-01-01 | Material | 17912594 | 14590717 | 13337862
MCR012868 | HPR089 | 2024-01-01 | Equipment | 5267436 | 4290594 | 4320675
MCR012869 | HPR089 | 2024-01-01 | Subcontract | 21267057 | 17323098 | 40756581
MCR012870 | HPR089 | 2024-01-01 | Overhead | 4894363 | 3986707 | 10127892
MCR012871 | HPR089 | 2024-02-01 | Labor | 3697368 | 12351960 | 14916153
MCR012872 | HPR089 | 2024-02-01 | Material | 12090085 | 40389874 | 33836725
MCR012873 | HPR089 | 2024-02-01 | Equipment | 3555250 | 11877180 | 12363193
MCR012874 | HPR089 | 2024-02-01 | Subcontract | 14354176 | 47953623 | 67583707
MCR012875 | HPR089 | 2024-02-01 | Overhead | 3303445 | 11035962 | 9709504
MCR012876 | HPR089 | 2024-03-01 | Labor | 1991281 | 11683738 | 11479666
MCR012877 | HPR089 | 2024-03-01 | Material | 6511323 | 38204845 | 40353307
MCR012878 | HPR089 | 2024-03-01 | Equipment | 1914741 | 11234643 | 11560481
MCR012879 | HPR089 | 2024-03-01 | Subcontract | 7730688 | 45359406 | 59867657
MCR012880 | HPR089 | 2024-03-01 | Overhead | 1779127 | 10438934 | 10465709
MCR012881 | HPR089 | 2024-04-01 | Labor | 525552 | 9014902 | 11177266
MCR012882 | HPR089 | 2024-04-01 | Material | 1718512 | 29477974 | 29186524
MCR012883 | HPR089 | 2024-04-01 | Equipment | 505351 | 8668390 | 7512640
MCR012884 | HPR089 | 2024-04-01 | Subcontract | 2040335 | 34998267 | 44971613
MCR012885 | HPR089 | 2024-04-01 | Overhead | 469559 | 8054440 | 10613037
MCR012886 | HPR089 | 2024-05-01 | Labor | 0 | 4436678 | 5605049
MCR012887 | HPR089 | 2024-05-01 | Material | 0 | 14507565 | 13434873
MCR012888 | HPR089 | 2024-05-01 | Equipment | 0 | 4266142 | 4673000
MCR012889 | HPR089 | 2024-05-01 | Subcontract | 0 | 17224374 | 47933455
MCR012890 | HPR089 | 2024-05-01 | Overhead | 0 | 3963987 | 10190273
MCR012891 | HPR089 | 2024-06-01 | Labor | 0 | 2721102 | 3516299
MCR012892 | HPR089 | 2024-06-01 | Material | 0 | 8897775 | 9961510
MCR012893 | HPR089 | 2024-06-01 | Equipment | 0 | 2616509 | 3328146
MCR012894 | HPR089 | 2024-06-01 | Subcontract | 0 | 10564047 | 39832847
MCR012895 | HPR089 | 2024-06-01 | Overhead | 0 | 2431191 | 9678528
MCR012896 | HPR089 | 2024-07-01 | Labor | 0 | 2425965 | 2681686
MCR012897 | HPR089 | 2024-07-01 | Material | 0 | 7932704 | 6907583
MCR012898 | HPR089 | 2024-07-01 | Equipment | 0 | 2332717 | 2294298
MCR012899 | HPR089 | 2024-07-01 | Subcontract | 0 | 9418249 | 27259145
MCR012900 | HPR089 | 2024-07-01 | Overhead | 0 | 2167499 | 10437615
MCR012901 | HPR089 | 2024-08-01 | Labor | 0 | 1092171 | 1346604
MCR012902 | HPR089 | 2024-08-01 | Material | 0 | 3571307 | 3872729
MCR012903 | HPR089 | 2024-08-01 | Equipment | 0 | 1050190 | 1081205
MCR012904 | HPR089 | 2024-08-01 | Subcontract | 0 | 4240099 | 31117549
MCR012905 | HPR089 | 2024-08-01 | Overhead | 0 | 975809 | 9242393
MCR012906 | HPR089 | 2024-09-01 | Labor | 0 | 2157172 | 2606428
MCR012907 | HPR089 | 2024-09-01 | Material | 0 | 7053771 | 6640856
MCR012908 | HPR089 | 2024-09-01 | Equipment | 0 | 2074255 | 2272868
MCR012909 | HPR089 | 2024-09-01 | Subcontract | 0 | 8374720 | 28206388
MCR012910 | HPR089 | 2024-09-01 | Overhead | 0 | 1927343 | 9336826
MCR012911 | HPR089 | 2024-10-01 | Labor | 0 | 388870 | 538608
MCR012912 | HPR089 | 2024-10-01 | Material | 0 | 1271572 | 1229522
MCR012913 | HPR089 | 2024-10-01 | Equipment | 0 | 373923 | 481893
MCR012914 | HPR089 | 2024-10-01 | Subcontract | 0 | 1509697 | 27595953
MCR012915 | HPR089 | 2024-10-01 | Overhead | 0 | 347439 | 9861717
MCR012916 | HPR090 | 2020-08-01 | Labor | 1695958 | 594451 | 637169
MCR012917 | HPR090 | 2020-08-01 | Material | 5435789 | 1905300 | 1745814
MCR012918 | HPR090 | 2020-08-01 | Equipment | 1903649 | 667249 | 664413
MCR012919 | HPR090 | 2020-08-01 | Subcontract | 3656301 | 1281571 | 1255129
MCR012920 | HPR090 | 2020-08-01 | Overhead | 1550014 | 543296 | 13656847
MCR012921 | HPR090 | 2020-09-01 | Labor | 4888393 | 2807465 | 3129942
MCR012922 | HPR090 | 2020-09-01 | Material | 15668003 | 8998329 | 9685048
MCR012923 | HPR090 | 2020-09-01 | Equipment | 5487039 | 3151274 | 3391075
MCR012924 | HPR090 | 2020-09-01 | Subcontract | 10538845 | 6052590 | 5390148
MCR012925 | HPR090 | 2020-09-01 | Overhead | 4467727 | 2565871 | 12369680
MCR012926 | HPR090 | 2020-10-01 | Labor | 7785146 | 5336557 | 5884912
MCR012927 | HPR090 | 2020-10-01 | Material | 24952512 | 17104432 | 16366402
MCR012928 | HPR090 | 2020-10-01 | Equipment | 8738535 | 5990086 | 6138522
MCR012929 | HPR090 | 2020-10-01 | Subcontract | 16783930 | 11505038 | 12244335
MCR012930 | HPR090 | 2020-10-01 | Overhead | 7115202 | 4877324 | 12419003
MCR012931 | HPR090 | 2020-11-01 | Labor | 10391063 | 5193744 | 5958283
MCR012932 | HPR090 | 2020-11-01 | Material | 33304850 | 16646695 | 17140294
MCR012933 | HPR090 | 2020-11-01 | Equipment | 11663580 | 5829783 | 6757810
MCR012934 | HPR090 | 2020-11-01 | Subcontract | 22402004 | 11197148 | 10195317
MCR012935 | HPR090 | 2020-11-01 | Overhead | 9496869 | 4746801 | 12742089
MCR012936 | HPR090 | 2020-12-01 | Labor | 12711161 | 5436950 | 5155802
MCR012937 | HPR090 | 2020-12-01 | Material | 40741096 | 17426205 | 18220332
MCR012938 | HPR090 | 2020-12-01 | Equipment | 14267802 | 6102773 | 6719160
MCR012939 | HPR090 | 2020-12-01 | Subcontract | 27403882 | 11721473 | 10465580
MCR012940 | HPR090 | 2020-12-01 | Overhead | 11617313 | 4969078 | 13656125
MCR012941 | HPR090 | 2021-01-01 | Labor | 14750640 | 4489762 | 5819260
MCR012942 | HPR090 | 2021-01-01 | Material | 47277921 | 14390331 | 15257277
MCR012943 | HPR090 | 2021-01-01 | Equipment | 16557042 | 5039589 | 5009554
MCR012944 | HPR090 | 2021-01-01 | Subcontract | 31800779 | 9679438 | 10828704
MCR012945 | HPR090 | 2021-01-01 | Overhead | 13481287 | 4103399 | 12532446
MCR012946 | HPR090 | 2021-02-01 | Labor | 16514904 | 11387657 | 11719355
MCR012947 | HPR090 | 2021-02-01 | Material | 52932639 | 36499078 | 39971493
MCR012948 | HPR090 | 2021-02-01 | Equipment | 18537362 | 12782219 | 13480771
MCR012949 | HPR090 | 2021-02-01 | Subcontract | 35604339 | 24550553 | 24288575
MCR012950 | HPR090 | 2021-02-01 | Overhead | 15093728 | 10407703 | 12327881
MCR012951 | HPR090 | 2021-03-01 | Labor | 18009572 | 14881671 | 16244649
MCR012952 | HPR090 | 2021-03-01 | Material | 57723265 | 47697893 | 52021007
MCR012953 | HPR090 | 2021-03-01 | Equipment | 20215071 | 16704119 | 19571020
MCR012954 | HPR090 | 2021-03-01 | Subcontract | 38826682 | 32083267 | 31475865
MCR012955 | HPR090 | 2021-03-01 | Overhead | 16459774 | 13601042 | 12341066
MCR012956 | HPR090 | 2021-04-01 | Labor | 19240505 | 12813576 | 16000558
MCR012957 | HPR090 | 2021-04-01 | Material | 61668584 | 41069353 | 42487607
MCR012958 | HPR090 | 2021-04-01 | Equipment | 21596748 | 14382760 | 15657525
MCR012959 | HPR090 | 2021-04-01 | Subcontract | 41480441 | 27624679 | 26009763
MCR012960 | HPR090 | 2021-04-01 | Overhead | 17584781 | 11710915 | 11102904
MCR012961 | HPR090 | 2021-05-01 | Labor | 20213828 | 7717193 | 7597474
MCR012962 | HPR090 | 2021-05-01 | Material | 64788224 | 24734714 | 26543419
MCR012963 | HPR090 | 2021-05-01 | Equipment | 22689266 | 8662261 | 9099508
MCR012964 | HPR090 | 2021-05-01 | Subcontract | 43578820 | 16637431 | 16219841
MCR012965 | HPR090 | 2021-05-01 | Overhead | 18474345 | 7053097 | 12501091
MCR012966 | HPR090 | 2021-06-01 | Labor | 20935957 | 12784833 | 16565734
MCR012967 | HPR090 | 2021-06-01 | Material | 67102750 | 40977227 | 45607527
MCR012968 | HPR090 | 2021-06-01 | Equipment | 23499829 | 14350497 | 14156152
MCR012969 | HPR090 | 2021-06-01 | Subcontract | 45135650 | 27562712 | 30930139
MCR012970 | HPR090 | 2021-06-01 | Overhead | 19134332 | 11684646 | 12279266
MCR012971 | HPR090 | 2021-07-01 | Labor | 21413631 | 4466822 | 4221787
MCR012972 | HPR090 | 2021-07-01 | Material | 68633764 | 14316807 | 16954915
MCR012973 | HPR090 | 2021-07-01 | Equipment | 24036000 | 5013841 | 5667932
MCR012974 | HPR090 | 2021-07-01 | Subcontract | 46165464 | 9629984 | 8099519
MCR012975 | HPR090 | 2021-07-01 | Overhead | 19570900 | 4082434 | 11900427
MCR012976 | HPR090 | 2021-08-01 | Labor | 21653953 | 10166684 | 12298401
MCR012977 | HPR090 | 2021-08-01 | Material | 69404032 | 32585682 | 37012677
MCR012978 | HPR090 | 2021-08-01 | Equipment | 24305753 | 11411722 | 12605705
MCR012979 | HPR090 | 2021-08-01 | Subcontract | 46683573 | 21918266 | 21517974
MCR012980 | HPR090 | 2021-08-01 | Overhead | 19790542 | 9291799 | 12754591
MCR012981 | HPR090 | 2021-09-01 | Labor | 21664435 | 16068150 | 18366954
MCR012982 | HPR090 | 2021-09-01 | Material | 69437626 | 51500731 | 58321284
MCR012983 | HPR090 | 2021-09-01 | Equipment | 24317518 | 18035898 | 18865218
MCR012984 | HPR090 | 2021-09-01 | Subcontract | 46706169 | 34641188 | 38859139
MCR012985 | HPR090 | 2021-09-01 | Overhead | 19800121 | 14685420 | 12019294
MCR012986 | HPR090 | 2021-10-01 | Labor | 21453048 | 16919594 | 20968242
MCR012987 | HPR090 | 2021-10-01 | Material | 68760102 | 54229731 | 61954918
MCR012988 | HPR090 | 2021-10-01 | Equipment | 24080244 | 18991612 | 22899778
MCR012989 | HPR090 | 2021-10-01 | Subcontract | 46250443 | 36476809 | 31036030
MCR012990 | HPR090 | 2021-10-01 | Overhead | 19606926 | 15463594 | 11843818
MCR012991 | HPR090 | 2021-11-01 | Labor | 21028297 | 9585501 | 9414382
MCR012992 | HPR090 | 2021-11-01 | Material | 67398712 | 30722909 | 38456512
MCR012993 | HPR090 | 2021-11-01 | Equipment | 23603477 | 10759367 | 9097341
MCR012994 | HPR090 | 2021-11-01 | Subcontract | 45334725 | 20665300 | 21891885
MCR012995 | HPR090 | 2021-11-01 | Overhead | 19218726 | 8760630 | 12610883
MCR012996 | HPR090 | 2021-12-01 | Labor | 20399293 | 12156677 | 13484898
MCR012997 | HPR090 | 2021-12-01 | Material | 65382666 | 38963897 | 53509587
MCR012998 | HPR090 | 2021-12-01 | Equipment | 22897444 | 13645415 | 13803796
MCR012999 | HPR090 | 2021-12-01 | Subcontract | 43978662 | 26208476 | 27461167
MCR013000 | HPR090 | 2021-12-01 | Overhead | 18643850 | 11110545 | 12581065
MCR013001 | HPR090 | 2022-01-01 | Labor | 19575863 | 25457103 | 28851196
MCR013002 | HPR090 | 2022-01-01 | Material | 62743455 | 81593674 | 97853968
MCR013003 | HPR090 | 2022-01-01 | Equipment | 21973175 | 28574646 | 27368853
MCR013004 | HPR090 | 2022-01-01 | Subcontract | 42203436 | 54882751 | 51080929
MCR013005 | HPR090 | 2022-01-01 | Overhead | 17891280 | 23266415 | 12507359
MCR013006 | HPR090 | 2022-02-01 | Labor | 18568675 | 16230885 | 18727712
MCR013007 | HPR090 | 2022-02-01 | Material | 59515272 | 52022320 | 63412110
MCR013008 | HPR090 | 2022-02-01 | Equipment | 20842643 | 18218562 | 21743226
MCR013009 | HPR090 | 2022-02-01 | Subcontract | 40032048 | 34992027 | 39152761
MCR013010 | HPR090 | 2022-02-01 | Overhead | 16970764 | 14834151 | 12924254
MCR013011 | HPR090 | 2022-03-01 | Labor | 17389404 | 9237105 | 11295891
MCR013012 | HPR090 | 2022-03-01 | Material | 55735540 | 29606248 | 34908657
MCR013013 | HPR090 | 2022-03-01 | Equipment | 19518956 | 10368304 | 10960460
MCR013014 | HPR090 | 2022-03-01 | Subcontract | 37489668 | 19914195 | 16687989
MCR013015 | HPR090 | 2022-03-01 | Overhead | 15892975 | 8442214 | 12450766
MCR013016 | HPR090 | 2022-04-01 | Labor | 16050958 | 23373764 | 26254505
MCR013017 | HPR090 | 2022-04-01 | Material | 51445626 | 74916271 | 89268712
MCR013018 | HPR090 | 2022-04-01 | Equipment | 18016600 | 26236176 | 28407480
MCR013019 | HPR090 | 2022-04-01 | Subcontract | 34604122 | 50391297 | 57225732
MCR013020 | HPR090 | 2022-04-01 | Overhead | 14669707 | 21362355 | 12357186
MCR013021 | HPR090 | 2022-05-01 | Labor | 14567771 | 11468667 | 12970485
MCR013022 | HPR090 | 2022-05-01 | Material | 46691798 | 36758726 | 42053341
MCR013023 | HPR090 | 2022-05-01 | Equipment | 16351778 | 12873150 | 12245636
MCR013024 | HPR090 | 2022-05-01 | Subcontract | 31406532 | 24725201 | 18846302
MCR013025 | HPR090 | 2022-05-01 | Overhead | 13314154 | 10481741 | 11833546
MCR013026 | HPR090 | 2022-06-01 | Labor | 12956230 | 8011098 | 9924746
MCR013027 | HPR090 | 2022-06-01 | Material | 41526578 | 25676720 | 36275631
MCR013028 | HPR090 | 2022-06-01 | Equipment | 14542883 | 8992158 | 11374839
MCR013029 | HPR090 | 2022-06-01 | Subcontract | 27932225 | 17271057 | 17701161
MCR013030 | HPR090 | 2022-06-01 | Overhead | 11841293 | 7321710 | 12567141
MCR013031 | HPR090 | 2022-07-01 | Labor | 11235286 | 8168866 | 9518061
MCR013032 | HPR090 | 2022-07-01 | Material | 36010705 | 26182389 | 31652857
MCR013033 | HPR090 | 2022-07-01 | Equipment | 12611188 | 9169246 | 8144942
MCR013034 | HPR090 | 2022-07-01 | Subcontract | 24222056 | 17611188 | 17699796
MCR013035 | HPR090 | 2022-07-01 | Overhead | 10268443 | 7465901 | 13391270
MCR013036 | HPR090 | 2022-08-01 | Labor | 9427394 | 12118090 | 14334454
MCR013037 | HPR090 | 2022-08-01 | Material | 30216154 | 38840221 | 45617620
MCR013038 | HPR090 | 2022-08-01 | Equipment | 10581898 | 13602103 | 14841891
MCR013039 | HPR090 | 2022-08-01 | Subcontract | 20324439 | 26125288 | 23871379
MCR013040 | HPR090 | 2022-08-01 | Overhead | 8616129 | 11075279 | 12145039
MCR013041 | HPR090 | 2022-09-01 | Labor | 7560058 | 12303416 | 14203212
MCR013042 | HPR090 | 2022-09-01 | Material | 24231071 | 39434215 | 55218917
MCR013043 | HPR090 | 2022-09-01 | Equipment | 8485882 | 13810124 | 15194209
MCR013044 | HPR090 | 2022-09-01 | Subcontract | 16298663 | 26524828 | 29614424
MCR013045 | HPR090 | 2022-09-01 | Overhead | 6909484 | 11244656 | 12850404
MCR013046 | HPR090 | 2022-10-01 | Labor | 5668575 | 10401222 | 11146833
MCR013047 | HPR090 | 2022-10-01 | Material | 18168597 | 33337410 | 32176516
MCR013048 | HPR090 | 2022-10-01 | Equipment | 6362763 | 11674982 | 13784908
MCR013049 | HPR090 | 2022-10-01 | Subcontract | 12220832 | 22423905 | 21104736
MCR013050 | HPR090 | 2022-10-01 | Overhead | 5180771 | 9506154 | 12324435
MCR013051 | HPR090 | 2022-11-01 | Labor | 3801652 | 10780398 | 12659235
MCR013052 | HPR090 | 2022-11-01 | Material | 12184842 | 34552725 | 45673813
MCR013053 | HPR090 | 2022-11-01 | Equipment | 4267212 | 12100594 | 14247751
MCR013054 | HPR090 | 2022-11-01 | Subcontract | 8195949 | 23241368 | 25672864
MCR013055 | HPR090 | 2022-11-01 | Overhead | 3474504 | 9852701 | 13261427
MCR013056 | HPR090 | 2022-12-01 | Labor | 2035581 | 16485852 | 21056320
MCR013057 | HPR090 | 2022-12-01 | Material | 6524329 | 52839525 | 68307103
MCR013058 | HPR090 | 2022-12-01 | Equipment | 2284863 | 18504752 | 19157155
MCR013059 | HPR090 | 2022-12-01 | Subcontract | 4388491 | 35541707 | 27931215
MCR013060 | HPR090 | 2022-12-01 | Overhead | 1860411 | 15067177 | 12834358
MCR013061 | HPR090 | 2023-01-01 | Labor | 534631 | 10789726 | 10739658
MCR013062 | HPR090 | 2023-01-01 | Material | 1713571 | 34582622 | 39149912
MCR013063 | HPR090 | 2023-01-01 | Equipment | 600104 | 12111064 | 10052719
MCR013064 | HPR090 | 2023-01-01 | Subcontract | 1152607 | 23261478 | 28452262
MCR013065 | HPR090 | 2023-01-01 | Overhead | 488624 | 9861226 | 11721884
MCR013066 | HPR090 | 2023-02-01 | Labor | 0 | 12141755 | 13480961
MCR013067 | HPR090 | 2023-02-01 | Material | 0 | 38916071 | 45809017
MCR013068 | HPR090 | 2023-02-01 | Equipment | 0 | 13628666 | 16547058
MCR013069 | HPR090 | 2023-02-01 | Subcontract | 0 | 26176307 | 40027048
MCR013070 | HPR090 | 2023-02-01 | Overhead | 0 | 11096908 | 12878063
MCR013071 | HPR090 | 2023-03-01 | Labor | 0 | 6972293 | 8529880
MCR013072 | HPR090 | 2023-03-01 | Material | 0 | 22347201 | 26961269
MCR013073 | HPR090 | 2023-03-01 | Equipment | 0 | 7826138 | 7209382
MCR013074 | HPR090 | 2023-03-01 | Subcontract | 0 | 15031507 | 36519522
MCR013075 | HPR090 | 2023-03-01 | Overhead | 0 | 6372299 | 12758869
MCR013076 | HPR090 | 2023-04-01 | Labor | 0 | 10568394 | 13677720
MCR013077 | HPR090 | 2023-04-01 | Material | 0 | 33873220 | 39409839
MCR013078 | HPR090 | 2023-04-01 | Equipment | 0 | 11862627 | 12892977
MCR013079 | HPR090 | 2023-04-01 | Subcontract | 0 | 22784310 | 36709295
MCR013080 | HPR090 | 2023-04-01 | Overhead | 0 | 9658940 | 12456833
MCR013081 | HPR090 | 2023-05-01 | Labor | 0 | 8375767 | 9056776
MCR013082 | HPR090 | 2023-05-01 | Material | 0 | 26845537 | 25211317
MCR013083 | HPR090 | 2023-05-01 | Equipment | 0 | 9401485 | 10231956
MCR013084 | HPR090 | 2023-05-01 | Subcontract | 0 | 18057245 | 48155540
MCR013085 | HPR090 | 2023-05-01 | Overhead | 0 | 7654998 | 13131314
MCR013086 | HPR090 | 2023-06-01 | Labor | 0 | 7765531 | 9812978
MCR013087 | HPR090 | 2023-06-01 | Material | 0 | 24889643 | 32052733
MCR013088 | HPR090 | 2023-06-01 | Equipment | 0 | 8716518 | 10688553
MCR013089 | HPR090 | 2023-06-01 | Subcontract | 0 | 16741642 | 31821037
MCR013090 | HPR090 | 2023-06-01 | Overhead | 0 | 7097275 | 12552530
MCR013091 | HPR090 | 2023-07-01 | Labor | 0 | 6419646 | 8069613
MCR013092 | HPR090 | 2023-07-01 | Material | 0 | 20575888 | 22563418
MCR013093 | HPR090 | 2023-07-01 | Equipment | 0 | 7205813 | 8944379
MCR013094 | HPR090 | 2023-07-01 | Subcontract | 0 | 13840060 | 26909083
MCR013095 | HPR090 | 2023-07-01 | Overhead | 0 | 5867209 | 13364108
MCR013096 | HPR090 | 2023-08-01 | Labor | 0 | 3663673 | 3723506
MCR013097 | HPR090 | 2023-08-01 | Material | 0 | 11742597 | 13409060
MCR013098 | HPR090 | 2023-08-01 | Equipment | 0 | 4112336 | 4343906
MCR013099 | HPR090 | 2023-08-01 | Subcontract | 0 | 7898481 | 31458579
MCR013100 | HPR090 | 2023-08-01 | Overhead | 0 | 3348399 | 11923639
MCR013101 | HPR090 | 2023-09-01 | Labor | 0 | 10282417 | 11719571
MCR013102 | HPR090 | 2023-09-01 | Material | 0 | 32956625 | 33875070
MCR013103 | HPR090 | 2023-09-01 | Equipment | 0 | 11541629 | 16278802
MCR013104 | HPR090 | 2023-09-01 | Subcontract | 0 | 22167776 | 41790443
MCR013105 | HPR090 | 2023-09-01 | Overhead | 0 | 9397573 | 12514839
MCR013106 | HPR090 | 2023-10-01 | Labor | 0 | 9498575 | 12429557
MCR013107 | HPR090 | 2023-10-01 | Material | 0 | 30444297 | 35806708
MCR013108 | HPR090 | 2023-10-01 | Equipment | 0 | 10661795 | 12807479
MCR013109 | HPR090 | 2023-10-01 | Subcontract | 0 | 20477896 | 35587480
MCR013110 | HPR090 | 2023-10-01 | Overhead | 0 | 8681183 | 12756739
MCR013111 | HPR090 | 2023-11-01 | Labor | 0 | 4333919 | 4743275
MCR013112 | HPR090 | 2023-11-01 | Material | 0 | 13890833 | 17642142
MCR013113 | HPR090 | 2023-11-01 | Equipment | 0 | 4864662 | 5832667
MCR013114 | HPR090 | 2023-11-01 | Subcontract | 0 | 9343459 | 22804945
MCR013115 | HPR090 | 2023-11-01 | Overhead | 0 | 3960968 | 12829458
MCR013116 | HPR090 | 2023-12-01 | Labor | 0 | 2021358 | 2490708
MCR013117 | HPR090 | 2023-12-01 | Material | 0 | 6478744 | 7636905
MCR013118 | HPR090 | 2023-12-01 | Equipment | 0 | 2268899 | 2486710
MCR013119 | HPR090 | 2023-12-01 | Subcontract | 0 | 4357829 | 24074070
MCR013120 | HPR090 | 2023-12-01 | Overhead | 0 | 1847412 | 12222090
MCR013121 | HPR090 | 2024-01-01 | Labor | 0 | 2963901 | 3774873
MCR013122 | HPR090 | 2024-01-01 | Material | 0 | 9499728 | 11239407
MCR013123 | HPR090 | 2024-01-01 | Equipment | 0 | 3326868 | 4004841
MCR013124 | HPR090 | 2024-01-01 | Subcontract | 0 | 6389848 | 23515072
MCR013125 | HPR090 | 2024-01-01 | Overhead | 0 | 2708845 | 13182961
MCR013126 | HPR090 | 2024-02-01 | Labor | 0 | 1123131 | 1349110
MCR013127 | HPR090 | 2024-02-01 | Material | 0 | 3599798 | 3418134
MCR013128 | HPR090 | 2024-02-01 | Equipment | 0 | 1260673 | 1901959
MCR013129 | HPR090 | 2024-02-01 | Subcontract | 0 | 2421350 | 15885479
MCR013130 | HPR090 | 2024-02-01 | Overhead | 0 | 1026481 | 11750672
MCR013131 | HPR090 | 2024-03-01 | Labor | 0 | 358023 | 386942
MCR013132 | HPR090 | 2024-03-01 | Material | 0 | 1147516 | 1644584
MCR013133 | HPR090 | 2024-03-01 | Equipment | 0 | 401868 | 441523
MCR013134 | HPR090 | 2024-03-01 | Subcontract | 0 | 771859 | 15592801
MCR013135 | HPR090 | 2024-03-01 | Overhead | 0 | 327214 | 13274998
MCR013136 | HPR091 | 2017-03-01 | Labor | 2632005 | 1269284 | 1427732
MCR013137 | HPR091 | 2017-03-01 | Material | 6569604 | 3168191 | 3594220
MCR013138 | HPR091 | 2017-03-01 | Equipment | 2125733 | 1025135 | 1256871
MCR013139 | HPR091 | 2017-03-01 | Subcontract | 4894385 | 2360317 | 2650820
MCR013140 | HPR091 | 2017-03-01 | Overhead | 1766833 | 852055 | 12410334
MCR013141 | HPR091 | 2017-04-01 | Labor | 7563900 | 3456403 | 4102673
MCR013142 | HPR091 | 2017-04-01 | Material | 18879837 | 8627339 | 8076883
MCR013143 | HPR091 | 2017-04-01 | Equipment | 6108967 | 2791556 | 2494581
MCR013144 | HPR091 | 2017-04-01 | Subcontract | 14065566 | 6427407 | 5678770
MCR013145 | HPR091 | 2017-04-01 | Overhead | 5077556 | 2320242 | 14145038
MCR013146 | HPR091 | 2017-05-01 | Labor | 12003960 | 4032201 | 4152401
MCR013147 | HPR091 | 2017-05-01 | Material | 29962426 | 10064556 | 11628700
MCR013148 | HPR091 | 2017-05-01 | Equipment | 9694971 | 3256598 | 3753824
MCR013149 | HPR091 | 2017-05-01 | Subcontract | 22322145 | 7498140 | 8721363
MCR013150 | HPR091 | 2017-05-01 | Overhead | 8058114 | 2706768 | 13945145
MCR013151 | HPR091 | 2017-06-01 | Labor | 15960877 | 9671678 | 10489638
MCR013152 | HPR091 | 2017-06-01 | Material | 39839071 | 24140946 | 23250574
MCR013153 | HPR091 | 2017-06-01 | Equipment | 12890767 | 7811309 | 8611990
MCR013154 | HPR091 | 2017-06-01 | Subcontract | 29680291 | 17985115 | 19718730
MCR013155 | HPR091 | 2017-06-01 | Overhead | 10714346 | 6492482 | 13742919
MCR013156 | HPR091 | 2017-07-01 | Labor | 19443679 | 9031534 | 10995867
MCR013157 | HPR091 | 2017-07-01 | Material | 48532302 | 22543118 | 21515528
MCR013158 | HPR091 | 2017-07-01 | Equipment | 15703644 | 7294299 | 7741501
MCR013159 | HPR091 | 2017-07-01 | Subcontract | 36156788 | 16794726 | 16283192
MCR013160 | HPR091 | 2017-07-01 | Overhead | 13052309 | 6062761 | 14080493
MCR013161 | HPR091 | 2017-08-01 | Labor | 22461751 | 7430303 | 9476642
MCR013162 | HPR091 | 2017-08-01 | Material | 56065546 | 18546371 | 21595346
MCR013163 | HPR091 | 2017-08-01 | Equipment | 18141183 | 6001067 | 6704051
MCR013164 | HPR091 | 2017-08-01 | Subcontract | 41769089 | 13817132 | 16005137
MCR013165 | HPR091 | 2017-08-01 | Overhead | 15078304 | 4987873 | 14525392
MCR013166 | HPR091 | 2017-09-01 | Labor | 25024874 | 11457394 | 13334237
MCR013167 | HPR091 | 2017-09-01 | Material | 62463216 | 28598173 | 26801969
MCR013168 | HPR091 | 2017-09-01 | Equipment | 20211283 | 9253539 | 9701760
MCR013169 | HPR091 | 2017-09-01 | Subcontract | 46535383 | 21305770 | 21765695
MCR013170 | HPR091 | 2017-09-01 | Overhead | 16798898 | 7691211 | 14386263
MCR013171 | HPR091 | 2017-10-01 | Labor | 27143261 | 13376242 | 13751804
MCR013172 | HPR091 | 2017-10-01 | Material | 67750807 | 33387705 | 30170097
MCR013173 | HPR091 | 2017-10-01 | Equipment | 21922194 | 10803292 | 11985742
MCR013174 | HPR091 | 2017-10-01 | Subcontract | 50474662 | 24873993 | 23966545
MCR013175 | HPR091 | 2017-10-01 | Overhead | 18220946 | 8979311 | 12508404
MCR013176 | HPR091 | 2017-11-01 | Labor | 28827607 | 9162532 | 10596118
MCR013177 | HPR091 | 2017-11-01 | Material | 71955011 | 22870094 | 22952979
MCR013178 | HPR091 | 2017-11-01 | Equipment | 23282553 | 7400099 | 6629792
MCR013179 | HPR091 | 2017-11-01 | Subcontract | 53606814 | 17038325 | 20598618
MCR013180 | HPR091 | 2017-11-01 | Overhead | 19351627 | 6150698 | 14273576
MCR013181 | HPR091 | 2017-12-01 | Labor | 30089138 | 30773026 | 36992489
MCR013182 | HPR091 | 2017-12-01 | Material | 75103850 | 76810864 | 90279658
MCR013183 | HPR091 | 2017-12-01 | Equipment | 24301426 | 24853766 | 23255916
MCR013184 | HPR091 | 2017-12-01 | Subcontract | 55952713 | 57224446 | 58490329
MCR013185 | HPR091 | 2017-12-01 | Overhead | 20198478 | 20657563 | 14249814
MCR013186 | HPR091 | 2018-01-01 | Labor | 30939675 | 28729590 | 35647069
MCR013187 | HPR091 | 2018-01-01 | Material | 77226828 | 71710357 | 67375908
MCR013188 | HPR091 | 2018-01-01 | Equipment | 24988360 | 23203390 | 28062769
MCR013189 | HPR091 | 2018-01-01 | Subcontract | 57534342 | 53424545 | 66048367
MCR013190 | HPR091 | 2018-01-01 | Overhead | 20769433 | 19285830 | 13346217
MCR013191 | HPR091 | 2018-02-01 | Labor | 31391707 | 22557295 | 26724341
MCR013192 | HPR091 | 2018-02-01 | Material | 78355121 | 56304028 | 54294700
MCR013193 | HPR091 | 2018-02-01 | Equipment | 25353442 | 18218349 | 17836522
MCR013194 | HPR091 | 2018-02-01 | Subcontract | 58374925 | 41946760 | 36422449
MCR013195 | HPR091 | 2018-02-01 | Overhead | 21072877 | 15142442 | 12932649
MCR013196 | HPR091 | 2018-03-01 | Labor | 31458482 | 31613869 | 35764498
MCR013197 | HPR091 | 2018-03-01 | Material | 78521794 | 78909647 | 86459322
MCR013198 | HPR091 | 2018-03-01 | Equipment | 25407373 | 25532871 | 31011142
MCR013199 | HPR091 | 2018-03-01 | Subcontract | 58499097 | 58788049 | 73350391
MCR013200 | HPR091 | 2018-03-01 | Overhead | 21117702 | 21222012 | 11964734
MCR013201 | HPR091 | 2018-04-01 | Labor | 31154113 | 17959386 | 21734353
MCR013202 | HPR091 | 2018-04-01 | Material | 77762075 | 44827441 | 44870814
MCR013203 | HPR091 | 2018-04-01 | Equipment | 25161550 | 14504858 | 14189424
MCR013204 | HPR091 | 2018-04-01 | Subcontract | 57933103 | 33396649 | 33444884
MCR013205 | HPR091 | 2018-04-01 | Overhead | 20913383 | 12055921 | 13220470
MCR013206 | HPR091 | 2018-05-01 | Labor | 30493711 | 18237405 | 23746686
MCR013207 | HPR091 | 2018-05-01 | Material | 76113682 | 45521387 | 44948023
MCR013208 | HPR091 | 2018-05-01 | Equipment | 24628178 | 14729400 | 13971246
MCR013209 | HPR091 | 2018-05-01 | Subcontract | 56705043 | 33913643 | 32352285
MCR013210 | HPR091 | 2018-05-01 | Overhead | 20470063 | 12242551 | 14690018
MCR013211 | HPR091 | 2018-06-01 | Labor | 29493551 | 19705339 | 22258937
MCR013212 | HPR091 | 2018-06-01 | Material | 73617237 | 49185417 | 48676876
MCR013213 | HPR091 | 2018-06-01 | Equipment | 23820401 | 15914973 | 20487213
MCR013214 | HPR091 | 2018-06-01 | Subcontract | 54845180 | 36643361 | 48662404
MCR013215 | HPR091 | 2018-06-01 | Overhead | 19798667 | 13227958 | 13805466
MCR013216 | HPR091 | 2018-07-01 | Labor | 28171279 | 18614971 | 21806760
MCR013217 | HPR091 | 2018-07-01 | Material | 70316787 | 46463809 | 51652848
MCR013218 | HPR091 | 2018-07-01 | Equipment | 22752471 | 15034340 | 14568964
MCR013219 | HPR091 | 2018-07-01 | Subcontract | 52386329 | 34615751 | 26815463
MCR013220 | HPR091 | 2018-07-01 | Overhead | 18911042 | 12496007 | 12533307
MCR013221 | HPR091 | 2018-08-01 | Labor | 26546186 | 17088288 | 22127848
MCR013222 | HPR091 | 2018-08-01 | Material | 66260480 | 42653139 | 36746141
MCR013223 | HPR091 | 2018-08-01 | Equipment | 21439968 | 13801318 | 14613803
MCR013224 | HPR091 | 2018-08-01 | Subcontract | 49364362 | 31776785 | 39984661
MCR013225 | HPR091 | 2018-08-01 | Overhead | 17820136 | 11471163 | 13575888
MCR013226 | HPR091 | 2018-09-01 | Labor | 24639560 | 21068327 | 23125167
MCR013227 | HPR091 | 2018-09-01 | Material | 61501455 | 52587496 | 51446136
MCR013228 | HPR091 | 2018-09-01 | Equipment | 19900086 | 17015787 | 17589502
MCR013229 | HPR091 | 2018-09-01 | Subcontract | 45818867 | 39177926 | 33759866
MCR013230 | HPR091 | 2018-09-01 | Overhead | 16540241 | 14142915 | 13658272
MCR013231 | HPR091 | 2018-10-01 | Labor | 22475175 | 24324987 | 27208411
MCR013232 | HPR091 | 2018-10-01 | Material | 56099054 | 60716266 | 65844943
MCR013233 | HPR091 | 2018-10-01 | Equipment | 18152025 | 19646021 | 22054785
MCR013234 | HPR091 | 2018-10-01 | Subcontract | 41794053 | 45233897 | 53770926
MCR013235 | HPR091 | 2018-10-01 | Overhead | 15087316 | 16329072 | 12425730
MCR013236 | HPR091 | 2018-11-01 | Labor | 20079969 | 18024827 | 23884924
MCR013237 | HPR091 | 2018-11-01 | Material | 50120510 | 44990782 | 44599930
MCR013238 | HPR091 | 2018-11-01 | Equipment | 16217542 | 14557711 | 17451105
MCR013239 | HPR091 | 2018-11-01 | Subcontract | 37340010 | 33518339 | 34024563
MCR013240 | HPR091 | 2018-11-01 | Overhead | 13479442 | 12099850 | 13000391
MCR013241 | HPR091 | 2018-12-01 | Labor | 17485027 | 14560121 | 16728098
MCR013242 | HPR091 | 2018-12-01 | Material | 43643418 | 36342721 | 35123447
MCR013243 | HPR091 | 2018-12-01 | Equipment | 14121743 | 11759449 | 10417490
MCR013244 | HPR091 | 2018-12-01 | Subcontract | 32514547 | 27075494 | 27292552
MCR013245 | HPR091 | 2018-12-01 | Overhead | 11737489 | 9774035 | 13627116
MCR013246 | HPR091 | 2019-01-01 | Labor | 14727103 | 26318394 | 32775676
MCR013247 | HPR091 | 2019-01-01 | Material | 36759515 | 65691900 | 71487622
MCR013248 | HPR091 | 2019-01-01 | Equipment | 11894312 | 21255992 | 25543522
MCR013249 | HPR091 | 2019-01-01 | Subcontract | 27386008 | 48940768 | 60348784
MCR013250 | HPR091 | 2019-01-01 | Overhead | 9886128 | 17667222 | 13215000
MCR013251 | HPR091 | 2019-02-01 | Labor | 11851086 | 18206249 | 47643981
MCR013252 | HPR091 | 2019-02-01 | Material | 29580846 | 45443621 | 69433482
MCR013253 | HPR091 | 2019-02-01 | Equipment | 9571503 | 14704237 | 14668536
MCR013254 | HPR091 | 2019-02-01 | Subcontract | 22037866 | 33855706 | 30950415
MCR013255 | HPR091 | 2019-02-01 | Overhead | 7955492 | 12221637 | 12833988
MCR013256 | HPR091 | 2019-03-01 | Labor | 8914417 | 15998810 | 44914532
MCR013257 | HPR091 | 2019-03-01 | Material | 22250789 | 39933752 | 70581279
MCR013258 | HPR091 | 2019-03-01 | Equipment | 7199709 | 12921403 | 14864881
MCR013259 | HPR091 | 2019-03-01 | Subcontract | 16576940 | 29750829 | 34669044
MCR013260 | HPR091 | 2019-03-01 | Overhead | 5984142 | 10739809 | 13900804
MCR013261 | HPR091 | 2019-04-01 | Labor | 5996068 | 9636628 | 9685235
MCR013262 | HPR091 | 2019-04-01 | Material | 14966457 | 24053460 | 19120570
MCR013263 | HPR091 | 2019-04-01 | Equipment | 4842711 | 7783001 | 7943532
MCR013264 | HPR091 | 2019-04-01 | Subcontract | 11150079 | 17919938 | 20051293
MCR013265 | HPR091 | 2019-04-01 | Overhead | 4025089 | 6468953 | 13494626
MCR013266 | HPR091 | 2019-05-01 | Labor | 3219194 | 20901321 | 22555128
MCR013267 | HPR091 | 2019-05-01 | Material | 8035254 | 52170641 | 55632141
MCR013268 | HPR091 | 2019-05-01 | Equipment | 2599975 | 16880905 | 16081270
MCR013269 | HPR091 | 2019-05-01 | Subcontract | 5986301 | 38867367 | 40674729
MCR013270 | HPR091 | 2019-05-01 | Overhead | 2161006 | 14030806 | 14885900
MCR013271 | HPR091 | 2019-06-01 | Labor | 847409 | 21430568 | 25131740
MCR013272 | HPR091 | 2019-06-01 | Material | 2115171 | 53491666 | 53126025
MCR013273 | HPR091 | 2019-06-01 | Equipment | 684408 | 17308350 | 18176285
MCR013274 | HPR091 | 2019-06-01 | Subcontract | 1575812 | 39851537 | 46413661
MCR013275 | HPR091 | 2019-06-01 | Overhead | 568855 | 14386083 | 13376574
MCR013276 | HPR091 | 2019-07-01 | Labor | 0 | 11860842 | 14148706
MCR013277 | HPR091 | 2019-07-01 | Material | 0 | 29605199 | 34797472
MCR013278 | HPR091 | 2019-07-01 | Equipment | 0 | 9579383 | 11256601
MCR013279 | HPR091 | 2019-07-01 | Subcontract | 0 | 22056009 | 57633621
MCR013280 | HPR091 | 2019-07-01 | Overhead | 0 | 7962041 | 12761106
MCR013281 | HPR091 | 2019-08-01 | Labor | 0 | 13342448 | 14467581
MCR013282 | HPR091 | 2019-08-01 | Material | 0 | 33303354 | 34317347
MCR013283 | HPR091 | 2019-08-01 | Equipment | 0 | 10775999 | 11656599
MCR013284 | HPR091 | 2019-08-01 | Subcontract | 0 | 24811152 | 42192859
MCR013285 | HPR091 | 2019-08-01 | Overhead | 0 | 8956626 | 12773666
MCR013286 | HPR091 | 2019-09-01 | Labor | 0 | 7594010 | 8661933
MCR013287 | HPR091 | 2019-09-01 | Material | 0 | 18954993 | 18051226
MCR013288 | HPR091 | 2019-09-01 | Equipment | 0 | 6133285 | 6872956
MCR013289 | HPR091 | 2019-09-01 | Subcontract | 0 | 14121557 | 36482492
MCR013290 | HPR091 | 2019-09-01 | Overhead | 0 | 5097768 | 13389131
MCR013291 | HPR091 | 2019-10-01 | Labor | 0 | 11773232 | 12303448
MCR013292 | HPR091 | 2019-10-01 | Material | 0 | 29386519 | 33911828
MCR013293 | HPR091 | 2019-10-01 | Equipment | 0 | 9508624 | 9725107
MCR013294 | HPR091 | 2019-10-01 | Subcontract | 0 | 21893092 | 58658824
MCR013295 | HPR091 | 2019-10-01 | Overhead | 0 | 7903229 | 12711243
MCR013296 | HPR091 | 2019-11-01 | Labor | 0 | 17693899 | 20526301
MCR013297 | HPR091 | 2019-11-01 | Material | 0 | 44164772 | 39133724
MCR013298 | HPR091 | 2019-11-01 | Equipment | 0 | 14290438 | 15436353
MCR013299 | HPR091 | 2019-11-01 | Subcontract | 0 | 32902958 | 50379137
MCR013300 | HPR091 | 2019-11-01 | Overhead | 0 | 11877702 | 13039548
MCR013301 | HPR091 | 2019-12-01 | Labor | 0 | 7433079 | 7632891
MCR013302 | HPR091 | 2019-12-01 | Material | 0 | 18553302 | 20820207
MCR013303 | HPR091 | 2019-12-01 | Equipment | 0 | 6003310 | 7950965
MCR013304 | HPR091 | 2019-12-01 | Subcontract | 0 | 13822295 | 38891514
MCR013305 | HPR091 | 2019-12-01 | Overhead | 0 | 4989737 | 14048828
MCR013306 | HPR091 | 2020-01-01 | Labor | 0 | 8118482 | 9371846
MCR013307 | HPR091 | 2020-01-01 | Material | 0 | 20264097 | 20149548
MCR013308 | HPR091 | 2020-01-01 | Equipment | 0 | 6556874 | 7611436
MCR013309 | HPR091 | 2020-01-01 | Subcontract | 0 | 15096846 | 34207216
MCR013310 | HPR091 | 2020-01-01 | Overhead | 0 | 5449839 | 12915293
MCR013311 | HPR091 | 2020-02-01 | Labor | 0 | 5491476 | 6428691
MCR013312 | HPR091 | 2020-02-01 | Material | 0 | 13706973 | 14991630
MCR013313 | HPR091 | 2020-02-01 | Equipment | 0 | 4435179 | 5845673
MCR013314 | HPR091 | 2020-02-01 | Subcontract | 0 | 10211758 | 30421097
MCR013315 | HPR091 | 2020-02-01 | Overhead | 0 | 3686362 | 13594845
MCR013316 | HPR091 | 2020-03-01 | Labor | 0 | 4619844 | 5427476
MCR013317 | HPR091 | 2020-03-01 | Material | 0 | 11531339 | 12514785
MCR013318 | HPR091 | 2020-03-01 | Equipment | 0 | 3731207 | 4818234
MCR013319 | HPR091 | 2020-03-01 | Subcontract | 0 | 8590901 | 35328205
MCR013320 | HPR091 | 2020-03-01 | Overhead | 0 | 3101246 | 13015006
MCR013321 | HPR091 | 2020-04-01 | Labor | 0 | 4903201 | 5078005
MCR013322 | HPR091 | 2020-04-01 | Material | 0 | 12238611 | 12878707
MCR013323 | HPR091 | 2020-04-01 | Equipment | 0 | 3960059 | 4762791
MCR013324 | HPR091 | 2020-04-01 | Subcontract | 0 | 9117821 | 39222345
MCR013325 | HPR091 | 2020-04-01 | Overhead | 0 | 3291460 | 13009857
MCR013326 | HPR091 | 2020-05-01 | Labor | 0 | 2296338 | 3232441
MCR013327 | HPR091 | 2020-05-01 | Material | 0 | 5731764 | 6229576
MCR013328 | HPR091 | 2020-05-01 | Equipment | 0 | 1854633 | 2467058
MCR013329 | HPR091 | 2020-05-01 | Subcontract | 0 | 4270191 | 31423285
MCR013330 | HPR091 | 2020-05-01 | Overhead | 0 | 1541504 | 15076181
MCR013331 | HPR091 | 2020-06-01 | Labor | 0 | 993094 | 946631
MCR013332 | HPR091 | 2020-06-01 | Material | 0 | 2478807 | 1798634
MCR013333 | HPR091 | 2020-06-01 | Equipment | 0 | 802070 | 1086089
MCR013334 | HPR091 | 2020-06-01 | Subcontract | 0 | 1846722 | 20524169
MCR013335 | HPR091 | 2020-06-01 | Overhead | 0 | 666652 | 13026880
MCR013336 | HPR091 | 2020-07-01 | Labor | 0 | 277850 | 386963
MCR013337 | HPR091 | 2020-07-01 | Material | 0 | 693526 | 914847
MCR013338 | HPR091 | 2020-07-01 | Equipment | 0 | 224405 | 364725
MCR013339 | HPR091 | 2020-07-01 | Subcontract | 0 | 516680 | 34498041
MCR013340 | HPR091 | 2020-07-01 | Overhead | 0 | 186517 | 14572806
MCR013341 | HPR092 | 2016-10-01 | Labor | 3682717 | 2084642 | 2012057
MCR013342 | HPR092 | 2016-10-01 | Material | 8892934 | 5033942 | 5566274
MCR013343 | HPR092 | 2016-10-01 | Equipment | 2424498 | 1372413 | 1324604
MCR013344 | HPR092 | 2016-10-01 | Subcontract | 9743658 | 5515503 | 5019223
MCR013345 | HPR092 | 2016-10-01 | Overhead | 2069703 | 1171578 | 12298253
MCR013346 | HPR092 | 2016-11-01 | Labor | 10453629 | 5432455 | 4676734
MCR013347 | HPR092 | 2016-11-01 | Material | 25243166 | 13118160 | 12232822
MCR013348 | HPR092 | 2016-11-01 | Equipment | 6882093 | 3576429 | 3955570
MCR013349 | HPR092 | 2016-11-01 | Subcontract | 27658000 | 14373080 | 15707826
MCR013350 | HPR092 | 2016-11-01 | Overhead | 5874986 | 3053064 | 13273418
MCR013351 | HPR092 | 2016-12-01 | Labor | 16347416 | 7906437 | 9598435
MCR013352 | HPR092 | 2016-12-01 | Material | 39475339 | 19092270 | 18857855
MCR013353 | HPR092 | 2016-12-01 | Equipment | 10762237 | 5205162 | 4948985
MCR013354 | HPR092 | 2016-12-01 | Subcontract | 43251662 | 20918691 | 22606656
MCR013355 | HPR092 | 2016-12-01 | Overhead | 9187321 | 4443453 | 12407236
MCR013356 | HPR092 | 2017-01-01 | Labor | 21384367 | 13301434 | 14092255
MCR013357 | HPR092 | 2017-01-01 | Material | 51638444 | 32119976 | 33030403
MCR013358 | HPR092 | 2017-01-01 | Equipment | 14078287 | 8756930 | 9828372
MCR013359 | HPR092 | 2017-01-01 | Subcontract | 56578325 | 35192665 | 35233500
MCR013360 | HPR092 | 2017-01-01 | Overhead | 12018110 | 7475466 | 12139725
MCR013361 | HPR092 | 2017-02-01 | Labor | 25585793 | 20241676 | 21920316
MCR013362 | HPR092 | 2017-02-01 | Material | 61783944 | 48879102 | 51502876
MCR013363 | HPR092 | 2017-02-01 | Equipment | 16844274 | 13326003 | 14531180
MCR013364 | HPR092 | 2017-02-01 | Subcontract | 67694372 | 53555016 | 56634657
MCR013365 | HPR092 | 2017-02-01 | Overhead | 14379330 | 11375913 | 12931752
MCR013366 | HPR092 | 2017-03-01 | Labor | 28974150 | 13867573 | 17064231
MCR013367 | HPR092 | 2017-03-01 | Material | 69966065 | 33487073 | 36614435
MCR013368 | HPR092 | 2017-03-01 | Equipment | 19074981 | 9129645 | 8986798
MCR013369 | HPR092 | 2017-03-01 | Subcontract | 76659218 | 36690542 | 33564481
MCR013370 | HPR092 | 2017-03-01 | Overhead | 16283602 | 7793638 | 12038113
MCR013371 | HPR092 | 2017-04-01 | Labor | 31573187 | 28658360 | 31455636
MCR013372 | HPR092 | 2017-04-01 | Material | 76242155 | 69203501 | 61123205
MCR013373 | HPR092 | 2017-04-01 | Equipment | 20786044 | 18867082 | 17703230
MCR013374 | HPR092 | 2017-04-01 | Subcontract | 83535697 | 75823706 | 81851854
MCR013375 | HPR092 | 2017-04-01 | Overhead | 17744272 | 16106126 | 12240323
MCR013376 | HPR092 | 2017-05-01 | Labor | 33408126 | 22064778 | 24597001
MCR013377 | HPR092 | 2017-05-01 | Material | 80673119 | 53281483 | 60743253
MCR013378 | HPR092 | 2017-05-01 | Equipment | 21994066 | 14526232 | 16388383
MCR013379 | HPR092 | 2017-05-01 | Subcontract | 88390540 | 58378542 | 46951045
MCR013380 | HPR092 | 2017-05-01 | Overhead | 18775516 | 12400504 | 14058898
MCR013381 | HPR092 | 2017-06-01 | Labor | 34505877 | 31597355 | 35887555
MCR013382 | HPR092 | 2017-06-01 | Material | 83323943 | 76300516 | 68568317
MCR013383 | HPR092 | 2017-06-01 | Equipment | 22716765 | 20801955 | 21780879
MCR013384 | HPR092 | 2017-06-01 | Subcontract | 91294949 | 83599641 | 85896178
MCR013385 | HPR092 | 2017-06-01 | Overhead | 19392457 | 17757855 | 12658878
MCR013386 | HPR092 | 2017-07-01 | Labor | 34895317 | 36308270 | 38569962
MCR013387 | HPR092 | 2017-07-01 | Material | 84264352 | 87676317 | 96988398
MCR013388 | HPR092 | 2017-07-01 | Equipment | 22973151 | 23903361 | 23245458
MCR013389 | HPR092 | 2017-07-01 | Subcontract | 92325320 | 96063684 | 101543224
MCR013390 | HPR092 | 2017-07-01 | Overhead | 19611324 | 20405410 | 12255858
MCR013391 | HPR092 | 2017-08-01 | Labor | 34607624 | 20106606 | 46312594
MCR013392 | HPR092 | 2017-08-01 | Material | 83569639 | 48552938 | 74122667
MCR013393 | HPR092 | 2017-08-01 | Equipment | 22783750 | 13237080 | 11807563
MCR013394 | HPR092 | 2017-08-01 | Subcontract | 91564149 | 53197650 | 58675064
MCR013395 | HPR092 | 2017-08-01 | Overhead | 19449640 | 11300003 | 13239524
MCR013396 | HPR092 | 2017-09-01 | Labor | 33676728 | 46024517 | 69520759
MCR013397 | HPR092 | 2017-09-01 | Material | 81321733 | 111138870 | 129839199
MCR013398 | HPR092 | 2017-09-01 | Equipment | 22170899 | 30300002 | 30478244
MCR013399 | HPR092 | 2017-09-01 | Subcontract | 89101202 | 121770731 | 113220217
MCR013400 | HPR092 | 2017-09-01 | Overhead | 18926472 | 25865984 | 13312072
MCR013401 | HPR092 | 2017-10-01 | Labor | 32139883 | 15147772 | 20087236
MCR013402 | HPR092 | 2017-10-01 | Material | 77610599 | 36578468 | 38529801
MCR013403 | HPR092 | 2017-10-01 | Equipment | 21159125 | 9972457 | 12127101
MCR013404 | HPR092 | 2017-10-01 | Subcontract | 85035050 | 40077669 | 41219452
MCR013405 | HPR092 | 2017-10-01 | Overhead | 18062758 | 8513116 | 13102170
MCR013406 | HPR092 | 2017-11-01 | Labor | 30038459 | 29522495 | 33533326
MCR013407 | HPR092 | 2017-11-01 | Material | 72536133 | 71290194 | 75747351
MCR013408 | HPR092 | 2017-11-01 | Equipment | 19775664 | 19435981 | 17414082
MCR013409 | HPR092 | 2017-11-01 | Subcontract | 79475146 | 78110018 | 80781574
MCR013410 | HPR092 | 2017-11-01 | Overhead | 16881749 | 16591774 | 12357049
MCR013411 | HPR092 | 2017-12-01 | Labor | 27419032 | 21204921 | 21445213
MCR013412 | HPR092 | 2017-12-01 | Material | 66210804 | 51205122 | 60311965
MCR013413 | HPR092 | 2017-12-01 | Equipment | 18051178 | 13960150 | 15733164
MCR013414 | HPR092 | 2017-12-01 | Subcontract | 72544718 | 56103550 | 51501842
MCR013415 | HPR092 | 2017-12-01 | Overhead | 15409619 | 11917261 | 13601396
MCR013416 | HPR092 | 2018-01-01 | Labor | 24334969 | 28851010 | 31857162
MCR013417 | HPR092 | 2018-01-01 | Material | 58763485 | 69668708 | 70551536
MCR013418 | HPR092 | 2018-01-01 | Equipment | 16020801 | 18993913 | 18773199
MCR013419 | HPR092 | 2018-01-01 | Subcontract | 64384968 | 76333415 | 85149893
MCR013420 | HPR092 | 2018-01-01 | Overhead | 13676362 | 16214396 | 12668713
MCR013421 | HPR092 | 2018-02-01 | Labor | 20848849 | 21865187 | 22092448
MCR013422 | HPR092 | 2018-02-01 | Material | 50345288 | 52799515 | 50941575
MCR013423 | HPR092 | 2018-02-01 | Equipment | 13725732 | 14394832 | 16653175
MCR013424 | HPR092 | 2018-02-01 | Subcontract | 55161461 | 57850467 | 60161726
MCR013425 | HPR092 | 2018-02-01 | Overhead | 11717146 | 12288333 | 12880427
MCR013426 | HPR092 | 2018-03-01 | Labor | 17036383 | 19378480 | 23250094
MCR013427 | HPR092 | 2018-03-01 | Material | 41139039 | 46794678 | 42634424
MCR013428 | HPR092 | 2018-03-01 | Equipment | 11215815 | 12757722 | 11485071
MCR013429 | HPR092 | 2018-03-01 | Subcontract | 45074517 | 51271190 | 44045084
MCR013430 | HPR092 | 2018-03-01 | Overhead | 9574524 | 10890793 | 12751434
MCR013431 | HPR092 | 2018-04-01 | Labor | 12993386 | 26754154 | 22895361
MCR013432 | HPR092 | 2018-04-01 | Material | 31376109 | 64605273 | 66829556
MCR013433 | HPR092 | 2018-04-01 | Equipment | 8554128 | 17613459 | 18661128
MCR013434 | HPR092 | 2018-04-01 | Subcontract | 34377637 | 70785597 | 80577612
MCR013435 | HPR092 | 2018-04-01 | Overhead | 7302341 | 15035954 | 12255791
MCR013436 | HPR092 | 2018-05-01 | Labor | 8849849 | 14917354 | 21024069
MCR013437 | HPR092 | 2018-05-01 | Material | 21370398 | 36022060 | 37704173
MCR013438 | HPR092 | 2018-05-01 | Equipment | 5826252 | 9820763 | 10194194
MCR013439 | HPR092 | 2018-05-01 | Subcontract | 23414751 | 39468034 | 35614760
MCR013440 | HPR092 | 2018-05-01 | Overhead | 4973655 | 8383620 | 12822665
MCR013441 | HPR092 | 2018-06-01 | Labor | 4805213 | 17637599 | 21270716
MCR013442 | HPR092 | 2018-06-01 | Material | 11603509 | 42590840 | 43448235
MCR013443 | HPR092 | 2018-06-01 | Equipment | 3163487 | 11611622 | 12919836
MCR013444 | HPR092 | 2018-06-01 | Subcontract | 12713534 | 46665201 | 42211851
MCR013445 | HPR092 | 2018-06-01 | Overhead | 2700551 | 9912409 | 11957407
MCR013446 | HPR092 | 2018-07-01 | Labor | 1276807 | 12484931 | 11012389
MCR013447 | HPR092 | 2018-07-01 | Material | 3083202 | 30148304 | 33572233
MCR013448 | HPR092 | 2018-07-01 | Equipment | 840579 | 8219390 | 8099372
MCR013449 | HPR092 | 2018-07-01 | Subcontract | 3378150 | 33032377 | 39341019
MCR013450 | HPR092 | 2018-07-01 | Overhead | 717571 | 7016587 | 11967189
MCR013451 | HPR092 | 2018-08-01 | Labor | 0 | 9106076 | 11052007
MCR013452 | HPR092 | 2018-08-01 | Material | 0 | 21989127 | 22945806
MCR013453 | HPR092 | 2018-08-01 | Equipment | 0 | 5994938 | 6249030
MCR013454 | HPR092 | 2018-08-01 | Subcontract | 0 | 24092670 | 21361729
MCR013455 | HPR092 | 2018-08-01 | Overhead | 0 | 5117655 | 12406320
MCR013456 | HPR092 | 2018-09-01 | Labor | 0 | 12482665 | 14371931
MCR013457 | HPR092 | 2018-09-01 | Material | 0 | 30142832 | 27340183
MCR013458 | HPR092 | 2018-09-01 | Equipment | 0 | 8217898 | 8026657
MCR013459 | HPR092 | 2018-09-01 | Subcontract | 0 | 33026381 | 38621210
MCR013460 | HPR092 | 2018-09-01 | Overhead | 0 | 7015313 | 13069798
MCR013461 | HPR092 | 2018-10-01 | Labor | 0 | 8081670 | 8738975
MCR013462 | HPR092 | 2018-10-01 | Material | 0 | 19515418 | 21051286
MCR013463 | HPR092 | 2018-10-01 | Equipment | 0 | 5320525 | 6208864
MCR013464 | HPR092 | 2018-10-01 | Subcontract | 0 | 21382318 | 20697722
MCR013465 | HPR092 | 2018-10-01 | Overhead | 0 | 4541935 | 12930653
MCR013466 | HPR092 | 2018-11-01 | Labor | 0 | 3178714 | 3929245
MCR013467 | HPR092 | 2018-11-01 | Material | 0 | 7675881 | 7444517
MCR013468 | HPR092 | 2018-11-01 | Equipment | 0 | 2092690 | 2029223
MCR013469 | HPR092 | 2018-11-01 | Subcontract | 0 | 8410178 | 6364121
MCR013470 | HPR092 | 2018-11-01 | Overhead | 0 | 1786452 | 13220625
MCR013471 | HPR092 | 2018-12-01 | Labor | 0 | 630630 | 571833
MCR013472 | HPR092 | 2018-12-01 | Material | 0 | 1522830 | 1714048
MCR013473 | HPR092 | 2018-12-01 | Equipment | 0 | 415172 | 587108
MCR013474 | HPR092 | 2018-12-01 | Subcontract | 0 | 1668508 | 1978748
MCR013475 | HPR092 | 2018-12-01 | Overhead | 0 | 354417 | 13095630
MCR013476 | HPR093 | 2018-04-01 | Labor | 1321197 | 1096434 | 1106425
MCR013477 | HPR093 | 2018-04-01 | Material | 3279908 | 2721927 | 2743027
MCR013478 | HPR093 | 2018-04-01 | Equipment | 643889 | 534350 | 541196
MCR013479 | HPR093 | 2018-04-01 | Subcontract | 3465565 | 2876000 | 3105990
MCR013480 | HPR093 | 2018-04-01 | Overhead | 792582 | 657747 | 6077637
MCR013481 | HPR093 | 2018-05-01 | Labor | 3796879 | 2013235 | 1924433
MCR013482 | HPR093 | 2018-05-01 | Material | 9425854 | 4997910 | 4091427
MCR013483 | HPR093 | 2018-05-01 | Equipment | 1850419 | 981155 | 969435
MCR013484 | HPR093 | 2018-05-01 | Subcontract | 9959398 | 5280813 | 4842755
MCR013485 | HPR093 | 2018-05-01 | Overhead | 2277734 | 1207732 | 5643280
MCR013486 | HPR093 | 2018-06-01 | Labor | 6025672 | 4478217 | 4985908
MCR013487 | HPR093 | 2018-06-01 | Material | 14958892 | 11117292 | 13491747
MCR013488 | HPR093 | 2018-06-01 | Equipment | 2936627 | 2182470 | 2318781
MCR013489 | HPR093 | 2018-06-01 | Subcontract | 15805630 | 11746579 | 11632564
MCR013490 | HPR093 | 2018-06-01 | Overhead | 3614779 | 2686466 | 5695120
MCR013491 | HPR093 | 2018-07-01 | Labor | 8011941 | 8410958 | 7699787
MCR013492 | HPR093 | 2018-07-01 | Material | 19889857 | 20880428 | 24633823
MCR013493 | HPR093 | 2018-07-01 | Equipment | 3904640 | 4099102 | 4159744
MCR013494 | HPR093 | 2018-07-01 | Subcontract | 21015709 | 22062351 | 21560101
MCR013495 | HPR093 | 2018-07-01 | Overhead | 4806335 | 5045704 | 5862740
MCR013496 | HPR093 | 2018-08-01 | Labor | 9760216 | 5290123 | 6208055
MCR013497 | HPR093 | 2018-08-01 | Material | 24229997 | 13132872 | 10329353
MCR013498 | HPR093 | 2018-08-01 | Equipment | 4756667 | 2578155 | 2393106
MCR013499 | HPR093 | 2018-08-01 | Subcontract | 25601519 | 13876249 | 15535943
MCR013500 | HPR093 | 2018-08-01 | Overhead | 5855118 | 3173526 | 6800992
MCR013501 | HPR093 | 2018-09-01 | Labor | 11275209 | 7968370 | 7848717
MCR013502 | HPR093 | 2018-09-01 | Material | 27991007 | 19781692 | 19845705
MCR013503 | HPR093 | 2018-09-01 | Equipment | 5495002 | 3883406 | 4290001
MCR013504 | HPR093 | 2018-09-01 | Subcontract | 29575419 | 20901421 | 20817723
MCR013505 | HPR093 | 2018-09-01 | Overhead | 6763957 | 4780197 | 5795820
MCR013506 | HPR093 | 2018-10-01 | Labor | 12561829 | 13760566 | 15700354
MCR013507 | HPR093 | 2018-10-01 | Material | 31185075 | 34160972 | 39436730
MCR013508 | HPR093 | 2018-10-01 | Equipment | 6122040 | 6706247 | 6338467
MCR013509 | HPR093 | 2018-10-01 | Subcontract | 32950286 | 36094631 | 34255260
MCR013510 | HPR093 | 2018-10-01 | Overhead | 7535796 | 8254914 | 6264227
MCR013511 | HPR093 | 2018-11-01 | Labor | 13625204 | 13786494 | 13237146
MCR013512 | HPR093 | 2018-11-01 | Material | 33824932 | 34225339 | 32828343
MCR013513 | HPR093 | 2018-11-01 | Equipment | 6640278 | 6718884 | 6222376
MCR013514 | HPR093 | 2018-11-01 | Subcontract | 35739570 | 36162642 | 38912704
MCR013515 | HPR093 | 2018-11-01 | Overhead | 8173711 | 8270468 | 5982963
MCR013516 | HPR093 | 2018-12-01 | Labor | 14470701 | 19611197 | 20425456
MCR013517 | HPR093 | 2018-12-01 | Material | 35923902 | 48685320 | 50427921
MCR013518 | HPR093 | 2018-12-01 | Equipment | 7052334 | 9557568 | 9281904
MCR013519 | HPR093 | 2018-12-01 | Subcontract | 37957351 | 51441120 | 57699367
MCR013520 | HPR093 | 2018-12-01 | Overhead | 8680922 | 11764687 | 5758344
MCR013521 | HPR093 | 2019-01-01 | Labor | 15103957 | 11695327 | 12647756
MCR013522 | HPR093 | 2019-01-01 | Material | 37495976 | 29033961 | 27326086
MCR013523 | HPR093 | 2019-01-01 | Equipment | 7360952 | 5699748 | 6342636
MCR013524 | HPR093 | 2019-01-01 | Subcontract | 39618410 | 30677409 | 25364959
MCR013525 | HPR093 | 2019-01-01 | Overhead | 9060809 | 7015984 | 6079137
MCR013526 | HPR093 | 2019-02-01 | Labor | 15530904 | 9947392 | 10827647
MCR013527 | HPR093 | 2019-02-01 | Material | 38555883 | 24694668 | 29215938
MCR013528 | HPR093 | 2019-02-01 | Equipment | 7569026 | 4847888 | 4141672
MCR013529 | HPR093 | 2019-02-01 | Subcontract | 40738313 | 26092493 | 24746713
MCR013530 | HPR093 | 2019-02-01 | Overhead | 9316933 | 5967405 | 5898406
MCR013531 | HPR093 | 2019-03-01 | Labor | 15757812 | 17558741 | 18430468
MCR013532 | HPR093 | 2019-03-01 | Material | 39119189 | 43590044 | 44263103
MCR013533 | HPR093 | 2019-03-01 | Equipment | 7679611 | 8557298 | 8662451
MCR013534 | HPR093 | 2019-03-01 | Subcontract | 41333505 | 46057430 | 52267728
MCR013535 | HPR093 | 2019-03-01 | Overhead | 9453055 | 10533426 | 5996893
MCR013536 | HPR093 | 2019-04-01 | Labor | 15791331 | 11444201 | 11140526
MCR013537 | HPR093 | 2019-04-01 | Material | 39202402 | 28410534 | 29050343
MCR013538 | HPR093 | 2019-04-01 | Equipment | 7695946 | 5577361 | 5698750
MCR013539 | HPR093 | 2019-04-01 | Subcontract | 41421427 | 30018693 | 29718455
MCR013540 | HPR093 | 2019-04-01 | Overhead | 9473163 | 6865335 | 5899926
MCR013541 | HPR093 | 2019-05-01 | Labor | 15638546 | 15924251 | 18416749
MCR013542 | HPR093 | 2019-05-01 | Material | 38823108 | 39532379 | 44543035
MCR013543 | HPR093 | 2019-05-01 | Equipment | 7621486 | 7760725 | 7631500
MCR013544 | HPR093 | 2019-05-01 | Subcontract | 41020664 | 41770083 | 34581720
MCR013545 | HPR093 | 2019-05-01 | Overhead | 9381508 | 9552901 | 6110639
MCR013546 | HPR093 | 2019-06-01 | Labor | 15307041 | 16820145 | 17098526
MCR013547 | HPR093 | 2019-06-01 | Material | 38000140 | 41756459 | 46059439
MCR013548 | HPR093 | 2019-06-01 | Equipment | 7459926 | 8197341 | 8390136
MCR013549 | HPR093 | 2019-06-01 | Subcontract | 40151112 | 44120056 | 46891381
MCR013550 | HPR093 | 2019-06-01 | Overhead | 9182639 | 10090345 | 5975531
MCR013551 | HPR093 | 2019-07-01 | Labor | 14804987 | 10759187 | 9317302
MCR013552 | HPR093 | 2019-07-01 | Material | 36753777 | 26709969 | 25210076
MCR013553 | HPR093 | 2019-07-01 | Equipment | 7215249 | 5243518 | 5437442
MCR013554 | HPR093 | 2019-07-01 | Subcontract | 38834200 | 28221869 | 30613833
MCR013555 | HPR093 | 2019-07-01 | Overhead | 8881459 | 6454398 | 5672218
MCR013556 | HPR093 | 2019-08-01 | Labor | 14141242 | 12013483 | 13432223
MCR013557 | HPR093 | 2019-08-01 | Material | 35106010 | 29823792 | 30191241
MCR013558 | HPR093 | 2019-08-01 | Equipment | 6891771 | 5854802 | 5010008
MCR013559 | HPR093 | 2019-08-01 | Subcontract | 37093163 | 31511948 | 29747716
MCR013560 | HPR093 | 2019-08-01 | Overhead | 8483280 | 7206845 | 6178655
MCR013561 | HPR093 | 2019-09-01 | Labor | 13325487 | 10606794 | 11523751
MCR013562 | HPR093 | 2019-09-01 | Material | 33080879 | 26331649 | 28437051
MCR013563 | HPR093 | 2019-09-01 | Equipment | 6494211 | 5169248 | 5728869
MCR013564 | HPR093 | 2019-09-01 | Subcontract | 34953400 | 27822134 | 28637042
MCR013565 | HPR093 | 2019-09-01 | Overhead | 7993912 | 6362977 | 6214084
MCR013566 | HPR093 | 2019-10-01 | Labor | 12368411 | 14737064 | 15982383
MCR013567 | HPR093 | 2019-10-01 | Material | 30704912 | 36585156 | 40067761
MCR013568 | HPR093 | 2019-10-01 | Equipment | 6027777 | 7182147 | 7022553
MCR013569 | HPR093 | 2019-10-01 | Subcontract | 32442943 | 38656034 | 44331799
MCR013570 | HPR093 | 2019-10-01 | Overhead | 7419766 | 8840712 | 6210773
MCR013571 | HPR093 | 2019-11-01 | Labor | 11281947 | 12111847 | 13137184
MCR013572 | HPR093 | 2019-11-01 | Material | 28007736 | 30067984 | 28596032
MCR013573 | HPR093 | 2019-11-01 | Equipment | 5498286 | 5902740 | 6961947
MCR013574 | HPR093 | 2019-11-01 | Subcontract | 29593095 | 31769963 | 30352628
MCR013575 | HPR093 | 2019-11-01 | Overhead | 6768000 | 7265854 | 6242192
MCR013576 | HPR093 | 2019-12-01 | Labor | 10079616 | 11009296 | 12685961
MCR013577 | HPR093 | 2019-12-01 | Material | 25022917 | 27330872 | 28279731
MCR013578 | HPR093 | 2019-12-01 | Equipment | 4912327 | 5365409 | 5237338
MCR013579 | HPR093 | 2019-12-01 | Subcontract | 26439323 | 28877918 | 30935468
MCR013580 | HPR093 | 2019-12-01 | Overhead | 6046726 | 6604437 | 5865435
MCR013581 | HPR093 | 2020-01-01 | Labor | 8777024 | 7627338 | 6250675
MCR013582 | HPR093 | 2020-01-01 | Material | 21789197 | 18935071 | 21707793
MCR013583 | HPR093 | 2020-01-01 | Equipment | 4277505 | 3717203 | 3377496
MCR013584 | HPR093 | 2020-01-01 | Subcontract | 23022560 | 20006878 | 21627190
MCR013585 | HPR093 | 2020-01-01 | Overhead | 5265305 | 4575613 | 6781786
MCR013586 | HPR093 | 2020-02-01 | Labor | 7392619 | 4880377 | 5379483
MCR013587 | HPR093 | 2020-02-01 | Material | 18352373 | 12115667 | 13754556
MCR013588 | HPR093 | 2020-02-01 | Equipment | 3602812 | 2378465 | 2813477
MCR013589 | HPR093 | 2020-02-01 | Subcontract | 19391197 | 12801467 | 11972195
MCR013590 | HPR093 | 2020-02-01 | Overhead | 4434805 | 2927721 | 6268341
MCR013591 | HPR093 | 2020-03-01 | Labor | 5948934 | 11957364 | 11743038
MCR013592 | HPR093 | 2020-03-01 | Material | 14768387 | 29684476 | 34720236
MCR013593 | HPR093 | 2020-03-01 | Equipment | 2899228 | 5827452 | 5851446
MCR013594 | HPR093 | 2020-03-01 | Subcontract | 15604341 | 31364746 | 31187490
MCR013595 | HPR093 | 2020-03-01 | Overhead | 3568744 | 7173180 | 6363309
MCR013596 | HPR093 | 2020-04-01 | Labor | 4474803 | 8507655 | 8496268
MCR013597 | HPR093 | 2020-04-01 | Material | 11108818 | 21120481 | 22563195
MCR013598 | HPR093 | 2020-04-01 | Equipment | 2180807 | 4146228 | 4055424
MCR013599 | HPR093 | 2020-04-01 | Subcontract | 11737626 | 22315992 | 23094353
MCR013600 | HPR093 | 2020-04-01 | Overhead | 2684418 | 5103712 | 6516012
MCR013601 | HPR093 | 2020-05-01 | Labor | 3009868 | 8276910 | 8369084
MCR013602 | HPR093 | 2020-05-01 | Material | 7472079 | 20547649 | 21710555
MCR013603 | HPR093 | 2020-05-01 | Equipment | 1466867 | 4033773 | 4572281
MCR013604 | HPR093 | 2020-05-01 | Subcontract | 7895031 | 21710735 | 18899925
MCR013605 | HPR093 | 2020-05-01 | Overhead | 1805609 | 4965288 | 6219237
MCR013606 | HPR093 | 2020-06-01 | Labor | 1615951 | 2592144 | 2919234
MCR013607 | HPR093 | 2020-06-01 | Material | 4011641 | 6435067 | 6339497
MCR013608 | HPR093 | 2020-06-01 | Equipment | 787538 | 1263288 | 1077025
MCR013609 | HPR093 | 2020-06-01 | Subcontract | 4238717 | 6799320 | 9873393
MCR013610 | HPR093 | 2020-06-01 | Overhead | 969403 | 1555018 | 6210133
MCR013611 | HPR093 | 2020-07-01 | Labor | 425377 | 3663015 | 3949797
MCR013612 | HPR093 | 2020-07-01 | Material | 1056010 | 9093532 | 10814220
MCR013613 | HPR093 | 2020-07-01 | Equipment | 207309 | 1785180 | 1565504
MCR013614 | HPR093 | 2020-07-01 | Subcontract | 1115785 | 9608265 | 9547769
MCR013615 | HPR093 | 2020-07-01 | Overhead | 255182 | 2197429 | 5584360
MCR013616 | HPR093 | 2020-08-01 | Labor | 0 | 1741604 | 1603551
MCR013617 | HPR093 | 2020-08-01 | Material | 0 | 4323580 | 3800496
MCR013618 | HPR093 | 2020-08-01 | Equipment | 0 | 848775 | 1123322
MCR013619 | HPR093 | 2020-08-01 | Subcontract | 0 | 4568313 | 4765826
MCR013620 | HPR093 | 2020-08-01 | Overhead | 0 | 1044782 | 5997651
MCR013621 | HPR093 | 2020-09-01 | Labor | 0 | 987844 | 1003208
MCR013622 | HPR093 | 2020-09-01 | Material | 0 | 2452350 | 2416196
MCR013623 | HPR093 | 2020-09-01 | Equipment | 0 | 481428 | 415413
MCR013624 | HPR093 | 2020-09-01 | Subcontract | 0 | 2591163 | 2396399
MCR013625 | HPR093 | 2020-09-01 | Overhead | 0 | 592604 | 6533923
MCR013626 | HPR093 | 2020-10-01 | Labor | 0 | 347132 | 395677
MCR013627 | HPR093 | 2020-10-01 | Material | 0 | 861763 | 1079589
MCR013628 | HPR093 | 2020-10-01 | Equipment | 0 | 169175 | 226724
MCR013629 | HPR093 | 2020-10-01 | Subcontract | 0 | 910543 | 886847
MCR013630 | HPR093 | 2020-10-01 | Overhead | 0 | 208243 | 6215913
MCR013631 | HPR094 | 2018-10-01 | Labor | 7107398 | 6287736 | 6015253
MCR013632 | HPR094 | 2018-10-01 | Material | 13929808 | 12323349 | 12197350
MCR013633 | HPR094 | 2018-10-01 | Equipment | 3381135 | 2991205 | 3214946
MCR013634 | HPR094 | 2018-10-01 | Subcontract | 18161921 | 16067393 | 16639655
MCR013635 | HPR094 | 2018-10-01 | Overhead | 4728913 | 4183550 | 17628497
MCR013636 | HPR094 | 2018-11-01 | Labor | 19620089 | 13576252 | 14306493
MCR013637 | HPR094 | 2018-11-01 | Material | 38453461 | 26608131 | 29991642
MCR013638 | HPR094 | 2018-11-01 | Equipment | 9333678 | 6458501 | 5918341
MCR013639 | HPR094 | 2018-11-01 | Subcontract | 50136280 | 34692135 | 40097702
MCR013640 | HPR094 | 2018-11-01 | Overhead | 13054241 | 9032970 | 20794462
MCR013641 | HPR094 | 2018-12-01 | Labor | 29643309 | 16062849 | 17837672
MCR013642 | HPR094 | 2018-12-01 | Material | 58097994 | 31481617 | 29113566
MCR013643 | HPR094 | 2018-12-01 | Equipment | 14101929 | 7641426 | 7870074
MCR013644 | HPR094 | 2018-12-01 | Subcontract | 75749157 | 41046270 | 36765465
MCR013645 | HPR094 | 2018-12-01 | Overhead | 19723198 | 10687429 | 19207719
MCR013646 | HPR094 | 2019-01-01 | Labor | 37267027 | 40628214 | 39762333
MCR013647 | HPR094 | 2019-01-01 | Material | 73039739 | 79627337 | 82998821
MCR013648 | HPR094 | 2019-01-01 | Equipment | 17728688 | 19327674 | 18421933
MCR013649 | HPR094 | 2019-01-01 | Subcontract | 95230459 | 103819482 | 107517794
MCR013650 | HPR094 | 2019-01-01 | Overhead | 24795645 | 27032013 | 20894806
MCR013651 | HPR094 | 2019-02-01 | Labor | 42588503 | 38123932 | 39237424
MCR013652 | HPR094 | 2019-02-01 | Material | 83469313 | 74719189 | 75370281
MCR013653 | HPR094 | 2019-02-01 | Equipment | 20260223 | 18136336 | 18550338
MCR013654 | HPR094 | 2019-02-01 | Subcontract | 108828715 | 97420154 | 94792302
MCR013655 | HPR094 | 2019-02-01 | Overhead | 28336293 | 25365787 | 19020142
MCR013656 | HPR094 | 2019-03-01 | Labor | 45713750 | 43430185 | 42716751
MCR013657 | HPR094 | 2019-03-01 | Material | 89594492 | 85118928 | 89568020
MCR013658 | HPR094 | 2019-03-01 | Equipment | 21746968 | 20660629 | 23228417
MCR013659 | HPR094 | 2019-03-01 | Subcontract | 116814829 | 110979512 | 101573012
MCR013660 | HPR094 | 2019-03-01 | Overhead | 30415678 | 28896307 | 19893158
MCR013661 | HPR094 | 2019-04-01 | Labor | 46759510 | 40139756 | 34021718
MCR013662 | HPR094 | 2019-04-01 | Material | 91644079 | 78670006 | 86629093
MCR013663 | HPR094 | 2019-04-01 | Equipment | 22244457 | 19095304 | 19413673
MCR013664 | HPR094 | 2019-04-01 | Subcontract | 119487116 | 102571298 | 122836831
MCR013665 | HPR094 | 2019-04-01 | Overhead | 31111475 | 26707017 | 19626073
MCR013666 | HPR094 | 2019-05-01 | Labor | 45855974 | 54547926 | 56913548
MCR013667 | HPR094 | 2019-05-01 | Material | 89873237 | 106908615 | 100174439
MCR013668 | HPR094 | 2019-05-01 | Equipment | 21814626 | 25949566 | 21587227
MCR013669 | HPR094 | 2019-05-01 | Subcontract | 117178261 | 139389279 | 127590447
MCR013670 | HPR094 | 2019-05-01 | Overhead | 30510307 | 36293504 | 18797717
MCR013671 | HPR094 | 2019-06-01 | Labor | 43150699 | 44402869 | 69292538
MCR013672 | HPR094 | 2019-06-01 | Material | 84571162 | 87025292 | 118971360
MCR013673 | HPR094 | 2019-06-01 | Equipment | 20527672 | 21123354 | 24260932
MCR013674 | HPR094 | 2019-06-01 | Subcontract | 110265325 | 113465062 | 118514102
MCR013675 | HPR094 | 2019-06-01 | Overhead | 28710350 | 29543482 | 20206940
MCR013676 | HPR094 | 2019-07-01 | Labor | 38814514 | 19397557 | 41751131
MCR013677 | HPR094 | 2019-07-01 | Material | 76072662 | 38017321 | 66446817
MCR013678 | HPR094 | 2019-07-01 | Equipment | 18464859 | 9227816 | 9193550
MCR013679 | HPR094 | 2019-07-01 | Subcontract | 99184836 | 49567632 | 55970818
MCR013680 | HPR094 | 2019-07-01 | Overhead | 25825266 | 12906180 | 19142462
MCR013681 | HPR094 | 2019-08-01 | Labor | 33051016 | 19242855 | 19334885
MCR013682 | HPR094 | 2019-08-01 | Material | 64776768 | 37714119 | 31328885
MCR013683 | HPR094 | 2019-08-01 | Equipment | 15723045 | 9154220 | 10299241
MCR013684 | HPR094 | 2019-08-01 | Subcontract | 84457057 | 49172313 | 46591011
MCR013685 | HPR094 | 2019-08-01 | Overhead | 21990518 | 12803248 | 19276057
MCR013686 | HPR094 | 2019-09-01 | Labor | 26113239 | 41084731 | 40883323
MCR013687 | HPR094 | 2019-09-01 | Material | 51179401 | 80522065 | 87869215
MCR013688 | HPR094 | 2019-09-01 | Equipment | 12422603 | 19544848 | 19968991
MCR013689 | HPR094 | 2019-09-01 | Subcontract | 66728577 | 104986044 | 115333267
MCR013690 | HPR094 | 2019-09-01 | Overhead | 17374463 | 27335756 | 19007067
MCR013691 | HPR094 | 2019-10-01 | Labor | 18336900 | 20959746 | 23064768
MCR013692 | HPR094 | 2019-10-01 | Material | 35938535 | 41079058 | 38574980
MCR013693 | HPR094 | 2019-10-01 | Equipment | 8723239 | 9970981 | 10655884
MCR013694 | HPR094 | 2019-10-01 | Subcontract | 46857275 | 53559577 | 77104182
MCR013695 | HPR094 | 2019-10-01 | Overhead | 12200470 | 13945583 | 19371346
MCR013696 | HPR094 | 2019-11-01 | Labor | 10222522 | 16057152 | 17025547
MCR013697 | HPR094 | 2019-11-01 | Material | 20035146 | 31470453 | 31898528
MCR013698 | HPR094 | 2019-11-01 | Equipment | 4863063 | 7638716 | 8179787
MCR013699 | HPR094 | 2019-11-01 | Subcontract | 26122166 | 41031714 | 72097678
MCR013700 | HPR094 | 2019-11-01 | Overhead | 6801563 | 10683638 | 19467838
MCR013701 | HPR094 | 2019-12-01 | Labor | 2774385 | 19694235 | 17021574
MCR013702 | HPR094 | 2019-12-01 | Material | 5437523 | 38598779 | 39274340
MCR013703 | HPR094 | 2019-12-01 | Equipment | 1319832 | 9368951 | 10043640
MCR013704 | HPR094 | 2019-12-01 | Subcontract | 7089536 | 50325748 | 69840238
MCR013705 | HPR094 | 2019-12-01 | Overhead | 1845939 | 13103574 | 19981822
MCR013706 | HPR094 | 2020-01-01 | Labor | 0 | 11732763 | 14773630
MCR013707 | HPR094 | 2020-01-01 | Material | 0 | 22995072 | 24151830
MCR013708 | HPR094 | 2020-01-01 | Equipment | 0 | 5581516 | 4864985
MCR013709 | HPR094 | 2020-01-01 | Subcontract | 0 | 29981367 | 58227261
MCR013710 | HPR094 | 2020-01-01 | Overhead | 0 | 7806403 | 19060160
MCR013711 | HPR094 | 2020-02-01 | Labor | 0 | 1650076 | 1044788
MCR013712 | HPR094 | 2020-02-01 | Material | 0 | 3233989 | 3122038
MCR013713 | HPR094 | 2020-02-01 | Equipment | 0 | 784975 | 1007979
MCR013714 | HPR094 | 2020-02-01 | Subcontract | 0 | 4216530 | 21556646
MCR013715 | HPR094 | 2020-02-01 | Overhead | 0 | 1097879 | 20859779
MCR013716 | HPR095 | 2021-03-01 | Labor | 3390064 | 2492878 | 2223319
MCR013717 | HPR095 | 2021-03-01 | Material | 10076632 | 7409834 | 8012561
MCR013718 | HPR095 | 2021-03-01 | Equipment | 2531094 | 1861236 | 2179695
MCR013719 | HPR095 | 2021-03-01 | Subcontract | 9003656 | 6620823 | 6821653
MCR013720 | HPR095 | 2021-03-01 | Overhead | 2278328 | 1675365 | 10462198
MCR013721 | HPR095 | 2021-04-01 | Labor | 9456855 | 10488485 | 8579546
MCR013722 | HPR095 | 2021-04-01 | Material | 28109571 | 31175989 | 34278645
MCR013723 | HPR095 | 2021-04-01 | Equipment | 7060689 | 7830925 | 8029652
MCR013724 | HPR095 | 2021-04-01 | Subcontract | 25116418 | 27856318 | 28925460
MCR013725 | HPR095 | 2021-04-01 | Overhead | 6355578 | 7048896 | 10645577
MCR013726 | HPR095 | 2021-05-01 | Labor | 14476892 | 14043398 | 12200867
MCR013727 | HPR095 | 2021-05-01 | Material | 43031134 | 41742616 | 46668073
MCR013728 | HPR095 | 2021-05-01 | Equipment | 10808754 | 10485098 | 8895149
MCR013729 | HPR095 | 2021-05-01 | Subcontract | 38449108 | 37297794 | 31703094
MCR013730 | HPR095 | 2021-05-01 | Overhead | 9729346 | 9438012 | 11366200
MCR013731 | HPR095 | 2021-06-01 | Labor | 18482766 | 21228513 | 18129972
MCR013732 | HPR095 | 2021-06-01 | Material | 54938199 | 63099664 | 73404845
MCR013733 | HPR095 | 2021-06-01 | Equipment | 13799624 | 15849658 | 14806669
MCR013734 | HPR095 | 2021-06-01 | Subcontract | 49088290 | 56380708 | 63579787
MCR013735 | HPR095 | 2021-06-01 | Overhead | 12421536 | 14266844 | 10682146
MCR013736 | HPR095 | 2021-07-01 | Labor | 21509318 | 13918093 | 13867336
MCR013737 | HPR095 | 2021-07-01 | Material | 63934328 | 41370161 | 41226320
MCR013738 | HPR095 | 2021-07-01 | Equipment | 16059312 | 10391543 | 11046687
MCR013739 | HPR095 | 2021-07-01 | Subcontract | 57126496 | 36964998 | 35608920
MCR013740 | HPR095 | 2021-07-01 | Overhead | 14455562 | 9353800 | 11268368
MCR013741 | HPR095 | 2021-08-01 | Labor | 23594019 | 12611995 | 12619151
MCR013742 | HPR095 | 2021-08-01 | Material | 70130897 | 37487912 | 50215393
MCR013743 | HPR095 | 2021-08-01 | Equipment | 17615795 | 9416383 | 10749473
MCR013744 | HPR095 | 2021-08-01 | Subcontract | 62663244 | 33496138 | 31079932
MCR013745 | HPR095 | 2021-08-01 | Overhead | 15856607 | 8476023 | 11091522
MCR013746 | HPR095 | 2021-09-01 | Labor | 24777458 | 16985897 | 15103961
MCR013747 | HPR095 | 2021-09-01 | Material | 73648551 | 50488906 | 59674871
MCR013748 | HPR095 | 2021-09-01 | Equipment | 18499375 | 12682031 | 12140423
MCR013749 | HPR095 | 2021-09-01 | Subcontract | 65806333 | 45112764 | 36057612
MCR013750 | HPR095 | 2021-09-01 | Overhead | 16651949 | 11415550 | 11098947
MCR013751 | HPR095 | 2021-10-01 | Labor | 25103977 | 22096819 | 21896926
MCR013752 | HPR095 | 2021-10-01 | Material | 74619098 | 65680616 | 80811815
MCR013753 | HPR095 | 2021-10-01 | Equipment | 18743161 | 16497953 | 17110711
MCR013754 | HPR095 | 2021-10-01 | Subcontract | 66673534 | 58686836 | 60366906
MCR013755 | HPR095 | 2021-10-01 | Overhead | 16871390 | 14850398 | 10498801
MCR013756 | HPR095 | 2021-11-01 | Labor | 24622536 | 21227958 | 19489130
MCR013757 | HPR095 | 2021-11-01 | Material | 73188062 | 63098015 | 62728920
MCR013758 | HPR095 | 2021-11-01 | Equipment | 18383707 | 15849243 | 17299356
MCR013759 | HPR095 | 2021-11-01 | Subcontract | 65394877 | 56379235 | 57130296
MCR013760 | HPR095 | 2021-11-01 | Overhead | 16547832 | 14266471 | 10670423
MCR013761 | HPR095 | 2021-12-01 | Labor | 23387898 | 23803148 | 21684011
MCR013762 | HPR095 | 2021-12-01 | Material | 69518223 | 70752512 | 85794096
MCR013763 | HPR095 | 2021-12-01 | Equipment | 17461900 | 17771935 | 18974590
MCR013764 | HPR095 | 2021-12-01 | Subcontract | 62115808 | 63218669 | 47318461
MCR013765 | HPR095 | 2021-12-01 | Overhead | 15718081 | 15997154 | 11058250
MCR013766 | HPR095 | 2022-01-01 | Labor | 21462347 | 26426210 | 25019227
MCR013767 | HPR095 | 2022-01-01 | Material | 63794713 | 78549304 | 99064841
MCR013768 | HPR095 | 2022-01-01 | Equipment | 16024243 | 19730368 | 17040387
MCR013769 | HPR095 | 2022-01-01 | Subcontract | 57001747 | 70185245 | 77049714
MCR013770 | HPR095 | 2022-01-01 | Overhead | 14423995 | 17760010 | 11271174
MCR013771 | HPR095 | 2022-02-01 | Labor | 18918286 | 23398742 | 24134017
MCR013772 | HPR095 | 2022-02-01 | Material | 56232740 | 69550455 | 91713224
MCR013773 | HPR095 | 2022-02-01 | Equipment | 14124793 | 17469996 | 18743224
MCR013774 | HPR095 | 2022-02-01 | Subcontract | 50244985 | 62144609 | 62666989
MCR013775 | HPR095 | 2022-02-01 | Overhead | 12714231 | 15725369 | 10895798
MCR013776 | HPR095 | 2022-03-01 | Labor | 15842424 | 16792864 | 16249499
MCR013777 | HPR095 | 2022-03-01 | Material | 47090043 | 49915133 | 56967520
MCR013778 | HPR095 | 2022-03-01 | Equipment | 11828289 | 12537908 | 13734267
MCR013779 | HPR095 | 2022-03-01 | Subcontract | 42075818 | 44600088 | 44977967
MCR013780 | HPR095 | 2022-03-01 | Overhead | 10647066 | 11285820 | 10975708
MCR013781 | HPR095 | 2022-04-01 | Labor | 12343166 | 16887781 | 14578349
MCR013782 | HPR095 | 2022-04-01 | Material | 36688845 | 50197264 | 65768960
MCR013783 | HPR095 | 2022-04-01 | Equipment | 9215669 | 12608775 | 12077363
MCR013784 | HPR095 | 2022-04-01 | Subcontract | 32782157 | 44852177 | 38231986
MCR013785 | HPR095 | 2022-04-01 | Overhead | 8295354 | 11349609 | 10347809
MCR013786 | HPR095 | 2022-05-01 | Labor | 8565409 | 13816596 | 14164571
MCR013787 | HPR095 | 2022-05-01 | Material | 25459835 | 41068471 | 49666407
MCR013788 | HPR095 | 2022-05-01 | Equipment | 6395116 | 10315764 | 10004438
MCR013789 | HPR095 | 2022-05-01 | Subcontract | 22748830 | 36695433 | 41296465
MCR013790 | HPR095 | 2022-05-01 | Overhead | 5756473 | 9285588 | 10529626
MCR013791 | HPR095 | 2022-06-01 | Labor | 4727276 | 8375644 | 8750067
MCR013792 | HPR095 | 2022-06-01 | Material | 14051363 | 24895778 | 34339646
MCR013793 | HPR095 | 2022-06-01 | Equipment | 3529485 | 6253434 | 5340614
MCR013794 | HPR095 | 2022-06-01 | Subcontract | 12555151 | 22244835 | 17341168
MCR013795 | HPR095 | 2022-06-01 | Overhead | 3177015 | 5628939 | 11054204
MCR013796 | HPR095 | 2022-07-01 | Labor | 1272810 | 3490501 | 2556482
MCR013797 | HPR095 | 2022-07-01 | Material | 3783302 | 10375171 | 11622545
MCR013798 | HPR095 | 2022-07-01 | Equipment | 950307 | 2606082 | 3201355
MCR013799 | HPR095 | 2022-07-01 | Subcontract | 3380450 | 9270406 | 9676578
MCR013800 | HPR095 | 2022-07-01 | Overhead | 855405 | 2345828 | 10070474
MCR013801 | HPR095 | 2022-08-01 | Labor | 0 | 2525044 | 2501140
MCR013802 | HPR095 | 2022-08-01 | Material | 0 | 7505445 | 8313707
MCR013803 | HPR095 | 2022-08-01 | Equipment | 0 | 1885251 | 2040497
MCR013804 | HPR095 | 2022-08-01 | Subcontract | 0 | 6706253 | 5918730
MCR013805 | HPR095 | 2022-08-01 | Overhead | 0 | 1696982 | 11186792
MCR013806 | HPR095 | 2022-09-01 | Labor | 0 | 1322933 | 1400445
MCR013807 | HPR095 | 2022-09-01 | Material | 0 | 3932289 | 6090756
MCR013808 | HPR095 | 2022-09-01 | Equipment | 0 | 987730 | 828781
MCR013809 | HPR095 | 2022-09-01 | Subcontract | 0 | 3513573 | 4287230
MCR013810 | HPR095 | 2022-09-01 | Overhead | 0 | 889091 | 10303670
MCR013811 | HPR096 | 2016-10-01 | Labor | 6323171 | 8507089 | 10074779
MCR013812 | HPR096 | 2016-10-01 | Material | 11725251 | 15774958 | 15946207
MCR013813 | HPR096 | 2016-10-01 | Equipment | 3453217 | 4645900 | 5241514
MCR013814 | HPR096 | 2016-10-01 | Subcontract | 22055096 | 29672559 | 30234944
MCR013815 | HPR096 | 2016-10-01 | Overhead | 4456893 | 5996230 | 19209647
MCR013816 | HPR096 | 2016-11-01 | Labor | 17638991 | 9208873 | 9682477
MCR013817 | HPR096 | 2016-11-01 | Material | 32708526 | 17076297 | 17929766
MCR013818 | HPR096 | 2016-11-01 | Equipment | 9633024 | 5029159 | 5253320
MCR013819 | HPR096 | 2016-11-01 | Subcontract | 61524454 | 32120368 | 28142138
MCR013820 | HPR096 | 2016-11-01 | Overhead | 12432860 | 6490883 | 19275911
MCR013821 | HPR096 | 2016-12-01 | Labor | 27002396 | 30513986 | 36324856
MCR013822 | HPR096 | 2016-12-01 | Material | 50071378 | 56583028 | 59859930
MCR013823 | HPR096 | 2016-12-01 | Equipment | 14746577 | 16664330 | 15425579
MCR013824 | HPR096 | 2016-12-01 | Subcontract | 94183830 | 106432186 | 104347067
MCR013825 | HPR096 | 2016-12-01 | Overhead | 19032666 | 21507814 | 20744979
MCR013826 | HPR096 | 2017-01-01 | Labor | 34474179 | 31217392 | 34225330
MCR013827 | HPR096 | 2017-01-01 | Material | 63926537 | 57887375 | 51148452
MCR013828 | HPR096 | 2017-01-01 | Equipment | 18827074 | 17048474 | 17712392
MCR013829 | HPR096 | 2017-01-01 | Subcontract | 120245263 | 108885652 | 99303033
MCR013830 | HPR096 | 2017-01-01 | Overhead | 24299160 | 22003610 | 22938702
MCR013831 | HPR096 | 2017-02-01 | Labor | 40119325 | 44405578 | 50468004
MCR013832 | HPR096 | 2017-02-01 | Material | 74394505 | 82342637 | 82953441
MCR013833 | HPR096 | 2017-02-01 | Equipment | 21910007 | 24250820 | 25154655
MCR013834 | HPR096 | 2017-02-01 | Subcontract | 139935421 | 154885788 | 129987182
MCR013835 | HPR096 | 2017-02-01 | Overhead | 28278147 | 31299316 | 20785392
MCR013836 | HPR096 | 2017-03-01 | Labor | 44007724 | 51762057 | 49741006
MCR013837 | HPR096 | 2017-03-01 | Material | 81604884 | 95983984 | 104349844
MCR013838 | HPR096 | 2017-03-01 | Equipment | 24033544 | 28268348 | 25789581
MCR013839 | HPR096 | 2017-03-01 | Subcontract | 153498081 | 180545044 | 188455469
MCR013840 | HPR096 | 2017-03-01 | Overhead | 31018889 | 36484538 | 23014414
MCR013841 | HPR096 | 2017-04-01 | Labor | 46215081 | 47090132 | 61713590
MCR013842 | HPR096 | 2017-04-01 | Material | 85698054 | 87320689 | 81437429
MCR013843 | HPR096 | 2017-04-01 | Equipment | 25239028 | 25716912 | 26174061
MCR013844 | HPR096 | 2017-04-01 | Subcontract | 161197299 | 164249461 | 148591639
MCR013845 | HPR096 | 2017-04-01 | Overhead | 32574746 | 33191527 | 21551757
MCR013846 | HPR096 | 2017-05-01 | Labor | 46824107 | 37006251 | 36360062
MCR013847 | HPR096 | 2017-05-01 | Material | 86827390 | 68621836 | 76368548
MCR013848 | HPR096 | 2017-05-01 | Equipment | 25571630 | 20209892 | 24966688
MCR013849 | HPR096 | 2017-05-01 | Subcontract | 163321570 | 129077080 | 132301903
MCR013850 | HPR096 | 2017-05-01 | Overhead | 33004019 | 26083893 | 21594706
MCR013851 | HPR096 | 2017-06-01 | Labor | 45926120 | 20200396 | 23271865
MCR013852 | HPR096 | 2017-06-01 | Material | 85162225 | 37458220 | 36374862
MCR013853 | HPR096 | 2017-06-01 | Equipment | 25081220 | 11031861 | 10492581
MCR013854 | HPR096 | 2017-06-01 | Subcontract | 160189410 | 70458588 | 64458305
MCR013855 | HPR096 | 2017-06-01 | Overhead | 32371072 | 14238270 | 20308510
MCR013856 | HPR096 | 2017-07-01 | Labor | 43623266 | 17770584 | 19855512
MCR013857 | HPR096 | 2017-07-01 | Material | 80891971 | 32952543 | 34698658
MCR013858 | HPR096 | 2017-07-01 | Equipment | 23823583 | 9704890 | 9146644
MCR013859 | HPR096 | 2017-07-01 | Subcontract | 152157097 | 61983449 | 59212484
MCR013860 | HPR096 | 2017-07-01 | Overhead | 30747903 | 12525614 | 22012187
MCR013861 | HPR096 | 2017-08-01 | Labor | 40031715 | 22635769 | 22694694
MCR013862 | HPR096 | 2017-08-01 | Material | 74232048 | 41974207 | 39161468
MCR013863 | HPR096 | 2017-08-01 | Equipment | 21862162 | 12361870 | 13141688
MCR013864 | HPR096 | 2017-08-01 | Subcontract | 139629841 | 78953121 | 72517653
MCR013865 | HPR096 | 2017-08-01 | Overhead | 28216395 | 15954845 | 20410386
MCR013866 | HPR096 | 2017-09-01 | Labor | 35286514 | 51593802 | 64829864
MCR013867 | HPR096 | 2017-09-01 | Material | 65432874 | 95671983 | 101353369
MCR013868 | HPR096 | 2017-09-01 | Equipment | 19270708 | 28176461 | 28428707
MCR013869 | HPR096 | 2017-09-01 | Subcontract | 123078671 | 179958174 | 195556561
MCR013870 | HPR096 | 2017-09-01 | Overhead | 24871735 | 36365943 | 20235630
MCR013871 | HPR096 | 2017-10-01 | Labor | 29549395 | 31472893 | 30192465
MCR013872 | HPR096 | 2017-10-01 | Material | 54794358 | 58361159 | 57890772
MCR013873 | HPR096 | 2017-10-01 | Equipment | 16137546 | 17188009 | 16865460
MCR013874 | HPR096 | 2017-10-01 | Subcontract | 103067713 | 109776835 | 80957056
MCR013875 | HPR096 | 2017-10-01 | Overhead | 20827921 | 22183700 | 20574557
MCR013876 | HPR096 | 2017-11-01 | Labor | 23022557 | 16608202 | 20644925
MCR013877 | HPR096 | 2017-11-01 | Material | 42691439 | 30797103 | 31625276
MCR013878 | HPR096 | 2017-11-01 | Equipment | 12573102 | 9070089 | 11287072
MCR013879 | HPR096 | 2017-11-01 | Subcontract | 80302228 | 57929085 | 61270912
MCR013880 | HPR096 | 2017-11-01 | Overhead | 16227472 | 11706308 | 20763945
MCR013881 | HPR096 | 2017-12-01 | Labor | 15976259 | 27136876 | 26777566
MCR013882 | HPR096 | 2017-12-01 | Material | 29625271 | 50320749 | 55059971
MCR013883 | HPR096 | 2017-12-01 | Equipment | 8724971 | 14820019 | 13234484
MCR013884 | HPR096 | 2017-12-01 | Subcontract | 55724879 | 94652894 | 94573931
MCR013885 | HPR096 | 2017-12-01 | Overhead | 11260882 | 19127455 | 20561533
MCR013886 | HPR096 | 2018-01-01 | Labor | 8817348 | 28087245 | 32360448
MCR013887 | HPR096 | 2018-01-01 | Material | 16350281 | 52083047 | 48367543
MCR013888 | HPR096 | 2018-01-01 | Equipment | 4815339 | 15339035 | 16708456
MCR013889 | HPR096 | 2018-01-01 | Subcontract | 30754736 | 97967761 | 98450751
MCR013890 | HPR096 | 2018-01-01 | Overhead | 6214916 | 19797323 | 21521135
MCR013891 | HPR096 | 2018-02-01 | Labor | 2374054 | 15061590 | 18302489
MCR013892 | HPR096 | 2018-02-01 | Material | 4402281 | 27929173 | 28870356
MCR013893 | HPR096 | 2018-02-01 | Equipment | 1296521 | 8225451 | 8087860
MCR013894 | HPR096 | 2018-02-01 | Subcontract | 8280653 | 52534533 | 43024348
MCR013895 | HPR096 | 2018-02-01 | Overhead | 1673354 | 10616177 | 22796534
MCR013896 | HPR096 | 2018-03-01 | Labor | 0 | 11174229 | 15316010
MCR013897 | HPR096 | 2018-03-01 | Material | 0 | 20720718 | 18760793
MCR013898 | HPR096 | 2018-03-01 | Equipment | 0 | 6102481 | 5590682
MCR013899 | HPR096 | 2018-03-01 | Subcontract | 0 | 38975492 | 36046851
MCR013900 | HPR096 | 2018-03-01 | Overhead | 0 | 7876166 | 20916773
MCR013901 | HPR096 | 2018-04-01 | Labor | 0 | 4828967 | 4856725
MCR013902 | HPR096 | 2018-04-01 | Material | 0 | 8954502 | 10791428
MCR013903 | HPR096 | 2018-04-01 | Equipment | 0 | 2637200 | 2968248
MCR013904 | HPR096 | 2018-04-01 | Subcontract | 0 | 16843341 | 17043133
MCR013905 | HPR096 | 2018-04-01 | Overhead | 0 | 3403702 | 22088959
MCR013906 | HPR096 | 2018-05-01 | Labor | 0 | 930290 | 1070050
MCR013907 | HPR096 | 2018-05-01 | Material | 0 | 1725066 | 1895196
MCR013908 | HPR096 | 2018-05-01 | Equipment | 0 | 508051 | 620392
MCR013909 | HPR096 | 2018-05-01 | Subcontract | 0 | 3244833 | 2031016
MCR013910 | HPR096 | 2018-05-01 | Overhead | 0 | 655716 | 21201689
MCR013911 | HPR097 | 2018-08-01 | Labor | 10244331 | 6710144 | 6201701
MCR013912 | HPR097 | 2018-08-01 | Material | 34726352 | 22746126 | 25306079
MCR013913 | HPR097 | 2018-08-01 | Equipment | 8214253 | 5380422 | 5413061
MCR013914 | HPR097 | 2018-08-01 | Subcontract | 31475780 | 20616968 | 19755932
MCR013915 | HPR097 | 2018-08-01 | Overhead | 7358355 | 4819800 | 26813640
MCR013916 | HPR097 | 2018-09-01 | Labor | 27638630 | 23488793 | 22522117
MCR013917 | HPR097 | 2018-09-01 | Material | 93689751 | 79622585 | 73703611
MCR013918 | HPR097 | 2018-09-01 | Equipment | 22161595 | 18834114 | 22743064
MCR013919 | HPR097 | 2018-09-01 | Subcontract | 84919891 | 72169487 | 74293670
MCR013920 | HPR097 | 2018-09-01 | Overhead | 19852430 | 16871661 | 25056665
MCR013921 | HPR097 | 2018-10-01 | Labor | 40540204 | 44148484 | 42156814
MCR013922 | HPR097 | 2018-10-01 | Material | 137423661 | 149655051 | 174261351
MCR013923 | HPR097 | 2018-10-01 | Equipment | 32506517 | 35399759 | 34565180
MCR013924 | HPR097 | 2018-10-01 | Subcontract | 124560074 | 135646541 | 105671596
MCR013925 | HPR097 | 2018-10-01 | Overhead | 29119445 | 31711221 | 25731342
MCR013926 | HPR097 | 2018-11-01 | Labor | 49163019 | 40582892 | 39967811
MCR013927 | HPR097 | 2018-11-01 | Material | 166653378 | 137568364 | 141203451
MCR013928 | HPR097 | 2018-11-01 | Equipment | 39420584 | 32540746 | 35525773
MCR013929 | HPR097 | 2018-11-01 | Subcontract | 151053735 | 124691232 | 131830449
MCR013930 | HPR097 | 2018-11-01 | Overhead | 35313088 | 29150107 | 24948220
MCR013931 | HPR097 | 2018-12-01 | Labor | 53744494 | 66445391 | 64851172
MCR013932 | HPR097 | 2018-12-01 | Material | 182183718 | 225237368 | 245224301
MCR013933 | HPR097 | 2018-12-01 | Equipment | 43094167 | 53278179 | 47245395
MCR013934 | HPR097 | 2018-12-01 | Subcontract | 165130352 | 204153951 | 167584279
MCR013935 | HPR097 | 2018-12-01 | Overhead | 38603896 | 47726768 | 22697974
MCR013936 | HPR097 | 2019-01-01 | Labor | 54552145 | 49017613 | 40464721
MCR013937 | HPR097 | 2019-01-01 | Material | 184921502 | 166160479 | 169763381
MCR013938 | HPR097 | 2019-01-01 | Equipment | 43741769 | 39303992 | 40283188
MCR013939 | HPR097 | 2019-01-01 | Subcontract | 167611864 | 150606974 | 158596740
MCR013940 | HPR097 | 2019-01-01 | Overhead | 39184020 | 35208645 | 25414491
MCR013941 | HPR097 | 2019-02-01 | Labor | 51893527 | 42743211 | 45519101
MCR013942 | HPR097 | 2019-02-01 | Material | 175909286 | 144891439 | 107581905
MCR013943 | HPR097 | 2019-02-01 | Equipment | 41609998 | 34272963 | 42515241
MCR013944 | HPR097 | 2019-02-01 | Subcontract | 159443240 | 131328829 | 139164498
MCR013945 | HPR097 | 2019-02-01 | Overhead | 37274373 | 30701833 | 25086063
MCR013946 | HPR097 | 2019-03-01 | Labor | 46132124 | 71501064 | 69080207
MCR013947 | HPR097 | 2019-03-01 | Material | 156379216 | 242375145 | 247681029
MCR013948 | HPR097 | 2019-03-01 | Equipment | 36990309 | 57331989 | 48392917
MCR013949 | HPR097 | 2019-03-01 | Subcontract | 141741289 | 219687541 | 206844702
MCR013950 | HPR097 | 2019-03-01 | Overhead | 33136041 | 51358184 | 25465704
MCR013951 | HPR097 | 2019-04-01 | Labor | 37715019 | 33109972 | 34489602
MCR013952 | HPR097 | 2019-04-01 | Material | 127846814 | 112236570 | 128515491
MCR013953 | HPR097 | 2019-04-01 | Equipment | 30241187 | 26548703 | 29706294
MCR013954 | HPR097 | 2019-04-01 | Subcontract | 115879671 | 101730630 | 143642419
MCR013955 | HPR097 | 2019-04-01 | Overhead | 27090155 | 23782416 | 23809325
MCR013956 | HPR097 | 2019-05-01 | Labor | 27227605 | 22074425 | 20150247
MCR013957 | HPR097 | 2019-05-01 | Material | 92296454 | 74828144 | 83751456
MCR013958 | HPR097 | 2019-05-01 | Equipment | 21832021 | 17700026 | 18322564
MCR013959 | HPR097 | 2019-05-01 | Subcontract | 83657014 | 67823831 | 107320135
MCR013960 | HPR097 | 2019-05-01 | Overhead | 19557196 | 15855741 | 24662058
MCR013961 | HPR097 | 2019-06-01 | Labor | 15527365 | 15358865 | 15840333
MCR013962 | HPR097 | 2019-06-01 | Material | 52634843 | 52063662 | 58168394
MCR013963 | HPR097 | 2019-06-01 | Equipment | 12450370 | 12315262 | 12004621
MCR013964 | HPR097 | 2019-06-01 | Subcontract | 47707942 | 47190226 | 69980349
MCR013965 | HPR097 | 2019-06-01 | Overhead | 11153083 | 11032052 | 25154229
MCR013966 | HPR097 | 2019-07-01 | Labor | 4288241 | 3485849 | 3885011
MCR013967 | HPR097 | 2019-07-01 | Material | 14536328 | 11816370 | 7658018
MCR013968 | HPR097 | 2019-07-01 | Equipment | 3438457 | 2795072 | 3223442
MCR013969 | HPR097 | 2019-07-01 | Subcontract | 13175651 | 10710295 | 35555855
MCR013970 | HPR097 | 2019-07-01 | Overhead | 3080181 | 2503835 | 25978003
MCR013971 | HPR098 | 2017-06-01 | Labor | 5784949 | 2769002 | 3245010
MCR013972 | HPR098 | 2017-06-01 | Material | 16863908 | 8072015 | 8443135
MCR013973 | HPR098 | 2017-06-01 | Equipment | 5785527 | 2769278 | 2720689
MCR013974 | HPR098 | 2017-06-01 | Subcontract | 11447195 | 5479271 | 5772417
MCR013975 | HPR098 | 2017-06-01 | Overhead | 4798494 | 2296829 | 23412595
MCR013976 | HPR098 | 2017-07-01 | Labor | 16207221 | 5980901 | 5769110
MCR013977 | HPR098 | 2017-07-01 | Material | 47246236 | 17435132 | 17034739
MCR013978 | HPR098 | 2017-07-01 | Equipment | 16208838 | 5981497 | 5789033
MCR013979 | HPR098 | 2017-07-01 | Subcontract | 32070673 | 11834941 | 11891335
MCR013980 | HPR098 | 2017-07-01 | Overhead | 13443550 | 4961032 | 25178626
MCR013981 | HPR098 | 2017-08-01 | Labor | 24943193 | 10021761 | 11092556
MCR013982 | HPR098 | 2017-08-01 | Material | 72712775 | 29214786 | 34957620
MCR013983 | HPR098 | 2017-08-01 | Equipment | 24945683 | 10022761 | 9969741
MCR013984 | HPR098 | 2017-08-01 | Subcontract | 49357322 | 19830952 | 20720263
MCR013985 | HPR098 | 2017-08-01 | Overhead | 20689856 | 8312841 | 25006643
MCR013986 | HPR098 | 2017-09-01 | Labor | 32041974 | 20119412 | 21730406
MCR013987 | HPR098 | 2017-09-01 | Material | 93406679 | 58650801 | 61758954
MCR013988 | HPR098 | 2017-09-01 | Equipment | 32045172 | 20121420 | 23499163
MCR013989 | HPR098 | 2017-09-01 | Subcontract | 63404312 | 39812075 | 39900465
MCR013990 | HPR098 | 2017-09-01 | Overhead | 26578146 | 16688630 | 25293036
MCR013991 | HPR098 | 2017-10-01 | Labor | 37555823 | 18625085 | 16993840
MCR013992 | HPR098 | 2017-10-01 | Material | 109480294 | 54294635 | 51372743
MCR013993 | HPR098 | 2017-10-01 | Equipment | 37559572 | 18626943 | 20010619
MCR013994 | HPR098 | 2017-10-01 | Subcontract | 74315058 | 36855116 | 37068100
MCR013995 | HPR098 | 2017-10-01 | Overhead | 31151768 | 15449117 | 22669883
MCR013996 | HPR098 | 2017-11-01 | Labor | 41540651 | 33918877 | 39848413
MCR013997 | HPR098 | 2017-11-01 | Material | 121096604 | 98878103 | 104850549
MCR013998 | HPR098 | 2017-11-01 | Equipment | 41544797 | 33922262 | 31498260
MCR013999 | HPR098 | 2017-11-01 | Subcontract | 82200192 | 67118307 | 63289114
MCR014000 | HPR098 | 2017-11-01 | Overhead | 34457099 | 28134997 | 24711236
MCR014001 | HPR098 | 2017-12-01 | Labor | 44056639 | 32550285 | 34425368
MCR014002 | HPR098 | 2017-12-01 | Material | 128431048 | 94888474 | 103324506
MCR014003 | HPR098 | 2017-12-01 | Equipment | 44061036 | 32553534 | 35895704
MCR014004 | HPR098 | 2017-12-01 | Subcontract | 87178801 | 64410153 | 69388632
MCR014005 | HPR098 | 2017-12-01 | Overhead | 36544058 | 26999779 | 23131344
MCR014006 | HPR098 | 2018-01-01 | Labor | 45169038 | 21003985 | 20859081
MCR014007 | HPR098 | 2018-01-01 | Material | 131673842 | 61229450 | 45313621
MCR014008 | HPR098 | 2018-01-01 | Equipment | 45173546 | 21006081 | 20550749
MCR014009 | HPR098 | 2018-01-01 | Subcontract | 89380005 | 41562458 | 36794205
MCR014010 | HPR098 | 2018-01-01 | Overhead | 37466770 | 17422365 | 22352874
MCR014011 | HPR098 | 2018-02-01 | Labor | 44949217 | 43702242 | 42854336
MCR014012 | HPR098 | 2018-02-01 | Material | 131033034 | 127397935 | 136377379
MCR014013 | HPR098 | 2018-02-01 | Equipment | 44953703 | 43706604 | 47268094
MCR014014 | HPR098 | 2018-02-01 | Subcontract | 88945025 | 86477525 | 88167169
MCR014015 | HPR098 | 2018-02-01 | Overhead | 37284433 | 36250094 | 24335930
MCR014016 | HPR098 | 2018-03-01 | Labor | 43476067 | 29413423 | 33009209
MCR014017 | HPR098 | 2018-03-01 | Material | 126738602 | 85744099 | 91739365
MCR014018 | HPR098 | 2018-03-01 | Equipment | 43480406 | 29416359 | 31486734
MCR014019 | HPR098 | 2018-03-01 | Subcontract | 86029971 | 58202964 | 64516049
MCR014020 | HPR098 | 2018-03-01 | Overhead | 36062486 | 24397818 | 21713541
MCR014021 | HPR098 | 2018-04-01 | Labor | 40837957 | 25911399 | 25765685
MCR014022 | HPR098 | 2018-04-01 | Material | 119048156 | 75535225 | 77912717
MCR014023 | HPR098 | 2018-04-01 | Equipment | 40842033 | 25913985 | 27815109
MCR014024 | HPR098 | 2018-04-01 | Subcontract | 80809708 | 51273197 | 52911631
MCR014025 | HPR098 | 2018-04-01 | Overhead | 33874229 | 21492962 | 21524730
MCR014026 | HPR098 | 2018-05-01 | Labor | 37135556 | 43698732 | 68431862
MCR014027 | HPR098 | 2018-05-01 | Material | 108255158 | 127387700 | 140963120
MCR014028 | HPR098 | 2018-05-01 | Equipment | 37139262 | 43703093 | 46794553
MCR014029 | HPR098 | 2018-05-01 | Subcontract | 73483437 | 86470578 | 90738527
MCR014030 | HPR098 | 2018-05-01 | Overhead | 30803165 | 36247181 | 24044878
MCR014031 | HPR098 | 2018-06-01 | Labor | 32486107 | 41132911 | 75156113
MCR014032 | HPR098 | 2018-06-01 | Material | 94701388 | 119907987 | 152080588
MCR014033 | HPR098 | 2018-06-01 | Equipment | 32489350 | 41137016 | 44739109
MCR014034 | HPR098 | 2018-06-01 | Subcontract | 64283159 | 81393360 | 91137248
MCR014035 | HPR098 | 2018-06-01 | Overhead | 26946545 | 34118887 | 23122191
MCR014036 | HPR098 | 2018-07-01 | Labor | 27030342 | 19379502 | 19001359
MCR014037 | HPR098 | 2018-07-01 | Material | 78797096 | 56493863 | 68953599
MCR014038 | HPR098 | 2018-07-01 | Equipment | 27033040 | 19381436 | 15950576
MCR014039 | HPR098 | 2018-07-01 | Subcontract | 53487349 | 38347949 | 34688093
MCR014040 | HPR098 | 2018-07-01 | Overhead | 22421102 | 16074890 | 22578215
MCR014041 | HPR098 | 2018-08-01 | Labor | 20944677 | 20555637 | 21256924
MCR014042 | HPR098 | 2018-08-01 | Material | 61056561 | 59922457 | 44952562
MCR014043 | HPR098 | 2018-08-01 | Equipment | 20946768 | 20557689 | 20760983
MCR014044 | HPR098 | 2018-08-01 | Subcontract | 41445101 | 40675273 | 39171164
MCR014045 | HPR098 | 2018-08-01 | Overhead | 17373171 | 17050470 | 21555521
MCR014046 | HPR098 | 2018-09-01 | Labor | 14465707 | 32216412 | 33670729
MCR014047 | HPR098 | 2018-09-01 | Material | 42169488 | 93915188 | 110023941
MCR014048 | HPR098 | 2018-09-01 | Equipment | 14467151 | 32219627 | 32779080
MCR014049 | HPR098 | 2018-09-01 | Subcontract | 28624585 | 63749487 | 54570294
MCR014050 | HPR098 | 2018-09-01 | Overhead | 11999001 | 26722838 | 26837394
MCR014051 | HPR098 | 2018-10-01 | Labor | 7951140 | 26800461 | 28023095
MCR014052 | HPR098 | 2018-10-01 | Material | 23178647 | 78126960 | 78134454
MCR014053 | HPR098 | 2018-10-01 | Equipment | 7951934 | 26803136 | 30869748
MCR014054 | HPR098 | 2018-10-01 | Subcontract | 15733630 | 53032462 | 57593928
MCR014055 | HPR098 | 2018-10-01 | Overhead | 6595304 | 22230420 | 23074640
MCR014056 | HPR098 | 2018-11-01 | Labor | 2133838 | 23869161 | 27501776
MCR014057 | HPR098 | 2018-11-01 | Material | 6220427 | 69581827 | 78115453
MCR014058 | HPR098 | 2018-11-01 | Equipment | 2134051 | 23871544 | 24632684
MCR014059 | HPR098 | 2018-11-01 | Subcontract | 4222417 | 47232039 | 45708418
MCR014060 | HPR098 | 2018-11-01 | Overhead | 1769974 | 19798969 | 25000423
MCR014061 | HPR098 | 2018-12-01 | Labor | 0 | 15144887 | 12796374
MCR014062 | HPR098 | 2018-12-01 | Material | 0 | 44149390 | 41136008
MCR014063 | HPR098 | 2018-12-01 | Equipment | 0 | 15146399 | 15720622
MCR014064 | HPR098 | 2018-12-01 | Subcontract | 0 | 29968539 | 32833533
MCR014065 | HPR098 | 2018-12-01 | Overhead | 0 | 12562366 | 23082903
MCR014066 | HPR098 | 2019-01-01 | Labor | 0 | 17900925 | 21271324
MCR014067 | HPR098 | 2019-01-01 | Material | 0 | 52183612 | 45499042
MCR014068 | HPR098 | 2019-01-01 | Equipment | 0 | 17902712 | 20376944
MCR014069 | HPR098 | 2019-01-01 | Subcontract | 0 | 35422157 | 37093317
MCR014070 | HPR098 | 2019-01-01 | Overhead | 0 | 14848442 | 22957130
MCR014071 | HPR098 | 2019-02-01 | Labor | 0 | 10646823 | 9357346
MCR014072 | HPR098 | 2019-02-01 | Material | 0 | 31036927 | 38208769
MCR014073 | HPR098 | 2019-02-01 | Equipment | 0 | 10647886 | 11035531
MCR014074 | HPR098 | 2019-02-01 | Subcontract | 0 | 21067819 | 21872950
MCR014075 | HPR098 | 2019-02-01 | Overhead | 0 | 8831317 | 22256731
MCR014076 | HPR098 | 2019-03-01 | Labor | 0 | 8433259 | 7549652
MCR014077 | HPR098 | 2019-03-01 | Material | 0 | 24584087 | 24746866
MCR014078 | HPR098 | 2019-03-01 | Equipment | 0 | 8434100 | 10354813
MCR014079 | HPR098 | 2019-03-01 | Subcontract | 0 | 16687641 | 17766209
MCR014080 | HPR098 | 2019-03-01 | Overhead | 0 | 6995211 | 23909676
MCR014081 | HPR098 | 2019-04-01 | Labor | 0 | 8774939 | 8800237
MCR014082 | HPR098 | 2019-04-01 | Material | 0 | 25580131 | 28181568
MCR014083 | HPR098 | 2019-04-01 | Equipment | 0 | 8775815 | 10714233
MCR014084 | HPR098 | 2019-04-01 | Subcontract | 0 | 17363754 | 16813771
MCR014085 | HPR098 | 2019-04-01 | Overhead | 0 | 7278628 | 24416822
MCR014086 | HPR098 | 2019-05-01 | Labor | 0 | 5368632 | 5548982
MCR014087 | HPR098 | 2019-05-01 | Material | 0 | 15650286 | 12654403
MCR014088 | HPR098 | 2019-05-01 | Equipment | 0 | 5369168 | 6409408
MCR014089 | HPR098 | 2019-05-01 | Subcontract | 0 | 10623390 | 11929986
MCR014090 | HPR098 | 2019-05-01 | Overhead | 0 | 4453167 | 21267952
MCR014091 | HPR098 | 2019-06-01 | Labor | 0 | 771447 | 904585
MCR014092 | HPR098 | 2019-06-01 | Material | 0 | 2248872 | 3066032
MCR014093 | HPR098 | 2019-06-01 | Equipment | 0 | 771524 | 859738
MCR014094 | HPR098 | 2019-06-01 | Subcontract | 0 | 1526531 | 1237581
MCR014095 | HPR098 | 2019-06-01 | Overhead | 0 | 639899 | 23836167
MCR014096 | HPR099 | 2019-10-01 | Labor | 10030181 | 9915883 | 10282353
MCR014097 | HPR099 | 2019-10-01 | Material | 28589118 | 28263333 | 29857178
MCR014098 | HPR099 | 2019-10-01 | Equipment | 7067986 | 6987443 | 7034073
MCR014099 | HPR099 | 2019-10-01 | Subcontract | 30703553 | 30353673 | 30797374
MCR014100 | HPR099 | 2019-10-01 | Overhead | 6106760 | 6037171 | 23695055
MCR014101 | HPR099 | 2019-11-01 | Labor | 27688478 | 21249016 | 23508183
MCR014102 | HPR099 | 2019-11-01 | Material | 78920727 | 60566269 | 65412929
MCR014103 | HPR099 | 2019-11-01 | Equipment | 19511291 | 14973584 | 16623981
MCR014104 | HPR099 | 2019-11-01 | Subcontract | 84757660 | 65045716 | 65922264
MCR014105 | HPR099 | 2019-11-01 | Overhead | 16857810 | 12937218 | 24221712
MCR014106 | HPR099 | 2019-12-01 | Labor | 41833556 | 49632311 | 58416189
MCR014107 | HPR099 | 2019-12-01 | Material | 119238575 | 141467439 | 140743127
MCR014108 | HPR099 | 2019-12-01 | Equipment | 29478930 | 34974493 | 34273733
MCR014109 | HPR099 | 2019-12-01 | Subcontract | 128057392 | 151930291 | 160446154
MCR014110 | HPR099 | 2019-12-01 | Overhead | 25469878 | 30218060 | 24735520
MCR014111 | HPR099 | 2020-01-01 | Labor | 52592384 | 34860511 | 31144163
MCR014112 | HPR099 | 2020-01-01 | Material | 149904563 | 99363240 | 107104595
MCR014113 | HPR099 | 2020-01-01 | Equipment | 37060373 | 24565221 | 26360655
MCR014114 | HPR099 | 2020-01-01 | Subcontract | 160991420 | 106712089 | 101268212
MCR014115 | HPR099 | 2020-01-01 | Overhead | 32020266 | 21224420 | 24798535
MCR014116 | HPR099 | 2020-02-01 | Labor | 60102216 | 24534144 | 26572987
MCR014117 | HPR099 | 2020-02-01 | Material | 171309906 | 69929900 | 68336429
MCR014118 | HPR099 | 2020-02-01 | Equipment | 42352340 | 17288521 | 16176881
MCR014119 | HPR099 | 2020-02-01 | Subcontract | 183979890 | 75101875 | 74250743
MCR014120 | HPR099 | 2020-02-01 | Overhead | 36592541 | 14937331 | 25918943
MCR014121 | HPR099 | 2020-03-01 | Labor | 64512661 | 43031424 | 43422512
MCR014122 | HPR099 | 2020-03-01 | Material | 183881040 | 122652869 | 124773594
MCR014123 | HPR099 | 2020-03-01 | Equipment | 45460257 | 30323034 | 35574448
MCR014124 | HPR099 | 2020-03-01 | Subcontract | 197480778 | 131724206 | 145648954
MCR014125 | HPR099 | 2020-03-01 | Overhead | 39277790 | 26199186 | 25996410
MCR014126 | HPR099 | 2020-04-01 | Labor | 65988470 | 47011976 | 47735337
MCR014127 | HPR099 | 2020-04-01 | Material | 188087551 | 133998673 | 145623786
MCR014128 | HPR099 | 2020-04-01 | Equipment | 46500218 | 33128016 | 29413543
MCR014129 | HPR099 | 2020-04-01 | Subcontract | 201998400 | 143909139 | 158263674
MCR014130 | HPR099 | 2020-04-01 | Overhead | 40176319 | 28622699 | 25969557
MCR014131 | HPR099 | 2020-05-01 | Labor | 64713372 | 53667438 | 55288469
MCR014132 | HPR099 | 2020-05-01 | Material | 184453127 | 152968798 | 142398870
MCR014133 | HPR099 | 2020-05-01 | Equipment | 45601692 | 37817933 | 38417253
MCR014134 | HPR099 | 2020-05-01 | Subcontract | 198095176 | 164282284 | 162188151
MCR014135 | HPR099 | 2020-05-01 | Overhead | 39399990 | 32674800 | 25768191
MCR014136 | HPR099 | 2020-06-01 | Labor | 60895604 | 57830666 | 89746751
MCR014137 | HPR099 | 2020-06-01 | Material | 173571308 | 164835286 | 221012964
MCR014138 | HPR099 | 2020-06-01 | Equipment | 42911419 | 40751643 | 44741602
MCR014139 | HPR099 | 2020-06-01 | Subcontract | 186408544 | 177026410 | 196148296
MCR014140 | HPR099 | 2020-06-01 | Overhead | 37075586 | 35209534 | 24344463
MCR014141 | HPR099 | 2020-07-01 | Labor | 54776245 | 41168620 | 77266504
MCR014142 | HPR099 | 2020-07-01 | Material | 156129242 | 117343303 | 160100966
MCR014143 | HPR099 | 2020-07-01 | Equipment | 38599279 | 29010368 | 24966550
MCR014144 | HPR099 | 2020-07-01 | Subcontract | 167676473 | 126021947 | 116361674
MCR014145 | HPR099 | 2020-07-01 | Overhead | 33349885 | 25065040 | 25632519
MCR014146 | HPR099 | 2020-08-01 | Labor | 46642618 | 50087718 | 50699756
MCR014147 | HPR099 | 2020-08-01 | Material | 132945890 | 142765489 | 140641903
MCR014148 | HPR099 | 2020-08-01 | Equipment | 32867741 | 35295405 | 42276218
MCR014149 | HPR099 | 2020-08-01 | Subcontract | 142778493 | 153324344 | 136372315
MCR014150 | HPR099 | 2020-08-01 | Overhead | 28397820 | 30495329 | 24507007
MCR014151 | HPR099 | 2020-09-01 | Labor | 36851812 | 42070852 | 43168601
MCR014152 | HPR099 | 2020-09-01 | Material | 105039063 | 119914941 | 120285632
MCR014153 | HPR099 | 2020-09-01 | Equipment | 25968435 | 29646145 | 28386803
MCR014154 | HPR099 | 2020-09-01 | Subcontract | 112807693 | 128783782 | 146030611
MCR014155 | HPR099 | 2020-09-01 | Overhead | 22436801 | 25614353 | 26429542
MCR014156 | HPR099 | 2020-10-01 | Labor | 25877601 | 35770403 | 34931802
MCR014157 | HPR099 | 2020-10-01 | Material | 73759167 | 101956713 | 95858224
MCR014158 | HPR099 | 2020-10-01 | Equipment | 18235217 | 25206396 | 26448668
MCR014159 | HPR099 | 2020-10-01 | Subcontract | 79214354 | 109497374 | 119791645
MCR014160 | HPR099 | 2020-10-01 | Overhead | 15755279 | 21778397 | 25248988
MCR014161 | HPR099 | 2020-11-01 | Labor | 14426340 | 26520782 | 29558853
MCR014162 | HPR099 | 2020-11-01 | Material | 41119531 | 75592432 | 76207411
MCR014163 | HPR099 | 2020-11-01 | Equipment | 10165836 | 18688449 | 20424279
MCR014164 | HPR099 | 2020-11-01 | Subcontract | 44160708 | 81183206 | 72304830
MCR014165 | HPR099 | 2020-11-01 | Overhead | 8783311 | 16146872 | 24904384
MCR014166 | HPR099 | 2020-12-01 | Labor | 3915298 | 32751379 | 33830765
MCR014167 | HPR099 | 2020-12-01 | Material | 11159809 | 93351562 | 108993031
MCR014168 | HPR099 | 2020-12-01 | Equipment | 2759000 | 23078975 | 24028877
MCR014169 | HPR099 | 2020-12-01 | Subcontract | 11985182 | 100255791 | 109186231
MCR014170 | HPR099 | 2020-12-01 | Overhead | 2383784 | 19940300 | 24757836
MCR014171 | HPR099 | 2021-01-01 | Labor | 0 | 22611582 | 20640544
MCR014172 | HPR099 | 2021-01-01 | Material | 0 | 64450003 | 66493487
MCR014173 | HPR099 | 2021-01-01 | Equipment | 0 | 15933745 | 16191314
MCR014174 | HPR099 | 2021-01-01 | Subcontract | 0 | 69216688 | 60281777
MCR014175 | HPR099 | 2021-01-01 | Overhead | 0 | 13766801 | 25304859
MCR014176 | HPR099 | 2021-02-01 | Labor | 0 | 17089469 | 16600319
MCR014177 | HPR099 | 2021-02-01 | Material | 0 | 48710273 | 49710034
MCR014178 | HPR099 | 2021-02-01 | Equipment | 0 | 12042468 | 14176072
MCR014179 | HPR099 | 2021-02-01 | Subcontract | 0 | 52312857 | 61638651
MCR014180 | HPR099 | 2021-02-01 | Overhead | 0 | 10404726 | 25810972
MCR014181 | HPR099 | 2021-03-01 | Labor | 0 | 12704366 | 12890357
MCR014182 | HPR099 | 2021-03-01 | Material | 0 | 36211373 | 38397557
MCR014183 | HPR099 | 2021-03-01 | Equipment | 0 | 8952409 | 10910516
MCR014184 | HPR099 | 2021-03-01 | Subcontract | 0 | 38889546 | 39117769
MCR014185 | HPR099 | 2021-03-01 | Overhead | 0 | 7734907 | 25821005
MCR014186 | HPR099 | 2021-04-01 | Labor | 0 | 6694583 | 5833910
MCR014187 | HPR099 | 2021-04-01 | Material | 0 | 19081633 | 22017069
MCR014188 | HPR099 | 2021-04-01 | Equipment | 0 | 4717484 | 5659876
MCR014189 | HPR099 | 2021-04-01 | Subcontract | 0 | 20492900 | 21093214
MCR014190 | HPR099 | 2021-04-01 | Overhead | 0 | 4075920 | 26009613
MCR014191 | HPR099 | 2021-05-01 | Labor | 0 | 1643713 | 1539166
MCR014192 | HPR099 | 2021-05-01 | Material | 0 | 4685089 | 4688251
MCR014193 | HPR099 | 2021-05-01 | Equipment | 0 | 1158278 | 1216340
MCR014194 | HPR099 | 2021-05-01 | Subcontract | 0 | 5031596 | 4057920
MCR014195 | HPR099 | 2021-05-01 | Overhead | 0 | 1000755 | 25420273
MCR014196 | HPR100 | 2017-05-01 | Labor | 30042496 | 27176852 | 27532746
MCR014197 | HPR100 | 2017-05-01 | Material | 67199779 | 60789840 | 57490002
MCR014198 | HPR100 | 2017-05-01 | Equipment | 16622435 | 15036882 | 15574454
MCR014199 | HPR100 | 2017-05-01 | Subcontract | 95300564 | 86210194 | 84389343
MCR014200 | HPR100 | 2017-05-01 | Overhead | 21183845 | 19163196 | 63785878
MCR014201 | HPR100 | 2017-06-01 | Labor | 80187407 | 77341216 | 84042012
MCR014202 | HPR100 | 2017-06-01 | Material | 179365129 | 172998700 | 195194928
MCR014203 | HPR100 | 2017-06-01 | Equipment | 44367484 | 42792694 | 45559355
MCR014204 | HPR100 | 2017-06-01 | Subcontract | 254369852 | 245341187 | 285497000
MCR014205 | HPR100 | 2017-06-01 | Overhead | 56542493 | 54535560 | 60574145
MCR014206 | HPR100 | 2017-07-01 | Labor | 115950532 | 88168191 | 78534838
MCR014207 | HPR100 | 2017-07-01 | Material | 259360950 | 197216739 | 192159728
MCR014208 | HPR100 | 2017-07-01 | Equipment | 64155128 | 48783231 | 50588218
MCR014209 | HPR100 | 2017-07-01 | Subcontract | 367817352 | 279686431 | 251844472
MCR014210 | HPR100 | 2017-07-01 | Overhead | 81760121 | 62169977 | 68729867
MCR014211 | HPR100 | 2017-08-01 | Labor | 138097977 | 61768507 | 58498068
MCR014212 | HPR100 | 2017-08-01 | Material | 308900888 | 138165287 | 136472967
MCR014213 | HPR100 | 2017-08-01 | Equipment | 76409252 | 34176354 | 29884183
MCR014214 | HPR100 | 2017-08-01 | Subcontract | 438073297 | 195941564 | 226922816
MCR014215 | HPR100 | 2017-08-01 | Overhead | 97376933 | 43554786 | 67986559
MCR014216 | HPR100 | 2017-09-01 | Labor | 147491087 | 127936405 | 123412308
MCR014217 | HPR100 | 2017-09-01 | Material | 329911624 | 286171240 | 282495053
MCR014218 | HPR100 | 2017-09-01 | Equipment | 81606435 | 70786881 | 69633449
MCR014219 | HPR100 | 2017-09-01 | Subcontract | 467870047 | 405838842 | 452276597
MCR014220 | HPR100 | 2017-09-01 | Overhead | 104000291 | 90211711 | 69826542
MCR014221 | HPR100 | 2017-10-01 | Labor | 145117580 | 159898063 | 164026932
MCR014222 | HPR100 | 2017-10-01 | Material | 324602507 | 357663847 | 387760024
MCR014223 | HPR100 | 2017-10-01 | Equipment | 80293180 | 88471183 | 83632579
MCR014224 | HPR100 | 2017-10-01 | Subcontract | 460340828 | 507227356 | 502501709
MCR014225 | HPR100 | 2017-10-01 | Overhead | 102326662 | 112748813 | 66385521
MCR014226 | HPR100 | 2017-11-01 | Labor | 132141118 | 106050349 | 99114357
MCR014227 | HPR100 | 2017-11-01 | Material | 295576444 | 237215982 | 245836335
MCR014228 | HPR100 | 2017-11-01 | Equipment | 73113337 | 58677383 | 64584220
MCR014229 | HPR100 | 2017-11-01 | Subcontract | 419176999 | 336412071 | 357444536
MCR014230 | HPR100 | 2017-11-01 | Overhead | 93176578 | 74779212 | 67460745
MCR014231 | HPR100 | 2017-12-01 | Labor | 109987358 | 172005662 | 136668762
MCR014232 | HPR100 | 2017-12-01 | Material | 246022377 | 384746417 | 416603048
MCR014233 | HPR100 | 2017-12-01 | Equipment | 60855719 | 95170286 | 95921710
MCR014234 | HPR100 | 2017-12-01 | Subcontract | 348901017 | 545634985 | 617956589
MCR014235 | HPR100 | 2017-12-01 | Overhead | 77555312 | 121286237 | 69339075
MCR014236 | HPR100 | 2018-01-01 | Labor | 80513516 | 108446782 | 126000010
MCR014237 | HPR100 | 2018-01-01 | Material | 180094575 | 242576381 | 262799610
MCR014238 | HPR100 | 2018-01-01 | Equipment | 44547919 | 60003323 | 61564795
MCR014239 | HPR100 | 2018-01-01 | Subcontract | 255404330 | 344014016 | 346559360
MCR014240 | HPR100 | 2018-01-01 | Overhead | 56772441 | 76469007 | 73017572
MCR014241 | HPR100 | 2018-02-01 | Labor | 46421139 | 63813777 | 48553268
MCR014242 | HPR100 | 2018-02-01 | Material | 103835925 | 142740198 | 126779086
MCR014243 | HPR100 | 2018-02-01 | Equipment | 25684696 | 35307997 | 31485571
MCR014244 | HPR100 | 2018-02-01 | Subcontract | 147256767 | 202429555 | 283887375
MCR014245 | HPR100 | 2018-02-01 | Overhead | 32732907 | 44996966 | 71869246
MCR014246 | HPR100 | 2018-03-01 | Labor | 12925479 | 37818555 | 37762112
MCR014247 | HPR100 | 2018-03-01 | Material | 28912023 | 84593457 | 75974975
MCR014248 | HPR100 | 2018-03-01 | Equipment | 7151634 | 20924908 | 23712573
MCR014249 | HPR100 | 2018-03-01 | Subcontract | 41002100 | 119967718 | 184386583
MCR014250 | HPR100 | 2018-03-01 | Overhead | 9114134 | 26666972 | 67119981
MCR014251 | HPR100 | 2018-04-01 | Labor | 0 | 8451328 | 8917158
MCR014252 | HPR100 | 2018-04-01 | Material | 0 | 18904135 | 24470493
MCR014253 | HPR100 | 2018-04-01 | Equipment | 0 | 4676098 | 3446813
MCR014254 | HPR100 | 2018-04-01 | Subcontract | 0 | 26809236 | 83901743
MCR014255 | HPR100 | 2018-04-01 | Overhead | 0 | 5959279 | 65962732
MCR014256 | HPR101 | 2020-09-01 | Labor | 12901903 | 12329307 | 13939321
MCR014257 | HPR101 | 2020-09-01 | Material | 27449512 | 26231282 | 27869817
MCR014258 | HPR101 | 2020-09-01 | Equipment | 5526353 | 5281090 | 5993657
MCR014259 | HPR101 | 2020-09-01 | Subcontract | 31693606 | 30287019 | 32699600
MCR014260 | HPR101 | 2020-09-01 | Overhead | 7391524 | 7063482 | 21917024
MCR014261 | HPR101 | 2020-10-01 | Labor | 33986852 | 19235073 | 16789744
MCR014262 | HPR101 | 2020-10-01 | Material | 72308906 | 40923682 | 41248664
MCR014263 | HPR101 | 2020-10-01 | Equipment | 14557802 | 8239080 | 8022472
MCR014264 | HPR101 | 2020-10-01 | Subcontract | 83488914 | 47251078 | 51755866
MCR014265 | HPR101 | 2020-10-01 | Overhead | 19471129 | 11019809 | 21021286
MCR014266 | HPR101 | 2020-11-01 | Labor | 48273822 | 26603843 | 30191920
MCR014267 | HPR101 | 2020-11-01 | Material | 102705226 | 56601147 | 53335003
MCR014268 | HPR101 | 2020-11-01 | Equipment | 20677430 | 11395392 | 12222121
MCR014269 | HPR101 | 2020-11-01 | Subcontract | 118584947 | 65352507 | 68410752
MCR014270 | HPR101 | 2020-11-01 | Overhead | 27656161 | 15241390 | 21599495
MCR014271 | HPR101 | 2020-12-01 | Labor | 56173651 | 33275972 | 30613954
MCR014272 | HPR101 | 2020-12-01 | Material | 119512547 | 70796469 | 78433201
MCR014273 | HPR101 | 2020-12-01 | Equipment | 24061213 | 14253306 | 16054661
MCR014274 | HPR101 | 2020-12-01 | Subcontract | 137990924 | 81742633 | 80354837
MCR014275 | HPR101 | 2020-12-01 | Overhead | 32181987 | 19063865 | 21493741
MCR014276 | HPR101 | 2021-01-01 | Labor | 58156160 | 38128017 | 38731670
MCR014277 | HPR101 | 2021-01-01 | Material | 123730445 | 81119463 | 86681774
MCR014278 | HPR101 | 2021-01-01 | Equipment | 24910394 | 16331613 | 15196825
MCR014279 | HPR101 | 2021-01-01 | Subcontract | 142860971 | 93661711 | 97162335
MCR014280 | HPR101 | 2021-01-01 | Overhead | 33317770 | 21843610 | 21389696
MCR014281 | HPR101 | 2021-02-01 | Labor | 54773011 | 38232554 | 42878437
MCR014282 | HPR101 | 2021-02-01 | Material | 116532608 | 81341872 | 76858594
MCR014283 | HPR101 | 2021-02-01 | Equipment | 23461268 | 16376391 | 16404327
MCR014284 | HPR101 | 2021-02-01 | Subcontract | 134550243 | 93918508 | 88386780
MCR014285 | HPR101 | 2021-02-01 | Overhead | 31379558 | 21903500 | 20853432
MCR014286 | HPR101 | 2021-03-01 | Labor | 46697218 | 79714376 | 84193273
MCR014287 | HPR101 | 2021-03-01 | Material | 99350912 | 169596741 | 160408935
MCR014288 | HPR101 | 2021-03-01 | Equipment | 20002113 | 34144560 | 37164164
MCR014289 | HPR101 | 2021-03-01 | Subcontract | 114712008 | 195818863 | 186228268
MCR014290 | HPR101 | 2021-03-01 | Overhead | 26752922 | 45668512 | 19644806
MCR014291 | HPR101 | 2021-04-01 | Labor | 34800699 | 37408210 | 37373220
MCR014292 | HPR101 | 2021-04-01 | Material | 74040410 | 79588034 | 99989218
MCR014293 | HPR101 | 2021-04-01 | Equipment | 14906402 | 16023294 | 15200101
MCR014294 | HPR101 | 2021-04-01 | Subcontract | 85488134 | 91893502 | 105528698
MCR014295 | HPR101 | 2021-04-01 | Overhead | 19937384 | 21431232 | 21950409
MCR014296 | HPR101 | 2021-05-01 | Labor | 20342107 | 32129288 | 34286097
MCR014297 | HPR101 | 2021-05-01 | Material | 43278958 | 68356836 | 67269616
MCR014298 | HPR101 | 2021-05-01 | Equipment | 8713263 | 13762140 | 13937574
MCR014299 | HPR101 | 2021-05-01 | Subcontract | 49970514 | 78925797 | 98665218
MCR014300 | HPR101 | 2021-05-01 | Overhead | 11654031 | 18406928 | 23076067
MCR014301 | HPR101 | 2021-06-01 | Labor | 5721089 | 28064467 | 29800780
MCR014302 | HPR101 | 2021-06-01 | Material | 12171934 | 59708704 | 77166900
MCR014303 | HPR101 | 2021-06-01 | Equipment | 2450550 | 12021030 | 13084497
MCR014304 | HPR101 | 2021-06-01 | Subcontract | 14053892 | 68940538 | 90591877
MCR014305 | HPR101 | 2021-06-01 | Overhead | 3277623 | 16078184 | 21412055
MCR014306 | HPR101 | 2021-07-01 | Labor | 0 | 14464803 | 13854714
MCR014307 | HPR101 | 2021-07-01 | Material | 0 | 30774667 | 33454765
MCR014308 | HPR101 | 2021-07-01 | Equipment | 0 | 6195800 | 6763590
MCR014309 | HPR101 | 2021-07-01 | Subcontract | 0 | 35532878 | 56285175
MCR014310 | HPR101 | 2021-07-01 | Overhead | 0 | 8286912 | 21264206
MCR014311 | HPR101 | 2021-08-01 | Labor | 0 | 7996520 | 8343930
MCR014312 | HPR101 | 2021-08-01 | Material | 0 | 17013039 | 21562199
MCR014313 | HPR101 | 2021-08-01 | Equipment | 0 | 3425200 | 3834567
MCR014314 | HPR101 | 2021-08-01 | Subcontract | 0 | 19643502 | 44304648
MCR014315 | HPR101 | 2021-08-01 | Overhead | 0 | 4581221 | 21495935
MCR014316 | HPR101 | 2021-09-01 | Labor | 0 | 4244083 | 3871652
MCR014317 | HPR101 | 2021-09-01 | Material | 0 | 9029521 | 9874904
MCR014318 | HPR101 | 2021-09-01 | Equipment | 0 | 1817895 | 1727989
MCR014319 | HPR101 | 2021-09-01 | Subcontract | 0 | 10425616 | 21664786
MCR014320 | HPR101 | 2021-09-01 | Overhead | 0 | 2431443 | 20614802
MCR014321 | HPR102 | 2018-09-01 | Labor | 6831161 | 6184294 | 6898364
MCR014322 | HPR102 | 2018-09-01 | Material | 13106808 | 11865679 | 11700358
MCR014323 | HPR102 | 2018-09-01 | Equipment | 2057881 | 1863013 | 1695127
MCR014324 | HPR102 | 2018-09-01 | Subcontract | 12300034 | 11135301 | 11168320
MCR014325 | HPR102 | 2018-09-01 | Overhead | 2585308 | 2340496 | 16869957
MCR014326 | HPR102 | 2018-10-01 | Labor | 19484636 | 14224321 | 15750751
MCR014327 | HPR102 | 2018-10-01 | Material | 37384773 | 27291913 | 25989321
MCR014328 | HPR102 | 2018-10-01 | Equipment | 5869730 | 4285065 | 4461104
MCR014329 | HPR102 | 2018-10-01 | Subcontract | 35083596 | 25611991 | 27785644
MCR014330 | HPR102 | 2018-10-01 | Overhead | 7374118 | 5383309 | 17587336
MCR014331 | HPR102 | 2018-11-01 | Labor | 30647507 | 26911496 | 28655639
MCR014332 | HPR102 | 2018-11-01 | Material | 58802745 | 51634537 | 58604767
MCR014333 | HPR102 | 2018-11-01 | Equipment | 9232535 | 8107065 | 7870089
MCR014334 | HPR102 | 2018-11-01 | Subcontract | 55183210 | 48456232 | 43153740
MCR014335 | HPR102 | 2018-11-01 | Overhead | 11598796 | 10184872 | 16650194
MCR014336 | HPR102 | 2018-12-01 | Labor | 40351038 | 34438235 | 40376946
MCR014337 | HPR102 | 2018-12-01 | Material | 77420711 | 66075938 | 68934337
MCR014338 | HPR102 | 2018-12-01 | Equipment | 12155716 | 10374489 | 11012161
MCR014339 | HPR102 | 2018-12-01 | Subcontract | 72655168 | 62008709 | 69005048
MCR014340 | HPR102 | 2018-12-01 | Overhead | 15271175 | 13033428 | 17270976
MCR014341 | HPR102 | 2019-01-01 | Labor | 48627914 | 42750674 | 48315725
MCR014342 | HPR102 | 2019-01-01 | Material | 93301385 | 82024845 | 85373154
MCR014343 | HPR102 | 2019-01-01 | Equipment | 14649118 | 12878604 | 15569323
MCR014344 | HPR102 | 2019-01-01 | Subcontract | 87558326 | 76975900 | 69927632
MCR014345 | HPR102 | 2019-01-01 | Overhead | 18403626 | 16179337 | 16694255
MCR014346 | HPR102 | 2019-02-01 | Labor | 55512398 | 60213717 | 71608271
MCR014347 | HPR102 | 2019-02-01 | Material | 106510503 | 115530828 | 111671203
MCR014348 | HPR102 | 2019-02-01 | Equipment | 16723063 | 18139331 | 19059899
MCR014349 | HPR102 | 2019-02-01 | Subcontract | 99954372 | 108419460 | 117153056
MCR014350 | HPR102 | 2019-02-01 | Overhead | 21009114 | 22788366 | 17860973
MCR014351 | HPR102 | 2019-03-01 | Labor | 61040506 | 41693567 | 42813420
MCR014352 | HPR102 | 2019-03-01 | Material | 117117171 | 79996594 | 81062665
MCR014353 | HPR102 | 2019-03-01 | Equipment | 18388401 | 12560152 | 11577674
MCR014354 | HPR102 | 2019-03-01 | Subcontract | 109908158 | 75072496 | 74497531
MCR014355 | HPR102 | 2019-03-01 | Overhead | 23101271 | 15779266 | 16904803
MCR014356 | HPR102 | 2019-04-01 | Labor | 65250227 | 40040566 | 54815366
MCR014357 | HPR102 | 2019-04-01 | Material | 125194277 | 76825016 | 80519977
MCR014358 | HPR102 | 2019-04-01 | Equipment | 19656576 | 12062187 | 11965202
MCR014359 | HPR102 | 2019-04-01 | Subcontract | 117488087 | 72096141 | 73430569
MCR014360 | HPR102 | 2019-04-01 | Overhead | 24694474 | 15153675 | 16385289
MCR014361 | HPR102 | 2019-05-01 | Labor | 68181779 | 64352353 | 57178489
MCR014362 | HPR102 | 2019-05-01 | Material | 130818986 | 123471544 | 108216906
MCR014363 | HPR102 | 2019-05-01 | Equipment | 20539703 | 19386092 | 20978120
MCR014364 | HPR102 | 2019-05-01 | Subcontract | 122766574 | 115871395 | 128509199
MCR014365 | HPR102 | 2019-05-01 | Overhead | 25803944 | 24354667 | 16826237
MCR014366 | HPR102 | 2019-06-01 | Labor | 69877920 | 62149984 | 77978240
MCR014367 | HPR102 | 2019-06-01 | Material | 134073336 | 119245904 | 120744932
MCR014368 | HPR102 | 2019-06-01 | Equipment | 21050664 | 18722630 | 19539695
MCR014369 | HPR102 | 2019-06-01 | Subcontract | 125820606 | 111905859 | 118159176
MCR014370 | HPR102 | 2019-06-01 | Overhead | 26445862 | 23521162 | 16661245
MCR014371 | HPR102 | 2019-07-01 | Labor | 70384327 | 50519594 | 59847999
MCR014372 | HPR102 | 2019-07-01 | Material | 135044970 | 96930913 | 108182951
MCR014373 | HPR102 | 2019-07-01 | Equipment | 21203219 | 15218985 | 16015867
MCR014374 | HPR102 | 2019-07-01 | Subcontract | 126732432 | 90964442 | 94376922
MCR014375 | HPR102 | 2019-07-01 | Overhead | 26637516 | 19119548 | 16447947
MCR014376 | HPR102 | 2019-08-01 | Labor | 69750078 | 32510595 | 31267964
MCR014377 | HPR102 | 2019-08-01 | Material | 133828048 | 62377414 | 57930192
MCR014378 | HPR102 | 2019-08-01 | Equipment | 21012152 | 9793789 | 10326141
MCR014379 | HPR102 | 2019-08-01 | Subcontract | 125590416 | 58537844 | 53812703
MCR014380 | HPR102 | 2019-08-01 | Overhead | 26397479 | 12303897 | 17175527
MCR014381 | HPR102 | 2019-09-01 | Labor | 68028242 | 57871439 | 67598552
MCR014382 | HPR102 | 2019-09-01 | Material | 130524398 | 111036747 | 112320766
MCR014383 | HPR102 | 2019-09-01 | Equipment | 20493450 | 17433722 | 16766857
MCR014384 | HPR102 | 2019-09-01 | Subcontract | 122490118 | 104202008 | 103144017
MCR014385 | HPR102 | 2019-09-01 | Overhead | 25745836 | 21901912 | 17303991
MCR014386 | HPR102 | 2019-10-01 | Labor | 65276662 | 63084752 | 65796968
MCR014387 | HPR102 | 2019-10-01 | Material | 125244998 | 121039424 | 119128578
MCR014388 | HPR102 | 2019-10-01 | Equipment | 19664539 | 19004228 | 19284720
MCR014389 | HPR102 | 2019-10-01 | Subcontract | 117535686 | 113588981 | 122470579
MCR014390 | HPR102 | 2019-10-01 | Overhead | 24704479 | 23874933 | 14897138
MCR014391 | HPR102 | 2019-11-01 | Labor | 61558968 | 40471805 | 44792386
MCR014392 | HPR102 | 2019-11-01 | Material | 118111934 | 77652426 | 88348933
MCR014393 | HPR102 | 2019-11-01 | Equipment | 18544587 | 12192097 | 14806649
MCR014394 | HPR102 | 2019-11-01 | Subcontract | 110841689 | 72872620 | 78726011
MCR014395 | HPR102 | 2019-11-01 | Overhead | 23297488 | 15316881 | 16817090
MCR014396 | HPR102 | 2019-12-01 | Labor | 56945956 | 65905566 | 71832494
MCR014397 | HPR102 | 2019-12-01 | Material | 109261041 | 126451663 | 141969458
MCR014398 | HPR102 | 2019-12-01 | Equipment | 17154921 | 19853996 | 15941106
MCR014399 | HPR102 | 2019-12-01 | Subcontract | 102535603 | 118668076 | 105494877
MCR014400 | HPR102 | 2019-12-01 | Overhead | 21551656 | 24942493 | 17034893
MCR014401 | HPR102 | 2020-01-01 | Labor | 51517514 | 43929064 | 49987112
MCR014402 | HPR102 | 2020-01-01 | Material | 98845600 | 84285797 | 68445188
MCR014403 | HPR102 | 2020-01-01 | Equipment | 15519607 | 13233593 | 15790432
MCR014404 | HPR102 | 2020-01-01 | Subcontract | 92761273 | 79097682 | 79079093
MCR014405 | HPR102 | 2020-01-01 | Overhead | 19497218 | 16625308 | 17661069
MCR014406 | HPR102 | 2020-02-01 | Labor | 45365418 | 44478619 | 54472744
MCR014407 | HPR102 | 2020-02-01 | Material | 87041700 | 85340217 | 87137557
MCR014408 | HPR102 | 2020-02-01 | Equipment | 13666294 | 13399146 | 12957881
MCR014409 | HPR102 | 2020-02-01 | Subcontract | 81683948 | 80087198 | 89524309
MCR014410 | HPR102 | 2020-02-01 | Overhead | 17168908 | 16833292 | 17998406
MCR014411 | HPR102 | 2020-03-01 | Labor | 38597600 | 74843615 | 83177970
MCR014412 | HPR102 | 2020-03-01 | Material | 74056427 | 143600914 | 143822065
MCR014413 | HPR102 | 2020-03-01 | Equipment | 11627494 | 22546576 | 22794698
MCR014414 | HPR102 | 2020-03-01 | Subcontract | 69497969 | 134761725 | 134396003
MCR014415 | HPR102 | 2020-03-01 | Overhead | 14607573 | 28325169 | 18092971
MCR014416 | HPR102 | 2020-04-01 | Labor | 31345097 | 56188596 | 61031097
MCR014417 | HPR102 | 2020-04-01 | Material | 60141197 | 107807911 | 107691077
MCR014418 | HPR102 | 2020-04-01 | Equipment | 9442684 | 16926767 | 17494306
MCR014419 | HPR102 | 2020-04-01 | Subcontract | 56439275 | 101171919 | 103555660
MCR014420 | HPR102 | 2020-04-01 | Overhead | 11862805 | 21265027 | 16200467
MCR014421 | HPR102 | 2020-05-01 | Labor | 23774408 | 49406430 | 49406794
MCR014422 | HPR102 | 2020-05-01 | Material | 45615471 | 94795108 | 85702602
MCR014423 | HPR102 | 2020-05-01 | Equipment | 7162020 | 14883645 | 16522464
MCR014424 | HPR102 | 2020-05-01 | Subcontract | 42807663 | 88960104 | 93836423
MCR014425 | HPR102 | 2020-05-01 | Overhead | 8997616 | 18698262 | 17666400
MCR014426 | HPR102 | 2020-06-01 | Labor | 16112530 | 43669185 | 53369170
MCR014427 | HPR102 | 2020-06-01 | Material | 30914782 | 83787172 | 82328374
MCR014428 | HPR102 | 2020-06-01 | Equipment | 4853886 | 13155305 | 12045525
MCR014429 | HPR102 | 2020-06-01 | Subcontract | 29011858 | 78629749 | 73502621
MCR014430 | HPR102 | 2020-06-01 | Overhead | 6097917 | 16526955 | 17883739
MCR014431 | HPR102 | 2020-07-01 | Labor | 8709852 | 20511038 | 22450312
MCR014432 | HPR102 | 2020-07-01 | Material | 16711415 | 39354110 | 49657792
MCR014433 | HPR102 | 2020-07-01 | Equipment | 2623836 | 6178933 | 4907421
MCR014434 | HPR102 | 2020-07-01 | Subcontract | 15682763 | 36931713 | 38991968
MCR014435 | HPR102 | 2020-07-01 | Overhead | 3296314 | 7762568 | 14208799
MCR014436 | HPR102 | 2020-08-01 | Labor | 2305848 | 20059353 | 22246309
MCR014437 | HPR102 | 2020-08-01 | Material | 4424183 | 38487471 | 39863460
MCR014438 | HPR102 | 2020-08-01 | Equipment | 694635 | 6042863 | 6446270
MCR014439 | HPR102 | 2020-08-01 | Subcontract | 4151857 | 36118419 | 35121926
MCR014440 | HPR102 | 2020-08-01 | Overhead | 872667 | 7591624 | 16519470
MCR014441 | HPR102 | 2020-09-01 | Labor | 0 | 11616804 | 11808932
MCR014442 | HPR102 | 2020-09-01 | Material | 0 | 22288924 | 21368551
MCR014443 | HPR102 | 2020-09-01 | Equipment | 0 | 3499552 | 3307095
MCR014444 | HPR102 | 2020-09-01 | Subcontract | 0 | 20916955 | 20996026
MCR014445 | HPR102 | 2020-09-01 | Overhead | 0 | 4396473 | 16428487
MCR014446 | HPR102 | 2020-10-01 | Labor | 0 | 5435611 | 7155064
MCR014447 | HPR102 | 2020-10-01 | Material | 0 | 10429196 | 10907580
MCR014448 | HPR102 | 2020-10-01 | Equipment | 0 | 1637473 | 1945206
MCR014449 | HPR102 | 2020-10-01 | Subcontract | 0 | 9787239 | 10091489
MCR014450 | HPR102 | 2020-10-01 | Overhead | 0 | 2057151 | 18145202
MCR014451 | HPR102 | 2020-11-01 | Labor | 0 | 2016311 | 2441683
MCR014452 | HPR102 | 2020-11-01 | Material | 0 | 3868655 | 4011940
MCR014453 | HPR102 | 2020-11-01 | Equipment | 0 | 607412 | 575203
MCR014454 | HPR102 | 2020-11-01 | Subcontract | 0 | 3630524 | 2978701
MCR014455 | HPR102 | 2020-11-01 | Overhead | 0 | 763089 | 18796238
MCR014456 | HPR103 | 2018-12-01 | Labor | 15051279 | 10739844 | 10953226
MCR014457 | HPR103 | 2018-12-01 | Material | 29104154 | 20767276 | 19661883
MCR014458 | HPR103 | 2018-12-01 | Equipment | 7151109 | 5102676 | 5868811
MCR014459 | HPR103 | 2018-12-01 | Subcontract | 29299046 | 20906342 | 18609171
MCR014460 | HPR103 | 2018-12-01 | Overhead | 8050563 | 5744481 | 37389725
MCR014461 | HPR103 | 2019-01-01 | Labor | 41986747 | 24022708 | 24764549
MCR014462 | HPR103 | 2019-01-01 | Material | 81188366 | 46451905 | 45657109
MCR014463 | HPR103 | 2019-01-01 | Equipment | 19948591 | 11413582 | 11380499
MCR014464 | HPR103 | 2019-01-01 | Subcontract | 81732034 | 46762965 | 45367734
MCR014465 | HPR103 | 2019-01-01 | Overhead | 22457688 | 12849161 | 37446997
MCR014466 | HPR103 | 2019-02-01 | Labor | 64274810 | 48487642 | 47409837
MCR014467 | HPR103 | 2019-02-01 | Material | 124286047 | 93758928 | 98782735
MCR014468 | HPR103 | 2019-02-01 | Equipment | 30538015 | 23037273 | 24945811
MCR014469 | HPR103 | 2019-02-01 | Subcontract | 125118314 | 94386773 | 94586741
MCR014470 | HPR103 | 2019-02-01 | Overhead | 34379031 | 25934859 | 40036268
MCR014471 | HPR103 | 2019-03-01 | Labor | 82060174 | 70995760 | 70817687
MCR014472 | HPR103 | 2019-03-01 | Material | 158677008 | 137282123 | 137830474
MCR014473 | HPR103 | 2019-03-01 | Equipment | 38988132 | 33731248 | 34351762
MCR014474 | HPR103 | 2019-03-01 | Subcontract | 159739570 | 138201416 | 150901758
MCR014475 | HPR103 | 2019-03-01 | Overhead | 43891988 | 37973903 | 40056123
MCR014476 | HPR103 | 2019-04-01 | Labor | 95497525 | 99779077 | 94598622
MCR014477 | HPR103 | 2019-04-01 | Material | 184660364 | 192939459 | 176063794
MCR014478 | HPR103 | 2019-04-01 | Equipment | 45372438 | 47406674 | 52081808
MCR014479 | HPR103 | 2019-04-01 | Subcontract | 185896920 | 194231455 | 179464950
MCR014480 | HPR103 | 2019-04-01 | Overhead | 51079300 | 53369398 | 39949353
MCR014481 | HPR103 | 2019-05-01 | Labor | 104753226 | 61877604 | 72304484
MCR014482 | HPR103 | 2019-05-01 | Material | 202557804 | 119650650 | 133007738
MCR014483 | HPR103 | 2019-05-01 | Equipment | 49769973 | 29399063 | 27374439
MCR014484 | HPR103 | 2019-05-01 | Subcontract | 203914208 | 120451877 | 114814155
MCR014485 | HPR103 | 2019-05-01 | Overhead | 56029949 | 33096824 | 38592085
MCR014486 | HPR103 | 2019-06-01 | Labor | 110007480 | 107471802 | 101966231
MCR014487 | HPR103 | 2019-06-01 | Material | 212717779 | 207814622 | 218245708
MCR014488 | HPR103 | 2019-06-01 | Equipment | 52266355 | 51061613 | 50405491
MCR014489 | HPR103 | 2019-06-01 | Subcontract | 214142218 | 209206228 | 188935570
MCR014490 | HPR103 | 2019-06-01 | Overhead | 58840322 | 57484049 | 41246455
MCR014491 | HPR103 | 2019-07-01 | Labor | 111457168 | 68274985 | 76302951
MCR014492 | HPR103 | 2019-07-01 | Material | 215520991 | 132021050 | 128524509
MCR014493 | HPR103 | 2019-07-01 | Equipment | 52955126 | 32438563 | 35696096
MCR014494 | HPR103 | 2019-07-01 | Subcontract | 216964202 | 132905113 | 149142163
MCR014495 | HPR103 | 2019-07-01 | Overhead | 59615725 | 36518626 | 38957313
MCR014496 | HPR103 | 2019-08-01 | Labor | 109319656 | 93453136 | 85148654
MCR014497 | HPR103 | 2019-08-01 | Material | 211387757 | 180707198 | 196598073
MCR014498 | HPR103 | 2019-08-01 | Equipment | 51939559 | 44401115 | 41529603
MCR014499 | HPR103 | 2019-08-01 | Subcontract | 212803289 | 181917282 | 165738282
MCR014500 | HPR103 | 2019-08-01 | Overhead | 58472422 | 49985806 | 37068214
MCR014501 | HPR103 | 2019-09-01 | Labor | 103838085 | 106835002 | 102614813
MCR014502 | HPR103 | 2019-09-01 | Material | 200788227 | 206583264 | 206706101
MCR014503 | HPR103 | 2019-09-01 | Equipment | 49335175 | 50759059 | 47754911
MCR014504 | HPR103 | 2019-09-01 | Subcontract | 202132781 | 207966624 | 223681946
MCR014505 | HPR103 | 2019-09-01 | Overhead | 55540463 | 57143441 | 39885626
MCR014506 | HPR103 | 2019-10-01 | Labor | 95288985 | 90957719 | 79777508
MCR014507 | HPR103 | 2019-10-01 | Material | 184257117 | 175881895 | 181818446
MCR014508 | HPR103 | 2019-10-01 | Equipment | 45273357 | 43215502 | 41147949
MCR014509 | HPR103 | 2019-10-01 | Subcontract | 185490973 | 177059667 | 162472506
MCR014510 | HPR103 | 2019-10-01 | Overhead | 50967757 | 48651069 | 36783600
MCR014511 | HPR103 | 2019-11-01 | Labor | 83993805 | 56573395 | 64717455
MCR014512 | HPR103 | 2019-11-01 | Material | 162416006 | 109394079 | 108165401
MCR014513 | HPR103 | 2019-11-01 | Equipment | 39906832 | 26878947 | 30071944
MCR014514 | HPR103 | 2019-11-01 | Subcontract | 163503606 | 110126623 | 119883507
MCR014515 | HPR103 | 2019-11-01 | Overhead | 44926241 | 30259731 | 42871241
MCR014516 | HPR103 | 2019-12-01 | Labor | 70337527 | 82117591 | 110573189
MCR014517 | HPR103 | 2019-12-01 | Material | 136009320 | 158788034 | 175227322
MCR014518 | HPR103 | 2019-12-01 | Equipment | 33418511 | 39015412 | 44001476
MCR014519 | HPR103 | 2019-12-01 | Subcontract | 136920090 | 159851339 | 153000319
MCR014520 | HPR103 | 2019-12-01 | Overhead | 37621830 | 43922699 | 38824801
MCR014521 | HPR103 | 2020-01-01 | Labor | 54801450 | 79594183 | 131314054
MCR014522 | HPR103 | 2020-01-01 | Material | 105967728 | 153908605 | 218615732
MCR014523 | HPR103 | 2020-01-01 | Equipment | 26037066 | 37816500 | 33741742
MCR014524 | HPR103 | 2020-01-01 | Subcontract | 106677328 | 154939235 | 219036111
MCR014525 | HPR103 | 2020-01-01 | Overhead | 29311961 | 42572990 | 36983786
MCR014526 | HPR103 | 2020-02-01 | Labor | 38028885 | 58759299 | 51162722
MCR014527 | HPR103 | 2020-02-01 | Material | 73535181 | 113620888 | 115068419
MCR014528 | HPR103 | 2020-02-01 | Equipment | 18068146 | 27917505 | 26599222
MCR014529 | HPR103 | 2020-02-01 | Subcontract | 74027601 | 114381736 | 177120239
MCR014530 | HPR103 | 2020-02-01 | Overhead | 20340724 | 31428918 | 33960754
MCR014531 | HPR103 | 2020-03-01 | Labor | 20988261 | 62796595 | 66183259
MCR014532 | HPR103 | 2020-03-01 | Material | 40584298 | 121427673 | 131281853
MCR014533 | HPR103 | 2020-03-01 | Equipment | 9971867 | 29835691 | 33161470
MCR014534 | HPR103 | 2020-03-01 | Subcontract | 40856066 | 122240798 | 151496704
MCR014535 | HPR103 | 2020-03-01 | Overhead | 11226110 | 33588369 | 40438284
MCR014536 | HPR103 | 2020-04-01 | Labor | 5651048 | 28804234 | 25630787
MCR014537 | HPR103 | 2020-04-01 | Material | 10927243 | 55697783 | 44853482
MCR014538 | HPR103 | 2020-04-01 | Equipment | 2684906 | 13685363 | 13561854
MCR014539 | HPR103 | 2020-04-01 | Subcontract | 11000416 | 56070756 | 105017837
MCR014540 | HPR103 | 2020-04-01 | Overhead | 3022608 | 15406683 | 36149475
MCR014541 | HPR103 | 2020-05-01 | Labor | 0 | 32900740 | 29441926
MCR014542 | HPR103 | 2020-05-01 | Material | 0 | 63619060 | 63323243
MCR014543 | HPR103 | 2020-05-01 | Equipment | 0 | 15631681 | 13938449
MCR014544 | HPR103 | 2020-05-01 | Subcontract | 0 | 64045077 | 91359950
MCR014545 | HPR103 | 2020-05-01 | Overhead | 0 | 17597805 | 34457001
MCR014546 | HPR103 | 2020-06-01 | Labor | 0 | 13938629 | 12263351
MCR014547 | HPR103 | 2020-06-01 | Material | 0 | 26952660 | 31235830
MCR014548 | HPR103 | 2020-06-01 | Equipment | 0 | 6622471 | 8728748
MCR014549 | HPR103 | 2020-06-01 | Subcontract | 0 | 27133146 | 55352684
MCR014550 | HPR103 | 2020-06-01 | Overhead | 0 | 7455433 | 36462988
MCR014551 | HPR103 | 2020-07-01 | Labor | 0 | 7478842 | 8323365
MCR014552 | HPR103 | 2020-07-01 | Material | 0 | 14461586 | 15823110
MCR014553 | HPR103 | 2020-07-01 | Equipment | 0 | 3553320 | 3418277
MCR014554 | HPR103 | 2020-07-01 | Subcontract | 0 | 14558426 | 49389164
MCR014555 | HPR103 | 2020-07-01 | Overhead | 0 | 4000250 | 38606553
MCR014556 | HPR103 | 2020-08-01 | Labor | 0 | 1477324 | 823185
MCR014557 | HPR103 | 2020-08-01 | Material | 0 | 2856651 | 2031791
MCR014558 | HPR103 | 2020-08-01 | Equipment | 0 | 701901 | 1016982
MCR014559 | HPR103 | 2020-08-01 | Subcontract | 0 | 2875780 | 28864945
MCR014560 | HPR103 | 2020-08-01 | Overhead | 0 | 790184 | 39712948
MCR014561 | HPR104 | 2023-04-01 | Labor | 27898895 | 22840107 | 22588227
MCR014562 | HPR104 | 2023-04-01 | Material | 55935782 | 45793184 | 41192493
MCR014563 | HPR104 | 2023-04-01 | Equipment | 11662150 | 9547502 | 10672220
MCR014564 | HPR104 | 2023-04-01 | Subcontract | 60545086 | 49566702 | 49864658
MCR014565 | HPR104 | 2023-04-01 | Overhead | 14346347 | 11744985 | 40717511
MCR014566 | HPR104 | 2023-05-01 | Labor | 73492693 | 46463018 | 54255463
MCR014567 | HPR104 | 2023-05-01 | Material | 147348893 | 93155850 | 85408232
MCR014568 | HPR104 | 2023-05-01 | Equipment | 30721032 | 19422228 | 17677361
MCR014569 | HPR104 | 2023-05-01 | Subcontract | 159490955 | 100832217 | 99190206
MCR014570 | HPR104 | 2023-05-01 | Overhead | 37791880 | 23892509 | 45722273
MCR014571 | HPR104 | 2023-06-01 | Labor | 104386639 | 102230743 | 130983874
MCR014572 | HPR104 | 2023-06-01 | Material | 209289590 | 204967135 | 169007419
MCR014573 | HPR104 | 2023-06-01 | Equipment | 43635158 | 42733961 | 47905148
MCR014574 | HPR104 | 2023-06-01 | Subcontract | 226535782 | 221857142 | 269992069
MCR014575 | HPR104 | 2023-06-01 | Overhead | 53678362 | 52569743 | 44227211
MCR014576 | HPR104 | 2023-07-01 | Labor | 121469117 | 89095767 | 93367744
MCR014577 | HPR104 | 2023-07-01 | Material | 243539039 | 178632215 | 168552377
MCR014578 | HPR104 | 2023-07-01 | Equipment | 50775886 | 37243347 | 33869099
MCR014579 | HPR104 | 2023-07-01 | Subcontract | 263607505 | 193352132 | 169064885
MCR014580 | HPR104 | 2023-07-01 | Overhead | 62462622 | 45815392 | 39810214
MCR014581 | HPR104 | 2023-08-01 | Labor | 125756068 | 89460382 | 101036753
MCR014582 | HPR104 | 2023-08-01 | Material | 252134144 | 179363249 | 158516867
MCR014583 | HPR104 | 2023-08-01 | Equipment | 52567895 | 37395762 | 43104822
MCR014584 | HPR104 | 2023-08-01 | Subcontract | 272910876 | 194143406 | 201175109
MCR014585 | HPR104 | 2023-08-01 | Overhead | 64667085 | 46002887 | 40937762
MCR014586 | HPR104 | 2023-09-01 | Labor | 118440393 | 97529547 | 158386012
MCR014587 | HPR104 | 2023-09-01 | Material | 237466610 | 195541490 | 222597325
MCR014588 | HPR104 | 2023-09-01 | Equipment | 49509835 | 40768792 | 37695181
MCR014589 | HPR104 | 2023-09-01 | Subcontract | 257034687 | 211654791 | 177044083
MCR014590 | HPR104 | 2023-09-01 | Overhead | 60905173 | 50152264 | 39644652
MCR014591 | HPR104 | 2023-10-01 | Labor | 100977412 | 122052138 | 168687118
MCR014592 | HPR104 | 2023-10-01 | Material | 202454273 | 244707965 | 270157075
MCR014593 | HPR104 | 2023-10-01 | Equipment | 42210050 | 51019598 | 54986614
MCR014594 | HPR104 | 2023-10-01 | Subcontract | 219137211 | 264872755 | 289665303
MCR014595 | HPR104 | 2023-10-01 | Overhead | 51925247 | 62762427 | 41465752
MCR014596 | HPR104 | 2023-11-01 | Labor | 75252545 | 99130818 | 103039395
MCR014597 | HPR104 | 2023-11-01 | Material | 150877300 | 198751953 | 187402505
MCR014598 | HPR104 | 2023-11-01 | Equipment | 31456676 | 41438147 | 42242503
MCR014599 | HPR104 | 2023-11-01 | Subcontract | 163310116 | 215129807 | 221135934
MCR014600 | HPR104 | 2023-11-01 | Overhead | 38696842 | 50975680 | 40243788
MCR014601 | HPR104 | 2023-12-01 | Labor | 43987489 | 64680369 | 76793248
MCR014602 | HPR104 | 2023-12-01 | Material | 88192547 | 129680657 | 128949859
MCR014603 | HPR104 | 2023-12-01 | Equipment | 18387420 | 27037350 | 28736668
MCR014604 | HPR104 | 2023-12-01 | Subcontract | 95459920 | 140366795 | 186285815
MCR014605 | HPR104 | 2023-12-01 | Overhead | 22619526 | 33260351 | 40255459
MCR014606 | HPR104 | 2024-01-01 | Labor | 12371204 | 24995097 | 31597620
MCR014607 | HPR104 | 2024-01-01 | Material | 24803597 | 50113824 | 45185473
MCR014608 | HPR104 | 2024-01-01 | Equipment | 5171346 | 10448320 | 10783753
MCR014609 | HPR104 | 2024-01-01 | Subcontract | 26847500 | 54243377 | 102041912
MCR014610 | HPR104 | 2024-01-01 | Overhead | 6361599 | 12853138 | 39273443
MCR014611 | HPR104 | 2024-02-01 | Labor | 0 | 37880199 | 36767801
MCR014612 | HPR104 | 2024-02-01 | Material | 0 | 75947759 | 66869391
MCR014613 | HPR104 | 2024-02-01 | Equipment | 0 | 15834483 | 16331098
MCR014614 | HPR104 | 2024-02-01 | Subcontract | 0 | 82206119 | 108859872
MCR014615 | HPR104 | 2024-02-01 | Overhead | 0 | 19478997 | 41710561
MCR014616 | HPR104 | 2024-03-01 | Labor | 0 | 7674268 | 13013700
MCR014617 | HPR104 | 2024-03-01 | Material | 0 | 15386494 | 14362806
MCR014618 | HPR104 | 2024-03-01 | Equipment | 0 | 3207957 | 3869966
MCR014619 | HPR104 | 2024-03-01 | Subcontract | 0 | 16654395 | 64186846
MCR014620 | HPR104 | 2024-03-01 | Overhead | 0 | 3946311 | 40597033
MCR014621 | HPR105 | 2019-12-01 | Labor | 10690585 | 6848560 | 7750532
MCR014622 | HPR105 | 2019-12-01 | Material | 19249857 | 12331766 | 13417949
MCR014623 | HPR105 | 2019-12-01 | Equipment | 4871424 | 3120712 | 3142227
MCR014624 | HPR105 | 2019-12-01 | Subcontract | 19989132 | 12805357 | 14288843
MCR014625 | HPR105 | 2019-12-01 | Overhead | 5539986 | 3549003 | 20072743
MCR014626 | HPR105 | 2020-01-01 | Labor | 29101289 | 21535963 | 21913762
MCR014627 | HPR105 | 2020-01-01 | Material | 52400839 | 38778439 | 38232293
MCR014628 | HPR105 | 2020-01-01 | Equipment | 13260706 | 9813383 | 10611202
MCR014629 | HPR105 | 2020-01-01 | Subcontract | 54413251 | 40267694 | 41670032
MCR014630 | HPR105 | 2020-01-01 | Overhead | 15080627 | 11160187 | 20272955
MCR014631 | HPR105 | 2020-02-01 | Labor | 43186742 | 21766516 | 23410285
MCR014632 | HPR105 | 2020-02-01 | Material | 77763619 | 39193581 | 46019347
MCR014633 | HPR105 | 2020-02-01 | Equipment | 19679084 | 9918440 | 10017978
MCR014634 | HPR105 | 2020-02-01 | Subcontract | 80750067 | 40698778 | 37444968
MCR014635 | HPR105 | 2020-02-01 | Overhead | 22379873 | 11279662 | 20633426
MCR014636 | HPR105 | 2020-03-01 | Labor | 53133201 | 57307495 | 60698017
MCR014637 | HPR105 | 2020-03-01 | Material | 95673575 | 103189960 | 96718499
MCR014638 | HPR105 | 2020-03-01 | Equipment | 24211428 | 26113546 | 24426913
MCR014639 | HPR105 | 2020-03-01 | Subcontract | 99347840 | 107152886 | 101734116
MCR014640 | HPR105 | 2020-03-01 | Overhead | 27534244 | 29697412 | 18659572
MCR014641 | HPR105 | 2020-04-01 | Labor | 59145187 | 48622808 | 46995248
MCR014642 | HPR105 | 2020-04-01 | Material | 106498976 | 87551997 | 89871543
MCR014643 | HPR105 | 2020-04-01 | Equipment | 26950935 | 22156158 | 24862923
MCR014644 | HPR105 | 2020-04-01 | Subcontract | 110588983 | 90914360 | 99712414
MCR014645 | HPR105 | 2020-04-01 | Overhead | 30649725 | 25196906 | 18464393
MCR014646 | HPR105 | 2020-05-01 | Labor | 61450042 | 60627908 | 70135393
MCR014647 | HPR105 | 2020-05-01 | Material | 110649183 | 109168817 | 113387151
MCR014648 | HPR105 | 2020-05-01 | Equipment | 28001198 | 27626573 | 32122027
MCR014649 | HPR105 | 2020-05-01 | Subcontract | 114898574 | 113361357 | 107972570
MCR014650 | HPR105 | 2020-05-01 | Overhead | 31844128 | 31418089 | 20264344
MCR014651 | HPR105 | 2020-06-01 | Labor | 60304449 | 43873529 | 35326752
MCR014652 | HPR105 | 2020-06-01 | Material | 108586386 | 79000273 | 70496529
MCR014653 | HPR105 | 2020-06-01 | Equipment | 27479181 | 19992035 | 17158482
MCR014654 | HPR105 | 2020-06-01 | Subcontract | 112756558 | 82034214 | 79542111
MCR014655 | HPR105 | 2020-06-01 | Overhead | 31250469 | 22735774 | 19251572
MCR014656 | HPR105 | 2020-07-01 | Labor | 56004234 | 35926162 | 46854459
MCR014657 | HPR105 | 2020-07-01 | Material | 100843262 | 64689954 | 74929835
MCR014658 | HPR105 | 2020-07-01 | Equipment | 25519684 | 16370625 | 15843190
MCR014659 | HPR105 | 2020-07-01 | Subcontract | 104716065 | 67174319 | 69103934
MCR014660 | HPR105 | 2020-07-01 | Overhead | 29022047 | 18617356 | 21310637
MCR014661 | HPR105 | 2020-08-01 | Labor | 48900057 | 28740377 | 30194370
MCR014662 | HPR105 | 2020-08-01 | Material | 88051222 | 51750969 | 50260856
MCR014663 | HPR105 | 2020-08-01 | Equipment | 22282494 | 13096248 | 14735782
MCR014664 | HPR105 | 2020-08-01 | Subcontract | 91432758 | 53738422 | 57202538
MCR014665 | HPR105 | 2020-08-01 | Overhead | 25340580 | 14893598 | 20779483
MCR014666 | HPR105 | 2020-09-01 | Labor | 39424817 | 57461360 | 59243786
MCR014667 | HPR105 | 2020-09-01 | Material | 70989760 | 103467016 | 105888560
MCR014668 | HPR105 | 2020-09-01 | Equipment | 17964872 | 26183659 | 28007698
MCR014669 | HPR105 | 2020-09-01 | Subcontract | 73716064 | 107440582 | 98984847
MCR014670 | HPR105 | 2020-09-01 | Overhead | 20430400 | 29777146 | 19971272
MCR014671 | HPR105 | 2020-10-01 | Labor | 28148022 | 29628088 | 32979328
MCR014672 | HPR105 | 2020-10-01 | Material | 50684354 | 53349413 | 50054901
MCR014673 | HPR105 | 2020-10-01 | Equipment | 12826327 | 13500755 | 12275985
MCR014674 | HPR105 | 2020-10-01 | Subcontract | 52630845 | 55398254 | 68351884
MCR014675 | HPR105 | 2020-10-01 | Overhead | 14586633 | 15353621 | 22346194
MCR014676 | HPR105 | 2020-11-01 | Labor | 15909231 | 20568565 | 20196469
MCR014677 | HPR105 | 2020-11-01 | Material | 28646740 | 37036506 | 43449942
MCR014678 | HPR105 | 2020-11-01 | Equipment | 7249426 | 9372564 | 9041281
MCR014679 | HPR105 | 2020-11-01 | Subcontract | 29746894 | 38458863 | 57247531
MCR014680 | HPR105 | 2020-11-01 | Overhead | 8244349 | 10658870 | 20367702
MCR014681 | HPR105 | 2020-12-01 | Labor | 4363955 | 35870826 | 39729347
MCR014682 | HPR105 | 2020-12-01 | Material | 7857896 | 64590314 | 53475191
MCR014683 | HPR105 | 2020-12-01 | Equipment | 1988542 | 16345409 | 18512098
MCR014684 | HPR105 | 2020-12-01 | Subcontract | 8159672 | 67070852 | 70869469
MCR014685 | HPR105 | 2020-12-01 | Overhead | 2261452 | 18588680 | 21361216
MCR014686 | HPR105 | 2021-01-01 | Labor | 0 | 28960352 | 34249546
MCR014687 | HPR105 | 2021-01-01 | Material | 0 | 52147063 | 68622189
MCR014688 | HPR105 | 2021-01-01 | Equipment | 0 | 13196485 | 12751045
MCR014689 | HPR105 | 2021-01-01 | Subcontract | 0 | 54149728 | 79190380
MCR014690 | HPR105 | 2021-01-01 | Overhead | 0 | 15007592 | 21124606
MCR014691 | HPR105 | 2021-02-01 | Labor | 0 | 9689562 | 11259220
MCR014692 | HPR105 | 2021-02-01 | Material | 0 | 17447378 | 14471361
MCR014693 | HPR105 | 2021-02-01 | Equipment | 0 | 4415283 | 4778541
MCR014694 | HPR105 | 2021-02-01 | Subcontract | 0 | 18117430 | 38639466
MCR014695 | HPR105 | 2021-02-01 | Overhead | 0 | 5021244 | 20304317
MCR014696 | HPR105 | 2021-03-01 | Labor | 0 | 2333743 | 2231372
MCR014697 | HPR105 | 2021-03-01 | Material | 0 | 4202223 | 4509572
MCR014698 | HPR105 | 2021-03-01 | Equipment | 0 | 1063427 | 1191842
MCR014699 | HPR105 | 2021-03-01 | Subcontract | 0 | 4363606 | 27226684
MCR014700 | HPR105 | 2021-03-01 | Overhead | 0 | 1209373 | 19554219
MCR014701 | HPR106 | 2018-11-01 | Labor | 9819460 | 4618712 | 4782957
MCR014702 | HPR106 | 2018-11-01 | Material | 23824352 | 11206096 | 11979446
MCR014703 | HPR106 | 2018-11-01 | Equipment | 4270254 | 2008570 | 1797306
MCR014704 | HPR106 | 2018-11-01 | Subcontract | 41668368 | 19599263 | 18699662
MCR014705 | HPR106 | 2018-11-01 | Overhead | 8314159 | 3910673 | 35332377
MCR014706 | HPR106 | 2018-12-01 | Labor | 27106781 | 19672389 | 19878243
MCR014707 | HPR106 | 2018-12-01 | Material | 65767513 | 47729907 | 46304973
MCR014708 | HPR106 | 2018-12-01 | Equipment | 11788105 | 8555062 | 8181567
MCR014709 | HPR106 | 2018-12-01 | Subcontract | 115026210 | 83478757 | 85190046
MCR014710 | HPR106 | 2018-12-01 | Overhead | 22951370 | 16656655 | 36218243
MCR014711 | HPR106 | 2019-01-01 | Labor | 40954689 | 15742962 | 13980103
MCR014712 | HPR106 | 2019-01-01 | Material | 99365843 | 38196179 | 42860590
MCR014713 | HPR106 | 2019-01-01 | Equipment | 17810236 | 6846246 | 7341972
MCR014714 | HPR106 | 2019-01-01 | Subcontract | 173789089 | 66804437 | 62794905
MCR014715 | HPR106 | 2019-01-01 | Overhead | 34676425 | 13329600 | 36863374
MCR014716 | HPR106 | 2019-02-01 | Labor | 51487489 | 45228209 | 49758099
MCR014717 | HPR106 | 2019-02-01 | Material | 124920926 | 109734421 | 108032208
MCR014718 | HPR106 | 2019-02-01 | Equipment | 22390704 | 19668690 | 20322207
MCR014719 | HPR106 | 2019-02-01 | Subcontract | 218484476 | 191923549 | 204652554
MCR014720 | HPR106 | 2019-02-01 | Overhead | 43594570 | 38294824 | 33990800
MCR014721 | HPR106 | 2019-03-01 | Labor | 58839549 | 28390742 | 26688852
MCR014722 | HPR106 | 2019-03-01 | Material | 142758777 | 68882709 | 68260014
MCR014723 | HPR106 | 2019-03-01 | Equipment | 25587943 | 12346469 | 15134944
MCR014724 | HPR106 | 2019-03-01 | Subcontract | 249682559 | 120474632 | 126027119
MCR014725 | HPR106 | 2019-03-01 | Overhead | 49819575 | 24038503 | 33846679
MCR014726 | HPR106 | 2019-04-01 | Labor | 63157337 | 46242904 | 45467679
MCR014727 | HPR106 | 2019-04-01 | Material | 153234761 | 112196312 | 113489505
MCR014728 | HPR106 | 2019-04-01 | Equipment | 27465648 | 20109957 | 17713535
MCR014729 | HPR106 | 2019-04-01 | Subcontract | 268004868 | 196229351 | 193112217
MCR014730 | HPR106 | 2019-04-01 | Overhead | 53475456 | 39153968 | 33643614
MCR014731 | HPR106 | 2019-05-01 | Labor | 64602141 | 34050597 | 34305247
MCR014732 | HPR106 | 2019-05-01 | Material | 156740200 | 82614867 | 76398589
MCR014733 | HPR106 | 2019-05-01 | Equipment | 28093960 | 14807808 | 17732456
MCR014734 | HPR106 | 2019-05-01 | Subcontract | 274135818 | 144491932 | 163815106
MCR014735 | HPR106 | 2019-05-01 | Overhead | 54698774 | 28830715 | 35426630
MCR014736 | HPR106 | 2019-06-01 | Labor | 63353831 | 78469650 | 80211539
MCR014737 | HPR106 | 2019-06-01 | Material | 153711502 | 190386084 | 221504846
MCR014738 | HPR106 | 2019-06-01 | Equipment | 27551099 | 34124615 | 31058194
MCR014739 | HPR106 | 2019-06-01 | Subcontract | 268838679 | 332981870 | 323282972
MCR014740 | HPR106 | 2019-06-01 | Overhead | 53641827 | 66440425 | 33011621
MCR014741 | HPR106 | 2019-07-01 | Labor | 59616270 | 43996917 | 37827457
MCR014742 | HPR106 | 2019-07-01 | Material | 144643286 | 106747013 | 75951360
MCR014743 | HPR106 | 2019-07-01 | Equipment | 25925721 | 19133230 | 19562108
MCR014744 | HPR106 | 2019-07-01 | Subcontract | 252978532 | 186698624 | 201172473
MCR014745 | HPR106 | 2019-07-01 | Overhead | 50477226 | 37252286 | 36927080
MCR014746 | HPR106 | 2019-08-01 | Labor | 53625470 | 25597751 | 29303032
MCR014747 | HPR106 | 2019-08-01 | Material | 130108178 | 62106247 | 68255875
MCR014748 | HPR106 | 2019-08-01 | Equipment | 23320462 | 11131863 | 13350776
MCR014749 | HPR106 | 2019-08-01 | Subcontract | 227556886 | 108622720 | 122743642
MCR014750 | HPR106 | 2019-08-01 | Overhead | 45404803 | 21673671 | 35502335
MCR014751 | HPR106 | 2019-09-01 | Labor | 45662720 | 44406405 | 49800743
MCR014752 | HPR106 | 2019-09-01 | Material | 110788647 | 107740527 | 116675729
MCR014753 | HPR106 | 2019-09-01 | Equipment | 19857648 | 19311306 | 20799713
MCR014754 | HPR106 | 2019-09-01 | Subcontract | 193767371 | 188436263 | 173446486
MCR014755 | HPR106 | 2019-09-01 | Overhead | 38662725 | 37599000 | 36126061
MCR014756 | HPR106 | 2019-10-01 | Labor | 36077605 | 44640396 | 32340480
MCR014757 | HPR106 | 2019-10-01 | Material | 87532873 | 108308246 | 97667766
MCR014758 | HPR106 | 2019-10-01 | Equipment | 15689306 | 19413064 | 23397292
MCR014759 | HPR106 | 2019-10-01 | Subcontract | 153093436 | 189429193 | 205673896
MCR014760 | HPR106 | 2019-10-01 | Overhead | 30546987 | 37797121 | 32767171
MCR014761 | HPR106 | 2019-11-01 | Labor | 25333948 | 33506225 | 37984240
MCR014762 | HPR106 | 2019-11-01 | Material | 61466198 | 81294091 | 82595713
MCR014763 | HPR106 | 2019-11-01 | Equipment | 11017141 | 14571073 | 13349192
MCR014764 | HPR106 | 2019-11-01 | Subcontract | 107503285 | 142181918 | 141191468
MCR014765 | HPR106 | 2019-11-01 | Overhead | 21450309 | 28369794 | 33981738
MCR014766 | HPR106 | 2019-12-01 | Labor | 14123262 | 68050935 | 71262331
MCR014767 | HPR106 | 2019-12-01 | Material | 34266401 | 165107797 | 151182281
MCR014768 | HPR106 | 2019-12-01 | Equipment | 6141876 | 29593760 | 29982113
MCR014769 | HPR106 | 2019-12-01 | Subcontract | 59931326 | 288770596 | 291547839
MCR014770 | HPR106 | 2019-12-01 | Overhead | 11958197 | 57618876 | 36500596
MCR014771 | HPR106 | 2020-01-01 | Labor | 3833042 | 38662693 | 38088982
MCR014772 | HPR106 | 2020-01-01 | Material | 9299875 | 93804913 | 113372725
MCR014773 | HPR106 | 2020-01-01 | Equipment | 1666900 | 16813501 | 19129975
MCR014774 | HPR106 | 2020-01-01 | Subcontract | 16265316 | 164063122 | 188048407
MCR014775 | HPR106 | 2020-01-01 | Overhead | 3245445 | 32735787 | 35389538
MCR014776 | HPR106 | 2020-02-01 | Labor | 0 | 18088990 | 16279797
MCR014777 | HPR106 | 2020-02-01 | Material | 0 | 43888202 | 39180132
MCR014778 | HPR106 | 2020-02-01 | Equipment | 0 | 7866478 | 7105482
MCR014779 | HPR106 | 2020-02-01 | Subcontract | 0 | 76759684 | 77402779
MCR014780 | HPR106 | 2020-02-01 | Overhead | 0 | 15315987 | 33661685
MCR014781 | HPR106 | 2020-03-01 | Labor | 0 | 11363579 | 12588599
MCR014782 | HPR106 | 2020-03-01 | Material | 0 | 27570752 | 29887354
MCR014783 | HPR106 | 2020-03-01 | Equipment | 0 | 4941754 | 4372547
MCR014784 | HPR106 | 2020-03-01 | Subcontract | 0 | 48220754 | 44457283
MCR014785 | HPR106 | 2020-03-01 | Overhead | 0 | 9621567 | 38544039
MCR014786 | HPR106 | 2020-04-01 | Labor | 0 | 13807489 | 13029322
MCR014787 | HPR106 | 2020-04-01 | Material | 0 | 33500262 | 37507528
MCR014788 | HPR106 | 2020-04-01 | Equipment | 0 | 6004554 | 7665220
MCR014789 | HPR106 | 2020-04-01 | Subcontract | 0 | 58591362 | 64296630
MCR014790 | HPR106 | 2020-04-01 | Overhead | 0 | 11690832 | 33920096
MCR014791 | HPR106 | 2020-05-01 | Labor | 0 | 3056051 | 3112929
MCR014792 | HPR106 | 2020-05-01 | Material | 0 | 7414709 | 5502511
MCR014793 | HPR106 | 2020-05-01 | Equipment | 0 | 1329005 | 1253580
MCR014794 | HPR106 | 2020-05-01 | Subcontract | 0 | 12968194 | 13502395
MCR014795 | HPR106 | 2020-05-01 | Overhead | 0 | 2587565 | 33931877
MCR014796 | HPR107 | 2023-05-01 | Labor | 2088391 | 1275863 | 1407434
MCR014797 | HPR107 | 2023-05-01 | Material | 5936847 | 3627003 | 3658608
MCR014798 | HPR107 | 2023-05-01 | Equipment | 1586897 | 969484 | 873727
MCR014799 | HPR107 | 2023-05-01 | Subcontract | 5783906 | 3533566 | 3500844
MCR014800 | HPR107 | 2023-05-01 | Overhead | 1376060 | 840678 | 9863853
MCR014801 | HPR107 | 2023-06-01 | Labor | 5980967 | 4353891 | 5225987
MCR014802 | HPR107 | 2023-06-01 | Material | 17002600 | 12377175 | 10269444
MCR014803 | HPR107 | 2023-06-01 | Equipment | 4544731 | 3308372 | 3349026
MCR014804 | HPR107 | 2023-06-01 | Subcontract | 16564592 | 12058323 | 13289162
MCR014805 | HPR107 | 2023-06-01 | Overhead | 3940914 | 2868819 | 9928318
MCR014806 | HPR107 | 2023-07-01 | Labor | 9453095 | 8966831 | 9009233
MCR014807 | HPR107 | 2023-07-01 | Material | 26873113 | 25490769 | 27139819
MCR014808 | HPR107 | 2023-07-01 | Equipment | 7183081 | 6813586 | 7234595
MCR014809 | HPR107 | 2023-07-01 | Subcontract | 26180827 | 24834094 | 18450297
MCR014810 | HPR107 | 2023-07-01 | Overhead | 6228731 | 5908327 | 10025544
MCR014811 | HPR107 | 2023-08-01 | Labor | 12512843 | 6049078 | 7778268
MCR014812 | HPR107 | 2023-08-01 | Material | 35571316 | 17196226 | 18083108
MCR014813 | HPR107 | 2023-08-01 | Equipment | 9508078 | 4596486 | 4119995
MCR014814 | HPR107 | 2023-08-01 | Subcontract | 34654953 | 16753229 | 23954249
MCR014815 | HPR107 | 2023-08-01 | Overhead | 8244827 | 3985793 | 9162493
MCR014816 | HPR107 | 2023-09-01 | Labor | 15168610 | 10132499 | 12079119
MCR014817 | HPR107 | 2023-09-01 | Material | 43121091 | 28804511 | 28107524
MCR014818 | HPR107 | 2023-09-01 | Equipment | 11526104 | 7699336 | 6801137
MCR014819 | HPR107 | 2023-09-01 | Subcontract | 42010237 | 28062470 | 27067082
MCR014820 | HPR107 | 2023-09-01 | Overhead | 9994737 | 6676397 | 8996706
MCR014821 | HPR107 | 2023-10-01 | Labor | 17429165 | 15161743 | 17613698
MCR014822 | HPR107 | 2023-10-01 | Material | 49547363 | 43101569 | 50159518
MCR014823 | HPR107 | 2023-10-01 | Equipment | 13243822 | 11520886 | 12612516
MCR014824 | HPR107 | 2023-10-01 | Subcontract | 48270959 | 41991217 | 41683738
MCR014825 | HPR107 | 2023-10-01 | Overhead | 11484238 | 9990212 | 9788832
MCR014826 | HPR107 | 2023-11-01 | Labor | 19303681 | 12082461 | 12375658
MCR014827 | HPR107 | 2023-11-01 | Material | 54876207 | 34347834 | 29157590
MCR014828 | HPR107 | 2023-11-01 | Equipment | 14668202 | 9181046 | 7646678
MCR014829 | HPR107 | 2023-11-01 | Subcontract | 53462525 | 33462990 | 36106577
MCR014830 | HPR107 | 2023-11-01 | Overhead | 12719373 | 7961245 | 10012560
MCR014831 | HPR107 | 2023-12-01 | Labor | 20801779 | 21562749 | 25318110
MCR014832 | HPR107 | 2023-12-01 | Material | 59134977 | 61298251 | 65777715
MCR014833 | HPR107 | 2023-12-01 | Equipment | 15806555 | 16384790 | 18764865
MCR014834 | HPR107 | 2023-12-01 | Subcontract | 57611584 | 59719130 | 61637937
MCR014835 | HPR107 | 2023-12-01 | Overhead | 13706484 | 14207894 | 9600177
MCR014836 | HPR107 | 2024-01-01 | Labor | 21933584 | 15496894 | 19201845
MCR014837 | HPR107 | 2024-01-01 | Material | 62352454 | 44054331 | 47073695
MCR014838 | HPR107 | 2024-01-01 | Equipment | 16666574 | 11775555 | 9571627
MCR014839 | HPR107 | 2024-01-01 | Subcontract | 60746175 | 42919435 | 44391418
MCR014840 | HPR107 | 2024-01-01 | Overhead | 14452240 | 10211046 | 9520289
MCR014841 | HPR107 | 2024-02-01 | Labor | 22709783 | 20951575 | 21555972
MCR014842 | HPR107 | 2024-02-01 | Material | 64559020 | 59560815 | 55088583
MCR014843 | HPR107 | 2024-02-01 | Equipment | 17256381 | 15920380 | 16321116
MCR014844 | HPR107 | 2024-02-01 | Subcontract | 62895897 | 58026453 | 52739050
MCR014845 | HPR107 | 2024-02-01 | Overhead | 14963685 | 13805186 | 11084552
MCR014846 | HPR107 | 2024-03-01 | Labor | 23141701 | 32461356 | 40535213
MCR014847 | HPR107 | 2024-03-01 | Material | 65786871 | 92280642 | 85046479
MCR014848 | HPR107 | 2024-03-01 | Equipment | 17584581 | 24666265 | 27291075
MCR014849 | HPR107 | 2024-03-01 | Subcontract | 64092117 | 89903375 | 98982285
MCR014850 | HPR107 | 2024-03-01 | Overhead | 15248280 | 21389086 | 9579161
MCR014851 | HPR107 | 2024-04-01 | Labor | 23241393 | 19726963 | 20002848
MCR014852 | HPR107 | 2024-04-01 | Material | 66070273 | 56079506 | 73494413
MCR014853 | HPR107 | 2024-04-01 | Equipment | 17660333 | 14989839 | 16473061
MCR014854 | HPR107 | 2024-04-01 | Subcontract | 64368218 | 54634827 | 50630760
MCR014855 | HPR107 | 2024-04-01 | Overhead | 15313968 | 12998278 | 10445366
MCR014856 | HPR107 | 2024-05-01 | Labor | 23021750 | 24463371 | 25980199
MCR014857 | HPR107 | 2024-05-01 | Material | 65445875 | 69544095 | 73126372
MCR014858 | HPR107 | 2024-05-01 | Equipment | 17493434 | 18588873 | 15937363
MCR014859 | HPR107 | 2024-05-01 | Subcontract | 63759905 | 67752550 | 66752105
MCR014860 | HPR107 | 2024-05-01 | Overhead | 15169243 | 16119141 | 9505205
MCR014861 | HPR107 | 2024-06-01 | Labor | 22496639 | 19918327 | 24757967
MCR014862 | HPR107 | 2024-06-01 | Material | 63953100 | 56623514 | 48056746
MCR014863 | HPR107 | 2024-06-01 | Equipment | 17094421 | 15135250 | 17494268
MCR014864 | HPR107 | 2024-06-01 | Subcontract | 62305586 | 55164820 | 64960631
MCR014865 | HPR107 | 2024-06-01 | Overhead | 14823243 | 13124369 | 9523826
MCR014866 | HPR107 | 2024-07-01 | Labor | 21681080 | 14294852 | 14525734
MCR014867 | HPR107 | 2024-07-01 | Material | 61634640 | 40637184 | 38403788
MCR014868 | HPR107 | 2024-07-01 | Equipment | 16474705 | 10862165 | 9061492
MCR014869 | HPR107 | 2024-07-01 | Subcontract | 60046853 | 39590318 | 39654806
MCR014870 | HPR107 | 2024-07-01 | Overhead | 14285863 | 9419009 | 9669446
MCR014871 | HPR107 | 2024-08-01 | Labor | 20591464 | 11675004 | 15870641
MCR014872 | HPR107 | 2024-08-01 | Material | 58537097 | 33189522 | 37663060
MCR014873 | HPR107 | 2024-08-01 | Equipment | 15646744 | 8871433 | 8931038
MCR014874 | HPR107 | 2024-08-01 | Subcontract | 57029106 | 32334518 | 36274490
MCR014875 | HPR107 | 2024-08-01 | Overhead | 13567905 | 7692768 | 9122581
MCR014876 | HPR107 | 2024-09-01 | Labor | 19245855 | 14450107 | 14363971
MCR014877 | HPR107 | 2024-09-01 | Material | 54711819 | 41078540 | 43176831
MCR014878 | HPR107 | 2024-09-01 | Equipment | 14624261 | 10980138 | 10981896
MCR014879 | HPR107 | 2024-09-01 | Subcontract | 53302373 | 40020305 | 40413132
MCR014880 | HPR107 | 2024-09-01 | Overhead | 12681271 | 9521308 | 10617709
MCR014881 | HPR107 | 2024-10-01 | Labor | 17664387 | 29433830 | 38412937
MCR014882 | HPR107 | 2024-10-01 | Material | 50216048 | 83674038 | 82055328
MCR014883 | HPR107 | 2024-10-01 | Equipment | 13422559 | 22365753 | 23181353
MCR014884 | HPR107 | 2024-10-01 | Subcontract | 48922418 | 81518488 | 82669623
MCR014885 | HPR107 | 2024-10-01 | Overhead | 11639227 | 19394222 | 9886376
MCR014886 | HPR107 | 2024-11-01 | Labor | 15869831 | 17416848 | 18115930
MCR014887 | HPR107 | 2024-11-01 | Material | 45114511 | 49512347 | 44831208
MCR014888 | HPR107 | 2024-11-01 | Equipment | 12058938 | 13234462 | 14315698
MCR014889 | HPR107 | 2024-11-01 | Subcontract | 43952304 | 48236846 | 47627902
MCR014890 | HPR107 | 2024-11-01 | Overhead | 10456778 | 11476122 | 9674040
MCR014891 | HPR107 | 2024-12-01 | Labor | 13888407 | 13158856 | 16956884
MCR014892 | HPR107 | 2024-12-01 | Material | 39481749 | 37407793 | 44377387
MCR014893 | HPR107 | 2024-12-01 | Equipment | 10553321 | 9998961 | 9825504
MCR014894 | HPR107 | 2024-12-01 | Subcontract | 38464648 | 36444121 | 36127332
MCR014895 | HPR107 | 2024-12-01 | Overhead | 9151199 | 8670491 | 9755772
MCR014896 | HPR107 | 2025-01-01 | Labor | 11751034 | 15556177 | 19618120
MCR014897 | HPR107 | 2025-01-01 | Material | 33405658 | 44222859 | 48291148
MCR014898 | HPR107 | 2025-01-01 | Equipment | 8929205 | 11820602 | 12428654
MCR014899 | HPR107 | 2025-01-01 | Subcontract | 32545085 | 43083622 | 40500582
MCR014900 | HPR107 | 2025-01-01 | Overhead | 7742864 | 10250108 | 9946904
MCR014901 | HPR107 | 2025-02-01 | Labor | 9495369 | 12646773 | 13070945
MCR014902 | HPR107 | 2025-02-01 | Material | 26993289 | 35952050 | 36126665
MCR014903 | HPR107 | 2025-02-01 | Equipment | 7215204 | 9609847 | 8757627
MCR014904 | HPR107 | 2025-02-01 | Subcontract | 26297908 | 35025880 | 33114345
MCR014905 | HPR107 | 2025-02-01 | Overhead | 6256586 | 8333075 | 10629889
MCR014906 | HPR107 | 2025-03-01 | Labor | 7169439 | 10995341 | 13428102
MCR014907 | HPR107 | 2025-03-01 | Material | 20381169 | 31257386 | 33515858
MCR014908 | HPR107 | 2025-03-01 | Equipment | 5447809 | 8354981 | 9992199
MCR014909 | HPR107 | 2025-03-01 | Subcontract | 19856124 | 30452156 | 37292915
MCR014910 | HPR107 | 2025-03-01 | Overhead | 4724009 | 7244932 | 9640200
MCR014911 | HPR107 | 2025-04-01 | Labor | 4839005 | 11776278 | 13734244
MCR014912 | HPR107 | 2025-04-01 | Material | 13756247 | 33477421 | 32984562
MCR014913 | HPR107 | 2025-04-01 | Equipment | 3676993 | 8948388 | 7510602
MCR014914 | HPR107 | 2025-04-01 | Subcontract | 13401869 | 32615000 | 32252487
MCR014915 | HPR107 | 2025-04-01 | Overhead | 3188465 | 7759498 | 10298600
MCR014916 | HPR107 | 2025-05-01 | Labor | 2606129 | 4834089 | 4197579
MCR014917 | HPR107 | 2025-05-01 | Material | 7408663 | 13742273 | 14767975
MCR014918 | HPR107 | 2025-05-01 | Equipment | 1980308 | 3673258 | 3924698
MCR014919 | HPR107 | 2025-05-01 | Subcontract | 7217807 | 13388255 | 13716019
MCR014920 | HPR107 | 2025-05-01 | Overhead | 1717202 | 3185226 | 8744146
MCR014921 | HPR107 | 2025-06-01 | Labor | 687827 | 6828594 | 9124203
MCR014922 | HPR107 | 2025-06-01 | Material | 1955344 | 19412221 | 19985829
MCR014923 | HPR107 | 2025-06-01 | Equipment | 522656 | 5188813 | 5982577
MCR014924 | HPR107 | 2025-06-01 | Subcontract | 1904972 | 18912137 | 14849276
MCR014925 | HPR107 | 2025-06-01 | Overhead | 453216 | 4499423 | 9478733
MCR014926 | HPR107 | 2025-07-01 | Labor | 0 | 3182725 | 3126480
MCR014927 | HPR107 | 2025-07-01 | Material | 0 | 9047803 | 7795470
MCR014928 | HPR107 | 2025-07-01 | Equipment | 0 | 2418443 | 2152548
MCR014929 | HPR107 | 2025-07-01 | Subcontract | 0 | 8814720 | 9527181
MCR014930 | HPR107 | 2025-07-01 | Overhead | 0 | 2097127 | 9407041
MCR014931 | HPR107 | 2025-08-01 | Labor | 0 | 3620202 | 4549680
MCR014932 | HPR107 | 2025-08-01 | Material | 0 | 10291455 | 9377186
MCR014933 | HPR107 | 2025-08-01 | Equipment | 0 | 2750867 | 2682291
MCR014934 | HPR107 | 2025-08-01 | Subcontract | 0 | 10026334 | 11221566
MCR014935 | HPR107 | 2025-08-01 | Overhead | 0 | 2385385 | 9453015
MCR014936 | HPR107 | 2025-09-01 | Labor | 0 | 1751347 | 1846776
MCR014937 | HPR107 | 2025-09-01 | Material | 0 | 4978703 | 5984869
MCR014938 | HPR107 | 2025-09-01 | Equipment | 0 | 1330788 | 1330138
MCR014939 | HPR107 | 2025-09-01 | Subcontract | 0 | 4850445 | 4700972
MCR014940 | HPR107 | 2025-09-01 | Overhead | 0 | 1153979 | 9677707
MCR014941 | HPR107 | 2025-10-01 | Labor | 0 | 548582 | 597887
MCR014942 | HPR107 | 2025-10-01 | Material | 0 | 1559501 | 1391633
MCR014943 | HPR107 | 2025-10-01 | Equipment | 0 | 416849 | 450585
MCR014944 | HPR107 | 2025-10-01 | Subcontract | 0 | 1519326 | 1596816
MCR014945 | HPR107 | 2025-10-01 | Overhead | 0 | 361466 | 9893812
MCR014946 | HPR108 | 2020-06-01 | Labor | 2436187 | 1048378 | 1099712
MCR014947 | HPR108 | 2020-06-01 | Material | 4933322 | 2122985 | 2312210
MCR014948 | HPR108 | 2020-06-01 | Equipment | 1073393 | 461919 | 448808
MCR014949 | HPR108 | 2020-06-01 | Subcontract | 8504418 | 3659755 | 4152041
MCR014950 | HPR108 | 2020-06-01 | Overhead | 1464969 | 630428 | 7995292
MCR014951 | HPR108 | 2020-07-01 | Labor | 6896067 | 3049833 | 3575356
MCR014952 | HPR108 | 2020-07-01 | Material | 13964660 | 6175966 | 5842642
MCR014953 | HPR108 | 2020-07-01 | Equipment | 3038432 | 1343767 | 1450956
MCR014954 | HPR108 | 2020-07-01 | Subcontract | 24073293 | 10646578 | 9987023
MCR014955 | HPR108 | 2020-07-01 | Overhead | 4146859 | 1833977 | 8834540
MCR014956 | HPR108 | 2020-08-01 | Labor | 10747897 | 6327381 | 6908580
MCR014957 | HPR108 | 2020-08-01 | Material | 21764686 | 12813061 | 11700929
MCR014958 | HPR108 | 2020-08-01 | Equipment | 4735563 | 2787867 | 3303538
MCR014959 | HPR108 | 2020-08-01 | Subcontract | 37519545 | 22088083 | 27311503
MCR014960 | HPR108 | 2020-08-01 | Overhead | 6463107 | 3804887 | 7872753
MCR014961 | HPR108 | 2020-09-01 | Labor | 14006506 | 10643801 | 11577936
MCR014962 | HPR108 | 2020-09-01 | Material | 28363428 | 21553890 | 23532862
MCR014963 | HPR108 | 2020-09-01 | Equipment | 6171317 | 4689698 | 4969278
MCR014964 | HPR108 | 2020-09-01 | Subcontract | 48894935 | 37156160 | 34677412
MCR014965 | HPR108 | 2020-09-01 | Overhead | 8422628 | 6400510 | 8435436
MCR014966 | HPR108 | 2020-10-01 | Labor | 16687510 | 14491040 | 15148764
MCR014967 | HPR108 | 2020-10-01 | Material | 33792509 | 29344619 | 29413760
MCR014968 | HPR108 | 2020-10-01 | Equipment | 7352577 | 6384805 | 6877923
MCR014969 | HPR108 | 2020-10-01 | Subcontract | 58253978 | 50586383 | 55422448
MCR014970 | HPR108 | 2020-10-01 | Overhead | 10034815 | 8713997 | 8291308
MCR014971 | HPR108 | 2020-11-01 | Labor | 18807415 | 8573158 | 9314672
MCR014972 | HPR108 | 2020-11-01 | Material | 38085356 | 17360800 | 15603371
MCR014973 | HPR108 | 2020-11-01 | Equipment | 8286615 | 3777365 | 3471830
MCR014974 | HPR108 | 2020-11-01 | Subcontract | 65654299 | 29927806 | 33813741
MCR014975 | HPR108 | 2020-11-01 | Overhead | 11309592 | 5155356 | 8687130
MCR014976 | HPR108 | 2020-12-01 | Labor | 20383743 | 10089087 | 12736280
MCR014977 | HPR108 | 2020-12-01 | Material | 41277448 | 20430583 | 23932390
MCR014978 | HPR108 | 2020-12-01 | Equipment | 8981151 | 4445288 | 4034775
MCR014979 | HPR108 | 2020-12-01 | Subcontract | 71157059 | 35219722 | 38280375
MCR014980 | HPR108 | 2020-12-01 | Overhead | 12257496 | 6066940 | 8175367
MCR014981 | HPR108 | 2021-01-01 | Labor | 21435175 | 17421731 | 16997188
MCR014982 | HPR108 | 2021-01-01 | Material | 43406618 | 35279320 | 33453638
MCR014983 | HPR108 | 2021-01-01 | Equipment | 9444416 | 7676078 | 7709398
MCR014984 | HPR108 | 2021-01-01 | Subcontract | 74827477 | 60817051 | 63831161
MCR014985 | HPR108 | 2021-01-01 | Overhead | 12889761 | 10476329 | 8361865
MCR014986 | HPR108 | 2021-02-01 | Labor | 21981745 | 16245181 | 17845692
MCR014987 | HPR108 | 2021-02-01 | Material | 44513431 | 32896786 | 37103485
MCR014988 | HPR108 | 2021-02-01 | Equipment | 9685237 | 7157686 | 7351640
MCR014989 | HPR108 | 2021-02-01 | Subcontract | 76735482 | 56709866 | 53608855
MCR014990 | HPR108 | 2021-02-01 | Overhead | 13218433 | 9768826 | 8954505
MCR014991 | HPR108 | 2021-03-01 | Labor | 22045066 | 18327493 | 18499874
MCR014992 | HPR108 | 2021-03-01 | Material | 44641657 | 37113504 | 37932097
MCR014993 | HPR108 | 2021-03-01 | Equipment | 9713136 | 8075160 | 9374188
MCR014994 | HPR108 | 2021-03-01 | Subcontract | 76956526 | 63978951 | 66046461
MCR014995 | HPR108 | 2021-03-01 | Overhead | 13256511 | 11020997 | 8829279
MCR014996 | HPR108 | 2021-04-01 | Labor | 21648637 | 19644659 | 22068118
MCR014997 | HPR108 | 2021-04-01 | Material | 43838882 | 39780790 | 39329181
MCR014998 | HPR108 | 2021-04-01 | Equipment | 9538468 | 8655508 | 7849469
MCR014999 | HPR108 | 2021-04-01 | Subcontract | 75572644 | 68577011 | 81896156
MCR015000 | HPR108 | 2021-04-01 | Overhead | 13018123 | 11813057 | 8477620
MCR015001 | HPR108 | 2021-05-01 | Labor | 20818239 | 22629056 | 24426972
MCR015002 | HPR108 | 2021-05-01 | Material | 42157311 | 45824247 | 56005492
MCR015003 | HPR108 | 2021-05-01 | Equipment | 9172592 | 9970444 | 10143697
MCR015004 | HPR108 | 2021-05-01 | Subcontract | 72673831 | 78995162 | 78838670
MCR015005 | HPR108 | 2021-05-01 | Overhead | 12518775 | 13607685 | 8553851
MCR015006 | HPR108 | 2021-06-01 | Labor | 19582468 | 14213587 | 17839365
MCR015007 | HPR108 | 2021-06-01 | Material | 39654852 | 28782771 | 32599997
MCR015008 | HPR108 | 2021-06-01 | Equipment | 8628107 | 6262558 | 6919506
MCR015009 | HPR108 | 2021-06-01 | Subcontract | 68359911 | 49617828 | 49616301
MCR015010 | HPR108 | 2021-06-01 | Overhead | 11775660 | 8547154 | 8769151
MCR015011 | HPR108 | 2021-07-01 | Labor | 17973480 | 13210361 | 12823792
MCR015012 | HPR108 | 2021-07-01 | Material | 36396622 | 26751220 | 27591525
MCR015013 | HPR108 | 2021-07-01 | Equipment | 7919181 | 5820533 | 5287938
MCR015014 | HPR108 | 2021-07-01 | Subcontract | 62743137 | 46115694 | 55764599
MCR015015 | HPR108 | 2021-07-01 | Overhead | 10808116 | 7943877 | 8021553
MCR015016 | HPR108 | 2021-08-01 | Labor | 16028070 | 23140736 | 23470449
MCR015017 | HPR108 | 2021-08-01 | Material | 32457132 | 46860409 | 53935181
MCR015018 | HPR108 | 2021-08-01 | Equipment | 7062026 | 10195893 | 10670505
MCR015019 | HPR108 | 2021-08-01 | Subcontract | 55951959 | 80781373 | 88695274
MCR015020 | HPR108 | 2021-08-01 | Overhead | 9638269 | 13915378 | 8867472
MCR015021 | HPR108 | 2021-09-01 | Labor | 13789316 | 26178921 | 31344623
MCR015022 | HPR108 | 2021-09-01 | Material | 27923614 | 53012789 | 61749513
MCR015023 | HPR108 | 2021-09-01 | Equipment | 6075623 | 11534528 | 13532522
MCR015024 | HPR108 | 2021-09-01 | Subcontract | 48136752 | 91387291 | 91982197
MCR015025 | HPR108 | 2021-09-01 | Overhead | 8292024 | 15742350 | 8201780
MCR015026 | HPR108 | 2021-10-01 | Labor | 11309240 | 15772019 | 17774476
MCR015027 | HPR108 | 2021-10-01 | Material | 22901416 | 31938625 | 38286056
MCR015028 | HPR108 | 2021-10-01 | Equipment | 4982892 | 6949209 | 5958550
MCR015029 | HPR108 | 2021-10-01 | Subcontract | 39479122 | 55058118 | 63311898
MCR015030 | HPR108 | 2021-10-01 | Overhead | 6800663 | 9484297 | 8573115
MCR015031 | HPR108 | 2021-11-01 | Labor | 8653534 | 9838010 | 10775932
MCR015032 | HPR108 | 2021-11-01 | Material | 17523562 | 19922148 | 26980894
MCR015033 | HPR108 | 2021-11-01 | Equipment | 3812778 | 4334663 | 4427820
MCR015034 | HPR108 | 2021-11-01 | Subcontract | 30208388 | 34343245 | 35168217
MCR015035 | HPR108 | 2021-11-01 | Overhead | 5203689 | 5915958 | 7834522
MCR015036 | HPR108 | 2021-12-01 | Labor | 5911085 | 8009739 | 10509321
MCR015037 | HPR108 | 2021-12-01 | Material | 11970055 | 16219865 | 18605794
MCR015038 | HPR108 | 2021-12-01 | Equipment | 2604446 | 3529120 | 3734040
MCR015039 | HPR108 | 2021-12-01 | Subcontract | 20634848 | 27960981 | 28058652
MCR015040 | HPR108 | 2021-12-01 | Overhead | 3554553 | 4816551 | 8357013
MCR015041 | HPR108 | 2022-01-01 | Labor | 3217820 | 9629834 | 9196255
MCR015042 | HPR108 | 2022-01-01 | Material | 6516143 | 19500589 | 22432948
MCR015043 | HPR108 | 2022-01-01 | Equipment | 1417783 | 4242940 | 4218986
MCR015044 | HPR108 | 2022-01-01 | Subcontract | 11233000 | 33616529 | 34191043
MCR015045 | HPR108 | 2022-01-01 | Overhead | 1934994 | 5790774 | 8669754
MCR015046 | HPR108 | 2022-02-01 | Labor | 856823 | 11294160 | 13271900
MCR015047 | HPR108 | 2022-02-01 | Material | 1735082 | 22870879 | 29038862
MCR015048 | HPR108 | 2022-02-01 | Equipment | 377519 | 4976248 | 5035977
MCR015049 | HPR108 | 2022-02-01 | Subcontract | 2991060 | 39426480 | 41772805
MCR015050 | HPR108 | 2022-02-01 | Overhead | 515239 | 6791595 | 8416642
MCR015051 | HPR108 | 2022-03-01 | Labor | 0 | 7364028 | 10030330
MCR015052 | HPR108 | 2022-03-01 | Material | 0 | 14912290 | 19306595
MCR015053 | HPR108 | 2022-03-01 | Equipment | 0 | 3244618 | 3411728
MCR015054 | HPR108 | 2022-03-01 | Subcontract | 0 | 25706888 | 28630780
MCR015055 | HPR108 | 2022-03-01 | Overhead | 0 | 4428262 | 7755457
MCR015056 | HPR108 | 2022-04-01 | Labor | 0 | 4388091 | 5001547
MCR015057 | HPR108 | 2022-04-01 | Material | 0 | 8885964 | 12927827
MCR015058 | HPR108 | 2022-04-01 | Equipment | 0 | 1933409 | 1683425
MCR015059 | HPR108 | 2022-04-01 | Subcontract | 0 | 15318269 | 18845407
MCR015060 | HPR108 | 2022-04-01 | Overhead | 0 | 2638721 | 8148737
MCR015061 | HPR108 | 2022-05-01 | Labor | 0 | 2966861 | 2777486
MCR015062 | HPR108 | 2022-05-01 | Material | 0 | 6007948 | 5942594
MCR015063 | HPR108 | 2022-05-01 | Equipment | 0 | 1307210 | 1791133
MCR015064 | HPR108 | 2022-05-01 | Subcontract | 0 | 10356936 | 9566723
MCR015065 | HPR108 | 2022-05-01 | Overhead | 0 | 1784083 | 8277695
MCR015066 | HPR108 | 2022-06-01 | Labor | 0 | 718876 | 839142
MCR015067 | HPR108 | 2022-06-01 | Material | 0 | 1455737 | 1962014
MCR015068 | HPR108 | 2022-06-01 | Equipment | 0 | 316739 | 229813
MCR015069 | HPR108 | 2022-06-01 | Subcontract | 0 | 2509505 | 3071026
MCR015070 | HPR108 | 2022-06-01 | Overhead | 0 | 432287 | 8280240
MCR015071 | HPR109 | 2022-12-01 | Labor | 4670974 | 5157764 | 5772265
MCR015072 | HPR109 | 2022-12-01 | Material | 16108929 | 17787737 | 17995981
MCR015073 | HPR109 | 2022-12-01 | Equipment | 2987401 | 3298735 | 3353642
MCR015074 | HPR109 | 2022-12-01 | Subcontract | 11843179 | 13077427 | 12838070
MCR015075 | HPR109 | 2022-12-01 | Overhead | 2797287 | 3088809 | 9630086
MCR015076 | HPR109 | 2023-01-01 | Labor | 12602026 | 11291561 | 10804886
MCR015077 | HPR109 | 2023-01-01 | Material | 43460988 | 38941549 | 33899090
MCR015078 | HPR109 | 2023-01-01 | Equipment | 8059840 | 7221710 | 6467845
MCR015079 | HPR109 | 2023-01-01 | Subcontract | 31952232 | 28629570 | 23740085
MCR015080 | HPR109 | 2023-01-01 | Overhead | 7546924 | 6762132 | 9106432
MCR015081 | HPR109 | 2023-02-01 | Labor | 18484589 | 19502090 | 17513308
MCR015082 | HPR109 | 2023-02-01 | Material | 63748362 | 67257447 | 63822433
MCR015083 | HPR109 | 2023-02-01 | Equipment | 11822133 | 12472892 | 11933545
MCR015084 | HPR109 | 2023-02-01 | Subcontract | 46867375 | 49447231 | 55223746
MCR015085 | HPR109 | 2023-02-01 | Overhead | 11069791 | 11679138 | 9994381
MCR015086 | HPR109 | 2023-03-01 | Labor | 22416222 | 25029947 | 24752228
MCR015087 | HPR109 | 2023-03-01 | Material | 77307501 | 86321534 | 91358022
MCR015088 | HPR109 | 2023-03-01 | Equipment | 14336675 | 16008327 | 15022450
MCR015089 | HPR109 | 2023-03-01 | Subcontract | 56835965 | 63463022 | 63101431
MCR015090 | HPR109 | 2023-03-01 | Overhead | 13424312 | 14989583 | 10050041
MCR015091 | HPR109 | 2023-04-01 | Labor | 24505177 | 40792242 | 40772540
MCR015092 | HPR109 | 2023-04-01 | Material | 84511746 | 140681439 | 118969522
MCR015093 | HPR109 | 2023-04-01 | Equipment | 15672702 | 26089371 | 25699016
MCR015094 | HPR109 | 2023-04-01 | Subcontract | 62132478 | 103428066 | 97142069
MCR015095 | HPR109 | 2023-04-01 | Overhead | 14675317 | 24429085 | 9732985
MCR015096 | HPR109 | 2023-05-01 | Labor | 24873431 | 14629063 | 14230025
MCR015097 | HPR109 | 2023-05-01 | Material | 85781755 | 50451693 | 40232918
MCR015098 | HPR109 | 2023-05-01 | Equipment | 15908225 | 9356266 | 9528874
MCR015099 | HPR109 | 2023-05-01 | Subcontract | 63066180 | 37091752 | 38035271
MCR015100 | HPR109 | 2023-05-01 | Overhead | 14895851 | 8760848 | 9882837
MCR015101 | HPR109 | 2023-06-01 | Labor | 23661216 | 24367756 | 24759358
MCR015102 | HPR109 | 2023-06-01 | Material | 81601150 | 84037818 | 79825315
MCR015103 | HPR109 | 2023-06-01 | Equipment | 15132932 | 15584812 | 16670474
MCR015104 | HPR109 | 2023-06-01 | Subcontract | 59992627 | 61784050 | 60401922
MCR015105 | HPR109 | 2023-06-01 | Overhead | 14169897 | 14593020 | 9339183
MCR015106 | HPR109 | 2023-07-01 | Labor | 21034264 | 19081247 | 28753078
MCR015107 | HPR109 | 2023-07-01 | Material | 72541503 | 65806075 | 71416334
MCR015108 | HPR109 | 2023-07-01 | Equipment | 13452821 | 12203736 | 10998632
MCR015109 | HPR109 | 2023-07-01 | Subcontract | 53332034 | 48380192 | 43203859
MCR015110 | HPR109 | 2023-07-01 | Overhead | 12596705 | 11427109 | 9271945
MCR015111 | HPR109 | 2023-08-01 | Labor | 17196426 | 11337612 | 19943755
MCR015112 | HPR109 | 2023-08-01 | Material | 59305835 | 39100366 | 41192299
MCR015113 | HPR109 | 2023-08-01 | Equipment | 10998266 | 7251162 | 7392516
MCR015114 | HPR109 | 2023-08-01 | Subcontract | 43601259 | 28746331 | 31198965
MCR015115 | HPR109 | 2023-08-01 | Overhead | 10298354 | 6789710 | 9723752
MCR015116 | HPR109 | 2023-09-01 | Labor | 12414616 | 12668594 | 12628771
MCR015117 | HPR109 | 2023-09-01 | Material | 42814663 | 43690564 | 46521542
MCR015118 | HPR109 | 2023-09-01 | Equipment | 7939979 | 8102414 | 8418666
MCR015119 | HPR109 | 2023-09-01 | Subcontract | 31477058 | 32121015 | 27942189
MCR015120 | HPR109 | 2023-09-01 | Overhead | 7434691 | 7586790 | 9621273
MCR015121 | HPR109 | 2023-10-01 | Labor | 7079810 | 5356106 | 6280354
MCR015122 | HPR109 | 2023-10-01 | Material | 24416356 | 18471766 | 14572000
MCR015123 | HPR109 | 2023-10-01 | Equipment | 4528013 | 3425589 | 3197925
MCR015124 | HPR109 | 2023-10-01 | Subcontract | 17950744 | 13580321 | 15524630
MCR015125 | HPR109 | 2023-10-01 | Overhead | 4239857 | 3207590 | 9698569
MCR015126 | HPR109 | 2023-11-01 | Labor | 1955253 | 1680022 | 1135205
MCR015127 | HPR109 | 2023-11-01 | Material | 6743141 | 5793942 | 6549941
MCR015128 | HPR109 | 2023-11-01 | Equipment | 1250515 | 1074486 | 1119416
MCR015129 | HPR109 | 2023-11-01 | Subcontract | 4957513 | 4259668 | 3851766
MCR015130 | HPR109 | 2023-11-01 | Overhead | 1170935 | 1006108 | 9389726
MCR015131 | HPR110 | 2016-06-01 | Labor | 8425821 | 6174826 | 7400085
MCR015132 | HPR110 | 2016-06-01 | Material | 22432358 | 16439456 | 14185601
MCR015133 | HPR110 | 2016-06-01 | Equipment | 7688233 | 5634288 | 6301281
MCR015134 | HPR110 | 2016-06-01 | Subcontract | 15936604 | 11679071 | 12431414
MCR015135 | HPR110 | 2016-06-01 | Overhead | 7264312 | 5323620 | 36631252
MCR015136 | HPR110 | 2016-07-01 | Labor | 23605935 | 9593108 | 10019351
MCR015137 | HPR110 | 2016-07-01 | Material | 62846907 | 25540067 | 24941692
MCR015138 | HPR110 | 2016-07-01 | Equipment | 21539494 | 8753336 | 8444820
MCR015139 | HPR110 | 2016-07-01 | Subcontract | 44648283 | 18144411 | 18442282
MCR015140 | HPR110 | 2016-07-01 | Overhead | 20351832 | 8270688 | 36645980
MCR015141 | HPR110 | 2016-08-01 | Labor | 36329942 | 15036857 | 15700693
MCR015142 | HPR110 | 2016-08-01 | Material | 96722478 | 40033150 | 44354339
MCR015143 | HPR110 | 2016-08-01 | Equipment | 33149654 | 13720545 | 13604609
MCR015144 | HPR110 | 2016-08-01 | Subcontract | 68714481 | 28440722 | 27400421
MCR015145 | HPR110 | 2016-08-01 | Overhead | 31321821 | 12964010 | 38956252
MCR015146 | HPR110 | 2016-09-01 | Labor | 46669368 | 41827498 | 45035041
MCR015147 | HPR110 | 2016-09-01 | Material | 124249493 | 111358812 | 120583219
MCR015148 | HPR110 | 2016-09-01 | Equipment | 42583976 | 38165959 | 35807538
MCR015149 | HPR110 | 2016-09-01 | Subcontract | 88270479 | 79112561 | 85689862
MCR015150 | HPR110 | 2016-09-01 | Overhead | 40235946 | 36061533 | 35912328
MCR015151 | HPR110 | 2016-10-01 | Labor | 54700329 | 42391827 | 45513086
MCR015152 | HPR110 | 2016-10-01 | Material | 145630603 | 112861245 | 123012553
MCR015153 | HPR110 | 2016-10-01 | Equipment | 49911915 | 38680887 | 40929304
MCR015154 | HPR110 | 2016-10-01 | Subcontract | 103460245 | 80179934 | 71049216
MCR015155 | HPR110 | 2016-10-01 | Overhead | 47159831 | 36548069 | 36643428
MCR015156 | HPR110 | 2016-11-01 | Labor | 60504260 | 43972249 | 42378765
MCR015157 | HPR110 | 2016-11-01 | Material | 161082610 | 117068859 | 95505509
MCR015158 | HPR110 | 2016-11-01 | Equipment | 55207775 | 40122961 | 35158970
MCR015159 | HPR110 | 2016-11-01 | Subcontract | 114437804 | 83169146 | 87264353
MCR015160 | HPR110 | 2016-11-01 | Overhead | 52163684 | 37910628 | 38818746
MCR015161 | HPR110 | 2016-12-01 | Labor | 64168814 | 43342187 | 55926584
MCR015162 | HPR110 | 2016-12-01 | Material | 170838882 | 115391421 | 132164440
MCR015163 | HPR110 | 2016-12-01 | Equipment | 58551538 | 39548053 | 47294532
MCR015164 | HPR110 | 2016-12-01 | Subcontract | 121368945 | 81977445 | 87191771
MCR015165 | HPR110 | 2016-12-01 | Overhead | 55323075 | 37367420 | 37023970
MCR015166 | HPR110 | 2017-01-01 | Labor | 65789032 | 55674693 | 65704720
MCR015167 | HPR110 | 2017-01-01 | Material | 175152444 | 148224686 | 149056220
MCR015168 | HPR110 | 2017-01-01 | Equipment | 60029924 | 50800984 | 47693425
MCR015169 | HPR110 | 2017-01-01 | Subcontract | 124433426 | 105303158 | 116653939
MCR015170 | HPR110 | 2017-01-01 | Overhead | 56719944 | 47999878 | 33999074
MCR015171 | HPR110 | 2017-02-01 | Labor | 65468861 | 84791625 | 79380110
MCR015172 | HPR110 | 2017-02-01 | Material | 174300041 | 225743713 | 207270403
MCR015173 | HPR110 | 2017-02-01 | Equipment | 59737780 | 77369048 | 81108162
MCR015174 | HPR110 | 2017-02-01 | Subcontract | 123827854 | 160374945 | 161298592
MCR015175 | HPR110 | 2017-02-01 | Overhead | 56443909 | 73103010 | 37120939
MCR015176 | HPR110 | 2017-03-01 | Labor | 63323207 | 35286819 | 42349344
MCR015177 | HPR110 | 2017-03-01 | Material | 168587591 | 93945333 | 109339140
MCR015178 | HPR110 | 2017-03-01 | Equipment | 57779954 | 32197844 | 29262841
MCR015179 | HPR110 | 2017-03-01 | Subcontract | 119769562 | 66741516 | 68229928
MCR015180 | HPR110 | 2017-03-01 | Overhead | 54594036 | 30422493 | 34717537
MCR015181 | HPR110 | 2017-04-01 | Labor | 59480781 | 84502061 | 91816521
MCR015182 | HPR110 | 2017-04-01 | Material | 158357766 | 224972797 | 221750778
MCR015183 | HPR110 | 2017-04-01 | Equipment | 54273890 | 77104832 | 82905105
MCR015184 | HPR110 | 2017-04-01 | Subcontract | 112501995 | 159827264 | 163227530
MCR015185 | HPR110 | 2017-04-01 | Overhead | 51281292 | 72853363 | 37839532
MCR015186 | HPR110 | 2017-05-01 | Labor | 54088207 | 50964712 | 58105868
MCR015187 | HPR110 | 2017-05-01 | Material | 144000928 | 135685138 | 126610793
MCR015188 | HPR110 | 2017-05-01 | Equipment | 49353377 | 46503310 | 46695935
MCR015189 | HPR110 | 2017-05-01 | Subcontract | 102302476 | 96394696 | 84609111
MCR015190 | HPR110 | 2017-05-01 | Overhead | 46632091 | 43939173 | 31701696
MCR015191 | HPR110 | 2017-06-01 | Labor | 47316251 | 32964793 | 34856826
MCR015192 | HPR110 | 2017-06-01 | Material | 125971713 | 87763322 | 95972342
MCR015193 | HPR110 | 2017-06-01 | Equipment | 43174232 | 30079086 | 36800150
MCR015194 | HPR110 | 2017-06-01 | Subcontract | 89493995 | 62349634 | 74528251
MCR015195 | HPR110 | 2017-06-01 | Overhead | 40793656 | 28420561 | 33849835
MCR015196 | HPR110 | 2017-07-01 | Labor | 39369890 | 30902608 | 36591077
MCR015197 | HPR110 | 2017-07-01 | Material | 104815836 | 82273095 | 84150837
MCR015198 | HPR110 | 2017-07-01 | Equipment | 35923487 | 28197423 | 24969276
MCR015199 | HPR110 | 2017-07-01 | Subcontract | 74464240 | 58449216 | 49906026
MCR015200 | HPR110 | 2017-07-01 | Overhead | 33942709 | 26642651 | 37687125
MCR015201 | HPR110 | 2017-08-01 | Labor | 30506074 | 28138823 | 22504981
MCR015202 | HPR110 | 2017-08-01 | Material | 81217391 | 74914975 | 74446914
MCR015203 | HPR110 | 2017-08-01 | Equipment | 27835602 | 25675578 | 27959988
MCR015204 | HPR110 | 2017-08-01 | Subcontract | 57699213 | 53221792 | 90314486
MCR015205 | HPR110 | 2017-08-01 | Overhead | 26300780 | 24259857 | 36410200
MCR015206 | HPR110 | 2017-09-01 | Labor | 21069407 | 48480297 | 53460492
MCR015207 | HPR110 | 2017-09-01 | Material | 56093821 | 129070793 | 138906703
MCR015208 | HPR110 | 2017-09-01 | Equipment | 19225012 | 44236378 | 35566182
MCR015209 | HPR110 | 2017-09-01 | Subcontract | 39850693 | 91695671 | 123330245
MCR015210 | HPR110 | 2017-09-01 | Overhead | 18164967 | 41797237 | 36203542
MCR015211 | HPR110 | 2017-10-01 | Labor | 11580893 | 36459063 | 36745067
MCR015212 | HPR110 | 2017-10-01 | Material | 30832218 | 97066239 | 93907647
MCR015213 | HPR110 | 2017-10-01 | Equipment | 10567113 | 33267471 | 35625233
MCR015214 | HPR110 | 2017-10-01 | Subcontract | 21904111 | 68958699 | 92407498
MCR015215 | HPR110 | 2017-10-01 | Overhead | 9984455 | 31433142 | 36336435
MCR015216 | HPR110 | 2017-11-01 | Labor | 3107951 | 25622678 | 29790564
MCR015217 | HPR110 | 2017-11-01 | Material | 8274407 | 68216154 | 70790934
MCR015218 | HPR110 | 2017-11-01 | Equipment | 2835884 | 23379694 | 25248150
MCR015219 | HPR110 | 2017-11-01 | Subcontract | 5878381 | 48462753 | 81011353
MCR015220 | HPR110 | 2017-11-01 | Overhead | 2679517 | 22090565 | 37335851
MCR015221 | HPR110 | 2017-12-01 | Labor | 0 | 17496222 | 18783175
MCR015222 | HPR110 | 2017-12-01 | Material | 0 | 46580805 | 44377087
MCR015223 | HPR110 | 2017-12-01 | Equipment | 0 | 15964620 | 16619658
MCR015224 | HPR110 | 2017-12-01 | Subcontract | 0 | 33092368 | 62711214
MCR015225 | HPR110 | 2017-12-01 | Overhead | 0 | 15084349 | 35617208
MCR015226 | HPR110 | 2018-01-01 | Labor | 0 | 10947107 | 9908427
MCR015227 | HPR110 | 2018-01-01 | Material | 0 | 29144866 | 34397343
MCR015228 | HPR110 | 2018-01-01 | Equipment | 0 | 9988808 | 10485516
MCR015229 | HPR110 | 2018-01-01 | Subcontract | 0 | 20705366 | 34128273
MCR015230 | HPR110 | 2018-01-01 | Overhead | 0 | 9438037 | 39098425
MCR015231 | HPR110 | 2018-02-01 | Labor | 0 | 9090299 | 9611710
MCR015232 | HPR110 | 2018-02-01 | Material | 0 | 24201420 | 23512314
MCR015233 | HPR110 | 2018-02-01 | Equipment | 0 | 8294543 | 9254425
MCR015234 | HPR110 | 2018-02-01 | Subcontract | 0 | 17193398 | 47338585
MCR015235 | HPR110 | 2018-02-01 | Overhead | 0 | 7837191 | 35595370
MCR015236 | HPR110 | 2018-03-01 | Labor | 0 | 1844674 | 2005716
MCR015237 | HPR110 | 2018-03-01 | Material | 0 | 4911140 | 5203427
MCR015238 | HPR110 | 2018-03-01 | Equipment | 0 | 1683193 | 1533198
MCR015239 | HPR110 | 2018-03-01 | Subcontract | 0 | 3489018 | 51176768
MCR015240 | HPR110 | 2018-03-01 | Overhead | 0 | 1590384 | 36001551
MCR015241 | HPR111 | 2019-05-01 | Labor | 3377974 | 2362016 | 2486590
MCR015242 | HPR111 | 2019-05-01 | Material | 7607205 | 5319265 | 5038976
MCR015243 | HPR111 | 2019-05-01 | Equipment | 1970929 | 1378153 | 1508644
MCR015244 | HPR111 | 2019-05-01 | Subcontract | 9878862 | 6907700 | 7079667
MCR015245 | HPR111 | 2019-05-01 | Overhead | 2028512 | 1418418 | 11205884
MCR015246 | HPR111 | 2019-06-01 | Labor | 9532602 | 5160896 | 5681403
MCR015247 | HPR111 | 2019-06-01 | Material | 21467439 | 11622348 | 11066635
MCR015248 | HPR111 | 2019-06-01 | Equipment | 5561936 | 3011200 | 3008445
MCR015249 | HPR111 | 2019-06-01 | Subcontract | 27878027 | 15093003 | 15184990
MCR015250 | HPR111 | 2019-06-01 | Overhead | 5724436 | 3099177 | 12542597
MCR015251 | HPR111 | 2019-07-01 | Labor | 14801674 | 5392803 | 5407140
MCR015252 | HPR111 | 2019-07-01 | Material | 33333401 | 12144605 | 13295226
MCR015253 | HPR111 | 2019-07-01 | Equipment | 8636254 | 3146510 | 3503517
MCR015254 | HPR111 | 2019-07-01 | Subcontract | 43287393 | 15771216 | 15341946
MCR015255 | HPR111 | 2019-07-01 | Overhead | 8888574 | 3238440 | 11096852
MCR015256 | HPR111 | 2019-08-01 | Labor | 19208023 | 5881131 | 5867630
MCR015257 | HPR111 | 2019-08-01 | Material | 43256508 | 13244320 | 13333200
MCR015258 | HPR111 | 2019-08-01 | Equipment | 11207203 | 3431433 | 3416962
MCR015259 | HPR111 | 2019-08-01 | Subcontract | 56173731 | 17199328 | 18504084
MCR015260 | HPR111 | 2019-08-01 | Overhead | 11534637 | 3531686 | 11229072
MCR015261 | HPR111 | 2019-09-01 | Labor | 22775770 | 11108989 | 12378833
MCR015262 | HPR111 | 2019-09-01 | Material | 51291082 | 25017466 | 24374003
MCR015263 | HPR111 | 2019-09-01 | Equipment | 13288858 | 6481703 | 6947844
MCR015264 | HPR111 | 2019-09-01 | Subcontract | 66607582 | 32488161 | 33632813
MCR015265 | HPR111 | 2019-09-01 | Overhead | 13677110 | 6671074 | 12090105
MCR015266 | HPR111 | 2019-10-01 | Labor | 25530501 | 15711999 | 15772824
MCR015267 | HPR111 | 2019-10-01 | Material | 57494742 | 35383454 | 35851482
MCR015268 | HPR111 | 2019-10-01 | Equipment | 14896146 | 9167397 | 9811337
MCR015269 | HPR111 | 2019-10-01 | Subcontract | 74663774 | 45949632 | 46425322
MCR015270 | HPR111 | 2019-10-01 | Overhead | 15331357 | 9435234 | 10989071
MCR015271 | HPR111 | 2019-11-01 | Labor | 27499482 | 12387485 | 15314391
MCR015272 | HPR111 | 2019-11-01 | Material | 61928892 | 27896643 | 29228273
MCR015273 | HPR111 | 2019-11-01 | Equipment | 16044977 | 7227660 | 7638634
MCR015274 | HPR111 | 2019-11-01 | Subcontract | 80422045 | 36227115 | 36902394
MCR015275 | HPR111 | 2019-11-01 | Overhead | 16513752 | 7438826 | 11024605
MCR015276 | HPR111 | 2019-12-01 | Labor | 28711927 | 34498567 | 37548103
MCR015277 | HPR111 | 2019-12-01 | Material | 64659321 | 77690845 | 89423681
MCR015278 | HPR111 | 2019-12-01 | Equipment | 16752396 | 20128696 | 21234834
MCR015279 | HPR111 | 2019-12-01 | Subcontract | 83967833 | 100890821 | 96865986
MCR015280 | HPR111 | 2019-12-01 | Overhead | 17241840 | 20716783 | 10582504
MCR015281 | HPR111 | 2020-01-01 | Labor | 29199334 | 20365081 | 21095427
MCR015282 | HPR111 | 2020-01-01 | Material | 65756962 | 45862205 | 43298950
MCR015283 | HPR111 | 2020-01-01 | Equipment | 17036781 | 11882306 | 12106641
MCR015284 | HPR111 | 2020-01-01 | Subcontract | 85393251 | 59557538 | 64154418
MCR015285 | HPR111 | 2020-01-01 | Overhead | 17534533 | 12229463 | 10797150
MCR015286 | HPR111 | 2020-02-01 | Labor | 28995917 | 19183969 | 20284821
MCR015287 | HPR111 | 2020-02-01 | Material | 65298866 | 43202338 | 42964293
MCR015288 | HPR111 | 2020-02-01 | Equipment | 16918094 | 11193168 | 12452362
MCR015289 | HPR111 | 2020-02-01 | Subcontract | 84798359 | 56103384 | 58009717
MCR015290 | HPR111 | 2020-02-01 | Overhead | 17412379 | 11520192 | 10584548
MCR015291 | HPR111 | 2020-03-01 | Labor | 28139174 | 18392688 | 21399669
MCR015292 | HPR111 | 2020-03-01 | Material | 63369480 | 41420371 | 40470377
MCR015293 | HPR111 | 2020-03-01 | Equipment | 16418215 | 10731484 | 11436267
MCR015294 | HPR111 | 2020-03-01 | Subcontract | 82292821 | 53789288 | 54796965
MCR015295 | HPR111 | 2020-03-01 | Overhead | 16897895 | 11045018 | 11159566
MCR015296 | HPR111 | 2020-04-01 | Labor | 26670654 | 21585529 | 23454136
MCR015297 | HPR111 | 2020-04-01 | Material | 60062368 | 48610656 | 49735617
MCR015298 | HPR111 | 2020-04-01 | Equipment | 15561385 | 12594394 | 12841144
MCR015299 | HPR111 | 2020-04-01 | Subcontract | 77998143 | 63126730 | 57768833
MCR015300 | HPR111 | 2020-04-01 | Overhead | 16016032 | 12962356 | 10810370
MCR015301 | HPR111 | 2020-05-01 | Labor | 24637019 | 32555041 | 34461819
MCR015302 | HPR111 | 2020-05-01 | Material | 55482618 | 73314021 | 75543577
MCR015303 | HPR111 | 2020-05-01 | Equipment | 14374831 | 18994717 | 17239575
MCR015304 | HPR111 | 2020-05-01 | Subcontract | 72050791 | 95206993 | 106599149
MCR015305 | HPR111 | 2020-05-01 | Overhead | 14794810 | 19549673 | 10803247
MCR015306 | HPR111 | 2020-06-01 | Labor | 22091588 | 24465389 | 26705076
MCR015307 | HPR111 | 2020-06-01 | Material | 49750303 | 55096108 | 59376430
MCR015308 | HPR111 | 2020-06-01 | Equipment | 12889662 | 14274691 | 16387523
MCR015309 | HPR111 | 2020-06-01 | Subcontract | 64606697 | 71548862 | 69777106
MCR015310 | HPR111 | 2020-06-01 | Overhead | 13266251 | 14691745 | 11738238
MCR015311 | HPR111 | 2020-07-01 | Labor | 19096681 | 9702854 | 10385157
MCR015312 | HPR111 | 2020-07-01 | Material | 43005765 | 21850847 | 21129859
MCR015313 | HPR111 | 2020-07-01 | Equipment | 11142239 | 5661273 | 6187057
MCR015314 | HPR111 | 2020-07-01 | Subcontract | 55848111 | 28375928 | 30606421
MCR015315 | HPR111 | 2020-07-01 | Overhead | 11467774 | 5826674 | 12010584
MCR015316 | HPR111 | 2020-08-01 | Labor | 15727411 | 17836671 | 18041054
MCR015317 | HPR111 | 2020-08-01 | Material | 35418161 | 40168220 | 37914624
MCR015318 | HPR111 | 2020-08-01 | Equipment | 9176389 | 10407068 | 10551215
MCR015319 | HPR111 | 2020-08-01 | Subcontract | 45994703 | 52163220 | 55287100
MCR015320 | HPR111 | 2020-08-01 | Overhead | 9444489 | 10711124 | 11667393
MCR015321 | HPR111 | 2020-09-01 | Labor | 12078410 | 21730134 | 25609454
MCR015322 | HPR111 | 2020-09-01 | Material | 27200605 | 48936308 | 52628804
MCR015323 | HPR111 | 2020-09-01 | Equipment | 7047326 | 12678766 | 14515026
MCR015324 | HPR111 | 2020-09-01 | Subcontract | 35323227 | 63549628 | 64146848
MCR015325 | HPR111 | 2020-09-01 | Overhead | 7253223 | 13049193 | 10550207
MCR015326 | HPR111 | 2020-10-01 | Labor | 8277371 | 21914860 | 23869800
MCR015327 | HPR111 | 2020-10-01 | Material | 18640657 | 49352310 | 45843880
MCR015328 | HPR111 | 2020-10-01 | Equipment | 4829554 | 12786547 | 14561290
MCR015329 | HPR111 | 2020-10-01 | Subcontract | 24207114 | 64089855 | 88839495
MCR015330 | HPR111 | 2020-10-01 | Overhead | 4970656 | 13160123 | 9601695
MCR015331 | HPR111 | 2020-11-01 | Labor | 4518865 | 11953896 | 9904502
MCR015332 | HPR111 | 2020-11-01 | Material | 10176493 | 26920198 | 30574359
MCR015333 | HPR111 | 2020-11-01 | Equipment | 2636598 | 6974676 | 6146782
MCR015334 | HPR111 | 2020-11-01 | Subcontract | 13215388 | 34959085 | 62084183
MCR015335 | HPR111 | 2020-11-01 | Overhead | 2713630 | 7178451 | 10673246
MCR015336 | HPR111 | 2020-12-01 | Labor | 1206070 | 8044932 | 9594683
MCR015337 | HPR111 | 2020-12-01 | Material | 2716073 | 18117205 | 14070263
MCR015338 | HPR111 | 2020-12-01 | Equipment | 703699 | 4693934 | 4557816
MCR015339 | HPR111 | 2020-12-01 | Subcontract | 3527144 | 23527349 | 36348472
MCR015340 | HPR111 | 2020-12-01 | Overhead | 724259 | 4831074 | 11866229
MCR015341 | HPR111 | 2021-01-01 | Labor | 0 | 14455481 | 15468442
MCR015342 | HPR111 | 2021-01-01 | Material | 0 | 32553773 | 35218900
MCR015343 | HPR111 | 2021-01-01 | Equipment | 0 | 8434263 | 9135521
MCR015344 | HPR111 | 2021-01-01 | Subcontract | 0 | 42274953 | 59395223
MCR015345 | HPR111 | 2021-01-01 | Overhead | 0 | 8680681 | 11045707
MCR015346 | HPR111 | 2021-02-01 | Labor | 0 | 9741880 | 8574005
MCR015347 | HPR111 | 2021-02-01 | Material | 0 | 21938735 | 18733184
MCR015348 | HPR111 | 2021-02-01 | Equipment | 0 | 5684043 | 5753730
MCR015349 | HPR111 | 2021-02-01 | Subcontract | 0 | 28490061 | 58823408
MCR015350 | HPR111 | 2021-02-01 | Overhead | 0 | 5850110 | 11642399
MCR015351 | HPR111 | 2021-03-01 | Labor | 0 | 13255566 | 12889750
MCR015352 | HPR111 | 2021-03-01 | Material | 0 | 29851563 | 30686164
MCR015353 | HPR111 | 2021-03-01 | Equipment | 0 | 7734155 | 8822023
MCR015354 | HPR111 | 2021-03-01 | Subcontract | 0 | 38765812 | 48114967
MCR015355 | HPR111 | 2021-03-01 | Overhead | 0 | 7960119 | 10375905
MCR015356 | HPR111 | 2021-04-01 | Labor | 0 | 6293253 | 7817990
MCR015357 | HPR111 | 2021-04-01 | Material | 0 | 14172420 | 13771734
MCR015358 | HPR111 | 2021-04-01 | Equipment | 0 | 3671891 | 3896565
MCR015359 | HPR111 | 2021-04-01 | Subcontract | 0 | 18404576 | 39469512
MCR015360 | HPR111 | 2021-04-01 | Overhead | 0 | 3779170 | 11513669
MCR015361 | HPR111 | 2021-05-01 | Labor | 0 | 4707843 | 5499681
MCR015362 | HPR111 | 2021-05-01 | Material | 0 | 10602073 | 11873388
MCR015363 | HPR111 | 2021-05-01 | Equipment | 0 | 2746860 | 3375967
MCR015364 | HPR111 | 2021-05-01 | Subcontract | 0 | 13768055 | 33578245
MCR015365 | HPR111 | 2021-05-01 | Overhead | 0 | 2827113 | 11376259
MCR015366 | HPR111 | 2021-06-01 | Labor | 0 | 2879336 | 2623995
MCR015367 | HPR111 | 2021-06-01 | Material | 0 | 6484271 | 7420869
MCR015368 | HPR111 | 2021-06-01 | Equipment | 0 | 1679991 | 1922064
MCR015369 | HPR111 | 2021-06-01 | Subcontract | 0 | 8420599 | 22067024
MCR015370 | HPR111 | 2021-06-01 | Overhead | 0 | 1729074 | 11843521
MCR015371 | HPR111 | 2021-07-01 | Labor | 0 | 508158 | 702062
MCR015372 | HPR111 | 2021-07-01 | Material | 0 | 1144373 | 1504764
MCR015373 | HPR111 | 2021-07-01 | Equipment | 0 | 296492 | 477185
MCR015374 | HPR111 | 2021-07-01 | Subcontract | 0 | 1486105 | 32479464
MCR015375 | HPR111 | 2021-07-01 | Overhead | 0 | 305155 | 10436087
MCR015376 | HPR112 | 2022-01-01 | Labor | 6643302 | 2457547 | 2500894
MCR015377 | HPR112 | 2022-01-01 | Material | 16598370 | 6140212 | 6476607
MCR015378 | HPR112 | 2022-01-01 | Equipment | 4687406 | 1734006 | 1792801
MCR015379 | HPR112 | 2022-01-01 | Subcontract | 24741029 | 9152414 | 8648606
MCR015380 | HPR112 | 2022-01-01 | Overhead | 5755875 | 2129263 | 25069299
MCR015381 | HPR112 | 2022-02-01 | Labor | 18338943 | 9189162 | 10197036
MCR015382 | HPR112 | 2022-02-01 | Material | 45820071 | 22959231 | 22393079
MCR015383 | HPR112 | 2022-02-01 | Equipment | 12939662 | 6483724 | 6878173
MCR015384 | HPR112 | 2022-02-01 | Subcontract | 68298014 | 34222337 | 37127303
MCR015385 | HPR112 | 2022-02-01 | Overhead | 15889186 | 7961653 | 24626534
MCR015386 | HPR112 | 2022-03-01 | Labor | 27707669 | 21395557 | 20692207
MCR015387 | HPR112 | 2022-03-01 | Material | 69227948 | 53457059 | 60925033
MCR015388 | HPR112 | 2022-03-01 | Equipment | 19550084 | 15096359 | 17308158
MCR015389 | HPR112 | 2022-03-01 | Subcontract | 103189088 | 79681477 | 69695823
MCR015390 | HPR112 | 2022-03-01 | Overhead | 24006416 | 18537490 | 24985060
MCR015391 | HPR112 | 2022-04-01 | Labor | 34833577 | 18848225 | 22166785
MCR015392 | HPR112 | 2022-04-01 | Material | 87032114 | 47092520 | 46829002
MCR015393 | HPR112 | 2022-04-01 | Equipment | 24578009 | 13299003 | 13235010
MCR015394 | HPR112 | 2022-04-01 | Subcontract | 129727441 | 70194687 | 74854934
MCR015395 | HPR112 | 2022-04-01 | Overhead | 30180429 | 16330437 | 26047141
MCR015396 | HPR112 | 2022-05-01 | Labor | 39807573 | 27046673 | 25761622
MCR015397 | HPR112 | 2022-05-01 | Material | 99459703 | 67576440 | 73963643
MCR015398 | HPR112 | 2022-05-01 | Equipment | 28087580 | 19083695 | 22067921
MCR015399 | HPR112 | 2022-05-01 | Subcontract | 148251629 | 100727400 | 104104360
MCR015400 | HPR112 | 2022-05-01 | Overhead | 34489987 | 23433717 | 22512090
MCR015401 | HPR112 | 2022-06-01 | Labor | 42728749 | 28906651 | 33687570
MCR015402 | HPR112 | 2022-06-01 | Material | 106758296 | 72223618 | 75161182
MCR015403 | HPR112 | 2022-06-01 | Equipment | 30148714 | 20396066 | 17295255
MCR015404 | HPR112 | 2022-06-01 | Subcontract | 159130691 | 107654343 | 119748120
MCR015405 | HPR112 | 2022-06-01 | Overhead | 37020946 | 25045235 | 24490766
MCR015406 | HPR112 | 2022-07-01 | Labor | 43706223 | 23213816 | 24924544
MCR015407 | HPR112 | 2022-07-01 | Material | 109200527 | 58000000 | 60638619
MCR015408 | HPR112 | 2022-07-01 | Equipment | 30838404 | 16379293 | 20586041
MCR015409 | HPR112 | 2022-07-01 | Subcontract | 162771006 | 86453047 | 79201725
MCR015410 | HPR112 | 2022-07-01 | Overhead | 37867847 | 20112862 | 24600072
MCR015411 | HPR112 | 2022-08-01 | Labor | 42861685 | 28880889 | 26076335
MCR015412 | HPR112 | 2022-08-01 | Material | 107090440 | 72159252 | 61786921
MCR015413 | HPR112 | 2022-08-01 | Equipment | 30242512 | 20377888 | 22727878
MCR015414 | HPR112 | 2022-08-01 | Subcontract | 159625775 | 107558401 | 125254671
MCR015415 | HPR112 | 2022-08-01 | Overhead | 37136125 | 25022915 | 23770072
MCR015416 | HPR112 | 2022-09-01 | Labor | 40333059 | 40544497 | 48434864
MCR015417 | HPR112 | 2022-09-01 | Material | 100772636 | 101300918 | 103398834
MCR015418 | HPR112 | 2022-09-01 | Equipment | 28458354 | 28607542 | 29229873
MCR015419 | HPR112 | 2022-09-01 | Subcontract | 150208647 | 150996088 | 125241205
MCR015420 | HPR112 | 2022-09-01 | Overhead | 34945278 | 35128472 | 22302461
MCR015421 | HPR112 | 2022-10-01 | Labor | 36280016 | 31124852 | 33758840
MCR015422 | HPR112 | 2022-10-01 | Material | 90646060 | 77765819 | 99040548
MCR015423 | HPR112 | 2022-10-01 | Equipment | 25598593 | 21961192 | 22552167
MCR015424 | HPR112 | 2022-10-01 | Subcontract | 135114279 | 115915380 | 128861165
MCR015425 | HPR112 | 2022-10-01 | Overhead | 31433650 | 26967124 | 25173019
MCR015426 | HPR112 | 2022-11-01 | Labor | 30892862 | 18679449 | 20580295
MCR015427 | HPR112 | 2022-11-01 | Material | 77186189 | 46670831 | 35751830
MCR015428 | HPR112 | 2022-11-01 | Equipment | 21797503 | 13179917 | 11396484
MCR015429 | HPR112 | 2022-11-01 | Subcontract | 115051401 | 69566130 | 68233145
MCR015430 | HPR112 | 2022-11-01 | Overhead | 26766123 | 16184206 | 23313397
MCR015431 | HPR112 | 2022-12-01 | Labor | 24408105 | 44183432 | 48271636
MCR015432 | HPR112 | 2022-12-01 | Material | 60983946 | 110392840 | 109086939
MCR015433 | HPR112 | 2022-12-01 | Equipment | 17221964 | 31175115 | 39011634
MCR015434 | HPR112 | 2022-12-01 | Subcontract | 90900828 | 164548232 | 179490758
MCR015435 | HPR112 | 2022-12-01 | Overhead | 21147615 | 38281309 | 23780914
MCR015436 | HPR112 | 2023-01-01 | Labor | 17139543 | 30176341 | 36253780
MCR015437 | HPR112 | 2023-01-01 | Material | 42823355 | 75395953 | 86684432
MCR015438 | HPR112 | 2023-01-01 | Equipment | 12093384 | 21291938 | 18723192
MCR015439 | HPR112 | 2023-01-01 | Subcontract | 63831199 | 112382930 | 104421620
MCR015440 | HPR112 | 2023-01-01 | Overhead | 14850004 | 26145317 | 26069524
MCR015441 | HPR112 | 2023-02-01 | Labor | 9555015 | 24494186 | 24603822
MCR015442 | HPR112 | 2023-02-01 | Material | 23873321 | 61199019 | 56348253
MCR015443 | HPR112 | 2023-02-01 | Equipment | 6741864 | 17282701 | 17989206
MCR015444 | HPR112 | 2023-02-01 | Subcontract | 35584851 | 91221410 | 131976155
MCR015445 | HPR112 | 2023-02-01 | Overhead | 8278635 | 21222197 | 25160249
MCR015446 | HPR112 | 2023-03-01 | Labor | 2593224 | 23155306 | 25799486
MCR015447 | HPR112 | 2023-03-01 | Material | 6479201 | 57853812 | 60933111
MCR015448 | HPR112 | 2023-03-01 | Equipment | 1829737 | 16338009 | 14114943
MCR015449 | HPR112 | 2023-03-01 | Subcontract | 9657701 | 86235145 | 135183096
MCR015450 | HPR112 | 2023-03-01 | Overhead | 2246815 | 20062168 | 27182139
MCR015451 | HPR112 | 2023-04-01 | Labor | 0 | 11394080 | 13912664
MCR015452 | HPR112 | 2023-04-01 | Material | 0 | 28468248 | 29964822
MCR015453 | HPR112 | 2023-04-01 | Equipment | 0 | 8039479 | 9796084
MCR015454 | HPR112 | 2023-04-01 | Subcontract | 0 | 42433911 | 62956925
MCR015455 | HPR112 | 2023-04-01 | Overhead | 0 | 9872033 | 25728565
MCR015456 | HPR112 | 2023-05-01 | Labor | 0 | 17433578 | 20826963
MCR015457 | HPR112 | 2023-05-01 | Material | 0 | 43558006 | 42762693
MCR015458 | HPR112 | 2023-05-01 | Equipment | 0 | 12300851 | 13103118
MCR015459 | HPR112 | 2023-05-01 | Subcontract | 0 | 64926247 | 89883989
MCR015460 | HPR112 | 2023-05-01 | Overhead | 0 | 15104761 | 25467582
MCR015461 | HPR112 | 2023-06-01 | Labor | 0 | 12408148 | 13057107
MCR015462 | HPR112 | 2023-06-01 | Material | 0 | 31001908 | 29591675
MCR015463 | HPR112 | 2023-06-01 | Equipment | 0 | 8754988 | 9600745
MCR015464 | HPR112 | 2023-06-01 | Subcontract | 0 | 46210507 | 90874121
MCR015465 | HPR112 | 2023-06-01 | Overhead | 0 | 10750639 | 22187842
MCR015466 | HPR112 | 2023-07-01 | Labor | 0 | 3493476 | 4070437
MCR015467 | HPR112 | 2023-07-01 | Material | 0 | 8728492 | 10083444
MCR015468 | HPR112 | 2023-07-01 | Equipment | 0 | 2464940 | 2326612
MCR015469 | HPR112 | 2023-07-01 | Subcontract | 0 | 13010426 | 46019977
MCR015470 | HPR112 | 2023-07-01 | Overhead | 0 | 3026809 | 25920887
MCR015471 | HPR112 | 2023-08-01 | Labor | 0 | 803679 | 870870
MCR015472 | HPR112 | 2023-08-01 | Material | 0 | 2008003 | 1817893
MCR015473 | HPR112 | 2023-08-01 | Equipment | 0 | 567063 | 950657
MCR015474 | HPR112 | 2023-08-01 | Subcontract | 0 | 2993068 | 40857634
MCR015475 | HPR112 | 2023-08-01 | Overhead | 0 | 696322 | 24360663
MCR015476 | HPR113 | 2019-03-01 | Labor | 6030381 | 7015954 | 6352444
MCR015477 | HPR113 | 2019-03-01 | Material | 15613241 | 18164983 | 16729515
MCR015478 | HPR113 | 2019-03-01 | Equipment | 2630123 | 3059976 | 3077772
MCR015479 | HPR113 | 2019-03-01 | Subcontract | 32467116 | 37773362 | 41483617
MCR015480 | HPR113 | 2019-03-01 | Overhead | 5893450 | 6856642 | 30397600
MCR015481 | HPR113 | 2019-04-01 | Labor | 16822232 | 14907600 | 15101605
MCR015482 | HPR113 | 2019-04-01 | Material | 43554386 | 38597219 | 38357211
MCR015483 | HPR113 | 2019-04-01 | Equipment | 7336939 | 6501881 | 5697661
MCR015484 | HPR113 | 2019-04-01 | Subcontract | 90569617 | 80261385 | 81459934
MCR015485 | HPR113 | 2019-04-01 | Overhead | 16440249 | 14569093 | 27629900
MCR015486 | HPR113 | 2019-05-01 | Labor | 25752072 | 22285799 | 24532451
MCR015487 | HPR113 | 2019-05-01 | Material | 66674608 | 57700091 | 52097243
MCR015488 | HPR113 | 2019-05-01 | Equipment | 11231648 | 9719849 | 10289447
MCR015489 | HPR113 | 2019-05-01 | Subcontract | 138647201 | 119985048 | 125100552
MCR015490 | HPR113 | 2019-05-01 | Overhead | 25167320 | 21779755 | 25413762
MCR015491 | HPR113 | 2019-06-01 | Labor | 32877880 | 22704422 | 18720856
MCR015492 | HPR113 | 2019-06-01 | Material | 85124015 | 58783946 | 66709133
MCR015493 | HPR113 | 2019-06-01 | Equipment | 14339537 | 9902430 | 9888243
MCR015494 | HPR113 | 2019-06-01 | Subcontract | 177012010 | 122238883 | 127164139
MCR015495 | HPR113 | 2019-06-01 | Overhead | 32131322 | 22188872 | 25619297
MCR015496 | HPR113 | 2019-07-01 | Labor | 38261632 | 27594674 | 28344412
MCR015497 | HPR113 | 2019-07-01 | Material | 99063070 | 71445282 | 71192161
MCR015498 | HPR113 | 2019-07-01 | Equipment | 16687636 | 12035291 | 11993979
MCR015499 | HPR113 | 2019-07-01 | Subcontract | 205997722 | 148567628 | 158321525
MCR015500 | HPR113 | 2019-07-01 | Overhead | 37392825 | 26968082 | 28378596
MCR015501 | HPR113 | 2019-08-01 | Labor | 41969982 | 22033854 | 25414504
MCR015502 | HPR113 | 2019-08-01 | Material | 108664347 | 57047780 | 55010981
MCR015503 | HPR113 | 2019-08-01 | Equipment | 18305016 | 9609964 | 12687284
MCR015504 | HPR113 | 2019-08-01 | Subcontract | 225963196 | 118628594 | 126953257
MCR015505 | HPR113 | 2019-08-01 | Overhead | 41016970 | 21533531 | 24998762
MCR015506 | HPR113 | 2019-09-01 | Labor | 44075130 | 41042756 | 36845540
MCR015507 | HPR113 | 2019-09-01 | Material | 114114777 | 106263668 | 101988597
MCR015508 | HPR113 | 2019-09-01 | Equipment | 19223166 | 17900610 | 18409078
MCR015509 | HPR113 | 2019-09-01 | Subcontract | 237297149 | 220971080 | 233335687
MCR015510 | HPR113 | 2019-09-01 | Overhead | 43074315 | 40110798 | 26376184
MCR015511 | HPR113 | 2019-10-01 | Labor | 44655955 | 34478172 | 35117141
MCR015512 | HPR113 | 2019-10-01 | Material | 115618591 | 89267326 | 96298797
MCR015513 | HPR113 | 2019-10-01 | Equipment | 19476490 | 15037497 | 16160038
MCR015514 | HPR113 | 2019-10-01 | Subcontract | 240424270 | 185627862 | 193786557
MCR015515 | HPR113 | 2019-10-01 | Overhead | 43641952 | 33695276 | 27995424
MCR015516 | HPR113 | 2019-11-01 | Labor | 43799549 | 25683595 | 27616528
MCR015517 | HPR113 | 2019-11-01 | Material | 113401272 | 66497314 | 59799598
MCR015518 | HPR113 | 2019-11-01 | Equipment | 19102973 | 11201782 | 10743275
MCR015519 | HPR113 | 2019-11-01 | Subcontract | 235813444 | 138278525 | 140613337
MCR015520 | HPR113 | 2019-11-01 | Overhead | 42804992 | 25100398 | 27324874
MCR015521 | HPR113 | 2019-12-01 | Labor | 41603326 | 33378991 | 31811959
MCR015522 | HPR113 | 2019-12-01 | Material | 107715038 | 86421438 | 89509791
MCR015523 | HPR113 | 2019-12-01 | Equipment | 18145100 | 14558094 | 13434958
MCR015524 | HPR113 | 2019-12-01 | Subcontract | 223989146 | 179709950 | 183087412
MCR015525 | HPR113 | 2019-12-01 | Overhead | 40658639 | 32621054 | 28201202
MCR015526 | HPR113 | 2020-01-01 | Labor | 38178080 | 38532610 | 42662232
MCR015527 | HPR113 | 2020-01-01 | Material | 98846744 | 99764658 | 89229724
MCR015528 | HPR113 | 2020-01-01 | Equipment | 16651195 | 16805821 | 17149733
MCR015529 | HPR113 | 2020-01-01 | Subcontract | 205547880 | 207456646 | 218153204
MCR015530 | HPR113 | 2020-01-01 | Overhead | 37311170 | 37657650 | 28109929
MCR015531 | HPR113 | 2020-02-01 | Labor | 33652601 | 29017378 | 26218760
MCR015532 | HPR113 | 2020-02-01 | Material | 87129841 | 75128800 | 83099919
MCR015533 | HPR113 | 2020-02-01 | Equipment | 14677428 | 12655796 | 13952520
MCR015534 | HPR113 | 2020-02-01 | Subcontract | 181183047 | 156227357 | 159598623
MCR015535 | HPR113 | 2020-02-01 | Overhead | 32888451 | 28358480 | 28392326
MCR015536 | HPR113 | 2020-03-01 | Labor | 28181135 | 53367792 | 61743190
MCR015537 | HPR113 | 2020-03-01 | Material | 72963686 | 138174381 | 140383479
MCR015538 | HPR113 | 2020-03-01 | Equipment | 12291073 | 23276118 | 22702907
MCR015539 | HPR113 | 2020-03-01 | Subcontract | 151725088 | 287328141 | 275459049
MCR015540 | HPR113 | 2020-03-01 | Overhead | 27541225 | 52155970 | 27313867
MCR015541 | HPR113 | 2020-04-01 | Labor | 21956516 | 28903793 | 31042703
MCR015542 | HPR113 | 2020-04-01 | Material | 56847546 | 74834718 | 76175230
MCR015543 | HPR113 | 2020-04-01 | Equipment | 9576234 | 12606257 | 14817528
MCR015544 | HPR113 | 2020-04-01 | Subcontract | 118212214 | 155615826 | 241675060
MCR015545 | HPR113 | 2020-04-01 | Overhead | 21457949 | 28247474 | 30647624
MCR015546 | HPR113 | 2020-05-01 | Labor | 15236491 | 27194569 | 23944765
MCR015547 | HPR113 | 2020-05-01 | Material | 39448751 | 70409372 | 75294664
MCR015548 | HPR113 | 2020-05-01 | Equipment | 6645326 | 11860787 | 10859379
MCR015549 | HPR113 | 2020-05-01 | Subcontract | 82032113 | 146413495 | 227634583
MCR015550 | HPR113 | 2020-05-01 | Overhead | 14890516 | 26577062 | 25377524
MCR015551 | HPR113 | 2020-06-01 | Labor | 8409068 | 18343849 | 20621444
MCR015552 | HPR113 | 2020-06-01 | Material | 21771890 | 47494002 | 57461880
MCR015553 | HPR113 | 2020-06-01 | Equipment | 3667576 | 8000586 | 7884946
MCR015554 | HPR113 | 2020-06-01 | Subcontract | 45273781 | 98761892 | 167072348
MCR015555 | HPR113 | 2020-06-01 | Overhead | 8218123 | 17927316 | 30500606
MCR015556 | HPR113 | 2020-07-01 | Labor | 2264125 | 14126397 | 15390251
MCR015557 | HPR113 | 2020-07-01 | Material | 5862039 | 36574610 | 29402038
MCR015558 | HPR113 | 2020-07-01 | Equipment | 987488 | 6161163 | 6233661
MCR015559 | HPR113 | 2020-07-01 | Subcontract | 12189877 | 76055449 | 110544293
MCR015560 | HPR113 | 2020-07-01 | Overhead | 2212714 | 13805629 | 27535739
MCR015561 | HPR113 | 2020-08-01 | Labor | 0 | 12401632 | 11273537
MCR015562 | HPR113 | 2020-08-01 | Material | 0 | 32109026 | 32484632
MCR015563 | HPR113 | 2020-08-01 | Equipment | 0 | 5408915 | 5471205
MCR015564 | HPR113 | 2020-08-01 | Subcontract | 0 | 66769445 | 135217579
MCR015565 | HPR113 | 2020-08-01 | Overhead | 0 | 12120028 | 25535264
MCR015566 | HPR113 | 2020-09-01 | Labor | 0 | 9623235 | 10229941
MCR015567 | HPR113 | 2020-09-01 | Material | 0 | 24915487 | 26430034
MCR015568 | HPR113 | 2020-09-01 | Equipment | 0 | 4197130 | 5049797
MCR015569 | HPR113 | 2020-09-01 | Subcontract | 0 | 51810765 | 77058920
MCR015570 | HPR113 | 2020-09-01 | Overhead | 0 | 9404720 | 25654341
MCR015571 | HPR113 | 2020-10-01 | Labor | 0 | 1089083 | 635117
MCR015572 | HPR113 | 2020-10-01 | Material | 0 | 2819741 | 2586110
MCR015573 | HPR113 | 2020-10-01 | Equipment | 0 | 474999 | 18136
MCR015574 | HPR113 | 2020-10-01 | Subcontract | 0 | 5863540 | 79162333
MCR015575 | HPR113 | 2020-10-01 | Overhead | 0 | 1064353 | 26200061
MCR015576 | HPR114 | 2017-07-01 | Labor | 11616870 | 6693172 | 7357018
MCR015577 | HPR114 | 2017-07-01 | Material | 26610219 | 15331735 | 15913023
MCR015578 | HPR114 | 2017-07-01 | Equipment | 5177114 | 2982844 | 2929279
MCR015579 | HPR114 | 2017-07-01 | Subcontract | 27255751 | 15703664 | 14132805
MCR015580 | HPR114 | 2017-07-01 | Overhead | 6140861 | 3538117 | 27577921
MCR015581 | HPR114 | 2017-08-01 | Labor | 31862189 | 18520690 | 17433804
MCR015582 | HPR114 | 2017-08-01 | Material | 72985223 | 42424476 | 40334553
MCR015583 | HPR114 | 2017-08-01 | Equipment | 14199537 | 8253834 | 8467620
MCR015584 | HPR114 | 2017-08-01 | Subcontract | 74755757 | 43453643 | 42942182
MCR015585 | HPR114 | 2017-08-01 | Overhead | 16842858 | 9790330 | 27160204
MCR015586 | HPR114 | 2017-09-01 | Labor | 47745629 | 21152632 | 26462739
MCR015587 | HPR114 | 2017-09-01 | Material | 109368675 | 48453342 | 52555740
MCR015588 | HPR114 | 2017-09-01 | Equipment | 21278068 | 9426772 | 10427069
MCR015589 | HPR114 | 2017-09-01 | Subcontract | 112021828 | 49628762 | 48245216
MCR015590 | HPR114 | 2017-09-01 | Overhead | 25239096 | 11181616 | 21963528
MCR015591 | HPR114 | 2017-10-01 | Labor | 59438607 | 30856465 | 32336787
MCR015592 | HPR114 | 2017-10-01 | Material | 136153233 | 70681459 | 75195038
MCR015593 | HPR114 | 2017-10-01 | Equipment | 26489100 | 13751331 | 13777098
MCR015594 | HPR114 | 2017-10-01 | Subcontract | 139456146 | 72396106 | 76388214
MCR015595 | HPR114 | 2017-10-01 | Overhead | 31420190 | 16311217 | 22806514
MCR015596 | HPR114 | 2017-11-01 | Labor | 67127746 | 49463711 | 56341780
MCR015597 | HPR114 | 2017-11-01 | Material | 153766383 | 113304206 | 124966160
MCR015598 | HPR114 | 2017-11-01 | Equipment | 29915802 | 22043740 | 25030209
MCR015599 | HPR114 | 2017-11-01 | Subcontract | 157496571 | 116052830 | 107476081
MCR015600 | HPR114 | 2017-11-01 | Overhead | 35484791 | 26147302 | 26323244
MCR015601 | HPR114 | 2017-12-01 | Labor | 71018268 | 41094787 | 40052436
MCR015602 | HPR114 | 2017-12-01 | Material | 162678219 | 94133903 | 85347880
MCR015603 | HPR114 | 2017-12-01 | Equipment | 31649631 | 18314089 | 18437195
MCR015604 | HPR114 | 2017-12-01 | Subcontract | 166624597 | 96417478 | 102085174
MCR015605 | HPR114 | 2017-12-01 | Overhead | 37541382 | 21723356 | 23962182
MCR015606 | HPR114 | 2018-01-01 | Labor | 71338672 | 57558213 | 60386050
MCR015607 | HPR114 | 2018-01-01 | Material | 163412154 | 131845903 | 150515757
MCR015608 | HPR114 | 2018-01-01 | Equipment | 31792421 | 25651093 | 24437969
MCR015609 | HPR114 | 2018-01-01 | Subcontract | 167376337 | 135044326 | 127634111
MCR015610 | HPR114 | 2018-01-01 | Overhead | 37710753 | 30426184 | 24447840
MCR015611 | HPR114 | 2018-02-01 | Labor | 68347457 | 39483670 | 34748491
MCR015612 | HPR114 | 2018-02-01 | Material | 156560317 | 90443393 | 80342348
MCR015613 | HPR114 | 2018-02-01 | Equipment | 30459371 | 17596087 | 18767892
MCR015614 | HPR114 | 2018-02-01 | Subcontract | 160358282 | 92637441 | 91260069
MCR015615 | HPR114 | 2018-02-01 | Overhead | 36129549 | 20871694 | 24951657
MCR015616 | HPR114 | 2018-03-01 | Labor | 62343228 | 59124575 | 69496879
MCR015617 | HPR114 | 2018-03-01 | Material | 142806711 | 135433893 | 145402635
MCR015618 | HPR114 | 2018-03-01 | Equipment | 27783558 | 26349150 | 26341596
MCR015619 | HPR114 | 2018-03-01 | Subcontract | 146271030 | 138719357 | 142578531
MCR015620 | HPR114 | 2018-03-01 | Overhead | 32955618 | 31254187 | 23893519
MCR015621 | HPR114 | 2018-04-01 | Labor | 53680935 | 77067795 | 74598574
MCR015622 | HPR114 | 2018-04-01 | Material | 122964402 | 176535588 | 178002984
MCR015623 | HPR114 | 2018-04-01 | Equipment | 23923166 | 34345632 | 39629776
MCR015624 | HPR114 | 2018-04-01 | Subcontract | 125947371 | 180818129 | 165532076
MCR015625 | HPR114 | 2018-04-01 | Overhead | 28376593 | 40739258 | 24102473
MCR015626 | HPR114 | 2018-05-01 | Labor | 42800285 | 40601232 | 44352427
MCR015627 | HPR114 | 2018-05-01 | Material | 98040608 | 93003340 | 82444686
MCR015628 | HPR114 | 2018-05-01 | Equipment | 19074152 | 18094134 | 17394514
MCR015629 | HPR114 | 2018-05-01 | Subcontract | 100418955 | 95259490 | 87330316
MCR015630 | HPR114 | 2018-05-01 | Overhead | 22624909 | 21462455 | 23570582
MCR015631 | HPR114 | 2018-06-01 | Labor | 30282289 | 41164513 | 44773784
MCR015632 | HPR114 | 2018-06-01 | Material | 69366221 | 94293621 | 102998609
MCR015633 | HPR114 | 2018-06-01 | Equipment | 13495447 | 18345162 | 22702924
MCR015634 | HPR114 | 2018-06-01 | Subcontract | 71048962 | 96581071 | 91431358
MCR015635 | HPR114 | 2018-06-01 | Overhead | 16007698 | 21760214 | 23544161
MCR015636 | HPR114 | 2018-07-01 | Labor | 16988502 | 28981607 | 27992066
MCR015637 | HPR114 | 2018-07-01 | Material | 38914766 | 66386810 | 72629984
MCR015638 | HPR114 | 2018-07-01 | Equipment | 7571007 | 12915792 | 11052193
MCR015639 | HPR114 | 2018-07-01 | Subcontract | 39858792 | 67997274 | 93159109
MCR015640 | HPR114 | 2018-07-01 | Overhead | 8980392 | 15320137 | 23696369
MCR015641 | HPR114 | 2018-08-01 | Labor | 4633350 | 31864970 | 32603272
MCR015642 | HPR114 | 2018-08-01 | Material | 10613397 | 72991594 | 74992854
MCR015643 | HPR114 | 2018-08-01 | Equipment | 2064875 | 14200777 | 16212581
MCR015644 | HPR114 | 2018-08-01 | Subcontract | 10870866 | 74762282 | 103768367
MCR015645 | HPR114 | 2018-08-01 | Overhead | 2449262 | 16844328 | 25531828
MCR015646 | HPR114 | 2018-09-01 | Labor | 0 | 46120268 | 43796501
MCR015647 | HPR114 | 2018-09-01 | Material | 0 | 105645537 | 103463711
MCR015648 | HPR114 | 2018-09-01 | Equipment | 0 | 20553718 | 21782740
MCR015649 | HPR114 | 2018-09-01 | Subcontract | 0 | 108208371 | 124280588
MCR015650 | HPR114 | 2018-09-01 | Overhead | 0 | 24379905 | 23551479
MCR015651 | HPR114 | 2018-10-01 | Labor | 0 | 15507910 | 17654371
MCR015652 | HPR114 | 2018-10-01 | Material | 0 | 35523242 | 42688143
MCR015653 | HPR114 | 2018-10-01 | Equipment | 0 | 6911174 | 7094325
MCR015654 | HPR114 | 2018-10-01 | Subcontract | 0 | 36384994 | 71447482
MCR015655 | HPR114 | 2018-10-01 | Overhead | 0 | 8197727 | 23739328
MCR015656 | HPR114 | 2018-11-01 | Labor | 0 | 19384408 | 16556073
MCR015657 | HPR114 | 2018-11-01 | Material | 0 | 44402955 | 45238317
MCR015658 | HPR114 | 2018-11-01 | Equipment | 0 | 8638754 | 10002084
MCR015659 | HPR114 | 2018-11-01 | Subcontract | 0 | 45480117 | 62883919
MCR015660 | HPR114 | 2018-11-01 | Overhead | 0 | 10246905 | 24266735
MCR015661 | HPR114 | 2018-12-01 | Labor | 0 | 10908542 | 13933758
MCR015662 | HPR114 | 2018-12-01 | Material | 0 | 24987687 | 24133661
MCR015663 | HPR114 | 2018-12-01 | Equipment | 0 | 4861444 | 5394072
MCR015664 | HPR114 | 2018-12-01 | Subcontract | 0 | 25593858 | 58126140
MCR015665 | HPR114 | 2018-12-01 | Overhead | 0 | 5766428 | 25916615
MCR015666 | HPR114 | 2019-01-01 | Labor | 0 | 3674866 | 3039652
MCR015667 | HPR114 | 2019-01-01 | Material | 0 | 8417844 | 8094836
MCR015668 | HPR114 | 2019-01-01 | Equipment | 0 | 1637722 | 2250321
MCR015669 | HPR114 | 2019-01-01 | Subcontract | 0 | 8622050 | 54387645
MCR015670 | HPR114 | 2019-01-01 | Overhead | 0 | 1942592 | 24637858
MCR015671 | HPR115 | 2022-08-01 | Labor | 12208350 | 6066367 | 6950034
MCR015672 | HPR115 | 2022-08-01 | Material | 25941122 | 12890224 | 12679055
MCR015673 | HPR115 | 2022-08-01 | Equipment | 4539591 | 2255737 | 2482793
MCR015674 | HPR115 | 2022-08-01 | Subcontract | 22645623 | 11252681 | 12787400
MCR015675 | HPR115 | 2022-08-01 | Overhead | 5895492 | 2929489 | 22236926
MCR015676 | HPR115 | 2022-09-01 | Labor | 33484472 | 21552162 | 24038377
MCR015677 | HPR115 | 2022-09-01 | Material | 71150057 | 45795482 | 46687658
MCR015678 | HPR115 | 2022-09-01 | Equipment | 12450971 | 8014024 | 8521512
MCR015679 | HPR115 | 2022-09-01 | Subcontract | 62111322 | 39977732 | 36256003
MCR015680 | HPR115 | 2022-09-01 | Overhead | 16169872 | 10407681 | 24540783
MCR015681 | HPR115 | 2022-10-01 | Labor | 50176627 | 59872561 | 70380203
MCR015682 | HPR115 | 2022-10-01 | Material | 106618671 | 127221242 | 114752436
MCR015683 | HPR115 | 2022-10-01 | Equipment | 18657835 | 22263202 | 25075698
MCR015684 | HPR115 | 2022-10-01 | Subcontract | 93074087 | 111059356 | 126821488
MCR015685 | HPR115 | 2022-10-01 | Overhead | 24230624 | 28912854 | 21779067
MCR015686 | HPR115 | 2022-11-01 | Labor | 62464960 | 30351145 | 30124471
MCR015687 | HPR115 | 2022-11-01 | Material | 132729747 | 64492154 | 80773459
MCR015688 | HPR115 | 2022-11-01 | Equipment | 23227168 | 11285866 | 10305759
MCR015689 | HPR115 | 2022-11-01 | Subcontract | 115868074 | 56299224 | 58513385
MCR015690 | HPR115 | 2022-11-01 | Overhead | 30164741 | 14656768 | 24961647
MCR015691 | HPR115 | 2022-12-01 | Labor | 70545597 | 44395009 | 47145947
MCR015692 | HPR115 | 2022-12-01 | Material | 149900027 | 94333501 | 84688127
MCR015693 | HPR115 | 2022-12-01 | Equipment | 26231897 | 16507980 | 17066105
MCR015694 | HPR115 | 2022-12-01 | Subcontract | 130857082 | 82349595 | 95537155
MCR015695 | HPR115 | 2022-12-01 | Overhead | 34066933 | 21438642 | 23706200
MCR015696 | HPR115 | 2023-01-01 | Labor | 74634206 | 48980384 | 61264174
MCR015697 | HPR115 | 2023-01-01 | Material | 158587780 | 104076812 | 110219553
MCR015698 | HPR115 | 2023-01-01 | Equipment | 27752218 | 18213020 | 17464960
MCR015699 | HPR115 | 2023-01-01 | Subcontract | 138441163 | 90855140 | 92726087
MCR015700 | HPR115 | 2023-01-01 | Overhead | 36041350 | 23652950 | 23395002
MCR015701 | HPR115 | 2023-02-01 | Labor | 74970925 | 47702370 | 56776686
MCR015702 | HPR115 | 2023-02-01 | Material | 159303261 | 101361204 | 117256854
MCR015703 | HPR115 | 2023-02-01 | Equipment | 27877425 | 17737800 | 19141460
MCR015704 | HPR115 | 2023-02-01 | Subcontract | 139065751 | 88484516 | 91988049
MCR015705 | HPR115 | 2023-02-01 | Overhead | 36203953 | 23035789 | 23249996
MCR015706 | HPR115 | 2023-03-01 | Labor | 71827409 | 38563621 | 44688958
MCR015707 | HPR115 | 2023-03-01 | Material | 152623708 | 81942574 | 59578860
MCR015708 | HPR115 | 2023-03-01 | Equipment | 26708530 | 14339618 | 14702055
MCR015709 | HPR115 | 2023-03-01 | Subcontract | 133234753 | 71532783 | 79436192
MCR015710 | HPR115 | 2023-03-01 | Overhead | 34685929 | 18622626 | 23017057
MCR015711 | HPR115 | 2023-04-01 | Labor | 65517472 | 65168379 | 69310022
MCR015712 | HPR115 | 2023-04-01 | Material | 139215928 | 138474153 | 144471431
MCR015713 | HPR115 | 2023-04-01 | Equipment | 24362223 | 24232415 | 25123118
MCR015714 | HPR115 | 2023-04-01 | Subcontract | 121530266 | 120882724 | 130954138
MCR015715 | HPR115 | 2023-04-01 | Overhead | 31638819 | 31470239 | 22354178
MCR015716 | HPR115 | 2023-05-01 | Labor | 56414133 | 32297361 | 35803737
MCR015717 | HPR115 | 2023-05-01 | Material | 119872542 | 68627605 | 70862417
MCR015718 | HPR115 | 2023-05-01 | Equipment | 20977209 | 12009553 | 12645479
MCR015719 | HPR115 | 2023-05-01 | Subcontract | 104644217 | 59909316 | 65170479
MCR015720 | HPR115 | 2023-05-01 | Overhead | 27242756 | 15596609 | 24539246
MCR015721 | HPR115 | 2023-06-01 | Labor | 44979488 | 54999801 | 63693909
MCR015722 | HPR115 | 2023-06-01 | Material | 95575440 | 116867274 | 112146984
MCR015723 | HPR115 | 2023-06-01 | Equipment | 16725314 | 20451299 | 22189881
MCR015724 | HPR115 | 2023-06-01 | Subcontract | 83433762 | 102020732 | 104082120
MCR015725 | HPR115 | 2023-06-01 | Overhead | 21720891 | 26559766 | 23333389
MCR015726 | HPR115 | 2023-07-01 | Labor | 31824130 | 29921951 | 33107479
MCR015727 | HPR115 | 2023-07-01 | Material | 67622052 | 63580173 | 64137968
MCR015728 | HPR115 | 2023-07-01 | Equipment | 11833585 | 11126272 | 11284577
MCR015729 | HPR115 | 2023-07-01 | Subcontract | 59031506 | 55503098 | 59931162
MCR015730 | HPR115 | 2023-07-01 | Overhead | 15368082 | 14449507 | 22922658
MCR015731 | HPR115 | 2023-08-01 | Labor | 17853482 | 35847972 | 36528546
MCR015732 | HPR115 | 2023-08-01 | Material | 37936280 | 76172182 | 86385039
MCR015733 | HPR115 | 2023-08-01 | Equipment | 6638695 | 13329823 | 16172223
MCR015734 | HPR115 | 2023-08-01 | Subcontract | 33116944 | 66495448 | 61503192
MCR015735 | HPR115 | 2023-08-01 | Overhead | 8621564 | 17311222 | 23110602
MCR015736 | HPR115 | 2023-09-01 | Labor | 4869260 | 55699367 | 60089482
MCR015737 | HPR115 | 2023-09-01 | Material | 10346530 | 118353759 | 88352002
MCR015738 | HPR115 | 2023-09-01 | Equipment | 1810601 | 20711428 | 24646999
MCR015739 | HPR115 | 2023-09-01 | Subcontract | 9032132 | 103318377 | 146519188
MCR015740 | HPR115 | 2023-09-01 | Overhead | 2351398 | 26897591 | 22434825
MCR015741 | HPR115 | 2023-10-01 | Labor | 0 | 27778857 | 35723268
MCR015742 | HPR115 | 2023-10-01 | Material | 0 | 59026383 | 72326252
MCR015743 | HPR115 | 2023-10-01 | Equipment | 0 | 10329378 | 8671340
MCR015744 | HPR115 | 2023-10-01 | Subcontract | 0 | 51527810 | 91665028
MCR015745 | HPR115 | 2023-10-01 | Overhead | 0 | 13414593 | 22056944
MCR015746 | HPR115 | 2023-11-01 | Labor | 0 | 25678667 | 30098786
MCR015747 | HPR115 | 2023-11-01 | Material | 0 | 54563758 | 46761414
MCR015748 | HPR115 | 2023-11-01 | Equipment | 0 | 9548436 | 10849871
MCR015749 | HPR115 | 2023-11-01 | Subcontract | 0 | 47632107 | 88235702
MCR015750 | HPR115 | 2023-11-01 | Overhead | 0 | 12400397 | 21655289
MCR015751 | HPR115 | 2023-12-01 | Labor | 0 | 15693990 | 18927960
MCR015752 | HPR115 | 2023-12-01 | Material | 0 | 33347646 | 37661027
MCR015753 | HPR115 | 2023-12-01 | Equipment | 0 | 5835703 | 5922642
MCR015754 | HPR115 | 2023-12-01 | Subcontract | 0 | 29111240 | 70656043
MCR015755 | HPR115 | 2023-12-01 | Overhead | 0 | 7578731 | 22398398
MCR015756 | HPR115 | 2024-01-01 | Labor | 0 | 18884933 | 21201060
MCR015757 | HPR115 | 2024-01-01 | Material | 0 | 40127975 | 44629242
MCR015758 | HPR115 | 2024-01-01 | Equipment | 0 | 7022233 | 8872002
MCR015759 | HPR115 | 2024-01-01 | Subcontract | 0 | 35030212 | 54434940
MCR015760 | HPR115 | 2024-01-01 | Overhead | 0 | 9119659 | 21908352
MCR015761 | HPR115 | 2024-02-01 | Labor | 0 | 9702786 | 10887399
MCR015762 | HPR115 | 2024-02-01 | Material | 0 | 20617132 | 17499744
MCR015763 | HPR115 | 2024-02-01 | Equipment | 0 | 3607914 | 3726061
MCR015764 | HPR115 | 2024-02-01 | Subcontract | 0 | 17997980 | 44436491
MCR015765 | HPR115 | 2024-02-01 | Overhead | 0 | 4685539 | 21517304
MCR015766 | HPR115 | 2024-03-01 | Labor | 0 | 2612827 | 3194634
MCR015767 | HPR115 | 2024-03-01 | Material | 0 | 5551911 | 5570497
MCR015768 | HPR115 | 2024-03-01 | Equipment | 0 | 971562 | 1681832
MCR015769 | HPR115 | 2024-03-01 | Subcontract | 0 | 4846609 | 19593465
MCR015770 | HPR115 | 2024-03-01 | Overhead | 0 | 1261751 | 23425822
MCR015771 | HPR116 | 2020-06-01 | Labor | 2869666 | 3917243 | 4000155
MCR015772 | HPR116 | 2020-06-01 | Material | 8903303 | 12153473 | 12589034
MCR015773 | HPR116 | 2020-06-01 | Equipment | 2513986 | 3431722 | 3201619
MCR015774 | HPR116 | 2020-06-01 | Subcontract | 8990378 | 12272334 | 12586443
MCR015775 | HPR116 | 2020-06-01 | Overhead | 1879385 | 2565458 | 10195209
MCR015776 | HPR116 | 2020-07-01 | Labor | 8123107 | 4558658 | 4951047
MCR015777 | HPR116 | 2020-07-01 | Material | 25202410 | 14143499 | 14852385
MCR015778 | HPR116 | 2020-07-01 | Equipment | 7116293 | 3993637 | 4622188
MCR015779 | HPR116 | 2020-07-01 | Subcontract | 25448890 | 14281823 | 15650454
MCR015780 | HPR116 | 2020-07-01 | Overhead | 5319938 | 2985529 | 10407952
MCR015781 | HPR116 | 2020-08-01 | Labor | 12660307 | 7045124 | 6551064
MCR015782 | HPR116 | 2020-08-01 | Material | 39279336 | 21857903 | 21199881
MCR015783 | HPR116 | 2020-08-01 | Equipment | 11091132 | 6171919 | 6567641
MCR015784 | HPR116 | 2020-08-01 | Subcontract | 39663488 | 22071674 | 24032191
MCR015785 | HPR116 | 2020-08-01 | Overhead | 8291414 | 4613951 | 10006376
MCR015786 | HPR116 | 2020-09-01 | Labor | 16498731 | 17160456 | 18180881
MCR015787 | HPR116 | 2020-09-01 | Material | 51188269 | 53241308 | 53462567
MCR015788 | HPR116 | 2020-09-01 | Equipment | 14453804 | 15033512 | 14052711
MCR015789 | HPR116 | 2020-09-01 | Subcontract | 51688890 | 53762008 | 47287059
MCR015790 | HPR116 | 2020-09-01 | Overhead | 10805253 | 11238626 | 10519889
MCR015791 | HPR116 | 2020-10-01 | Labor | 19656775 | 11879014 | 10890457
MCR015792 | HPR116 | 2020-10-01 | Material | 60986281 | 36855328 | 39363707
MCR015793 | HPR116 | 2020-10-01 | Equipment | 17220426 | 10406675 | 13170413
MCR015794 | HPR116 | 2020-10-01 | Subcontract | 61582728 | 37215773 | 43335831
MCR015795 | HPR116 | 2020-10-01 | Overhead | 12873500 | 7779734 | 10652239
MCR015796 | HPR116 | 2020-11-01 | Labor | 22153882 | 11010170 | 12754465
MCR015797 | HPR116 | 2020-11-01 | Material | 68733702 | 34159690 | 28641275
MCR015798 | HPR116 | 2020-11-01 | Equipment | 19408030 | 9645520 | 8529929
MCR015799 | HPR116 | 2020-11-01 | Subcontract | 69405918 | 34493772 | 36098854
MCR015800 | HPR116 | 2020-11-01 | Overhead | 14508891 | 7210716 | 11071516
MCR015801 | HPR116 | 2020-12-01 | Labor | 24010691 | 18611146 | 18594990
MCR015802 | HPR116 | 2020-12-01 | Material | 74494559 | 57742157 | 58830702
MCR015803 | HPR116 | 2020-12-01 | Equipment | 21034698 | 16304397 | 18071178
MCR015804 | HPR116 | 2020-12-01 | Subcontract | 75223116 | 58306876 | 62028974
MCR015805 | HPR116 | 2020-12-01 | Overhead | 15724942 | 12188703 | 10074735
MCR015806 | HPR116 | 2021-01-01 | Labor | 25249209 | 21728783 | 21598684
MCR015807 | HPR116 | 2021-01-01 | Material | 78337132 | 67414807 | 75785545
MCR015808 | HPR116 | 2021-01-01 | Equipment | 22119708 | 19035620 | 16675594
MCR015809 | HPR116 | 2021-01-01 | Subcontract | 79103270 | 68074124 | 69792604
MCR015810 | HPR116 | 2021-01-01 | Overhead | 16536064 | 14230488 | 10191451
MCR015811 | HPR116 | 2021-02-01 | Labor | 25893032 | 26568696 | 27721105
MCR015812 | HPR116 | 2021-02-01 | Material | 80334628 | 82430916 | 87473179
MCR015813 | HPR116 | 2021-02-01 | Equipment | 22683732 | 23275652 | 26110466
MCR015814 | HPR116 | 2021-02-01 | Subcontract | 81120301 | 83237091 | 89453928
MCR015815 | HPR116 | 2021-02-01 | Overhead | 16957713 | 17400215 | 10969365
MCR015816 | HPR116 | 2021-03-01 | Labor | 25967619 | 16235549 | 17365657
MCR015817 | HPR116 | 2021-03-01 | Material | 80566041 | 50371731 | 49288690
MCR015818 | HPR116 | 2021-03-01 | Equipment | 22749075 | 14223242 | 13787527
MCR015819 | HPR116 | 2021-03-01 | Subcontract | 81353977 | 50864367 | 52478936
MCR015820 | HPR116 | 2021-03-01 | Overhead | 17006561 | 10632891 | 11622947
MCR015821 | HPR116 | 2021-04-01 | Labor | 25500653 | 25334313 | 26947113
MCR015822 | HPR116 | 2021-04-01 | Material | 79117250 | 78601172 | 86674441
MCR015823 | HPR116 | 2021-04-01 | Equipment | 22339987 | 22194264 | 23750773
MCR015824 | HPR116 | 2021-04-01 | Subcontract | 79891017 | 79369892 | 78866021
MCR015825 | HPR116 | 2021-04-01 | Overhead | 16700738 | 16591800 | 11147097
MCR015826 | HPR116 | 2021-05-01 | Labor | 24522500 | 36642970 | 35829265
MCR015827 | HPR116 | 2021-05-01 | Material | 76082473 | 113686934 | 120812878
MCR015828 | HPR116 | 2021-05-01 | Equipment | 21483070 | 32101275 | 31741868
MCR015829 | HPR116 | 2021-05-01 | Subcontract | 76826560 | 114798792 | 122146262
MCR015830 | HPR116 | 2021-05-01 | Overhead | 16060132 | 23997999 | 10448106
MCR015831 | HPR116 | 2021-06-01 | Labor | 23066843 | 19548797 | 23825471
MCR015832 | HPR116 | 2021-06-01 | Material | 71566216 | 60651273 | 76560271
MCR015833 | HPR116 | 2021-06-01 | Equipment | 20207835 | 17125831 | 16868748
MCR015834 | HPR116 | 2021-06-01 | Subcontract | 72266134 | 61244443 | 60791383
MCR015835 | HPR116 | 2021-06-01 | Overhead | 15106802 | 12802784 | 11283051
MCR015836 | HPR116 | 2021-07-01 | Labor | 21171562 | 14119735 | 13043470
MCR015837 | HPR116 | 2021-07-01 | Material | 65685997 | 43807294 | 51601367
MCR015838 | HPR116 | 2021-07-01 | Equipment | 18547463 | 12369671 | 13544964
MCR015839 | HPR116 | 2021-07-01 | Subcontract | 66328406 | 44235730 | 48652181
MCR015840 | HPR116 | 2021-07-01 | Overhead | 13865556 | 9247214 | 11606276
MCR015841 | HPR116 | 2021-08-01 | Labor | 18879999 | 10660696 | 10754952
MCR015842 | HPR116 | 2021-08-01 | Material | 58576290 | 33075425 | 38076963
MCR015843 | HPR116 | 2021-08-01 | Equipment | 16539927 | 9339361 | 9323386
MCR015844 | HPR116 | 2021-08-01 | Subcontract | 59149166 | 33398903 | 33376895
MCR015845 | HPR116 | 2021-08-01 | Overhead | 12364779 | 6981840 | 10594095
MCR015846 | HPR116 | 2021-09-01 | Labor | 16242896 | 19160558 | 20480656
MCR015847 | HPR116 | 2021-09-01 | Material | 50394524 | 59446740 | 74392372
MCR015848 | HPR116 | 2021-09-01 | Equipment | 14229678 | 16785712 | 16820280
MCR015849 | HPR116 | 2021-09-01 | Subcontract | 50887383 | 60028129 | 67807804
MCR015850 | HPR116 | 2021-09-01 | Overhead | 10637702 | 12548521 | 11366736
MCR015851 | HPR116 | 2021-10-01 | Labor | 13321532 | 20732698 | 19532015
MCR015852 | HPR116 | 2021-10-01 | Material | 41330823 | 64324396 | 73518474
MCR015853 | HPR116 | 2021-10-01 | Equipment | 11670401 | 18162994 | 19028172
MCR015854 | HPR116 | 2021-10-01 | Subcontract | 41735038 | 64953489 | 72366120
MCR015855 | HPR116 | 2021-10-01 | Overhead | 8724460 | 13578137 | 10119387
MCR015856 | HPR116 | 2021-11-01 | Labor | 10193286 | 10972794 | 14134949
MCR015857 | HPR116 | 2021-11-01 | Material | 31625261 | 34043729 | 47318292
MCR015858 | HPR116 | 2021-11-01 | Equipment | 8929885 | 9612777 | 8942636
MCR015859 | HPR116 | 2021-11-01 | Subcontract | 31934556 | 34376676 | 32987626
MCR015860 | HPR116 | 2021-11-01 | Overhead | 6675727 | 7186238 | 11501569
MCR015861 | HPR116 | 2021-12-01 | Labor | 6962865 | 11837404 | 11235183
MCR015862 | HPR116 | 2021-12-01 | Material | 21602691 | 36726231 | 42356017
MCR015863 | HPR116 | 2021-12-01 | Equipment | 6099856 | 10370223 | 9908897
MCR015864 | HPR116 | 2021-12-01 | Subcontract | 21813965 | 37085414 | 37291641
MCR015865 | HPR116 | 2021-12-01 | Overhead | 4560079 | 7752483 | 11537765
MCR015866 | HPR116 | 2022-01-01 | Labor | 3790377 | 8590544 | 9364350
MCR015867 | HPR116 | 2022-01-01 | Material | 11759865 | 26652660 | 32450644
MCR015868 | HPR116 | 2022-01-01 | Equipment | 3320581 | 7525793 | 8719247
MCR015869 | HPR116 | 2022-01-01 | Subcontract | 11874877 | 26913323 | 28872569
MCR015870 | HPR116 | 2022-01-01 | Overhead | 2482372 | 5626069 | 10241162
MCR015871 | HPR116 | 2022-02-01 | Labor | 1009280 | 18506864 | 18776073
MCR015872 | HPR116 | 2022-02-01 | Material | 3131350 | 57418617 | 68823790
MCR015873 | HPR116 | 2022-02-01 | Equipment | 884186 | 16213040 | 16129574
MCR015874 | HPR116 | 2022-02-01 | Subcontract | 3161975 | 57980172 | 52853128
MCR015875 | HPR116 | 2022-02-01 | Overhead | 660992 | 12120407 | 10271186
MCR015876 | HPR116 | 2022-03-01 | Labor | 0 | 4652379 | 4570672
MCR015877 | HPR116 | 2022-03-01 | Material | 0 | 14434276 | 19104208
MCR015878 | HPR116 | 2022-03-01 | Equipment | 0 | 4075742 | 4429104
MCR015879 | HPR116 | 2022-03-01 | Subcontract | 0 | 14575443 | 15668986
MCR015880 | HPR116 | 2022-03-01 | Overhead | 0 | 3046909 | 10332930
MCR015881 | HPR116 | 2022-04-01 | Labor | 0 | 4445763 | 4293198
MCR015882 | HPR116 | 2022-04-01 | Material | 0 | 13793237 | 15953981
MCR015883 | HPR116 | 2022-04-01 | Equipment | 0 | 3894735 | 3731833
MCR015884 | HPR116 | 2022-04-01 | Subcontract | 0 | 13928135 | 15664378
MCR015885 | HPR116 | 2022-04-01 | Overhead | 0 | 2911593 | 10879176
MCR015886 | HPR116 | 2022-05-01 | Labor | 0 | 2999759 | 3034462
MCR015887 | HPR116 | 2022-05-01 | Material | 0 | 9306927 | 11419721
MCR015888 | HPR116 | 2022-05-01 | Equipment | 0 | 2627956 | 2924537
MCR015889 | HPR116 | 2022-05-01 | Subcontract | 0 | 9397949 | 9536227
MCR015890 | HPR116 | 2022-05-01 | Overhead | 0 | 1964585 | 10826638
MCR015891 | HPR116 | 2022-06-01 | Labor | 0 | 824700 | 967562
MCR015892 | HPR116 | 2022-06-01 | Material | 0 | 2558679 | 3354718
MCR015893 | HPR116 | 2022-06-01 | Equipment | 0 | 722483 | 832734
MCR015894 | HPR116 | 2022-06-01 | Subcontract | 0 | 2583702 | 2863386
MCR015895 | HPR116 | 2022-06-01 | Overhead | 0 | 540108 | 10884862
MCR015896 | HPR117 | 2022-11-01 | Labor | 5497380 | 3120267 | 3339508
MCR015897 | HPR117 | 2022-11-01 | Material | 22415733 | 12722984 | 13842513
MCR015898 | HPR117 | 2022-11-01 | Equipment | 12482739 | 7085099 | 7912849
MCR015899 | HPR117 | 2022-11-01 | Subcontract | 13462941 | 7641454 | 7428841
MCR015900 | HPR117 | 2022-11-01 | Overhead | 5697659 | 3233944 | 22601848
MCR015901 | HPR117 | 2022-12-01 | Labor | 14964649 | 10526788 | 12245147
MCR015902 | HPR117 | 2022-12-01 | Material | 61018804 | 42923293 | 38935668
MCR015903 | HPR117 | 2022-12-01 | Equipment | 33979786 | 23902866 | 25593352
MCR015904 | HPR117 | 2022-12-01 | Subcontract | 36648034 | 25779828 | 26623800
MCR015905 | HPR117 | 2022-12-01 | Overhead | 15509835 | 10910295 | 21996148
MCR015906 | HPR117 | 2023-01-01 | Labor | 22207760 | 16008713 | 17881502
MCR015907 | HPR117 | 2023-01-01 | Material | 90552806 | 65276006 | 69636800
MCR015908 | HPR117 | 2023-01-01 | Equipment | 50426503 | 36350511 | 35467384
MCR015909 | HPR117 | 2023-01-01 | Subcontract | 54386223 | 39204919 | 43696683
MCR015910 | HPR117 | 2023-01-01 | Overhead | 23016824 | 16591936 | 21559118
MCR015911 | HPR117 | 2023-02-01 | Labor | 27322491 | 16142000 | 17785215
MCR015912 | HPR117 | 2023-02-01 | Material | 111408275 | 65819488 | 69662530
MCR015913 | HPR117 | 2023-02-01 | Equipment | 62040372 | 36653162 | 38557492
MCR015914 | HPR117 | 2023-02-01 | Subcontract | 66912066 | 39531336 | 36478924
MCR015915 | HPR117 | 2023-02-01 | Overhead | 28317892 | 16730079 | 22641118
MCR015916 | HPR117 | 2023-03-01 | Labor | 30414012 | 23507120 | 28026607
MCR015917 | HPR117 | 2023-03-01 | Material | 124014047 | 95850988 | 84935203
MCR015918 | HPR117 | 2023-03-01 | Equipment | 69060198 | 53376923 | 57164844
MCR015919 | HPR117 | 2023-03-01 | Subcontract | 74483121 | 57568324 | 65414345
MCR015920 | HPR117 | 2023-03-01 | Overhead | 31522043 | 24363522 | 22235307
MCR015921 | HPR117 | 2023-04-01 | Labor | 31599229 | 25072777 | 25563264
MCR015922 | HPR117 | 2023-04-01 | Material | 128846806 | 102234999 | 95784971
MCR015923 | HPR117 | 2023-04-01 | Equipment | 71751436 | 56932013 | 64077335
MCR015924 | HPR117 | 2023-04-01 | Subcontract | 77385687 | 61402575 | 56123320
MCR015925 | HPR117 | 2023-04-01 | Overhead | 32750440 | 25986218 | 20261034
MCR015926 | HPR117 | 2023-05-01 | Labor | 31010135 | 26750036 | 34378350
MCR015927 | HPR117 | 2023-05-01 | Material | 126444757 | 109074073 | 110149613
MCR015928 | HPR117 | 2023-05-01 | Equipment | 70413798 | 60740515 | 55858464
MCR015929 | HPR117 | 2023-05-01 | Subcontract | 75943012 | 65510138 | 71444937
MCR015930 | HPR117 | 2023-05-01 | Overhead | 32139884 | 27724582 | 21087936
MCR015931 | HPR117 | 2023-06-01 | Labor | 28798852 | 34080344 | 31754946
MCR015932 | HPR117 | 2023-06-01 | Material | 117428181 | 138963624 | 146105262
MCR015933 | HPR117 | 2023-06-01 | Equipment | 65392701 | 77385229 | 87560314
MCR015934 | HPR117 | 2023-06-01 | Subcontract | 70527635 | 83461872 | 80362190
MCR015935 | HPR117 | 2023-06-01 | Overhead | 29848040 | 35321945 | 19600174
MCR015936 | HPR117 | 2023-07-01 | Labor | 25145697 | 22292822 | 26200334
MCR015937 | HPR117 | 2023-07-01 | Material | 102532332 | 90899652 | 86595500
MCR015938 | HPR117 | 2023-07-01 | Equipment | 57097590 | 50619653 | 47739758
MCR015939 | HPR117 | 2023-07-01 | Subcontract | 61581154 | 54594540 | 52380220
MCR015940 | HPR117 | 2023-07-01 | Overhead | 26061794 | 23104985 | 21751436
MCR015941 | HPR117 | 2023-08-01 | Labor | 20273279 | 20828629 | 25131835
MCR015942 | HPR117 | 2023-08-01 | Material | 82664902 | 84929361 | 97168915
MCR015943 | HPR117 | 2023-08-01 | Equipment | 46033935 | 47294953 | 46051805
MCR015944 | HPR117 | 2023-08-01 | Subcontract | 49648730 | 51008769 | 55664797
MCR015945 | HPR117 | 2023-08-01 | Overhead | 21011867 | 21587450 | 20700676
MCR015946 | HPR117 | 2023-09-01 | Labor | 14474454 | 17251937 | 17758886
MCR015947 | HPR117 | 2023-09-01 | Material | 59020021 | 70345289 | 52686998
MCR015948 | HPR117 | 2023-09-01 | Equipment | 32866715 | 39173462 | 42868868
MCR015949 | HPR117 | 2023-09-01 | Subcontract | 35447560 | 42249542 | 42381339
MCR015950 | HPR117 | 2023-09-01 | Overhead | 15001782 | 17880452 | 23210161
MCR015951 | HPR117 | 2023-10-01 | Labor | 8180945 | 12651031 | 14197773
MCR015952 | HPR117 | 2023-10-01 | Material | 33358050 | 51584957 | 57879096
MCR015953 | HPR117 | 2023-10-01 | Equipment | 18576230 | 28726322 | 26511854
MCR015954 | HPR117 | 2023-10-01 | Subcontract | 20034921 | 30982044 | 33299645
MCR015955 | HPR117 | 2023-10-01 | Overhead | 8478990 | 13111928 | 21872643
MCR015956 | HPR117 | 2023-11-01 | Labor | 2244061 | 14409987 | 15998376
MCR015957 | HPR117 | 2023-11-01 | Material | 9150224 | 58757153 | 57800945
MCR015958 | HPR117 | 2023-11-01 | Equipment | 5095522 | 32720331 | 39620697
MCR015959 | HPR117 | 2023-11-01 | Subcontract | 5495646 | 35289681 | 36009795
MCR015960 | HPR117 | 2023-11-01 | Overhead | 2325815 | 14934965 | 21260863
MCR015961 | HPR117 | 2023-12-01 | Labor | 0 | 11540439 | 13580645
MCR015962 | HPR117 | 2023-12-01 | Material | 0 | 47056487 | 44883718
MCR015963 | HPR117 | 2023-12-01 | Equipment | 0 | 26204534 | 20941220
MCR015964 | HPR117 | 2023-12-01 | Subcontract | 0 | 28262234 | 29380165
MCR015965 | HPR117 | 2023-12-01 | Overhead | 0 | 11960876 | 22320700
MCR015966 | HPR117 | 2024-01-01 | Labor | 0 | 7018266 | 6354223
MCR015967 | HPR117 | 2024-01-01 | Material | 0 | 28617191 | 26581296
MCR015968 | HPR117 | 2024-01-01 | Equipment | 0 | 15936170 | 18850168
MCR015969 | HPR117 | 2024-01-01 | Subcontract | 0 | 17187551 | 17088970
MCR015970 | HPR117 | 2024-01-01 | Overhead | 0 | 7273953 | 22238281
MCR015971 | HPR117 | 2024-02-01 | Labor | 0 | 931788 | 1748478
MCR015972 | HPR117 | 2024-02-01 | Material | 0 | 3799392 | 5070623
MCR015973 | HPR117 | 2024-02-01 | Equipment | 0 | 2115783 | 2630481
MCR015974 | HPR117 | 2024-02-01 | Subcontract | 0 | 2281923 | 2461616
MCR015975 | HPR117 | 2024-02-01 | Overhead | 0 | 965734 | 20812805
MCR015976 | HPR118 | 2018-06-01 | Labor | 3342507 | 2226100 | 2173551
MCR015977 | HPR118 | 2018-06-01 | Material | 8257204 | 5499275 | 6367122
MCR015978 | HPR118 | 2018-06-01 | Equipment | 2628751 | 1750741 | 1683991
MCR015979 | HPR118 | 2018-06-01 | Subcontract | 9116342 | 6071458 | 6095096
MCR015980 | HPR118 | 2018-06-01 | Overhead | 2254937 | 1501782 | 17219378
MCR015981 | HPR118 | 2018-07-01 | Labor | 9572642 | 2669398 | 2873820
MCR015982 | HPR118 | 2018-07-01 | Material | 23647896 | 6594379 | 6506727
MCR015983 | HPR118 | 2018-07-01 | Equipment | 7528510 | 2099377 | 2195221
MCR015984 | HPR118 | 2018-07-01 | Subcontract | 26108391 | 7280506 | 6664895
MCR015985 | HPR118 | 2018-07-01 | Overhead | 6457937 | 1800841 | 15883905
MCR015986 | HPR118 | 2018-08-01 | Labor | 15129844 | 6995498 | 7580800
MCR015987 | HPR118 | 2018-08-01 | Material | 37376199 | 17281416 | 17310783
MCR015988 | HPR118 | 2018-08-01 | Equipment | 11899032 | 5501686 | 5785207
MCR015989 | HPR118 | 2018-08-01 | Subcontract | 41265085 | 19079497 | 21242349
MCR015990 | HPR118 | 2018-08-01 | Overhead | 10206961 | 4719333 | 15441515
MCR015991 | HPR118 | 2018-09-01 | Labor | 20027024 | 13556090 | 15439669
MCR015992 | HPR118 | 2018-09-01 | Material | 49474007 | 33488454 | 35839724
MCR015993 | HPR118 | 2018-09-01 | Equipment | 15750473 | 10661335 | 11237261
MCR015994 | HPR118 | 2018-09-01 | Subcontract | 54621635 | 36972832 | 33159826
MCR015995 | HPR118 | 2018-09-01 | Overhead | 13510718 | 9145268 | 15474935
MCR015996 | HPR118 | 2018-10-01 | Labor | 24277626 | 9936337 | 10057085
MCR015997 | HPR118 | 2018-10-01 | Material | 59974536 | 24546353 | 21828906
MCR015998 | HPR118 | 2018-10-01 | Equipment | 19093406 | 7814541 | 8186923
MCR015999 | HPR118 | 2018-10-01 | Subcontract | 66214714 | 27100330 | 32637434
MCR016000 | HPR118 | 2018-10-01 | Overhead | 16378278 | 6703295 | 16914021
MCR016001 | HPR118 | 2018-11-01 | Labor | 27895685 | 14421873 | 15804995
MCR016002 | HPR118 | 2018-11-01 | Material | 68912451 | 35627252 | 41972271
MCR016003 | HPR118 | 2018-11-01 | Equipment | 21938867 | 11342240 | 11660420
MCR016004 | HPR118 | 2018-11-01 | Subcontract | 76082593 | 39334165 | 39971983
MCR016005 | HPR118 | 2018-11-01 | Overhead | 18819108 | 9729346 | 15632430
MCR016006 | HPR118 | 2018-12-01 | Labor | 30895880 | 16344280 | 18339973
MCR016007 | HPR118 | 2018-12-01 | Material | 76324020 | 40376296 | 35721386
MCR016008 | HPR118 | 2018-12-01 | Equipment | 24298403 | 12854139 | 14007118
MCR016009 | HPR118 | 2018-12-01 | Subcontract | 84265315 | 44577333 | 37265350
MCR016010 | HPR118 | 2018-12-01 | Overhead | 20843112 | 11026249 | 15904144
MCR016011 | HPR118 | 2019-01-01 | Labor | 33293612 | 20685696 | 24231261
MCR016012 | HPR118 | 2019-01-01 | Material | 82247288 | 51101167 | 53021047
MCR016013 | HPR118 | 2019-01-01 | Equipment | 26184126 | 16268493 | 15393966
MCR016014 | HPR118 | 2019-01-01 | Subcontract | 90804882 | 56418096 | 55693938
MCR016015 | HPR118 | 2019-01-01 | Overhead | 22460681 | 13955074 | 16275173
MCR016016 | HPR118 | 2019-02-01 | Labor | 35105085 | 28296597 | 30492590
MCR016017 | HPR118 | 2019-02-01 | Material | 86722283 | 69902848 | 68591567
MCR016018 | HPR118 | 2019-02-01 | Equipment | 27608779 | 22254169 | 23547285
MCR016019 | HPR118 | 2019-02-01 | Subcontract | 95745488 | 77176039 | 82684724
MCR016020 | HPR118 | 2019-02-01 | Overhead | 23682745 | 19089573 | 16820728
MCR016021 | HPR118 | 2019-03-01 | Labor | 36347405 | 15501734 | 18792617
MCR016022 | HPR118 | 2019-03-01 | Material | 89791263 | 38294900 | 38956986
MCR016023 | HPR118 | 2019-03-01 | Equipment | 28585815 | 12191508 | 12270323
MCR016024 | HPR118 | 2019-03-01 | Subcontract | 99133786 | 42279375 | 40992664
MCR016025 | HPR118 | 2019-03-01 | Overhead | 24520844 | 10457847 | 15713544
MCR016026 | HPR118 | 2019-04-01 | Labor | 37038698 | 17570985 | 18721499
MCR016027 | HPR118 | 2019-04-01 | Material | 91499007 | 43406702 | 48908640
MCR016028 | HPR118 | 2019-04-01 | Equipment | 29129490 | 13818894 | 13748648
MCR016029 | HPR118 | 2019-04-01 | Subcontract | 101019216 | 47923044 | 46852852
MCR016030 | HPR118 | 2019-04-01 | Overhead | 24987207 | 11853814 | 15636237
MCR016031 | HPR118 | 2019-05-01 | Labor | 37198256 | 21822380 | 23643390
MCR016032 | HPR118 | 2019-05-01 | Material | 91893174 | 53909186 | 51965979
MCR016033 | HPR118 | 2019-05-01 | Equipment | 29254977 | 17162450 | 19275127
MCR016034 | HPR118 | 2019-05-01 | Subcontract | 101454395 | 59518282 | 64362299
MCR016035 | HPR118 | 2019-05-01 | Overhead | 25094849 | 14721908 | 16107335
MCR016036 | HPR118 | 2019-06-01 | Labor | 36846714 | 46648374 | 58389761
MCR016037 | HPR118 | 2019-06-01 | Material | 91024736 | 115238389 | 117121501
MCR016038 | HPR118 | 2019-06-01 | Equipment | 28978502 | 36687125 | 36784433
MCR016039 | HPR118 | 2019-06-01 | Subcontract | 100495598 | 127228613 | 114854959
MCR016040 | HPR118 | 2019-06-01 | Overhead | 24857690 | 31470128 | 16783243
MCR016041 | HPR118 | 2019-07-01 | Labor | 36006266 | 33114950 | 28260265
MCR016042 | HPR118 | 2019-07-01 | Material | 88948525 | 81805929 | 94338854
MCR016043 | HPR118 | 2019-07-01 | Equipment | 28317522 | 26043616 | 24807641
MCR016044 | HPR118 | 2019-07-01 | Subcontract | 98203364 | 90317601 | 100129938
MCR016045 | HPR118 | 2019-07-01 | Overhead | 24290703 | 22340151 | 15795909
MCR016046 | HPR118 | 2019-08-01 | Labor | 34700949 | 19567933 | 27643381
MCR016047 | HPR118 | 2019-08-01 | Material | 85723919 | 48339886 | 47738753
MCR016048 | HPR118 | 2019-08-01 | Equipment | 27290942 | 15389415 | 17400870
MCR016049 | HPR118 | 2019-08-01 | Subcontract | 94643247 | 53369512 | 52505590
MCR016050 | HPR118 | 2019-08-01 | Overhead | 23410105 | 13201004 | 15988433
MCR016051 | HPR118 | 2019-09-01 | Labor | 32956999 | 26353357 | 28830626
MCR016052 | HPR118 | 2019-09-01 | Material | 81415732 | 65102343 | 61239316
MCR016053 | HPR118 | 2019-09-01 | Equipment | 25919393 | 20725887 | 19539708
MCR016054 | HPR118 | 2019-09-01 | Subcontract | 89886805 | 71876055 | 75814102
MCR016055 | HPR118 | 2019-09-01 | Overhead | 22233594 | 17778616 | 16503567
MCR016056 | HPR118 | 2019-10-01 | Labor | 30803328 | 28093218 | 34524230
MCR016057 | HPR118 | 2019-10-01 | Material | 76095383 | 69400431 | 73708648
MCR016058 | HPR118 | 2019-10-01 | Equipment | 24225615 | 22094220 | 22101415
MCR016059 | HPR118 | 2019-10-01 | Subcontract | 84012889 | 76621346 | 72930205
MCR016060 | HPR118 | 2019-10-01 | Overhead | 20780675 | 18952369 | 16546659
MCR016061 | HPR118 | 2019-11-01 | Labor | 28272161 | 26653071 | 29750947
MCR016062 | HPR118 | 2019-11-01 | Material | 69842485 | 65842745 | 66450267
MCR016063 | HPR118 | 2019-11-01 | Equipment | 22234951 | 20961600 | 23059857
MCR016064 | HPR118 | 2019-11-01 | Subcontract | 77109395 | 72693494 | 79362628
MCR016065 | HPR118 | 2019-11-01 | Overhead | 19073088 | 17980811 | 17773207
MCR016066 | HPR118 | 2019-12-01 | Labor | 25399943 | 15377136 | 16154806
MCR016067 | HPR118 | 2019-12-01 | Material | 62747064 | 37987100 | 42917045
MCR016068 | HPR118 | 2019-12-01 | Equipment | 19976064 | 12093518 | 12994067
MCR016069 | HPR118 | 2019-12-01 | Subcontract | 69275716 | 41939548 | 34875658
MCR016070 | HPR118 | 2019-12-01 | Overhead | 17135420 | 10373790 | 15683744
MCR016071 | HPR118 | 2020-01-01 | Labor | 22228638 | 24057565 | 28019167
MCR016072 | HPR118 | 2020-01-01 | Material | 54912793 | 59430904 | 59639961
MCR016073 | HPR118 | 2020-01-01 | Equipment | 17481956 | 18920336 | 19104177
MCR016074 | HPR118 | 2020-01-01 | Subcontract | 60626311 | 65614519 | 71988742
MCR016075 | HPR118 | 2020-01-01 | Overhead | 14995980 | 16229819 | 14923771
MCR016076 | HPR118 | 2020-02-01 | Labor | 18807735 | 34146999 | 43958954
MCR016077 | HPR118 | 2020-02-01 | Material | 46461923 | 84355464 | 94352634
MCR016078 | HPR118 | 2020-02-01 | Equipment | 14791550 | 26855282 | 28419138
MCR016079 | HPR118 | 2020-02-01 | Subcontract | 51296152 | 93132407 | 102361585
MCR016080 | HPR118 | 2020-02-01 | Overhead | 12688156 | 23036397 | 16862045
MCR016081 | HPR118 | 2020-03-01 | Labor | 15197505 | 17615246 | 20095700
MCR016082 | HPR118 | 2020-03-01 | Material | 37543345 | 43516042 | 50054688
MCR016083 | HPR118 | 2020-03-01 | Equipment | 11952244 | 13853703 | 13717743
MCR016084 | HPR118 | 2020-03-01 | Subcontract | 41449622 | 48043761 | 36329494
MCR016085 | HPR118 | 2020-03-01 | Overhead | 10252607 | 11883674 | 15645369
MCR016086 | HPR118 | 2020-04-01 | Labor | 11474812 | 21562765 | 22315808
MCR016087 | HPR118 | 2020-04-01 | Material | 28346944 | 53267844 | 46556215
MCR016088 | HPR118 | 2020-04-01 | Equipment | 9024492 | 16958273 | 17415882
MCR016089 | HPR118 | 2020-04-01 | Subcontract | 31296363 | 58810210 | 59024345
MCR016090 | HPR118 | 2020-04-01 | Overhead | 7741187 | 14546766 | 14933187
MCR016091 | HPR118 | 2020-05-01 | Labor | 7744912 | 27679935 | 38585320
MCR016092 | HPR118 | 2020-05-01 | Material | 19132738 | 68379470 | 74343329
MCR016093 | HPR118 | 2020-05-01 | Equipment | 6091071 | 21769188 | 23926821
MCR016094 | HPR118 | 2020-05-01 | Subcontract | 21123445 | 75494157 | 80700729
MCR016095 | HPR118 | 2020-05-01 | Overhead | 5224906 | 18673558 | 16258175
MCR016096 | HPR118 | 2020-06-01 | Labor | 4171155 | 36052960 | 33340381
MCR016097 | HPR118 | 2020-06-01 | Material | 10304265 | 89063878 | 89377032
MCR016098 | HPR118 | 2020-06-01 | Equipment | 3280451 | 28354246 | 27248277
MCR016099 | HPR118 | 2020-06-01 | Subcontract | 11376394 | 98330718 | 95232870
MCR016100 | HPR118 | 2020-06-01 | Overhead | 2813963 | 24322204 | 14828619
MCR016101 | HPR118 | 2020-07-01 | Labor | 1100879 | 14874185 | 21460272
MCR016102 | HPR118 | 2020-07-01 | Material | 2719571 | 36744628 | 37548631
MCR016103 | HPR118 | 2020-07-01 | Equipment | 865799 | 11697966 | 13459209
MCR016104 | HPR118 | 2020-07-01 | Subcontract | 3002534 | 40567801 | 42299114
MCR016105 | HPR118 | 2020-07-01 | Overhead | 742680 | 10034487 | 17807014
MCR016106 | HPR118 | 2020-08-01 | Labor | 0 | 16785741 | 20067046
MCR016107 | HPR118 | 2020-08-01 | Material | 0 | 41466863 | 44037282
MCR016108 | HPR118 | 2020-08-01 | Equipment | 0 | 13201330 | 14790438
MCR016109 | HPR118 | 2020-08-01 | Subcontract | 0 | 45781371 | 35837163
MCR016110 | HPR118 | 2020-08-01 | Overhead | 0 | 11324069 | 17316291
MCR016111 | HPR118 | 2020-09-01 | Labor | 0 | 11563492 | 12648314
MCR016112 | HPR118 | 2020-09-01 | Material | 0 | 28566017 | 25520910
MCR016113 | HPR118 | 2020-09-01 | Equipment | 0 | 9094235 | 9909317
MCR016114 | HPR118 | 2020-09-01 | Subcontract | 0 | 31538229 | 37471103
MCR016115 | HPR118 | 2020-09-01 | Overhead | 0 | 7801013 | 16212780
MCR016116 | HPR118 | 2020-10-01 | Labor | 0 | 15208045 | 20247454
MCR016117 | HPR118 | 2020-10-01 | Material | 0 | 37569383 | 40523662
MCR016118 | HPR118 | 2020-10-01 | Equipment | 0 | 11960534 | 13020185
MCR016119 | HPR118 | 2020-10-01 | Subcontract | 0 | 41478370 | 42283308
MCR016120 | HPR118 | 2020-10-01 | Overhead | 0 | 10259717 | 17414425
MCR016121 | HPR118 | 2020-11-01 | Labor | 0 | 13497570 | 15246261
MCR016122 | HPR118 | 2020-11-01 | Material | 0 | 33343889 | 37174024
MCR016123 | HPR118 | 2020-11-01 | Equipment | 0 | 10615312 | 10991826
MCR016124 | HPR118 | 2020-11-01 | Subcontract | 0 | 36813224 | 35927223
MCR016125 | HPR118 | 2020-11-01 | Overhead | 0 | 9105789 | 16465581
MCR016126 | HPR118 | 2020-12-01 | Labor | 0 | 9035527 | 11077943
MCR016127 | HPR118 | 2020-12-01 | Material | 0 | 22321025 | 21189853
MCR016128 | HPR118 | 2020-12-01 | Equipment | 0 | 7106089 | 8403490
MCR016129 | HPR118 | 2020-12-01 | Subcontract | 0 | 24643464 | 23194003
MCR016130 | HPR118 | 2020-12-01 | Overhead | 0 | 6095586 | 15123204
MCR016131 | HPR118 | 2021-01-01 | Labor | 0 | 4340456 | 5593355
MCR016132 | HPR118 | 2021-01-01 | Material | 0 | 10722498 | 11073002
MCR016133 | HPR118 | 2021-01-01 | Equipment | 0 | 3413599 | 4343268
MCR016134 | HPR118 | 2021-01-01 | Subcontract | 0 | 11838143 | 10744142
MCR016135 | HPR118 | 2021-01-01 | Overhead | 0 | 2928177 | 15692326
MCR016136 | HPR118 | 2021-02-01 | Labor | 0 | 3158174 | 3454849
MCR016137 | HPR118 | 2021-02-01 | Material | 0 | 7801835 | 7971766
MCR016138 | HPR118 | 2021-02-01 | Equipment | 0 | 2483781 | 2614593
MCR016139 | HPR118 | 2021-02-01 | Subcontract | 0 | 8613594 | 9480389
MCR016140 | HPR118 | 2021-02-01 | Overhead | 0 | 2130581 | 15468767
MCR016141 | HPR118 | 2021-03-01 | Labor | 0 | 422594 | 558187
MCR016142 | HPR118 | 2021-03-01 | Material | 0 | 1043961 | 944835
MCR016143 | HPR118 | 2021-03-01 | Equipment | 0 | 332354 | 255538
MCR016144 | HPR118 | 2021-03-01 | Subcontract | 0 | 1152583 | 1227235
MCR016145 | HPR118 | 2021-03-01 | Overhead | 0 | 285093 | 14685129
MCR016146 | HPR119 | 2016-04-01 | Labor | 2917610 | 2199040 | 2515544
MCR016147 | HPR119 | 2016-04-01 | Material | 10759516 | 8109585 | 7582396
MCR016148 | HPR119 | 2016-04-01 | Equipment | 2245636 | 1692565 | 1706846
MCR016149 | HPR119 | 2016-04-01 | Subcontract | 8282101 | 6242326 | 6513213
MCR016150 | HPR119 | 2016-04-01 | Overhead | 2212294 | 1667434 | 12276174
MCR016151 | HPR119 | 2016-05-01 | Labor | 8233459 | 8316105 | 8278720
MCR016152 | HPR119 | 2016-05-01 | Material | 30363223 | 30668001 | 32361004
MCR016153 | HPR119 | 2016-05-01 | Equipment | 6337158 | 6400769 | 6426853
MCR016154 | HPR119 | 2016-05-01 | Subcontract | 23371988 | 23606591 | 25966593
MCR016155 | HPR119 | 2016-05-01 | Overhead | 6243066 | 6305732 | 11975287
MCR016156 | HPR119 | 2016-06-01 | Labor | 12784441 | 14327774 | 13460306
MCR016157 | HPR119 | 2016-06-01 | Material | 47146261 | 52837741 | 47848105
MCR016158 | HPR119 | 2016-06-01 | Equipment | 9839973 | 11027851 | 11114102
MCR016159 | HPR119 | 2016-06-01 | Subcontract | 36290676 | 40671673 | 42730313
MCR016160 | HPR119 | 2016-06-01 | Overhead | 9693873 | 10864114 | 12491656
MCR016161 | HPR119 | 2016-07-01 | Labor | 16590275 | 11775180 | 15305823
MCR016162 | HPR119 | 2016-07-01 | Material | 61181355 | 43424323 | 49818648
MCR016163 | HPR119 | 2016-07-01 | Equipment | 12769261 | 9063161 | 9534183
MCR016164 | HPR119 | 2016-07-01 | Subcontract | 47094142 | 33425727 | 33983984
MCR016165 | HPR119 | 2016-07-01 | Overhead | 12579667 | 8928595 | 11889854
MCR016166 | HPR119 | 2016-08-01 | Labor | 19671795 | 8793277 | 8049619
MCR016167 | HPR119 | 2016-08-01 | Material | 72545336 | 32427710 | 27799121
MCR016168 | HPR119 | 2016-08-01 | Equipment | 15141056 | 6768040 | 7653575
MCR016169 | HPR119 | 2016-08-01 | Subcontract | 55841528 | 24961120 | 25734209
MCR016170 | HPR119 | 2016-08-01 | Overhead | 14916247 | 6667551 | 11998338
MCR016171 | HPR119 | 2016-09-01 | Labor | 22051099 | 14303402 | 15987153
MCR016172 | HPR119 | 2016-09-01 | Material | 81319699 | 52747861 | 66423322
MCR016173 | HPR119 | 2016-09-01 | Equipment | 16972367 | 11009092 | 11099998
MCR016174 | HPR119 | 2016-09-01 | Subcontract | 62595564 | 40602488 | 43787756
MCR016175 | HPR119 | 2016-09-01 | Overhead | 16720368 | 10845633 | 11280787
MCR016176 | HPR119 | 2016-10-01 | Labor | 23751740 | 18492096 | 18777342
MCR016177 | HPR119 | 2016-10-01 | Material | 87591294 | 68194864 | 64121911
MCR016178 | HPR119 | 2016-10-01 | Equipment | 18281322 | 14233061 | 16096781
MCR016179 | HPR119 | 2016-10-01 | Subcontract | 67423103 | 52492767 | 55406977
MCR016180 | HPR119 | 2016-10-01 | Overhead | 18009888 | 14021734 | 12682091
MCR016181 | HPR119 | 2016-11-01 | Labor | 24798948 | 14544260 | 17120195
MCR016182 | HPR119 | 2016-11-01 | Material | 91453171 | 53636095 | 51884418
MCR016183 | HPR119 | 2016-11-01 | Equipment | 19087341 | 11194477 | 9853566
MCR016184 | HPR119 | 2016-11-01 | Subcontract | 70395771 | 41286203 | 41893761
MCR016185 | HPR119 | 2016-11-01 | Overhead | 18803939 | 11028266 | 12085309
MCR016186 | HPR119 | 2016-12-01 | Labor | 25219929 | 15873953 | 16345852
MCR016187 | HPR119 | 2016-12-01 | Material | 93005659 | 58539715 | 67290377
MCR016188 | HPR119 | 2016-12-01 | Equipment | 19411363 | 12217920 | 13212326
MCR016189 | HPR119 | 2016-12-01 | Subcontract | 71590793 | 45060748 | 44083152
MCR016190 | HPR119 | 2016-12-01 | Overhead | 19123150 | 12036512 | 11930562
MCR016191 | HPR119 | 2017-01-01 | Labor | 25044234 | 13750186 | 13619174
MCR016192 | HPR119 | 2017-01-01 | Material | 92357735 | 50707722 | 50332177
MCR016193 | HPR119 | 2017-01-01 | Equipment | 19276134 | 10583292 | 10691088
MCR016194 | HPR119 | 2017-01-01 | Subcontract | 71092056 | 39032099 | 41050255
MCR016195 | HPR119 | 2017-01-01 | Overhead | 18989929 | 10426155 | 11988966
MCR016196 | HPR119 | 2017-02-01 | Labor | 24304252 | 20349525 | 20383105
MCR016197 | HPR119 | 2017-02-01 | Material | 89628840 | 75044658 | 86218264
MCR016198 | HPR119 | 2017-02-01 | Equipment | 18706582 | 15662693 | 16014573
MCR016199 | HPR119 | 2017-02-01 | Subcontract | 68991497 | 57765373 | 65637124
MCR016200 | HPR119 | 2017-02-01 | Overhead | 18428833 | 15430139 | 13198188
MCR016201 | HPR119 | 2017-03-01 | Labor | 23035867 | 22933144 | 25674021
MCR016202 | HPR119 | 2017-03-01 | Material | 84951311 | 84572489 | 91023429
MCR016203 | HPR119 | 2017-03-01 | Equipment | 17730327 | 17651262 | 17839601
MCR016204 | HPR119 | 2017-03-01 | Subcontract | 65390986 | 65099389 | 68350066
MCR016205 | HPR119 | 2017-03-01 | Overhead | 17467074 | 17389183 | 12610402
MCR016206 | HPR119 | 2017-04-01 | Labor | 21279384 | 17420711 | 19449524
MCR016207 | HPR119 | 2017-04-01 | Material | 78473781 | 64243824 | 59177574
MCR016208 | HPR119 | 2017-04-01 | Equipment | 16378391 | 13408434 | 13536140
MCR016209 | HPR119 | 2017-04-01 | Subcontract | 60404929 | 49451467 | 56511479
MCR016210 | HPR119 | 2017-04-01 | Overhead | 16135211 | 13209350 | 12356121
MCR016211 | HPR119 | 2017-05-01 | Labor | 19080856 | 20403945 | 24132011
MCR016212 | HPR119 | 2017-05-01 | Material | 70366081 | 75245350 | 78444190
MCR016213 | HPR119 | 2017-05-01 | Equipment | 14686220 | 15704580 | 18131712
MCR016214 | HPR119 | 2017-05-01 | Subcontract | 54164054 | 57919855 | 58062097
MCR016215 | HPR119 | 2017-05-01 | Overhead | 14468164 | 15471404 | 11648851
MCR016216 | HPR119 | 2017-06-01 | Labor | 16494107 | 16744955 | 16418396
MCR016217 | HPR119 | 2017-06-01 | Material | 60826708 | 61751783 | 76630231
MCR016218 | HPR119 | 2017-06-01 | Equipment | 12695242 | 12888316 | 11920947
MCR016219 | HPR119 | 2017-06-01 | Subcontract | 46821153 | 47533227 | 52359397
MCR016220 | HPR119 | 2017-06-01 | Overhead | 12506747 | 12696955 | 11902656
MCR016221 | HPR119 | 2017-07-01 | Labor | 13584014 | 20083393 | 20549183
MCR016222 | HPR119 | 2017-07-01 | Material | 50094915 | 74063223 | 74160581
MCR016223 | HPR119 | 2017-07-01 | Equipment | 10455392 | 15457856 | 14579182
MCR016224 | HPR119 | 2017-07-01 | Subcontract | 38560392 | 57009916 | 53518965
MCR016225 | HPR119 | 2017-07-01 | Overhead | 10300154 | 15228344 | 12367449
MCR016226 | HPR119 | 2017-08-01 | Labor | 10432315 | 12956594 | 14638767
MCR016227 | HPR119 | 2017-08-01 | Material | 38472127 | 47781124 | 47565597
MCR016228 | HPR119 | 2017-08-01 | Equipment | 8029580 | 9972476 | 12501236
MCR016229 | HPR119 | 2017-08-01 | Subcontract | 29613790 | 36779359 | 37140280
MCR016230 | HPR119 | 2017-08-01 | Overhead | 7910360 | 9824409 | 11058626
MCR016231 | HPR119 | 2017-09-01 | Labor | 7149297 | 16132326 | 18771856
MCR016232 | HPR119 | 2017-09-01 | Material | 26365065 | 59492539 | 61994115
MCR016233 | HPR119 | 2017-09-01 | Equipment | 5502696 | 12416785 | 12334909
MCR016234 | HPR119 | 2017-09-01 | Subcontract | 20294420 | 45794182 | 45963831
MCR016235 | HPR119 | 2017-09-01 | Overhead | 5420994 | 12232425 | 11642710
MCR016236 | HPR119 | 2017-10-01 | Labor | 3903015 | 21560420 | 25170271
MCR016237 | HPR119 | 2017-10-01 | Material | 14393478 | 79510178 | 87491823
MCR016238 | HPR119 | 2017-10-01 | Equipment | 3004086 | 16594699 | 17536534
MCR016239 | HPR119 | 2017-10-01 | Subcontract | 11079331 | 61202692 | 61213996
MCR016240 | HPR119 | 2017-10-01 | Overhead | 2959483 | 16348307 | 11973177
MCR016241 | HPR119 | 2017-11-01 | Labor | 1041702 | 12532456 | 11982633
MCR016242 | HPR119 | 2017-11-01 | Material | 3841573 | 46216994 | 48227097
MCR016243 | HPR119 | 2017-11-01 | Equipment | 801781 | 9646024 | 9232600
MCR016244 | HPR119 | 2017-11-01 | Subcontract | 2957038 | 35575376 | 42091594
MCR016245 | HPR119 | 2017-11-01 | Overhead | 789876 | 9502804 | 11638408
MCR016246 | HPR119 | 2017-12-01 | Labor | 0 | 8431967 | 9614061
MCR016247 | HPR119 | 2017-12-01 | Material | 0 | 31095277 | 31801919
MCR016248 | HPR119 | 2017-12-01 | Equipment | 0 | 6489946 | 6773615
MCR016249 | HPR119 | 2017-12-01 | Subcontract | 0 | 23935485 | 25731025
MCR016250 | HPR119 | 2017-12-01 | Overhead | 0 | 6393586 | 12570056
MCR016251 | HPR119 | 2018-01-01 | Labor | 0 | 5951997 | 6601865
MCR016252 | HPR119 | 2018-01-01 | Material | 0 | 21949680 | 21975182
MCR016253 | HPR119 | 2018-01-01 | Equipment | 0 | 4581154 | 5246273
MCR016254 | HPR119 | 2018-01-01 | Subcontract | 0 | 16895692 | 16762365
MCR016255 | HPR119 | 2018-01-01 | Overhead | 0 | 4513134 | 12007359
MCR016256 | HPR119 | 2018-02-01 | Labor | 0 | 2961506 | 3753105
MCR016257 | HPR119 | 2018-02-01 | Material | 0 | 10921394 | 12048403
MCR016258 | HPR119 | 2018-02-01 | Equipment | 0 | 2279422 | 2148475
MCR016259 | HPR119 | 2018-02-01 | Subcontract | 0 | 8406706 | 9656157
MCR016260 | HPR119 | 2018-02-01 | Overhead | 0 | 2245578 | 12101603
MCR016261 | HPR119 | 2018-03-01 | Labor | 0 | 530128 | 859462
MCR016262 | HPR119 | 2018-03-01 | Material | 0 | 1954997 | 1807591
MCR016263 | HPR119 | 2018-03-01 | Equipment | 0 | 408031 | 533109
MCR016264 | HPR119 | 2018-03-01 | Subcontract | 0 | 1504852 | 1515708
MCR016265 | HPR119 | 2018-03-01 | Overhead | 0 | 401972 | 12083201
MCR016266 | HPR120 | 2018-02-01 | Labor | 3146019 | 2917954 | 2693109
MCR016267 | HPR120 | 2018-02-01 | Material | 12865161 | 11932522 | 12218304
MCR016268 | HPR120 | 2018-02-01 | Equipment | 7849999 | 7280926 | 7047960
MCR016269 | HPR120 | 2018-02-01 | Subcontract | 6896288 | 6396353 | 6667234
MCR016270 | HPR120 | 2018-02-01 | Overhead | 3287920 | 3049567 | 16133376
MCR016271 | HPR120 | 2018-03-01 | Labor | 8813945 | 5596815 | 5499930
MCR016272 | HPR120 | 2018-03-01 | Material | 36043273 | 22887314 | 24361060
MCR016273 | HPR120 | 2018-03-01 | Equipment | 21992701 | 13965265 | 15334137
MCR016274 | HPR120 | 2018-03-01 | Subcontract | 19320768 | 12268600 | 12253113
MCR016275 | HPR120 | 2018-03-01 | Overhead | 9211497 | 5849258 | 17455434
MCR016276 | HPR120 | 2018-04-01 | Labor | 13564814 | 18611214 | 18011140
MCR016277 | HPR120 | 2018-04-01 | Material | 55471222 | 76107697 | 78533025
MCR016278 | HPR120 | 2018-04-01 | Equipment | 33847148 | 46439007 | 46802527
MCR016279 | HPR120 | 2018-04-01 | Subcontract | 29734996 | 40797048 | 38402207
MCR016280 | HPR120 | 2018-04-01 | Overhead | 14176653 | 19450670 | 16643645
MCR016281 | HPR120 | 2018-05-01 | Labor | 17425332 | 10481016 | 12401109
MCR016282 | HPR120 | 2018-05-01 | Material | 71258215 | 42860504 | 43048082
MCR016283 | HPR120 | 2018-05-01 | Equipment | 43479975 | 26152404 | 27171555
MCR016284 | HPR120 | 2018-05-01 | Subcontract | 38197514 | 22975101 | 23287934
MCR016285 | HPR120 | 2018-05-01 | Overhead | 18211299 | 10953761 | 15889743
MCR016286 | HPR120 | 2018-06-01 | Labor | 20423919 | 19013198 | 19943840
MCR016287 | HPR120 | 2018-06-01 | Material | 83520476 | 77751549 | 80138391
MCR016288 | HPR120 | 2018-06-01 | Equipment | 50962099 | 47442044 | 52931701
MCR016289 | HPR120 | 2018-06-01 | Subcontract | 44770621 | 41678224 | 43913948
MCR016290 | HPR120 | 2018-06-01 | Overhead | 21345137 | 19870785 | 14911445
MCR016291 | HPR120 | 2018-07-01 | Labor | 22590981 | 12176819 | 11589103
MCR016292 | HPR120 | 2018-07-01 | Material | 92382343 | 49795229 | 48423598
MCR016293 | HPR120 | 2018-07-01 | Equipment | 56369388 | 30383799 | 29444961
MCR016294 | HPR120 | 2018-07-01 | Subcontract | 49520969 | 26692416 | 21018335
MCR016295 | HPR120 | 2018-07-01 | Overhead | 23609944 | 12726052 | 15977353
MCR016296 | HPR120 | 2018-08-01 | Labor | 23959247 | 5986084 | 6751608
MCR016297 | HPR120 | 2018-08-01 | Material | 97977654 | 24479168 | 26294669
MCR016298 | HPR120 | 2018-08-01 | Equipment | 59783506 | 14936574 | 17774701
MCR016299 | HPR120 | 2018-08-01 | Subcontract | 52520299 | 13121903 | 14803477
MCR016300 | HPR120 | 2018-08-01 | Overhead | 25039924 | 6256085 | 16482113
MCR016301 | HPR120 | 2018-09-01 | Labor | 24564201 | 22940049 | 24120259
MCR016302 | HPR120 | 2018-09-01 | Material | 100451521 | 93809800 | 82940776
MCR016303 | HPR120 | 2018-09-01 | Equipment | 61292998 | 57240386 | 61267868
MCR016304 | HPR120 | 2018-09-01 | Subcontract | 53846400 | 50286148 | 51856366
MCR016305 | HPR120 | 2018-09-01 | Overhead | 25672165 | 23974755 | 16163149
MCR016306 | HPR120 | 2018-10-01 | Labor | 24444656 | 14444167 | 14454349
MCR016307 | HPR120 | 2018-10-01 | Material | 99962660 | 59067198 | 66295358
MCR016308 | HPR120 | 2018-10-01 | Equipment | 60994707 | 36041322 | 35101277
MCR016309 | HPR120 | 2018-10-01 | Subcontract | 53584349 | 31662597 | 30507842
MCR016310 | HPR120 | 2018-10-01 | Overhead | 25547228 | 15095668 | 15334246
MCR016311 | HPR120 | 2018-11-01 | Labor | 23643515 | 19037380 | 21162892
MCR016312 | HPR120 | 2018-11-01 | Material | 96686518 | 77850437 | 63545355
MCR016313 | HPR120 | 2018-11-01 | Equipment | 58995687 | 47502383 | 45616288
MCR016314 | HPR120 | 2018-11-01 | Subcontract | 51828194 | 41731232 | 43137602
MCR016315 | HPR120 | 2018-11-01 | Overhead | 24709952 | 19896058 | 17094768
MCR016316 | HPR120 | 2018-12-01 | Labor | 22208837 | 35211562 | 35621023
MCR016317 | HPR120 | 2018-12-01 | Material | 90819620 | 143992264 | 163514930
MCR016318 | HPR120 | 2018-12-01 | Equipment | 55415853 | 87860467 | 95226247
MCR016319 | HPR120 | 2018-12-01 | Subcontract | 48683281 | 77186139 | 74735706
MCR016320 | HPR120 | 2018-12-01 | Overhead | 23210562 | 36799773 | 15935381
MCR016321 | HPR120 | 2019-01-01 | Labor | 20195366 | 16079451 | 20383477
MCR016322 | HPR120 | 2019-01-01 | Material | 82585843 | 65754439 | 64486015
MCR016323 | HPR120 | 2019-01-01 | Equipment | 50391809 | 40121709 | 48210990
MCR016324 | HPR120 | 2019-01-01 | Subcontract | 44269617 | 35247250 | 38750273
MCR016325 | HPR120 | 2019-01-01 | Overhead | 21106274 | 16804711 | 17408538
MCR016326 | HPR120 | 2019-02-01 | Labor | 17666864 | 17643928 | 16132903
MCR016327 | HPR120 | 2019-02-01 | Material | 72245924 | 72152128 | 76519299
MCR016328 | HPR120 | 2019-02-01 | Equipment | 44082650 | 44025418 | 44988751
MCR016329 | HPR120 | 2019-02-01 | Subcontract | 38726969 | 38676690 | 31791274
MCR016330 | HPR120 | 2019-02-01 | Overhead | 18463725 | 18439754 | 16604352
MCR016331 | HPR120 | 2019-03-01 | Labor | 14699865 | 10291522 | 12296267
MCR016332 | HPR120 | 2019-03-01 | Material | 60112836 | 42085597 | 40617517
MCR016333 | HPR120 | 2019-03-01 | Equipment | 36679344 | 25679575 | 26676272
MCR016334 | HPR120 | 2019-03-01 | Subcontract | 32223104 | 22559717 | 25135730
MCR016335 | HPR120 | 2019-03-01 | Overhead | 15362900 | 10755720 | 16198272
MCR016336 | HPR120 | 2019-04-01 | Labor | 11390308 | 9999218 | 11186895
MCR016337 | HPR120 | 2019-04-01 | Material | 46578913 | 40890263 | 42110002
MCR016338 | HPR120 | 2019-04-01 | Equipment | 28421284 | 24950213 | 22903413
MCR016339 | HPR120 | 2019-04-01 | Subcontract | 24968330 | 21918966 | 19725901
MCR016340 | HPR120 | 2019-04-01 | Overhead | 11904066 | 10450231 | 16267856
MCR016341 | HPR120 | 2019-05-01 | Labor | 7866861 | 24351639 | 25563808
MCR016342 | HPR120 | 2019-05-01 | Material | 32170317 | 99582281 | 101062187
MCR016343 | HPR120 | 2019-05-01 | Equipment | 19629520 | 60762609 | 66808265
MCR016344 | HPR120 | 2019-05-01 | Subcontract | 17244694 | 53380450 | 53688065
MCR016345 | HPR120 | 2019-05-01 | Overhead | 8221694 | 25450015 | 17923443
MCR016346 | HPR120 | 2019-06-01 | Labor | 4324055 | 11821841 | 11008557
MCR016347 | HPR120 | 2019-06-01 | Material | 17682558 | 48343600 | 48187828
MCR016348 | HPR120 | 2019-06-01 | Equipment | 10789453 | 29498051 | 25252773
MCR016349 | HPR120 | 2019-06-01 | Subcontract | 9478623 | 25914280 | 23204107
MCR016350 | HPR120 | 2019-06-01 | Overhead | 4519091 | 12355063 | 16628897
MCR016351 | HPR120 | 2019-07-01 | Labor | 1160442 | 6831886 | 7512082
MCR016352 | HPR120 | 2019-07-01 | Material | 4745448 | 27937948 | 30851198
MCR016353 | HPR120 | 2019-07-01 | Equipment | 2895553 | 17047035 | 19391269
MCR016354 | HPR120 | 2019-07-01 | Subcontract | 2543767 | 14975960 | 16651136
MCR016355 | HPR120 | 2019-07-01 | Overhead | 1212783 | 7140037 | 17559288
MCR016356 | HPR120 | 2019-08-01 | Labor | 0 | 5500817 | 5716038
MCR016357 | HPR120 | 2019-08-01 | Material | 0 | 22494746 | 20800186
MCR016358 | HPR120 | 2019-08-01 | Equipment | 0 | 13725729 | 14416588
MCR016359 | HPR120 | 2019-08-01 | Subcontract | 0 | 12058166 | 11262504
MCR016360 | HPR120 | 2019-08-01 | Overhead | 0 | 5748931 | 14916100
MCR016361 | HPR120 | 2019-09-01 | Labor | 0 | 6510508 | 5885302
MCR016362 | HPR120 | 2019-09-01 | Material | 0 | 26623720 | 26303483
MCR016363 | HPR120 | 2019-09-01 | Equipment | 0 | 16245126 | 18057463
MCR016364 | HPR120 | 2019-09-01 | Subcontract | 0 | 14271476 | 12835745
MCR016365 | HPR120 | 2019-09-01 | Overhead | 0 | 6804163 | 16554405
MCR016366 | HPR120 | 2019-10-01 | Labor | 0 | 2939628 | 2904548
MCR016367 | HPR120 | 2019-10-01 | Material | 0 | 12021157 | 14154321
MCR016368 | HPR120 | 2019-10-01 | Equipment | 0 | 7335008 | 8169396
MCR016369 | HPR120 | 2019-10-01 | Subcontract | 0 | 6443865 | 6773596
MCR016370 | HPR120 | 2019-10-01 | Overhead | 0 | 3072219 | 17087260
MCR016371 | HPR120 | 2019-11-01 | Labor | 0 | 3025013 | 3102982
MCR016372 | HPR120 | 2019-11-01 | Material | 0 | 12370326 | 13504821
MCR016373 | HPR120 | 2019-11-01 | Equipment | 0 | 7548062 | 7809490
MCR016374 | HPR120 | 2019-11-01 | Subcontract | 0 | 6631035 | 6454665
MCR016375 | HPR120 | 2019-11-01 | Overhead | 0 | 3161456 | 17281796
MCR016376 | HPR120 | 2019-12-01 | Labor | 0 | 677520 | 743362
MCR016377 | HPR120 | 2019-12-01 | Material | 0 | 2770616 | 1954234
MCR016378 | HPR120 | 2019-12-01 | Equipment | 0 | 1690560 | 2395981
MCR016379 | HPR120 | 2019-12-01 | Subcontract | 0 | 1485171 | 1638113
MCR016380 | HPR120 | 2019-12-01 | Overhead | 0 | 708080 | 17022511
MCR016381 | HPR121 | 2016-12-01 | Labor | 12234423 | 11029774 | 10466267
MCR016382 | HPR121 | 2016-12-01 | Material | 29376971 | 26484400 | 26365016
MCR016383 | HPR121 | 2016-12-01 | Equipment | 6297416 | 5677348 | 6063118
MCR016384 | HPR121 | 2016-12-01 | Subcontract | 30287296 | 27305090 | 25560261
MCR016385 | HPR121 | 2016-12-01 | Overhead | 8811830 | 7944183 | 25068128
MCR016386 | HPR121 | 2017-01-01 | Labor | 32228542 | 23209641 | 24388807
MCR016387 | HPR121 | 2017-01-01 | Material | 77386316 | 55730371 | 64032969
MCR016388 | HPR121 | 2017-01-01 | Equipment | 16588975 | 11946682 | 12606050
MCR016389 | HPR121 | 2017-01-01 | Subcontract | 79784341 | 57457328 | 53770718
MCR016390 | HPR121 | 2017-01-01 | Overhead | 23212572 | 16716719 | 25181767
MCR016391 | HPR121 | 2017-02-01 | Labor | 45776377 | 27947576 | 29868681
MCR016392 | HPR121 | 2017-02-01 | Material | 109917015 | 67106975 | 52327251
MCR016393 | HPR121 | 2017-02-01 | Equipment | 23562442 | 14385436 | 13428131
MCR016394 | HPR121 | 2017-02-01 | Subcontract | 113323091 | 69186466 | 67888348
MCR016395 | HPR121 | 2017-02-01 | Overhead | 32970385 | 20129211 | 26298900
MCR016396 | HPR121 | 2017-03-01 | Labor | 53267508 | 40098145 | 44224423
MCR016397 | HPR121 | 2017-03-01 | Material | 127904518 | 96282595 | 99336149
MCR016398 | HPR121 | 2017-03-01 | Equipment | 27418347 | 20639690 | 23069164
MCR016399 | HPR121 | 2017-03-01 | Subcontract | 131867986 | 99266172 | 93170106
MCR016400 | HPR121 | 2017-03-01 | Overhead | 38365864 | 28880645 | 23941159
MCR016401 | HPR121 | 2017-04-01 | Labor | 55147452 | 39584262 | 43544822
MCR016402 | HPR121 | 2017-04-01 | Material | 132418590 | 95048674 | 104761101
MCR016403 | HPR121 | 2017-04-01 | Equipment | 28386009 | 20375179 | 18769378
MCR016404 | HPR121 | 2017-04-01 | Subcontract | 136521939 | 97994015 | 97115768
MCR016405 | HPR121 | 2017-04-01 | Overhead | 39719892 | 28510522 | 22980575
MCR016406 | HPR121 | 2017-05-01 | Labor | 51939330 | 47463339 | 55914114
MCR016407 | HPR121 | 2017-05-01 | Material | 124715333 | 113967703 | 121294165
MCR016408 | HPR121 | 2017-05-01 | Equipment | 26734695 | 24430771 | 23349984
MCR016409 | HPR121 | 2017-05-01 | Subcontract | 128579975 | 117499300 | 113273670
MCR016410 | HPR121 | 2017-05-01 | Overhead | 37409246 | 34185418 | 25269739
MCR016411 | HPR121 | 2017-06-01 | Labor | 44281338 | 39117950 | 46096339
MCR016412 | HPR121 | 2017-06-01 | Material | 106327168 | 93928977 | 107445587
MCR016413 | HPR121 | 2017-06-01 | Equipment | 22792902 | 20135155 | 22468071
MCR016414 | HPR121 | 2017-06-01 | Subcontract | 109622003 | 96839621 | 91325657
MCR016415 | HPR121 | 2017-06-01 | Overhead | 31893585 | 28174660 | 25428316
MCR016416 | HPR121 | 2017-07-01 | Labor | 33000285 | 16881910 | 15851179
MCR016417 | HPR121 | 2017-07-01 | Material | 79239404 | 40536393 | 35080799
MCR016418 | HPR121 | 2017-07-01 | Equipment | 16986214 | 8689614 | 8431452
MCR016419 | HPR121 | 2017-07-01 | Subcontract | 81694852 | 41792523 | 45727187
MCR016420 | HPR121 | 2017-07-01 | Overhead | 23768419 | 12159177 | 25447819
MCR016421 | HPR121 | 2017-08-01 | Labor | 19289709 | 32835633 | 36162359
MCR016422 | HPR121 | 2017-08-01 | Material | 46317934 | 78844046 | 82151268
MCR016423 | HPR121 | 2017-08-01 | Equipment | 9928978 | 16901462 | 17331611
MCR016424 | HPR121 | 2017-08-01 | Subcontract | 47753221 | 81287242 | 84363446
MCR016425 | HPR121 | 2017-08-01 | Overhead | 13893392 | 23649829 | 26319110
MCR016426 | HPR121 | 2017-09-01 | Labor | 5425109 | 34498239 | 36281286
MCR016427 | HPR121 | 2017-09-01 | Material | 13026627 | 82836252 | 80773415
MCR016428 | HPR121 | 2017-09-01 | Equipment | 2792462 | 17757255 | 22039739
MCR016429 | HPR121 | 2017-09-01 | Subcontract | 13430292 | 85403158 | 106137726
MCR016430 | HPR121 | 2017-09-01 | Overhead | 3907429 | 24847319 | 25119640
MCR016431 | HPR121 | 2017-10-01 | Labor | 0 | 23044563 | 30736194
MCR016432 | HPR121 | 2017-10-01 | Material | 0 | 55333990 | 53024440
MCR016433 | HPR121 | 2017-10-01 | Equipment | 0 | 11861712 | 11735868
MCR016434 | HPR121 | 2017-10-01 | Subcontract | 0 | 57048664 | 63084946
MCR016435 | HPR121 | 2017-10-01 | Overhead | 0 | 16597821 | 27714377
MCR016436 | HPR121 | 2017-11-01 | Labor | 0 | 12902963 | 10702602
MCR016437 | HPR121 | 2017-11-01 | Material | 0 | 30982250 | 37641739
MCR016438 | HPR121 | 2017-11-01 | Equipment | 0 | 6641533 | 7164264
MCR016439 | HPR121 | 2017-11-01 | Subcontract | 0 | 31942319 | 53990196
MCR016440 | HPR121 | 2017-11-01 | Overhead | 0 | 9293345 | 23128894
MCR016441 | HPR121 | 2017-12-01 | Labor | 0 | 3976078 | 5645998
MCR016442 | HPR121 | 2017-12-01 | Material | 0 | 9547251 | 8681818
MCR016443 | HPR121 | 2017-12-01 | Equipment | 0 | 2046604 | 2214814
MCR016444 | HPR121 | 2017-12-01 | Subcontract | 0 | 9843099 | 33222825
MCR016445 | HPR121 | 2017-12-01 | Overhead | 0 | 2863765 | 26422076
MCR016446 | HPR122 | 2018-11-01 | Labor | 18553253 | 7718979 | 9471385
MCR016447 | HPR122 | 2018-11-01 | Material | 55370784 | 23036709 | 24617069
MCR016448 | HPR122 | 2018-11-01 | Equipment | 14445652 | 6010034 | 5977717
MCR016449 | HPR122 | 2018-11-01 | Subcontract | 53717850 | 22349015 | 21713959
MCR016450 | HPR122 | 2018-11-01 | Overhead | 13821238 | 5750250 | 55181116
MCR016451 | HPR122 | 2018-12-01 | Labor | 50886966 | 23258632 | 24477646
MCR016452 | HPR122 | 2018-12-01 | Material | 151868313 | 69413635 | 75784228
MCR016453 | HPR122 | 2018-12-01 | Equipment | 39620835 | 18109282 | 17677913
MCR016454 | HPR122 | 2018-12-01 | Subcontract | 147334725 | 67341492 | 69124387
MCR016455 | HPR122 | 2018-12-01 | Overhead | 37908224 | 17326508 | 50018315
MCR016456 | HPR122 | 2019-01-01 | Labor | 76254341 | 28582300 | 27326730
MCR016457 | HPR122 | 2019-01-01 | Material | 227575330 | 85301718 | 90324475
MCR016458 | HPR122 | 2019-01-01 | Equipment | 59371995 | 22254315 | 25512621
MCR016459 | HPR122 | 2019-01-01 | Subcontract | 220781729 | 82755283 | 93177503
MCR016460 | HPR122 | 2019-01-01 | Overhead | 56805639 | 21292372 | 55490607
MCR016461 | HPR122 | 2019-02-01 | Labor | 94929147 | 66254085 | 72542245
MCR016462 | HPR122 | 2019-02-01 | Material | 283308879 | 197730321 | 195398207
MCR016463 | HPR122 | 2019-02-01 | Equipment | 73912288 | 51585748 | 57506713
MCR016464 | HPR122 | 2019-02-01 | Subcontract | 274851514 | 191827656 | 216163563
MCR016465 | HPR122 | 2019-02-01 | Overhead | 70717428 | 49355953 | 49358174
MCR016466 | HPR122 | 2019-03-01 | Labor | 107209438 | 79343934 | 89639919
MCR016467 | HPR122 | 2019-03-01 | Material | 319958483 | 236795987 | 212825312
MCR016468 | HPR122 | 2019-03-01 | Equipment | 83473781 | 61777566 | 64036047
MCR016469 | HPR122 | 2019-03-01 | Subcontract | 310407050 | 229727130 | 217940412
MCR016470 | HPR122 | 2019-03-01 | Overhead | 79865626 | 59107230 | 58448209
MCR016471 | HPR122 | 2019-04-01 | Labor | 113422973 | 79643255 | 86303402
MCR016472 | HPR122 | 2019-04-01 | Material | 338502310 | 237689287 | 291466567
MCR016473 | HPR122 | 2019-04-01 | Equipment | 88311670 | 62010619 | 63601402
MCR016474 | HPR122 | 2019-04-01 | Subcontract | 328397306 | 230593763 | 259637189
MCR016475 | HPR122 | 2019-04-01 | Overhead | 84494396 | 59330209 | 51642844
MCR016476 | HPR122 | 2019-05-01 | Labor | 113934690 | 45516516 | 50201334
MCR016477 | HPR122 | 2019-05-01 | Material | 340029490 | 135840609 | 87671694
MCR016478 | HPR122 | 2019-05-01 | Equipment | 88710095 | 35439377 | 37208267
MCR016479 | HPR122 | 2019-05-01 | Subcontract | 329878896 | 131785482 | 120986526
MCR016480 | HPR122 | 2019-05-01 | Overhead | 84875599 | 33907509 | 59014473
MCR016481 | HPR122 | 2019-06-01 | Labor | 109157432 | 60774845 | 57132903
MCR016482 | HPR122 | 2019-06-01 | Material | 325772124 | 181377942 | 209284373
MCR016483 | HPR122 | 2019-06-01 | Equipment | 84990499 | 47319585 | 55579866
MCR016484 | HPR122 | 2019-06-01 | Subcontract | 316047143 | 175963429 | 164393664
MCR016485 | HPR122 | 2019-06-01 | Overhead | 81316783 | 45274195 | 52997893
MCR016486 | HPR122 | 2019-07-01 | Labor | 99568104 | 47167727 | 55274779
MCR016487 | HPR122 | 2019-07-01 | Material | 297153497 | 140768524 | 144205152
MCR016488 | HPR122 | 2019-07-01 | Equipment | 77524202 | 36725018 | 34090441
MCR016489 | HPR122 | 2019-07-01 | Subcontract | 288282842 | 136566288 | 145495028
MCR016490 | HPR122 | 2019-07-01 | Overhead | 74173217 | 35137578 | 53908200
MCR016491 | HPR122 | 2019-08-01 | Labor | 85733593 | 76405228 | 74960776
MCR016492 | HPR122 | 2019-08-01 | Material | 255865442 | 228025640 | 230159372
MCR016493 | HPR122 | 2019-08-01 | Equipment | 66752585 | 59489476 | 61212744
MCR016494 | HPR122 | 2019-08-01 | Subcontract | 248227321 | 221218596 | 241582895
MCR016495 | HPR122 | 2019-08-01 | Overhead | 63867204 | 56918042 | 56331346
MCR016496 | HPR122 | 2019-09-01 | Labor | 68356153 | 98858758 | 108681905
MCR016497 | HPR122 | 2019-09-01 | Material | 204003784 | 295036508 | 262222682
MCR016498 | HPR122 | 2019-09-01 | Equipment | 53222428 | 76971902 | 85339696
MCR016499 | HPR122 | 2019-09-01 | Subcontract | 197913843 | 286229049 | 305039052
MCR016500 | HPR122 | 2019-09-01 | Overhead | 50921887 | 73644790 | 52953834
MCR016501 | HPR122 | 2019-10-01 | Labor | 48363715 | 59752155 | 67186289
MCR016502 | HPR122 | 2019-10-01 | Material | 144337860 | 178325801 | 207481883
MCR016503 | HPR122 | 2019-10-01 | Equipment | 37656220 | 46523314 | 43620844
MCR016504 | HPR122 | 2019-10-01 | Subcontract | 140029072 | 173002402 | 171636489
MCR016505 | HPR122 | 2019-10-01 | Overhead | 36028529 | 44512343 | 53882829
MCR016506 | HPR122 | 2019-11-01 | Labor | 27132265 | 43921210 | 46680708
MCR016507 | HPR122 | 2019-11-01 | Material | 80974198 | 131079540 | 141790105
MCR016508 | HPR122 | 2019-11-01 | Equipment | 21125311 | 34197265 | 40373885
MCR016509 | HPR122 | 2019-11-01 | Subcontract | 78556948 | 127166541 | 139463855
MCR016510 | HPR122 | 2019-11-01 | Overhead | 20212169 | 32719087 | 54658400
MCR016511 | HPR122 | 2019-12-01 | Labor | 7399903 | 64851728 | 67911305
MCR016512 | HPR122 | 2019-12-01 | Material | 22084453 | 193545091 | 207652499
MCR016513 | HPR122 | 2019-12-01 | Equipment | 5761600 | 50493866 | 54329882
MCR016514 | HPR122 | 2019-12-01 | Subcontract | 21425186 | 187767364 | 185099938
MCR016515 | HPR122 | 2019-12-01 | Overhead | 5512555 | 48311267 | 51095604
MCR016516 | HPR122 | 2020-01-01 | Labor | 0 | 50288311 | 57176024
MCR016517 | HPR122 | 2020-01-01 | Material | 0 | 150081671 | 121249474
MCR016518 | HPR122 | 2020-01-01 | Equipment | 0 | 39154719 | 42141513
MCR016519 | HPR122 | 2020-01-01 | Subcontract | 0 | 145601418 | 157152631
MCR016520 | HPR122 | 2020-01-01 | Overhead | 0 | 37462256 | 51912414
MCR016521 | HPR122 | 2020-02-01 | Labor | 0 | 61443030 | 66977459
MCR016522 | HPR122 | 2020-02-01 | Material | 0 | 183372090 | 170690489
MCR016523 | HPR122 | 2020-02-01 | Equipment | 0 | 47839837 | 48545335
MCR016524 | HPR122 | 2020-02-01 | Subcontract | 0 | 177898048 | 185602051
MCR016525 | HPR122 | 2020-02-01 | Overhead | 0 | 45771960 | 52123344
MCR016526 | HPR122 | 2020-03-01 | Labor | 0 | 63258232 | 57789172
MCR016527 | HPR122 | 2020-03-01 | Material | 0 | 188789421 | 223314799
MCR016528 | HPR122 | 2020-03-01 | Equipment | 0 | 49253162 | 54955376
MCR016529 | HPR122 | 2020-03-01 | Subcontract | 0 | 183153661 | 186485195
MCR016530 | HPR122 | 2020-03-01 | Overhead | 0 | 47124193 | 54916389
MCR016531 | HPR122 | 2020-04-01 | Labor | 0 | 40372527 | 51120091
MCR016532 | HPR122 | 2020-04-01 | Material | 0 | 120488762 | 110838506
MCR016533 | HPR122 | 2020-04-01 | Equipment | 0 | 31434243 | 37593705
MCR016534 | HPR122 | 2020-04-01 | Subcontract | 0 | 116891920 | 109907700
MCR016535 | HPR122 | 2020-04-01 | Overhead | 0 | 30075497 | 52090148
MCR016536 | HPR122 | 2020-05-01 | Labor | 0 | 17811333 | 15858424
MCR016537 | HPR122 | 2020-05-01 | Material | 0 | 53156581 | 60616783
MCR016538 | HPR122 | 2020-05-01 | Equipment | 0 | 13867989 | 20405192
MCR016539 | HPR122 | 2020-05-01 | Subcontract | 0 | 51569746 | 62934234
MCR016540 | HPR122 | 2020-05-01 | Overhead | 0 | 13268545 | 53850277
MCR016541 | HPR122 | 2020-06-01 | Labor | 0 | 5679188 | 4642017
MCR016542 | HPR122 | 2020-06-01 | Material | 0 | 16949110 | 12337585
MCR016543 | HPR122 | 2020-06-01 | Equipment | 0 | 4421843 | 4038059
MCR016544 | HPR122 | 2020-06-01 | Subcontract | 0 | 16443143 | 18490454
MCR016545 | HPR122 | 2020-06-01 | Overhead | 0 | 4230709 | 54933334
MCR016546 | HPR123 | 2017-05-01 | Labor | 3848583 | 5694143 | 5761171
MCR016547 | HPR123 | 2017-05-01 | Material | 8901942 | 13170801 | 12379943
MCR016548 | HPR123 | 2017-05-01 | Equipment | 1815863 | 2686647 | 3121883
MCR016549 | HPR123 | 2017-05-01 | Subcontract | 9939507 | 14705923 | 13431198
MCR016550 | HPR123 | 2017-05-01 | Overhead | 2545346 | 3765947 | 9792299
MCR016551 | HPR123 | 2017-06-01 | Labor | 10555709 | 8492426 | 9376278
MCR016552 | HPR123 | 2017-06-01 | Material | 24415816 | 19643353 | 18711199
MCR016553 | HPR123 | 2017-06-01 | Equipment | 4980462 | 4006951 | 3451212
MCR016554 | HPR123 | 2017-06-01 | Subcontract | 27261600 | 21932883 | 22359304
MCR016555 | HPR123 | 2017-06-01 | Overhead | 6981251 | 5616654 | 10254844
MCR016556 | HPR123 | 2017-07-01 | Labor | 15817775 | 12410502 | 12563419
MCR016557 | HPR123 | 2017-07-01 | Material | 36587207 | 28706034 | 31715694
MCR016558 | HPR123 | 2017-07-01 | Equipment | 7463244 | 5855602 | 5943349
MCR016559 | HPR123 | 2017-07-01 | Subcontract | 40851626 | 32051864 | 35427868
MCR016560 | HPR123 | 2017-07-01 | Overhead | 10461436 | 8207960 | 9843453
MCR016561 | HPR123 | 2017-08-01 | Labor | 19691573 | 11600037 | 10011210
MCR016562 | HPR123 | 2017-08-01 | Material | 45547470 | 26831393 | 27156564
MCR016563 | HPR123 | 2017-08-01 | Equipment | 9291004 | 5473204 | 5344151
MCR016564 | HPR123 | 2017-08-01 | Subcontract | 50856253 | 29958724 | 27570317
MCR016565 | HPR123 | 2017-08-01 | Overhead | 13023457 | 7671941 | 11036045
MCR016566 | HPR123 | 2017-09-01 | Labor | 22238928 | 21620676 | 22410619
MCR016567 | HPR123 | 2017-09-01 | Material | 51439614 | 50009570 | 47413430
MCR016568 | HPR123 | 2017-09-01 | Equipment | 10492913 | 10201206 | 11757739
MCR016569 | HPR123 | 2017-09-01 | Subcontract | 57435155 | 55838432 | 59225981
MCR016570 | HPR123 | 2017-09-01 | Overhead | 14708207 | 14299312 | 9187459
MCR016571 | HPR123 | 2017-10-01 | Labor | 23527829 | 23511051 | 23092174
MCR016572 | HPR123 | 2017-10-01 | Material | 54420899 | 54382090 | 59600801
MCR016573 | HPR123 | 2017-10-01 | Equipment | 11101051 | 11093135 | 10515627
MCR016574 | HPR123 | 2017-10-01 | Subcontract | 60763923 | 60720591 | 66737254
MCR016575 | HPR123 | 2017-10-01 | Overhead | 15560650 | 15549554 | 9794754
MCR016576 | HPR123 | 2017-11-01 | Labor | 23633977 | 15637006 | 14042891
MCR016577 | HPR123 | 2017-11-01 | Material | 54666423 | 36169079 | 32448078
MCR016578 | HPR123 | 2017-11-01 | Equipment | 11151134 | 7377952 | 7637829
MCR016579 | HPR123 | 2017-11-01 | Subcontract | 61038065 | 40384763 | 35811426
MCR016580 | HPR123 | 2017-11-01 | Overhead | 15630853 | 10341880 | 9779313
MCR016581 | HPR123 | 2017-12-01 | Labor | 22643009 | 26020851 | 26099313
MCR016582 | HPR123 | 2017-12-01 | Material | 52374272 | 60187367 | 64234880
MCR016583 | HPR123 | 2017-12-01 | Equipment | 10683569 | 12277324 | 12704008
MCR016584 | HPR123 | 2017-12-01 | Subcontract | 58478751 | 67202501 | 73350739
MCR016585 | HPR123 | 2017-12-01 | Overhead | 14975455 | 17209465 | 10467415
MCR016586 | HPR123 | 2018-01-01 | Labor | 20653852 | 25236490 | 24548152
MCR016587 | HPR123 | 2018-01-01 | Material | 47773265 | 58373105 | 58546041
MCR016588 | HPR123 | 2018-01-01 | Equipment | 9745033 | 11907242 | 10237414
MCR016589 | HPR123 | 2018-01-01 | Subcontract | 53341474 | 65176779 | 68180680
MCR016590 | HPR123 | 2018-01-01 | Overhead | 13659882 | 16690711 | 9428868
MCR016591 | HPR123 | 2018-02-01 | Labor | 17784099 | 21402960 | 30714394
MCR016592 | HPR123 | 2018-02-01 | Material | 41135398 | 49505983 | 58387305
MCR016593 | HPR123 | 2018-02-01 | Equipment | 8391007 | 10098481 | 11581854
MCR016594 | HPR123 | 2018-02-01 | Subcontract | 45929932 | 55276149 | 55941103
MCR016595 | HPR123 | 2018-02-01 | Overhead | 11761907 | 14155321 | 10659027
MCR016596 | HPR123 | 2018-03-01 | Labor | 14179419 | 16342111 | 20421091
MCR016597 | HPR123 | 2018-03-01 | Material | 32797618 | 37800018 | 44916678
MCR016598 | HPR123 | 2018-03-01 | Equipment | 6690224 | 7710639 | 6856454
MCR016599 | HPR123 | 2018-03-01 | Subcontract | 36620342 | 42205797 | 43067426
MCR016600 | HPR123 | 2018-03-01 | Overhead | 9377873 | 10808217 | 9985693
MCR016601 | HPR123 | 2018-04-01 | Labor | 10032299 | 15178935 | 15450586
MCR016602 | HPR123 | 2018-04-01 | Material | 23205148 | 35109541 | 33444557
MCR016603 | HPR123 | 2018-04-01 | Equipment | 4733504 | 7161822 | 7035941
MCR016604 | HPR123 | 2018-04-01 | Subcontract | 25909822 | 39201731 | 38474576
MCR016605 | HPR123 | 2018-04-01 | Overhead | 6635083 | 10038924 | 8349862
MCR016606 | HPR123 | 2018-05-01 | Labor | 5628166 | 5523392 | 6035523
MCR016607 | HPR123 | 2018-05-01 | Material | 13018194 | 12775848 | 12146928
MCR016608 | HPR123 | 2018-05-01 | Equipment | 2655517 | 2606082 | 2577121
MCR016609 | HPR123 | 2018-05-01 | Subcontract | 14535528 | 14264936 | 14281669
MCR016610 | HPR123 | 2018-05-01 | Overhead | 3722312 | 3653018 | 10801685
MCR016611 | HPR123 | 2018-06-01 | Labor | 1534995 | 3099635 | 2738611
MCR016612 | HPR123 | 2018-06-01 | Material | 3550510 | 7169593 | 7639219
MCR016613 | HPR123 | 2018-06-01 | Equipment | 724251 | 1462490 | 1471629
MCR016614 | HPR123 | 2018-06-01 | Subcontract | 3964339 | 8005244 | 7490244
MCR016615 | HPR123 | 2018-06-01 | Overhead | 1015203 | 2050012 | 9692692
MCR016616 | HPR124 | 2022-12-01 | Labor | 3858871 | 2148151 | 2429099
MCR016617 | HPR124 | 2022-12-01 | Material | 9425488 | 5246967 | 5962714
MCR016618 | HPR124 | 2022-12-01 | Equipment | 2521846 | 1403858 | 1575276
MCR016619 | HPR124 | 2022-12-01 | Subcontract | 12153463 | 6765572 | 5481814
MCR016620 | HPR124 | 2022-12-01 | Overhead | 2841102 | 1581581 | 13987926
MCR016621 | HPR124 | 2023-01-01 | Labor | 10811085 | 13032838 | 14626255
MCR016622 | HPR124 | 2023-01-01 | Material | 26406622 | 31833366 | 28017370
MCR016623 | HPR124 | 2023-01-01 | Equipment | 7065250 | 8517208 | 7791347
MCR016624 | HPR124 | 2023-01-01 | Subcontract | 34049365 | 41046744 | 42573205
MCR016625 | HPR124 | 2023-01-01 | Overhead | 7959684 | 9595454 | 14739568
MCR016626 | HPR124 | 2023-02-01 | Labor | 16638448 | 13600480 | 14009333
MCR016627 | HPR124 | 2023-02-01 | Material | 40640249 | 33219861 | 37562805
MCR016628 | HPR124 | 2023-02-01 | Equipment | 10873542 | 8888173 | 8739564
MCR016629 | HPR124 | 2023-02-01 | Subcontract | 52402562 | 42834526 | 49897557
MCR016630 | HPR124 | 2023-02-01 | Overhead | 12250092 | 10013382 | 14161927
MCR016631 | HPR124 | 2023-03-01 | Labor | 21373715 | 13856637 | 16248462
MCR016632 | HPR124 | 2023-03-01 | Material | 52206379 | 33845537 | 30928653
MCR016633 | HPR124 | 2023-03-01 | Equipment | 13968130 | 9055576 | 9679565
MCR016634 | HPR124 | 2023-03-01 | Subcontract | 67316221 | 43641289 | 39476313
MCR016635 | HPR124 | 2023-03-01 | Overhead | 15736442 | 10201978 | 14421415
MCR016636 | HPR124 | 2023-04-01 | Labor | 25051748 | 31390779 | 35672984
MCR016637 | HPR124 | 2023-04-01 | Material | 61190160 | 76673565 | 80946509
MCR016638 | HPR124 | 2023-04-01 | Equipment | 16371794 | 20514472 | 21012058
MCR016639 | HPR124 | 2023-04-01 | Subcontract | 78900136 | 98864829 | 95974580
MCR016640 | HPR124 | 2023-04-01 | Overhead | 18444401 | 23111527 | 13186305
MCR016641 | HPR124 | 2023-05-01 | Labor | 27709842 | 28078826 | 27662229
MCR016642 | HPR124 | 2023-05-01 | Material | 67682689 | 68583952 | 67319847
MCR016643 | HPR124 | 2023-05-01 | Equipment | 18108909 | 18350048 | 18916517
MCR016644 | HPR124 | 2023-05-01 | Subcontract | 87271766 | 88433878 | 95611717
MCR016645 | HPR124 | 2023-05-01 | Overhead | 20401429 | 20673094 | 13943811
MCR016646 | HPR124 | 2023-06-01 | Labor | 29388140 | 29296649 | 37672549
MCR016647 | HPR124 | 2023-06-01 | Material | 71782018 | 71558545 | 64423728
MCR016648 | HPR124 | 2023-06-01 | Equipment | 19205710 | 19145918 | 18279279
MCR016649 | HPR124 | 2023-06-01 | Subcontract | 92557545 | 92269393 | 93517627
MCR016650 | HPR124 | 2023-06-01 | Overhead | 21637079 | 21569719 | 13226704
MCR016651 | HPR124 | 2023-07-01 | Labor | 30130170 | 18196500 | 17289771
MCR016652 | HPR124 | 2023-07-01 | Material | 73594464 | 44445871 | 48308469
MCR016653 | HPR124 | 2023-07-01 | Equipment | 19690640 | 11891759 | 11543877
MCR016654 | HPR124 | 2023-07-01 | Subcontract | 94894558 | 57309626 | 51349373
MCR016655 | HPR124 | 2023-07-01 | Overhead | 22183401 | 13397211 | 15143337
MCR016656 | HPR124 | 2023-08-01 | Labor | 29983538 | 16002881 | 17998884
MCR016657 | HPR124 | 2023-08-01 | Material | 73236307 | 39087845 | 35529865
MCR016658 | HPR124 | 2023-08-01 | Equipment | 19594813 | 10458188 | 12007611
MCR016659 | HPR124 | 2023-08-01 | Subcontract | 94432741 | 50400854 | 58141478
MCR016660 | HPR124 | 2023-08-01 | Overhead | 22075442 | 11782154 | 13650517
MCR016661 | HPR124 | 2023-09-01 | Labor | 29000868 | 27727733 | 28711217
MCR016662 | HPR124 | 2023-09-01 | Material | 70836085 | 67726390 | 59969654
MCR016663 | HPR124 | 2023-09-01 | Equipment | 18952619 | 18120602 | 19570633
MCR016664 | HPR124 | 2023-09-01 | Subcontract | 91337834 | 87328115 | 91461604
MCR016665 | HPR124 | 2023-09-01 | Overhead | 21351949 | 20414601 | 13670444
MCR016666 | HPR124 | 2023-10-01 | Labor | 27241107 | 16413598 | 17755716
MCR016667 | HPR124 | 2023-10-01 | Material | 66537781 | 40091043 | 43458912
MCR016668 | HPR124 | 2023-10-01 | Equipment | 17802582 | 10726599 | 9916206
MCR016669 | HPR124 | 2023-10-01 | Subcontract | 85795492 | 51694401 | 52576839
MCR016670 | HPR124 | 2023-10-01 | Overhead | 20056322 | 12084546 | 14031004
MCR016671 | HPR124 | 2023-11-01 | Labor | 24771407 | 20752019 | 24067194
MCR016672 | HPR124 | 2023-11-01 | Material | 60505414 | 50687855 | 52637748
MCR016673 | HPR124 | 2023-11-01 | Equipment | 16188586 | 13561840 | 14088537
MCR016674 | HPR124 | 2023-11-01 | Subcontract | 78017206 | 65358199 | 69615319
MCR016675 | HPR124 | 2023-11-01 | Overhead | 18238000 | 15278717 | 14100736
MCR016676 | HPR124 | 2023-12-01 | Labor | 21669976 | 14560599 | 15450643
MCR016677 | HPR124 | 2023-12-01 | Material | 52930011 | 35564998 | 38005196
MCR016678 | HPR124 | 2023-12-01 | Equipment | 14161742 | 9515629 | 9922031
MCR016679 | HPR124 | 2023-12-01 | Subcontract | 68249291 | 45858405 | 43717173
MCR016680 | HPR124 | 2023-12-01 | Overhead | 15954565 | 10720271 | 14146762
MCR016681 | HPR124 | 2024-01-01 | Labor | 18030688 | 14014155 | 16136731
MCR016682 | HPR124 | 2024-01-01 | Material | 44040866 | 34230282 | 30404622
MCR016683 | HPR124 | 2024-01-01 | Equipment | 11783398 | 9158517 | 10370951
MCR016684 | HPR124 | 2024-01-01 | Subcontract | 56787403 | 44137390 | 49790870
MCR016685 | HPR124 | 2024-01-01 | Overhead | 13275131 | 10317951 | 12798328
MCR016686 | HPR124 | 2024-02-01 | Labor | 13971223 | 15746108 | 20195559
MCR016687 | HPR124 | 2024-02-01 | Material | 34125418 | 38460663 | 39517928
MCR016688 | HPR124 | 2024-02-01 | Equipment | 9130460 | 10290381 | 9903729
MCR016689 | HPR124 | 2024-02-01 | Subcontract | 44002174 | 49592149 | 41813414
MCR016690 | HPR124 | 2024-02-01 | Overhead | 10286342 | 11593104 | 14435542
MCR016691 | HPR124 | 2024-03-01 | Labor | 9649402 | 25299210 | 30145213
MCR016692 | HPR124 | 2024-03-01 | Material | 23569153 | 61794598 | 53282851
MCR016693 | HPR124 | 2024-03-01 | Equipment | 6306068 | 16533515 | 16811804
MCR016694 | HPR124 | 2024-03-01 | Subcontract | 30390660 | 79679513 | 85292821
MCR016695 | HPR124 | 2024-03-01 | Overhead | 7104392 | 18626596 | 14488651
MCR016696 | HPR124 | 2024-04-01 | Labor | 5303837 | 14879069 | 13276005
MCR016697 | HPR124 | 2024-04-01 | Material | 12954890 | 36342878 | 40258413
MCR016698 | HPR124 | 2024-04-01 | Equipment | 3466158 | 9723755 | 9666658
MCR016699 | HPR124 | 2024-04-01 | Subcontract | 16704361 | 46861423 | 51615099
MCR016700 | HPR124 | 2024-04-01 | Overhead | 3904961 | 10954745 | 14113091
MCR016701 | HPR124 | 2024-05-01 | Labor | 1423385 | 12307168 | 14407501
MCR016702 | HPR124 | 2024-05-01 | Material | 3476689 | 30060881 | 28529862
MCR016703 | HPR124 | 2024-05-01 | Equipment | 930209 | 8042969 | 9768396
MCR016704 | HPR124 | 2024-05-01 | Subcontract | 4482931 | 38761257 | 33944030
MCR016705 | HPR124 | 2024-05-01 | Overhead | 1047970 | 9061178 | 14892387
MCR016706 | HPR124 | 2024-06-01 | Labor | 0 | 8178699 | 9964219
MCR016707 | HPR124 | 2024-06-01 | Material | 0 | 19976886 | 20264682
MCR016708 | HPR124 | 2024-06-01 | Equipment | 0 | 5344936 | 5003766
MCR016709 | HPR124 | 2024-06-01 | Subcontract | 0 | 25758701 | 28263488
MCR016710 | HPR124 | 2024-06-01 | Overhead | 0 | 6021584 | 13896301
MCR016711 | HPR124 | 2024-07-01 | Labor | 0 | 6277830 | 6814220
MCR016712 | HPR124 | 2024-07-01 | Material | 0 | 15333916 | 13504174
MCR016713 | HPR124 | 2024-07-01 | Equipment | 0 | 4102681 | 4381670
MCR016714 | HPR124 | 2024-07-01 | Subcontract | 0 | 19771938 | 20995064
MCR016715 | HPR124 | 2024-07-01 | Overhead | 0 | 4622065 | 13200701
MCR016716 | HPR124 | 2024-08-01 | Labor | 0 | 3207123 | 3428731
MCR016717 | HPR124 | 2024-08-01 | Material | 0 | 7833561 | 8117399
MCR016718 | HPR124 | 2024-08-01 | Equipment | 0 | 2095916 | 2618034
MCR016719 | HPR124 | 2024-08-01 | Subcontract | 0 | 10100791 | 10245188
MCR016720 | HPR124 | 2024-08-01 | Overhead | 0 | 2361251 | 14705802
MCR016721 | HPR124 | 2024-09-01 | Labor | 0 | 1040397 | 1308971
MCR016722 | HPR124 | 2024-09-01 | Material | 0 | 2541221 | 2849491
MCR016723 | HPR124 | 2024-09-01 | Equipment | 0 | 679919 | 702646
MCR016724 | HPR124 | 2024-09-01 | Subcontract | 0 | 3276715 | 2497781
MCR016725 | HPR124 | 2024-09-01 | Overhead | 0 | 765994 | 14390471
MCR016726 | HPR125 | 2017-09-01 | Labor | 7617020 | 9522749 | 9924462
MCR016727 | HPR125 | 2017-09-01 | Material | 14285209 | 17859276 | 20045359
MCR016728 | HPR125 | 2017-09-01 | Equipment | 3672051 | 4590775 | 4247480
MCR016729 | HPR125 | 2017-09-01 | Subcontract | 17254548 | 21571525 | 21315823
MCR016730 | HPR125 | 2017-09-01 | Overhead | 4262439 | 5328874 | 23132084
MCR016731 | HPR125 | 2017-10-01 | Labor | 21495138 | 21501729 | 23378264
MCR016732 | HPR125 | 2017-10-01 | Material | 40312685 | 40325047 | 49019237
MCR016733 | HPR125 | 2017-10-01 | Equipment | 10362484 | 10365662 | 11154026
MCR016734 | HPR125 | 2017-10-01 | Subcontract | 48692125 | 48707056 | 48237857
MCR016735 | HPR125 | 2017-10-01 | Overhead | 12028551 | 12032239 | 21924600
MCR016736 | HPR125 | 2017-11-01 | Labor | 33376410 | 22026221 | 22509843
MCR016737 | HPR125 | 2017-11-01 | Material | 62595212 | 41308697 | 34555925
MCR016738 | HPR125 | 2017-11-01 | Equipment | 16090267 | 10618511 | 10375802
MCR016739 | HPR125 | 2017-11-01 | Subcontract | 75606323 | 49895169 | 53677779
MCR016740 | HPR125 | 2017-11-01 | Overhead | 18677240 | 12325742 | 24466806
MCR016741 | HPR125 | 2017-12-01 | Labor | 43312321 | 32256201 | 31926947
MCR016742 | HPR125 | 2017-12-01 | Material | 81229345 | 60494336 | 61714695
MCR016743 | HPR125 | 2017-12-01 | Equipment | 20880221 | 15550231 | 16632267
MCR016744 | HPR125 | 2017-12-01 | Subcontract | 98113768 | 73068756 | 69024016
MCR016745 | HPR125 | 2017-12-01 | Overhead | 24237316 | 18050377 | 22742644
MCR016746 | HPR125 | 2018-01-01 | Labor | 51357262 | 48569771 | 54443161
MCR016747 | HPR125 | 2018-01-01 | Material | 96317090 | 91089339 | 90018509
MCR016748 | HPR125 | 2018-01-01 | Equipment | 24758567 | 23414759 | 22562360
MCR016749 | HPR125 | 2018-01-01 | Subcontract | 116337668 | 110023271 | 112394880
MCR016750 | HPR125 | 2018-01-01 | Overhead | 28739217 | 27179354 | 24278574
MCR016751 | HPR125 | 2018-02-01 | Labor | 57568926 | 62419451 | 61432291
MCR016752 | HPR125 | 2018-02-01 | Material | 107966649 | 117063482 | 132244462
MCR016753 | HPR125 | 2018-02-01 | Equipment | 27753117 | 30091482 | 33893657
MCR016754 | HPR125 | 2018-02-01 | Subcontract | 130408717 | 141396429 | 138552625
MCR016755 | HPR125 | 2018-02-01 | Overhead | 32215227 | 34929552 | 25360677
MCR016756 | HPR125 | 2018-03-01 | Labor | 62008797 | 43401947 | 46936207
MCR016757 | HPR125 | 2018-03-01 | Material | 116293328 | 81397433 | 74327744
MCR016758 | HPR125 | 2018-03-01 | Equipment | 29893512 | 20923429 | 22416798
MCR016759 | HPR125 | 2018-03-01 | Subcontract | 140466189 | 98316794 | 99723937
MCR016760 | HPR125 | 2018-03-01 | Overhead | 34699752 | 24287470 | 22415413
MCR016761 | HPR125 | 2018-04-01 | Labor | 64742749 | 48080856 | 47949016
MCR016762 | HPR125 | 2018-04-01 | Material | 121420671 | 90172412 | 91834249
MCR016763 | HPR125 | 2018-04-01 | Equipment | 31211510 | 23179060 | 23769001
MCR016764 | HPR125 | 2018-04-01 | Subcontract | 146659308 | 108915750 | 106486110
MCR016765 | HPR125 | 2018-04-01 | Overhead | 36229655 | 26905760 | 24339082
MCR016766 | HPR125 | 2018-05-01 | Labor | 65841806 | 44441943 | 48257754
MCR016767 | HPR125 | 2018-05-01 | Material | 123481880 | 83347876 | 87106974
MCR016768 | HPR125 | 2018-05-01 | Equipment | 31741349 | 21424795 | 21987481
MCR016769 | HPR125 | 2018-05-01 | Subcontract | 149148962 | 100672659 | 115884566
MCR016770 | HPR125 | 2018-05-01 | Overhead | 36844682 | 24869446 | 26175711
MCR016771 | HPR125 | 2018-06-01 | Labor | 65383120 | 71425067 | 73415923
MCR016772 | HPR125 | 2018-06-01 | Material | 122621644 | 133952910 | 138735637
MCR016773 | HPR125 | 2018-06-01 | Equipment | 31520223 | 34432955 | 30204166
MCR016774 | HPR125 | 2018-06-01 | Subcontract | 148109916 | 161796512 | 174849191
MCR016775 | HPR125 | 2018-06-01 | Overhead | 36588003 | 39969041 | 22523258
MCR016776 | HPR125 | 2018-07-01 | Labor | 63451243 | 46038729 | 46673539
MCR016777 | HPR125 | 2018-07-01 | Material | 118998540 | 86342540 | 83000393
MCR016778 | HPR125 | 2018-07-01 | Equipment | 30588894 | 22194582 | 22222959
MCR016779 | HPR125 | 2018-07-01 | Subcontract | 143733709 | 104289796 | 94710607
MCR016780 | HPR125 | 2018-07-01 | Overhead | 35506937 | 25762998 | 23627647
MCR016781 | HPR125 | 2018-08-01 | Labor | 60139865 | 41862036 | 42496694
MCR016782 | HPR125 | 2018-08-01 | Material | 112788273 | 78509433 | 83912851
MCR016783 | HPR125 | 2018-08-01 | Equipment | 28992528 | 20181061 | 20355326
MCR016784 | HPR125 | 2018-08-01 | Subcontract | 136232569 | 94828492 | 104242672
MCR016785 | HPR125 | 2018-08-01 | Overhead | 33653909 | 23425745 | 24445149
MCR016786 | HPR125 | 2018-09-01 | Labor | 55554206 | 40916786 | 45832512
MCR016787 | HPR125 | 2018-09-01 | Material | 104188177 | 76736681 | 67392151
MCR016788 | HPR125 | 2018-09-01 | Equipment | 26781850 | 19725370 | 19894666
MCR016789 | HPR125 | 2018-09-01 | Subcontract | 125844847 | 92687253 | 83141291
MCR016790 | HPR125 | 2018-09-01 | Overhead | 31087802 | 22896789 | 21380784
MCR016791 | HPR125 | 2018-10-01 | Labor | 49814495 | 63428465 | 69494087
MCR016792 | HPR125 | 2018-10-01 | Material | 93423735 | 118955820 | 123113842
MCR016793 | HPR125 | 2018-10-01 | Equipment | 24014822 | 30577913 | 31574153
MCR016794 | HPR125 | 2018-10-01 | Subcontract | 112842896 | 143682110 | 151975828
MCR016795 | HPR125 | 2018-10-01 | Overhead | 27875894 | 35494190 | 24968398
MCR016796 | HPR125 | 2018-11-01 | Labor | 43061254 | 47474364 | 47078157
MCR016797 | HPR125 | 2018-11-01 | Material | 80758486 | 89034978 | 95963825
MCR016798 | HPR125 | 2018-11-01 | Equipment | 20759186 | 22886680 | 22008195
MCR016799 | HPR125 | 2018-11-01 | Subcontract | 97545036 | 107541887 | 102145482
MCR016800 | HPR125 | 2018-11-01 | Overhead | 24096821 | 26566371 | 23196791
MCR016801 | HPR125 | 2018-12-01 | Labor | 35463860 | 33647361 | 38612323
MCR016802 | HPR125 | 2018-12-01 | Material | 66510085 | 63103363 | 62132862
MCR016803 | HPR125 | 2018-12-01 | Equipment | 17096596 | 16220889 | 17377630
MCR016804 | HPR125 | 2018-12-01 | Subcontract | 80334946 | 76220098 | 102596882
MCR016805 | HPR125 | 2018-12-01 | Overhead | 19845365 | 18828862 | 24634412
MCR016806 | HPR125 | 2019-01-01 | Labor | 27235701 | 37427413 | 37521347
MCR016807 | HPR125 | 2019-01-01 | Material | 51078726 | 70192597 | 67172794
MCR016808 | HPR125 | 2019-01-01 | Equipment | 13129924 | 18043195 | 18143358
MCR016809 | HPR125 | 2019-01-01 | Subcontract | 61696007 | 84782909 | 131278709
MCR016810 | HPR125 | 2019-01-01 | Overhead | 15240936 | 20944157 | 23166077
MCR016811 | HPR125 | 2019-02-01 | Labor | 18664708 | 47701730 | 53135901
MCR016812 | HPR125 | 2019-02-01 | Material | 35004405 | 89461387 | 98413464
MCR016813 | HPR125 | 2019-02-01 | Equipment | 8997976 | 22996290 | 22124493
MCR016814 | HPR125 | 2019-02-01 | Subcontract | 42280460 | 108056930 | 131101127
MCR016815 | HPR125 | 2019-02-01 | Overhead | 10444659 | 26693603 | 24216876
MCR016816 | HPR125 | 2019-03-01 | Labor | 10189623 | 32457845 | 35877189
MCR016817 | HPR125 | 2019-03-01 | Material | 19109953 | 60872505 | 61962607
MCR016818 | HPR125 | 2019-03-01 | Equipment | 4912265 | 15647441 | 16785499
MCR016819 | HPR125 | 2019-03-01 | Subcontract | 23082169 | 73525532 | 115040171
MCR016820 | HPR125 | 2019-03-01 | Overhead | 5702052 | 18163216 | 24129463
MCR016821 | HPR125 | 2019-04-01 | Labor | 2719577 | 21359174 | 23475154
MCR016822 | HPR125 | 2019-04-01 | Material | 5100384 | 40057695 | 41528812
MCR016823 | HPR125 | 2019-04-01 | Equipment | 1311068 | 10296938 | 10430623
MCR016824 | HPR125 | 2019-04-01 | Subcontract | 6160556 | 48384132 | 82268212
MCR016825 | HPR125 | 2019-04-01 | Overhead | 1521859 | 11952466 | 23649404
MCR016826 | HPR125 | 2019-05-01 | Labor | 0 | 17225673 | 17344971
MCR016827 | HPR125 | 2019-05-01 | Material | 0 | 32305591 | 29949256
MCR016828 | HPR125 | 2019-05-01 | Equipment | 0 | 8304239 | 8771074
MCR016829 | HPR125 | 2019-05-01 | Subcontract | 0 | 39020667 | 62596791
MCR016830 | HPR125 | 2019-05-01 | Overhead | 0 | 9639384 | 21352326
MCR016831 | HPR125 | 2019-06-01 | Labor | 0 | 4385924 | 3856142
MCR016832 | HPR125 | 2019-06-01 | Material | 0 | 8225505 | 7824983
MCR016833 | HPR125 | 2019-06-01 | Equipment | 0 | 2114388 | 2095424
MCR016834 | HPR125 | 2019-06-01 | Subcontract | 0 | 9935268 | 47575696
MCR016835 | HPR125 | 2019-06-01 | Overhead | 0 | 2454337 | 21680046
MCR016836 | HPR125 | 2019-07-01 | Labor | 0 | 1426645 | 1456031
MCR016837 | HPR125 | 2019-07-01 | Material | 0 | 2675576 | 3483529
MCR016838 | HPR125 | 2019-07-01 | Equipment | 0 | 687764 | 667510
MCR016839 | HPR125 | 2019-07-01 | Subcontract | 0 | 3231724 | 27513026
MCR016840 | HPR125 | 2019-07-01 | Overhead | 0 | 798342 | 23213244
MCR016841 | HPR126 | 2018-05-01 | Labor | 4131865 | 3277818 | 3634279
MCR016842 | HPR126 | 2018-05-01 | Material | 15355653 | 12181674 | 13163931
MCR016843 | HPR126 | 2018-05-01 | Equipment | 4690454 | 3720947 | 4075072
MCR016844 | HPR126 | 2018-05-01 | Subcontract | 13529792 | 10733214 | 10297186
MCR016845 | HPR126 | 2018-05-01 | Overhead | 3273347 | 2596753 | 23600569
MCR016846 | HPR126 | 2018-06-01 | Labor | 11785390 | 15023481 | 14477294
MCR016847 | HPR126 | 2018-06-01 | Material | 43799192 | 55833227 | 60537495
MCR016848 | HPR126 | 2018-06-01 | Equipment | 13378661 | 17054511 | 16454079
MCR016849 | HPR126 | 2018-06-01 | Subcontract | 38591256 | 49194386 | 51307925
MCR016850 | HPR126 | 2018-06-01 | Overhead | 9336623 | 11901904 | 21100609
MCR016851 | HPR126 | 2018-07-01 | Labor | 18537314 | 11736081 | 13903235
MCR016852 | HPR126 | 2018-07-01 | Material | 68892025 | 43615942 | 46600295
MCR016853 | HPR126 | 2018-07-01 | Equipment | 21043380 | 13322686 | 12972627
MCR016854 | HPR126 | 2018-07-01 | Subcontract | 60700429 | 38429795 | 38429111
MCR016855 | HPR126 | 2018-07-01 | Overhead | 14685632 | 9297559 | 21506417
MCR016856 | HPR126 | 2018-08-01 | Labor | 24406548 | 20522283 | 19394844
MCR016857 | HPR126 | 2018-08-01 | Material | 90704432 | 76268961 | 74960503
MCR016858 | HPR126 | 2018-08-01 | Equipment | 27706078 | 23296698 | 22239440
MCR016859 | HPR126 | 2018-08-01 | Subcontract | 79919235 | 67200211 | 77639058
MCR016860 | HPR126 | 2018-08-01 | Overhead | 19335358 | 16258165 | 19871896
MCR016861 | HPR126 | 2018-09-01 | Labor | 29412863 | 31340812 | 36087872
MCR016862 | HPR126 | 2018-09-01 | Material | 109309887 | 116474914 | 124140242
MCR016863 | HPR126 | 2018-09-01 | Equipment | 33389199 | 35577789 | 39169014
MCR016864 | HPR126 | 2018-09-01 | Subcontract | 96312411 | 102625482 | 97920398
MCR016865 | HPR126 | 2018-09-01 | Overhead | 23301461 | 24828821 | 20490419
MCR016866 | HPR126 | 2018-10-01 | Labor | 33576981 | 33353654 | 36105061
MCR016867 | HPR126 | 2018-10-01 | Material | 124785404 | 123955435 | 128312677
MCR016868 | HPR126 | 2018-10-01 | Equipment | 38116265 | 37862747 | 31624977
MCR016869 | HPR126 | 2018-10-01 | Subcontract | 109947814 | 109216533 | 92943105
MCR016870 | HPR126 | 2018-10-01 | Overhead | 26600359 | 26423435 | 20674169
MCR016871 | HPR126 | 2018-11-01 | Labor | 36920687 | 32611237 | 33614297
MCR016872 | HPR126 | 2018-11-01 | Material | 137211947 | 121196318 | 121639131
MCR016873 | HPR126 | 2018-11-01 | Equipment | 41912009 | 37019963 | 40392166
MCR016874 | HPR126 | 2018-11-01 | Subcontract | 120896781 | 106785488 | 125589553
MCR016875 | HPR126 | 2018-11-01 | Overhead | 29249310 | 25835277 | 21636537
MCR016876 | HPR126 | 2018-12-01 | Labor | 39466960 | 36714548 | 38444770
MCR016877 | HPR126 | 2018-12-01 | Material | 146674910 | 136445851 | 130010141
MCR016878 | HPR126 | 2018-12-01 | Equipment | 44802514 | 41678001 | 41840334
MCR016879 | HPR126 | 2018-12-01 | Subcontract | 129234552 | 120221777 | 101879485
MCR016880 | HPR126 | 2018-12-01 | Overhead | 31266519 | 29086002 | 23218691
MCR016881 | HPR126 | 2019-01-01 | Labor | 41240126 | 51970760 | 53423782
MCR016882 | HPR126 | 2019-01-01 | Material | 153264697 | 193143999 | 200461386
MCR016883 | HPR126 | 2019-01-01 | Equipment | 46815394 | 58996707 | 64195230
MCR016884 | HPR126 | 2019-01-01 | Subcontract | 135040782 | 170178241 | 212648128
MCR016885 | HPR126 | 2019-01-01 | Overhead | 32671256 | 41172281 | 20265901
MCR016886 | HPR126 | 2019-02-01 | Labor | 42266046 | 63015065 | 73500241
MCR016887 | HPR126 | 2019-02-01 | Material | 157077423 | 234189025 | 252059412
MCR016888 | HPR126 | 2019-02-01 | Equipment | 47980008 | 71534095 | 59179479
MCR016889 | HPR126 | 2019-02-01 | Subcontract | 138400156 | 206342815 | 206815024
MCR016890 | HPR126 | 2019-02-01 | Overhead | 33484011 | 49921801 | 23293396
MCR016891 | HPR126 | 2019-03-01 | Labor | 42572349 | 38798144 | 38589798
MCR016892 | HPR126 | 2019-03-01 | Material | 158215769 | 144189323 | 146565826
MCR016893 | HPR126 | 2019-03-01 | Equipment | 48327721 | 44043280 | 54209338
MCR016894 | HPR126 | 2019-03-01 | Subcontract | 139403147 | 127044513 | 111420683
MCR016895 | HPR126 | 2019-03-01 | Overhead | 33726670 | 30736669 | 20973219
MCR016896 | HPR126 | 2019-04-01 | Labor | 42188720 | 44296200 | 42639610
MCR016897 | HPR126 | 2019-04-01 | Material | 156790049 | 164622285 | 175836698
MCR016898 | HPR126 | 2019-04-01 | Equipment | 47892229 | 50284620 | 41535765
MCR016899 | HPR126 | 2019-04-01 | Subcontract | 138146952 | 145047897 | 140700203
MCR016900 | HPR126 | 2019-04-01 | Overhead | 33422751 | 35092340 | 21622034
MCR016901 | HPR126 | 2019-05-01 | Labor | 41147258 | 41988402 | 40939815
MCR016902 | HPR126 | 2019-05-01 | Material | 152919563 | 156045590 | 159839144
MCR016903 | HPR126 | 2019-05-01 | Equipment | 46709971 | 47664830 | 47918506
MCR016904 | HPR126 | 2019-05-01 | Subcontract | 134736686 | 137491013 | 158306075
MCR016905 | HPR126 | 2019-05-01 | Overhead | 32597685 | 33264056 | 23092637
MCR016906 | HPR126 | 2019-06-01 | Labor | 39482950 | 34105277 | 75140451
MCR016907 | HPR126 | 2019-06-01 | Material | 146734333 | 126748764 | 218149679
MCR016908 | HPR126 | 2019-06-01 | Equipment | 44820665 | 38715982 | 38132648
MCR016909 | HPR126 | 2019-06-01 | Subcontract | 129286909 | 111677722 | 100432690
MCR016910 | HPR126 | 2019-06-01 | Overhead | 31279186 | 27018886 | 21321639
MCR016911 | HPR126 | 2019-07-01 | Labor | 37234282 | 15376621 | 34549732
MCR016912 | HPR126 | 2019-07-01 | Material | 138377389 | 57145634 | 116550886
MCR016913 | HPR126 | 2019-07-01 | Equipment | 42267998 | 17455392 | 19074245
MCR016914 | HPR126 | 2019-07-01 | Subcontract | 121923646 | 50350741 | 58071972
MCR016915 | HPR126 | 2019-07-01 | Overhead | 29497746 | 12181668 | 20657593
MCR016916 | HPR126 | 2019-08-01 | Labor | 34444076 | 29264216 | 30261646
MCR016917 | HPR126 | 2019-08-01 | Material | 128007875 | 108757455 | 120262277
MCR016918 | HPR126 | 2019-08-01 | Equipment | 39100583 | 33220456 | 31870422
MCR016919 | HPR126 | 2019-08-01 | Subcontract | 112787118 | 95825666 | 86683284
MCR016920 | HPR126 | 2019-08-01 | Overhead | 27287289 | 23183700 | 21769834
MCR016921 | HPR126 | 2019-09-01 | Labor | 31160653 | 27639646 | 28417568
MCR016922 | HPR126 | 2019-09-01 | Material | 115805369 | 102719909 | 91809292
MCR016923 | HPR126 | 2019-09-01 | Equipment | 35373273 | 31376260 | 33520759
MCR016924 | HPR126 | 2019-09-01 | Subcontract | 102035549 | 90506014 | 94308665
MCR016925 | HPR126 | 2019-09-01 | Overhead | 24686095 | 21896683 | 20337252
MCR016926 | HPR126 | 2019-10-01 | Labor | 27439524 | 19188742 | 15326711
MCR016927 | HPR126 | 2019-10-01 | Material | 101976175 | 71312991 | 78514512
MCR016928 | HPR126 | 2019-10-01 | Equipment | 31149083 | 21782875 | 20719254
MCR016929 | HPR126 | 2019-10-01 | Subcontract | 89850713 | 62833530 | 65362124
MCR016930 | HPR126 | 2019-10-01 | Overhead | 21738142 | 15201707 | 20865224
MCR016931 | HPR126 | 2019-11-01 | Labor | 23345972 | 31589244 | 32250459
MCR016932 | HPR126 | 2019-11-01 | Material | 86762910 | 117398185 | 109311917
MCR016933 | HPR126 | 2019-11-01 | Equipment | 26502123 | 35859806 | 35651361
MCR016934 | HPR126 | 2019-11-01 | Subcontract | 76446379 | 103438972 | 101084922
MCR016935 | HPR126 | 2019-11-01 | Overhead | 18495148 | 25025634 | 21180778
MCR016936 | HPR126 | 2019-12-01 | Labor | 18959255 | 30615164 | 35919900
MCR016937 | HPR126 | 2019-12-01 | Material | 70460127 | 113778115 | 116843255
MCR016938 | HPR126 | 2019-12-01 | Equipment | 21522364 | 34754039 | 33277309
MCR016939 | HPR126 | 2019-12-01 | Subcontract | 62082076 | 100249345 | 104360596
MCR016940 | HPR126 | 2019-12-01 | Overhead | 15019903 | 24253948 | 21148739
MCR016941 | HPR126 | 2020-01-01 | Labor | 14380082 | 14902585 | 11069856
MCR016942 | HPR126 | 2020-01-01 | Material | 53442100 | 55383928 | 65093266
MCR016943 | HPR126 | 2020-01-01 | Equipment | 16324131 | 16917271 | 18544029
MCR016944 | HPR126 | 2020-01-01 | Subcontract | 47087575 | 48798510 | 48884557
MCR016945 | HPR126 | 2020-01-01 | Overhead | 11392190 | 11806127 | 20286017
MCR016946 | HPR126 | 2020-02-01 | Labor | 9745753 | 11026391 | 12480076
MCR016947 | HPR126 | 2020-02-01 | Material | 36219090 | 40978449 | 41882866
MCR016948 | HPR126 | 2020-02-01 | Equipment | 11063285 | 12517052 | 14187281
MCR016949 | HPR126 | 2020-02-01 | Subcontract | 31912465 | 36105913 | 39028316
MCR016950 | HPR126 | 2020-02-01 | Overhead | 7720781 | 8735328 | 22926951
MCR016951 | HPR126 | 2020-03-01 | Labor | 5268202 | 6564405 | 6866548
MCR016952 | HPR126 | 2020-03-01 | Material | 19578733 | 24395937 | 26726020
MCR016953 | HPR126 | 2020-03-01 | Equipment | 5980412 | 7451849 | 6804552
MCR016954 | HPR126 | 2020-03-01 | Subcontract | 17250726 | 21495142 | 19474966
MCR016955 | HPR126 | 2020-03-01 | Overhead | 4173576 | 5200453 | 20026610
MCR016956 | HPR126 | 2020-04-01 | Labor | 1394705 | 4342121 | 4358806
MCR016957 | HPR126 | 2020-04-01 | Material | 5183277 | 16137047 | 16174355
MCR016958 | HPR126 | 2020-04-01 | Equipment | 1583255 | 4929134 | 5119729
MCR016959 | HPR126 | 2020-04-01 | Subcontract | 4566960 | 14218274 | 16380480
MCR016960 | HPR126 | 2020-04-01 | Overhead | 1104913 | 3439916 | 19287111
MCR016961 | HPR126 | 2020-05-01 | Labor | 0 | 1245660 | 1129597
MCR016962 | HPR126 | 2020-05-01 | Material | 0 | 4629369 | 5019476
MCR016963 | HPR126 | 2020-05-01 | Equipment | 0 | 1414062 | 1291774
MCR016964 | HPR126 | 2020-05-01 | Subcontract | 0 | 4078914 | 3525484
MCR016965 | HPR126 | 2020-05-01 | Overhead | 0 | 986837 | 20273160
MCR016966 | HPR127 | 2018-03-01 | Labor | 17987891 | 20028088 | 21327137
MCR016967 | HPR127 | 2018-03-01 | Material | 41566267 | 46280736 | 46408407
MCR016968 | HPR127 | 2018-03-01 | Equipment | 11361460 | 12650083 | 11905412
MCR016969 | HPR127 | 2018-03-01 | Subcontract | 58340740 | 64957778 | 65393343
MCR016970 | HPR127 | 2018-03-01 | Overhead | 15078612 | 16788837 | 46671315
MCR016971 | HPR127 | 2018-04-01 | Labor | 47384621 | 51595577 | 50530775
MCR016972 | HPR127 | 2018-04-01 | Material | 109495983 | 119226625 | 108390219
MCR016973 | HPR127 | 2018-04-01 | Equipment | 29928939 | 32588651 | 32941115
MCR016974 | HPR127 | 2018-04-01 | Subcontract | 153684156 | 167341693 | 176956328
MCR016975 | HPR127 | 2018-04-01 | Overhead | 39720850 | 43250746 | 39711397
MCR016976 | HPR127 | 2018-05-01 | Labor | 67303580 | 52596979 | 60489460
MCR016977 | HPR127 | 2018-05-01 | Material | 155524545 | 121540656 | 127355090
MCR016978 | HPR127 | 2018-05-01 | Equipment | 42510094 | 33221153 | 38031885
MCR016979 | HPR127 | 2018-05-01 | Subcontract | 218287993 | 170589574 | 175400642
MCR016980 | HPR127 | 2018-05-01 | Overhead | 56418208 | 44090185 | 42351134
MCR016981 | HPR127 | 2018-06-01 | Labor | 78317556 | 62459087 | 69296605
MCR016982 | HPR127 | 2018-06-01 | Material | 180975547 | 144329931 | 153526973
MCR016983 | HPR127 | 2018-06-01 | Equipment | 49466710 | 39450230 | 33540327
MCR016984 | HPR127 | 2018-06-01 | Subcontract | 254009996 | 202575683 | 229294387
MCR016985 | HPR127 | 2018-06-01 | Overhead | 65650834 | 52357241 | 46989107
MCR016986 | HPR127 | 2018-07-01 | Labor | 81081579 | 73872672 | 70146391
MCR016987 | HPR127 | 2018-07-01 | Material | 187362629 | 170704347 | 165683274
MCR016988 | HPR127 | 2018-07-01 | Equipment | 51212515 | 46659246 | 43198587
MCR016989 | HPR127 | 2018-07-01 | Subcontract | 262974647 | 239593752 | 213495831
MCR016990 | HPR127 | 2018-07-01 | Overhead | 67967817 | 61924845 | 43446921
MCR016991 | HPR127 | 2018-08-01 | Labor | 76364777 | 56739935 | 69457583
MCR016992 | HPR127 | 2018-08-01 | Material | 176463083 | 131114163 | 160681109
MCR016993 | HPR127 | 2018-08-01 | Equipment | 48233302 | 35837915 | 42982671
MCR016994 | HPR127 | 2018-08-01 | Subcontract | 247676483 | 184026563 | 202418560
MCR016995 | HPR127 | 2018-08-01 | Overhead | 64013889 | 47563078 | 42289772
MCR016996 | HPR127 | 2018-09-01 | Labor | 65105471 | 124957734 | 128343892
MCR016997 | HPR127 | 2018-09-01 | Material | 150445173 | 288751278 | 270115049
MCR016998 | HPR127 | 2018-09-01 | Equipment | 41121731 | 78925447 | 74480798
MCR016999 | HPR127 | 2018-09-01 | Subcontract | 211158791 | 405279675 | 445440305
MCR017000 | HPR127 | 2018-09-01 | Overhead | 54575611 | 104747645 | 43181186
MCR017001 | HPR127 | 2018-10-01 | Labor | 48519290 | 29649607 | 31750479
MCR017002 | HPR127 | 2018-10-01 | Material | 112117967 | 68514061 | 81598372
MCR017003 | HPR127 | 2018-10-01 | Equipment | 30645615 | 18727200 | 20666544
MCR017004 | HPR127 | 2018-10-01 | Subcontract | 157364267 | 96163579 | 93768319
MCR017005 | HPR127 | 2018-10-01 | Overhead | 40672003 | 24854216 | 45656289
MCR017006 | HPR127 | 2018-11-01 | Labor | 28361057 | 36145281 | 44658461
MCR017007 | HPR127 | 2018-11-01 | Material | 65536492 | 83524211 | 99401296
MCR017008 | HPR127 | 2018-11-01 | Equipment | 17913330 | 22829979 | 22784237
MCR017009 | HPR127 | 2018-11-01 | Subcontract | 91984384 | 117231222 | 110087289
MCR017010 | HPR127 | 2018-11-01 | Overhead | 23774070 | 30299310 | 42898732
MCR017011 | HPR127 | 2018-12-01 | Labor | 7976368 | 10357232 | 9561055
MCR017012 | HPR127 | 2018-12-01 | Material | 18431725 | 23933405 | 20032771
MCR017013 | HPR127 | 2018-12-01 | Equipment | 5038011 | 6541806 | 7633021
MCR017014 | HPR127 | 2018-12-01 | Subcontract | 25870027 | 33591965 | 43372040
MCR017015 | HPR127 | 2018-12-01 | Overhead | 6686307 | 8682101 | 47237705
MCR017016 | HPR128 | 2016-11-01 | Labor | 1686160 | 1334354 | 1420203
MCR017017 | HPR128 | 2016-11-01 | Material | 2939332 | 2326061 | 2410088
MCR017018 | HPR128 | 2016-11-01 | Equipment | 678177 | 536680 | 542047
MCR017019 | HPR128 | 2016-11-01 | Subcontract | 2883783 | 2282103 | 2574217
MCR017020 | HPR128 | 2016-11-01 | Overhead | 792851 | 627428 | 5204628
MCR017021 | HPR128 | 2016-12-01 | Labor | 4809462 | 3059947 | 3165912
MCR017022 | HPR128 | 2016-12-01 | Material | 8383906 | 5334133 | 5060984
MCR017023 | HPR128 | 2016-12-01 | Equipment | 1934375 | 1230717 | 1226898
MCR017024 | HPR128 | 2016-12-01 | Subcontract | 8225464 | 5233327 | 4453009
MCR017025 | HPR128 | 2016-12-01 | Overhead | 2261461 | 1438821 | 4867052
MCR017026 | HPR128 | 2017-01-01 | Labor | 7564833 | 6700355 | 6309489
MCR017027 | HPR128 | 2017-01-01 | Material | 13187098 | 11680130 | 13275074
MCR017028 | HPR128 | 2017-01-01 | Equipment | 3042591 | 2694896 | 2585303
MCR017029 | HPR128 | 2017-01-01 | Subcontract | 12937885 | 11459396 | 9748199
MCR017030 | HPR128 | 2017-01-01 | Overhead | 3557067 | 3150580 | 4883146
MCR017031 | HPR128 | 2017-02-01 | Labor | 9959990 | 8870157 | 9666601
MCR017032 | HPR128 | 2017-02-01 | Material | 17362362 | 15462554 | 17182723
MCR017033 | HPR128 | 2017-02-01 | Equipment | 4005928 | 3567595 | 3665821
MCR017034 | HPR128 | 2017-02-01 | Subcontract | 17034243 | 15170338 | 16511206
MCR017035 | HPR128 | 2017-02-01 | Overhead | 4683295 | 4170844 | 4882708
MCR017036 | HPR128 | 2017-03-01 | Labor | 12003001 | 12396036 | 11917082
MCR017037 | HPR128 | 2017-03-01 | Material | 20923760 | 21608904 | 19544775
MCR017038 | HPR128 | 2017-03-01 | Equipment | 4827632 | 4985711 | 5157375
MCR017039 | HPR128 | 2017-03-01 | Subcontract | 20528337 | 21200533 | 19941967
MCR017040 | HPR128 | 2017-03-01 | Overhead | 5643941 | 5828751 | 5522318
MCR017041 | HPR128 | 2017-04-01 | Labor | 13702322 | 10944065 | 12893953
MCR017042 | HPR128 | 2017-04-01 | Material | 23886036 | 19077813 | 22166083
MCR017043 | HPR128 | 2017-04-01 | Equipment | 5511102 | 4401726 | 4157781
MCR017044 | HPR128 | 2017-04-01 | Subcontract | 23434631 | 18717275 | 18778475
MCR017045 | HPR128 | 2017-04-01 | Overhead | 6442981 | 5146018 | 5236668
MCR017046 | HPR128 | 2017-05-01 | Labor | 15066845 | 19986985 | 16801425
MCR017047 | HPR128 | 2017-05-01 | Material | 26264686 | 34841528 | 32981805
MCR017048 | HPR128 | 2017-05-01 | Equipment | 6059916 | 8038806 | 6790444
MCR017049 | HPR128 | 2017-05-01 | Subcontract | 25768329 | 34183083 | 32388397
MCR017050 | HPR128 | 2017-05-01 | Overhead | 7084594 | 9398098 | 5339885
MCR017051 | HPR128 | 2017-06-01 | Labor | 16105945 | 14851181 | 17223485
MCR017052 | HPR128 | 2017-06-01 | Material | 28076057 | 25888739 | 28002457
MCR017053 | HPR128 | 2017-06-01 | Equipment | 6477844 | 5973175 | 6671707
MCR017054 | HPR128 | 2017-06-01 | Subcontract | 27545468 | 25399486 | 25340341
MCR017055 | HPR128 | 2017-06-01 | Overhead | 7573190 | 6983187 | 5532848
MCR017056 | HPR128 | 2017-07-01 | Labor | 16829551 | 9072417 | 10224399
MCR017057 | HPR128 | 2017-07-01 | Material | 29337454 | 15815135 | 16657263
MCR017058 | HPR128 | 2017-07-01 | Equipment | 6768880 | 3648945 | 3309845
MCR017059 | HPR128 | 2017-07-01 | Subcontract | 28783027 | 15516257 | 15614453
MCR017060 | HPR128 | 2017-07-01 | Overhead | 7913437 | 4265949 | 5207067
MCR017061 | HPR128 | 2017-08-01 | Labor | 17248215 | 11699341 | 11182710
MCR017062 | HPR128 | 2017-08-01 | Material | 30067274 | 20394417 | 20479212
MCR017063 | HPR128 | 2017-08-01 | Equipment | 6937267 | 4705499 | 5333623
MCR017064 | HPR128 | 2017-08-01 | Subcontract | 29499054 | 20008998 | 18659338
MCR017065 | HPR128 | 2017-08-01 | Overhead | 8110298 | 5501157 | 5093219
MCR017066 | HPR128 | 2017-09-01 | Labor | 17373213 | 14747232 | 17367182
MCR017067 | HPR128 | 2017-09-01 | Material | 30285173 | 25707533 | 25791444
MCR017068 | HPR128 | 2017-09-01 | Equipment | 6987542 | 5931367 | 6584199
MCR017069 | HPR128 | 2017-09-01 | Subcontract | 29712835 | 25221705 | 24840371
MCR017070 | HPR128 | 2017-09-01 | Overhead | 8169074 | 6934308 | 5071723
MCR017071 | HPR128 | 2017-10-01 | Labor | 17216659 | 15484698 | 14539405
MCR017072 | HPR128 | 2017-10-01 | Material | 30012266 | 26993093 | 28966359
MCR017073 | HPR128 | 2017-10-01 | Equipment | 6924576 | 6227977 | 4640665
MCR017074 | HPR128 | 2017-10-01 | Subcontract | 29445086 | 26482970 | 27840988
MCR017075 | HPR128 | 2017-10-01 | Overhead | 8095460 | 7281073 | 4643026
MCR017076 | HPR128 | 2017-11-01 | Labor | 16791652 | 16246002 | 18518918
MCR017077 | HPR128 | 2017-11-01 | Material | 29271389 | 28320206 | 28220014
MCR017078 | HPR128 | 2017-11-01 | Equipment | 6753637 | 6534175 | 7329743
MCR017079 | HPR128 | 2017-11-01 | Subcontract | 28718211 | 27785003 | 28511111
MCR017080 | HPR128 | 2017-11-01 | Overhead | 7895617 | 7639047 | 4970483
MCR017081 | HPR128 | 2017-12-01 | Labor | 16112470 | 29345276 | 31674834
MCR017082 | HPR128 | 2017-12-01 | Material | 28087432 | 51155001 | 58563297
MCR017083 | HPR128 | 2017-12-01 | Equipment | 6480469 | 11802730 | 11865818
MCR017084 | HPR128 | 2017-12-01 | Subcontract | 27556628 | 50188260 | 45742277
MCR017085 | HPR128 | 2017-12-01 | Overhead | 7576258 | 13798468 | 5361748
MCR017086 | HPR128 | 2018-01-01 | Labor | 15194819 | 14731211 | 16573349
MCR017087 | HPR128 | 2018-01-01 | Material | 26487771 | 25679606 | 21784974
MCR017088 | HPR128 | 2018-01-01 | Equipment | 6111387 | 5924923 | 5692546
MCR017089 | HPR128 | 2018-01-01 | Subcontract | 25987198 | 25194305 | 26179242
MCR017090 | HPR128 | 2018-01-01 | Overhead | 7144769 | 6926775 | 4667935
MCR017091 | HPR128 | 2018-02-01 | Labor | 14056172 | 12050765 | 12891060
MCR017092 | HPR128 | 2018-02-01 | Material | 24502871 | 21007023 | 21253483
MCR017093 | HPR128 | 2018-02-01 | Equipment | 5653421 | 4846842 | 4971426
MCR017094 | HPR128 | 2018-02-01 | Subcontract | 24039809 | 20610026 | 19133545
MCR017095 | HPR128 | 2018-02-01 | Overhead | 6609365 | 5666400 | 5642976
MCR017096 | HPR128 | 2018-03-01 | Labor | 12716251 | 12691649 | 13179444
MCR017097 | HPR128 | 2018-03-01 | Material | 22167105 | 22124219 | 27495138
MCR017098 | HPR128 | 2018-03-01 | Equipment | 5114502 | 5104607 | 5348078
MCR017099 | HPR128 | 2018-03-01 | Subcontract | 21748185 | 21706110 | 19870458
MCR017100 | HPR128 | 2018-03-01 | Overhead | 5979319 | 5967751 | 5533137
MCR017101 | HPR128 | 2018-04-01 | Labor | 11197707 | 16760513 | 17887401
MCR017102 | HPR128 | 2018-04-01 | Material | 19519964 | 29217106 | 30171963
MCR017103 | HPR128 | 2018-04-01 | Equipment | 4503741 | 6741113 | 6780557
MCR017104 | HPR128 | 2018-04-01 | Subcontract | 19151070 | 28664953 | 30569183
MCR017105 | HPR128 | 2018-04-01 | Overhead | 5265284 | 7880975 | 4989877
MCR017106 | HPR128 | 2018-05-01 | Labor | 9527183 | 10466442 | 10830616
MCR017107 | HPR128 | 2018-05-01 | Material | 16607887 | 18245215 | 19067395
MCR017108 | HPR128 | 2018-05-01 | Equipment | 3831852 | 4209625 | 3756158
MCR017109 | HPR128 | 2018-05-01 | Subcontract | 16294027 | 17900412 | 15589485
MCR017110 | HPR128 | 2018-05-01 | Overhead | 4479785 | 4921435 | 5302279
MCR017111 | HPR128 | 2018-06-01 | Labor | 7737022 | 9829458 | 11005273
MCR017112 | HPR128 | 2018-06-01 | Material | 13487259 | 17134817 | 15838772
MCR017113 | HPR128 | 2018-06-01 | Equipment | 3111846 | 3953428 | 4419038
MCR017114 | HPR128 | 2018-06-01 | Subcontract | 13232373 | 16810999 | 17064666
MCR017115 | HPR128 | 2018-06-01 | Overhead | 3638032 | 4621918 | 4888601
MCR017116 | HPR128 | 2018-07-01 | Labor | 5868322 | 3242904 | 2543495
MCR017117 | HPR128 | 2018-07-01 | Material | 10229721 | 5653065 | 7150484
MCR017118 | HPR128 | 2018-07-01 | Equipment | 2360251 | 1304303 | 1141756
MCR017119 | HPR128 | 2018-07-01 | Subcontract | 10036397 | 5546232 | 6043790
MCR017120 | HPR128 | 2018-07-01 | Overhead | 2759349 | 1524849 | 5094550
MCR017121 | HPR128 | 2018-08-01 | Labor | 3977113 | 4405427 | 4545925
MCR017122 | HPR128 | 2018-08-01 | Material | 6932946 | 7679588 | 9295923
MCR017123 | HPR128 | 2018-08-01 | Equipment | 1599603 | 1771872 | 1802581
MCR017124 | HPR128 | 2018-08-01 | Subcontract | 6801925 | 7534457 | 6375943
MCR017125 | HPR128 | 2018-08-01 | Overhead | 1870082 | 2071480 | 5270278
MCR017126 | HPR128 | 2018-09-01 | Labor | 2149884 | 4542529 | 4626919
MCR017127 | HPR128 | 2018-09-01 | Material | 3747700 | 7918586 | 7491796
MCR017128 | HPR128 | 2018-09-01 | Equipment | 864688 | 1827015 | 1816774
MCR017129 | HPR128 | 2018-09-01 | Subcontract | 3676875 | 7768938 | 8377102
MCR017130 | HPR128 | 2018-09-01 | Overhead | 1010899 | 2135947 | 5111432
MCR017131 | HPR128 | 2018-10-01 | Labor | 569161 | 1556800 | 1348034
MCR017132 | HPR128 | 2018-10-01 | Material | 992167 | 2713831 | 2981910
MCR017133 | HPR128 | 2018-10-01 | Equipment | 228918 | 626148 | 600256
MCR017134 | HPR128 | 2018-10-01 | Subcontract | 973417 | 2662544 | 1926624
MCR017135 | HPR128 | 2018-10-01 | Overhead | 267625 | 732024 | 4832939
MCR017136 | HPR128 | 2018-11-01 | Labor | 0 | 448203 | 548983
MCR017137 | HPR128 | 2018-11-01 | Material | 0 | 781313 | 875174
MCR017138 | HPR128 | 2018-11-01 | Equipment | 0 | 180268 | 195754
MCR017139 | HPR128 | 2018-11-01 | Subcontract | 0 | 766548 | 873550
MCR017140 | HPR128 | 2018-11-01 | Overhead | 0 | 210750 | 4990203
MCR017141 | HPR129 | 2017-10-01 | Labor | 2890179 | 1890124 | 2092994
MCR017142 | HPR129 | 2017-10-01 | Material | 5361809 | 3506525 | 3397935
MCR017143 | HPR129 | 2017-10-01 | Equipment | 1369032 | 895322 | 971640
MCR017144 | HPR129 | 2017-10-01 | Subcontract | 9764883 | 6386055 | 6532470
MCR017145 | HPR129 | 2017-10-01 | Overhead | 1810089 | 1183765 | 12949544
MCR017146 | HPR129 | 2017-11-01 | Labor | 8243707 | 7090561 | 7004496
MCR017147 | HPR129 | 2017-11-01 | Material | 15293579 | 13154284 | 12780255
MCR017148 | HPR129 | 2017-11-01 | Equipment | 3904914 | 3358688 | 3076533
MCR017149 | HPR129 | 2017-11-01 | Subcontract | 27852544 | 23956477 | 28163721
MCR017150 | HPR129 | 2017-11-01 | Overhead | 5162949 | 4440746 | 12549993
MCR017151 | HPR129 | 2017-12-01 | Labor | 12966578 | 6511964 | 7235111
MCR017152 | HPR129 | 2017-12-01 | Material | 24055367 | 12080880 | 12637150
MCR017153 | HPR129 | 2017-12-01 | Equipment | 6142065 | 3084615 | 3570396
MCR017154 | HPR129 | 2017-12-01 | Subcontract | 43809441 | 22001603 | 17008955
MCR017155 | HPR129 | 2017-12-01 | Overhead | 8120835 | 4078376 | 12512187
MCR017156 | HPR129 | 2018-01-01 | Labor | 17072021 | 19312498 | 22586680
MCR017157 | HPR129 | 2018-01-01 | Material | 31671712 | 35828204 | 34512384
MCR017158 | HPR129 | 2018-01-01 | Equipment | 8086748 | 9148027 | 9786173
MCR017159 | HPR129 | 2018-01-01 | Subcontract | 57680268 | 65250038 | 68685181
MCR017160 | HPR129 | 2018-01-01 | Overhead | 10692031 | 12095219 | 12091044
MCR017161 | HPR129 | 2018-02-01 | Labor | 20573865 | 16543460 | 16591091
MCR017162 | HPR129 | 2018-02-01 | Material | 38168270 | 30691135 | 29890058
MCR017163 | HPR129 | 2018-02-01 | Equipment | 9745517 | 7836377 | 7946475
MCR017164 | HPR129 | 2018-02-01 | Subcontract | 69511748 | 55894449 | 62009020
MCR017165 | HPR129 | 2018-02-01 | Overhead | 12885200 | 10360999 | 11800980
MCR017166 | HPR129 | 2018-03-01 | Labor | 23486604 | 11590604 | 11290361
MCR017167 | HPR129 | 2018-03-01 | Material | 43571932 | 21502684 | 24959413
MCR017168 | HPR129 | 2018-03-01 | Equipment | 11125236 | 5490287 | 5427214
MCR017169 | HPR129 | 2018-03-01 | Subcontract | 79352854 | 39160516 | 37694361
MCR017170 | HPR129 | 2018-03-01 | Overhead | 14709419 | 7259076 | 10698635
MCR017171 | HPR129 | 2018-04-01 | Labor | 25825477 | 22129930 | 22864138
MCR017172 | HPR129 | 2018-04-01 | Material | 47910969 | 41055055 | 39528018
MCR017173 | HPR129 | 2018-04-01 | Equipment | 12233123 | 10482601 | 10463371
MCR017174 | HPR129 | 2018-04-01 | Subcontract | 87255074 | 74769139 | 77263581
MCR017175 | HPR129 | 2018-04-01 | Overhead | 16174231 | 13859748 | 10861918
MCR017176 | HPR129 | 2018-05-01 | Labor | 27606558 | 15031535 | 13661063
MCR017177 | HPR129 | 2018-05-01 | Material | 51215198 | 27886237 | 30034732
MCR017178 | HPR129 | 2018-05-01 | Equipment | 13076793 | 7120202 | 8251442
MCR017179 | HPR129 | 2018-05-01 | Subcontract | 93272709 | 50786193 | 51972412
MCR017180 | HPR129 | 2018-05-01 | Overhead | 17289703 | 9414096 | 11146830
MCR017181 | HPR129 | 2018-06-01 | Labor | 28846861 | 13652837 | 13769249
MCR017182 | HPR129 | 2018-06-01 | Material | 53516186 | 25328501 | 25220772
MCR017183 | HPR129 | 2018-06-01 | Equipment | 13664305 | 6467134 | 6126575
MCR017184 | HPR129 | 2018-06-01 | Subcontract | 97463251 | 46128064 | 50843066
MCR017185 | HPR129 | 2018-06-01 | Overhead | 18066493 | 8550631 | 11029582
MCR017186 | HPR129 | 2018-07-01 | Labor | 29564477 | 14041629 | 14839934
MCR017187 | HPR129 | 2018-07-01 | Material | 54847495 | 26049782 | 23430440
MCR017188 | HPR129 | 2018-07-01 | Equipment | 14004229 | 6651299 | 7576629
MCR017189 | HPR129 | 2018-07-01 | Subcontract | 99887819 | 47441656 | 47643080
MCR017190 | HPR129 | 2018-07-01 | Overhead | 18515928 | 8794128 | 12170468
MCR017191 | HPR129 | 2018-08-01 | Labor | 29778732 | 13455368 | 36550209
MCR017192 | HPR129 | 2018-08-01 | Material | 55244976 | 24962161 | 37730249
MCR017193 | HPR129 | 2018-08-01 | Equipment | 14105718 | 6373597 | 7171618
MCR017194 | HPR129 | 2018-08-01 | Subcontract | 100611710 | 45460889 | 38968536
MCR017195 | HPR129 | 2018-08-01 | Overhead | 18650114 | 8426959 | 11884433
MCR017196 | HPR129 | 2018-09-01 | Labor | 29510389 | 27963684 | 53166950
MCR017197 | HPR129 | 2018-09-01 | Material | 54747151 | 51877732 | 54147513
MCR017198 | HPR129 | 2018-09-01 | Equipment | 13978608 | 13245958 | 12249711
MCR017199 | HPR129 | 2018-09-01 | Subcontract | 99705074 | 94479312 | 98664763
MCR017200 | HPR129 | 2018-09-01 | Overhead | 18482053 | 17513368 | 12164563
MCR017201 | HPR129 | 2018-10-01 | Labor | 28781902 | 19299711 | 22073768
MCR017202 | HPR129 | 2018-10-01 | Material | 53395674 | 35804482 | 46276854
MCR017203 | HPR129 | 2018-10-01 | Equipment | 13633535 | 9141970 | 9907027
MCR017204 | HPR129 | 2018-10-01 | Subcontract | 97243776 | 65206837 | 67555798
MCR017205 | HPR129 | 2018-10-01 | Overhead | 18025809 | 12087211 | 13251210
MCR017206 | HPR129 | 2018-11-01 | Labor | 27617742 | 17790820 | 17176792
MCR017207 | HPR129 | 2018-11-01 | Material | 51235947 | 33005215 | 35927269
MCR017208 | HPR129 | 2018-11-01 | Equipment | 13082091 | 8427232 | 8716683
MCR017209 | HPR129 | 2018-11-01 | Subcontract | 93310497 | 60108834 | 62658457
MCR017210 | HPR129 | 2018-11-01 | Overhead | 17296708 | 11142208 | 12272050
MCR017211 | HPR129 | 2018-12-01 | Labor | 26044832 | 32496095 | 34045558
MCR017212 | HPR129 | 2018-12-01 | Material | 48317912 | 60286180 | 63052436
MCR017213 | HPR129 | 2018-12-01 | Equipment | 12337028 | 15392890 | 16919825
MCR017214 | HPR129 | 2018-12-01 | Subcontract | 87996195 | 109792710 | 117994245
MCR017215 | HPR129 | 2018-12-01 | Overhead | 16311611 | 20351970 | 11773791
MCR017216 | HPR129 | 2019-01-01 | Labor | 24093124 | 32385881 | 33118736
MCR017217 | HPR129 | 2019-01-01 | Material | 44697138 | 60081713 | 65077627
MCR017218 | HPR129 | 2019-01-01 | Equipment | 11412535 | 15340683 | 15011827
MCR017219 | HPR129 | 2019-01-01 | Subcontract | 81402070 | 109420335 | 114242730
MCR017220 | HPR129 | 2019-01-01 | Overhead | 15089276 | 20282944 | 12060377
MCR017221 | HPR129 | 2019-02-01 | Labor | 21796418 | 21456676 | 25166951
MCR017222 | HPR129 | 2019-02-01 | Material | 40436329 | 39806046 | 40467548
MCR017223 | HPR129 | 2019-02-01 | Equipment | 10324621 | 10163691 | 11293364
MCR017224 | HPR129 | 2019-02-01 | Subcontract | 73642320 | 72494453 | 80934062
MCR017225 | HPR129 | 2019-02-01 | Overhead | 13650873 | 13438096 | 12783484
MCR017226 | HPR129 | 2019-03-01 | Labor | 19193543 | 12689926 | 11106461
MCR017227 | HPR129 | 2019-03-01 | Material | 35607521 | 23542127 | 20106699
MCR017228 | HPR129 | 2019-03-01 | Equipment | 9091680 | 6011019 | 6342669
MCR017229 | HPR129 | 2019-03-01 | Subcontract | 64848134 | 42874733 | 38323803
MCR017230 | HPR129 | 2019-03-01 | Overhead | 12020719 | 7947570 | 12082771
MCR017231 | HPR129 | 2019-04-01 | Labor | 16330164 | 22061464 | 22802815
MCR017232 | HPR129 | 2019-04-01 | Material | 30295431 | 40928038 | 42076486
MCR017233 | HPR129 | 2019-04-01 | Equipment | 7735342 | 10450169 | 9706467
MCR017234 | HPR129 | 2019-04-01 | Subcontract | 55173797 | 74537817 | 75751413
MCR017235 | HPR129 | 2019-04-01 | Overhead | 10227414 | 13816868 | 11107681
MCR017236 | HPR129 | 2019-05-01 | Labor | 13261720 | 29561839 | 33499481
MCR017237 | HPR129 | 2019-05-01 | Material | 24602908 | 54842601 | 53802324
MCR017238 | HPR129 | 2019-05-01 | Equipment | 6281869 | 14002979 | 15479202
MCR017239 | HPR129 | 2019-05-01 | Subcontract | 44806620 | 99878907 | 95501996
MCR017240 | HPR129 | 2019-05-01 | Overhead | 8305679 | 18514276 | 11978358
MCR017241 | HPR129 | 2019-06-01 | Labor | 10058656 | 17459144 | 17674351
MCR017242 | HPR129 | 2019-06-01 | Material | 18660640 | 32389895 | 39646798
MCR017243 | HPR129 | 2019-06-01 | Equipment | 4764627 | 8270123 | 9341795
MCR017244 | HPR129 | 2019-06-01 | Subcontract | 33984609 | 58988219 | 91669025
MCR017245 | HPR129 | 2019-06-01 | Overhead | 6299633 | 10934483 | 11848703
MCR017246 | HPR129 | 2019-07-01 | Labor | 6817011 | 9878720 | 11665043
MCR017247 | HPR129 | 2019-07-01 | Material | 12646797 | 18326827 | 17398759
MCR017248 | HPR129 | 2019-07-01 | Equipment | 3229111 | 4679395 | 4883726
MCR017249 | HPR129 | 2019-07-01 | Subcontract | 23032246 | 33376671 | 67304634
MCR017250 | HPR129 | 2019-07-01 | Overhead | 4269424 | 6186941 | 11768119
MCR017251 | HPR129 | 2019-08-01 | Labor | 3685030 | 9347110 | 11359831
MCR017252 | HPR129 | 2019-08-01 | Material | 6836402 | 17340593 | 17185455
MCR017253 | HPR129 | 2019-08-01 | Equipment | 1745541 | 4427579 | 3882557
MCR017254 | HPR129 | 2019-08-01 | Subcontract | 12450401 | 31580550 | 56342754
MCR017255 | HPR129 | 2019-08-01 | Overhead | 2307896 | 5853999 | 12809958
MCR017256 | HPR129 | 2019-09-01 | Labor | 975575 | 15669050 | 18659881
MCR017257 | HPR129 | 2019-09-01 | Material | 1809870 | 29068944 | 29951238
MCR017258 | HPR129 | 2019-09-01 | Equipment | 462115 | 7422183 | 7005825
MCR017259 | HPR129 | 2019-09-01 | Subcontract | 3296121 | 52940128 | 96143740
MCR017260 | HPR129 | 2019-09-01 | Overhead | 610993 | 9813365 | 12342554
MCR017261 | HPR129 | 2019-10-01 | Labor | 0 | 14341977 | 15589411
MCR017262 | HPR129 | 2019-10-01 | Material | 0 | 26606983 | 27815362
MCR017263 | HPR129 | 2019-10-01 | Equipment | 0 | 6793570 | 7479807
MCR017264 | HPR129 | 2019-10-01 | Subcontract | 0 | 48456424 | 92159845
MCR017265 | HPR129 | 2019-10-01 | Overhead | 0 | 8982233 | 11363167
MCR017266 | HPR129 | 2019-11-01 | Labor | 0 | 9761248 | 8837405
MCR017267 | HPR129 | 2019-11-01 | Material | 0 | 18108895 | 19647289
MCR017268 | HPR129 | 2019-11-01 | Equipment | 0 | 4623750 | 4903282
MCR017269 | HPR129 | 2019-11-01 | Subcontract | 0 | 32979774 | 80486022
MCR017270 | HPR129 | 2019-11-01 | Overhead | 0 | 6113369 | 11462820
MCR017271 | HPR129 | 2019-12-01 | Labor | 0 | 6086547 | 7413615
MCR017272 | HPR129 | 2019-12-01 | Material | 0 | 11291654 | 9400346
MCR017273 | HPR129 | 2019-12-01 | Equipment | 0 | 2883102 | 3382000
MCR017274 | HPR129 | 2019-12-01 | Subcontract | 0 | 20564269 | 38335817
MCR017275 | HPR129 | 2019-12-01 | Overhead | 0 | 3811942 | 12200820
MCR017276 | HPR129 | 2020-01-01 | Labor | 0 | 5616672 | 5456454
MCR017277 | HPR129 | 2020-01-01 | Material | 0 | 10419951 | 10821230
MCR017278 | HPR129 | 2020-01-01 | Equipment | 0 | 2660529 | 2903013
MCR017279 | HPR129 | 2020-01-01 | Subcontract | 0 | 18976731 | 54217831
MCR017280 | HPR129 | 2020-01-01 | Overhead | 0 | 3517664 | 13612886
MCR017281 | HPR129 | 2020-02-01 | Labor | 0 | 6244474 | 7219336
MCR017282 | HPR129 | 2020-02-01 | Material | 0 | 11584637 | 12927540
MCR017283 | HPR129 | 2020-02-01 | Equipment | 0 | 2957909 | 3228603
MCR017284 | HPR129 | 2020-02-01 | Subcontract | 0 | 21097848 | 50722858
MCR017285 | HPR129 | 2020-02-01 | Overhead | 0 | 3910850 | 10879001
MCR017286 | HPR129 | 2020-03-01 | Labor | 0 | 3118251 | 3792169
MCR017287 | HPR129 | 2020-03-01 | Material | 0 | 5784924 | 5017541
MCR017288 | HPR129 | 2020-03-01 | Equipment | 0 | 1477067 | 1824715
MCR017289 | HPR129 | 2020-03-01 | Subcontract | 0 | 10535458 | 30083274
MCR017290 | HPR129 | 2020-03-01 | Overhead | 0 | 1952929 | 10743282
MCR017291 | HPR129 | 2020-04-01 | Labor | 0 | 541362 | 588906
MCR017292 | HPR129 | 2020-04-01 | Material | 0 | 1004326 | 1324313
MCR017293 | HPR129 | 2020-04-01 | Equipment | 0 | 256435 | 280276
MCR017294 | HPR129 | 2020-04-01 | Subcontract | 0 | 1829070 | 28727297
MCR017295 | HPR129 | 2020-04-01 | Overhead | 0 | 339050 | 10419575
MCR017296 | HPR130 | 2019-04-01 | Labor | 13668721 | 8290206 | 8074514
MCR017297 | HPR130 | 2019-04-01 | Material | 49292473 | 29896339 | 30834321
MCR017298 | HPR130 | 2019-04-01 | Equipment | 9091965 | 5514361 | 6253091
MCR017299 | HPR130 | 2019-04-01 | Subcontract | 38355471 | 23262947 | 25737829
MCR017300 | HPR130 | 2019-04-01 | Overhead | 9169857 | 5561603 | 30998622
MCR017301 | HPR130 | 2019-05-01 | Labor | 36877444 | 26999873 | 26524073
MCR017302 | HPR130 | 2019-05-01 | Material | 132988329 | 97367595 | 102343448
MCR017303 | HPR130 | 2019-05-01 | Equipment | 24529612 | 17959391 | 18049890
MCR017304 | HPR130 | 2019-05-01 | Subcontract | 103480910 | 75763696 | 71103523
MCR017305 | HPR130 | 2019-05-01 | Overhead | 24739761 | 18113252 | 31731470
MCR017306 | HPR130 | 2019-06-01 | Labor | 54091652 | 29087793 | 29319063
MCR017307 | HPR130 | 2019-06-01 | Material | 195066619 | 104897101 | 114912501
MCR017308 | HPR130 | 2019-06-01 | Equipment | 35979913 | 19348203 | 20912138
MCR017309 | HPR130 | 2019-06-01 | Subcontract | 151785285 | 81622557 | 104094157
MCR017310 | HPR130 | 2019-06-01 | Overhead | 36288159 | 19513962 | 32304839
MCR017311 | HPR130 | 2019-07-01 | Labor | 65596830 | 30834663 | 31162231
MCR017312 | HPR130 | 2019-07-01 | Material | 236556870 | 111196707 | 110858885
MCR017313 | HPR130 | 2019-07-01 | Equipment | 43632764 | 20510162 | 18044745
MCR017314 | HPR130 | 2019-07-01 | Subcontract | 184069689 | 86524408 | 74285385
MCR017315 | HPR130 | 2019-07-01 | Overhead | 44006572 | 20685875 | 29735289
MCR017316 | HPR130 | 2019-08-01 | Labor | 71709763 | 37686944 | 37417490
MCR017317 | HPR130 | 2019-08-01 | Material | 258601479 | 135907567 | 140748142
MCR017318 | HPR130 | 2019-08-01 | Equipment | 47698878 | 25068064 | 26258942
MCR017319 | HPR130 | 2019-08-01 | Subcontract | 201223045 | 105752429 | 112743270
MCR017320 | HPR130 | 2019-08-01 | Overhead | 48107521 | 25282826 | 30087088
MCR017321 | HPR130 | 2019-09-01 | Labor | 72787389 | 66720838 | 66758170
MCR017322 | HPR130 | 2019-09-01 | Material | 262487638 | 240610295 | 231105591
MCR017323 | HPR130 | 2019-09-01 | Equipment | 48415677 | 44380415 | 43787013
MCR017324 | HPR130 | 2019-09-01 | Subcontract | 204246944 | 187223741 | 188435949
MCR017325 | HPR130 | 2019-09-01 | Overhead | 48830462 | 44760629 | 27081833
MCR017326 | HPR130 | 2019-10-01 | Labor | 69240069 | 91264095 | 93401795
MCR017327 | HPR130 | 2019-10-01 | Material | 249695209 | 329118780 | 327282672
MCR017328 | HPR130 | 2019-10-01 | Equipment | 46056122 | 60705749 | 64003599
MCR017329 | HPR130 | 2019-10-01 | Subcontract | 194292896 | 256093985 | 274999481
MCR017330 | HPR130 | 2019-10-01 | Overhead | 46450692 | 61225825 | 33342361
MCR017331 | HPR130 | 2019-11-01 | Labor | 61552793 | 41357321 | 38547201
MCR017332 | HPR130 | 2019-11-01 | Material | 221973166 | 149143770 | 180387809
MCR017333 | HPR130 | 2019-11-01 | Equipment | 40942809 | 27509473 | 25954318
MCR017334 | HPR130 | 2019-11-01 | Subcontract | 172721813 | 116051786 | 138283391
MCR017335 | HPR130 | 2019-11-01 | Overhead | 41293572 | 27745151 | 32895302
MCR017336 | HPR130 | 2019-12-01 | Labor | 50322086 | 63511752 | 58299902
MCR017337 | HPR130 | 2019-12-01 | Material | 181472722 | 229037614 | 217740632
MCR017338 | HPR130 | 2019-12-01 | Equipment | 33472528 | 42245842 | 43788514
MCR017339 | HPR130 | 2019-12-01 | Subcontract | 141207598 | 178218803 | 194862339
MCR017340 | HPR130 | 2019-12-01 | Overhead | 33759292 | 42607768 | 32340250
MCR017341 | HPR130 | 2020-01-01 | Labor | 36329025 | 48832389 | 52430187
MCR017342 | HPR130 | 2020-01-01 | Material | 131010607 | 176100540 | 198263008
MCR017343 | HPR130 | 2020-01-01 | Equipment | 24164823 | 32481632 | 31798000
MCR017344 | HPR130 | 2020-01-01 | Subcontract | 101942005 | 137027394 | 145824776
MCR017345 | HPR130 | 2020-01-01 | Overhead | 24371847 | 32759907 | 29547857
MCR017346 | HPR130 | 2020-02-01 | Labor | 20717725 | 42984352 | 44834255
MCR017347 | HPR130 | 2020-02-01 | Material | 74712760 | 155011206 | 134778030
MCR017348 | HPR130 | 2020-02-01 | Equipment | 13780721 | 28591718 | 31298664
MCR017349 | HPR130 | 2020-02-01 | Subcontract | 58135511 | 120617357 | 127410691
MCR017350 | HPR130 | 2020-02-01 | Overhead | 13898782 | 28836668 | 31509013
MCR017351 | HPR130 | 2020-03-01 | Labor | 5721678 | 26862379 | 26651513
MCR017352 | HPR130 | 2020-03-01 | Material | 20633655 | 96871760 | 100705710
MCR017353 | HPR130 | 2020-03-01 | Equipment | 3805864 | 17867934 | 18684939
MCR017354 | HPR130 | 2020-03-01 | Subcontract | 16055465 | 75377878 | 77207276
MCR017355 | HPR130 | 2020-03-01 | Overhead | 3838470 | 18021012 | 31477581
MCR017356 | HPR130 | 2020-04-01 | Labor | 0 | 22929829 | 21967123
MCR017357 | HPR130 | 2020-04-01 | Material | 0 | 82690101 | 94930788
MCR017358 | HPR130 | 2020-04-01 | Equipment | 0 | 15252136 | 16386468
MCR017359 | HPR130 | 2020-04-01 | Subcontract | 0 | 64342841 | 73958856
MCR017360 | HPR130 | 2020-04-01 | Overhead | 0 | 15382804 | 28586553
MCR017361 | HPR130 | 2020-05-01 | Labor | 0 | 16912037 | 20074972
MCR017362 | HPR130 | 2020-05-01 | Material | 0 | 60988595 | 55753225
MCR017363 | HPR130 | 2020-05-01 | Equipment | 0 | 11249307 | 12402086
MCR017364 | HPR130 | 2020-05-01 | Subcontract | 0 | 47456460 | 44831512
MCR017365 | HPR130 | 2020-05-01 | Overhead | 0 | 11345682 | 31165838
MCR017366 | HPR130 | 2020-06-01 | Labor | 0 | 4340705 | 3501707
MCR017367 | HPR130 | 2020-06-01 | Material | 0 | 15653556 | 19998366
MCR017368 | HPR130 | 2020-06-01 | Equipment | 0 | 2887288 | 3388648
MCR017369 | HPR130 | 2020-06-01 | Subcontract | 0 | 12180349 | 13377934
MCR017370 | HPR130 | 2020-06-01 | Overhead | 0 | 2912024 | 32224623
MCR017371 | HPR131 | 2023-08-01 | Labor | 7622497 | 3093365 | 2769529
MCR017372 | HPR131 | 2023-08-01 | Material | 12912828 | 5240290 | 5563984
MCR017373 | HPR131 | 2023-08-01 | Equipment | 3346157 | 1357939 | 1416568
MCR017374 | HPR131 | 2023-08-01 | Subcontract | 14916249 | 6053320 | 6083379
MCR017375 | HPR131 | 2023-08-01 | Overhead | 4066044 | 1650084 | 28496874
MCR017376 | HPR131 | 2023-09-01 | Labor | 21787770 | 12344303 | 12893921
MCR017377 | HPR131 | 2023-09-01 | Material | 36909393 | 20911765 | 22161045
MCR017378 | HPR131 | 2023-09-01 | Equipment | 9564489 | 5418955 | 5525529
MCR017379 | HPR131 | 2023-09-01 | Subcontract | 42635873 | 24156218 | 26054681
MCR017380 | HPR131 | 2023-09-01 | Overhead | 11622179 | 6584781 | 29252356
MCR017381 | HPR131 | 2023-10-01 | Labor | 34356686 | 20038353 | 21506135
MCR017382 | HPR131 | 2023-10-01 | Material | 58201662 | 33945808 | 26174487
MCR017383 | HPR131 | 2023-10-01 | Equipment | 15082046 | 8796523 | 8697018
MCR017384 | HPR131 | 2023-10-01 | Subcontract | 67231630 | 39212488 | 39398750
MCR017385 | HPR131 | 2023-10-01 | Overhead | 18326775 | 10688993 | 26922712
MCR017386 | HPR131 | 2023-11-01 | Labor | 45361237 | 23529149 | 22522558
MCR017387 | HPR131 | 2023-11-01 | Material | 76843832 | 39859362 | 43683426
MCR017388 | HPR131 | 2023-11-01 | Equipment | 19912871 | 10328927 | 10346762
MCR017389 | HPR131 | 2023-11-01 | Subcontract | 88766126 | 46043529 | 42865008
MCR017390 | HPR131 | 2023-11-01 | Overhead | 24196897 | 12551077 | 29049255
MCR017391 | HPR131 | 2023-12-01 | Labor | 54834801 | 38869724 | 39566929
MCR017392 | HPR131 | 2023-12-01 | Material | 92892445 | 65846938 | 65291637
MCR017393 | HPR131 | 2023-12-01 | Equipment | 24071617 | 17063199 | 14484075
MCR017394 | HPR131 | 2023-12-01 | Subcontract | 107304677 | 76063069 | 86803773
MCR017395 | HPR131 | 2023-12-01 | Overhead | 29250349 | 20734151 | 27932208
MCR017396 | HPR131 | 2024-01-01 | Labor | 62812285 | 54937103 | 54395835
MCR017397 | HPR131 | 2024-01-01 | Material | 106406638 | 93065749 | 99949560
MCR017398 | HPR131 | 2024-01-01 | Equipment | 27573608 | 24116526 | 27314909
MCR017399 | HPR131 | 2024-01-01 | Subcontract | 122915592 | 107504869 | 102679462
MCR017400 | HPR131 | 2024-01-01 | Overhead | 33505753 | 29304920 | 27151677
MCR017401 | HPR131 | 2024-02-01 | Labor | 69330294 | 56343315 | 55102439
MCR017402 | HPR131 | 2024-02-01 | Material | 117448418 | 95447931 | 90418173
MCR017403 | HPR131 | 2024-02-01 | Equipment | 30434912 | 24733831 | 22872014
MCR017404 | HPR131 | 2024-02-01 | Subcontract | 135670500 | 110256646 | 125772104
MCR017405 | HPR131 | 2024-02-01 | Overhead | 36982633 | 30055031 | 29496291
MCR017406 | HPR131 | 2024-03-01 | Labor | 74427325 | 61049079 | 57515029
MCR017407 | HPR131 | 2024-03-01 | Material | 126083001 | 103419693 | 107160169
MCR017408 | HPR131 | 2024-03-01 | Equipment | 32672428 | 26799588 | 29693140
MCR017409 | HPR131 | 2024-03-01 | Subcontract | 145644736 | 119465223 | 132320374
MCR017410 | HPR131 | 2024-03-01 | Overhead | 39701526 | 32565212 | 28425320
MCR017411 | HPR131 | 2024-04-01 | Labor | 78144000 | 53367777 | 61173995
MCR017412 | HPR131 | 2024-04-01 | Material | 132379204 | 90407246 | 100955209
MCR017413 | HPR131 | 2024-04-01 | Equipment | 34303990 | 23427617 | 21317062
MCR017414 | HPR131 | 2024-04-01 | Subcontract | 152917793 | 104433900 | 92363282
MCR017415 | HPR131 | 2024-04-01 | Overhead | 41684100 | 28467800 | 26849602
MCR017416 | HPR131 | 2024-05-01 | Labor | 80523346 | 110698731 | 123749156
MCR017417 | HPR131 | 2024-05-01 | Material | 136409915 | 187528280 | 208325203
MCR017418 | HPR131 | 2024-05-01 | Equipment | 35348486 | 48595006 | 57285287
MCR017419 | HPR131 | 2024-05-01 | Subcontract | 157573868 | 216623230 | 226975413
MCR017420 | HPR131 | 2024-05-01 | Overhead | 42953307 | 59049664 | 29653142
MCR017421 | HPR131 | 2024-06-01 | Labor | 81611131 | 71808992 | 73148961
MCR017422 | HPR131 | 2024-06-01 | Material | 138252669 | 121647435 | 117971364
MCR017423 | HPR131 | 2024-06-01 | Equipment | 35826006 | 31523021 | 31168253
MCR017424 | HPR131 | 2024-06-01 | Subcontract | 159702524 | 140520994 | 132968918
MCR017425 | HPR131 | 2024-06-01 | Overhead | 43533560 | 38304837 | 27671178
MCR017426 | HPR131 | 2024-07-01 | Labor | 81456280 | 48074769 | 57911553
MCR017427 | HPR131 | 2024-07-01 | Material | 137990344 | 81440670 | 72667739
MCR017428 | HPR131 | 2024-07-01 | Equipment | 35758029 | 21104070 | 20648367
MCR017429 | HPR131 | 2024-07-01 | Subcontract | 159399500 | 94076162 | 84084300
MCR017430 | HPR131 | 2024-07-01 | Overhead | 43450958 | 25644368 | 29057976
MCR017431 | HPR131 | 2024-08-01 | Labor | 80111387 | 39276962 | 33224084
MCR017432 | HPR131 | 2024-08-01 | Material | 135712040 | 66536816 | 65925400
MCR017433 | HPR131 | 2024-08-01 | Equipment | 35167642 | 17241970 | 18120378
MCR017434 | HPR131 | 2024-08-01 | Subcontract | 156767717 | 76859981 | 91477429
MCR017435 | HPR131 | 2024-08-01 | Overhead | 42733557 | 20951382 | 30587930
MCR017436 | HPR131 | 2024-09-01 | Labor | 77633371 | 63238690 | 142467860
MCR017437 | HPR131 | 2024-09-01 | Material | 131514178 | 107128985 | 141691060
MCR017438 | HPR131 | 2024-09-01 | Equipment | 34079832 | 27760793 | 28677051
MCR017439 | HPR131 | 2024-09-01 | Subcontract | 151918558 | 123750011 | 121363258
MCR017440 | HPR131 | 2024-09-01 | Overhead | 41411717 | 33733209 | 24982854
MCR017441 | HPR131 | 2024-10-01 | Labor | 74084314 | 57562560 | 152879294
MCR017442 | HPR131 | 2024-10-01 | Material | 125501926 | 97513384 | 155749941
MCR017443 | HPR131 | 2024-10-01 | Equipment | 32521852 | 25269061 | 24751353
MCR017444 | HPR131 | 2024-10-01 | Subcontract | 144973507 | 112642553 | 101390474
MCR017445 | HPR131 | 2024-10-01 | Overhead | 39518555 | 30705409 | 25433629
MCR017446 | HPR131 | 2024-11-01 | Labor | 69532566 | 61606494 | 62012428
MCR017447 | HPR131 | 2024-11-01 | Material | 117791075 | 104363977 | 98182533
MCR017448 | HPR131 | 2024-11-01 | Equipment | 30523706 | 27044284 | 28101323
MCR017449 | HPR131 | 2024-11-01 | Subcontract | 136066321 | 120556013 | 122174132
MCR017450 | HPR131 | 2024-11-01 | Overhead | 37090531 | 32862552 | 27828022
MCR017451 | HPR131 | 2024-12-01 | Labor | 64054253 | 73506492 | 67634373
MCR017452 | HPR131 | 2024-12-01 | Material | 108510583 | 124523071 | 131020367
MCR017453 | HPR131 | 2024-12-01 | Equipment | 28118812 | 32268197 | 30734764
MCR017454 | HPR131 | 2024-12-01 | Subcontract | 125345964 | 143842783 | 147483134
MCR017455 | HPR131 | 2024-12-01 | Overhead | 34168252 | 39210329 | 27953503
MCR017456 | HPR131 | 2025-01-01 | Labor | 57735366 | 72458525 | 92710800
MCR017457 | HPR131 | 2025-01-01 | Material | 97806124 | 122747771 | 116718094
MCR017458 | HPR131 | 2025-01-01 | Equipment | 25344920 | 31808156 | 35696528
MCR017459 | HPR131 | 2025-01-01 | Subcontract | 112980711 | 141792046 | 149090801
MCR017460 | HPR131 | 2025-01-01 | Overhead | 30797588 | 38651315 | 28971438
MCR017461 | HPR131 | 2025-02-01 | Labor | 50674812 | 77673031 | 76160203
MCR017462 | HPR131 | 2025-02-01 | Material | 85845251 | 131581362 | 134671721
MCR017463 | HPR131 | 2025-02-01 | Equipment | 22245448 | 34097242 | 42605966
MCR017464 | HPR131 | 2025-02-01 | Subcontract | 99164113 | 151996166 | 146743002
MCR017465 | HPR131 | 2025-02-01 | Overhead | 27031300 | 41432872 | 29561672
MCR017466 | HPR131 | 2025-03-01 | Labor | 42989074 | 51461395 | 62409095
MCR017467 | HPR131 | 2025-03-01 | Material | 72825290 | 87177755 | 89989824
MCR017468 | HPR131 | 2025-03-01 | Equipment | 18871529 | 22590745 | 23493279
MCR017469 | HPR131 | 2025-03-01 | Subcontract | 84124109 | 100703355 | 137841875
MCR017470 | HPR131 | 2025-03-01 | Overhead | 22931522 | 27450885 | 27491123
MCR017471 | HPR131 | 2025-04-01 | Labor | 34819795 | 47848065 | 47315324
MCR017472 | HPR131 | 2025-04-01 | Material | 58986189 | 81056624 | 83083893
MCR017473 | HPR131 | 2025-04-01 | Equipment | 15285344 | 21004550 | 19728882
MCR017474 | HPR131 | 2025-04-01 | Subcontract | 68137876 | 93632532 | 132540255
MCR017475 | HPR131 | 2025-04-01 | Overhead | 18573810 | 25523438 | 30384444
MCR017476 | HPR131 | 2025-05-01 | Labor | 26347292 | 53205250 | 58417682
MCR017477 | HPR131 | 2025-05-01 | Material | 44633415 | 90131919 | 84807590
MCR017478 | HPR131 | 2025-05-01 | Equipment | 11566048 | 23356270 | 20756162
MCR017479 | HPR131 | 2025-05-01 | Subcontract | 51558274 | 104115856 | 146435682
MCR017480 | HPR131 | 2025-05-01 | Overhead | 14054350 | 28381104 | 26631328
MCR017481 | HPR131 | 2025-06-01 | Labor | 17817954 | 32520443 | 36710957
MCR017482 | HPR131 | 2025-06-01 | Material | 30184358 | 55090991 | 58077446
MCR017483 | HPR131 | 2025-06-01 | Equipment | 7821802 | 14275964 | 16013794
MCR017484 | HPR131 | 2025-06-01 | Subcontract | 34867452 | 63638340 | 149261476
MCR017485 | HPR131 | 2025-06-01 | Overhead | 9504573 | 17347274 | 28121104
MCR017486 | HPR131 | 2025-07-01 | Labor | 9613161 | 28682836 | 29706060
MCR017487 | HPR131 | 2025-07-01 | Material | 16285098 | 48589924 | 48454478
MCR017488 | HPR131 | 2025-07-01 | Equipment | 4220027 | 12591315 | 13951891
MCR017489 | HPR131 | 2025-07-01 | Subcontract | 18811725 | 56128634 | 90171117
MCR017490 | HPR131 | 2025-07-01 | Overhead | 5127917 | 15300192 | 28580873
MCR017491 | HPR131 | 2025-08-01 | Labor | 2540913 | 23891080 | 22816293
MCR017492 | HPR131 | 2025-08-01 | Material | 4304413 | 40472488 | 42765220
MCR017493 | HPR131 | 2025-08-01 | Equipment | 1115421 | 10487809 | 11691476
MCR017494 | HPR131 | 2025-08-01 | Subcontract | 4972241 | 46751781 | 73365785
MCR017495 | HPR131 | 2025-08-01 | Overhead | 1355391 | 12744141 | 28734285
MCR017496 | HPR131 | 2025-09-01 | Labor | 0 | 29988588 | 37035109
MCR017497 | HPR131 | 2025-09-01 | Material | 0 | 50801922 | 50122700
MCR017498 | HPR131 | 2025-09-01 | Equipment | 0 | 13164520 | 12085949
MCR017499 | HPR131 | 2025-09-01 | Subcontract | 0 | 58683823 | 121273110
MCR017500 | HPR131 | 2025-09-01 | Overhead | 0 | 15996715 | 25328215
MCR017501 | HPR131 | 2025-10-01 | Labor | 0 | 14487053 | 13922997
MCR017502 | HPR131 | 2025-10-01 | Material | 0 | 24541674 | 25736481
MCR017503 | HPR131 | 2025-10-01 | Equipment | 0 | 6359589 | 6928675
MCR017504 | HPR131 | 2025-10-01 | Subcontract | 0 | 28349306 | 64385871
MCR017505 | HPR131 | 2025-10-01 | Overhead | 0 | 7727782 | 28242742
MCR017506 | HPR131 | 2025-11-01 | Labor | 0 | 11493095 | 14094336
MCR017507 | HPR131 | 2025-11-01 | Material | 0 | 19469784 | 17037586
MCR017508 | HPR131 | 2025-11-01 | Equipment | 0 | 5045289 | 5130573
MCR017509 | HPR131 | 2025-11-01 | Subcontract | 0 | 22490515 | 73370921
MCR017510 | HPR131 | 2025-11-01 | Overhead | 0 | 6130724 | 25705784
MCR017511 | HPR131 | 2025-12-01 | Labor | 0 | 5950889 | 6215430
MCR017512 | HPR131 | 2025-12-01 | Material | 0 | 10081055 | 11874432
MCR017513 | HPR131 | 2025-12-01 | Equipment | 0 | 2612347 | 3572273
MCR017514 | HPR131 | 2025-12-01 | Subcontract | 0 | 11645128 | 78267467
MCR017515 | HPR131 | 2025-12-01 | Overhead | 0 | 3174363 | 27873499
MCR017516 | HPR131 | 2026-01-01 | Labor | 0 | 1215801 | 1638414
MCR017517 | HPR131 | 2026-01-01 | Material | 0 | 2059618 | 1656894
MCR017518 | HPR131 | 2026-01-01 | Equipment | 0 | 533718 | 447221
MCR017519 | HPR131 | 2026-01-01 | Subcontract | 0 | 2379167 | 48438105
MCR017520 | HPR131 | 2026-01-01 | Overhead | 0 | 648541 | 28380120
MCR017521 | HPR132 | 2019-10-01 | Labor | 16800774 | 11163140 | 11728227
MCR017522 | HPR132 | 2019-10-01 | Material | 45178341 | 30018386 | 32090400
MCR017523 | HPR132 | 2019-10-01 | Equipment | 14565636 | 9678020 | 10565671
MCR017524 | HPR132 | 2019-10-01 | Subcontract | 36675938 | 24369033 | 24968486
MCR017525 | HPR132 | 2019-10-01 | Overhead | 11310155 | 7514942 | 47450022
MCR017526 | HPR132 | 2019-11-01 | Labor | 46638725 | 30574535 | 31109048
MCR017527 | HPR132 | 2019-11-01 | Material | 125414471 | 82216853 | 88779204
MCR017528 | HPR132 | 2019-11-01 | Equipment | 40434010 | 26506965 | 25183392
MCR017529 | HPR132 | 2019-11-01 | Subcontract | 101811914 | 66743933 | 65586063
MCR017530 | HPR132 | 2019-11-01 | Overhead | 31396839 | 20582547 | 53297126
MCR017531 | HPR132 | 2019-12-01 | Labor | 70962400 | 25776803 | 27499974
MCR017532 | HPR132 | 2019-12-01 | Material | 190822368 | 69315448 | 80258090
MCR017533 | HPR132 | 2019-12-01 | Equipment | 61521716 | 22347513 | 22922500
MCR017534 | HPR132 | 2019-12-01 | Subcontract | 154910277 | 56270527 | 56167910
MCR017535 | HPR132 | 2019-12-01 | Overhead | 47771354 | 17352750 | 47506611
MCR017536 | HPR132 | 2020-01-01 | Labor | 89956266 | 39665458 | 42662109
MCR017537 | HPR132 | 2020-01-01 | Material | 241898072 | 106662917 | 101225550
MCR017538 | HPR132 | 2020-01-01 | Equipment | 77988680 | 34388451 | 37787216
MCR017539 | HPR132 | 2020-01-01 | Subcontract | 196373715 | 86589335 | 85648825
MCR017540 | HPR132 | 2020-01-01 | Overhead | 60557882 | 26702488 | 48785405
MCR017541 | HPR132 | 2020-02-01 | Labor | 103818533 | 134636793 | 120027177
MCR017542 | HPR132 | 2020-02-01 | Material | 279174582 | 362046824 | 377074858
MCR017543 | HPR132 | 2020-02-01 | Equipment | 90006741 | 116725006 | 143128591
MCR017544 | HPR132 | 2020-02-01 | Subcontract | 226634919 | 293910900 | 296732939
MCR017545 | HPR132 | 2020-02-01 | Overhead | 69889856 | 90636476 | 52220633
MCR017546 | HPR132 | 2020-03-01 | Labor | 112763687 | 107267083 | 125445425
MCR017547 | HPR132 | 2020-03-01 | Material | 303228664 | 288447949 | 246385616
MCR017548 | HPR132 | 2020-03-01 | Equipment | 97761850 | 92996503 | 78975559
MCR017549 | HPR132 | 2020-03-01 | Subcontract | 246162108 | 234163072 | 223467947
MCR017550 | HPR132 | 2020-03-01 | Overhead | 75911666 | 72211393 | 45907202
MCR017551 | HPR132 | 2020-04-01 | Labor | 117025798 | 96336511 | 99061264
MCR017552 | HPR132 | 2020-04-01 | Material | 314689749 | 259054953 | 308806817
MCR017553 | HPR132 | 2020-04-01 | Equipment | 101456940 | 83520111 | 100321150
MCR017554 | HPR132 | 2020-04-01 | Subcontract | 255466258 | 210301732 | 209975258
MCR017555 | HPR132 | 2020-04-01 | Overhead | 78780887 | 64853015 | 45666592
MCR017556 | HPR132 | 2020-05-01 | Labor | 116862966 | 56406658 | 61252214
MCR017557 | HPR132 | 2020-05-01 | Material | 314251882 | 151681060 | 149170218
MCR017558 | HPR132 | 2020-05-01 | Equipment | 101315770 | 48902439 | 55450821
MCR017559 | HPR132 | 2020-05-01 | Subcontract | 255110796 | 123135224 | 140635240
MCR017560 | HPR132 | 2020-05-01 | Overhead | 78671269 | 37972538 | 52738877
MCR017561 | HPR132 | 2020-06-01 | Labor | 112563466 | 79089559 | 80543014
MCR017562 | HPR132 | 2020-06-01 | Material | 302690257 | 212676810 | 238318398
MCR017563 | HPR132 | 2020-06-01 | Equipment | 97588266 | 68567655 | 78816733
MCR017564 | HPR132 | 2020-06-01 | Subcontract | 245725027 | 172651791 | 161098808
MCR017565 | HPR132 | 2020-06-01 | Overhead | 75776878 | 53242496 | 50822551
MCR017566 | HPR132 | 2020-07-01 | Labor | 104454608 | 58716831 | 61782020
MCR017567 | HPR132 | 2020-07-01 | Material | 280885027 | 157893259 | 158472023
MCR017568 | HPR132 | 2020-07-01 | Equipment | 90558194 | 50905271 | 51318939
MCR017569 | HPR132 | 2020-07-01 | Subcontract | 228023464 | 128178310 | 137760252
MCR017570 | HPR132 | 2020-07-01 | Overhead | 70318056 | 39527729 | 50653771
MCR017571 | HPR132 | 2020-08-01 | Labor | 92916115 | 50842883 | 57610143
MCR017572 | HPR132 | 2020-08-01 | Material | 249857290 | 136719718 | 138102514
MCR017573 | HPR132 | 2020-08-01 | Equipment | 80554756 | 44078856 | 43457667
MCR017574 | HPR132 | 2020-08-01 | Subcontract | 202835037 | 110989553 | 123010232
MCR017575 | HPR132 | 2020-08-01 | Overhead | 62550429 | 34227046 | 47277033
MCR017576 | HPR132 | 2020-09-01 | Labor | 78401680 | 58404702 | 51352915
MCR017577 | HPR132 | 2020-09-01 | Material | 210827061 | 157053925 | 142629172
MCR017578 | HPR132 | 2020-09-01 | Equipment | 67971291 | 50634667 | 52172456
MCR017579 | HPR132 | 2020-09-01 | Subcontract | 171150158 | 127496935 | 134057711
MCR017580 | HPR132 | 2020-09-01 | Overhead | 52779421 | 39317606 | 55075181
MCR017581 | HPR132 | 2020-10-01 | Labor | 61476882 | 76726881 | 88544662
MCR017582 | HPR132 | 2020-10-01 | Material | 165315211 | 206323420 | 212477981
MCR017583 | HPR132 | 2020-10-01 | Equipment | 53298131 | 66519303 | 74274400
MCR017584 | HPR132 | 2020-10-01 | Subcontract | 134203477 | 167494086 | 181236730
MCR017585 | HPR132 | 2020-10-01 | Overhead | 41385774 | 51651959 | 48950557
MCR017586 | HPR132 | 2020-11-01 | Labor | 42894983 | 39537001 | 37793439
MCR017587 | HPR132 | 2020-11-01 | Material | 115347314 | 106317489 | 113699161
MCR017588 | HPR132 | 2020-11-01 | Equipment | 37188327 | 34277084 | 33482908
MCR017589 | HPR132 | 2020-11-01 | Subcontract | 93639360 | 86308916 | 84140226
MCR017590 | HPR132 | 2020-11-01 | Overhead | 28876580 | 26616012 | 50457292
MCR017591 | HPR132 | 2020-12-01 | Labor | 23784670 | 74337963 | 92625181
MCR017592 | HPR132 | 2020-12-01 | Material | 63958478 | 199899469 | 204074505
MCR017593 | HPR132 | 2020-12-01 | Equipment | 20620409 | 64448202 | 66981478
MCR017594 | HPR132 | 2020-12-01 | Subcontract | 51921720 | 162279101 | 143275466
MCR017595 | HPR132 | 2020-12-01 | Overhead | 16011661 | 50043757 | 50775946
MCR017596 | HPR132 | 2021-01-01 | Labor | 6427785 | 41051228 | 34159039
MCR017597 | HPR132 | 2021-01-01 | Material | 17284720 | 110389341 | 95739674
MCR017598 | HPR132 | 2021-01-01 | Equipment | 5572647 | 35589862 | 39014478
MCR017599 | HPR132 | 2021-01-01 | Subcontract | 14031798 | 89614460 | 128036927
MCR017600 | HPR132 | 2021-01-01 | Overhead | 4327137 | 27635378 | 51537281
MCR017601 | HPR132 | 2021-02-01 | Labor | 0 | 45693679 | 45252161
MCR017602 | HPR132 | 2021-02-01 | Material | 0 | 122873184 | 143516597
MCR017603 | HPR132 | 2021-02-01 | Equipment | 0 | 39614691 | 46466759
MCR017604 | HPR132 | 2021-02-01 | Subcontract | 0 | 99748888 | 148345583
MCR017605 | HPR132 | 2021-02-01 | Overhead | 0 | 30760641 | 49632619
MCR017606 | HPR132 | 2021-03-01 | Labor | 0 | 86233438 | 98874424
MCR017607 | HPR132 | 2021-03-01 | Material | 0 | 231887151 | 238557368
MCR017608 | HPR132 | 2021-03-01 | Equipment | 0 | 74761128 | 78327353
MCR017609 | HPR132 | 2021-03-01 | Subcontract | 0 | 188246815 | 250063485
MCR017610 | HPR132 | 2021-03-01 | Overhead | 0 | 58051702 | 51851756
MCR017611 | HPR132 | 2021-04-01 | Labor | 0 | 39647083 | 35441650
MCR017612 | HPR132 | 2021-04-01 | Material | 0 | 106613506 | 134664373
MCR017613 | HPR132 | 2021-04-01 | Equipment | 0 | 34372521 | 42534958
MCR017614 | HPR132 | 2021-04-01 | Subcontract | 0 | 86549223 | 144976462
MCR017615 | HPR132 | 2021-04-01 | Overhead | 0 | 26690118 | 52381803
MCR017616 | HPR132 | 2021-05-01 | Labor | 0 | 24356545 | 26801757
MCR017617 | HPR132 | 2021-05-01 | Material | 0 | 65496284 | 77906542
MCR017618 | HPR132 | 2021-05-01 | Equipment | 0 | 21116203 | 25233572
MCR017619 | HPR132 | 2021-05-01 | Subcontract | 0 | 53170117 | 86544909
MCR017620 | HPR132 | 2021-05-01 | Overhead | 0 | 16396643 | 52191238
MCR017621 | HPR132 | 2021-06-01 | Labor | 0 | 13495484 | 14122035
MCR017622 | HPR132 | 2021-06-01 | Material | 0 | 36290208 | 36737381
MCR017623 | HPR132 | 2021-06-01 | Equipment | 0 | 11700074 | 12165321
MCR017624 | HPR132 | 2021-06-01 | Subcontract | 0 | 29460520 | 93554104
MCR017625 | HPR132 | 2021-06-01 | Overhead | 0 | 9085059 | 54200862
MCR017626 | HPR132 | 2021-07-01 | Labor | 0 | 6527420 | 6599562
MCR017627 | HPR132 | 2021-07-01 | Material | 0 | 17552645 | 19198089
MCR017628 | HPR132 | 2021-07-01 | Equipment | 0 | 5659026 | 6248908
MCR017629 | HPR132 | 2021-07-01 | Subcontract | 0 | 14249299 | 44957077
MCR017630 | HPR132 | 2021-07-01 | Overhead | 0 | 4394210 | 45664531
MCR017631 | HPR132 | 2021-08-01 | Labor | 0 | 1261662 | 1279382
MCR017632 | HPR132 | 2021-08-01 | Material | 0 | 3392689 | 3961330
MCR017633 | HPR132 | 2021-08-01 | Equipment | 0 | 1093813 | 1826932
MCR017634 | HPR132 | 2021-08-01 | Subcontract | 0 | 2754197 | 28095786
MCR017635 | HPR132 | 2021-08-01 | Overhead | 0 | 849341 | 47636334
MCR017636 | HPR133 | 2022-06-01 | Labor | 6869798 | 4564621 | 4731777
MCR017637 | HPR133 | 2022-06-01 | Material | 12784869 | 8494876 | 8707755
MCR017638 | HPR133 | 2022-06-01 | Equipment | 2748581 | 1826288 | 2073007
MCR017639 | HPR133 | 2022-06-01 | Subcontract | 13144194 | 8733628 | 7931621
MCR017640 | HPR133 | 2022-06-01 | Overhead | 3573907 | 2374674 | 20430841
MCR017641 | HPR133 | 2022-07-01 | Labor | 19446206 | 11286473 | 11026474
MCR017642 | HPR133 | 2022-07-01 | Material | 36189884 | 21004412 | 20192927
MCR017643 | HPR133 | 2022-07-01 | Equipment | 7780356 | 4515676 | 4106435
MCR017644 | HPR133 | 2022-07-01 | Subcontract | 37207016 | 21594750 | 22065916
MCR017645 | HPR133 | 2022-07-01 | Overhead | 10116591 | 5871614 | 19552830
MCR017646 | HPR133 | 2022-08-01 | Labor | 30307977 | 15991069 | 18077590
MCR017647 | HPR133 | 2022-08-01 | Material | 56403916 | 29759786 | 30435123
MCR017648 | HPR133 | 2022-08-01 | Equipment | 12126110 | 6397968 | 6830064
MCR017649 | HPR133 | 2022-08-01 | Subcontract | 57989172 | 30596198 | 30784307
MCR017650 | HPR133 | 2022-08-01 | Overhead | 15767261 | 8319109 | 20859255
MCR017651 | HPR133 | 2022-09-01 | Labor | 39496923 | 28429824 | 31480500
MCR017652 | HPR133 | 2022-09-01 | Material | 73504777 | 52908624 | 50224255
MCR017653 | HPR133 | 2022-09-01 | Equipment | 15802573 | 11374668 | 11284238
MCR017654 | HPR133 | 2022-09-01 | Subcontract | 75570659 | 54395644 | 50498276
MCR017655 | HPR133 | 2022-09-01 | Overhead | 20547669 | 14790180 | 20887811
MCR017656 | HPR133 | 2022-10-01 | Labor | 47057080 | 38649924 | 38883927
MCR017657 | HPR133 | 2022-10-01 | Material | 87574421 | 71928491 | 80841237
MCR017658 | HPR133 | 2022-10-01 | Equipment | 18827364 | 15463693 | 14883143
MCR017659 | HPR133 | 2022-10-01 | Subcontract | 90035737 | 73950072 | 88988179
MCR017660 | HPR133 | 2022-10-01 | Overhead | 24480725 | 20107031 | 20637486
MCR017661 | HPR133 | 2022-11-01 | Labor | 53034998 | 28916646 | 26044817
MCR017662 | HPR133 | 2022-11-01 | Material | 98699478 | 53814612 | 48643171
MCR017663 | HPR133 | 2022-11-01 | Equipment | 21219107 | 11569444 | 13881915
MCR017664 | HPR133 | 2022-11-01 | Subcontract | 101473469 | 55327095 | 42142533
MCR017665 | HPR133 | 2022-11-01 | Overhead | 27590645 | 15043442 | 22494762
MCR017666 | HPR133 | 2022-12-01 | Labor | 57480081 | 42919437 | 45685127
MCR017667 | HPR133 | 2022-12-01 | Material | 106971892 | 79874163 | 84561075
MCR017668 | HPR133 | 2022-12-01 | Equipment | 22997569 | 17171909 | 19032520
MCR017669 | HPR133 | 2022-12-01 | Subcontract | 109978382 | 82119060 | 75656582
MCR017670 | HPR133 | 2022-12-01 | Overhead | 29903131 | 22328179 | 20626283
MCR017671 | HPR133 | 2023-01-01 | Labor | 60445015 | 66274128 | 64753516
MCR017672 | HPR133 | 2023-01-01 | Material | 112489708 | 123337835 | 112563154
MCR017673 | HPR133 | 2023-01-01 | Equipment | 24183828 | 26516035 | 27062571
MCR017674 | HPR133 | 2023-01-01 | Subcontract | 115651279 | 126804297 | 129469962
MCR017675 | HPR133 | 2023-01-01 | Overhead | 31445593 | 34478099 | 20710567
MCR017676 | HPR133 | 2023-02-01 | Labor | 61986285 | 50377346 | 60010900
MCR017677 | HPR133 | 2023-02-01 | Material | 115358051 | 93753521 | 98216385
MCR017678 | HPR133 | 2023-02-01 | Equipment | 24800485 | 20155791 | 18695907
MCR017679 | HPR133 | 2023-02-01 | Subcontract | 118600238 | 96388503 | 108527777
MCR017680 | HPR133 | 2023-02-01 | Overhead | 32247415 | 26208042 | 22159841
MCR017681 | HPR133 | 2023-03-01 | Labor | 62164843 | 51323986 | 52785517
MCR017682 | HPR133 | 2023-03-01 | Material | 115690353 | 95515243 | 98080503
MCR017683 | HPR133 | 2023-03-01 | Equipment | 24871925 | 20534538 | 18621608
MCR017684 | HPR133 | 2023-03-01 | Subcontract | 118941879 | 98199739 | 99881506
MCR017685 | HPR133 | 2023-03-01 | Overhead | 32340307 | 26700517 | 22474181
MCR017686 | HPR133 | 2023-04-01 | Labor | 61046955 | 43739854 | 44889665
MCR017687 | HPR133 | 2023-04-01 | Material | 113609934 | 81400979 | 80244291
MCR017688 | HPR133 | 2023-04-01 | Equipment | 24424662 | 17500155 | 19856615
MCR017689 | HPR133 | 2023-04-01 | Subcontract | 116802989 | 83688788 | 86050924
MCR017690 | HPR133 | 2023-04-01 | Overhead | 31758743 | 22754989 | 21209920
MCR017691 | HPR133 | 2023-05-01 | Labor | 58705317 | 36746667 | 38629854
MCR017692 | HPR133 | 2023-05-01 | Material | 109252087 | 68386481 | 81507423
MCR017693 | HPR133 | 2023-05-01 | Equipment | 23487782 | 14702206 | 15497530
MCR017694 | HPR133 | 2023-05-01 | Subcontract | 112322663 | 70308512 | 68365449
MCR017695 | HPR133 | 2023-05-01 | Overhead | 30540542 | 19116890 | 21151744
MCR017696 | HPR133 | 2023-06-01 | Labor | 55220568 | 49689251 | 55532715
MCR017697 | HPR133 | 2023-06-01 | Material | 102766881 | 92472958 | 80665164
MCR017698 | HPR133 | 2023-06-01 | Equipment | 22093546 | 19880486 | 21158634
MCR017699 | HPR133 | 2023-06-01 | Subcontract | 105655187 | 95071950 | 89029889
MCR017700 | HPR133 | 2023-06-01 | Overhead | 28727654 | 25850071 | 20858775
MCR017701 | HPR133 | 2023-07-01 | Labor | 50683385 | 43144147 | 44360800
MCR017702 | HPR133 | 2023-07-01 | Material | 94323067 | 80292355 | 80779634
MCR017703 | HPR133 | 2023-07-01 | Equipment | 20278236 | 17261815 | 13267590
MCR017704 | HPR133 | 2023-07-01 | Subcontract | 96974057 | 82549005 | 95710701
MCR017705 | HPR133 | 2023-07-01 | Overhead | 26367254 | 22445081 | 21674376
MCR017706 | HPR133 | 2023-08-01 | Labor | 45197528 | 28152651 | 30786826
MCR017707 | HPR133 | 2023-08-01 | Material | 84113747 | 52392800 | 47637111
MCR017708 | HPR133 | 2023-08-01 | Equipment | 18083365 | 11263772 | 13036488
MCR017709 | HPR133 | 2023-08-01 | Subcontract | 86477800 | 53865321 | 52246466
MCR017710 | HPR133 | 2023-08-01 | Overhead | 23513321 | 14645985 | 20827806
MCR017711 | HPR133 | 2023-09-01 | Labor | 38884469 | 79664948 | 82203727
MCR017712 | HPR133 | 2023-09-01 | Material | 72364984 | 148258493 | 156075289
MCR017713 | HPR133 | 2023-09-01 | Equipment | 15557533 | 31873653 | 34026631
MCR017714 | HPR133 | 2023-09-01 | Subcontract | 74398833 | 152425360 | 149911920
MCR017715 | HPR133 | 2023-09-01 | Overhead | 20229049 | 41444468 | 21910452
MCR017716 | HPR133 | 2023-10-01 | Labor | 31890907 | 46191542 | 47711198
MCR017717 | HPR133 | 2023-10-01 | Material | 59349788 | 85963634 | 77137100
MCR017718 | HPR133 | 2023-10-01 | Equipment | 12759435 | 18481066 | 16796166
MCR017719 | HPR133 | 2023-10-01 | Subcontract | 61017839 | 88379678 | 85771707
MCR017720 | HPR133 | 2023-10-01 | Overhead | 16590756 | 24030442 | 20745600
MCR017721 | HPR133 | 2023-11-01 | Labor | 24402085 | 48137750 | 49743810
MCR017722 | HPR133 | 2023-11-01 | Material | 45412900 | 89585576 | 83256478
MCR017723 | HPR133 | 2023-11-01 | Equipment | 9763184 | 19259737 | 19167287
MCR017724 | HPR133 | 2023-11-01 | Subcontract | 46689249 | 92103416 | 91029192
MCR017725 | HPR133 | 2023-11-01 | Overhead | 12694811 | 25042927 | 20111712
MCR017726 | HPR133 | 2023-12-01 | Labor | 16668659 | 25365376 | 28463713
MCR017727 | HPR133 | 2023-12-01 | Material | 31020798 | 47205610 | 44764276
MCR017728 | HPR133 | 2023-12-01 | Equipment | 6669069 | 10148594 | 10248644
MCR017729 | HPR133 | 2023-12-01 | Subcontract | 31892651 | 48532343 | 46386566
MCR017730 | HPR133 | 2023-12-01 | Overhead | 8671615 | 13195948 | 20350098
MCR017731 | HPR133 | 2024-01-01 | Labor | 9073924 | 23018647 | 23664747
MCR017732 | HPR133 | 2024-01-01 | Material | 16886804 | 42838288 | 44523527
MCR017733 | HPR133 | 2024-01-01 | Equipment | 3630444 | 9209676 | 8569245
MCR017734 | HPR133 | 2024-01-01 | Subcontract | 17361415 | 44042276 | 49557207
MCR017735 | HPR133 | 2024-01-01 | Overhead | 4720570 | 11975099 | 20236953
MCR017736 | HPR133 | 2024-02-01 | Labor | 2416153 | 26794192 | 28265281
MCR017737 | HPR133 | 2024-02-01 | Material | 4496523 | 49864673 | 49882247
MCR017738 | HPR133 | 2024-02-01 | Equipment | 966694 | 10720258 | 11393024
MCR017739 | HPR133 | 2024-02-01 | Subcontract | 4622899 | 51266140 | 44046303
MCR017740 | HPR133 | 2024-02-01 | Overhead | 1256967 | 13939268 | 21205859
MCR017741 | HPR133 | 2024-03-01 | Labor | 0 | 18596236 | 19167944
MCR017742 | HPR133 | 2024-03-01 | Material | 0 | 34608067 | 36864873
MCR017743 | HPR133 | 2024-03-01 | Equipment | 0 | 7440285 | 9114839
MCR017744 | HPR133 | 2024-03-01 | Subcontract | 0 | 35580742 | 40031447
MCR017745 | HPR133 | 2024-03-01 | Overhead | 0 | 9674407 | 21897520
MCR017746 | HPR133 | 2024-04-01 | Labor | 0 | 14776280 | 13753934
MCR017747 | HPR133 | 2024-04-01 | Material | 0 | 27499033 | 25872310
MCR017748 | HPR133 | 2024-04-01 | Equipment | 0 | 5911935 | 6801822
MCR017749 | HPR133 | 2024-04-01 | Subcontract | 0 | 28271905 | 29072398
MCR017750 | HPR133 | 2024-04-01 | Overhead | 0 | 7687133 | 22447717
MCR017751 | HPR133 | 2024-05-01 | Labor | 0 | 8377117 | 10364506
MCR017752 | HPR133 | 2024-05-01 | Material | 0 | 15590028 | 14859193
MCR017753 | HPR133 | 2024-05-01 | Equipment | 0 | 3351654 | 3059256
MCR017754 | HPR133 | 2024-05-01 | Subcontract | 0 | 16028192 | 14725668
MCR017755 | HPR133 | 2024-05-01 | Overhead | 0 | 4358067 | 20561007
MCR017756 | HPR133 | 2024-06-01 | Labor | 0 | 1351043 | 192410
MCR017757 | HPR133 | 2024-06-01 | Material | 0 | 2514326 | 2522899
MCR017758 | HPR133 | 2024-06-01 | Equipment | 0 | 540547 | 794139
MCR017759 | HPR133 | 2024-06-01 | Subcontract | 0 | 2584992 | 3908353
MCR017760 | HPR133 | 2024-06-01 | Overhead | 0 | 702860 | 18423278
MCR017761 | HPR134 | 2018-05-01 | Labor | 18328924 | 11255275 | 12005565
MCR017762 | HPR134 | 2018-05-01 | Material | 41644359 | 25572624 | 26926112
MCR017763 | HPR134 | 2018-05-01 | Equipment | 8373541 | 5141955 | 5245136
MCR017764 | HPR134 | 2018-05-01 | Subcontract | 51337917 | 31525165 | 34872188
MCR017765 | HPR134 | 2018-05-01 | Overhead | 13725061 | 8428172 | 39660971
MCR017766 | HPR134 | 2018-06-01 | Labor | 48282988 | 23271320 | 22220275
MCR017767 | HPR134 | 2018-06-01 | Material | 109701696 | 52873764 | 54005200
MCR017768 | HPR134 | 2018-06-01 | Equipment | 22058008 | 10631467 | 10631845
MCR017769 | HPR134 | 2018-06-01 | Subcontract | 135236962 | 65181190 | 72364980
MCR017770 | HPR134 | 2018-06-01 | Overhead | 36155257 | 17426025 | 39993536
MCR017771 | HPR134 | 2018-07-01 | Labor | 68579590 | 35404992 | 35015731
MCR017772 | HPR134 | 2018-07-01 | Material | 155816733 | 80442157 | 84920190
MCR017773 | HPR134 | 2018-07-01 | Equipment | 31330480 | 16174716 | 19151190
MCR017774 | HPR134 | 2018-07-01 | Subcontract | 192086197 | 99166680 | 107548745
MCR017775 | HPR134 | 2018-07-01 | Overhead | 51353755 | 26511959 | 37903328
MCR017776 | HPR134 | 2018-08-01 | Labor | 79802381 | 57390152 | 51078904
MCR017777 | HPR134 | 2018-08-01 | Material | 181315552 | 130393693 | 141696628
MCR017778 | HPR134 | 2018-08-01 | Equipment | 36457594 | 26218603 | 26380755
MCR017779 | HPR134 | 2018-08-01 | Subcontract | 223520376 | 160745436 | 179861594
MCR017780 | HPR134 | 2018-08-01 | Overhead | 59757602 | 42974882 | 41182628
MCR017781 | HPR134 | 2018-09-01 | Labor | 82618807 | 47942992 | 44935595
MCR017782 | HPR134 | 2018-09-01 | Material | 187714633 | 108929207 | 85650912
MCR017783 | HPR134 | 2018-09-01 | Equipment | 37744275 | 21902682 | 22721656
MCR017784 | HPR134 | 2018-09-01 | Subcontract | 231408972 | 134284660 | 142487632
MCR017785 | HPR134 | 2018-09-01 | Overhead | 61866598 | 35900661 | 42192923
MCR017786 | HPR134 | 2018-10-01 | Labor | 77812579 | 59584979 | 57399526
MCR017787 | HPR134 | 2018-10-01 | Material | 176794610 | 135380464 | 149757538
MCR017788 | HPR134 | 2018-10-01 | Equipment | 35548557 | 27221306 | 27566496
MCR017789 | HPR134 | 2018-10-01 | Subcontract | 217947095 | 166892977 | 147909777
MCR017790 | HPR134 | 2018-10-01 | Overhead | 58267600 | 44618412 | 37206596
MCR017791 | HPR134 | 2018-11-01 | Labor | 66339807 | 38900417 | 38229583
MCR017792 | HPR134 | 2018-11-01 | Material | 150727819 | 88383961 | 99720017
MCR017793 | HPR134 | 2018-11-01 | Equipment | 30307239 | 17771595 | 18678571
MCR017794 | HPR134 | 2018-11-01 | Subcontract | 185812736 | 108957097 | 120409320
MCR017795 | HPR134 | 2018-11-01 | Overhead | 49676561 | 29129402 | 41409014
MCR017796 | HPR134 | 2018-12-01 | Labor | 49439169 | 59751768 | 57015496
MCR017797 | HPR134 | 2018-12-01 | Material | 112328607 | 135759418 | 126679751
MCR017798 | HPR134 | 2018-12-01 | Equipment | 22586208 | 27297503 | 29317143
MCR017799 | HPR134 | 2018-12-01 | Subcontract | 138475338 | 167360140 | 174127562
MCR017800 | HPR134 | 2018-12-01 | Overhead | 37021029 | 44743307 | 40753216
MCR017801 | HPR134 | 2019-01-01 | Labor | 28898756 | 64429568 | 62444490
MCR017802 | HPR134 | 2019-01-01 | Material | 65659618 | 146387646 | 140376969
MCR017803 | HPR134 | 2019-01-01 | Equipment | 13202352 | 29434549 | 34001414
MCR017804 | HPR134 | 2019-01-01 | Subcontract | 80943208 | 180462301 | 221573382
MCR017805 | HPR134 | 2019-01-01 | Overhead | 21639960 | 48246136 | 42610940
MCR017806 | HPR134 | 2019-02-01 | Labor | 8127593 | 38996539 | 34286399
MCR017807 | HPR134 | 2019-02-01 | Material | 18466353 | 88602358 | 86340461
MCR017808 | HPR134 | 2019-02-01 | Equipment | 3713078 | 17815509 | 16220597
MCR017809 | HPR134 | 2019-02-01 | Subcontract | 22764766 | 109226330 | 136012468
MCR017810 | HPR134 | 2019-02-01 | Overhead | 6086102 | 29201381 | 37767593
MCR017811 | HPR134 | 2019-03-01 | Labor | 0 | 40352515 | 36598783
MCR017812 | HPR134 | 2019-03-01 | Material | 0 | 91683212 | 95507443
MCR017813 | HPR134 | 2019-03-01 | Equipment | 0 | 18434984 | 20399930
MCR017814 | HPR134 | 2019-03-01 | Subcontract | 0 | 113024315 | 135850648
MCR017815 | HPR134 | 2019-03-01 | Overhead | 0 | 30216762 | 34978142
MCR017816 | HPR134 | 2019-04-01 | Labor | 0 | 34344282 | 35124337
MCR017817 | HPR134 | 2019-04-01 | Material | 0 | 78032163 | 85984143
MCR017818 | HPR134 | 2019-04-01 | Equipment | 0 | 15690132 | 16585138
MCR017819 | HPR134 | 2019-04-01 | Subcontract | 0 | 96195711 | 131223660
MCR017820 | HPR134 | 2019-04-01 | Overhead | 0 | 25717678 | 39440210
MCR017821 | HPR134 | 2019-05-01 | Labor | 0 | 13228018 | 10907443
MCR017822 | HPR134 | 2019-05-01 | Material | 0 | 30054810 | 27289033
MCR017823 | HPR134 | 2019-05-01 | Equipment | 0 | 6043200 | 7091927
MCR017824 | HPR134 | 2019-05-01 | Subcontract | 0 | 37050668 | 75683175
MCR017825 | HPR134 | 2019-05-01 | Overhead | 0 | 9905402 | 39282276
MCR017826 | HPR134 | 2019-06-01 | Labor | 0 | 3377778 | 4243250
MCR017827 | HPR134 | 2019-06-01 | Material | 0 | 7674504 | 8300975
MCR017828 | HPR134 | 2019-06-01 | Equipment | 0 | 1543133 | 2365202
MCR017829 | HPR134 | 2019-06-01 | Subcontract | 0 | 9460898 | 45901140
MCR017830 | HPR134 | 2019-06-01 | Overhead | 0 | 2529347 | 44118730
MCR017831 | HPR135 | 2020-08-01 | Labor | 1617626 | 936771 | 953186
MCR017832 | HPR135 | 2020-08-01 | Material | 3920475 | 2270355 | 2313758
MCR017833 | HPR135 | 2020-08-01 | Equipment | 718444 | 416053 | 437088
MCR017834 | HPR135 | 2020-08-01 | Subcontract | 7447144 | 4312656 | 4421695
MCR017835 | HPR135 | 2020-08-01 | Overhead | 1272715 | 737032 | 6614839
MCR017836 | HPR135 | 2020-09-01 | Labor | 4531971 | 5915873 | 7200266
MCR017837 | HPR135 | 2020-09-01 | Material | 10983675 | 14337696 | 15116569
MCR017838 | HPR135 | 2020-09-01 | Equipment | 2012807 | 2627446 | 2389841
MCR017839 | HPR135 | 2020-09-01 | Subcontract | 20864054 | 27235189 | 26278884
MCR017840 | HPR135 | 2020-09-01 | Overhead | 3565661 | 4654486 | 6365272
MCR017841 | HPR135 | 2020-10-01 | Labor | 6974782 | 6729039 | 7304318
MCR017842 | HPR135 | 2020-10-01 | Material | 16904066 | 16308484 | 17445834
MCR017843 | HPR135 | 2020-10-01 | Equipment | 3097744 | 2988601 | 3435567
MCR017844 | HPR135 | 2020-10-01 | Subcontract | 32110141 | 30978802 | 33309865
MCR017845 | HPR135 | 2020-10-01 | Overhead | 5487614 | 5294268 | 6338372
MCR017846 | HPR135 | 2020-11-01 | Labor | 8959791 | 7892489 | 9189496
MCR017847 | HPR135 | 2020-11-01 | Material | 21714928 | 19128218 | 17023208
MCR017848 | HPR135 | 2020-11-01 | Equipment | 3979356 | 3505330 | 3354272
MCR017849 | HPR135 | 2020-11-01 | Subcontract | 41248620 | 36335031 | 42159306
MCR017850 | HPR135 | 2020-11-01 | Overhead | 7049377 | 6209646 | 6579821
MCR017851 | HPR135 | 2020-12-01 | Labor | 10501610 | 12803416 | 14623716
MCR017852 | HPR135 | 2020-12-01 | Material | 25451678 | 31030331 | 35340341
MCR017853 | HPR135 | 2020-12-01 | Equipment | 4664132 | 5686444 | 5573858
MCR017854 | HPR135 | 2020-12-01 | Subcontract | 48346768 | 58943705 | 60948553
MCR017855 | HPR135 | 2020-12-01 | Overhead | 8262449 | 10073462 | 6267788
MCR017856 | HPR135 | 2021-01-01 | Labor | 11615874 | 15474830 | 19926706
MCR017857 | HPR135 | 2021-01-01 | Material | 28152206 | 37504762 | 36834284
MCR017858 | HPR135 | 2021-01-01 | Equipment | 5159015 | 6872912 | 6781483
MCR017859 | HPR135 | 2021-01-01 | Subcontract | 53476560 | 71242219 | 63808464
MCR017860 | HPR135 | 2021-01-01 | Overhead | 9139129 | 12175275 | 6120177
MCR017861 | HPR135 | 2021-02-01 | Labor | 12319411 | 10226206 | 11113436
MCR017862 | HPR135 | 2021-02-01 | Material | 29857298 | 24784211 | 24784119
MCR017863 | HPR135 | 2021-02-01 | Equipment | 5471481 | 4541815 | 4466518
MCR017864 | HPR135 | 2021-02-01 | Subcontract | 56715468 | 47078880 | 47958222
MCR017865 | HPR135 | 2021-02-01 | Overhead | 9692657 | 8045767 | 6465246
MCR017866 | HPR135 | 2021-03-01 | Labor | 12630468 | 4145386 | 4610592
MCR017867 | HPR135 | 2021-03-01 | Material | 30611173 | 10046749 | 11480873
MCR017868 | HPR135 | 2021-03-01 | Equipment | 5609632 | 1841111 | 2142632
MCR017869 | HPR135 | 2021-03-01 | Subcontract | 58147494 | 19084315 | 21545627
MCR017870 | HPR135 | 2021-03-01 | Overhead | 9937390 | 3261504 | 6004913
MCR017871 | HPR135 | 2021-04-01 | Labor | 12569000 | 12296599 | 15345776
MCR017872 | HPR135 | 2021-04-01 | Material | 30462200 | 29802010 | 29776294
MCR017873 | HPR135 | 2021-04-01 | Equipment | 5582332 | 5461349 | 5322315
MCR017874 | HPR135 | 2021-04-01 | Subcontract | 57864511 | 56610447 | 57531843
MCR017875 | HPR135 | 2021-04-01 | Overhead | 9889028 | 9674709 | 6438710
MCR017876 | HPR135 | 2021-05-01 | Labor | 12157068 | 6780351 | 6765420
MCR017877 | HPR135 | 2021-05-01 | Material | 29463842 | 16432844 | 19777670
MCR017878 | HPR135 | 2021-05-01 | Equipment | 5399378 | 3011391 | 2722354
MCR017879 | HPR135 | 2021-05-01 | Subcontract | 55968080 | 31215031 | 33242555
MCR017880 | HPR135 | 2021-05-01 | Overhead | 9564929 | 5334640 | 6707882
MCR017881 | HPR135 | 2021-06-01 | Labor | 11419382 | 17048779 | 18833150
MCR017882 | HPR135 | 2021-06-01 | Material | 27675989 | 41319381 | 48799498
MCR017883 | HPR135 | 2021-06-01 | Equipment | 5071746 | 7571958 | 7389935
MCR017884 | HPR135 | 2021-06-01 | Subcontract | 52571960 | 78488284 | 89342380
MCR017885 | HPR135 | 2021-06-01 | Overhead | 8984533 | 13413625 | 6535125
MCR017886 | HPR135 | 2021-07-01 | Labor | 10384092 | 13430335 | 17449025
MCR017887 | HPR135 | 2021-07-01 | Material | 25166862 | 32549730 | 39542044
MCR017888 | HPR135 | 2021-07-01 | Equipment | 4611938 | 5964881 | 5576126
MCR017889 | HPR135 | 2021-07-01 | Subcontract | 47805745 | 61829881 | 58592251
MCR017890 | HPR135 | 2021-07-01 | Overhead | 8169988 | 10566709 | 5802447
MCR017891 | HPR135 | 2021-08-01 | Labor | 9083982 | 7403882 | 7516262
MCR017892 | HPR135 | 2021-08-01 | Material | 22015919 | 17944032 | 18875909
MCR017893 | HPR135 | 2021-08-01 | Equipment | 4034514 | 3288323 | 3684029
MCR017894 | HPR135 | 2021-08-01 | Subcontract | 41820367 | 34085610 | 33505642
MCR017895 | HPR135 | 2021-08-01 | Overhead | 7147089 | 5825221 | 6440713
MCR017896 | HPR135 | 2021-09-01 | Labor | 7558405 | 11146860 | 11740331
MCR017897 | HPR135 | 2021-09-01 | Material | 18318532 | 27015504 | 32613886
MCR017898 | HPR135 | 2021-09-01 | Equipment | 3356951 | 4950710 | 4301006
MCR017899 | HPR135 | 2021-09-01 | Subcontract | 34796992 | 51317335 | 44065064
MCR017900 | HPR135 | 2021-09-01 | Overhead | 5946796 | 8770118 | 6374707
MCR017901 | HPR135 | 2021-10-01 | Labor | 5856690 | 4260313 | 6333140
MCR017902 | HPR135 | 2021-10-01 | Material | 14194262 | 10325285 | 10695653
MCR017903 | HPR135 | 2021-10-01 | Equipment | 2601161 | 1892154 | 1817943
MCR017904 | HPR135 | 2021-10-01 | Subcontract | 26962728 | 19613408 | 27166969
MCR017905 | HPR135 | 2021-10-01 | Overhead | 4607922 | 3351926 | 6395537
MCR017906 | HPR135 | 2021-11-01 | Labor | 4044998 | 4513533 | 4952660
MCR017907 | HPR135 | 2021-11-01 | Material | 9803447 | 10938989 | 13111956
MCR017908 | HPR135 | 2021-11-01 | Equipment | 1796525 | 2004618 | 2185455
MCR017909 | HPR135 | 2021-11-01 | Subcontract | 18622150 | 20779170 | 21083830
MCR017910 | HPR135 | 2021-11-01 | Overhead | 3182520 | 3551154 | 5952376
MCR017911 | HPR135 | 2021-12-01 | Labor | 2223351 | 1922571 | 2373777
MCR017912 | HPR135 | 2021-12-01 | Material | 5388508 | 4659538 | 5855906
MCR017913 | HPR135 | 2021-12-01 | Equipment | 987468 | 853881 | 857992
MCR017914 | HPR135 | 2021-12-01 | Subcontract | 10235748 | 8851031 | 8404802
MCR017915 | HPR135 | 2021-12-01 | Overhead | 1749286 | 1512639 | 6376931
MCR017916 | HPR135 | 2022-01-01 | Labor | 596678 | 1443691 | 1637491
MCR017917 | HPR135 | 2022-01-01 | Material | 1446108 | 3498927 | 4488216
MCR017918 | HPR135 | 2022-01-01 | Equipment | 265006 | 641194 | 526297
MCR017919 | HPR135 | 2022-01-01 | Subcontract | 2746956 | 6646391 | 6273100
MCR017920 | HPR135 | 2022-01-01 | Overhead | 469454 | 1135866 | 6231655
MCR017921 | HPR135 | 2022-02-01 | Labor | 0 | 674256 | 944339
MCR017922 | HPR135 | 2022-02-01 | Material | 0 | 1634124 | 1814277
MCR017923 | HPR135 | 2022-02-01 | Equipment | 0 | 299460 | 351517
MCR017924 | HPR135 | 2022-02-01 | Subcontract | 0 | 3104103 | 3159176
MCR017925 | HPR135 | 2022-02-01 | Overhead | 0 | 530490 | 6527256
MCR017926 | HPR136 | 2018-08-01 | Labor | 940711 | 499636 | 535111
MCR017927 | HPR136 | 2018-08-01 | Material | 2461961 | 1307612 | 1335595
MCR017928 | HPR136 | 2018-08-01 | Equipment | 766000 | 406843 | 420396
MCR017929 | HPR136 | 2018-08-01 | Subcontract | 3217723 | 1709017 | 1667127
MCR017930 | HPR136 | 2018-08-01 | Overhead | 713299 | 378852 | 5382699
MCR017931 | HPR136 | 2018-09-01 | Labor | 2711486 | 1827805 | 2058390
MCR017932 | HPR136 | 2018-09-01 | Material | 7096304 | 4783600 | 4503591
MCR017933 | HPR136 | 2018-09-01 | Equipment | 2207903 | 1488342 | 1573487
MCR017934 | HPR136 | 2018-09-01 | Subcontract | 9274698 | 6252049 | 6251712
MCR017935 | HPR136 | 2018-09-01 | Overhead | 2055997 | 1385942 | 5999151
MCR017936 | HPR136 | 2018-10-01 | Labor | 4318252 | 3319586 | 3379579
MCR017937 | HPR136 | 2018-10-01 | Material | 11301416 | 8687780 | 9352645
MCR017938 | HPR136 | 2018-10-01 | Equipment | 3516257 | 2703066 | 2852724
MCR017939 | HPR136 | 2018-10-01 | Subcontract | 14770677 | 11354718 | 12131325
MCR017940 | HPR136 | 2018-10-01 | Overhead | 3274336 | 2517092 | 5942388
MCR017941 | HPR136 | 2018-11-01 | Labor | 5763698 | 1964437 | 2019935
MCR017942 | HPR136 | 2018-11-01 | Material | 15084331 | 5141182 | 5066023
MCR017943 | HPR136 | 2018-11-01 | Equipment | 4693251 | 1599598 | 1642291
MCR017944 | HPR136 | 2018-11-01 | Subcontract | 19714855 | 6719401 | 6230613
MCR017945 | HPR136 | 2018-11-01 | Overhead | 4370352 | 1489544 | 5847085
MCR017946 | HPR136 | 2018-12-01 | Labor | 7050605 | 6838242 | 7117229
MCR017947 | HPR136 | 2018-12-01 | Material | 18452333 | 17896551 | 18317880
MCR017948 | HPR136 | 2018-12-01 | Equipment | 5741152 | 5568229 | 5743440
MCR017949 | HPR136 | 2018-12-01 | Subcontract | 24116752 | 23390358 | 24641080
MCR017950 | HPR136 | 2018-12-01 | Overhead | 5346156 | 5185130 | 5770014
MCR017951 | HPR136 | 2019-01-01 | Labor | 8181860 | 5278092 | 5380026
MCR017952 | HPR136 | 2019-01-01 | Material | 21412972 | 13813438 | 13706220
MCR017953 | HPR136 | 2019-01-01 | Equipment | 6662308 | 4297833 | 5297178
MCR017954 | HPR136 | 2019-01-01 | Subcontract | 27986235 | 18053829 | 17111348
MCR017955 | HPR136 | 2019-01-01 | Overhead | 6203936 | 4002139 | 5819083
MCR017956 | HPR136 | 2019-02-01 | Labor | 9160459 | 6183896 | 6639502
MCR017957 | HPR136 | 2019-02-01 | Material | 23974089 | 16184043 | 17682210
MCR017958 | HPR136 | 2019-02-01 | Equipment | 7459159 | 5035410 | 5406022
MCR017959 | HPR136 | 2019-02-01 | Subcontract | 31333554 | 21152153 | 22151593
MCR017960 | HPR136 | 2019-02-01 | Overhead | 6945963 | 4688969 | 5795673
MCR017961 | HPR136 | 2019-03-01 | Labor | 9989519 | 8827719 | 9688380
MCR017962 | HPR136 | 2019-03-01 | Material | 26143845 | 23103266 | 21008686
MCR017963 | HPR136 | 2019-03-01 | Equipment | 8134245 | 7188217 | 7908090
MCR017964 | HPR136 | 2019-03-01 | Subcontract | 34169372 | 30195409 | 26512502
MCR017965 | HPR136 | 2019-03-01 | Overhead | 7574602 | 6693661 | 5662354
MCR017966 | HPR136 | 2019-04-01 | Labor | 10672291 | 9983314 | 12726036
MCR017967 | HPR136 | 2019-04-01 | Material | 27930747 | 26127604 | 25487428
MCR017968 | HPR136 | 2019-04-01 | Equipment | 8690211 | 8129192 | 6949215
MCR017969 | HPR136 | 2019-04-01 | Subcontract | 36504810 | 34148146 | 36275652
MCR017970 | HPR136 | 2019-04-01 | Overhead | 8092317 | 7569896 | 5720066
MCR017971 | HPR136 | 2019-05-01 | Labor | 11212173 | 9116553 | 8455972
MCR017972 | HPR136 | 2019-05-01 | Material | 29343685 | 23859180 | 24139377
MCR017973 | HPR136 | 2019-05-01 | Equipment | 9129824 | 7423407 | 8543127
MCR017974 | HPR136 | 2019-05-01 | Subcontract | 38351485 | 31183371 | 33681632
MCR017975 | HPR136 | 2019-05-01 | Overhead | 8501685 | 6912671 | 6251308
MCR017976 | HPR136 | 2019-06-01 | Labor | 11612722 | 7060881 | 7317138
MCR017977 | HPR136 | 2019-06-01 | Material | 30391973 | 18479225 | 21569689
MCR017978 | HPR136 | 2019-06-01 | Equipment | 9455983 | 5749519 | 4981936
MCR017979 | HPR136 | 2019-06-01 | Subcontract | 39721572 | 24151899 | 24434202
MCR017980 | HPR136 | 2019-06-01 | Overhead | 8805403 | 5353947 | 5676254
MCR017981 | HPR136 | 2019-07-01 | Labor | 11877677 | 5287050 | 5738041
MCR017982 | HPR136 | 2019-07-01 | Material | 31085395 | 13836884 | 14364184
MCR017983 | HPR136 | 2019-07-01 | Equipment | 9671730 | 4305128 | 4853092
MCR017984 | HPR136 | 2019-07-01 | Subcontract | 40627858 | 18084472 | 19907682
MCR017985 | HPR136 | 2019-07-01 | Overhead | 9006307 | 4008932 | 5910969
MCR017986 | HPR136 | 2019-08-01 | Labor | 12010979 | 7178043 | 18931860
MCR017987 | HPR136 | 2019-08-01 | Material | 31434262 | 18785853 | 32953632
MCR017988 | HPR136 | 2019-08-01 | Equipment | 9780274 | 5844922 | 5258886
MCR017989 | HPR136 | 2019-08-01 | Subcontract | 41083819 | 24552655 | 22642446
MCR017990 | HPR136 | 2019-08-01 | Overhead | 9107383 | 5442786 | 5955366
MCR017991 | HPR136 | 2019-09-01 | Labor | 12016793 | 6287209 | 19412993
MCR017992 | HPR136 | 2019-09-01 | Material | 31449478 | 16454427 | 21381462
MCR017993 | HPR136 | 2019-09-01 | Equipment | 9785008 | 5119535 | 5508866
MCR017994 | HPR136 | 2019-09-01 | Subcontract | 41103705 | 21505537 | 24838848
MCR017995 | HPR136 | 2019-09-01 | Overhead | 9111792 | 4767307 | 5431923
MCR017996 | HPR136 | 2019-10-01 | Labor | 11899541 | 17300987 | 16423969
MCR017997 | HPR136 | 2019-10-01 | Material | 31142616 | 45278888 | 48594433
MCR017998 | HPR136 | 2019-10-01 | Equipment | 9689533 | 14087811 | 14000527
MCR017999 | HPR136 | 2019-10-01 | Subcontract | 40702644 | 59178410 | 58439471
MCR018000 | HPR136 | 2019-10-01 | Overhead | 9022885 | 13118558 | 5523105
MCR018001 | HPR136 | 2019-11-01 | Labor | 11663941 | 14155636 | 14431690
MCR018002 | HPR136 | 2019-11-01 | Material | 30526019 | 37047105 | 36701287
MCR018003 | HPR136 | 2019-11-01 | Equipment | 9497689 | 11526622 | 13638604
MCR018004 | HPR136 | 2019-11-01 | Subcontract | 39896768 | 48419669 | 43164263
MCR018005 | HPR136 | 2019-11-01 | Overhead | 8844240 | 10733581 | 6100193
MCR018006 | HPR136 | 2019-12-01 | Labor | 11315046 | 10435729 | 11763637
MCR018007 | HPR136 | 2019-12-01 | Material | 29612917 | 27311633 | 29422076
MCR018008 | HPR136 | 2019-12-01 | Equipment | 9213592 | 8497584 | 7725457
MCR018009 | HPR136 | 2019-12-01 | Subcontract | 38703366 | 35695643 | 38309722
MCR018010 | HPR136 | 2019-12-01 | Overhead | 8579689 | 7912943 | 6488811
MCR018011 | HPR136 | 2020-01-01 | Labor | 10858307 | 8841570 | 10253659
MCR018012 | HPR136 | 2020-01-01 | Material | 28417574 | 23139517 | 25253053
MCR018013 | HPR136 | 2020-01-01 | Equipment | 8841680 | 7199495 | 7111491
MCR018014 | HPR136 | 2020-01-01 | Subcontract | 37141081 | 30242788 | 35037941
MCR018015 | HPR136 | 2020-01-01 | Overhead | 8233365 | 6704164 | 6322599
MCR018016 | HPR136 | 2020-02-01 | Labor | 10299642 | 6651685 | 7140507
MCR018017 | HPR136 | 2020-02-01 | Material | 26955475 | 17408308 | 14741064
MCR018018 | HPR136 | 2020-02-01 | Equipment | 8386771 | 5416320 | 6701986
MCR018019 | HPR136 | 2020-02-01 | Subcontract | 35230153 | 22752237 | 20403538
MCR018020 | HPR136 | 2020-02-01 | Overhead | 7809754 | 5043673 | 6151562
MCR018021 | HPR136 | 2020-03-01 | Labor | 9645526 | 8902362 | 9267535
MCR018022 | HPR136 | 2020-03-01 | Material | 25243571 | 23298615 | 25006583
MCR018023 | HPR136 | 2020-03-01 | Equipment | 7854138 | 7248996 | 6310127
MCR018024 | HPR136 | 2020-03-01 | Subcontract | 32992735 | 30450726 | 33038899
MCR018025 | HPR136 | 2020-03-01 | Overhead | 7313767 | 6750259 | 5893805
MCR018026 | HPR136 | 2020-04-01 | Labor | 8903118 | 11745259 | 12530380
MCR018027 | HPR136 | 2020-04-01 | Material | 23300596 | 30738841 | 27604018
MCR018028 | HPR136 | 2020-04-01 | Equipment | 7249613 | 9563905 | 9336000
MCR018029 | HPR136 | 2020-04-01 | Subcontract | 30453314 | 40174921 | 39145505
MCR018030 | HPR136 | 2020-04-01 | Overhead | 6750833 | 8905900 | 5794311
MCR018031 | HPR136 | 2020-05-01 | Labor | 8080427 | 11004746 | 14495467
MCR018032 | HPR136 | 2020-05-01 | Material | 21147507 | 28800822 | 32490720
MCR018033 | HPR136 | 2020-05-01 | Equipment | 6579713 | 8960921 | 9860795
MCR018034 | HPR136 | 2020-05-01 | Subcontract | 27639279 | 37641977 | 36879147
MCR018035 | HPR136 | 2020-05-01 | Overhead | 6127023 | 8344402 | 5688577
MCR018036 | HPR136 | 2020-06-01 | Labor | 7186540 | 17031066 | 17506614
MCR018037 | HPR136 | 2020-06-01 | Material | 18808091 | 44572470 | 50602290
MCR018038 | HPR136 | 2020-06-01 | Equipment | 5851841 | 13868020 | 14802155
MCR018039 | HPR136 | 2020-06-01 | Subcontract | 24581719 | 58255138 | 54444627
MCR018040 | HPR136 | 2020-06-01 | Overhead | 5449229 | 12913889 | 5593846
MCR018041 | HPR136 | 2020-07-01 | Labor | 6231970 | 6360775 | 7629481
MCR018042 | HPR136 | 2020-07-01 | Material | 16309859 | 16646960 | 17126245
MCR018043 | HPR136 | 2020-07-01 | Equipment | 5074555 | 5179439 | 4995505
MCR018044 | HPR136 | 2020-07-01 | Subcontract | 21316590 | 21757173 | 26012889
MCR018045 | HPR136 | 2020-07-01 | Overhead | 4725421 | 4823089 | 5518265
MCR018046 | HPR136 | 2020-08-01 | Labor | 5229171 | 3515972 | 3998838
MCR018047 | HPR136 | 2020-08-01 | Material | 13685408 | 9201747 | 8154843
MCR018048 | HPR136 | 2020-08-01 | Equipment | 4257999 | 2862978 | 2692900
MCR018049 | HPR136 | 2020-08-01 | Subcontract | 17886497 | 12026461 | 11481473
MCR018050 | HPR136 | 2020-08-01 | Overhead | 3965045 | 2666003 | 5734513
MCR018051 | HPR136 | 2020-09-01 | Labor | 4193400 | 7342462 | 7990488
MCR018052 | HPR136 | 2020-09-01 | Material | 10974663 | 19216158 | 20723424
MCR018053 | HPR136 | 2020-09-01 | Equipment | 3414593 | 5978804 | 5362136
MCR018054 | HPR136 | 2020-09-01 | Subcontract | 14343618 | 25115053 | 26181540
MCR018055 | HPR136 | 2020-09-01 | Overhead | 3179666 | 5567458 | 5746500
MCR018056 | HPR136 | 2020-10-01 | Labor | 3144236 | 8167850 | 9134636
MCR018057 | HPR136 | 2020-10-01 | Material | 8228865 | 21376305 | 21984290
MCR018058 | HPR136 | 2020-10-01 | Equipment | 2560282 | 6650900 | 7464913
MCR018059 | HPR136 | 2020-10-01 | Subcontract | 10754928 | 27938313 | 28135274
MCR018060 | HPR136 | 2020-10-01 | Overhead | 2384132 | 6193312 | 5864598
MCR018061 | HPR136 | 2020-11-01 | Labor | 2108694 | 5033908 | 5932929
MCR018062 | HPR136 | 2020-11-01 | Material | 5518721 | 13174379 | 11216652
MCR018063 | HPR136 | 2020-11-01 | Equipment | 1717063 | 4099000 | 4649424
MCR018064 | HPR136 | 2020-11-01 | Subcontract | 7212835 | 17218594 | 15721347
MCR018065 | HPR136 | 2020-11-01 | Overhead | 1598928 | 3816985 | 5215037
MCR018066 | HPR136 | 2020-12-01 | Labor | 1129093 | 3539577 | 3645760
MCR018067 | HPR136 | 2020-12-01 | Material | 2954979 | 9263523 | 11667762
MCR018068 | HPR136 | 2020-12-01 | Equipment | 919395 | 2882199 | 3152055
MCR018069 | HPR136 | 2020-12-01 | Subcontract | 3862086 | 12107200 | 14113541
MCR018070 | HPR136 | 2020-12-01 | Overhead | 856140 | 2683901 | 5424400
MCR018071 | HPR136 | 2021-01-01 | Labor | 296548 | 2716482 | 3360907
MCR018072 | HPR136 | 2021-01-01 | Material | 776105 | 7109380 | 6608856
MCR018073 | HPR136 | 2021-01-01 | Equipment | 241473 | 2211971 | 2280277
MCR018074 | HPR136 | 2021-01-01 | Subcontract | 1014351 | 9291788 | 8284978
MCR018075 | HPR136 | 2021-01-01 | Overhead | 224859 | 2059786 | 5427849
MCR018076 | HPR136 | 2021-02-01 | Labor | 0 | 2851140 | 2967736
MCR018077 | HPR136 | 2021-02-01 | Material | 0 | 7461797 | 7668831
MCR018078 | HPR136 | 2021-02-01 | Equipment | 0 | 2321620 | 1935382
MCR018079 | HPR136 | 2021-02-01 | Subcontract | 0 | 9752389 | 10740683
MCR018080 | HPR136 | 2021-02-01 | Overhead | 0 | 2161891 | 5761776
MCR018081 | HPR136 | 2021-03-01 | Labor | 0 | 1531729 | 1897405
MCR018082 | HPR136 | 2021-03-01 | Material | 0 | 4008729 | 4255745
MCR018083 | HPR136 | 2021-03-01 | Equipment | 0 | 1247253 | 1474075
MCR018084 | HPR136 | 2021-03-01 | Subcontract | 0 | 5239312 | 4741482
MCR018085 | HPR136 | 2021-03-01 | Overhead | 0 | 1161441 | 5586374
MCR018086 | HPR136 | 2021-04-01 | Labor | 0 | 1968080 | 2081608
MCR018087 | HPR136 | 2021-04-01 | Material | 0 | 5150716 | 5327212
MCR018088 | HPR136 | 2021-04-01 | Equipment | 0 | 1602564 | 1721339
MCR018089 | HPR136 | 2021-04-01 | Subcontract | 0 | 6731862 | 7852142
MCR018090 | HPR136 | 2021-04-01 | Overhead | 0 | 1492306 | 5996782
MCR018091 | HPR136 | 2021-05-01 | Labor | 0 | 772353 | 864445
MCR018092 | HPR136 | 2021-05-01 | Material | 0 | 2021346 | 2543124
MCR018093 | HPR136 | 2021-05-01 | Equipment | 0 | 628910 | 632922
MCR018094 | HPR136 | 2021-05-01 | Subcontract | 0 | 2641851 | 2191329
MCR018095 | HPR136 | 2021-05-01 | Overhead | 0 | 585641 | 5738614
MCR018096 | HPR136 | 2021-06-01 | Labor | 0 | 182593 | 279544
MCR018097 | HPR136 | 2021-06-01 | Material | 0 | 477870 | 358942
MCR018098 | HPR136 | 2021-06-01 | Equipment | 0 | 148682 | 197313
MCR018099 | HPR136 | 2021-06-01 | Subcontract | 0 | 624564 | 626142
MCR018100 | HPR136 | 2021-06-01 | Overhead | 0 | 138452 | 5460691
MCR018101 | HPR137 | 2021-12-01 | Labor | 9071985 | 6147140 | 6217555
MCR018102 | HPR137 | 2021-12-01 | Material | 18370853 | 12448015 | 13047548
MCR018103 | HPR137 | 2021-12-01 | Equipment | 4061441 | 2752016 | 3001497
MCR018104 | HPR137 | 2021-12-01 | Subcontract | 26272302 | 17802004 | 16126340
MCR018105 | HPR137 | 2021-12-01 | Overhead | 5645471 | 3825348 | 27135103
MCR018106 | HPR137 | 2022-01-01 | Labor | 25416240 | 14175153 | 14132051
MCR018107 | HPR137 | 2022-01-01 | Material | 51468120 | 28704815 | 25762269
MCR018108 | HPR137 | 2022-01-01 | Equipment | 11378609 | 6346081 | 5416767
MCR018109 | HPR137 | 2022-01-01 | Subcontract | 73604966 | 41050983 | 36053357
MCR018110 | HPR137 | 2022-01-01 | Overhead | 15816456 | 8821158 | 27460806
MCR018111 | HPR137 | 2022-02-01 | Labor | 39116034 | 19784656 | 21389212
MCR018112 | HPR137 | 2022-02-01 | Material | 79210329 | 40064110 | 40859841
MCR018113 | HPR137 | 2022-02-01 | Equipment | 17511876 | 8857402 | 9849248
MCR018114 | HPR137 | 2022-02-01 | Subcontract | 113279318 | 57296000 | 57298506
MCR018115 | HPR137 | 2022-02-01 | Overhead | 24341799 | 12311936 | 30952740
MCR018116 | HPR137 | 2022-03-01 | Labor | 50248376 | 49060103 | 51179108
MCR018117 | HPR137 | 2022-03-01 | Material | 101753422 | 99347159 | 101261819
MCR018118 | HPR137 | 2022-03-01 | Equipment | 22495719 | 21963741 | 23174518
MCR018119 | HPR137 | 2022-03-01 | Subcontract | 145518375 | 142077158 | 131312677
MCR018120 | HPR137 | 2022-03-01 | Overhead | 31269424 | 30529966 | 27783067
MCR018121 | HPR137 | 2022-04-01 | Labor | 58895220 | 72054359 | 75772554
MCR018122 | HPR137 | 2022-04-01 | Material | 119263362 | 145910738 | 160893726
MCR018123 | HPR137 | 2022-04-01 | Equipment | 26366829 | 32258050 | 35638218
MCR018124 | HPR137 | 2022-04-01 | Subcontract | 170559478 | 208668102 | 212688513
MCR018125 | HPR137 | 2022-04-01 | Overhead | 36650332 | 44839227 | 27974156
MCR018126 | HPR137 | 2022-05-01 | Labor | 65144246 | 55738069 | 50905646
MCR018127 | HPR137 | 2022-05-01 | Material | 131917696 | 112870102 | 122209231
MCR018128 | HPR137 | 2022-05-01 | Equipment | 29164458 | 24953403 | 23772472
MCR018129 | HPR137 | 2022-05-01 | Subcontract | 188656542 | 161416427 | 142156858
MCR018130 | HPR137 | 2022-05-01 | Overhead | 40539083 | 34685646 | 28292924
MCR018131 | HPR137 | 2022-06-01 | Labor | 69089830 | 49347142 | 57720290
MCR018132 | HPR137 | 2022-06-01 | Material | 139907540 | 99928416 | 84975760
MCR018133 | HPR137 | 2022-06-01 | Equipment | 30930859 | 22092245 | 21873322
MCR018134 | HPR137 | 2022-06-01 | Subcontract | 200082881 | 142908419 | 145859093
MCR018135 | HPR137 | 2022-06-01 | Overhead | 42994409 | 30708589 | 28305470
MCR018136 | HPR137 | 2022-07-01 | Labor | 70834300 | 36846188 | 33545758
MCR018137 | HPR137 | 2022-07-01 | Material | 143440108 | 74613869 | 79042343
MCR018138 | HPR137 | 2022-07-01 | Equipment | 31711841 | 16495687 | 16619496
MCR018139 | HPR137 | 2022-07-01 | Subcontract | 205134834 | 106705885 | 95927065
MCR018140 | HPR137 | 2022-07-01 | Overhead | 44079988 | 22929280 | 31041212
MCR018141 | HPR137 | 2022-08-01 | Labor | 70489575 | 55301890 | 57462866
MCR018142 | HPR137 | 2022-08-01 | Material | 142742037 | 111986836 | 111336109
MCR018143 | HPR137 | 2022-08-01 | Equipment | 31557511 | 24758129 | 24861927
MCR018144 | HPR137 | 2022-08-01 | Subcontract | 204136517 | 160153261 | 141391736
MCR018145 | HPR137 | 2022-08-01 | Overhead | 43865467 | 34414213 | 28796365
MCR018146 | HPR137 | 2022-09-01 | Labor | 68179374 | 58572973 | 56485324
MCR018147 | HPR137 | 2022-09-01 | Material | 138063858 | 118610808 | 130114399
MCR018148 | HPR137 | 2022-09-01 | Equipment | 30523256 | 26222562 | 25564995
MCR018149 | HPR137 | 2022-09-01 | Subcontract | 197446217 | 169626256 | 172791280
MCR018150 | HPR137 | 2022-09-01 | Overhead | 42427835 | 36449798 | 28130573
MCR018151 | HPR137 | 2022-10-01 | Labor | 64042278 | 52342729 | 52961300
MCR018152 | HPR137 | 2022-10-01 | Material | 129686200 | 105994506 | 121220272
MCR018153 | HPR137 | 2022-10-01 | Equipment | 28671118 | 23433341 | 25892321
MCR018154 | HPR137 | 2022-10-01 | Subcontract | 185465262 | 151583583 | 134323135
MCR018155 | HPR137 | 2022-10-01 | Overhead | 39853331 | 32572735 | 27731658
MCR018156 | HPR137 | 2022-11-01 | Labor | 58236155 | 28886444 | 30958327
MCR018157 | HPR137 | 2022-11-01 | Material | 117928749 | 58495314 | 52181699
MCR018158 | HPR137 | 2022-11-01 | Equipment | 26071772 | 12932186 | 11686729
MCR018159 | HPR137 | 2022-11-01 | Subcontract | 168650837 | 83654612 | 79401440
MCR018160 | HPR137 | 2022-11-01 | Overhead | 36240197 | 17975954 | 28078561
MCR018161 | HPR137 | 2022-12-01 | Labor | 50944868 | 85150353 | 96044183
MCR018162 | HPR137 | 2022-12-01 | Material | 103163825 | 172430246 | 161247909
MCR018163 | HPR137 | 2022-12-01 | Equipment | 22807532 | 38121002 | 41770732
MCR018164 | HPR137 | 2022-12-01 | Subcontract | 147535403 | 246593861 | 229140698
MCR018165 | HPR137 | 2022-12-01 | Overhead | 31702850 | 52988828 | 27333944
MCR018166 | HPR137 | 2023-01-01 | Labor | 42389111 | 42525849 | 42653687
MCR018167 | HPR137 | 2023-01-01 | Material | 85838339 | 86115235 | 93063322
MCR018168 | HPR137 | 2023-01-01 | Equipment | 18977201 | 19038418 | 16274105
MCR018169 | HPR137 | 2023-01-01 | Subcontract | 122758088 | 123154080 | 123509972
MCR018170 | HPR137 | 2023-01-01 | Overhead | 26378626 | 26463718 | 30768536
MCR018171 | HPR137 | 2023-02-01 | Labor | 32845542 | 40560177 | 41501566
MCR018172 | HPR137 | 2023-02-01 | Material | 66512524 | 82134730 | 82092594
MCR018173 | HPR137 | 2023-02-01 | Equipment | 14704636 | 18158405 | 19749367
MCR018174 | HPR137 | 2023-02-01 | Subcontract | 95120088 | 117461528 | 141183365
MCR018175 | HPR137 | 2023-02-01 | Overhead | 20439690 | 25240485 | 24227379
MCR018176 | HPR137 | 2023-03-01 | Labor | 22685190 | 40612324 | 40774444
MCR018177 | HPR137 | 2023-03-01 | Material | 45937718 | 82240329 | 81613230
MCR018178 | HPR137 | 2023-03-01 | Equipment | 10155944 | 18181751 | 19251577
MCR018179 | HPR137 | 2023-03-01 | Subcontract | 65695895 | 117612547 | 139144975
MCR018180 | HPR137 | 2023-03-01 | Overhead | 14116931 | 25272936 | 28609190
MCR018181 | HPR137 | 2023-04-01 | Labor | 12469016 | 30618601 | 27257955
MCR018182 | HPR137 | 2023-04-01 | Material | 25249871 | 62002947 | 65426129
MCR018183 | HPR137 | 2023-04-01 | Equipment | 5582260 | 13707656 | 13951478
MCR018184 | HPR137 | 2023-04-01 | Subcontract | 36110041 | 88670906 | 152108660
MCR018185 | HPR137 | 2023-04-01 | Overhead | 7759434 | 19053870 | 28117089
MCR018186 | HPR137 | 2023-05-01 | Labor | 3346296 | 35128583 | 40972457
MCR018187 | HPR137 | 2023-05-01 | Material | 6776279 | 71135704 | 65888457
MCR018188 | HPR137 | 2023-05-01 | Equipment | 1498105 | 15726732 | 16769399
MCR018189 | HPR137 | 2023-05-01 | Subcontract | 9690811 | 101731734 | 107924776
MCR018190 | HPR137 | 2023-05-01 | Overhead | 2082390 | 21860420 | 27182270
MCR018191 | HPR137 | 2023-06-01 | Labor | 0 | 14950295 | 11636635
MCR018192 | HPR137 | 2023-06-01 | Material | 0 | 30274485 | 34478738
MCR018193 | HPR137 | 2023-06-01 | Equipment | 0 | 6693105 | 6498862
MCR018194 | HPR137 | 2023-06-01 | Subcontract | 0 | 43295780 | 116732479
MCR018195 | HPR137 | 2023-06-01 | Overhead | 0 | 9303527 | 27828509
MCR018196 | HPR137 | 2023-07-01 | Labor | 0 | 16233384 | 16583937
MCR018197 | HPR137 | 2023-07-01 | Material | 0 | 32872751 | 30662097
MCR018198 | HPR137 | 2023-07-01 | Equipment | 0 | 7267531 | 7012510
MCR018199 | HPR137 | 2023-07-01 | Subcontract | 0 | 47011581 | 91163590
MCR018200 | HPR137 | 2023-07-01 | Overhead | 0 | 10101989 | 28103333
MCR018201 | HPR137 | 2023-08-01 | Labor | 0 | 7579793 | 7962370
MCR018202 | HPR137 | 2023-08-01 | Material | 0 | 15349150 | 16450584
MCR018203 | HPR137 | 2023-08-01 | Equipment | 0 | 3393401 | 4253543
MCR018204 | HPR137 | 2023-08-01 | Subcontract | 0 | 21950941 | 87179261
MCR018205 | HPR137 | 2023-08-01 | Overhead | 0 | 4716884 | 26020572
MCR018206 | HPR137 | 2023-09-01 | Labor | 0 | 1827432 | 1764017
MCR018207 | HPR137 | 2023-09-01 | Material | 0 | 3700566 | 3089601
MCR018208 | HPR137 | 2023-09-01 | Equipment | 0 | 818124 | 807919
MCR018209 | HPR137 | 2023-09-01 | Subcontract | 0 | 5292208 | 31173573
MCR018210 | HPR137 | 2023-09-01 | Overhead | 0 | 1137206 | 28022426
MCR018211 | HPR138 | 2018-07-01 | Labor | 17964452 | 8048975 | 9167589
MCR018212 | HPR138 | 2018-07-01 | Material | 35533411 | 15920750 | 15917586
MCR018213 | HPR138 | 2018-07-01 | Equipment | 8676969 | 3887717 | 4040902
MCR018214 | HPR138 | 2018-07-01 | Subcontract | 50143931 | 22466996 | 24443429
MCR018215 | HPR138 | 2018-07-01 | Overhead | 10030856 | 4494326 | 30871875
MCR018216 | HPR138 | 2018-08-01 | Labor | 47949505 | 23702245 | 22099801
MCR018217 | HPR138 | 2018-08-01 | Material | 94843389 | 46882679 | 48747194
MCR018218 | HPR138 | 2018-08-01 | Equipment | 23159981 | 11448368 | 12591587
MCR018219 | HPR138 | 2018-08-01 | Subcontract | 133840806 | 66159757 | 60545065
MCR018220 | HPR138 | 2018-08-01 | Overhead | 26773685 | 13234682 | 30089550
MCR018221 | HPR138 | 2018-09-01 | Labor | 69334710 | 65517780 | 57888379
MCR018222 | HPR138 | 2018-09-01 | Material | 137142998 | 129593168 | 127937346
MCR018223 | HPR138 | 2018-09-01 | Equipment | 33489200 | 31645594 | 30010809
MCR018224 | HPR138 | 2018-09-01 | Subcontract | 193533040 | 182878894 | 147623147
MCR018225 | HPR138 | 2018-09-01 | Overhead | 38714596 | 36583327 | 32770029
MCR018226 | HPR138 | 2018-10-01 | Labor | 82578173 | 50277810 | 51357943
MCR018227 | HPR138 | 2018-10-01 | Material | 163338366 | 99448741 | 102626012
MCR018228 | HPR138 | 2018-10-01 | Equipment | 39885895 | 24284571 | 23791488
MCR018229 | HPR138 | 2018-10-01 | Subcontract | 230499340 | 140339773 | 166473085
MCR018230 | HPR138 | 2018-10-01 | Overhead | 46109381 | 28073747 | 31869471
MCR018231 | HPR138 | 2018-11-01 | Labor | 88194953 | 49933950 | 50443251
MCR018232 | HPR138 | 2018-11-01 | Material | 174448270 | 98768592 | 96989066
MCR018233 | HPR138 | 2018-11-01 | Equipment | 42598843 | 24118484 | 22386222
MCR018234 | HPR138 | 2018-11-01 | Subcontract | 246177381 | 139379961 | 147446568
MCR018235 | HPR138 | 2018-11-01 | Overhead | 49245637 | 27881745 | 32519088
MCR018236 | HPR138 | 2018-12-01 | Labor | 86775672 | 151134905 | 161003151
MCR018237 | HPR138 | 2018-12-01 | Material | 171640954 | 298942534 | 288242037
MCR018238 | HPR138 | 2018-12-01 | Equipment | 41913319 | 72999326 | 79952931
MCR018239 | HPR138 | 2018-12-01 | Subcontract | 242215761 | 421860818 | 392941473
MCR018240 | HPR138 | 2018-12-01 | Overhead | 48453149 | 84389575 | 28564323
MCR018241 | HPR138 | 2019-01-01 | Labor | 79016163 | 62771225 | 54448777
MCR018242 | HPR138 | 2019-01-01 | Material | 156292763 | 124160525 | 140552839
MCR018243 | HPR138 | 2019-01-01 | Equipment | 38165417 | 30318986 | 30280423
MCR018244 | HPR138 | 2019-01-01 | Subcontract | 220556747 | 175212473 | 200005713
MCR018245 | HPR138 | 2019-01-01 | Overhead | 44120453 | 35049726 | 33153385
MCR018246 | HPR138 | 2019-02-01 | Labor | 65768922 | 65589034 | 63982122
MCR018247 | HPR138 | 2019-02-01 | Material | 130089924 | 129734108 | 122673249
MCR018248 | HPR138 | 2019-02-01 | Equipment | 31766897 | 31680010 | 31253475
MCR018249 | HPR138 | 2019-02-01 | Subcontract | 183579905 | 183077784 | 186979330
MCR018250 | HPR138 | 2019-02-01 | Overhead | 36723558 | 36623113 | 30561994
MCR018251 | HPR138 | 2019-03-01 | Labor | 48144507 | 73230494 | 72501933
MCR018252 | HPR138 | 2019-03-01 | Material | 95229100 | 144848798 | 140741389
MCR018253 | HPR138 | 2019-03-01 | Equipment | 23254169 | 35370894 | 34089310
MCR018254 | HPR138 | 2019-03-01 | Subcontract | 134385113 | 204407288 | 200391750
MCR018255 | HPR138 | 2019-03-01 | Overhead | 26882569 | 40889894 | 29261832
MCR018256 | HPR138 | 2019-04-01 | Labor | 27758357 | 46259604 | 49138661
MCR018257 | HPR138 | 2019-04-01 | Material | 54905605 | 91500791 | 105134603
MCR018258 | HPR138 | 2019-04-01 | Equipment | 13407501 | 22343746 | 21084207
MCR018259 | HPR138 | 2019-04-01 | Subcontract | 77481526 | 129123808 | 130495188
MCR018260 | HPR138 | 2019-04-01 | Overhead | 15499503 | 25830091 | 31461644
MCR018261 | HPR138 | 2019-05-01 | Labor | 7729023 | 19717892 | 19275776
MCR018262 | HPR138 | 2019-05-01 | Material | 15287889 | 39001689 | 33726346
MCR018263 | HPR138 | 2019-05-01 | Equipment | 3733178 | 9523894 | 9453412
MCR018264 | HPR138 | 2019-05-01 | Subcontract | 21573917 | 55038285 | 56596945
MCR018265 | HPR138 | 2019-05-01 | Overhead | 4315674 | 11009929 | 27599207
MCR018266 | HPR138 | 2019-06-01 | Labor | 0 | 5030521 | 4601299
MCR018267 | HPR138 | 2019-06-01 | Material | 0 | 9950294 | 11006779
MCR018268 | HPR138 | 2019-06-01 | Equipment | 0 | 2429781 | 3419845
MCR018269 | HPR138 | 2019-06-01 | Subcontract | 0 | 14041626 | 14394616
MCR018270 | HPR138 | 2019-06-01 | Overhead | 0 | 2808905 | 33086451
MCR018271 | HPR139 | 2021-11-01 | Labor | 833226 | 341316 | 386927
MCR018272 | HPR139 | 2021-11-01 | Material | 3382233 | 1385471 | 1458816
MCR018273 | HPR139 | 2021-11-01 | Equipment | 1543325 | 632195 | 632067
MCR018274 | HPR139 | 2021-11-01 | Subcontract | 1775162 | 727163 | 633674
MCR018275 | HPR139 | 2021-11-01 | Overhead | 644120 | 263852 | 3645884
MCR018276 | HPR139 | 2021-12-01 | Labor | 2351352 | 1589164 | 1617349
MCR018277 | HPR139 | 2021-12-01 | Material | 9544621 | 6450741 | 6308677
MCR018278 | HPR139 | 2021-12-01 | Equipment | 4355244 | 2943495 | 3482552
MCR018279 | HPR139 | 2021-12-01 | Subcontract | 5009485 | 3385665 | 3549223
MCR018280 | HPR139 | 2021-12-01 | Overhead | 1817698 | 1228493 | 3339217
MCR018281 | HPR139 | 2022-01-01 | Labor | 3651044 | 3072540 | 3331536
MCR018282 | HPR139 | 2022-01-01 | Material | 14820338 | 12472072 | 13428814
MCR018283 | HPR139 | 2022-01-01 | Equipment | 6762571 | 5691050 | 5455692
MCR018284 | HPR139 | 2022-01-01 | Subcontract | 7778439 | 6545954 | 7125900
MCR018285 | HPR139 | 2022-01-01 | Overhead | 2822417 | 2375208 | 3861051
MCR018286 | HPR139 | 2022-02-01 | Labor | 4737933 | 3461348 | 3396046
MCR018287 | HPR139 | 2022-02-01 | Material | 19232243 | 14050321 | 13733964
MCR018288 | HPR139 | 2022-02-01 | Equipment | 8775739 | 6411210 | 6743532
MCR018289 | HPR139 | 2022-02-01 | Subcontract | 10094023 | 7374297 | 7032861
MCR018290 | HPR139 | 2022-02-01 | Overhead | 3662630 | 2675773 | 3554682
MCR018291 | HPR139 | 2022-03-01 | Labor | 5617969 | 3946523 | 3754055
MCR018292 | HPR139 | 2022-03-01 | Material | 22804488 | 16019745 | 17716736
MCR018293 | HPR139 | 2022-03-01 | Equipment | 10405767 | 7309865 | 7579861
MCR018294 | HPR139 | 2022-03-01 | Subcontract | 11968913 | 8407947 | 8828838
MCR018295 | HPR139 | 2022-03-01 | Overhead | 4342936 | 3050835 | 3841957
MCR018296 | HPR139 | 2022-04-01 | Labor | 6297463 | 5487776 | 6066819
MCR018297 | HPR139 | 2022-04-01 | Material | 25562693 | 22276009 | 23861146
MCR018298 | HPR139 | 2022-04-01 | Equipment | 11664345 | 10164620 | 9534590
MCR018299 | HPR139 | 2022-04-01 | Subcontract | 13416554 | 11691541 | 14048967
MCR018300 | HPR139 | 2022-04-01 | Overhead | 4868214 | 4242291 | 3475686
MCR018301 | HPR139 | 2022-05-01 | Labor | 6783140 | 3949689 | 3552652
MCR018302 | HPR139 | 2022-05-01 | Material | 27534157 | 16032599 | 13949119
MCR018303 | HPR139 | 2022-05-01 | Equipment | 12563931 | 7315731 | 7473148
MCR018304 | HPR139 | 2022-05-01 | Subcontract | 14451275 | 8414694 | 7403055
MCR018305 | HPR139 | 2022-05-01 | Overhead | 5243664 | 3053283 | 3802524
MCR018306 | HPR139 | 2022-06-01 | Labor | 7082207 | 5095208 | 5452960
MCR018307 | HPR139 | 2022-06-01 | Material | 28748131 | 20682492 | 23600933
MCR018308 | HPR139 | 2022-06-01 | Equipment | 13117872 | 9437493 | 9322629
MCR018309 | HPR139 | 2022-06-01 | Subcontract | 15088428 | 10855185 | 11213291
MCR018310 | HPR139 | 2022-06-01 | Overhead | 5474856 | 3938818 | 3572930
MCR018311 | HPR139 | 2022-07-01 | Labor | 7202433 | 4626593 | 4928984
MCR018312 | HPR139 | 2022-07-01 | Material | 29236152 | 18780290 | 18501025
MCR018313 | HPR139 | 2022-07-01 | Equipment | 13340558 | 8569512 | 8547148
MCR018314 | HPR139 | 2022-07-01 | Subcontract | 15344565 | 9856817 | 10966091
MCR018315 | HPR139 | 2022-07-01 | Overhead | 5567796 | 3576559 | 3447577
MCR018316 | HPR139 | 2022-08-01 | Labor | 7152257 | 3562677 | 3138943
MCR018317 | HPR139 | 2022-08-01 | Material | 29032478 | 14461636 | 13731264
MCR018318 | HPR139 | 2022-08-01 | Equipment | 13247621 | 6598895 | 8418901
MCR018319 | HPR139 | 2022-08-01 | Subcontract | 15237667 | 7590175 | 7606727
MCR018320 | HPR139 | 2022-08-01 | Overhead | 5529008 | 2754105 | 3421900
MCR018321 | HPR139 | 2022-09-01 | Labor | 6940929 | 4492520 | 4210276
MCR018322 | HPR139 | 2022-09-01 | Material | 28174655 | 18236059 | 18784185
MCR018323 | HPR139 | 2022-09-01 | Equipment | 12856193 | 8321177 | 7366603
MCR018324 | HPR139 | 2022-09-01 | Subcontract | 14787440 | 9571177 | 11153526
MCR018325 | HPR139 | 2022-09-01 | Overhead | 5365642 | 3472914 | 3456995
MCR018326 | HPR139 | 2022-10-01 | Labor | 6578698 | 5745488 | 5764505
MCR018327 | HPR139 | 2022-10-01 | Material | 26704283 | 23322113 | 25972525
MCR018328 | HPR139 | 2022-10-01 | Equipment | 12185257 | 10641961 | 11234328
MCR018329 | HPR139 | 2022-10-01 | Subcontract | 14015716 | 12240588 | 9868967
MCR018330 | HPR139 | 2022-10-01 | Overhead | 5085621 | 4441513 | 3482420
MCR018331 | HPR139 | 2022-11-01 | Labor | 6077073 | 3742833 | 4151803
MCR018332 | HPR139 | 2022-11-01 | Material | 24668084 | 15192925 | 15173886
MCR018333 | HPR139 | 2022-11-01 | Equipment | 11256132 | 6932584 | 7083869
MCR018334 | HPR139 | 2022-11-01 | Subcontract | 12947019 | 7973992 | 10372419
MCR018335 | HPR139 | 2022-11-01 | Overhead | 4697843 | 2893373 | 3534642
MCR018336 | HPR139 | 2022-12-01 | Labor | 5449206 | 5337162 | 5118823
MCR018337 | HPR139 | 2022-12-01 | Material | 22119444 | 21664634 | 21098460
MCR018338 | HPR139 | 2022-12-01 | Equipment | 10093179 | 9885647 | 9943644
MCR018339 | HPR139 | 2022-12-01 | Subcontract | 11609368 | 11370661 | 12803629
MCR018340 | HPR139 | 2022-12-01 | Overhead | 4212474 | 4125859 | 3577131
MCR018341 | HPR139 | 2023-01-01 | Labor | 4710469 | 7440654 | 7165547
MCR018342 | HPR139 | 2023-01-01 | Material | 19120760 | 30203142 | 30859170
MCR018343 | HPR139 | 2023-01-01 | Equipment | 8724869 | 13781798 | 14085843
MCR018344 | HPR139 | 2023-01-01 | Subcontract | 10035512 | 15852089 | 15469038
MCR018345 | HPR139 | 2023-01-01 | Overhead | 3641399 | 5751951 | 3495501
MCR018346 | HPR139 | 2023-02-01 | Labor | 3879390 | 6354721 | 7343520
MCR018347 | HPR139 | 2023-02-01 | Material | 15747241 | 25795117 | 26733339
MCR018348 | HPR139 | 2023-02-01 | Equipment | 7185521 | 11770401 | 12716303
MCR018349 | HPR139 | 2023-02-01 | Subcontract | 8264924 | 13538541 | 15805013
MCR018350 | HPR139 | 2023-02-01 | Overhead | 2998939 | 4912478 | 3517847
MCR018351 | HPR139 | 2023-03-01 | Labor | 2979312 | 7206993 | 8604490
MCR018352 | HPR139 | 2023-03-01 | Material | 12093640 | 29254661 | 31801136
MCR018353 | HPR139 | 2023-03-01 | Equipment | 5518370 | 13349003 | 14923497
MCR018354 | HPR139 | 2023-03-01 | Subcontract | 6347335 | 15354280 | 21211412
MCR018355 | HPR139 | 2023-03-01 | Overhead | 2303139 | 5571321 | 3835156
MCR018356 | HPR139 | 2023-04-01 | Labor | 2041732 | 2998184 | 2534146
MCR018357 | HPR139 | 2023-04-01 | Material | 8287808 | 12170242 | 9868677
MCR018358 | HPR139 | 2023-04-01 | Equipment | 3781756 | 5553324 | 4418978
MCR018359 | HPR139 | 2023-04-01 | Subcontract | 4349848 | 6387540 | 10726691
MCR018360 | HPR139 | 2023-04-01 | Overhead | 1578348 | 2317727 | 3675727
MCR018361 | HPR139 | 2023-05-01 | Labor | 1114643 | 4651503 | 4539651
MCR018362 | HPR139 | 2023-05-01 | Material | 4524563 | 18881404 | 19109204
MCR018363 | HPR139 | 2023-05-01 | Equipment | 2064574 | 8615650 | 9491526
MCR018364 | HPR139 | 2023-05-01 | Subcontract | 2374712 | 9909886 | 13878548
MCR018365 | HPR139 | 2023-05-01 | Overhead | 861667 | 3595815 | 3454039
MCR018366 | HPR139 | 2023-06-01 | Labor | 297494 | 3734637 | 4365115
MCR018367 | HPR139 | 2023-06-01 | Material | 1207591 | 15159656 | 16088746
MCR018368 | HPR139 | 2023-06-01 | Equipment | 551028 | 6917404 | 6219763
MCR018369 | HPR139 | 2023-06-01 | Subcontract | 633803 | 7956530 | 12965942
MCR018370 | HPR139 | 2023-06-01 | Overhead | 229976 | 2887038 | 3583940
MCR018371 | HPR139 | 2023-07-01 | Labor | 0 | 2346655 | 2572011
MCR018372 | HPR139 | 2023-07-01 | Material | 0 | 9525552 | 9278650
MCR018373 | HPR139 | 2023-07-01 | Equipment | 0 | 4346543 | 5315120
MCR018374 | HPR139 | 2023-07-01 | Subcontract | 0 | 4999477 | 10812259
MCR018375 | HPR139 | 2023-07-01 | Overhead | 0 | 1814067 | 3438069
MCR018376 | HPR139 | 2023-08-01 | Labor | 0 | 982567 | 861888
MCR018377 | HPR139 | 2023-08-01 | Material | 0 | 3988439 | 4468708
MCR018378 | HPR139 | 2023-08-01 | Equipment | 0 | 1819939 | 1360128
MCR018379 | HPR139 | 2023-08-01 | Subcontract | 0 | 2093328 | 7613429
MCR018380 | HPR139 | 2023-08-01 | Overhead | 0 | 759567 | 3746684
MCR018381 | HPR139 | 2023-09-01 | Labor | 0 | 880641 | 924584
MCR018382 | HPR139 | 2023-09-01 | Material | 0 | 3574702 | 3268731
MCR018383 | HPR139 | 2023-09-01 | Equipment | 0 | 1631149 | 1703106
MCR018384 | HPR139 | 2023-09-01 | Subcontract | 0 | 1876179 | 5968075
MCR018385 | HPR139 | 2023-09-01 | Overhead | 0 | 680774 | 3404438
MCR018386 | HPR139 | 2023-10-01 | Labor | 0 | 573592 | 660705
MCR018387 | HPR139 | 2023-10-01 | Material | 0 | 2328327 | 2267184
MCR018388 | HPR139 | 2023-10-01 | Equipment | 0 | 1062424 | 1241372
MCR018389 | HPR139 | 2023-10-01 | Subcontract | 0 | 1222020 | 6317936
MCR018390 | HPR139 | 2023-10-01 | Overhead | 0 | 443412 | 3243666
MCR018391 | HPR139 | 2023-11-01 | Labor | 0 | 156990 | 139369
MCR018392 | HPR139 | 2023-11-01 | Material | 0 | 637253 | 686573
MCR018393 | HPR139 | 2023-11-01 | Equipment | 0 | 290781 | 383060
MCR018394 | HPR139 | 2023-11-01 | Subcontract | 0 | 334462 | 3243441
MCR018395 | HPR139 | 2023-11-01 | Overhead | 0 | 121360 | 3191874
MCR018396 | HPR140 | 2019-11-01 | Labor | 15566379 | 10930908 | 10350861
MCR018397 | HPR140 | 2019-11-01 | Material | 30121267 | 21151533 | 22600389
MCR018398 | HPR140 | 2019-11-01 | Equipment | 6033518 | 4236812 | 4645141
MCR018399 | HPR140 | 2019-11-01 | Subcontract | 26954863 | 18928045 | 16803136
MCR018400 | HPR140 | 2019-11-01 | Overhead | 9067567 | 6367360 | 47046984
MCR018401 | HPR140 | 2019-12-01 | Labor | 43611055 | 35483253 | 39157601
MCR018402 | HPR140 | 2019-12-01 | Material | 84388296 | 68660830 | 70019200
MCR018403 | HPR140 | 2019-12-01 | Equipment | 16903615 | 13753284 | 12273679
MCR018404 | HPR140 | 2019-12-01 | Subcontract | 75517241 | 61443076 | 58456905
MCR018405 | HPR140 | 2019-12-01 | Overhead | 25403864 | 20669340 | 44848439
MCR018406 | HPR140 | 2020-01-01 | Labor | 67118169 | 34547710 | 36752645
MCR018407 | HPR140 | 2020-01-01 | Material | 129875049 | 66850537 | 61688749
MCR018408 | HPR140 | 2020-01-01 | Equipment | 26014956 | 13390669 | 14092294
MCR018409 | HPR140 | 2020-01-01 | Subcontract | 116222341 | 59823083 | 53855622
MCR018410 | HPR140 | 2020-01-01 | Overhead | 39096987 | 20124378 | 46164481
MCR018411 | HPR140 | 2020-02-01 | Labor | 86219859 | 46490785 | 46211969
MCR018412 | HPR140 | 2020-02-01 | Material | 166837216 | 89960633 | 88485758
MCR018413 | HPR140 | 2020-02-01 | Equipment | 33418758 | 18019796 | 19005751
MCR018414 | HPR140 | 2020-02-01 | Subcontract | 149298976 | 80503804 | 89448353
MCR018415 | HPR140 | 2020-02-01 | Overhead | 50223907 | 27081335 | 46961770
MCR018416 | HPR140 | 2020-03-01 | Labor | 101056751 | 79018511 | 81372995
MCR018417 | HPR140 | 2020-03-01 | Material | 195546910 | 152902458 | 182817263
MCR018418 | HPR140 | 2020-03-01 | Equipment | 39169527 | 30627520 | 27719141
MCR018419 | HPR140 | 2020-03-01 | Subcontract | 174990653 | 136829066 | 116228997
MCR018420 | HPR140 | 2020-03-01 | Overhead | 58866541 | 46029052 | 43824430
MCR018421 | HPR140 | 2020-04-01 | Labor | 111779289 | 66342931 | 69743991
MCR018422 | HPR140 | 2020-04-01 | Material | 216295243 | 128374949 | 126595157
MCR018423 | HPR140 | 2020-04-01 | Equipment | 43325575 | 25714475 | 30853799
MCR018424 | HPR140 | 2020-04-01 | Subcontract | 193557883 | 114879934 | 120595327
MCR018425 | HPR140 | 2020-04-01 | Overhead | 65112524 | 38645404 | 46738609
MCR018426 | HPR140 | 2020-05-01 | Labor | 118549412 | 93400237 | 89717508
MCR018427 | HPR140 | 2020-05-01 | Material | 229395572 | 180731397 | 195596519
MCR018428 | HPR140 | 2020-05-01 | Equipment | 45949670 | 36201868 | 37106191
MCR018429 | HPR140 | 2020-05-01 | Subcontract | 205281081 | 161732575 | 156122511
MCR018430 | HPR140 | 2020-05-01 | Overhead | 69056187 | 54406548 | 47834746
MCR018431 | HPR140 | 2020-06-01 | Labor | 121542702 | 122535388 | 124842897
MCR018432 | HPR140 | 2020-06-01 | Material | 235187650 | 237108518 | 268543512
MCR018433 | HPR140 | 2020-06-01 | Equipment | 47109868 | 47494632 | 47950295
MCR018434 | HPR140 | 2020-06-01 | Subcontract | 210464285 | 212183228 | 207823633
MCR018435 | HPR140 | 2020-06-01 | Overhead | 70799807 | 71378057 | 47010426
MCR018436 | HPR140 | 2020-07-01 | Labor | 120951198 | 57593448 | 62574734
MCR018437 | HPR140 | 2020-07-01 | Material | 234043077 | 111444517 | 110758238
MCR018438 | HPR140 | 2020-07-01 | Equipment | 46880601 | 22323181 | 25454316
MCR018439 | HPR140 | 2020-07-01 | Subcontract | 209440032 | 99729261 | 96948720
MCR018440 | HPR140 | 2020-07-01 | Overhead | 70455251 | 33548744 | 43536445
MCR018441 | HPR140 | 2020-08-01 | Labor | 116987184 | 40965128 | 45074238
MCR018442 | HPR140 | 2020-08-01 | Material | 226372630 | 79268373 | 75673530
MCR018443 | HPR140 | 2020-08-01 | Equipment | 45344152 | 15878055 | 15709924
MCR018444 | HPR140 | 2020-08-01 | Subcontract | 202575916 | 70935533 | 69048877
MCR018445 | HPR140 | 2020-08-01 | Overhead | 68146174 | 23862586 | 45380192
MCR018446 | HPR140 | 2020-09-01 | Labor | 109888450 | 69573035 | 71292506
MCR018447 | HPR140 | 2020-09-01 | Material | 212636432 | 134625267 | 127469249
MCR018448 | HPR140 | 2020-09-01 | Equipment | 42592688 | 26966461 | 32037085
MCR018449 | HPR140 | 2020-09-01 | Subcontract | 190283693 | 120473207 | 117704063
MCR018450 | HPR140 | 2020-09-01 | Overhead | 64011093 | 40526971 | 46267268
MCR018451 | HPR140 | 2020-10-01 | Labor | 99925878 | 131608662 | 151212277
MCR018452 | HPR140 | 2020-10-01 | Material | 193358648 | 254665491 | 275860216
MCR018453 | HPR140 | 2020-10-01 | Equipment | 38731202 | 51011427 | 47798553
MCR018454 | HPR140 | 2020-10-01 | Subcontract | 173032426 | 227894579 | 204179822
MCR018455 | HPR140 | 2020-10-01 | Overhead | 58207797 | 76663327 | 40716354
MCR018456 | HPR140 | 2020-11-01 | Labor | 87414951 | 47288551 | 43975422
MCR018457 | HPR140 | 2020-11-01 | Material | 169149745 | 91504327 | 94411595
MCR018458 | HPR140 | 2020-11-01 | Equipment | 33881975 | 18329010 | 21355403
MCR018459 | HPR140 | 2020-11-01 | Subcontract | 151368407 | 81885221 | 94530208
MCR018460 | HPR140 | 2020-11-01 | Overhead | 50920060 | 27546041 | 42690973
MCR018461 | HPR140 | 2020-12-01 | Labor | 72734354 | 104199506 | 106667211
MCR018462 | HPR140 | 2020-12-01 | Material | 140742484 | 201628206 | 213635338
MCR018463 | HPR140 | 2020-12-01 | Equipment | 28191786 | 40387657 | 43709043
MCR018464 | HPR140 | 2020-12-01 | Subcontract | 125947372 | 180432672 | 177915147
MCR018465 | HPR140 | 2020-12-01 | Overhead | 42368470 | 60697227 | 46353043
MCR018466 | HPR140 | 2021-01-01 | Labor | 56358797 | 135194875 | 139628408
MCR018467 | HPR140 | 2021-01-01 | Material | 109055442 | 261604889 | 240305479
MCR018468 | HPR140 | 2021-01-01 | Equipment | 21844631 | 52401441 | 54041457
MCR018469 | HPR140 | 2021-01-01 | Subcontract | 97591330 | 234104494 | 208175616
MCR018470 | HPR140 | 2021-01-01 | Overhead | 32829548 | 78752331 | 42051631
MCR018471 | HPR140 | 2021-02-01 | Labor | 38924918 | 106816288 | 110071275
MCR018472 | HPR140 | 2021-02-01 | Material | 75320524 | 206691734 | 226358801
MCR018473 | HPR140 | 2021-02-01 | Equipment | 15087271 | 41401920 | 42863930
MCR018474 | HPR140 | 2021-02-01 | Subcontract | 67402690 | 184963912 | 246600224
MCR018475 | HPR140 | 2021-02-01 | Overhead | 22674144 | 62221528 | 44565920
MCR018476 | HPR140 | 2021-03-01 | Labor | 21395254 | 51835930 | 52644635
MCR018477 | HPR140 | 2021-03-01 | Material | 41400261 | 100303600 | 94849345
MCR018478 | HPR140 | 2021-03-01 | Equipment | 8292786 | 20091571 | 18063668
MCR018479 | HPR140 | 2021-03-01 | Subcontract | 37048188 | 89759498 | 172084750
MCR018480 | HPR140 | 2021-03-01 | Overhead | 12462944 | 30194934 | 42955273
MCR018481 | HPR140 | 2021-04-01 | Labor | 5741820 | 54253063 | 49071542
MCR018482 | HPR140 | 2021-04-01 | Material | 11110541 | 104980803 | 127290801
MCR018483 | HPR140 | 2021-04-01 | Equipment | 2225526 | 21028450 | 21976104
MCR018484 | HPR140 | 2021-04-01 | Subcontract | 9942580 | 93945025 | 110338595
MCR018485 | HPR140 | 2021-04-01 | Overhead | 3344666 | 31602938 | 48278093
MCR018486 | HPR140 | 2021-05-01 | Labor | 0 | 48512832 | 52068065
MCR018487 | HPR140 | 2021-05-01 | Material | 0 | 93873336 | 106028061
MCR018488 | HPR140 | 2021-05-01 | Equipment | 0 | 18803540 | 19166985
MCR018489 | HPR140 | 2021-05-01 | Subcontract | 0 | 84005196 | 148517332
MCR018490 | HPR140 | 2021-05-01 | Overhead | 0 | 28259197 | 45619988
MCR018491 | HPR140 | 2021-06-01 | Labor | 0 | 28578602 | 31014918
MCR018492 | HPR140 | 2021-06-01 | Material | 0 | 55300187 | 64491606
MCR018493 | HPR140 | 2021-06-01 | Equipment | 0 | 11077046 | 13005116
MCR018494 | HPR140 | 2021-06-01 | Subcontract | 0 | 49486928 | 78110706
MCR018495 | HPR140 | 2021-06-01 | Overhead | 0 | 16647314 | 43377229
MCR018496 | HPR140 | 2021-07-01 | Labor | 0 | 13539397 | 13456865
MCR018497 | HPR140 | 2021-07-01 | Material | 0 | 26199015 | 30113051
MCR018498 | HPR140 | 2021-07-01 | Equipment | 0 | 5247861 | 5084296
MCR018499 | HPR140 | 2021-07-01 | Subcontract | 0 | 23444926 | 94935743
MCR018500 | HPR140 | 2021-07-01 | Overhead | 0 | 7886831 | 44051069
MCR018501 | HPR140 | 2021-08-01 | Labor | 0 | 14884422 | 14640222
MCR018502 | HPR140 | 2021-08-01 | Material | 0 | 28801666 | 33688350
MCR018503 | HPR140 | 2021-08-01 | Equipment | 0 | 5769192 | 5643249
MCR018504 | HPR140 | 2021-08-01 | Subcontract | 0 | 25773981 | 89808935
MCR018505 | HPR140 | 2021-08-01 | Overhead | 0 | 8670321 | 48461586
MCR018506 | HPR140 | 2021-09-01 | Labor | 0 | 2172958 | 1859295
MCR018507 | HPR140 | 2021-09-01 | Material | 0 | 4204719 | 6096942
MCR018508 | HPR140 | 2021-09-01 | Equipment | 0 | 842237 | 1600138
MCR018509 | HPR140 | 2021-09-01 | Subcontract | 0 | 3762711 | 62009510
MCR018510 | HPR140 | 2021-09-01 | Overhead | 0 | 1265769 | 47155222
MCR018511 | HPR141 | 2021-07-01 | Labor | 4828749 | 4004060 | 4236539
MCR018512 | HPR141 | 2021-07-01 | Material | 10444946 | 8661081 | 8372411
MCR018513 | HPR141 | 2021-07-01 | Equipment | 2944066 | 2441257 | 2411524
MCR018514 | HPR141 | 2021-07-01 | Subcontract | 12532039 | 10391726 | 9887986
MCR018515 | HPR141 | 2021-07-01 | Overhead | 3032615 | 2514683 | 17713942
MCR018516 | HPR141 | 2021-08-01 | Labor | 13706715 | 8689587 | 8519198
MCR018517 | HPR141 | 2021-08-01 | Material | 29648652 | 18796228 | 18386156
MCR018518 | HPR141 | 2021-08-01 | Equipment | 8356920 | 5298001 | 5389478
MCR018519 | HPR141 | 2021-08-01 | Subcontract | 35573001 | 22552062 | 18305310
MCR018520 | HPR141 | 2021-08-01 | Overhead | 8608273 | 5457350 | 17807536
MCR018521 | HPR141 | 2021-09-01 | Labor | 21434602 | 31317412 | 35414880
MCR018522 | HPR141 | 2021-09-01 | Material | 46364649 | 67741907 | 67018579
MCR018523 | HPR141 | 2021-09-01 | Equipment | 13068577 | 19094079 | 18874643
MCR018524 | HPR141 | 2021-09-01 | Subcontract | 55629164 | 81277994 | 82472232
MCR018525 | HPR141 | 2021-09-01 | Overhead | 13461643 | 19668376 | 17774319
MCR018526 | HPR141 | 2021-10-01 | Labor | 28039012 | 15751532 | 14836230
MCR018527 | HPR141 | 2021-10-01 | Material | 60650483 | 34071744 | 35238703
MCR018528 | HPR141 | 2021-10-01 | Equipment | 17095255 | 9603636 | 8818841
MCR018529 | HPR141 | 2021-10-01 | Subcontract | 72769572 | 40879909 | 44965813
MCR018530 | HPR141 | 2021-10-01 | Overhead | 17609432 | 9892486 | 18275785
MCR018531 | HPR141 | 2021-11-01 | Labor | 33547888 | 22190855 | 24244775
MCR018532 | HPR141 | 2021-11-01 | Material | 72566595 | 48000482 | 45785205
MCR018533 | HPR141 | 2021-11-01 | Equipment | 20453991 | 13529661 | 15596918
MCR018534 | HPR141 | 2021-11-01 | Subcontract | 87066744 | 57591867 | 52311573
MCR018535 | HPR141 | 2021-11-01 | Overhead | 21069190 | 13936595 | 17410549
MCR018536 | HPR141 | 2021-12-01 | Labor | 37990675 | 34083684 | 35744105
MCR018537 | HPR141 | 2021-12-01 | Material | 82176675 | 73725560 | 79126534
MCR018538 | HPR141 | 2021-12-01 | Equipment | 23162737 | 20780662 | 19442559
MCR018539 | HPR141 | 2021-12-01 | Subcontract | 98597095 | 88457292 | 95846276
MCR018540 | HPR141 | 2021-12-01 | Overhead | 23859408 | 21405687 | 18838726
MCR018541 | HPR141 | 2022-01-01 | Labor | 41398511 | 33369767 | 38822146
MCR018542 | HPR141 | 2022-01-01 | Material | 89548081 | 72181305 | 77496020
MCR018543 | HPR141 | 2022-01-01 | Equipment | 25240479 | 20345391 | 21761000
MCR018544 | HPR141 | 2022-01-01 | Subcontract | 107441445 | 86604466 | 77452902
MCR018545 | HPR141 | 2022-01-01 | Overhead | 25999642 | 20957324 | 18144518
MCR018546 | HPR141 | 2022-02-01 | Labor | 43804468 | 41666043 | 41292152
MCR018547 | HPR141 | 2022-02-01 | Material | 94752345 | 90126771 | 102693125
MCR018548 | HPR141 | 2022-02-01 | Equipment | 26707379 | 25403592 | 26838910
MCR018549 | HPR141 | 2022-02-01 | Subcontract | 113685617 | 108135769 | 95208144
MCR018550 | HPR141 | 2022-02-01 | Overhead | 27510663 | 26167661 | 19322537
MCR018551 | HPR141 | 2022-03-01 | Labor | 45243831 | 63034774 | 73275616
MCR018552 | HPR141 | 2022-03-01 | Material | 97865795 | 136348938 | 164755819
MCR018553 | HPR141 | 2022-03-01 | Equipment | 27584952 | 38432007 | 40659590
MCR018554 | HPR141 | 2022-03-01 | Subcontract | 117421192 | 163593979 | 178612409
MCR018555 | HPR141 | 2022-03-01 | Overhead | 28414631 | 39587935 | 19412290
MCR018556 | HPR141 | 2022-04-01 | Labor | 45754461 | 50214888 | 53809556
MCR018557 | HPR141 | 2022-04-01 | Material | 98970326 | 108618564 | 97331395
MCR018558 | HPR141 | 2022-04-01 | Equipment | 27896281 | 30615783 | 32233962
MCR018559 | HPR141 | 2022-04-01 | Subcontract | 118746429 | 130322564 | 126661477
MCR018560 | HPR141 | 2022-04-01 | Overhead | 28735324 | 31536620 | 19146267
MCR018561 | HPR141 | 2022-05-01 | Labor | 45377241 | 43664274 | 76529377
MCR018562 | HPR141 | 2022-05-01 | Material | 98154371 | 94449096 | 103475147
MCR018563 | HPR141 | 2022-05-01 | Equipment | 27666292 | 26621904 | 26747860
MCR018564 | HPR141 | 2022-05-01 | Subcontract | 117767431 | 113321774 | 109917390
MCR018565 | HPR141 | 2022-05-01 | Overhead | 28498417 | 27422617 | 17895552
MCR018566 | HPR141 | 2022-06-01 | Labor | 44156657 | 39249821 | 75806881
MCR018567 | HPR141 | 2022-06-01 | Material | 95514156 | 84900303 | 135529413
MCR018568 | HPR141 | 2022-06-01 | Equipment | 26922107 | 23930433 | 25498490
MCR018569 | HPR141 | 2022-06-01 | Subcontract | 114599653 | 101864955 | 106643060
MCR018570 | HPR141 | 2022-06-01 | Overhead | 27731850 | 24650193 | 18682388
MCR018571 | HPR141 | 2022-07-01 | Labor | 42141559 | 35892058 | 31900370
MCR018572 | HPR141 | 2022-07-01 | Material | 91155348 | 77637210 | 77488090
MCR018573 | HPR141 | 2022-07-01 | Equipment | 25693511 | 21883220 | 17079264
MCR018574 | HPR141 | 2022-07-01 | Subcontract | 109369873 | 93150562 | 91265262
MCR018575 | HPR141 | 2022-07-01 | Overhead | 26466301 | 22541407 | 17772064
MCR018576 | HPR141 | 2022-08-01 | Labor | 39386189 | 30973932 | 37710144
MCR018577 | HPR141 | 2022-08-01 | Material | 85195276 | 66998935 | 62392152
MCR018578 | HPR141 | 2022-08-01 | Equipment | 24013575 | 18884662 | 23513650
MCR018579 | HPR141 | 2022-08-01 | Subcontract | 102218869 | 80386563 | 71639089
MCR018580 | HPR141 | 2022-08-01 | Overhead | 24735837 | 19452660 | 18635788
MCR018581 | HPR141 | 2022-09-01 | Labor | 35951616 | 28354553 | 31507757
MCR018582 | HPR141 | 2022-09-01 | Material | 77766039 | 61333021 | 65001019
MCR018583 | HPR141 | 2022-09-01 | Equipment | 21919532 | 17287638 | 14818944
MCR018584 | HPR141 | 2022-09-01 | Subcontract | 93305132 | 73588494 | 85011573
MCR018585 | HPR141 | 2022-09-01 | Overhead | 22578811 | 17807602 | 17831142
MCR018586 | HPR141 | 2022-10-01 | Labor | 31907818 | 24184315 | 23171371
MCR018587 | HPR141 | 2022-10-01 | Material | 69019000 | 52312484 | 52414425
MCR018588 | HPR141 | 2022-10-01 | Equipment | 19454047 | 14745064 | 15446999
MCR018589 | HPR141 | 2022-10-01 | Subcontract | 82810274 | 62765487 | 59660813
MCR018590 | HPR141 | 2022-10-01 | Overhead | 20039171 | 15188554 | 18323452
MCR018591 | HPR141 | 2022-11-01 | Labor | 27336845 | 33131675 | 35363081
MCR018592 | HPR141 | 2022-11-01 | Material | 59131643 | 71666294 | 78968191
MCR018593 | HPR141 | 2022-11-01 | Equipment | 16667146 | 20200227 | 22255258
MCR018594 | HPR141 | 2022-11-01 | Subcontract | 70947239 | 85986546 | 93380828
MCR018595 | HPR141 | 2022-11-01 | Overhead | 17168448 | 20807794 | 18843503
MCR018596 | HPR141 | 2022-12-01 | Labor | 22337970 | 21065042 | 24075323
MCR018597 | HPR141 | 2022-12-01 | Material | 48318702 | 45565265 | 46048361
MCR018598 | HPR141 | 2022-12-01 | Equipment | 13619356 | 12843258 | 12756554
MCR018599 | HPR141 | 2022-12-01 | Subcontract | 57973673 | 54670048 | 63849474
MCR018600 | HPR141 | 2022-12-01 | Overhead | 14028988 | 13229547 | 18267933
MCR018601 | HPR141 | 2023-01-01 | Labor | 17036824 | 24643775 | 27023192
MCR018602 | HPR141 | 2023-01-01 | Material | 36851926 | 53306331 | 49592781
MCR018603 | HPR141 | 2023-01-01 | Equipment | 10387272 | 15025194 | 13733828
MCR018604 | HPR141 | 2023-01-01 | Subcontract | 44215624 | 63957923 | 55245887
MCR018605 | HPR141 | 2023-01-01 | Overhead | 10699692 | 15477111 | 16949058
MCR018606 | HPR141 | 2023-02-01 | Labor | 11603852 | 17423411 | 14334288
MCR018607 | HPR141 | 2023-02-01 | Material | 25100000 | 37688143 | 45831873
MCR018608 | HPR141 | 2023-02-01 | Equipment | 7074814 | 10622972 | 11344034
MCR018609 | HPR141 | 2023-02-01 | Subcontract | 30115445 | 45218932 | 46316341
MCR018610 | HPR141 | 2023-02-01 | Overhead | 7287605 | 10942482 | 17930997
MCR018611 | HPR141 | 2023-03-01 | Labor | 6300556 | 10810865 | 11250740
MCR018612 | HPR141 | 2023-03-01 | Material | 13628575 | 23384710 | 17419698
MCR018613 | HPR141 | 2023-03-01 | Equipment | 3841420 | 6591334 | 7406821
MCR018614 | HPR141 | 2023-03-01 | Subcontract | 16351817 | 28057408 | 30553560
MCR018615 | HPR141 | 2023-03-01 | Overhead | 3956959 | 6789583 | 17783323
MCR018616 | HPR141 | 2023-04-01 | Labor | 1674139 | 10761880 | 11237093
MCR018617 | HPR141 | 2023-04-01 | Material | 3621288 | 23278753 | 23538891
MCR018618 | HPR141 | 2023-04-01 | Equipment | 1020715 | 6561468 | 6477567
MCR018619 | HPR141 | 2023-04-01 | Subcontract | 4344889 | 27930279 | 27497261
MCR018620 | HPR141 | 2023-04-01 | Overhead | 1051415 | 6758819 | 18308569
MCR018621 | HPR141 | 2023-05-01 | Labor | 0 | 9388755 | 10473841
MCR018622 | HPR141 | 2023-05-01 | Material | 0 | 20308580 | 23054837
MCR018623 | HPR141 | 2023-05-01 | Equipment | 0 | 5724280 | 6462479
MCR018624 | HPR141 | 2023-05-01 | Subcontract | 0 | 24366610 | 26762681
MCR018625 | HPR141 | 2023-05-01 | Overhead | 0 | 5896450 | 17616145
MCR018626 | HPR141 | 2023-06-01 | Labor | 0 | 5759747 | 5807875
MCR018627 | HPR141 | 2023-06-01 | Material | 0 | 12458763 | 12512492
MCR018628 | HPR141 | 2023-06-01 | Equipment | 0 | 3511691 | 2948528
MCR018629 | HPR141 | 2023-06-01 | Subcontract | 0 | 14948255 | 14172112
MCR018630 | HPR141 | 2023-06-01 | Overhead | 0 | 3617312 | 18149149
MCR018631 | HPR141 | 2023-07-01 | Labor | 0 | 1333471 | 1160486
MCR018632 | HPR141 | 2023-07-01 | Material | 0 | 2884398 | 2570278
MCR018633 | HPR141 | 2023-07-01 | Equipment | 0 | 813011 | 1028575
MCR018634 | HPR141 | 2023-07-01 | Subcontract | 0 | 3460754 | 2526914
MCR018635 | HPR141 | 2023-07-01 | Overhead | 0 | 837464 | 17159133
MCR018636 | HPR142 | 2021-05-01 | Labor | 5039630 | 4520375 | 4735934
MCR018637 | HPR142 | 2021-05-01 | Material | 8738893 | 7838488 | 7470568
MCR018638 | HPR142 | 2021-05-01 | Equipment | 1865289 | 1673100 | 1553913
MCR018639 | HPR142 | 2021-05-01 | Subcontract | 8586166 | 7701497 | 7412323
MCR018640 | HPR142 | 2021-05-01 | Overhead | 2286999 | 2051360 | 15803310
MCR018641 | HPR142 | 2021-06-01 | Labor | 14374623 | 9356761 | 10066631
MCR018642 | HPR142 | 2021-06-01 | Material | 24926095 | 16224948 | 18344860
MCR018643 | HPR142 | 2021-06-01 | Equipment | 5320394 | 3463163 | 4030683
MCR018644 | HPR142 | 2021-06-01 | Subcontract | 24490469 | 15941390 | 15212236
MCR018645 | HPR142 | 2021-06-01 | Overhead | 6523247 | 4246126 | 14758260
MCR018646 | HPR142 | 2021-07-01 | Labor | 22609935 | 19565075 | 20615847
MCR018647 | HPR142 | 2021-07-01 | Material | 39206411 | 33926518 | 41522215
MCR018648 | HPR142 | 2021-07-01 | Equipment | 8368482 | 7241506 | 6759932
MCR018649 | HPR142 | 2021-07-01 | Subcontract | 38521213 | 33333595 | 30012032
MCR018650 | HPR142 | 2021-07-01 | Overhead | 10260457 | 8878690 | 15124175
MCR018651 | HPR142 | 2021-08-01 | Labor | 29768631 | 13472780 | 13090760
MCR018652 | HPR142 | 2021-08-01 | Material | 51619839 | 23362267 | 20993554
MCR018653 | HPR142 | 2021-08-01 | Equipment | 11018088 | 4986600 | 5891698
MCR018654 | HPR142 | 2021-08-01 | Subcontract | 50717696 | 22953972 | 21588843
MCR018655 | HPR142 | 2021-08-01 | Overhead | 13509095 | 6113988 | 14963849
MCR018656 | HPR142 | 2021-09-01 | Labor | 35874826 | 35353521 | 37527354
MCR018657 | HPR142 | 2021-09-01 | Material | 62208193 | 61304233 | 64810160
MCR018658 | HPR142 | 2021-09-01 | Equipment | 13278138 | 13085190 | 12298326
MCR018659 | HPR142 | 2021-09-01 | Subcontract | 61121000 | 60232838 | 52299781
MCR018660 | HPR142 | 2021-09-01 | Overhead | 16280104 | 16043535 | 14844673
MCR018661 | HPR142 | 2021-10-01 | Labor | 40953794 | 28618757 | 30189912
MCR018662 | HPR142 | 2021-10-01 | Material | 71015301 | 49625918 | 56881967
MCR018663 | HPR142 | 2021-10-01 | Equipment | 15157986 | 10592492 | 10701416
MCR018664 | HPR142 | 2021-10-01 | Subcontract | 69774189 | 48758622 | 43566523
MCR018665 | HPR142 | 2021-10-01 | Overhead | 18584956 | 12987279 | 14639342
MCR018666 | HPR142 | 2021-11-01 | Labor | 45032108 | 22095991 | 22009270
MCR018667 | HPR142 | 2021-11-01 | Material | 78087239 | 38315216 | 46724694
MCR018668 | HPR142 | 2021-11-01 | Equipment | 16667469 | 8178259 | 7348006
MCR018669 | HPR142 | 2021-11-01 | Subcontract | 76722533 | 37645593 | 34128912
MCR018670 | HPR142 | 2021-11-01 | Overhead | 20435707 | 10027228 | 13747815
MCR018671 | HPR142 | 2021-12-01 | Labor | 48137794 | 47608450 | 49631495
MCR018672 | HPR142 | 2021-12-01 | Material | 83472606 | 82554705 | 107404414
MCR018673 | HPR142 | 2021-12-01 | Equipment | 17816958 | 17621035 | 19585278
MCR018674 | HPR142 | 2021-12-01 | Subcontract | 82013781 | 81111923 | 78308841
MCR018675 | HPR142 | 2021-12-01 | Overhead | 21845076 | 21604859 | 15547102
MCR018676 | HPR142 | 2022-01-01 | Labor | 50300522 | 48379457 | 51026769
MCR018677 | HPR142 | 2022-01-01 | Material | 87222850 | 83891658 | 107428342
MCR018678 | HPR142 | 2022-01-01 | Equipment | 18617435 | 17906403 | 18979154
MCR018679 | HPR142 | 2022-01-01 | Subcontract | 85698484 | 82425510 | 74250962
MCR018680 | HPR142 | 2022-01-01 | Overhead | 22826529 | 21954744 | 14636876
MCR018681 | HPR142 | 2022-02-01 | Labor | 51551834 | 45382425 | 42476893
MCR018682 | HPR142 | 2022-02-01 | Material | 89392670 | 78694700 | 87324678
MCR018683 | HPR142 | 2022-02-01 | Equipment | 19080576 | 16797129 | 18218858
MCR018684 | HPR142 | 2022-02-01 | Subcontract | 87830382 | 77319378 | 60746156
MCR018685 | HPR142 | 2022-02-01 | Overhead | 23394378 | 20594682 | 14819486
MCR018686 | HPR142 | 2022-03-01 | Labor | 51925432 | 61450464 | 69220867
MCR018687 | HPR142 | 2022-03-01 | Material | 90040502 | 106557238 | 122696819
MCR018688 | HPR142 | 2022-03-01 | Equipment | 19218854 | 22744298 | 23196210
MCR018689 | HPR142 | 2022-03-01 | Subcontract | 88466892 | 104694970 | 89463645
MCR018690 | HPR142 | 2022-03-01 | Overhead | 23563918 | 27886406 | 14349467
MCR018691 | HPR142 | 2022-04-01 | Labor | 51457520 | 34835983 | 37771636
MCR018692 | HPR142 | 2022-04-01 | Material | 89229126 | 60406804 | 69631452
MCR018693 | HPR142 | 2022-04-01 | Equipment | 19045668 | 12893637 | 12629703
MCR018694 | HPR142 | 2022-04-01 | Subcontract | 87669696 | 59351093 | 65260544
MCR018695 | HPR142 | 2022-04-01 | Overhead | 23351578 | 15808675 | 14029510
MCR018696 | HPR142 | 2022-05-01 | Labor | 50187251 | 75106587 | 81364085
MCR018697 | HPR142 | 2022-05-01 | Material | 87026434 | 130237429 | 193942974
MCR018698 | HPR142 | 2022-05-01 | Equipment | 18575511 | 27798758 | 29115477
MCR018699 | HPR142 | 2022-05-01 | Subcontract | 85505501 | 127961310 | 121607724
MCR018700 | HPR142 | 2022-05-01 | Overhead | 22775126 | 34083596 | 13339267
MCR018701 | HPR142 | 2022-06-01 | Labor | 48157296 | 43059377 | 45870544
MCR018702 | HPR142 | 2022-06-01 | Material | 83506423 | 74666455 | 80154601
MCR018703 | HPR142 | 2022-06-01 | Equipment | 17824176 | 15937313 | 17276504
MCR018704 | HPR142 | 2022-06-01 | Subcontract | 82047008 | 73361533 | 57431602
MCR018705 | HPR142 | 2022-06-01 | Overhead | 21853927 | 19540476 | 13539084
MCR018706 | HPR142 | 2022-07-01 | Labor | 45414599 | 49962255 | 59293253
MCR018707 | HPR142 | 2022-07-01 | Material | 78750491 | 86636284 | 106890293
MCR018708 | HPR142 | 2022-07-01 | Equipment | 16809038 | 18492235 | 18634932
MCR018709 | HPR142 | 2022-07-01 | Subcontract | 77374194 | 85122169 | 78038039
MCR018710 | HPR142 | 2022-07-01 | Overhead | 20609282 | 22673022 | 15142402
MCR018711 | HPR142 | 2022-08-01 | Labor | 42011389 | 16785917 | 14872566
MCR018712 | HPR142 | 2022-08-01 | Material | 72849207 | 29107362 | 26937603
MCR018713 | HPR142 | 2022-08-01 | Equipment | 15549428 | 6212872 | 5739279
MCR018714 | HPR142 | 2022-08-01 | Subcontract | 71576044 | 28598662 | 31481964
MCR018715 | HPR142 | 2022-08-01 | Overhead | 19064895 | 7617500 | 16834457
MCR018716 | HPR142 | 2022-09-01 | Labor | 38006603 | 44877397 | 50879960
MCR018717 | HPR142 | 2022-09-01 | Material | 65904768 | 77818964 | 89550996
MCR018718 | HPR142 | 2022-09-01 | Equipment | 14067160 | 16610206 | 16896817
MCR018719 | HPR142 | 2022-09-01 | Subcontract | 64752971 | 76458946 | 77688440
MCR018720 | HPR142 | 2022-09-01 | Overhead | 17247511 | 20365498 | 14983956
MCR018721 | HPR142 | 2022-10-01 | Labor | 33467947 | 32164199 | 32294001
MCR018722 | HPR142 | 2022-10-01 | Material | 58034582 | 55773837 | 77496845
MCR018723 | HPR142 | 2022-10-01 | Equipment | 12387294 | 11904745 | 11694113
MCR018724 | HPR142 | 2022-10-01 | Subcontract | 57020330 | 54799095 | 42592110
MCR018725 | HPR142 | 2022-10-01 | Overhead | 15187856 | 14596211 | 13703330
MCR018726 | HPR142 | 2022-11-01 | Labor | 28475048 | 36856171 | 38555621
MCR018727 | HPR142 | 2022-11-01 | Material | 49376721 | 63909879 | 82300136
MCR018728 | HPR142 | 2022-11-01 | Equipment | 10539302 | 13641357 | 13214266
MCR018729 | HPR142 | 2022-11-01 | Subcontract | 48513780 | 62792946 | 59343187
MCR018730 | HPR142 | 2022-11-01 | Overhead | 12922063 | 16725442 | 14881602
MCR018731 | HPR142 | 2022-12-01 | Labor | 23124576 | 29668095 | 33160354
MCR018732 | HPR142 | 2022-12-01 | Material | 40098817 | 51445506 | 54457181
MCR018733 | HPR142 | 2022-12-01 | Equipment | 8558963 | 10980877 | 10292827
MCR018734 | HPR142 | 2022-12-01 | Subcontract | 39398023 | 50546409 | 42148118
MCR018735 | HPR142 | 2022-12-01 | Overhead | 10494002 | 13463471 | 13205371
MCR018736 | HPR142 | 2023-01-01 | Labor | 17539365 | 25676525 | 27204568
MCR018737 | HPR142 | 2023-01-01 | Material | 30413868 | 44523986 | 48316787
MCR018738 | HPR142 | 2023-01-01 | Equipment | 6491742 | 9503501 | 10681730
MCR018739 | HPR142 | 2023-01-01 | Subcontract | 29882334 | 43745854 | 41848664
MCR018740 | HPR142 | 2023-01-01 | Overhead | 7959417 | 11652085 | 14551273
MCR018741 | HPR142 | 2023-02-01 | Labor | 11886880 | 30718526 | 31164148
MCR018742 | HPR142 | 2023-02-01 | Material | 20612263 | 53266991 | 62128191
MCR018743 | HPR142 | 2023-02-01 | Equipment | 4399621 | 11369667 | 10619863
MCR018744 | HPR142 | 2023-02-01 | Subcontract | 20252029 | 52336060 | 54124563
MCR018745 | HPR142 | 2023-02-01 | Overhead | 5394302 | 13940160 | 14470061
MCR018746 | HPR142 | 2023-03-01 | Labor | 6425618 | 15580392 | 20344321
MCR018747 | HPR142 | 2023-03-01 | Material | 11142245 | 27016940 | 30502416
MCR018748 | HPR142 | 2023-03-01 | Equipment | 2378276 | 5766678 | 5572224
MCR018749 | HPR142 | 2023-03-01 | Subcontract | 10947516 | 26544773 | 23127906
MCR018750 | HPR142 | 2023-03-01 | Overhead | 2915965 | 7070429 | 16323703
MCR018751 | HPR142 | 2023-04-01 | Labor | 1701119 | 14627611 | 17858941
MCR018752 | HPR142 | 2023-04-01 | Material | 2949800 | 25364785 | 28777724
MCR018753 | HPR142 | 2023-04-01 | Equipment | 629625 | 5414031 | 5954501
MCR018754 | HPR142 | 2023-04-01 | Subcontract | 2898247 | 24921493 | 19880697
MCR018755 | HPR142 | 2023-04-01 | Overhead | 771973 | 6638054 | 14771211
MCR018756 | HPR142 | 2023-05-01 | Labor | 0 | 6303807 | 4232742
MCR018757 | HPR142 | 2023-05-01 | Material | 0 | 10931020 | 12269673
MCR018758 | HPR142 | 2023-05-01 | Equipment | 0 | 2333191 | 2007621
MCR018759 | HPR142 | 2023-05-01 | Subcontract | 0 | 10739982 | 10391130
MCR018760 | HPR142 | 2023-05-01 | Overhead | 0 | 2860687 | 14500377
MCR018761 | HPR142 | 2023-06-01 | Labor | 0 | 1397443 | 1595064
MCR018762 | HPR142 | 2023-06-01 | Material | 0 | 2423215 | 2084095
MCR018763 | HPR142 | 2023-06-01 | Equipment | 0 | 517227 | 640369
MCR018764 | HPR142 | 2023-06-01 | Subcontract | 0 | 2380865 | 1960162
MCR018765 | HPR142 | 2023-06-01 | Overhead | 0 | 634164 | 14976198
MCR018766 | HPR143 | 2018-04-01 | Labor | 3173418 | 3094384 | 3183178
MCR018767 | HPR143 | 2018-04-01 | Material | 7111111 | 6934008 | 6287744
MCR018768 | HPR143 | 2018-04-01 | Equipment | 1442562 | 1406634 | 1498987
MCR018769 | HPR143 | 2018-04-01 | Subcontract | 10994685 | 10720862 | 9965223
MCR018770 | HPR143 | 2018-04-01 | Overhead | 2245501 | 2189576 | 13147501
MCR018771 | HPR143 | 2018-05-01 | Labor | 9007952 | 8586922 | 9385046
MCR018772 | HPR143 | 2018-05-01 | Material | 20185346 | 19241887 | 19389831
MCR018773 | HPR143 | 2018-05-01 | Equipment | 4094804 | 3903413 | 4344886
MCR018774 | HPR143 | 2018-05-01 | Subcontract | 31209121 | 29750412 | 30198776
MCR018775 | HPR143 | 2018-05-01 | Overhead | 6373998 | 6076079 | 13317915
MCR018776 | HPR143 | 2018-06-01 | Labor | 14086663 | 14100864 | 15776846
MCR018777 | HPR143 | 2018-06-01 | Material | 31565905 | 31597728 | 32097132
MCR018778 | HPR143 | 2018-06-01 | Equipment | 6403466 | 6409922 | 6211083
MCR018779 | HPR143 | 2018-06-01 | Subcontract | 48804915 | 48854119 | 48977737
MCR018780 | HPR143 | 2018-06-01 | Overhead | 9967677 | 9977726 | 13316749
MCR018781 | HPR143 | 2018-07-01 | Labor | 18427032 | 10536167 | 10449766
MCR018782 | HPR143 | 2018-07-01 | Material | 41291962 | 23609825 | 25625381
MCR018783 | HPR143 | 2018-07-01 | Equipment | 8376497 | 4789494 | 4850256
MCR018784 | HPR143 | 2018-07-01 | Subcontract | 63842641 | 36503801 | 39317810
MCR018785 | HPR143 | 2018-07-01 | Overhead | 13038909 | 7455358 | 13744649
MCR018786 | HPR143 | 2018-08-01 | Labor | 22047425 | 10470257 | 11866506
MCR018787 | HPR143 | 2018-08-01 | Material | 49404670 | 23462131 | 23792986
MCR018788 | HPR143 | 2018-08-01 | Equipment | 10022242 | 4759533 | 5091030
MCR018789 | HPR143 | 2018-08-01 | Subcontract | 76385922 | 36275448 | 38580037
MCR018790 | HPR143 | 2018-08-01 | Overhead | 15600687 | 7408720 | 13440312
MCR018791 | HPR143 | 2018-09-01 | Labor | 24967192 | 15734109 | 14696035
MCR018792 | HPR143 | 2018-09-01 | Material | 55947389 | 35257563 | 34400389
MCR018793 | HPR143 | 2018-09-01 | Equipment | 11349500 | 7152357 | 7787759
MCR018794 | HPR143 | 2018-09-01 | Subcontract | 86501800 | 54512690 | 51317085
MCR018795 | HPR143 | 2018-09-01 | Overhead | 17666705 | 11133405 | 14676644
MCR018796 | HPR143 | 2018-10-01 | Labor | 27206797 | 21819460 | 23653755
MCR018797 | HPR143 | 2018-10-01 | Material | 60965977 | 48893838 | 52153758
MCR018798 | HPR143 | 2018-10-01 | Equipment | 12367572 | 9918615 | 9035444
MCR018799 | HPR143 | 2018-10-01 | Subcontract | 94261178 | 75596110 | 81195257
MCR018800 | HPR143 | 2018-10-01 | Overhead | 19251442 | 15439380 | 13493652
MCR018801 | HPR143 | 2018-11-01 | Labor | 28787974 | 21548323 | 22978176
MCR018802 | HPR143 | 2018-11-01 | Material | 64509136 | 48286264 | 41765052
MCR018803 | HPR143 | 2018-11-01 | Equipment | 13086338 | 9795362 | 10640850
MCR018804 | HPR143 | 2018-11-01 | Subcontract | 99739353 | 74656724 | 71948245
MCR018805 | HPR143 | 2018-11-01 | Overhead | 20370278 | 15247524 | 13787198
MCR018806 | HPR143 | 2018-12-01 | Labor | 29733913 | 34582748 | 34478638
MCR018807 | HPR143 | 2018-12-01 | Material | 66628830 | 77494275 | 83930275
MCR018808 | HPR143 | 2018-12-01 | Equipment | 13516339 | 15720506 | 15553279
MCR018809 | HPR143 | 2018-12-01 | Subcontract | 103016671 | 119816035 | 135344317
MCR018810 | HPR143 | 2018-12-01 | Overhead | 21039621 | 24470641 | 11996285
MCR018811 | HPR143 | 2019-01-01 | Labor | 30069495 | 22451255 | 23559337
MCR018812 | HPR143 | 2019-01-01 | Material | 67380815 | 50309586 | 52175738
MCR018813 | HPR143 | 2019-01-01 | Equipment | 13668887 | 10205814 | 11155295
MCR018814 | HPR143 | 2019-01-01 | Subcontract | 104179335 | 77785038 | 74864734
MCR018815 | HPR143 | 2019-01-01 | Overhead | 21277078 | 15886436 | 12490886
MCR018816 | HPR143 | 2019-02-01 | Labor | 29821589 | 30822502 | 33612326
MCR018817 | HPR143 | 2019-02-01 | Material | 66825298 | 69068180 | 78227732
MCR018818 | HPR143 | 2019-02-01 | Equipment | 13556195 | 14011186 | 16034145
MCR018819 | HPR143 | 2019-02-01 | Subcontract | 103320435 | 106788218 | 109227510
MCR018820 | HPR143 | 2019-02-01 | Overhead | 21101661 | 21809904 | 13599102
MCR018821 | HPR143 | 2019-03-01 | Labor | 29019430 | 32541318 | 32748532
MCR018822 | HPR143 | 2019-03-01 | Material | 65027791 | 72919765 | 77079337
MCR018823 | HPR143 | 2019-03-01 | Equipment | 13191552 | 14792520 | 12183873
MCR018824 | HPR143 | 2019-03-01 | Subcontract | 100541261 | 112743258 | 121261766
MCR018825 | HPR143 | 2019-03-01 | Overhead | 20534056 | 23026132 | 14696912
MCR018826 | HPR143 | 2019-04-01 | Labor | 27695122 | 21468552 | 23235838
MCR018827 | HPR143 | 2019-04-01 | Material | 62060234 | 48107510 | 42858604
MCR018828 | HPR143 | 2019-04-01 | Equipment | 12589553 | 9759100 | 10814000
MCR018829 | HPR143 | 2019-04-01 | Subcontract | 95953039 | 74380348 | 67723362
MCR018830 | HPR143 | 2019-04-01 | Overhead | 19596980 | 15191079 | 13754601
MCR018831 | HPR143 | 2019-05-01 | Labor | 25884313 | 21998541 | 24656839
MCR018832 | HPR143 | 2019-05-01 | Material | 58002508 | 49295128 | 52674712
MCR018833 | HPR143 | 2019-05-01 | Equipment | 11766402 | 10000021 | 9722518
MCR018834 | HPR143 | 2019-05-01 | Subcontract | 89679276 | 76216557 | 70126668
MCR018835 | HPR143 | 2019-05-01 | Overhead | 18315657 | 15566097 | 13311093
MCR018836 | HPR143 | 2019-06-01 | Labor | 23627138 | 14946583 | 14559626
MCR018837 | HPR143 | 2019-06-01 | Material | 52944547 | 33492845 | 34146577
MCR018838 | HPR143 | 2019-06-01 | Equipment | 10740342 | 6794366 | 7464978
MCR018839 | HPR143 | 2019-06-01 | Subcontract | 81859023 | 51784211 | 58056398
MCR018840 | HPR143 | 2019-06-01 | Overhead | 16718487 | 10576154 | 12375406
MCR018841 | HPR143 | 2019-07-01 | Labor | 20969583 | 17137454 | 20011040
MCR018842 | HPR143 | 2019-07-01 | Material | 46989402 | 38402229 | 39247461
MCR018843 | HPR143 | 2019-07-01 | Equipment | 9532281 | 7790285 | 7585199
MCR018844 | HPR143 | 2019-07-01 | Subcontract | 72651610 | 59374744 | 67602120
MCR018845 | HPR143 | 2019-07-01 | Overhead | 14838010 | 12126408 | 13620699
MCR018846 | HPR143 | 2019-08-01 | Labor | 17965573 | 20944223 | 15790345
MCR018847 | HPR143 | 2019-08-01 | Material | 40257908 | 46932575 | 48542164
MCR018848 | HPR143 | 2019-08-01 | Equipment | 8166728 | 9520753 | 9864246
MCR018849 | HPR143 | 2019-08-01 | Subcontract | 62243861 | 72563749 | 63473829
MCR018850 | HPR143 | 2019-08-01 | Overhead | 12712382 | 14820065 | 13625287
MCR018851 | HPR143 | 2019-09-01 | Labor | 14680349 | 19170449 | 23356061
MCR018852 | HPR143 | 2019-09-01 | Material | 32896259 | 42957837 | 42895092
MCR018853 | HPR143 | 2019-09-01 | Equipment | 6673342 | 8714436 | 9441847
MCR018854 | HPR143 | 2019-09-01 | Subcontract | 50861813 | 66418297 | 68076272
MCR018855 | HPR143 | 2019-09-01 | Overhead | 10387768 | 13564948 | 14099317
MCR018856 | HPR143 | 2019-10-01 | Labor | 11196475 | 19391865 | 21023138
MCR018857 | HPR143 | 2019-10-01 | Material | 25089468 | 43453995 | 45296348
MCR018858 | HPR143 | 2019-10-01 | Equipment | 5089655 | 8815087 | 8550037
MCR018859 | HPR143 | 2019-10-01 | Subcontract | 38791518 | 67185420 | 71147301
MCR018860 | HPR143 | 2019-10-01 | Overhead | 7922590 | 13721622 | 14568058
MCR018861 | HPR143 | 2019-11-01 | Labor | 7625966 | 12722278 | 13043392
MCR018862 | HPR143 | 2019-11-01 | Material | 17088541 | 28508542 | 31245716
MCR018863 | HPR143 | 2019-11-01 | Equipment | 3466585 | 5783249 | 5883385
MCR018864 | HPR143 | 2019-11-01 | Subcontract | 26421064 | 44077842 | 44305391
MCR018865 | HPR143 | 2019-11-01 | Overhead | 5396109 | 9002243 | 13409687
MCR018866 | HPR143 | 2019-12-01 | Labor | 4140679 | 17759450 | 19158759
MCR018867 | HPR143 | 2019-12-01 | Material | 9278584 | 39796018 | 39869110
MCR018868 | HPR143 | 2019-12-01 | Equipment | 1882256 | 8073029 | 8676840
MCR018869 | HPR143 | 2019-12-01 | Subcontract | 14345875 | 61529721 | 66882786
MCR018870 | HPR143 | 2019-12-01 | Overhead | 2929931 | 12566529 | 13364392
MCR018871 | HPR143 | 2020-01-01 | Labor | 1100232 | 5962233 | 5294112
MCR018872 | HPR143 | 2020-01-01 | Material | 2465439 | 13360387 | 12115214
MCR018873 | HPR143 | 2020-01-01 | Equipment | 500140 | 2710291 | 2464948
MCR018874 | HPR143 | 2020-01-01 | Subcontract | 3811884 | 20656863 | 15571120
MCR018875 | HPR143 | 2020-01-01 | Overhead | 778521 | 4218857 | 12873752
MCR018876 | HPR143 | 2020-02-01 | Labor | 0 | 13188079 | 13516304
MCR018877 | HPR143 | 2020-02-01 | Material | 0 | 29552326 | 29951236
MCR018878 | HPR143 | 2020-02-01 | Equipment | 0 | 5994991 | 5836741
MCR018879 | HPR143 | 2020-02-01 | Subcontract | 0 | 45691666 | 46912033
MCR018880 | HPR143 | 2020-02-01 | Overhead | 0 | 9331842 | 13280090
MCR018881 | HPR143 | 2020-03-01 | Labor | 0 | 5374115 | 6346256
MCR018882 | HPR143 | 2020-03-01 | Material | 0 | 12042511 | 12173187
MCR018883 | HPR143 | 2020-03-01 | Equipment | 0 | 2442946 | 2630294
MCR018884 | HPR143 | 2020-03-01 | Subcontract | 0 | 18619258 | 16229671
MCR018885 | HPR143 | 2020-03-01 | Overhead | 0 | 3802706 | 13403394
MCR018886 | HPR143 | 2020-04-01 | Labor | 0 | 3800941 | 4271013
MCR018887 | HPR143 | 2020-04-01 | Material | 0 | 8517286 | 8704812
MCR018888 | HPR143 | 2020-04-01 | Equipment | 0 | 1727819 | 1925978
MCR018889 | HPR143 | 2020-04-01 | Subcontract | 0 | 13168811 | 15914523
MCR018890 | HPR143 | 2020-04-01 | Overhead | 0 | 2689534 | 12714155
MCR018891 | HPR143 | 2020-05-01 | Labor | 0 | 1081239 | 1041325
MCR018892 | HPR143 | 2020-05-01 | Material | 0 | 2422880 | 2784587
MCR018893 | HPR143 | 2020-05-01 | Equipment | 0 | 491506 | 563771
MCR018894 | HPR143 | 2020-05-01 | Subcontract | 0 | 3746081 | 3813122
MCR018895 | HPR143 | 2020-05-01 | Overhead | 0 | 765081 | 14244348
MCR018896 | HPR144 | 2018-05-01 | Labor | 2145834 | 1575422 | 1545549
MCR018897 | HPR144 | 2018-05-01 | Material | 4827743 | 3544419 | 3588237
MCR018898 | HPR144 | 2018-05-01 | Equipment | 1061758 | 779518 | 688025
MCR018899 | HPR144 | 2018-05-01 | Subcontract | 8007309 | 5878783 | 6124600
MCR018900 | HPR144 | 2018-05-01 | Overhead | 1285679 | 943916 | 8568906
MCR018901 | HPR144 | 2018-06-01 | Labor | 6106498 | 4085723 | 4239684
MCR018902 | HPR144 | 2018-06-01 | Material | 13738534 | 9192149 | 9031790
MCR018903 | HPR144 | 2018-06-01 | Equipment | 3021494 | 2021615 | 2303720
MCR018904 | HPR144 | 2018-06-01 | Subcontract | 22786773 | 15246125 | 14580283
MCR018905 | HPR144 | 2018-06-01 | Overhead | 3658718 | 2447967 | 7781775
MCR018906 | HPR144 | 2018-07-01 | Labor | 9578442 | 4854001 | 5102295
MCR018907 | HPR144 | 2018-07-01 | Material | 21549788 | 10920639 | 10627780
MCR018908 | HPR144 | 2018-07-01 | Equipment | 4739411 | 2401759 | 2602431
MCR018909 | HPR144 | 2018-07-01 | Subcontract | 35742541 | 18113003 | 17234348
MCR018910 | HPR144 | 2018-07-01 | Overhead | 5738938 | 2908282 | 8340131
MCR018911 | HPR144 | 2018-08-01 | Labor | 12572415 | 6663908 | 7045739
MCR018912 | HPR144 | 2018-08-01 | Material | 28285695 | 14992606 | 14907535
MCR018913 | HPR144 | 2018-08-01 | Equipment | 6220828 | 3297300 | 4026741
MCR018914 | HPR144 | 2018-08-01 | Subcontract | 46914737 | 24866780 | 27486919
MCR018915 | HPR144 | 2018-08-01 | Overhead | 7532782 | 3992691 | 7775558
MCR018916 | HPR144 | 2018-09-01 | Labor | 15099685 | 11700817 | 12877147
MCR018917 | HPR144 | 2018-09-01 | Material | 33971602 | 26324755 | 25362521
MCR018918 | HPR144 | 2018-09-01 | Equipment | 7471321 | 5789562 | 5483829
MCR018919 | HPR144 | 2018-09-01 | Subcontract | 56345398 | 43662316 | 42288954
MCR018920 | HPR144 | 2018-09-01 | Overhead | 9046999 | 7010563 | 7925869
MCR018921 | HPR144 | 2018-10-01 | Labor | 17172089 | 12195608 | 11433960
MCR018922 | HPR144 | 2018-10-01 | Material | 38634142 | 27437946 | 31956911
MCR018923 | HPR144 | 2018-10-01 | Equipment | 8496746 | 6034384 | 6615545
MCR018924 | HPR144 | 2018-10-01 | Subcontract | 64078700 | 45508657 | 44830437
MCR018925 | HPR144 | 2018-10-01 | Overhead | 10288683 | 7307017 | 7116621
MCR018926 | HPR144 | 2018-11-01 | Labor | 18802107 | 8935630 | 9273526
MCR018927 | HPR144 | 2018-11-01 | Material | 42301393 | 20103576 | 19535461
MCR018928 | HPR144 | 2018-11-01 | Equipment | 9303279 | 4421348 | 4372292
MCR018929 | HPR144 | 2018-11-01 | Subcontract | 70161213 | 33343850 | 29175407
MCR018930 | HPR144 | 2018-11-01 | Overhead | 11265311 | 5353796 | 7444741
MCR018931 | HPR144 | 2018-12-01 | Labor | 20002946 | 18884062 | 19074961
MCR018932 | HPR144 | 2018-12-01 | Material | 45003066 | 42485777 | 46408000
MCR018933 | HPR144 | 2018-12-01 | Equipment | 9897453 | 9343830 | 8719922
MCR018934 | HPR144 | 2018-12-01 | Subcontract | 74642216 | 70467033 | 65100892
MCR018935 | HPR144 | 2018-12-01 | Overhead | 11984796 | 11314415 | 8062892
MCR018936 | HPR144 | 2019-01-01 | Labor | 20788637 | 12114579 | 12855388
MCR018937 | HPR144 | 2019-01-01 | Material | 46770731 | 27255645 | 26646292
MCR018938 | HPR144 | 2019-01-01 | Equipment | 10286213 | 5994291 | 7342499
MCR018939 | HPR144 | 2019-01-01 | Subcontract | 77574071 | 45206292 | 48859403
MCR018940 | HPR144 | 2019-01-01 | Overhead | 12455544 | 7258469 | 8147067
MCR018941 | HPR144 | 2019-02-01 | Labor | 21174163 | 12036672 | 13768797
MCR018942 | HPR144 | 2019-02-01 | Material | 47638096 | 27080368 | 27903109
MCR018943 | HPR144 | 2019-02-01 | Equipment | 10476971 | 5955743 | 5638558
MCR018944 | HPR144 | 2019-02-01 | Subcontract | 79012684 | 44915577 | 43645645
MCR018945 | HPR144 | 2019-02-01 | Overhead | 12686532 | 7211790 | 7341989
MCR018946 | HPR144 | 2019-03-01 | Labor | 21175609 | 14105617 | 14351936
MCR018947 | HPR144 | 2019-03-01 | Material | 47641349 | 31735126 | 30869786
MCR018948 | HPR144 | 2019-03-01 | Equipment | 10477687 | 6979456 | 8062131
MCR018949 | HPR144 | 2019-03-01 | Subcontract | 79018080 | 52635973 | 54275632
MCR018950 | HPR144 | 2019-03-01 | Overhead | 12687399 | 8451402 | 8020967
MCR018951 | HPR144 | 2019-04-01 | Labor | 20810358 | 17905481 | 20033225
MCR018952 | HPR144 | 2019-04-01 | Material | 46819598 | 40284144 | 41743429
MCR018953 | HPR144 | 2019-04-01 | Equipment | 10296960 | 8859628 | 9562240
MCR018954 | HPR144 | 2019-04-01 | Subcontract | 77655122 | 66815398 | 61858061
MCR018955 | HPR144 | 2019-04-01 | Overhead | 12468558 | 10728097 | 7781169
MCR018956 | HPR144 | 2019-05-01 | Labor | 20097339 | 16932323 | 19833669
MCR018957 | HPR144 | 2019-05-01 | Material | 45215434 | 38094712 | 37121299
MCR018958 | HPR144 | 2019-05-01 | Equipment | 9944159 | 8378110 | 8854584
MCR018959 | HPR144 | 2019-05-01 | Subcontract | 74994450 | 63184000 | 67865577
MCR018960 | HPR144 | 2019-05-01 | Overhead | 12041352 | 10145028 | 7820703
MCR018961 | HPR144 | 2019-06-01 | Labor | 19057359 | 19026844 | 19495769
MCR018962 | HPR144 | 2019-06-01 | Material | 42875665 | 42807010 | 41167756
MCR018963 | HPR144 | 2019-06-01 | Equipment | 9429577 | 9414478 | 9529502
MCR018964 | HPR144 | 2019-06-01 | Subcontract | 71113702 | 70999832 | 64063307
MCR018965 | HPR144 | 2019-06-01 | Overhead | 11418246 | 11399963 | 7588775
MCR018966 | HPR144 | 2019-07-01 | Labor | 17713545 | 7794296 | 9968677
MCR018967 | HPR144 | 2019-07-01 | Material | 39852322 | 17535778 | 21035774
MCR018968 | HPR144 | 2019-07-01 | Equipment | 8764658 | 3856616 | 4096204
MCR018969 | HPR144 | 2019-07-01 | Subcontract | 66099178 | 29084892 | 38459851
MCR018970 | HPR144 | 2019-07-01 | Overhead | 10613098 | 4669964 | 7798713
MCR018971 | HPR144 | 2019-08-01 | Labor | 16091964 | 14754905 | 17202467
MCR018972 | HPR144 | 2019-08-01 | Material | 36204053 | 33195909 | 31393490
MCR018973 | HPR144 | 2019-08-01 | Equipment | 7962300 | 7300724 | 8002567
MCR018974 | HPR144 | 2019-08-01 | Subcontract | 60048148 | 55058831 | 52670951
MCR018975 | HPR144 | 2019-08-01 | Overhead | 9641525 | 8840424 | 8501841
MCR018976 | HPR144 | 2019-09-01 | Labor | 14222524 | 15266242 | 17345382
MCR018977 | HPR144 | 2019-09-01 | Material | 31998146 | 34346326 | 41877812
MCR018978 | HPR144 | 2019-09-01 | Equipment | 7037302 | 7553733 | 8161299
MCR018979 | HPR144 | 2019-09-01 | Subcontract | 53072218 | 56966917 | 53354785
MCR018980 | HPR144 | 2019-09-01 | Overhead | 8521447 | 9146793 | 8260684
MCR018981 | HPR144 | 2019-10-01 | Labor | 12140348 | 10028663 | 11434114
MCR018982 | HPR144 | 2019-10-01 | Material | 27313621 | 22562707 | 20122751
MCR018983 | HPR144 | 2019-10-01 | Equipment | 6007042 | 4962181 | 4819763
MCR018984 | HPR144 | 2019-10-01 | Subcontract | 45302451 | 37422571 | 40752579
MCR018985 | HPR144 | 2019-10-01 | Overhead | 7273908 | 6008689 | 8924346
MCR018986 | HPR144 | 2019-11-01 | Labor | 9888005 | 20577657 | 23632898
MCR018987 | HPR144 | 2019-11-01 | Material | 22246251 | 46296063 | 49547096
MCR018988 | HPR144 | 2019-11-01 | Equipment | 4892583 | 10181820 | 10410097
MCR018989 | HPR144 | 2019-11-01 | Subcontract | 36897697 | 76786785 | 67167667
MCR018990 | HPR144 | 2019-11-01 | Overhead | 5924414 | 12329135 | 8034374
MCR018991 | HPR144 | 2019-12-01 | Labor | 7519480 | 14324158 | 16753311
MCR018992 | HPR144 | 2019-12-01 | Material | 16917490 | 32226804 | 29916667
MCR018993 | HPR144 | 2019-12-01 | Equipment | 3720637 | 7087590 | 7328784
MCR018994 | HPR144 | 2019-12-01 | Subcontract | 28059398 | 53451471 | 56138397
MCR018995 | HPR144 | 2019-12-01 | Overhead | 4505308 | 8582341 | 7993234
MCR018996 | HPR144 | 2020-01-01 | Labor | 5108195 | 17245354 | 18766572
MCR018997 | HPR144 | 2020-01-01 | Material | 11492528 | 38798975 | 38708500
MCR018998 | HPR144 | 2020-01-01 | Equipment | 2527534 | 8532997 | 9305560
MCR018999 | HPR144 | 2020-01-01 | Subcontract | 19061541 | 64352093 | 84522736
MCR019000 | HPR144 | 2020-01-01 | Overhead | 3060583 | 10332580 | 7575638
MCR019001 | HPR144 | 2020-02-01 | Labor | 2767153 | 10025976 | 11586199
MCR019002 | HPR144 | 2020-02-01 | Material | 6225602 | 22556661 | 23039005
MCR019003 | HPR144 | 2020-02-01 | Equipment | 1369187 | 4960851 | 5716852
MCR019004 | HPR144 | 2020-02-01 | Subcontract | 10325802 | 37412543 | 52311827
MCR019005 | HPR144 | 2020-02-01 | Overhead | 1657944 | 6007079 | 8450898
MCR019006 | HPR144 | 2020-03-01 | Labor | 733860 | 12700033 | 14450868
MCR019007 | HPR144 | 2020-03-01 | Material | 1651054 | 28572812 | 26962279
MCR019008 | HPR144 | 2020-03-01 | Equipment | 363114 | 6283973 | 6315818
MCR019009 | HPR144 | 2020-03-01 | Subcontract | 2738442 | 47390949 | 63247355
MCR019010 | HPR144 | 2020-03-01 | Overhead | 439693 | 7609244 | 8666725
MCR019011 | HPR144 | 2020-04-01 | Labor | 0 | 10017620 | 10471004
MCR019012 | HPR144 | 2020-04-01 | Material | 0 | 22537861 | 22721380
MCR019013 | HPR144 | 2020-04-01 | Equipment | 0 | 4956716 | 4898872
MCR019014 | HPR144 | 2020-04-01 | Subcontract | 0 | 37381362 | 46663414
MCR019015 | HPR144 | 2020-04-01 | Overhead | 0 | 6002072 | 8266828
MCR019016 | HPR144 | 2020-05-01 | Labor | 0 | 6235750 | 7592130
MCR019017 | HPR144 | 2020-05-01 | Material | 0 | 14029327 | 14122378
MCR019018 | HPR144 | 2020-05-01 | Equipment | 0 | 3085448 | 3364705
MCR019019 | HPR144 | 2020-05-01 | Subcontract | 0 | 23269082 | 44555339
MCR019020 | HPR144 | 2020-05-01 | Overhead | 0 | 3736159 | 7877596
MCR019021 | HPR144 | 2020-06-01 | Labor | 0 | 6147680 | 8005093
MCR019022 | HPR144 | 2020-06-01 | Material | 0 | 13831184 | 15576280
MCR019023 | HPR144 | 2020-06-01 | Equipment | 0 | 3041871 | 3315987
MCR019024 | HPR144 | 2020-06-01 | Subcontract | 0 | 22940443 | 52754023
MCR019025 | HPR144 | 2020-06-01 | Overhead | 0 | 3683392 | 7700468
MCR019026 | HPR144 | 2020-07-01 | Labor | 0 | 1488468 | 1242439
MCR019027 | HPR144 | 2020-07-01 | Material | 0 | 3348788 | 3088349
MCR019028 | HPR144 | 2020-07-01 | Equipment | 0 | 736494 | 932357
MCR019029 | HPR144 | 2020-07-01 | Subcontract | 0 | 5554309 | 39089996
MCR019030 | HPR144 | 2020-07-01 | Overhead | 0 | 891818 | 7342947
MCR019031 | HPR144 | 2020-08-01 | Labor | 0 | 2410149 | 2726998
MCR019032 | HPR144 | 2020-08-01 | Material | 0 | 5422405 | 5808139
MCR019033 | HPR144 | 2020-08-01 | Equipment | 0 | 1192541 | 1375680
MCR019034 | HPR144 | 2020-08-01 | Subcontract | 0 | 8993617 | 22419265
MCR019035 | HPR144 | 2020-08-01 | Overhead | 0 | 1444044 | 7671050
MCR019036 | HPR144 | 2020-09-01 | Labor | 0 | 734917 | 997063
MCR019037 | HPR144 | 2020-09-01 | Material | 0 | 1653433 | 1554464
MCR019038 | HPR144 | 2020-09-01 | Equipment | 0 | 363637 | 369116
MCR019039 | HPR144 | 2020-09-01 | Subcontract | 0 | 2742388 | 28877337
MCR019040 | HPR144 | 2020-09-01 | Overhead | 0 | 440327 | 7642105
MCR019041 | HPR145 | 2018-05-01 | Labor | 3351098 | 1288897 | 1253023
MCR019042 | HPR145 | 2018-05-01 | Material | 9967000 | 3833502 | 3788223
MCR019043 | HPR145 | 2018-05-01 | Equipment | 2210425 | 850172 | 806921
MCR019044 | HPR145 | 2018-05-01 | Subcontract | 11560806 | 4446510 | 4738533
MCR019045 | HPR145 | 2018-05-01 | Overhead | 2824151 | 1086223 | 16740760
MCR019046 | HPR145 | 2018-06-01 | Labor | 9536375 | 7499824 | 7900680
MCR019047 | HPR145 | 2018-06-01 | Material | 28363558 | 22306347 | 23169053
MCR019048 | HPR145 | 2018-06-01 | Equipment | 6290309 | 4946975 | 4827418
MCR019049 | HPR145 | 2018-06-01 | Subcontract | 32899126 | 25873316 | 27879100
MCR019050 | HPR145 | 2018-06-01 | Overhead | 8036819 | 6320507 | 18028786
MCR019051 | HPR145 | 2018-07-01 | Labor | 14958427 | 3814723 | 4150774
MCR019052 | HPR145 | 2018-07-01 | Material | 44490093 | 11345937 | 10601479
MCR019053 | HPR145 | 2018-07-01 | Equipment | 9866761 | 2516238 | 2588499
MCR019054 | HPR145 | 2018-07-01 | Subcontract | 51604428 | 13160247 | 12400169
MCR019055 | HPR145 | 2018-07-01 | Overhead | 12606276 | 3214873 | 18534566
MCR019056 | HPR145 | 2018-08-01 | Labor | 19634045 | 8561894 | 10051549
MCR019057 | HPR145 | 2018-08-01 | Material | 58396548 | 25465210 | 28777088
MCR019058 | HPR145 | 2018-08-01 | Equipment | 12950855 | 5647530 | 5512235
MCR019059 | HPR145 | 2018-08-01 | Subcontract | 67734640 | 29537308 | 29993315
MCR019060 | HPR145 | 2018-08-01 | Overhead | 16546672 | 7215572 | 16731566
MCR019061 | HPR145 | 2018-09-01 | Labor | 23580823 | 14351181 | 13623252
MCR019062 | HPR145 | 2018-09-01 | Material | 70135249 | 42683993 | 43918692
MCR019063 | HPR145 | 2018-09-01 | Equipment | 15554198 | 9466214 | 9399940
MCR019064 | HPR145 | 2018-09-01 | Subcontract | 81350456 | 49509517 | 55307126
MCR019065 | HPR145 | 2018-09-01 | Overhead | 19872835 | 12094517 | 19132094
MCR019066 | HPR145 | 2018-10-01 | Labor | 26817247 | 11295957 | 12156726
MCR019067 | HPR145 | 2018-10-01 | Material | 79761182 | 33596993 | 28726851
MCR019068 | HPR145 | 2018-10-01 | Equipment | 17688983 | 7450951 | 8833289
MCR019069 | HPR145 | 2018-10-01 | Subcontract | 92515656 | 38969431 | 41780925
MCR019070 | HPR145 | 2018-10-01 | Overhead | 22600345 | 9519714 | 16669430
MCR019071 | HPR145 | 2018-11-01 | Labor | 29362808 | 18133775 | 17534469
MCR019072 | HPR145 | 2018-11-01 | Material | 87332317 | 53934372 | 55365262
MCR019073 | HPR145 | 2018-11-01 | Equipment | 19368066 | 11961259 | 12410422
MCR019074 | HPR145 | 2018-11-01 | Subcontract | 101297477 | 62558924 | 61508808
MCR019075 | HPR145 | 2018-11-01 | Overhead | 24745627 | 15282314 | 18423245
MCR019076 | HPR145 | 2018-12-01 | Labor | 31238130 | 22853732 | 25350394
MCR019077 | HPR145 | 2018-12-01 | Material | 92909991 | 67972700 | 72881214
MCR019078 | HPR145 | 2018-12-01 | Equipment | 20605051 | 15074600 | 15179000
MCR019079 | HPR145 | 2018-12-01 | Subcontract | 107767068 | 78842098 | 81362676
MCR019080 | HPR145 | 2018-12-01 | Overhead | 26326062 | 19260077 | 18312224
MCR019081 | HPR145 | 2019-01-01 | Labor | 32465125 | 29687885 | 34242495
MCR019082 | HPR145 | 2019-01-01 | Material | 96559382 | 88299177 | 77785541
MCR019083 | HPR145 | 2019-01-01 | Equipment | 21414392 | 19582491 | 19813614
MCR019084 | HPR145 | 2019-01-01 | Subcontract | 112000026 | 102418946 | 108989008
MCR019085 | HPR145 | 2019-01-01 | Overhead | 27360118 | 25019587 | 17439838
MCR019086 | HPR145 | 2019-02-01 | Labor | 33067192 | 13367392 | 40630542
MCR019087 | HPR145 | 2019-02-01 | Material | 98350078 | 39757959 | 83241682
MCR019088 | HPR145 | 2019-02-01 | Equipment | 21811523 | 8817295 | 9628808
MCR019089 | HPR145 | 2019-02-01 | Subcontract | 114077070 | 46115585 | 41194082
MCR019090 | HPR145 | 2019-02-01 | Overhead | 27867512 | 11265425 | 18728624
MCR019091 | HPR145 | 2019-03-01 | Labor | 33069450 | 21925348 | 44824704
MCR019092 | HPR145 | 2019-03-01 | Material | 98356794 | 65211454 | 105343555
MCR019093 | HPR145 | 2019-03-01 | Equipment | 21813012 | 14462227 | 17215197
MCR019094 | HPR145 | 2019-03-01 | Subcontract | 114084859 | 75639306 | 92214398
MCR019095 | HPR145 | 2019-03-01 | Overhead | 27869415 | 18477677 | 16682989
MCR019096 | HPR145 | 2019-04-01 | Labor | 32499046 | 25266413 | 29827695
MCR019097 | HPR145 | 2019-04-01 | Material | 96660269 | 75148615 | 59751596
MCR019098 | HPR145 | 2019-04-01 | Equipment | 21436766 | 16666034 | 13854067
MCR019099 | HPR145 | 2019-04-01 | Subcontract | 112117046 | 87165501 | 79361146
MCR019100 | HPR145 | 2019-04-01 | Overhead | 27388704 | 21293373 | 17096673
MCR019101 | HPR145 | 2019-05-01 | Labor | 31385541 | 23094451 | 18673837
MCR019102 | HPR145 | 2019-05-01 | Material | 93348430 | 68688658 | 88017001
MCR019103 | HPR145 | 2019-05-01 | Equipment | 20702285 | 15233381 | 16353286
MCR019104 | HPR145 | 2019-05-01 | Subcontract | 108275616 | 79672543 | 86109109
MCR019105 | HPR145 | 2019-05-01 | Overhead | 26450294 | 19462943 | 17001700
MCR019106 | HPR145 | 2019-06-01 | Labor | 29761430 | 39053723 | 46614997
MCR019107 | HPR145 | 2019-06-01 | Material | 88517916 | 116155514 | 98095436
MCR019108 | HPR145 | 2019-06-01 | Equipment | 19631002 | 25760311 | 25923897
MCR019109 | HPR145 | 2019-06-01 | Subcontract | 102672664 | 134729742 | 136986739
MCR019110 | HPR145 | 2019-06-01 | Overhead | 25081567 | 32912685 | 18208245
MCR019111 | HPR145 | 2019-07-01 | Labor | 27662827 | 21585748 | 21623739
MCR019112 | HPR145 | 2019-07-01 | Material | 82276148 | 64201399 | 73487139
MCR019113 | HPR145 | 2019-07-01 | Equipment | 18246738 | 14238222 | 16691118
MCR019114 | HPR145 | 2019-07-01 | Subcontract | 95432785 | 74467734 | 74325153
MCR019115 | HPR145 | 2019-07-01 | Overhead | 23312961 | 18191478 | 18992308
MCR019116 | HPR145 | 2019-08-01 | Labor | 25130441 | 24526601 | 32015268
MCR019117 | HPR145 | 2019-08-01 | Material | 74744202 | 72948230 | 65112885
MCR019118 | HPR145 | 2019-08-01 | Equipment | 16576345 | 16178045 | 16483377
MCR019119 | HPR145 | 2019-08-01 | Subcontract | 86696418 | 84613256 | 82787914
MCR019120 | HPR145 | 2019-08-01 | Overhead | 21178783 | 20669894 | 16871255
MCR019121 | HPR145 | 2019-09-01 | Labor | 22210981 | 24804548 | 28774485
MCR019122 | HPR145 | 2019-09-01 | Material | 66060998 | 73774912 | 80935895
MCR019123 | HPR145 | 2019-09-01 | Equipment | 14650634 | 16361382 | 17238447
MCR019124 | HPR145 | 2019-09-01 | Subcontract | 76624699 | 85572131 | 93332438
MCR019125 | HPR145 | 2019-09-01 | Overhead | 18718396 | 20904134 | 17702477
MCR019126 | HPR145 | 2019-10-01 | Labor | 18959296 | 42193667 | 47082199
MCR019127 | HPR145 | 2019-10-01 | Material | 56389675 | 125494490 | 104570503
MCR019128 | HPR145 | 2019-10-01 | Equipment | 12505783 | 27831456 | 30368410
MCR019129 | HPR145 | 2019-10-01 | Subcontract | 65406851 | 145562098 | 156501268
MCR019130 | HPR145 | 2019-10-01 | Overhead | 15978025 | 35558886 | 16971915
MCR019131 | HPR145 | 2019-11-01 | Labor | 15441865 | 21122710 | 22556045
MCR019132 | HPR145 | 2019-11-01 | Material | 45927959 | 62824208 | 86710962
MCR019133 | HPR145 | 2019-11-01 | Equipment | 10185642 | 13932797 | 12615459
MCR019134 | HPR145 | 2019-11-01 | Subcontract | 53272220 | 72870320 | 64468347
MCR019135 | HPR145 | 2019-11-01 | Overhead | 13013695 | 17801251 | 17551158
MCR019136 | HPR145 | 2019-12-01 | Labor | 11742994 | 16959514 | 18022772
MCR019137 | HPR145 | 2019-12-01 | Material | 34926595 | 50441826 | 43919307
MCR019138 | HPR145 | 2019-12-01 | Equipment | 7745822 | 11186702 | 10653581
MCR019139 | HPR145 | 2019-12-01 | Subcontract | 40511646 | 58507892 | 89018084
MCR019140 | HPR145 | 2019-12-01 | Overhead | 9896457 | 14292700 | 16455127
MCR019141 | HPR145 | 2020-01-01 | Labor | 7977347 | 15921045 | 20735495
MCR019142 | HPR145 | 2020-01-01 | Material | 23726621 | 47353159 | 53049732
MCR019143 | HPR145 | 2020-01-01 | Equipment | 5261956 | 10501715 | 11060293
MCR019144 | HPR145 | 2020-01-01 | Subcontract | 27520704 | 54925321 | 86930363
MCR019145 | HPR145 | 2020-01-01 | Overhead | 6722942 | 13417526 | 17221064
MCR019146 | HPR145 | 2020-02-01 | Labor | 4321398 | 15477074 | 16457415
MCR019147 | HPR145 | 2020-02-01 | Material | 12852917 | 46032677 | 47101138
MCR019148 | HPR145 | 2020-02-01 | Equipment | 2850447 | 10208866 | 13363982
MCR019149 | HPR145 | 2020-02-01 | Subcontract | 14908204 | 53393684 | 78120700
MCR019150 | HPR145 | 2020-02-01 | Overhead | 3641876 | 13043367 | 17168110
MCR019151 | HPR145 | 2020-03-01 | Labor | 1146051 | 13780684 | 17091288
MCR019152 | HPR145 | 2020-03-01 | Material | 3408643 | 40987193 | 40200686
MCR019153 | HPR145 | 2020-03-01 | Equipment | 755949 | 9089907 | 8209079
MCR019154 | HPR145 | 2020-03-01 | Subcontract | 3953713 | 47541385 | 87349809
MCR019155 | HPR145 | 2020-03-01 | Overhead | 965840 | 11613728 | 18906530
MCR019156 | HPR145 | 2020-04-01 | Labor | 0 | 17221626 | 19209869
MCR019157 | HPR145 | 2020-04-01 | Material | 0 | 51221410 | 46056188
MCR019158 | HPR145 | 2020-04-01 | Equipment | 0 | 11359594 | 11131976
MCR019159 | HPR145 | 2020-04-01 | Subcontract | 0 | 59412138 | 96976774
MCR019160 | HPR145 | 2020-04-01 | Overhead | 0 | 14513596 | 18442178
MCR019161 | HPR145 | 2020-05-01 | Labor | 0 | 11930478 | 13549958
MCR019162 | HPR145 | 2020-05-01 | Material | 0 | 35484217 | 39722772
MCR019163 | HPR145 | 2020-05-01 | Equipment | 0 | 7869488 | 10123880
MCR019164 | HPR145 | 2020-05-01 | Subcontract | 0 | 41158437 | 69677350
MCR019165 | HPR145 | 2020-05-01 | Overhead | 0 | 10054459 | 17317796
MCR019166 | HPR145 | 2020-06-01 | Labor | 0 | 9060332 | 10737076
MCR019167 | HPR145 | 2020-06-01 | Material | 0 | 26947689 | 34710904
MCR019168 | HPR145 | 2020-06-01 | Equipment | 0 | 5976306 | 5728479
MCR019169 | HPR145 | 2020-06-01 | Subcontract | 0 | 31256847 | 61935312
MCR019170 | HPR145 | 2020-06-01 | Overhead | 0 | 7635632 | 17383475
MCR019171 | HPR145 | 2020-07-01 | Labor | 0 | 4510573 | 5078563
MCR019172 | HPR145 | 2020-07-01 | Material | 0 | 13415571 | 9773144
MCR019173 | HPR145 | 2020-07-01 | Equipment | 0 | 2975229 | 3301208
MCR019174 | HPR145 | 2020-07-01 | Subcontract | 0 | 15560832 | 43969591
MCR019175 | HPR145 | 2020-07-01 | Overhead | 0 | 3801304 | 19142153
MCR019176 | HPR145 | 2020-08-01 | Labor | 0 | 3776372 | 4150210
MCR019177 | HPR145 | 2020-08-01 | Material | 0 | 11231872 | 12512166
MCR019178 | HPR145 | 2020-08-01 | Equipment | 0 | 2490941 | 2938224
MCR019179 | HPR145 | 2020-08-01 | Subcontract | 0 | 13027942 | 54888590
MCR019180 | HPR145 | 2020-08-01 | Overhead | 0 | 3182553 | 17095744
MCR019181 | HPR145 | 2020-09-01 | Labor | 0 | 1709400 | 1931582
MCR019182 | HPR145 | 2020-09-01 | Material | 0 | 5084182 | 4479851
MCR019183 | HPR145 | 2020-09-01 | Equipment | 0 | 1127541 | 1339655
MCR019184 | HPR145 | 2020-09-01 | Subcontract | 0 | 5897185 | 31044614
MCR019185 | HPR145 | 2020-09-01 | Overhead | 0 | 1440604 | 16872030
MCR019186 | HPR145 | 2020-10-01 | Labor | 0 | 544372 | 835921
MCR019187 | HPR145 | 2020-10-01 | Material | 0 | 1619099 | 1721077
MCR019188 | HPR145 | 2020-10-01 | Equipment | 0 | 359075 | 322681
MCR019189 | HPR145 | 2020-10-01 | Subcontract | 0 | 1878006 | 32027466
MCR019190 | HPR145 | 2020-10-01 | Overhead | 0 | 458772 | 18919175
MCR019191 | HPR146 | 2021-08-01 | Labor | 18095912 | 8760107 | 10525221
MCR019192 | HPR146 | 2021-08-01 | Material | 36443468 | 17642034 | 18427697
MCR019193 | HPR146 | 2021-08-01 | Equipment | 7474696 | 3618449 | 3457713
MCR019194 | HPR146 | 2021-08-01 | Subcontract | 31993741 | 15487951 | 13713031
MCR019195 | HPR146 | 2021-08-01 | Overhead | 10121928 | 4899956 | 40179809
MCR019196 | HPR146 | 2021-09-01 | Labor | 49632594 | 31726449 | 36562644
MCR019197 | HPR146 | 2021-09-01 | Material | 99955383 | 63894089 | 62963669
MCR019198 | HPR146 | 2021-09-01 | Equipment | 20501234 | 13104924 | 12450277
MCR019199 | HPR146 | 2021-09-01 | Subcontract | 87750888 | 56092657 | 56154380
MCR019200 | HPR146 | 2021-09-01 | Overhead | 27761936 | 17746154 | 39008688
MCR019201 | HPR146 | 2021-10-01 | Labor | 74374658 | 42675617 | 46230586
MCR019202 | HPR146 | 2021-10-01 | Material | 149783579 | 85944685 | 89030724
MCR019203 | HPR146 | 2021-10-01 | Equipment | 30721189 | 17627586 | 18433835
MCR019204 | HPR146 | 2021-10-01 | Subcontract | 131495089 | 75450888 | 75093582
MCR019205 | HPR146 | 2021-10-01 | Overhead | 41601382 | 23870559 | 40815489
MCR019206 | HPR146 | 2021-11-01 | Labor | 92589126 | 83090677 | 93169328
MCR019207 | HPR146 | 2021-11-01 | Material | 186465808 | 167336823 | 170800752
MCR019208 | HPR146 | 2021-11-01 | Equipment | 38244855 | 34321427 | 36644694
MCR019209 | HPR146 | 2021-11-01 | Subcontract | 163698438 | 146905092 | 146401879
MCR019210 | HPR146 | 2021-11-01 | Overhead | 51789625 | 46476678 | 36926430
MCR019211 | HPR146 | 2021-12-01 | Labor | 104566707 | 94394926 | 105309957
MCR019212 | HPR146 | 2021-12-01 | Material | 210587529 | 190102519 | 199166263
MCR019213 | HPR146 | 2021-12-01 | Equipment | 43192313 | 38990759 | 41799595
MCR019214 | HPR146 | 2021-12-01 | Subcontract | 184874912 | 166891110 | 157389203
MCR019215 | HPR146 | 2021-12-01 | Overhead | 58489271 | 52799697 | 39323857
MCR019216 | HPR146 | 2022-01-01 | Labor | 110627077 | 92568534 | 97544918
MCR019217 | HPR146 | 2022-01-01 | Material | 222792547 | 186424336 | 212092320
MCR019218 | HPR146 | 2022-01-01 | Equipment | 45695609 | 38236349 | 32440307
MCR019219 | HPR146 | 2022-01-01 | Subcontract | 195589703 | 163662030 | 150309506
MCR019220 | HPR146 | 2022-01-01 | Overhead | 61879132 | 51778106 | 38941663
MCR019221 | HPR146 | 2022-02-01 | Labor | 111126180 | 104291895 | 116779057
MCR019222 | HPR146 | 2022-02-01 | Material | 223797693 | 210034084 | 200925675
MCR019223 | HPR146 | 2022-02-01 | Equipment | 45901769 | 43078799 | 50038503
MCR019224 | HPR146 | 2022-02-01 | Subcontract | 196472122 | 184389042 | 187216881
MCR019225 | HPR146 | 2022-02-01 | Overhead | 62158305 | 58335555 | 37507888
MCR019226 | HPR146 | 2022-03-01 | Labor | 106466682 | 83807666 | 85695508
MCR019227 | HPR146 | 2022-03-01 | Material | 214413902 | 168780770 | 182314857
MCR019228 | HPR146 | 2022-03-01 | Equipment | 43977117 | 34617586 | 34741117
MCR019229 | HPR146 | 2022-03-01 | Subcontract | 188234087 | 148172734 | 163549752
MCR019230 | HPR146 | 2022-03-01 | Overhead | 59552020 | 46877724 | 36142606
MCR019231 | HPR146 | 2022-04-01 | Labor | 97113733 | 61089163 | 64610134
MCR019232 | HPR146 | 2022-04-01 | Material | 195577940 | 123027839 | 142092484
MCR019233 | HPR146 | 2022-04-01 | Equipment | 40113789 | 25233483 | 26442406
MCR019234 | HPR146 | 2022-04-01 | Subcontract | 171697984 | 108006210 | 112953222
MCR019235 | HPR146 | 2022-04-01 | Overhead | 54320458 | 34170155 | 39923356
MCR019236 | HPR146 | 2022-05-01 | Labor | 83620245 | 86763089 | 109006577
MCR019237 | HPR146 | 2022-05-01 | Material | 168403321 | 174732715 | 154393529
MCR019238 | HPR146 | 2022-05-01 | Equipment | 34540170 | 35838353 | 36855503
MCR019239 | HPR146 | 2022-05-01 | Subcontract | 147841372 | 153397950 | 165834306
MCR019240 | HPR146 | 2022-05-01 | Overhead | 46772891 | 48530837 | 40067979
MCR019241 | HPR146 | 2022-06-01 | Labor | 66671162 | 138502676 | 148846376
MCR019242 | HPR146 | 2022-06-01 | Material | 134269460 | 278931385 | 301032396
MCR019243 | HPR146 | 2022-06-01 | Equipment | 27539183 | 57209901 | 69705142
MCR019244 | HPR146 | 2022-06-01 | Subcontract | 117875236 | 244874022 | 252042874
MCR019245 | HPR146 | 2022-06-01 | Overhead | 37292440 | 77471317 | 41987137
MCR019246 | HPR146 | 2022-07-01 | Labor | 47171541 | 43143596 | 49763886
MCR019247 | HPR146 | 2022-07-01 | Material | 94999054 | 86887152 | 90309753
MCR019248 | HPR146 | 2022-07-01 | Equipment | 19484672 | 17820890 | 13840988
MCR019249 | HPR146 | 2022-07-01 | Subcontract | 83399724 | 76278281 | 108317962
MCR019250 | HPR146 | 2022-07-01 | Overhead | 26385349 | 24132323 | 40145703
MCR019251 | HPR146 | 2022-08-01 | Labor | 26463450 | 50848233 | 63847815
MCR019252 | HPR146 | 2022-08-01 | Material | 53294903 | 102403568 | 109109745
MCR019253 | HPR146 | 2022-08-01 | Equipment | 10930990 | 21003366 | 21683456
MCR019254 | HPR146 | 2022-08-01 | Subcontract | 46787626 | 89900150 | 112864857
MCR019255 | HPR146 | 2022-08-01 | Overhead | 14802301 | 28441903 | 39571044
MCR019256 | HPR146 | 2022-09-01 | Labor | 7217494 | 50607767 | 52050425
MCR019257 | HPR146 | 2022-09-01 | Material | 14535356 | 101919292 | 113598388
MCR019258 | HPR146 | 2022-09-01 | Equipment | 2981258 | 20904039 | 17621564
MCR019259 | HPR146 | 2022-09-01 | Subcontract | 12760597 | 89475004 | 83336766
MCR019260 | HPR146 | 2022-09-01 | Overhead | 4037097 | 28307398 | 38988242
MCR019261 | HPR146 | 2022-10-01 | Labor | 0 | 18856114 | 26194826
MCR019262 | HPR146 | 2022-10-01 | Material | 0 | 37974444 | 34597946
MCR019263 | HPR146 | 2022-10-01 | Equipment | 0 | 7788705 | 8891707
MCR019264 | HPR146 | 2022-10-01 | Subcontract | 0 | 33337786 | 83548812
MCR019265 | HPR146 | 2022-10-01 | Overhead | 0 | 10547147 | 36543543
MCR019266 | HPR146 | 2022-11-01 | Labor | 0 | 4610050 | 3290440
MCR019267 | HPR146 | 2022-11-01 | Material | 0 | 9284209 | 11202058
MCR019268 | HPR146 | 2022-11-01 | Equipment | 0 | 1904227 | 1660121
MCR019269 | HPR146 | 2022-11-01 | Subcontract | 0 | 8150612 | 45155319
MCR019270 | HPR146 | 2022-11-01 | Overhead | 0 | 2578627 | 43247273
MCR019271 | HPR147 | 2020-03-01 | Labor | 1378727 | 1551008 | 1580324
MCR019272 | HPR147 | 2020-03-01 | Material | 3513477 | 3952509 | 3512655
MCR019273 | HPR147 | 2020-03-01 | Equipment | 668697 | 752255 | 789052
MCR019274 | HPR147 | 2020-03-01 | Subcontract | 3003284 | 3378564 | 3423780
MCR019275 | HPR147 | 2020-03-01 | Overhead | 851111 | 957463 | 6045197
MCR019276 | HPR147 | 2020-04-01 | Labor | 3948552 | 3154527 | 3304512
MCR019277 | HPR147 | 2020-04-01 | Material | 10062284 | 8038832 | 8315490
MCR019278 | HPR147 | 2020-04-01 | Equipment | 1915088 | 1529978 | 1427441
MCR019279 | HPR147 | 2020-04-01 | Subcontract | 8601137 | 6871511 | 7664987
MCR019280 | HPR147 | 2020-04-01 | Overhead | 2437506 | 1947342 | 5729979
MCR019281 | HPR147 | 2020-05-01 | Labor | 6240804 | 2599899 | 2873011
MCR019282 | HPR147 | 2020-05-01 | Material | 15903737 | 6625448 | 7045285
MCR019283 | HPR147 | 2020-05-01 | Equipment | 3026853 | 1260978 | 1278863
MCR019284 | HPR147 | 2020-05-01 | Subcontract | 13594351 | 5663364 | 5587072
MCR019285 | HPR147 | 2020-05-01 | Overhead | 3852551 | 1604961 | 5979458
MCR019286 | HPR147 | 2020-06-01 | Labor | 8260807 | 6208174 | 6556661
MCR019287 | HPR147 | 2020-06-01 | Material | 21051408 | 15820585 | 15703101
MCR019288 | HPR147 | 2020-06-01 | Equipment | 4006576 | 3011028 | 3005604
MCR019289 | HPR147 | 2020-06-01 | Subcontract | 17994527 | 13523273 | 11878734
MCR019290 | HPR147 | 2020-06-01 | Overhead | 5099532 | 3832408 | 5870132
MCR019291 | HPR147 | 2020-07-01 | Labor | 10014108 | 7598292 | 7807144
MCR019292 | HPR147 | 2020-07-01 | Material | 25519429 | 19363089 | 18460910
MCR019293 | HPR147 | 2020-07-01 | Equipment | 4856945 | 3685249 | 3692133
MCR019294 | HPR147 | 2020-07-01 | Subcontract | 21813746 | 16551370 | 17882007
MCR019295 | HPR147 | 2020-07-01 | Overhead | 6181874 | 4690551 | 5575183
MCR019296 | HPR147 | 2020-08-01 | Labor | 11506496 | 4971312 | 6172847
MCR019297 | HPR147 | 2020-08-01 | Material | 29322552 | 12668631 | 12493005
MCR019298 | HPR147 | 2020-08-01 | Equipment | 5580768 | 2411137 | 2400589
MCR019299 | HPR147 | 2020-08-01 | Subcontract | 25064615 | 10829016 | 12194934
MCR019300 | HPR147 | 2020-08-01 | Overhead | 7103149 | 3068873 | 6090498
MCR019301 | HPR147 | 2020-09-01 | Labor | 12744025 | 10261349 | 10052858
MCR019302 | HPR147 | 2020-09-01 | Material | 32476207 | 26149486 | 29983178
MCR019303 | HPR147 | 2020-09-01 | Equipment | 6180982 | 4976859 | 4500431
MCR019304 | HPR147 | 2020-09-01 | Subcontract | 27760328 | 22352311 | 22434941
MCR019305 | HPR147 | 2020-09-01 | Overhead | 7867097 | 6334500 | 5841599
MCR019306 | HPR147 | 2020-10-01 | Labor | 13733049 | 10280943 | 11660031
MCR019307 | HPR147 | 2020-10-01 | Material | 34996584 | 26199417 | 26768710
MCR019308 | HPR147 | 2020-10-01 | Equipment | 6660669 | 4986362 | 5571452
MCR019309 | HPR147 | 2020-10-01 | Subcontract | 29914719 | 22394992 | 21606582
MCR019310 | HPR147 | 2020-10-01 | Overhead | 8477637 | 6346595 | 6201641
MCR019311 | HPR147 | 2020-11-01 | Labor | 14480251 | 11998388 | 11594016
MCR019312 | HPR147 | 2020-11-01 | Material | 36900714 | 30576064 | 30903864
MCR019313 | HPR147 | 2020-11-01 | Equipment | 7023070 | 5819341 | 5673474
MCR019314 | HPR147 | 2020-11-01 | Subcontract | 31542350 | 26136104 | 29769038
MCR019315 | HPR147 | 2020-11-01 | Overhead | 8938897 | 7406802 | 6088815
MCR019316 | HPR147 | 2020-12-01 | Labor | 14992687 | 11809289 | 12526191
MCR019317 | HPR147 | 2020-12-01 | Material | 38206578 | 30094174 | 28867709
MCR019318 | HPR147 | 2020-12-01 | Equipment | 7271606 | 5727626 | 6402559
MCR019319 | HPR147 | 2020-12-01 | Subcontract | 32658590 | 25724191 | 26140149
MCR019320 | HPR147 | 2020-12-01 | Overhead | 9255232 | 7290069 | 6330236
MCR019321 | HPR147 | 2021-01-01 | Labor | 15277833 | 23485909 | 22456951
MCR019322 | HPR147 | 2021-01-01 | Material | 38933231 | 59850261 | 68988488
MCR019323 | HPR147 | 2021-01-01 | Equipment | 7409905 | 11390906 | 10854953
MCR019324 | HPR147 | 2021-01-01 | Subcontract | 33279725 | 51159387 | 47282204
MCR019325 | HPR147 | 2021-01-01 | Overhead | 9431258 | 14498238 | 6254455
MCR019326 | HPR147 | 2021-02-01 | Labor | 15343649 | 20043783 | 23985761
MCR019327 | HPR147 | 2021-02-01 | Material | 39100951 | 51078527 | 48921344
MCR019328 | HPR147 | 2021-02-01 | Equipment | 7441826 | 9721439 | 9888454
MCR019329 | HPR147 | 2021-02-01 | Subcontract | 33423090 | 43661399 | 47803686
MCR019330 | HPR147 | 2021-02-01 | Overhead | 9471887 | 12373357 | 6331461
MCR019331 | HPR147 | 2021-03-01 | Labor | 15198643 | 14528397 | 16063018
MCR019332 | HPR147 | 2021-03-01 | Material | 38731427 | 37023406 | 41647239
MCR019333 | HPR147 | 2021-03-01 | Equipment | 7371497 | 7046421 | 7496090
MCR019334 | HPR147 | 2021-03-01 | Subcontract | 33107225 | 31647226 | 33105905
MCR019335 | HPR147 | 2021-03-01 | Overhead | 9382373 | 8968618 | 6489302
MCR019336 | HPR147 | 2021-04-01 | Labor | 14851973 | 16112614 | 15877214
MCR019337 | HPR147 | 2021-04-01 | Material | 37847990 | 41060543 | 46139833
MCR019338 | HPR147 | 2021-04-01 | Equipment | 7203358 | 7814782 | 7094798
MCR019339 | HPR147 | 2021-04-01 | Subcontract | 32352072 | 35098130 | 34293138
MCR019340 | HPR147 | 2021-04-01 | Overhead | 9168367 | 9946582 | 6200034
MCR019341 | HPR147 | 2021-05-01 | Labor | 14313552 | 16333580 | 18417849
MCR019342 | HPR147 | 2021-05-01 | Material | 36475906 | 41623641 | 43470947
MCR019343 | HPR147 | 2021-05-01 | Equipment | 6942219 | 7921953 | 9090356
MCR019344 | HPR147 | 2021-05-01 | Subcontract | 31179229 | 35579460 | 36441765
MCR019345 | HPR147 | 2021-05-01 | Overhead | 8835991 | 10082988 | 6174819
MCR019346 | HPR147 | 2021-06-01 | Labor | 13594202 | 11731755 | 13164248
MCR019347 | HPR147 | 2021-06-01 | Material | 34642753 | 29896590 | 44589034
MCR019348 | HPR147 | 2021-06-01 | Equipment | 6593327 | 5690021 | 5412165
MCR019349 | HPR147 | 2021-06-01 | Subcontract | 29612269 | 25555297 | 26905344
MCR019350 | HPR147 | 2021-06-01 | Overhead | 8391925 | 7242205 | 5757190
MCR019351 | HPR147 | 2021-07-01 | Labor | 12705849 | 8457361 | 9087862
MCR019352 | HPR147 | 2021-07-01 | Material | 32378921 | 21552297 | 23822091
MCR019353 | HPR147 | 2021-07-01 | Equipment | 6162467 | 4101907 | 4619653
MCR019354 | HPR147 | 2021-07-01 | Subcontract | 27677168 | 18422681 | 19054174
MCR019355 | HPR147 | 2021-07-01 | Overhead | 7843530 | 5220868 | 5974683
MCR019356 | HPR147 | 2021-08-01 | Labor | 11661786 | 7658211 | 8215040
MCR019357 | HPR147 | 2021-08-01 | Material | 29718285 | 19515783 | 20965942
MCR019358 | HPR147 | 2021-08-01 | Equipment | 5656085 | 3714310 | 3540121
MCR019359 | HPR147 | 2021-08-01 | Subcontract | 25402884 | 16681890 | 17235765
MCR019360 | HPR147 | 2021-08-01 | Overhead | 7199012 | 4727539 | 6307668
MCR019361 | HPR147 | 2021-09-01 | Labor | 10477045 | 12020675 | 15462055
MCR019362 | HPR147 | 2021-09-01 | Material | 26699153 | 30632858 | 33570137
MCR019363 | HPR147 | 2021-09-01 | Equipment | 5081474 | 5830150 | 6506853
MCR019364 | HPR147 | 2021-09-01 | Subcontract | 22822161 | 26184652 | 23500329
MCR019365 | HPR147 | 2021-09-01 | Overhead | 6467652 | 7420560 | 5948618
MCR019366 | HPR147 | 2021-10-01 | Labor | 9168936 | 15265484 | 17107086
MCR019367 | HPR147 | 2021-10-01 | Material | 23365636 | 38901760 | 47425354
MCR019368 | HPR147 | 2021-10-01 | Equipment | 4447027 | 7403915 | 6905969
MCR019369 | HPR147 | 2021-10-01 | Subcontract | 19972705 | 33252824 | 34385480
MCR019370 | HPR147 | 2021-10-01 | Overhead | 5660135 | 9423634 | 5910504
MCR019371 | HPR147 | 2021-11-01 | Labor | 7757871 | 8846479 | 8969123
MCR019372 | HPR147 | 2021-11-01 | Material | 19769753 | 22543903 | 27862465
MCR019373 | HPR147 | 2021-11-01 | Equipment | 3762647 | 4290632 | 4911674
MCR019374 | HPR147 | 2021-11-01 | Subcontract | 16898981 | 19270296 | 20889583
MCR019375 | HPR147 | 2021-11-01 | Overhead | 4789062 | 5461077 | 5777555
MCR019376 | HPR147 | 2021-12-01 | Labor | 6268712 | 5293038 | 7086942
MCR019377 | HPR147 | 2021-12-01 | Material | 15974859 | 13488502 | 16056345
MCR019378 | HPR147 | 2021-12-01 | Equipment | 3040390 | 2567178 | 2525963
MCR019379 | HPR147 | 2021-12-01 | Subcontract | 13655145 | 11529832 | 12497048
MCR019380 | HPR147 | 2021-12-01 | Overhead | 3869779 | 3267480 | 6027021
MCR019381 | HPR147 | 2022-01-01 | Labor | 4733165 | 5329764 | 4818624
MCR019382 | HPR147 | 2022-01-01 | Material | 12061750 | 13582090 | 18745830
MCR019383 | HPR147 | 2022-01-01 | Equipment | 2295633 | 2584990 | 2717493
MCR019384 | HPR147 | 2022-01-01 | Subcontract | 10310260 | 11609831 | 11664465
MCR019385 | HPR147 | 2022-01-01 | Overhead | 2921861 | 3290151 | 6807376
MCR019386 | HPR147 | 2022-02-01 | Labor | 3194644 | 3834080 | 4872946
MCR019387 | HPR147 | 2022-02-01 | Material | 8141065 | 9770570 | 10163312
MCR019388 | HPR147 | 2022-02-01 | Equipment | 1549435 | 1859568 | 1914340
MCR019389 | HPR147 | 2022-02-01 | Subcontract | 6958898 | 8351783 | 9184901
MCR019390 | HPR147 | 2022-02-01 | Overhead | 1972107 | 2366841 | 6368281
MCR019391 | HPR147 | 2022-03-01 | Labor | 1720531 | 6424599 | 6861030
MCR019392 | HPR147 | 2022-03-01 | Material | 4384510 | 16372113 | 20488820
MCR019393 | HPR147 | 2022-03-01 | Equipment | 834475 | 3115996 | 3361963
MCR019394 | HPR147 | 2022-03-01 | Subcontract | 3747834 | 13994713 | 13486482
MCR019395 | HPR147 | 2022-03-01 | Overhead | 1062112 | 3966011 | 6586445
MCR019396 | HPR147 | 2022-04-01 | Labor | 454094 | 4914632 | 5451738
MCR019397 | HPR147 | 2022-04-01 | Material | 1157189 | 12524191 | 15543380
MCR019398 | HPR147 | 2022-04-01 | Equipment | 220240 | 2383647 | 2302437
MCR019399 | HPR147 | 2022-04-01 | Subcontract | 989154 | 10705550 | 11395321
MCR019400 | HPR147 | 2022-04-01 | Overhead | 280320 | 3033883 | 5830534
MCR019401 | HPR147 | 2022-05-01 | Labor | 0 | 2169725 | 2811165
MCR019402 | HPR147 | 2022-05-01 | Material | 0 | 5529214 | 6807832
MCR019403 | HPR147 | 2022-05-01 | Equipment | 0 | 1052339 | 1295725
MCR019404 | HPR147 | 2022-05-01 | Subcontract | 0 | 4726315 | 4890060
MCR019405 | HPR147 | 2022-05-01 | Overhead | 0 | 1339407 | 5447552
MCR019406 | HPR147 | 2022-06-01 | Labor | 0 | 927581 | 957947
MCR019407 | HPR147 | 2022-06-01 | Material | 0 | 2363799 | 3515132
MCR019408 | HPR147 | 2022-06-01 | Equipment | 0 | 449886 | 464982
MCR019409 | HPR147 | 2022-06-01 | Subcontract | 0 | 2020551 | 1940124
MCR019410 | HPR147 | 2022-06-01 | Overhead | 0 | 572611 | 6094625
MCR019411 | HPR147 | 2022-07-01 | Labor | 0 | 211143 | 270617
MCR019412 | HPR147 | 2022-07-01 | Material | 0 | 538066 | 596547
MCR019413 | HPR147 | 2022-07-01 | Equipment | 0 | 102407 | 45640
MCR019414 | HPR147 | 2022-07-01 | Subcontract | 0 | 459933 | 414249
MCR019415 | HPR147 | 2022-07-01 | Overhead | 0 | 130342 | 5597283
MCR019416 | HPR148 | 2018-08-01 | Labor | 878193 | 747818 | 791161
MCR019417 | HPR148 | 2018-08-01 | Material | 2094797 | 1783807 | 1781046
MCR019418 | HPR148 | 2018-08-01 | Equipment | 468013 | 398532 | 350270
MCR019419 | HPR148 | 2018-08-01 | Subcontract | 3700333 | 3150988 | 3256845
MCR019420 | HPR148 | 2018-08-01 | Overhead | 646328 | 550375 | 6665755
MCR019421 | HPR148 | 2018-09-01 | Labor | 2546267 | 1549724 | 1615975
MCR019422 | HPR148 | 2018-09-01 | Material | 6073733 | 3696630 | 3915866
MCR019423 | HPR148 | 2018-09-01 | Equipment | 1356973 | 825889 | 953672
MCR019424 | HPR148 | 2018-09-01 | Subcontract | 10728883 | 6529874 | 5570178
MCR019425 | HPR148 | 2018-09-01 | Overhead | 1873988 | 1140557 | 6013027
MCR019426 | HPR148 | 2018-10-01 | Labor | 4083204 | 4030164 | 4332970
MCR019427 | HPR148 | 2018-10-01 | Material | 9739862 | 9613344 | 9544104
MCR019428 | HPR148 | 2018-10-01 | Equipment | 2176048 | 2147781 | 2450982
MCR019429 | HPR148 | 2018-10-01 | Subcontract | 17204879 | 16981393 | 19349719
MCR019430 | HPR148 | 2018-10-01 | Overhead | 3005134 | 2966099 | 6522694
MCR019431 | HPR148 | 2018-11-01 | Labor | 5490822 | 5082602 | 5539865
MCR019432 | HPR148 | 2018-11-01 | Material | 13097521 | 12123774 | 12647373
MCR019433 | HPR148 | 2018-11-01 | Equipment | 2926205 | 2708653 | 2665542
MCR019434 | HPR148 | 2018-11-01 | Subcontract | 23135982 | 21415916 | 18839240
MCR019435 | HPR148 | 2018-11-01 | Overhead | 4041106 | 3740666 | 5936817
MCR019436 | HPR148 | 2018-12-01 | Labor | 6770994 | 6542343 | 6684340
MCR019437 | HPR148 | 2018-12-01 | Material | 16151175 | 15605764 | 17028695
MCR019438 | HPR148 | 2018-12-01 | Equipment | 3608442 | 3486588 | 3860906
MCR019439 | HPR148 | 2018-12-01 | Subcontract | 28530079 | 27566643 | 26901469
MCR019440 | HPR148 | 2018-12-01 | Overhead | 4983279 | 4814998 | 6059234
MCR019441 | HPR148 | 2019-01-01 | Labor | 7925648 | 5043535 | 5690830
MCR019442 | HPR148 | 2019-01-01 | Material | 18905428 | 12030586 | 13261803
MCR019443 | HPR148 | 2019-01-01 | Equipment | 4223788 | 2687834 | 2591357
MCR019444 | HPR148 | 2019-01-01 | Subcontract | 33395300 | 21251306 | 21604115
MCR019445 | HPR148 | 2019-01-01 | Overhead | 5833076 | 3711914 | 6238692
MCR019446 | HPR148 | 2019-02-01 | Labor | 8956777 | 8543212 | 8519597
MCR019447 | HPR148 | 2019-02-01 | Material | 21365029 | 20378533 | 18792470
MCR019448 | HPR148 | 2019-02-01 | Equipment | 4773304 | 4552904 | 4913957
MCR019449 | HPR148 | 2019-02-01 | Subcontract | 37740037 | 35997451 | 34050230
MCR019450 | HPR148 | 2019-02-01 | Overhead | 6591960 | 6287587 | 6280280
MCR019451 | HPR148 | 2019-03-01 | Labor | 9866437 | 10232570 | 11317734
MCR019452 | HPR148 | 2019-03-01 | Material | 23534886 | 24408239 | 26313846
MCR019453 | HPR148 | 2019-03-01 | Equipment | 5258086 | 5453208 | 5235217
MCR019454 | HPR148 | 2019-03-01 | Subcontract | 41572958 | 43115683 | 40915320
MCR019455 | HPR148 | 2019-03-01 | Overhead | 7261447 | 7530911 | 6021679
MCR019456 | HPR148 | 2019-04-01 | Labor | 10656758 | 7434190 | 6885589
MCR019457 | HPR148 | 2019-04-01 | Material | 25420077 | 17733130 | 14306672
MCR019458 | HPR148 | 2019-04-01 | Equipment | 5679269 | 3961877 | 4149135
MCR019459 | HPR148 | 2019-04-01 | Subcontract | 44903035 | 31324506 | 30299027
MCR019460 | HPR148 | 2019-04-01 | Overhead | 7843104 | 5471375 | 6785276
MCR019461 | HPR148 | 2019-05-01 | Labor | 11329947 | 6760799 | 7942351
MCR019462 | HPR148 | 2019-05-01 | Material | 27025865 | 16126857 | 19268495
MCR019463 | HPR148 | 2019-05-01 | Equipment | 6038029 | 3603009 | 3385977
MCR019464 | HPR148 | 2019-05-01 | Subcontract | 47739563 | 28487121 | 28288814
MCR019465 | HPR148 | 2019-05-01 | Overhead | 8338553 | 4975776 | 6107154
MCR019466 | HPR148 | 2019-06-01 | Labor | 11888292 | 10567093 | 8993870
MCR019467 | HPR148 | 2019-06-01 | Material | 28357713 | 25206193 | 23019329
MCR019468 | HPR148 | 2019-06-01 | Equipment | 6335586 | 5631484 | 5374152
MCR019469 | HPR148 | 2019-06-01 | Subcontract | 50092193 | 44525221 | 50961687
MCR019470 | HPR148 | 2019-06-01 | Overhead | 8749481 | 7777112 | 5802033
MCR019471 | HPR148 | 2019-07-01 | Labor | 12334176 | 6104481 | 8069485
MCR019472 | HPR148 | 2019-07-01 | Material | 29421302 | 14561312 | 14877249
MCR019473 | HPR148 | 2019-07-01 | Equipment | 6573210 | 3253240 | 3511261
MCR019474 | HPR148 | 2019-07-01 | Subcontract | 51970958 | 25721681 | 20363372
MCR019475 | HPR148 | 2019-07-01 | Overhead | 9077641 | 4492743 | 6246929
MCR019476 | HPR148 | 2019-08-01 | Labor | 12670080 | 12256105 | 12108412
MCR019477 | HPR148 | 2019-08-01 | Material | 30222549 | 29235075 | 32202646
MCR019478 | HPR148 | 2019-08-01 | Equipment | 6752222 | 6531604 | 7650327
MCR019479 | HPR148 | 2019-08-01 | Subcontract | 53386312 | 51641999 | 53300641
MCR019480 | HPR148 | 2019-08-01 | Overhead | 9324857 | 9020182 | 6247467
MCR019481 | HPR148 | 2019-09-01 | Labor | 12898593 | 9784959 | 11398732
MCR019482 | HPR148 | 2019-09-01 | Material | 30767633 | 23340532 | 25351508
MCR019483 | HPR148 | 2019-09-01 | Equipment | 6874003 | 5214664 | 4756820
MCR019484 | HPR148 | 2019-09-01 | Subcontract | 54349170 | 41229643 | 37791675
MCR019485 | HPR148 | 2019-09-01 | Overhead | 9493037 | 7201481 | 6110543
MCR019486 | HPR148 | 2019-10-01 | Labor | 13022427 | 9102121 | 8777515
MCR019487 | HPR148 | 2019-10-01 | Material | 31063020 | 21711726 | 23983875
MCR019488 | HPR148 | 2019-10-01 | Equipment | 6939997 | 4850762 | 5424913
MCR019489 | HPR148 | 2019-10-01 | Subcontract | 54870954 | 38352457 | 38880239
MCR019490 | HPR148 | 2019-10-01 | Overhead | 9584176 | 6698930 | 6139367
MCR019491 | HPR148 | 2019-11-01 | Labor | 13044427 | 6555633 | 6971465
MCR019492 | HPR148 | 2019-11-01 | Material | 31115497 | 15637466 | 14512642
MCR019493 | HPR148 | 2019-11-01 | Equipment | 6951721 | 3493671 | 3682486
MCR019494 | HPR148 | 2019-11-01 | Subcontract | 54963651 | 27622642 | 24208420
MCR019495 | HPR148 | 2019-11-01 | Overhead | 9600367 | 4824780 | 5755055
MCR019496 | HPR148 | 2019-12-01 | Labor | 12967585 | 10341799 | 10776189
MCR019497 | HPR148 | 2019-12-01 | Material | 30932201 | 24668789 | 27114280
MCR019498 | HPR148 | 2019-12-01 | Equipment | 6910770 | 5511419 | 5936098
MCR019499 | HPR148 | 2019-12-01 | Subcontract | 54639871 | 43575930 | 41535106
MCR019500 | HPR148 | 2019-12-01 | Overhead | 9543813 | 7611302 | 6258540
MCR019501 | HPR148 | 2020-01-01 | Labor | 12795060 | 7808082 | 8705996
MCR019502 | HPR148 | 2020-01-01 | Material | 30520671 | 18624992 | 19094614
MCR019503 | HPR148 | 2020-01-01 | Equipment | 6818827 | 4161134 | 4294491
MCR019504 | HPR148 | 2020-01-01 | Subcontract | 53912927 | 32899927 | 38780972
MCR019505 | HPR148 | 2020-01-01 | Overhead | 9416840 | 5746550 | 5995889
MCR019506 | HPR148 | 2020-02-01 | Labor | 12530202 | 12353378 | 12495440
MCR019507 | HPR148 | 2020-02-01 | Material | 29888891 | 29467104 | 34074319
MCR019508 | HPR148 | 2020-02-01 | Equipment | 6677677 | 6583443 | 6487680
MCR019509 | HPR148 | 2020-02-01 | Subcontract | 52796925 | 52051865 | 53151565
MCR019510 | HPR148 | 2020-02-01 | Overhead | 9221910 | 9091773 | 5908852
MCR019511 | HPR148 | 2020-03-01 | Labor | 12176569 | 12816260 | 13292304
MCR019512 | HPR148 | 2020-03-01 | Material | 29045355 | 30571240 | 28011792
MCR019513 | HPR148 | 2020-03-01 | Equipment | 6489217 | 6830125 | 7588430
MCR019514 | HPR148 | 2020-03-01 | Subcontract | 51306870 | 54002254 | 52352158
MCR019515 | HPR148 | 2020-03-01 | Overhead | 8961646 | 9432442 | 6843195
MCR019516 | HPR148 | 2020-04-01 | Labor | 11737969 | 19210810 | 20348059
MCR019517 | HPR148 | 2020-04-01 | Material | 27999141 | 45824467 | 48183882
MCR019518 | HPR148 | 2020-04-01 | Equipment | 6255475 | 10237951 | 10334820
MCR019519 | HPR148 | 2020-04-01 | Subcontract | 49458796 | 80946160 | 80218373
MCR019520 | HPR148 | 2020-04-01 | Overhead | 8638847 | 14138669 | 6126539
MCR019521 | HPR148 | 2020-05-01 | Labor | 11218490 | 10676058 | 11099794
MCR019522 | HPR148 | 2020-05-01 | Material | 26760002 | 25466114 | 24156963
MCR019523 | HPR148 | 2020-05-01 | Equipment | 5978631 | 5689555 | 6321065
MCR019524 | HPR148 | 2020-05-01 | Subcontract | 47269932 | 44984357 | 37770418
MCR019525 | HPR148 | 2020-05-01 | Overhead | 8256524 | 7857308 | 6607012
MCR019526 | HPR148 | 2020-06-01 | Labor | 10622551 | 12012303 | 12892291
MCR019527 | HPR148 | 2020-06-01 | Material | 25338481 | 28653522 | 28632002
MCR019528 | HPR148 | 2020-06-01 | Equipment | 5661040 | 6401675 | 6189971
MCR019529 | HPR148 | 2020-06-01 | Subcontract | 44758900 | 50614721 | 54488301
MCR019530 | HPR148 | 2020-06-01 | Overhead | 7817928 | 8840750 | 6154717
MCR019531 | HPR148 | 2020-07-01 | Labor | 9954965 | 5796057 | 5808144
MCR019532 | HPR148 | 2020-07-01 | Material | 23746056 | 13825612 | 14418776
MCR019533 | HPR148 | 2020-07-01 | Equipment | 5305265 | 3088872 | 2928567
MCR019534 | HPR148 | 2020-07-01 | Subcontract | 41945978 | 24422110 | 22746808
MCR019535 | HPR148 | 2020-07-01 | Overhead | 7326602 | 4265751 | 6268031
MCR019536 | HPR148 | 2020-08-01 | Labor | 9221015 | 7781300 | 7547120
MCR019537 | HPR148 | 2020-08-01 | Material | 21995329 | 18561107 | 17754348
MCR019538 | HPR148 | 2020-08-01 | Equipment | 4914124 | 4146861 | 4513003
MCR019539 | HPR148 | 2020-08-01 | Subcontract | 38853424 | 32787077 | 32212148
MCR019540 | HPR148 | 2020-08-01 | Overhead | 6786433 | 5726839 | 6424386
MCR019541 | HPR148 | 2020-09-01 | Labor | 8426559 | 8425775 | 9485908
MCR019542 | HPR148 | 2020-09-01 | Material | 20100276 | 20098406 | 18929159
MCR019543 | HPR148 | 2020-09-01 | Equipment | 4490737 | 4490319 | 4383920
MCR019544 | HPR148 | 2020-09-01 | Subcontract | 35505927 | 35502623 | 38869861
MCR019545 | HPR148 | 2020-09-01 | Overhead | 6201734 | 6201157 | 5982507
MCR019546 | HPR148 | 2020-10-01 | Labor | 7578177 | 9011490 | 7575998
MCR019547 | HPR148 | 2020-10-01 | Material | 18076588 | 21495540 | 22857702
MCR019548 | HPR148 | 2020-10-01 | Equipment | 4038612 | 4802462 | 5008493
MCR019549 | HPR148 | 2020-10-01 | Subcontract | 31931205 | 37970576 | 29398267
MCR019550 | HPR148 | 2020-10-01 | Overhead | 5577346 | 6632228 | 6190932
MCR019551 | HPR148 | 2020-11-01 | Labor | 6683365 | 9888723 | 11996364
MCR019552 | HPR148 | 2020-11-01 | Material | 15942150 | 23588046 | 24183528
MCR019553 | HPR148 | 2020-11-01 | Equipment | 3561742 | 5269963 | 5404246
MCR019554 | HPR148 | 2020-11-01 | Subcontract | 28160848 | 41666863 | 45831826
MCR019555 | HPR148 | 2020-11-01 | Overhead | 4918787 | 7277849 | 5810641
MCR019556 | HPR148 | 2020-12-01 | Labor | 5750834 | 6223933 | 7568260
MCR019557 | HPR148 | 2020-12-01 | Material | 13717739 | 14846245 | 13850260
MCR019558 | HPR148 | 2020-12-01 | Equipment | 3064772 | 3316899 | 3151422
MCR019559 | HPR148 | 2020-12-01 | Subcontract | 24231560 | 26224997 | 28189272
MCR019560 | HPR148 | 2020-12-01 | Overhead | 4232468 | 4580656 | 5696370
MCR019561 | HPR148 | 2021-01-01 | Labor | 4790959 | 9767256 | 10725619
MCR019562 | HPR148 | 2021-01-01 | Material | 11428103 | 23298303 | 25130928
MCR019563 | HPR148 | 2021-01-01 | Equipment | 2553229 | 5205230 | 6276336
MCR019564 | HPR148 | 2021-01-01 | Subcontract | 20187056 | 41155050 | 34320436
MCR019565 | HPR148 | 2021-01-01 | Overhead | 3526024 | 7188452 | 5832957
MCR019566 | HPR148 | 2021-02-01 | Labor | 3816520 | 6374991 | 6291833
MCR019567 | HPR148 | 2021-02-01 | Material | 9103729 | 15206572 | 15386499
MCR019568 | HPR148 | 2021-02-01 | Equipment | 2033925 | 3397402 | 2675079
MCR019569 | HPR148 | 2021-02-01 | Subcontract | 16081189 | 26861494 | 28436897
MCR019570 | HPR148 | 2021-02-01 | Overhead | 2808862 | 4691832 | 6038324
MCR019571 | HPR148 | 2021-03-01 | Labor | 2844033 | 5975958 | 6461235
MCR019572 | HPR148 | 2021-03-01 | Material | 6784009 | 14254738 | 17707751
MCR019573 | HPR148 | 2021-03-01 | Equipment | 1515661 | 3184746 | 3418290
MCR019574 | HPR148 | 2021-03-01 | Subcontract | 11983543 | 25180136 | 24434690
MCR019575 | HPR148 | 2021-03-01 | Overhead | 2093136 | 4398153 | 6195334
MCR019576 | HPR148 | 2021-04-01 | Labor | 1896460 | 3951457 | 4499513
MCR019577 | HPR148 | 2021-04-01 | Material | 4523718 | 9425600 | 9072826
MCR019578 | HPR148 | 2021-04-01 | Equipment | 1010674 | 2105836 | 2204461
MCR019579 | HPR148 | 2021-04-01 | Subcontract | 7990875 | 16649754 | 16740150
MCR019580 | HPR148 | 2021-04-01 | Overhead | 1395747 | 2908172 | 6154323
MCR019581 | HPR148 | 2021-05-01 | Labor | 1010106 | 6122253 | 5262292
MCR019582 | HPR148 | 2021-05-01 | Material | 2409455 | 14603704 | 14946029
MCR019583 | HPR148 | 2021-05-01 | Equipment | 538312 | 3262711 | 3417205
MCR019584 | HPR148 | 2021-05-01 | Subcontract | 4256156 | 25796563 | 25714808
MCR019585 | HPR148 | 2021-05-01 | Overhead | 743412 | 4505823 | 5938118
MCR019586 | HPR148 | 2021-06-01 | Labor | 264113 | 4781177 | 5646157
MCR019587 | HPR148 | 2021-06-01 | Material | 630002 | 11404770 | 12450415
MCR019588 | HPR148 | 2021-06-01 | Equipment | 140753 | 2548016 | 2865255
MCR019589 | HPR148 | 2021-06-01 | Subcontract | 1112860 | 20145840 | 17080143
MCR019590 | HPR148 | 2021-06-01 | Overhead | 194381 | 3518825 | 5885945
MCR019591 | HPR148 | 2021-07-01 | Labor | 0 | 3128544 | 3558607
MCR019592 | HPR148 | 2021-07-01 | Material | 0 | 7462665 | 7675874
MCR019593 | HPR148 | 2021-07-01 | Equipment | 0 | 1667284 | 1768405
MCR019594 | HPR148 | 2021-07-01 | Subcontract | 0 | 13182349 | 14773785
MCR019595 | HPR148 | 2021-07-01 | Overhead | 0 | 2302529 | 6362357
MCR019596 | HPR148 | 2021-08-01 | Labor | 0 | 1408976 | 1308180
MCR019597 | HPR148 | 2021-08-01 | Material | 0 | 3360899 | 3861466
MCR019598 | HPR148 | 2021-08-01 | Equipment | 0 | 750881 | 650508
MCR019599 | HPR148 | 2021-08-01 | Subcontract | 0 | 5936825 | 5447495
MCR019600 | HPR148 | 2021-08-01 | Overhead | 0 | 1036971 | 6610738
MCR019601 | HPR148 | 2021-09-01 | Labor | 0 | 3790867 | 3911145
MCR019602 | HPR148 | 2021-09-01 | Material | 0 | 9042537 | 8725074
MCR019603 | HPR148 | 2021-09-01 | Equipment | 0 | 2020254 | 1897276
MCR019604 | HPR148 | 2021-09-01 | Subcontract | 0 | 15973097 | 15997335
MCR019605 | HPR148 | 2021-09-01 | Overhead | 0 | 2789982 | 5856228
MCR019606 | HPR148 | 2021-10-01 | Labor | 0 | 1718172 | 1720222
MCR019607 | HPR148 | 2021-10-01 | Material | 0 | 4098437 | 5222691
MCR019608 | HPR148 | 2021-10-01 | Equipment | 0 | 915659 | 1266140
MCR019609 | HPR148 | 2021-10-01 | Subcontract | 0 | 7239643 | 7442162
MCR019610 | HPR148 | 2021-10-01 | Overhead | 0 | 1264531 | 5667423
MCR019611 | HPR148 | 2021-11-01 | Labor | 0 | 772251 | 853576
MCR019612 | HPR148 | 2021-11-01 | Material | 0 | 1842087 | 1893978
MCR019613 | HPR148 | 2021-11-01 | Equipment | 0 | 411553 | 383638
MCR019614 | HPR148 | 2021-11-01 | Subcontract | 0 | 3253935 | 2419923
MCR019615 | HPR148 | 2021-11-01 | Overhead | 0 | 568357 | 5589629
MCR019616 | HPR148 | 2021-12-01 | Labor | 0 | 173358 | 165622
MCR019617 | HPR148 | 2021-12-01 | Material | 0 | 413519 | 476764
MCR019618 | HPR148 | 2021-12-01 | Equipment | 0 | 92387 | 107176
MCR019619 | HPR148 | 2021-12-01 | Subcontract | 0 | 730456 | 745296
MCR019620 | HPR148 | 2021-12-01 | Overhead | 0 | 127587 | 6512232
MCR019621 | HPR149 | 2017-03-01 | Labor | 8245069 | 6211934 | 6886286
MCR019622 | HPR149 | 2017-03-01 | Material | 31380493 | 23642440 | 23066466
MCR019623 | HPR149 | 2017-03-01 | Equipment | 16374756 | 12336937 | 12300404
MCR019624 | HPR149 | 2017-03-01 | Subcontract | 17916234 | 13498306 | 13450304
MCR019625 | HPR149 | 2017-03-01 | Overhead | 6991331 | 5267352 | 29171103
MCR019626 | HPR149 | 2017-04-01 | Labor | 22760648 | 14314110 | 15178471
MCR019627 | HPR149 | 2017-04-01 | Material | 86626363 | 54479084 | 53948613
MCR019628 | HPR149 | 2017-04-01 | Equipment | 45202780 | 28427905 | 30574622
MCR019629 | HPR149 | 2017-04-01 | Subcontract | 49458056 | 31104037 | 28235775
MCR019630 | HPR149 | 2017-04-01 | Overhead | 19299682 | 12137518 | 29685985
MCR019631 | HPR149 | 2017-05-01 | Labor | 34388269 | 18513507 | 22364374
MCR019632 | HPR149 | 2017-05-01 | Material | 130880750 | 70461867 | 77793000
MCR019633 | HPR149 | 2017-05-01 | Equipment | 68295304 | 36767933 | 39270858
MCR019634 | HPR149 | 2017-05-01 | Subcontract | 74724452 | 40229174 | 40351399
MCR019635 | HPR149 | 2017-05-01 | Overhead | 29159217 | 15698358 | 30793469
MCR019636 | HPR149 | 2017-06-01 | Labor | 43232305 | 25038481 | 26204549
MCR019637 | HPR149 | 2017-06-01 | Material | 164540894 | 95295728 | 87750356
MCR019638 | HPR149 | 2017-06-01 | Equipment | 85859611 | 49726569 | 46213124
MCR019639 | HPR149 | 2017-06-01 | Subcontract | 93942219 | 54407704 | 58847471
MCR019640 | HPR149 | 2017-06-01 | Overhead | 36658436 | 21231149 | 30592830
MCR019641 | HPR149 | 2017-07-01 | Labor | 49405582 | 18105196 | 17554836
MCR019642 | HPR149 | 2017-07-01 | Material | 188036205 | 68907850 | 68125173
MCR019643 | HPR149 | 2017-07-01 | Equipment | 98119774 | 35957026 | 41705373
MCR019644 | HPR149 | 2017-07-01 | Subcontract | 107356524 | 39341930 | 46367798
MCR019645 | HPR149 | 2017-07-01 | Overhead | 41893009 | 15352135 | 28360580
MCR019646 | HPR149 | 2017-08-01 | Labor | 53031083 | 21740822 | 26623123
MCR019647 | HPR149 | 2017-08-01 | Material | 201834755 | 82744937 | 101371831
MCR019648 | HPR149 | 2017-08-01 | Equipment | 105320040 | 43177400 | 37780894
MCR019649 | HPR149 | 2017-08-01 | Subcontract | 115234605 | 47242013 | 36595144
MCR019650 | HPR149 | 2017-08-01 | Overhead | 44967219 | 18434930 | 29241803
MCR019651 | HPR149 | 2017-09-01 | Labor | 54244236 | 37298645 | 41005937
MCR019652 | HPR149 | 2017-09-01 | Material | 206451980 | 141957556 | 125419357
MCR019653 | HPR149 | 2017-09-01 | Equipment | 107729369 | 74075327 | 77999295
MCR019654 | HPR149 | 2017-09-01 | Subcontract | 117870741 | 81048592 | 83859663
MCR019655 | HPR149 | 2017-09-01 | Overhead | 45995901 | 31627043 | 27263736
MCR019656 | HPR149 | 2017-10-01 | Labor | 53196072 | 33884022 | 37700098
MCR019657 | HPR149 | 2017-10-01 | Material | 202462699 | 128961600 | 127663561
MCR019658 | HPR149 | 2017-10-01 | Equipment | 105647710 | 67293866 | 70022586
MCR019659 | HPR149 | 2017-10-01 | Subcontract | 115593120 | 73628741 | 77672516
MCR019660 | HPR149 | 2017-10-01 | Overhead | 45107120 | 28731645 | 29515953
MCR019661 | HPR149 | 2017-11-01 | Labor | 50057768 | 36719058 | 40648362
MCR019662 | HPR149 | 2017-11-01 | Material | 190518405 | 139751666 | 145374347
MCR019663 | HPR149 | 2017-11-01 | Equipment | 99415019 | 72924264 | 73684596
MCR019664 | HPR149 | 2017-11-01 | Subcontract | 108773700 | 79789172 | 68046372
MCR019665 | HPR149 | 2017-11-01 | Overhead | 42446024 | 31135588 | 31121765
MCR019666 | HPR149 | 2017-12-01 | Labor | 45027496 | 67345509 | 78596976
MCR019667 | HPR149 | 2017-12-01 | Material | 171373336 | 256315044 | 266824878
MCR019668 | HPR149 | 2017-12-01 | Equipment | 89424870 | 133748574 | 137715684
MCR019669 | HPR149 | 2017-12-01 | Subcontract | 97843103 | 146339329 | 151454687
MCR019670 | HPR149 | 2017-12-01 | Overhead | 38180651 | 57105005 | 31082295
MCR019671 | HPR149 | 2018-01-01 | Labor | 38341443 | 47667054 | 54111131
MCR019672 | HPR149 | 2018-01-01 | Material | 145926416 | 181419418 | 164344907
MCR019673 | HPR149 | 2018-01-01 | Equipment | 76146330 | 94667047 | 103775002
MCR019674 | HPR149 | 2018-01-01 | Subcontract | 83314555 | 103578766 | 119136990
MCR019675 | HPR149 | 2018-01-01 | Overhead | 32511274 | 40418840 | 29143855
MCR019676 | HPR149 | 2018-02-01 | Labor | 30293146 | 32961223 | 38769967
MCR019677 | HPR149 | 2018-02-01 | Material | 115294832 | 125449453 | 132800120
MCR019678 | HPR149 | 2018-02-01 | Equipment | 60162366 | 65461181 | 65882055
MCR019679 | HPR149 | 2018-02-01 | Subcontract | 65825900 | 71623532 | 65310178
MCR019680 | HPR149 | 2018-02-01 | Overhead | 25686795 | 27949166 | 30891364
MCR019681 | HPR149 | 2018-03-01 | Labor | 21272060 | 31370848 | 35814731
MCR019682 | HPR149 | 2018-03-01 | Material | 80960840 | 119396533 | 135834580
MCR019683 | HPR149 | 2018-03-01 | Equipment | 42246435 | 62302687 | 61874182
MCR019684 | HPR149 | 2018-03-01 | Subcontract | 46223409 | 68167706 | 56566583
MCR019685 | HPR149 | 2018-03-01 | Overhead | 18037448 | 26600622 | 30405158
MCR019686 | HPR149 | 2018-04-01 | Labor | 11858826 | 32085136 | 29750154
MCR019687 | HPR149 | 2018-04-01 | Material | 45134346 | 122115094 | 118151078
MCR019688 | HPR149 | 2018-04-01 | Equipment | 23551698 | 63721268 | 66980455
MCR019689 | HPR149 | 2018-04-01 | Subcontract | 25768795 | 69719829 | 77567398
MCR019690 | HPR149 | 2018-04-01 | Overhead | 10055582 | 27206296 | 29099305
MCR019691 | HPR149 | 2018-05-01 | Labor | 3218476 | 34360535 | 59157573
MCR019692 | HPR149 | 2018-05-01 | Material | 12249427 | 130775195 | 169888360
MCR019693 | HPR149 | 2018-05-01 | Equipment | 6391913 | 68240223 | 68937230
MCR019694 | HPR149 | 2018-05-01 | Subcontract | 6993631 | 74664187 | 81786585
MCR019695 | HPR149 | 2018-05-01 | Overhead | 2729077 | 29135700 | 31746109
MCR019696 | HPR149 | 2018-06-01 | Labor | 0 | 22052592 | 47506778
MCR019697 | HPR149 | 2018-06-01 | Material | 0 | 83931524 | 130885644
MCR019698 | HPR149 | 2018-06-01 | Equipment | 0 | 43796577 | 43950778
MCR019699 | HPR149 | 2018-06-01 | Subcontract | 0 | 47919477 | 48650968
MCR019700 | HPR149 | 2018-06-01 | Overhead | 0 | 18699293 | 31389400
MCR019701 | HPR149 | 2018-07-01 | Labor | 0 | 20709156 | 20600371
MCR019702 | HPR149 | 2018-07-01 | Material | 0 | 78818444 | 84375396
MCR019703 | HPR149 | 2018-07-01 | Equipment | 0 | 41128505 | 41711966
MCR019704 | HPR149 | 2018-07-01 | Subcontract | 0 | 45000239 | 45639756
MCR019705 | HPR149 | 2018-07-01 | Overhead | 0 | 17560138 | 25952413
MCR019706 | HPR149 | 2018-08-01 | Labor | 0 | 6407221 | 7601295
MCR019707 | HPR149 | 2018-08-01 | Material | 0 | 24385697 | 24480135
MCR019708 | HPR149 | 2018-08-01 | Equipment | 0 | 12724779 | 16824258
MCR019709 | HPR149 | 2018-08-01 | Subcontract | 0 | 13922657 | 12581064
MCR019710 | HPR149 | 2018-08-01 | Overhead | 0 | 5432944 | 28327745
MCR019711 | HPR149 | 2018-09-01 | Labor | 0 | 10272718 | 10832579
MCR019712 | HPR149 | 2018-09-01 | Material | 0 | 39097664 | 41580329
MCR019713 | HPR149 | 2018-09-01 | Equipment | 0 | 20401677 | 21538645
MCR019714 | HPR149 | 2018-09-01 | Subcontract | 0 | 22322240 | 20179653
MCR019715 | HPR149 | 2018-09-01 | Overhead | 0 | 8710656 | 31610569
MCR019716 | HPR149 | 2018-10-01 | Labor | 0 | 1514712 | 2526260
MCR019717 | HPR149 | 2018-10-01 | Material | 0 | 5764948 | 6012136
MCR019718 | HPR149 | 2018-10-01 | Equipment | 0 | 3008226 | 5553518
MCR019719 | HPR149 | 2018-10-01 | Subcontract | 0 | 3291413 | 4295369
MCR019720 | HPR149 | 2018-10-01 | Overhead | 0 | 1284386 | 29396747
MCR019721 | HPR150 | 2018-06-01 | Labor | 5989013 | 2915550 | 3496894
MCR019722 | HPR150 | 2018-06-01 | Material | 22995392 | 11194533 | 9584283
MCR019723 | HPR150 | 2018-06-01 | Equipment | 11350974 | 5525840 | 5697720
MCR019724 | HPR150 | 2018-06-01 | Subcontract | 13018485 | 6337612 | 6716725
MCR019725 | HPR150 | 2018-06-01 | Overhead | 4963814 | 2416466 | 24133813
MCR019726 | HPR150 | 2018-07-01 | Labor | 16778930 | 8740068 | 10201466
MCR019727 | HPR150 | 2018-07-01 | Material | 64424313 | 33558332 | 32058754
MCR019728 | HPR150 | 2018-07-01 | Equipment | 31801098 | 16565047 | 16090814
MCR019729 | HPR150 | 2018-07-01 | Subcontract | 36472828 | 18998530 | 21723262
MCR019730 | HPR150 | 2018-07-01 | Overhead | 13906714 | 7243944 | 25894772
MCR019731 | HPR150 | 2018-08-01 | Labor | 25823064 | 7455610 | 6677902
MCR019732 | HPR150 | 2018-08-01 | Material | 99150134 | 28626529 | 31670119
MCR019733 | HPR150 | 2018-08-01 | Equipment | 48942441 | 14130613 | 15435135
MCR019734 | HPR150 | 2018-08-01 | Subcontract | 56132314 | 16206466 | 14436239
MCR019735 | HPR150 | 2018-08-01 | Overhead | 21402674 | 6179359 | 24940554
MCR019736 | HPR150 | 2018-09-01 | Labor | 33172254 | 18963493 | 22919558
MCR019737 | HPR150 | 2018-09-01 | Material | 127368054 | 72812152 | 78076730
MCR019738 | HPR150 | 2018-09-01 | Equipment | 62871357 | 35941499 | 38314926
MCR019739 | HPR150 | 2018-09-01 | Subcontract | 72107453 | 41221473 | 44284197
MCR019740 | HPR150 | 2018-09-01 | Overhead | 27493830 | 15717324 | 26673447
MCR019741 | HPR150 | 2018-10-01 | Labor | 38880604 | 22047554 | 23174791
MCR019742 | HPR150 | 2018-10-01 | Material | 149285813 | 84653700 | 84972592
MCR019743 | HPR150 | 2018-10-01 | Equipment | 73690390 | 41786718 | 38785908
MCR019744 | HPR150 | 2018-10-01 | Subcontract | 84515853 | 47925382 | 47632125
MCR019745 | HPR150 | 2018-10-01 | Overhead | 32225025 | 18273455 | 23846033
MCR019746 | HPR150 | 2018-11-01 | Labor | 43005996 | 31933030 | 36619677
MCR019747 | HPR150 | 2018-11-01 | Material | 165125653 | 122609936 | 125945782
MCR019748 | HPR150 | 2018-11-01 | Equipment | 81509244 | 60522657 | 62429938
MCR019749 | HPR150 | 2018-11-01 | Subcontract | 93483333 | 69413718 | 68432840
MCR019750 | HPR150 | 2018-11-01 | Overhead | 35644233 | 26466737 | 25760116
MCR019751 | HPR150 | 2018-12-01 | Labor | 45610735 | 37002225 | 40246995
MCR019752 | HPR150 | 2018-12-01 | Material | 175126799 | 142073598 | 147777390
MCR019753 | HPR150 | 2018-12-01 | Equipment | 86446005 | 70130301 | 69355296
MCR019754 | HPR150 | 2018-12-01 | Subcontract | 99145328 | 80432770 | 75639742
MCR019755 | HPR150 | 2018-12-01 | Overhead | 37803093 | 30668188 | 23686356
MCR019756 | HPR150 | 2019-01-01 | Labor | 46762375 | 34482132 | 38132048
MCR019757 | HPR150 | 2019-01-01 | Material | 179548628 | 132397458 | 120513302
MCR019758 | HPR150 | 2019-01-01 | Equipment | 88628707 | 65353969 | 67847905
MCR019759 | HPR150 | 2019-01-01 | Subcontract | 101648678 | 74954772 | 92115059
MCR019760 | HPR150 | 2019-01-01 | Overhead | 38757595 | 28579483 | 23375474
MCR019761 | HPR150 | 2019-02-01 | Labor | 46534799 | 49455502 | 62079520
MCR019762 | HPR150 | 2019-02-01 | Material | 178674831 | 189889151 | 199039234
MCR019763 | HPR150 | 2019-02-01 | Equipment | 88197383 | 93732990 | 100422776
MCR019764 | HPR150 | 2019-02-01 | Subcontract | 101153991 | 107502805 | 108799794
MCR019765 | HPR150 | 2019-02-01 | Overhead | 38568976 | 40989714 | 26776891
MCR019766 | HPR150 | 2019-03-01 | Labor | 45009684 | 44508572 | 50479670
MCR019767 | HPR150 | 2019-03-01 | Material | 172819003 | 170894935 | 184837106
MCR019768 | HPR150 | 2019-03-01 | Equipment | 85306832 | 84357075 | 95061212
MCR019769 | HPR150 | 2019-03-01 | Subcontract | 97838805 | 96749524 | 92249221
MCR019770 | HPR150 | 2019-03-01 | Overhead | 37304930 | 36889598 | 22468960
MCR019771 | HPR150 | 2019-04-01 | Labor | 42278515 | 53517210 | 53580585
MCR019772 | HPR150 | 2019-04-01 | Material | 162332417 | 205484466 | 219324110
MCR019773 | HPR150 | 2019-04-01 | Equipment | 80130449 | 101431142 | 104257464
MCR019774 | HPR150 | 2019-04-01 | Subcontract | 91901986 | 116331851 | 127243250
MCR019775 | HPR150 | 2019-04-01 | Overhead | 35041282 | 44356138 | 22623485
MCR019776 | HPR150 | 2019-05-01 | Labor | 38445512 | 62804164 | 67241287
MCR019777 | HPR150 | 2019-05-01 | Material | 147615234 | 241142618 | 237535207
MCR019778 | HPR150 | 2019-05-01 | Equipment | 72865760 | 119032702 | 123808189
MCR019779 | HPR150 | 2019-05-01 | Subcontract | 83570081 | 136519162 | 137935702
MCR019780 | HPR150 | 2019-05-01 | Overhead | 31864412 | 52053352 | 23286040
MCR019781 | HPR150 | 2019-06-01 | Labor | 33632054 | 47395871 | 51051101
MCR019782 | HPR150 | 2019-06-01 | Material | 129133501 | 181981000 | 214910602
MCR019783 | HPR150 | 2019-06-01 | Equipment | 63742816 | 89829373 | 87080891
MCR019784 | HPR150 | 2019-06-01 | Subcontract | 73106934 | 103025727 | 108324269
MCR019785 | HPR150 | 2019-06-01 | Overhead | 27874922 | 39282650 | 24493280
MCR019786 | HPR150 | 2019-07-01 | Labor | 27983837 | 12330625 | 19175789
MCR019787 | HPR150 | 2019-07-01 | Material | 107446628 | 47344619 | 30395215
MCR019788 | HPR150 | 2019-07-01 | Equipment | 53037752 | 23370228 | 23779988
MCR019789 | HPR150 | 2019-07-01 | Subcontract | 60829246 | 26803424 | 26336035
MCR019790 | HPR150 | 2019-07-01 | Overhead | 23193566 | 10219870 | 24986896
MCR019791 | HPR150 | 2019-08-01 | Labor | 21683500 | 15186146 | 16995586
MCR019792 | HPR150 | 2019-08-01 | Material | 83255881 | 58308665 | 56381765
MCR019793 | HPR150 | 2019-08-01 | Equipment | 41096727 | 28782295 | 31230323
MCR019794 | HPR150 | 2019-08-01 | Subcontract | 47134029 | 33010548 | 36611210
MCR019795 | HPR150 | 2019-08-01 | Overhead | 17971720 | 12586582 | 24936224
MCR019796 | HPR150 | 2019-09-01 | Labor | 14975984 | 23287900 | 29117463
MCR019797 | HPR150 | 2019-09-01 | Material | 57501730 | 89416129 | 89808438
MCR019798 | HPR150 | 2019-09-01 | Equipment | 28383976 | 44137546 | 42867179
MCR019799 | HPR150 | 2019-09-01 | Subcontract | 32553715 | 50621558 | 47462734
MCR019800 | HPR150 | 2019-09-01 | Overhead | 12412397 | 19301479 | 24397182
MCR019801 | HPR150 | 2019-10-01 | Labor | 8231616 | 21346161 | 22116742
MCR019802 | HPR150 | 2019-10-01 | Material | 31606082 | 81960636 | 83954655
MCR019803 | HPR150 | 2019-10-01 | Equipment | 15601379 | 40457369 | 45885952
MCR019804 | HPR150 | 2019-10-01 | Subcontract | 17893294 | 46400746 | 46986331
MCR019805 | HPR150 | 2019-10-01 | Overhead | 6822529 | 17692127 | 24582657
MCR019806 | HPR150 | 2019-11-01 | Labor | 2209110 | 15503259 | 17940740
MCR019807 | HPR150 | 2019-11-01 | Material | 8482088 | 59526252 | 72198821
MCR019808 | HPR150 | 2019-11-01 | Equipment | 4186924 | 29383319 | 24469237
MCR019809 | HPR150 | 2019-11-01 | Subcontract | 4802003 | 33699866 | 35808313
MCR019810 | HPR150 | 2019-11-01 | Overhead | 1830954 | 12849412 | 27724456
MCR019811 | HPR150 | 2019-12-01 | Labor | 0 | 10369592 | 12219954
MCR019812 | HPR150 | 2019-12-01 | Material | 0 | 39815046 | 34727040
MCR019813 | HPR150 | 2019-12-01 | Equipment | 0 | 19653484 | 22905970
MCR019814 | HPR150 | 2019-12-01 | Subcontract | 0 | 22540672 | 21003401
MCR019815 | HPR150 | 2019-12-01 | Overhead | 0 | 8594526 | 26134031
MCR019816 | HPR150 | 2020-01-01 | Labor | 0 | 8164969 | 8350893
MCR019817 | HPR150 | 2020-01-01 | Material | 0 | 31350184 | 30686910
MCR019818 | HPR150 | 2020-01-01 | Equipment | 0 | 15475062 | 16083413
MCR019819 | HPR150 | 2020-01-01 | Subcontract | 0 | 17748422 | 20581613
MCR019820 | HPR150 | 2020-01-01 | Overhead | 0 | 6767291 | 22257231
MCR019821 | HPR150 | 2020-02-01 | Labor | 0 | 8365144 | 10349757
MCR019822 | HPR150 | 2020-02-01 | Material | 0 | 32118773 | 39759012
MCR019823 | HPR150 | 2020-02-01 | Equipment | 0 | 15854453 | 16330828
MCR019824 | HPR150 | 2020-02-01 | Subcontract | 0 | 18183547 | 18503548
MCR019825 | HPR150 | 2020-02-01 | Overhead | 0 | 6933199 | 26056341
MCR019826 | HPR150 | 2020-03-01 | Labor | 0 | 1232804 | 1203876
MCR019827 | HPR150 | 2020-03-01 | Material | 0 | 4733470 | 4647704
MCR019828 | HPR150 | 2020-03-01 | Equipment | 0 | 2336533 | 3429008
MCR019829 | HPR150 | 2020-03-01 | Subcontract | 0 | 2679781 | 2350242
MCR019830 | HPR150 | 2020-03-01 | Overhead | 0 | 1021773 | 24784175
MCR019831 | HPR151 | 2017-03-01 | Labor | 11634667 | 8490881 | 8355089
MCR019832 | HPR151 | 2017-03-01 | Material | 29667166 | 21650846 | 20350577
MCR019833 | HPR151 | 2017-03-01 | Equipment | 5694730 | 4155966 | 3680998
MCR019834 | HPR151 | 2017-03-01 | Subcontract | 33960646 | 24784191 | 24804761
MCR019835 | HPR151 | 2017-03-01 | Overhead | 8735084 | 6374790 | 44055377
MCR019836 | HPR151 | 2017-04-01 | Labor | 32595898 | 22812920 | 17286573
MCR019837 | HPR151 | 2017-04-01 | Material | 83116079 | 58170523 | 53947513
MCR019838 | HPR151 | 2017-04-01 | Equipment | 15954461 | 11166062 | 11209698
MCR019839 | HPR151 | 2017-04-01 | Subcontract | 95144772 | 66589054 | 61423046
MCR019840 | HPR151 | 2017-04-01 | Overhead | 24472371 | 17127500 | 42992108
MCR019841 | HPR151 | 2017-05-01 | Labor | 50165652 | 89061288 | 95973296
MCR019842 | HPR151 | 2017-05-01 | Material | 127917086 | 227096827 | 264004280
MCR019843 | HPR151 | 2017-05-01 | Equipment | 24554192 | 43592136 | 42338950
MCR019844 | HPR151 | 2017-05-01 | Subcontract | 146429452 | 259962644 | 222302271
MCR019845 | HPR151 | 2017-05-01 | Overhead | 37663403 | 66865496 | 44279803
MCR019846 | HPR151 | 2017-06-01 | Labor | 64442692 | 50839494 | 44812820
MCR019847 | HPR151 | 2017-06-01 | Material | 164322021 | 129635311 | 117805534
MCR019848 | HPR151 | 2017-06-01 | Equipment | 31542263 | 24884012 | 25129259
MCR019849 | HPR151 | 2017-06-01 | Subcontract | 188102967 | 148396341 | 145601413
MCR019850 | HPR151 | 2017-06-01 | Overhead | 48382329 | 38169311 | 43133996
MCR019851 | HPR151 | 2017-07-01 | Labor | 75532124 | 43400460 | 44675887
MCR019852 | HPR151 | 2017-07-01 | Material | 192598894 | 110666563 | 119070292
MCR019853 | HPR151 | 2017-07-01 | Equipment | 36970121 | 21242885 | 21109496
MCR019854 | HPR151 | 2017-07-01 | Subcontract | 220472115 | 126682405 | 109240250
MCR019855 | HPR151 | 2017-07-01 | Overhead | 56708061 | 32584227 | 41016641
MCR019856 | HPR151 | 2017-08-01 | Labor | 83546394 | 74407075 | 75191629
MCR019857 | HPR151 | 2017-08-01 | Material | 213034431 | 189730139 | 182463389
MCR019858 | HPR151 | 2017-08-01 | Equipment | 40892803 | 36419452 | 40233439
MCR019859 | HPR151 | 2017-08-01 | Subcontract | 243865116 | 217188190 | 195232638
MCR019860 | HPR151 | 2017-08-01 | Overhead | 62725020 | 55863396 | 43295959
MCR019861 | HPR151 | 2017-09-01 | Labor | 88606538 | 52162531 | 52899562
MCR019862 | HPR151 | 2017-09-01 | Material | 225937262 | 133008914 | 137727348
MCR019863 | HPR151 | 2017-09-01 | Equipment | 43369553 | 25531588 | 22868976
MCR019864 | HPR151 | 2017-09-01 | Subcontract | 258635266 | 152258178 | 134006125
MCR019865 | HPR151 | 2017-09-01 | Overhead | 66524079 | 39162621 | 44142449
MCR019866 | HPR151 | 2017-10-01 | Labor | 90843792 | 83111789 | 83885687
MCR019867 | HPR151 | 2017-10-01 | Material | 231642021 | 211926235 | 230336364
MCR019868 | HPR151 | 2017-10-01 | Equipment | 44464604 | 40680081 | 42057492
MCR019869 | HPR151 | 2017-10-01 | Subcontract | 265165626 | 242596540 | 212132272
MCR019870 | HPR151 | 2017-10-01 | Overhead | 68203765 | 62398727 | 46240351
MCR019871 | HPR151 | 2017-11-01 | Labor | 90401688 | 48848238 | 47793909
MCR019872 | HPR151 | 2017-11-01 | Material | 230514703 | 124557819 | 129974187
MCR019873 | HPR151 | 2017-11-01 | Equipment | 44248211 | 23909367 | 19812596
MCR019874 | HPR151 | 2017-11-01 | Subcontract | 263875161 | 142584026 | 131152901
MCR019875 | HPR151 | 2017-11-01 | Overhead | 67871842 | 36674314 | 45773641
MCR019876 | HPR151 | 2017-12-01 | Labor | 87438894 | 56791975 | 63920244
MCR019877 | HPR151 | 2017-12-01 | Material | 222959893 | 144813504 | 150033940
MCR019878 | HPR151 | 2017-12-01 | Equipment | 42798035 | 27797526 | 30719160
MCR019879 | HPR151 | 2017-12-01 | Subcontract | 255227007 | 165771146 | 148935421
MCR019880 | HPR151 | 2017-12-01 | Overhead | 65647434 | 42638318 | 41872861
MCR019881 | HPR151 | 2018-01-01 | Labor | 82133138 | 68097342 | 63783388
MCR019882 | HPR151 | 2018-01-01 | Material | 209430779 | 173640991 | 177367161
MCR019883 | HPR151 | 2018-01-01 | Equipment | 40201068 | 33331076 | 30928735
MCR019884 | HPR151 | 2018-01-01 | Subcontract | 239739938 | 198770594 | 200450019
MCR019885 | HPR151 | 2018-01-01 | Overhead | 61663975 | 51126170 | 42602014
MCR019886 | HPR151 | 2018-02-01 | Labor | 74686884 | 118572337 | 112133467
MCR019887 | HPR151 | 2018-02-01 | Material | 190443622 | 302346867 | 344394491
MCR019888 | HPR151 | 2018-02-01 | Equipment | 36556408 | 58036679 | 57605354
MCR019889 | HPR151 | 2018-02-01 | Subcontract | 218004929 | 346102991 | 296051433
MCR019890 | HPR151 | 2018-02-01 | Overhead | 56073471 | 89021822 | 42852513
MCR019891 | HPR151 | 2018-03-01 | Labor | 65335931 | 93469259 | 92490284
MCR019892 | HPR151 | 2018-03-01 | Material | 166599686 | 238336683 | 188689424
MCR019893 | HPR151 | 2018-03-01 | Equipment | 31979470 | 45749671 | 54407396
MCR019894 | HPR151 | 2018-03-01 | Subcontract | 190710260 | 272829150 | 241830974
MCR019895 | HPR151 | 2018-03-01 | Overhead | 49052956 | 70174915 | 43171810
MCR019896 | HPR151 | 2018-04-01 | Labor | 54363318 | 60181018 | 116424912
MCR019897 | HPR151 | 2018-04-01 | Material | 138620686 | 153455204 | 227679254
MCR019898 | HPR151 | 2018-04-01 | Equipment | 26608790 | 29456335 | 22797094
MCR019899 | HPR151 | 2018-04-01 | Subcontract | 158682095 | 175663487 | 181942412
MCR019900 | HPR151 | 2018-04-01 | Overhead | 40814930 | 45182746 | 41001624
MCR019901 | HPR151 | 2018-05-01 | Labor | 42123852 | 70931940 | 123793006
MCR019902 | HPR151 | 2018-05-01 | Material | 107411350 | 180868913 | 267715541
MCR019903 | HPR151 | 2018-05-01 | Equipment | 20618034 | 34718505 | 39065295
MCR019904 | HPR151 | 2018-05-01 | Subcontract | 122956093 | 207044552 | 169759043
MCR019905 | HPR151 | 2018-05-01 | Overhead | 31625775 | 53254331 | 40738643
MCR019906 | HPR151 | 2018-06-01 | Labor | 29093373 | 55075409 | 58595107
MCR019907 | HPR151 | 2018-06-01 | Material | 74185011 | 140436445 | 150243222
MCR019908 | HPR151 | 2018-06-01 | Equipment | 14240107 | 26957332 | 23177254
MCR019909 | HPR151 | 2018-06-01 | Subcontract | 84921185 | 160760632 | 151817622
MCR019910 | HPR151 | 2018-06-01 | Overhead | 21842743 | 41349554 | 41436541
MCR019911 | HPR151 | 2018-07-01 | Labor | 15991302 | 16880653 | 14219975
MCR019912 | HPR151 | 2018-07-01 | Material | 40776121 | 43043873 | 45325670
MCR019913 | HPR151 | 2018-07-01 | Equipment | 7827138 | 8262442 | 10001359
MCR019914 | HPR151 | 2018-07-01 | Subcontract | 46677307 | 49273252 | 38271181
MCR019915 | HPR151 | 2018-07-01 | Overhead | 12005961 | 12673669 | 43192110
MCR019916 | HPR151 | 2018-08-01 | Labor | 4291568 | 14427284 | 14515798
MCR019917 | HPR151 | 2018-08-01 | Material | 10943041 | 36788043 | 35710789
MCR019918 | HPR151 | 2018-08-01 | Equipment | 2100560 | 7061611 | 6220962
MCR019919 | HPR151 | 2018-08-01 | Subcontract | 12526736 | 42112067 | 41858550
MCR019920 | HPR151 | 2018-08-01 | Overhead | 3222026 | 10831727 | 46108340
MCR019921 | HPR151 | 2018-09-01 | Labor | 0 | 11489118 | 12909183
MCR019922 | HPR151 | 2018-09-01 | Material | 0 | 29296030 | 31069988
MCR019923 | HPR151 | 2018-09-01 | Equipment | 0 | 5623489 | 6394797
MCR019924 | HPR151 | 2018-09-01 | Subcontract | 0 | 33535798 | 29865965
MCR019925 | HPR151 | 2018-09-01 | Overhead | 0 | 8625808 | 42582868
MCR019926 | HPR151 | 2018-10-01 | Labor | 0 | 4176694 | 4356386
MCR019927 | HPR151 | 2018-10-01 | Material | 0 | 10650126 | 12999703
MCR019928 | HPR151 | 2018-10-01 | Equipment | 0 | 2044334 | 2109138
MCR019929 | HPR151 | 2018-10-01 | Subcontract | 0 | 12191430 | 10337879
MCR019930 | HPR151 | 2018-10-01 | Overhead | 0 | 3135781 | 41744105
MCR019931 | HPR152 | 2017-10-01 | Labor | 23179928 | 9331656 | 9801718
MCR019932 | HPR152 | 2017-10-01 | Material | 65720678 | 26457492 | 26684510
MCR019933 | HPR152 | 2017-10-01 | Equipment | 11113513 | 4474021 | 4436462
MCR019934 | HPR152 | 2017-10-01 | Subcontract | 135778800 | 54661130 | 55784787
MCR019935 | HPR152 | 2017-10-01 | Overhead | 20798823 | 8373083 | 65081670
MCR019936 | HPR152 | 2017-11-01 | Labor | 61061750 | 35071018 | 32502718
MCR019937 | HPR152 | 2017-11-01 | Material | 173124764 | 99434781 | 107776784
MCR019938 | HPR152 | 2017-11-01 | Equipment | 29275784 | 16814643 | 18584751
MCR019939 | HPR152 | 2017-11-01 | Subcontract | 357675444 | 205432075 | 190232033
MCR019940 | HPR152 | 2017-11-01 | Overhead | 54789321 | 31468428 | 62729274
MCR019941 | HPR152 | 2017-12-01 | Labor | 86730131 | 61698589 | 73125691
MCR019942 | HPR152 | 2017-12-01 | Material | 245900802 | 174930354 | 173563577
MCR019943 | HPR152 | 2017-12-01 | Equipment | 41582375 | 29581113 | 29056400
MCR019944 | HPR152 | 2017-12-01 | Subcontract | 508030606 | 361405791 | 354683117
MCR019945 | HPR152 | 2017-12-01 | Overhead | 77820975 | 55360742 | 60353407
MCR019946 | HPR152 | 2018-01-01 | Labor | 100923188 | 55901062 | 71409495
MCR019947 | HPR152 | 2018-01-01 | Material | 286141537 | 158492971 | 161115808
MCR019948 | HPR152 | 2018-01-01 | Equipment | 48387173 | 26801515 | 29222261
MCR019949 | HPR152 | 2018-01-01 | Subcontract | 591167891 | 327446188 | 284073773
MCR019950 | HPR152 | 2018-01-01 | Overhead | 90556083 | 50158753 | 59579463
MCR019951 | HPR152 | 2018-02-01 | Labor | 104485021 | 111203822 | 110793463
MCR019952 | HPR152 | 2018-02-01 | Material | 296240191 | 315289608 | 252912058
MCR019953 | HPR152 | 2018-02-01 | Equipment | 50094878 | 53316177 | 59659906
MCR019954 | HPR152 | 2018-02-01 | Subcontract | 612031692 | 651387753 | 684622869
MCR019955 | HPR152 | 2018-02-01 | Overhead | 93752035 | 99780662 | 65233615
MCR019956 | HPR152 | 2018-03-01 | Labor | 98406758 | 71083545 | 63196933
MCR019957 | HPR152 | 2018-03-01 | Material | 279006853 | 201538965 | 228949523
MCR019958 | HPR152 | 2018-03-01 | Equipment | 47180682 | 34080689 | 33014894
MCR019959 | HPR152 | 2018-03-01 | Subcontract | 576427647 | 416379133 | 396904526
MCR019960 | HPR152 | 2018-03-01 | Overhead | 88298148 | 63781650 | 60937989
MCR019961 | HPR152 | 2018-04-01 | Labor | 83897558 | 78419562 | 85459218
MCR019962 | HPR152 | 2018-04-01 | Material | 237869777 | 222338340 | 229616177
MCR019963 | HPR152 | 2018-04-01 | Equipment | 40224310 | 37597910 | 31626423
MCR019964 | HPR152 | 2018-04-01 | Subcontract | 491438523 | 459350603 | 449789087
MCR019965 | HPR152 | 2018-04-01 | Overhead | 75279372 | 70364091 | 58365188
MCR019966 | HPR152 | 2018-05-01 | Labor | 62523931 | 78744525 | 86319767
MCR019967 | HPR152 | 2018-05-01 | Material | 177270399 | 223259689 | 232102381
MCR019968 | HPR152 | 2018-05-01 | Equipment | 29976820 | 37753712 | 38803343
MCR019969 | HPR152 | 2018-05-01 | Subcontract | 366240319 | 461254108 | 443034091
MCR019970 | HPR152 | 2018-05-01 | Overhead | 56101303 | 70655673 | 60247622
MCR019971 | HPR152 | 2018-06-01 | Labor | 36547212 | 78498557 | 100073473
MCR019972 | HPR152 | 2018-06-01 | Material | 103620146 | 222562308 | 244839720
MCR019973 | HPR152 | 2018-06-01 | Equipment | 17522398 | 37635783 | 39009554
MCR019974 | HPR152 | 2018-06-01 | Subcontract | 214079032 | 459813321 | 516240704
MCR019975 | HPR152 | 2018-06-01 | Overhead | 32792983 | 70434971 | 55436294
MCR019976 | HPR152 | 2018-07-01 | Labor | 10278673 | 42922153 | 25491399
MCR019977 | HPR152 | 2018-07-01 | Material | 29142512 | 121694638 | 108251230
MCR019978 | HPR152 | 2018-07-01 | Equipment | 4928064 | 20578835 | 23406210
MCR019979 | HPR152 | 2018-07-01 | Subcontract | 60208377 | 251420898 | 198696784
MCR019980 | HPR152 | 2018-07-01 | Overhead | 9222819 | 38513072 | 58138284
MCR019981 | HPR152 | 2018-08-01 | Labor | 0 | 21179736 | 26740299
MCR019982 | HPR152 | 2018-08-01 | Material | 0 | 60049652 | 68787867
MCR019983 | HPR152 | 2018-08-01 | Equipment | 0 | 10154530 | 9923851
MCR019984 | HPR152 | 2018-08-01 | Subcontract | 0 | 124062472 | 130357977
MCR019985 | HPR152 | 2018-08-01 | Overhead | 0 | 19004096 | 58087984
MCR019986 | HPR152 | 2018-09-01 | Labor | 0 | 18799834 | 17899303
MCR019987 | HPR152 | 2018-09-01 | Material | 0 | 53302054 | 48304626
MCR019988 | HPR152 | 2018-09-01 | Equipment | 0 | 9013496 | 11494479
MCR019989 | HPR152 | 2018-09-01 | Subcontract | 0 | 110121947 | 97852159
MCR019990 | HPR152 | 2018-09-01 | Overhead | 0 | 16868663 | 61570966
MCR019991 | HPR152 | 2018-10-01 | Labor | 0 | 5180091 | 5951091
MCR019992 | HPR152 | 2018-10-01 | Material | 0 | 14686805 | 17847958
MCR019993 | HPR152 | 2018-10-01 | Equipment | 0 | 2483572 | 2026351
MCR019994 | HPR152 | 2018-10-01 | Subcontract | 0 | 30342912 | 34526183
MCR019995 | HPR152 | 2018-10-01 | Overhead | 0 | 4647978 | 58635882
MCR019996 | HPR153 | 2016-07-01 | Labor | 11583756 | 3832121 | 4199384
MCR019997 | HPR153 | 2016-07-01 | Material | 25362067 | 8390241 | 9538634
MCR019998 | HPR153 | 2016-07-01 | Equipment | 5149563 | 1703571 | 1798884
MCR019999 | HPR153 | 2016-07-01 | Subcontract | 58536773 | 19365048 | 23843735
MCR020000 | HPR153 | 2016-07-01 | Overhead | 7843550 | 2594792 | 30867628
MCR020001 | HPR153 | 2016-08-01 | Labor | 31532626 | 17039583 | 16272519
MCR020002 | HPR153 | 2016-08-01 | Material | 69039142 | 37307334 | 34756386
MCR020003 | HPR153 | 2016-08-01 | Equipment | 14017840 | 7574953 | 9182519
MCR020004 | HPR153 | 2016-08-01 | Subcontract | 159345396 | 86106978 | 83557060
MCR020005 | HPR153 | 2016-08-01 | Overhead | 21351256 | 11537780 | 28070043
MCR020006 | HPR153 | 2016-09-01 | Labor | 46794882 | 47352394 | 55729411
MCR020007 | HPR153 | 2016-09-01 | Material | 102455106 | 103675751 | 106521346
MCR020008 | HPR153 | 2016-09-01 | Equipment | 20802681 | 21050523 | 22922477
MCR020009 | HPR153 | 2016-09-01 | Subcontract | 236470919 | 239288222 | 239614680
MCR020010 | HPR153 | 2016-09-01 | Overhead | 31685580 | 32063080 | 29677386
MCR020011 | HPR153 | 2016-10-01 | Labor | 57572342 | 24547567 | 23965271
MCR020012 | HPR153 | 2016-10-01 | Material | 126051827 | 53745698 | 55742844
MCR020013 | HPR153 | 2016-10-01 | Equipment | 25593804 | 10912629 | 10329219
MCR020014 | HPR153 | 2016-10-01 | Subcontract | 290933196 | 124047449 | 131484289
MCR020015 | HPR153 | 2016-10-01 | Overhead | 38983174 | 16621559 | 30050018
MCR020016 | HPR153 | 2016-11-01 | Labor | 64086614 | 43686652 | 38930247
MCR020017 | HPR153 | 2016-11-01 | Material | 140314508 | 95649789 | 110321391
MCR020018 | HPR153 | 2016-11-01 | Equipment | 28489726 | 19420916 | 20046564
MCR020019 | HPR153 | 2016-11-01 | Subcontract | 323852094 | 220763946 | 202288822
MCR020020 | HPR153 | 2016-11-01 | Overhead | 43394094 | 29580946 | 30127869
MCR020021 | HPR153 | 2016-12-01 | Labor | 66584034 | 47906422 | 58453928
MCR020022 | HPR153 | 2016-12-01 | Material | 145782486 | 104888769 | 87929279
MCR020023 | HPR153 | 2016-12-01 | Equipment | 29599955 | 21296817 | 23353244
MCR020024 | HPR153 | 2016-12-01 | Subcontract | 336472431 | 242087922 | 283790911
MCR020025 | HPR153 | 2016-12-01 | Overhead | 45085138 | 32438222 | 30291810
MCR020026 | HPR153 | 2017-01-01 | Labor | 65342729 | 91918552 | 106437068
MCR020027 | HPR153 | 2017-01-01 | Material | 143064711 | 201251175 | 202916887
MCR020028 | HPR153 | 2017-01-01 | Equipment | 29048133 | 40862424 | 44688992
MCR020029 | HPR153 | 2017-01-01 | Subcontract | 330199686 | 464496619 | 495289635
MCR020030 | HPR153 | 2017-01-01 | Overhead | 44244630 | 62239554 | 28974543
MCR020031 | HPR153 | 2017-02-01 | Labor | 60683242 | 73783023 | 68439913
MCR020032 | HPR153 | 2017-02-01 | Material | 132862992 | 161544321 | 164193715
MCR020033 | HPR153 | 2017-02-01 | Equipment | 26976756 | 32800269 | 31141514
MCR020034 | HPR153 | 2017-02-01 | Subcontract | 306653667 | 372851444 | 375023796
MCR020035 | HPR153 | 2017-02-01 | Overhead | 41089616 | 49959691 | 28705467
MCR020036 | HPR153 | 2017-03-01 | Labor | 52985530 | 41612870 | 52774461
MCR020037 | HPR153 | 2017-03-01 | Material | 116009227 | 91109344 | 86668708
MCR020038 | HPR153 | 2017-03-01 | Equipment | 23554736 | 18499016 | 17452475
MCR020039 | HPR153 | 2017-03-01 | Subcontract | 267754430 | 210284398 | 209306648
MCR020040 | HPR153 | 2017-03-01 | Overhead | 35877368 | 28176754 | 30158925
MCR020041 | HPR153 | 2017-04-01 | Labor | 42718658 | 18184925 | 23483591
MCR020042 | HPR153 | 2017-04-01 | Material | 93530413 | 39815005 | 43751198
MCR020043 | HPR153 | 2017-04-01 | Equipment | 18990594 | 8084115 | 8222537
MCR020044 | HPR153 | 2017-04-01 | Subcontract | 215872334 | 91894794 | 103078721
MCR020045 | HPR153 | 2017-04-01 | Overhead | 28925502 | 12313310 | 27644765
MCR020046 | HPR153 | 2017-05-01 | Labor | 30499717 | 43687161 | 46381066
MCR020047 | HPR153 | 2017-05-01 | Material | 66777638 | 95650903 | 103744786
MCR020048 | HPR153 | 2017-05-01 | Equipment | 13558660 | 19421143 | 18154082
MCR020049 | HPR153 | 2017-05-01 | Subcontract | 154125745 | 220766518 | 276112257
MCR020050 | HPR153 | 2017-05-01 | Overhead | 20651857 | 29581291 | 29494646
MCR020051 | HPR153 | 2017-06-01 | Labor | 17238406 | 22176787 | 29002829
MCR020052 | HPR153 | 2017-06-01 | Material | 37742646 | 48554991 | 40645593
MCR020053 | HPR153 | 2017-06-01 | Equipment | 7663339 | 9858698 | 11733490
MCR020054 | HPR153 | 2017-06-01 | Subcontract | 87111698 | 112067069 | 148497355
MCR020055 | HPR153 | 2017-06-01 | Overhead | 11672406 | 15016265 | 29115780
MCR020056 | HPR153 | 2017-07-01 | Labor | 4728552 | 22060549 | 22268936
MCR020057 | HPR153 | 2017-07-01 | Material | 10352934 | 48300493 | 45052911
MCR020058 | HPR153 | 2017-07-01 | Equipment | 2102080 | 9807025 | 10544080
MCR020059 | HPR153 | 2017-07-01 | Subcontract | 23895029 | 111479675 | 160356310
MCR020060 | HPR153 | 2017-07-01 | Overhead | 3201780 | 14937558 | 28073295
MCR020061 | HPR153 | 2017-08-01 | Labor | 0 | 18605673 | 24504065
MCR020062 | HPR153 | 2017-08-01 | Material | 0 | 40736210 | 44218528
MCR020063 | HPR153 | 2017-08-01 | Equipment | 0 | 8271158 | 8251296
MCR020064 | HPR153 | 2017-08-01 | Subcontract | 0 | 94020976 | 132034804
MCR020065 | HPR153 | 2017-08-01 | Overhead | 0 | 12598205 | 27846826
MCR020066 | HPR153 | 2017-09-01 | Labor | 0 | 28241642 | 28491922
MCR020067 | HPR153 | 2017-09-01 | Material | 0 | 61833694 | 68842107
MCR020068 | HPR153 | 2017-09-01 | Equipment | 0 | 12554832 | 15393256
MCR020069 | HPR153 | 2017-09-01 | Subcontract | 0 | 142714902 | 209967377
MCR020070 | HPR153 | 2017-09-01 | Overhead | 0 | 19122877 | 27737299
MCR020071 | HPR153 | 2017-10-01 | Labor | 0 | 5783815 | 9063593
MCR020072 | HPR153 | 2017-10-01 | Material | 0 | 12663380 | 11752810
MCR020073 | HPR153 | 2017-10-01 | Equipment | 0 | 2571197 | 2529341
MCR020074 | HPR153 | 2017-10-01 | Subcontract | 0 | 29227641 | 80359713
MCR020075 | HPR153 | 2017-10-01 | Overhead | 0 | 3916316 | 26346215
MCR020076 | HPR153 | 2017-11-01 | Labor | 0 | 1931352 | 2416559
MCR020077 | HPR153 | 2017-11-01 | Material | 0 | 4228601 | 4238074
MCR020078 | HPR153 | 2017-11-01 | Equipment | 0 | 858583 | 890451
MCR020079 | HPR153 | 2017-11-01 | Subcontract | 0 | 9759797 | 83167211
MCR020080 | HPR153 | 2017-11-01 | Overhead | 0 | 1307750 | 26807079
MCR020081 | HPR154 | 2017-04-01 | Labor | 2367467 | 1837535 | 2167621
MCR020082 | HPR154 | 2017-04-01 | Material | 6801588 | 5279127 | 5292635
MCR020083 | HPR154 | 2017-04-01 | Equipment | 2260170 | 1754255 | 1890036
MCR020084 | HPR154 | 2017-04-01 | Subcontract | 5399338 | 4190755 | 4137382
MCR020085 | HPR154 | 2017-04-01 | Overhead | 1575176 | 1222590 | 8904270
MCR020086 | HPR154 | 2017-05-01 | Labor | 6701543 | 4169549 | 5008766
MCR020087 | HPR154 | 2017-05-01 | Material | 19253124 | 11978860 | 13651557
MCR020088 | HPR154 | 2017-05-01 | Equipment | 6397819 | 3980578 | 4123506
MCR020089 | HPR154 | 2017-05-01 | Subcontract | 15283803 | 9509238 | 10321748
MCR020090 | HPR154 | 2017-05-01 | Overhead | 4458822 | 2774178 | 8713885
MCR020091 | HPR154 | 2017-06-01 | Labor | 10444721 | 4251369 | 4485188
MCR020092 | HPR154 | 2017-06-01 | Material | 30007048 | 12213925 | 12690603
MCR020093 | HPR154 | 2017-06-01 | Equipment | 9971350 | 4058691 | 4498181
MCR020094 | HPR154 | 2017-06-01 | Subcontract | 23820644 | 9695840 | 10427244
MCR020095 | HPR154 | 2017-06-01 | Overhead | 6949317 | 2828617 | 8753915
MCR020096 | HPR154 | 2017-07-01 | Labor | 13611411 | 5669505 | 7018943
MCR020097 | HPR154 | 2017-07-01 | Material | 39104756 | 16288144 | 19188314
MCR020098 | HPR154 | 2017-07-01 | Equipment | 12994521 | 5412555 | 5426432
MCR020099 | HPR154 | 2017-07-01 | Subcontract | 31042722 | 12930098 | 13466454
MCR020100 | HPR154 | 2017-07-01 | Overhead | 9056251 | 3772163 | 9050927
MCR020101 | HPR154 | 2017-08-01 | Labor | 16216789 | 8068332 | 9504586
MCR020102 | HPR154 | 2017-08-01 | Material | 46589848 | 23179825 | 20671038
MCR020103 | HPR154 | 2017-08-01 | Equipment | 15481819 | 7702662 | 7473050
MCR020104 | HPR154 | 2017-08-01 | Subcontract | 36984650 | 18400955 | 17228066
MCR020105 | HPR154 | 2017-08-01 | Overhead | 10789720 | 5368204 | 9447332
MCR020106 | HPR154 | 2017-09-01 | Labor | 18276897 | 14659865 | 15604979
MCR020107 | HPR154 | 2017-09-01 | Material | 52508411 | 42116898 | 44516878
MCR020108 | HPR154 | 2017-09-01 | Equipment | 17448560 | 13995457 | 13538669
MCR020109 | HPR154 | 2017-09-01 | Subcontract | 41683012 | 33433866 | 38105839
MCR020110 | HPR154 | 2017-09-01 | Overhead | 12160397 | 9753832 | 9266624
MCR020111 | HPR154 | 2017-10-01 | Labor | 19808759 | 6624173 | 8154130
MCR020112 | HPR154 | 2017-10-01 | Material | 56909359 | 19030846 | 16967678
MCR020113 | HPR154 | 2017-10-01 | Equipment | 18910996 | 6323955 | 6908926
MCR020114 | HPR154 | 2017-10-01 | Subcontract | 45176639 | 15107351 | 17005763
MCR020115 | HPR154 | 2017-10-01 | Overhead | 13179610 | 4407344 | 9058277
MCR020116 | HPR154 | 2017-11-01 | Labor | 20830533 | 12064327 | 12840225
MCR020117 | HPR154 | 2017-11-01 | Material | 59844854 | 34660077 | 38487559
MCR020118 | HPR154 | 2017-11-01 | Equipment | 19886461 | 11517553 | 11688772
MCR020119 | HPR154 | 2017-11-01 | Subcontract | 47506937 | 27514380 | 30688451
MCR020120 | HPR154 | 2017-11-01 | Overhead | 13859440 | 8026910 | 9030057
MCR020121 | HPR154 | 2017-12-01 | Labor | 21361685 | 26869181 | 31679255
MCR020122 | HPR154 | 2017-12-01 | Material | 61370821 | 77193521 | 80128962
MCR020123 | HPR154 | 2017-12-01 | Equipment | 20393541 | 25651428 | 28120930
MCR020124 | HPR154 | 2017-12-01 | Subcontract | 48718302 | 61278915 | 70779299
MCR020125 | HPR154 | 2017-12-01 | Overhead | 14212838 | 17877209 | 8609500
MCR020126 | HPR154 | 2018-01-01 | Labor | 21423220 | 13824300 | 12806198
MCR020127 | HPR154 | 2018-01-01 | Material | 61547606 | 39716372 | 39130835
MCR020128 | HPR154 | 2018-01-01 | Equipment | 20452286 | 13197761 | 12651122
MCR020129 | HPR154 | 2018-01-01 | Subcontract | 48858641 | 31528244 | 29577863
MCR020130 | HPR154 | 2018-01-01 | Overhead | 14253780 | 9197895 | 8775086
MCR020131 | HPR154 | 2018-02-01 | Labor | 21037974 | 26394753 | 30388790
MCR020132 | HPR154 | 2018-02-01 | Material | 60440817 | 75830517 | 90465449
MCR020133 | HPR154 | 2018-02-01 | Equipment | 20084500 | 25198502 | 24951482
MCR020134 | HPR154 | 2018-02-01 | Subcontract | 47980033 | 60196915 | 66888019
MCR020135 | HPR154 | 2018-02-01 | Overhead | 13997459 | 17561552 | 7952392
MCR020136 | HPR154 | 2018-03-01 | Labor | 20231000 | 21552681 | 22596146
MCR020137 | HPR154 | 2018-03-01 | Material | 58122430 | 61919540 | 60015079
MCR020138 | HPR154 | 2018-03-01 | Equipment | 19314100 | 20575880 | 23603559
MCR020139 | HPR154 | 2018-03-01 | Subcontract | 46139616 | 49153895 | 59794351
MCR020140 | HPR154 | 2018-03-01 | Overhead | 13460545 | 14339916 | 9357270
MCR020141 | HPR154 | 2018-04-01 | Labor | 19030087 | 28366925 | 26349533
MCR020142 | HPR154 | 2018-04-01 | Material | 54672281 | 81496448 | 87953054
MCR020143 | HPR154 | 2018-04-01 | Equipment | 18167614 | 27081292 | 26601929
MCR020144 | HPR154 | 2018-04-01 | Subcontract | 43400768 | 64694729 | 71707967
MCR020145 | HPR154 | 2018-04-01 | Overhead | 12661527 | 18873722 | 9226036
MCR020146 | HPR154 | 2018-05-01 | Labor | 17466485 | 17746678 | 26338432
MCR020147 | HPR154 | 2018-05-01 | Material | 50180148 | 50985124 | 45877557
MCR020148 | HPR154 | 2018-05-01 | Equipment | 16674877 | 16942371 | 18215964
MCR020149 | HPR154 | 2018-05-01 | Subcontract | 39834755 | 40473773 | 42297906
MCR020150 | HPR154 | 2018-05-01 | Overhead | 11621196 | 11807620 | 8996981
MCR020151 | HPR154 | 2018-06-01 | Labor | 15575951 | 11499329 | 11425658
MCR020152 | HPR154 | 2018-06-01 | Material | 44748760 | 33036873 | 38312091
MCR020153 | HPR154 | 2018-06-01 | Equipment | 14870025 | 10978162 | 10586429
MCR020154 | HPR154 | 2018-06-01 | Subcontract | 35523129 | 26225824 | 27735791
MCR020155 | HPR154 | 2018-06-01 | Overhead | 10363343 | 7650993 | 9651149
MCR020156 | HPR154 | 2018-07-01 | Labor | 13400348 | 9327842 | 10311089
MCR020157 | HPR154 | 2018-07-01 | Material | 38498383 | 26798322 | 29668443
MCR020158 | HPR154 | 2018-07-01 | Equipment | 12793023 | 8905090 | 9556829
MCR020159 | HPR154 | 2018-07-01 | Subcontract | 30561362 | 21273445 | 20669782
MCR020160 | HPR154 | 2018-07-01 | Overhead | 8915822 | 6206210 | 9900043
MCR020161 | HPR154 | 2018-08-01 | Labor | 10990230 | 7394358 | 8838936
MCR020162 | HPR154 | 2018-08-01 | Material | 31574261 | 21243542 | 18036552
MCR020163 | HPR154 | 2018-08-01 | Equipment | 10492136 | 7059235 | 7424231
MCR020164 | HPR154 | 2018-08-01 | Subcontract | 25064752 | 16863866 | 19002269
MCR020165 | HPR154 | 2018-08-01 | Overhead | 7312267 | 4919781 | 8243413
MCR020166 | HPR154 | 2018-09-01 | Labor | 8409435 | 8253853 | 8486534
MCR020167 | HPR154 | 2018-09-01 | Material | 24159796 | 23712816 | 26545539
MCR020168 | HPR154 | 2018-09-01 | Equipment | 8028307 | 7879775 | 7802701
MCR020169 | HPR154 | 2018-09-01 | Subcontract | 19178890 | 18824062 | 23245759
MCR020170 | HPR154 | 2018-09-01 | Overhead | 5595155 | 5491639 | 9072750
MCR020171 | HPR154 | 2018-10-01 | Labor | 5744346 | 14349121 | 15896833
MCR020172 | HPR154 | 2018-10-01 | Material | 16503156 | 41224151 | 45332186
MCR020173 | HPR154 | 2018-10-01 | Equipment | 5484003 | 13698797 | 14693162
MCR020174 | HPR154 | 2018-10-01 | Subcontract | 13100782 | 32725172 | 30424177
MCR020175 | HPR154 | 2018-10-01 | Overhead | 3821958 | 9547081 | 9119483
MCR020176 | HPR154 | 2018-11-01 | Labor | 3127052 | 13266199 | 17470198
MCR020177 | HPR154 | 2018-11-01 | Material | 8983829 | 38112982 | 38406313
MCR020178 | HPR154 | 2018-11-01 | Equipment | 2985329 | 12664955 | 14619982
MCR020179 | HPR154 | 2018-11-01 | Subcontract | 7131677 | 30255418 | 32946095
MCR020180 | HPR154 | 2018-11-01 | Overhead | 2080561 | 8826567 | 9500633
MCR020181 | HPR154 | 2018-12-01 | Labor | 832654 | 4726244 | 3994954
MCR020182 | HPR154 | 2018-12-01 | Material | 2392163 | 13578212 | 15683168
MCR020183 | HPR154 | 2018-12-01 | Equipment | 794917 | 4512044 | 4067431
MCR020184 | HPR154 | 2018-12-01 | Subcontract | 1898983 | 10778860 | 11433795
MCR020185 | HPR154 | 2018-12-01 | Overhead | 554000 | 3144571 | 8725722
MCR020186 | HPR154 | 2019-01-01 | Labor | 0 | 8292346 | 8562635
MCR020187 | HPR154 | 2019-01-01 | Material | 0 | 23823405 | 20167744
MCR020188 | HPR154 | 2019-01-01 | Equipment | 0 | 7916524 | 7039178
MCR020189 | HPR154 | 2019-01-01 | Subcontract | 0 | 18911852 | 23086271
MCR020190 | HPR154 | 2019-01-01 | Overhead | 0 | 5517251 | 8731401
MCR020191 | HPR154 | 2019-02-01 | Labor | 0 | 7727697 | 9067177
MCR020192 | HPR154 | 2019-02-01 | Material | 0 | 22201202 | 26659369
MCR020193 | HPR154 | 2019-02-01 | Equipment | 0 | 7377466 | 9346371
MCR020194 | HPR154 | 2019-02-01 | Subcontract | 0 | 17624090 | 16720372
MCR020195 | HPR154 | 2019-02-01 | Overhead | 0 | 5141565 | 9398214
MCR020196 | HPR154 | 2019-03-01 | Labor | 0 | 6017514 | 6903091
MCR020197 | HPR154 | 2019-03-01 | Material | 0 | 17287953 | 17941314
MCR020198 | HPR154 | 2019-03-01 | Equipment | 0 | 5744791 | 5841910
MCR020199 | HPR154 | 2019-03-01 | Subcontract | 0 | 13723781 | 15671686
MCR020200 | HPR154 | 2019-03-01 | Overhead | 0 | 4003708 | 8980268
MCR020201 | HPR154 | 2019-04-01 | Labor | 0 | 3482552 | 4080224
MCR020202 | HPR154 | 2019-04-01 | Material | 0 | 10005161 | 9984072
MCR020203 | HPR154 | 2019-04-01 | Equipment | 0 | 3324718 | 3614768
MCR020204 | HPR154 | 2019-04-01 | Subcontract | 0 | 7942446 | 9382449
MCR020205 | HPR154 | 2019-04-01 | Overhead | 0 | 2317090 | 9429200
MCR020206 | HPR154 | 2019-05-01 | Labor | 0 | 452358 | 417208
MCR020207 | HPR154 | 2019-05-01 | Material | 0 | 1299597 | 2123492
MCR020208 | HPR154 | 2019-05-01 | Equipment | 0 | 431856 | 472939
MCR020209 | HPR154 | 2019-05-01 | Subcontract | 0 | 1031665 | 980922
MCR020210 | HPR154 | 2019-05-01 | Overhead | 0 | 300973 | 9060898
MCR020211 | HPR155 | 2016-06-01 | Labor | 19611229 | 11384882 | 11874365
MCR020212 | HPR155 | 2016-06-01 | Material | 55860600 | 32428683 | 30450174
MCR020213 | HPR155 | 2016-06-01 | Equipment | 9792125 | 5684610 | 5822401
MCR020214 | HPR155 | 2016-06-01 | Subcontract | 120739145 | 70092542 | 66096227
MCR020215 | HPR155 | 2016-06-01 | Overhead | 18556002 | 10772292 | 55303972
MCR020216 | HPR155 | 2016-07-01 | Labor | 51660899 | 24519345 | 28077466
MCR020217 | HPR155 | 2016-07-01 | Material | 147150844 | 69840874 | 72872744
MCR020218 | HPR155 | 2016-07-01 | Equipment | 25794916 | 12242807 | 14404274
MCR020219 | HPR155 | 2016-07-01 | Subcontract | 318057218 | 150956619 | 161483858
MCR020220 | HPR155 | 2016-07-01 | Overhead | 48881166 | 23200026 | 55957920
MCR020221 | HPR155 | 2016-08-01 | Labor | 73377467 | 32230876 | 34341831
MCR020222 | HPR155 | 2016-08-01 | Material | 209008289 | 91806390 | 92844441
MCR020223 | HPR155 | 2016-08-01 | Equipment | 36638262 | 16093269 | 16131373
MCR020224 | HPR155 | 2016-08-01 | Subcontract | 451758162 | 198433689 | 204409944
MCR020225 | HPR155 | 2016-08-01 | Overhead | 69429224 | 30496620 | 50168585
MCR020226 | HPR155 | 2016-09-01 | Labor | 85385411 | 49624527 | 56681794
MCR020227 | HPR155 | 2016-09-01 | Material | 243211704 | 141350444 | 142811869
MCR020228 | HPR155 | 2016-09-01 | Equipment | 42633975 | 24778130 | 23138615
MCR020229 | HPR155 | 2016-09-01 | Subcontract | 525686674 | 305520020 | 299689230
MCR020230 | HPR155 | 2016-09-01 | Overhead | 80791054 | 46954366 | 49238151
MCR020231 | HPR155 | 2016-10-01 | Labor | 88398877 | 50865110 | 52637041
MCR020232 | HPR155 | 2016-10-01 | Material | 251795257 | 144884120 | 162641952
MCR020233 | HPR155 | 2016-10-01 | Equipment | 44138635 | 25397568 | 31398659
MCR020234 | HPR155 | 2016-10-01 | Subcontract | 544239478 | 313157837 | 330760195
MCR020235 | HPR155 | 2016-10-01 | Overhead | 83642373 | 48128197 | 50306071
MCR020236 | HPR155 | 2016-11-01 | Labor | 83256402 | 59258477 | 64371232
MCR020237 | HPR155 | 2016-11-01 | Material | 237147437 | 168791776 | 161617686
MCR020238 | HPR155 | 2016-11-01 | Equipment | 41570935 | 29588479 | 31811569
MCR020239 | HPR155 | 2016-11-01 | Subcontract | 512579146 | 364832718 | 377703360
MCR020240 | HPR155 | 2016-11-01 | Overhead | 78776601 | 56069939 | 52186822
MCR020241 | HPR155 | 2016-12-01 | Labor | 70980987 | 75847740 | 81439675
MCR020242 | HPR155 | 2016-12-01 | Material | 202182159 | 216044612 | 211272018
MCR020243 | HPR155 | 2016-12-01 | Equipment | 35441670 | 37871699 | 36624683
MCR020244 | HPR155 | 2016-12-01 | Subcontract | 437003915 | 466966727 | 413627554
MCR020245 | HPR155 | 2016-12-01 | Overhead | 67161693 | 71766578 | 52718477
MCR020246 | HPR155 | 2017-01-01 | Labor | 52897968 | 96225882 | 112103093
MCR020247 | HPR155 | 2017-01-01 | Material | 150674510 | 274089690 | 289723499
MCR020248 | HPR155 | 2017-01-01 | Equipment | 26412599 | 48046754 | 57156240
MCR020249 | HPR155 | 2017-01-01 | Subcontract | 325673397 | 592427481 | 636605997
MCR020250 | HPR155 | 2017-01-01 | Overhead | 50051672 | 91048229 | 48818293
MCR020251 | HPR155 | 2017-02-01 | Labor | 30920533 | 62178529 | 68422841
MCR020252 | HPR155 | 2017-02-01 | Material | 88074009 | 177109247 | 151578893
MCR020253 | HPR155 | 2017-02-01 | Equipment | 15438998 | 31046496 | 31367032
MCR020254 | HPR155 | 2017-02-01 | Subcontract | 190366385 | 382810406 | 462389474
MCR020255 | HPR155 | 2017-02-01 | Overhead | 29256783 | 58832871 | 48295369
MCR020256 | HPR155 | 2017-03-01 | Labor | 8696205 | 39161072 | 40171846
MCR020257 | HPR155 | 2017-03-01 | Material | 24770259 | 111546352 | 144129776
MCR020258 | HPR155 | 2017-03-01 | Equipment | 4342121 | 19553600 | 17148693
MCR020259 | HPR155 | 2017-03-01 | Subcontract | 53539344 | 241100366 | 306145576
MCR020260 | HPR155 | 2017-03-01 | Overhead | 8228286 | 37053921 | 52509014
MCR020261 | HPR155 | 2017-04-01 | Labor | 0 | 25374512 | 30141846
MCR020262 | HPR155 | 2017-04-01 | Material | 0 | 72276729 | 70398424
MCR020263 | HPR155 | 2017-04-01 | Equipment | 0 | 12669802 | 14550656
MCR020264 | HPR155 | 2017-04-01 | Subcontract | 0 | 156221567 | 270579766
MCR020265 | HPR155 | 2017-04-01 | Overhead | 0 | 24009178 | 55246253
MCR020266 | HPR155 | 2017-05-01 | Labor | 0 | 19666769 | 21364690
MCR020267 | HPR155 | 2017-05-01 | Material | 0 | 56018801 | 57503847
MCR020268 | HPR155 | 2017-05-01 | Equipment | 0 | 9819857 | 9011367
MCR020269 | HPR155 | 2017-05-01 | Subcontract | 0 | 121081085 | 180213739
MCR020270 | HPR155 | 2017-05-01 | Overhead | 0 | 18608553 | 52994967
MCR020271 | HPR155 | 2017-06-01 | Labor | 0 | 15492181 | 18189795
MCR020272 | HPR155 | 2017-06-01 | Material | 0 | 44127910 | 49823884
MCR020273 | HPR155 | 2017-06-01 | Equipment | 0 | 7735434 | 9564572
MCR020274 | HPR155 | 2017-06-01 | Subcontract | 0 | 95379679 | 163374425
MCR020275 | HPR155 | 2017-06-01 | Overhead | 0 | 14658589 | 54847182
MCR020276 | HPR155 | 2017-07-01 | Labor | 0 | 3356076 | 4104406
MCR020277 | HPR155 | 2017-07-01 | Material | 0 | 9559443 | 7788226
MCR020278 | HPR155 | 2017-07-01 | Equipment | 0 | 1675730 | 2219997
MCR020279 | HPR155 | 2017-07-01 | Subcontract | 0 | 20662129 | 86083733
MCR020280 | HPR155 | 2017-07-01 | Overhead | 0 | 3175495 | 51598072
MCR020281 | HPR156 | 2020-09-01 | Labor | 15988251 | 11348733 | 13321058
MCR020282 | HPR156 | 2020-09-01 | Material | 56291979 | 39957006 | 38009629
MCR020283 | HPR156 | 2020-09-01 | Equipment | 15500890 | 11002796 | 10968438
MCR020284 | HPR156 | 2020-09-01 | Subcontract | 48752259 | 34605185 | 38688518
MCR020285 | HPR156 | 2020-09-01 | Overhead | 10888842 | 7729086 | 42267668
MCR020286 | HPR156 | 2020-10-01 | Labor | 43851801 | 24226374 | 27031228
MCR020287 | HPR156 | 2020-10-01 | Material | 154394921 | 85297045 | 82222278
MCR020288 | HPR156 | 2020-10-01 | Equipment | 42515092 | 23487895 | 23957920
MCR020289 | HPR156 | 2020-10-01 | Subcontract | 133715341 | 73872401 | 85638920
MCR020290 | HPR156 | 2020-10-01 | Overhead | 29865389 | 16499438 | 44121215
MCR020291 | HPR156 | 2020-11-01 | Labor | 65712116 | 30604603 | 33674811
MCR020292 | HPR156 | 2020-11-01 | Material | 231361463 | 107753731 | 104729123
MCR020293 | HPR156 | 2020-11-01 | Equipment | 63709052 | 29671700 | 27203446
MCR020294 | HPR156 | 2020-11-01 | Subcontract | 200373023 | 93321250 | 104593528
MCR020295 | HPR156 | 2020-11-01 | Overhead | 44753416 | 20843349 | 41835955
MCR020296 | HPR156 | 2020-12-01 | Labor | 81805114 | 57590656 | 55850966
MCR020297 | HPR156 | 2020-12-01 | Material | 288022242 | 202767148 | 220935491
MCR020298 | HPR156 | 2020-12-01 | Equipment | 79311496 | 55835153 | 64514837
MCR020299 | HPR156 | 2020-12-01 | Subcontract | 249444685 | 175608616 | 203506829
MCR020300 | HPR156 | 2020-12-01 | Overhead | 55713597 | 39222274 | 42767528
MCR020301 | HPR156 | 2021-01-01 | Labor | 92387646 | 74006136 | 82960800
MCR020302 | HPR156 | 2021-01-01 | Material | 325281579 | 260563331 | 218652172
MCR020303 | HPR156 | 2021-01-01 | Equipment | 89571446 | 71750249 | 68021134
MCR020304 | HPR156 | 2021-01-01 | Subcontract | 281713525 | 225663607 | 220561909
MCR020305 | HPR156 | 2021-01-01 | Overhead | 62920859 | 50402081 | 44962992
MCR020306 | HPR156 | 2021-02-01 | Labor | 97742155 | 65759005 | 67045174
MCR020307 | HPR156 | 2021-02-01 | Material | 344133917 | 231526552 | 272723258
MCR020308 | HPR156 | 2021-02-01 | Equipment | 94762737 | 63754511 | 70277139
MCR020309 | HPR156 | 2021-02-01 | Subcontract | 298040790 | 200516000 | 233614451
MCR020310 | HPR156 | 2021-02-01 | Overhead | 66567562 | 44785350 | 42640897
MCR020311 | HPR156 | 2021-03-01 | Labor | 98183126 | 49025900 | 50496042
MCR020312 | HPR156 | 2021-03-01 | Material | 345686505 | 172612064 | 181522926
MCR020313 | HPR156 | 2021-03-01 | Equipment | 95190266 | 47531472 | 41595789
MCR020314 | HPR156 | 2021-03-01 | Subcontract | 299385425 | 149492490 | 166599373
MCR020315 | HPR156 | 2021-03-01 | Overhead | 66867887 | 33389223 | 42405837
MCR020316 | HPR156 | 2021-04-01 | Labor | 94066328 | 66996271 | 80389130
MCR020317 | HPR156 | 2021-04-01 | Material | 331191942 | 235882761 | 244334134
MCR020318 | HPR156 | 2021-04-01 | Equipment | 91198958 | 64954063 | 76730939
MCR020319 | HPR156 | 2021-04-01 | Subcontract | 286832256 | 204288741 | 238861760
MCR020320 | HPR156 | 2021-04-01 | Overhead | 64064130 | 45627994 | 42825236
MCR020321 | HPR156 | 2021-05-01 | Labor | 85802732 | 122794570 | 123909335
MCR020322 | HPR156 | 2021-05-01 | Material | 302097191 | 432339317 | 454378989
MCR020323 | HPR156 | 2021-05-01 | Equipment | 83187257 | 119051494 | 108593069
MCR020324 | HPR156 | 2021-05-01 | Subcontract | 261634442 | 374432002 | 415330500
MCR020325 | HPR156 | 2021-05-01 | Overhead | 58436185 | 83629578 | 41322167
MCR020326 | HPR156 | 2021-06-01 | Labor | 73880853 | 129530010 | 139932544
MCR020327 | HPR156 | 2021-06-01 | Material | 260122233 | 456053685 | 555853793
MCR020328 | HPR156 | 2021-06-01 | Equipment | 71628786 | 125581622 | 133901727
MCR020329 | HPR156 | 2021-06-01 | Subcontract | 225281589 | 394970080 | 355554651
MCR020330 | HPR156 | 2021-06-01 | Overhead | 50316757 | 88216768 | 44070707
MCR020331 | HPR156 | 2021-07-01 | Labor | 58905859 | 34819226 | 44838521
MCR020332 | HPR156 | 2021-07-01 | Material | 207397761 | 122592722 | 113658071
MCR020333 | HPR156 | 2021-07-01 | Equipment | 57110266 | 33757852 | 34709705
MCR020334 | HPR156 | 2021-07-01 | Subcontract | 179619008 | 106172713 | 153643103
MCR020335 | HPR156 | 2021-07-01 | Overhead | 40117996 | 23713729 | 41960250
MCR020336 | HPR156 | 2021-08-01 | Labor | 41677392 | 54714144 | 57888058
MCR020337 | HPR156 | 2021-08-01 | Material | 146739185 | 192639428 | 215020498
MCR020338 | HPR156 | 2021-08-01 | Equipment | 40406964 | 53046324 | 51667527
MCR020339 | HPR156 | 2021-08-01 | Subcontract | 127085011 | 166837398 | 229368952
MCR020340 | HPR156 | 2021-08-01 | Overhead | 28384502 | 37263218 | 42105680
MCR020341 | HPR156 | 2021-09-01 | Labor | 23381207 | 48722193 | 50869687
MCR020342 | HPR156 | 2021-09-01 | Material | 82321352 | 171542761 | 204561090
MCR020343 | HPR156 | 2021-09-01 | Equipment | 22668491 | 47237022 | 57411777
MCR020344 | HPR156 | 2021-09-01 | Subcontract | 71295271 | 148566408 | 207596152
MCR020345 | HPR156 | 2021-09-01 | Overhead | 15923835 | 33182383 | 43895028
MCR020346 | HPR156 | 2021-10-01 | Labor | 6376861 | 58591838 | 65107303
MCR020347 | HPR156 | 2021-10-01 | Material | 22451869 | 206292144 | 229827130
MCR020348 | HPR156 | 2021-10-01 | Equipment | 6182478 | 56805816 | 49611718
MCR020349 | HPR156 | 2021-10-01 | Subcontract | 19444677 | 178661476 | 255535065
MCR020350 | HPR156 | 2021-10-01 | Overhead | 4342978 | 39904131 | 44490940
MCR020351 | HPR156 | 2021-11-01 | Labor | 0 | 27107352 | 32430569
MCR020352 | HPR156 | 2021-11-01 | Material | 0 | 95440492 | 134133690
MCR020353 | HPR156 | 2021-11-01 | Equipment | 0 | 26281054 | 30427274
MCR020354 | HPR156 | 2021-11-01 | Subcontract | 0 | 82657239 | 113642940
MCR020355 | HPR156 | 2021-11-01 | Overhead | 0 | 18461536 | 43491538
MCR020356 | HPR156 | 2021-12-01 | Labor | 0 | 13987306 | 14415136
MCR020357 | HPR156 | 2021-12-01 | Material | 0 | 49246984 | 67093023
MCR020358 | HPR156 | 2021-12-01 | Equipment | 0 | 13560939 | 13764365
MCR020359 | HPR156 | 2021-12-01 | Subcontract | 0 | 42650867 | 102613979
MCR020360 | HPR156 | 2021-12-01 | Overhead | 0 | 9526093 | 41100605
MCR020361 | HPR156 | 2022-01-01 | Labor | 0 | 7676470 | 11865532
MCR020362 | HPR156 | 2022-01-01 | Material | 0 | 27027579 | 30205489
MCR020363 | HPR156 | 2022-01-01 | Equipment | 0 | 7442473 | 6929981
MCR020364 | HPR156 | 2022-01-01 | Subcontract | 0 | 23407519 | 92326023
MCR020365 | HPR156 | 2022-01-01 | Overhead | 0 | 5228081 | 43834356
MCR020366 | HPR156 | 2022-02-01 | Labor | 0 | 2260654 | 1927229
MCR020367 | HPR156 | 2022-02-01 | Material | 0 | 7959389 | 7382289
MCR020368 | HPR156 | 2022-02-01 | Equipment | 0 | 2191744 | 3133883
MCR020369 | HPR156 | 2022-02-01 | Subcontract | 0 | 6893312 | 86361070
MCR020370 | HPR156 | 2022-02-01 | Overhead | 0 | 1539625 | 42010191
MCR020371 | HPR157 | 2019-10-01 | Labor | 13827630 | 5798947 | 5693587
MCR020372 | HPR157 | 2019-10-01 | Material | 38468880 | 16132843 | 16301301
MCR020373 | HPR157 | 2019-10-01 | Equipment | 8300964 | 3481207 | 3401277
MCR020374 | HPR157 | 2019-10-01 | Subcontract | 29927236 | 12550700 | 13140076
MCR020375 | HPR157 | 2019-10-01 | Overhead | 6457676 | 2708181 | 26427719
MCR020376 | HPR157 | 2019-11-01 | Labor | 37925757 | 25213682 | 28663619
MCR020377 | HPR157 | 2019-11-01 | Material | 105510586 | 70145216 | 65061570
MCR020378 | HPR157 | 2019-11-01 | Equipment | 22767482 | 15136206 | 14364946
MCR020379 | HPR157 | 2019-11-01 | Subcontract | 82082976 | 54570146 | 63518337
MCR020380 | HPR157 | 2019-11-01 | Overhead | 17711802 | 11775104 | 25878180
MCR020381 | HPR157 | 2019-12-01 | Labor | 56831912 | 41119832 | 42537518
MCR020382 | HPR157 | 2019-12-01 | Material | 158108074 | 114396600 | 138555741
MCR020383 | HPR157 | 2019-12-01 | Equipment | 34117172 | 24684941 | 25834092
MCR020384 | HPR157 | 2019-12-01 | Subcontract | 123001699 | 88995936 | 90252094
MCR020385 | HPR157 | 2019-12-01 | Overhead | 26541212 | 19203475 | 28330776
MCR020386 | HPR157 | 2020-01-01 | Labor | 70750135 | 46125674 | 43301905
MCR020387 | HPR157 | 2020-01-01 | Material | 196828984 | 128323001 | 106200939
MCR020388 | HPR157 | 2020-01-01 | Equipment | 42472519 | 27690034 | 29306470
MCR020389 | HPR157 | 2020-01-01 | Subcontract | 153125004 | 99830115 | 91828135
MCR020390 | HPR157 | 2020-01-01 | Overhead | 33041196 | 21541266 | 25653122
MCR020391 | HPR157 | 2020-02-01 | Labor | 79902564 | 44484920 | 54011058
MCR020392 | HPR157 | 2020-02-01 | Material | 222291315 | 123758374 | 133873105
MCR020393 | HPR157 | 2020-02-01 | Equipment | 47966880 | 26705061 | 25588930
MCR020394 | HPR157 | 2020-02-01 | Subcontract | 172933669 | 96279019 | 93858534
MCR020395 | HPR157 | 2020-02-01 | Overhead | 37315495 | 20775013 | 26931486
MCR020396 | HPR157 | 2020-03-01 | Labor | 84533475 | 73058809 | 103751156
MCR020397 | HPR157 | 2020-03-01 | Material | 235174648 | 203251784 | 218834289
MCR020398 | HPR157 | 2020-03-01 | Equipment | 50746895 | 43858456 | 46972260
MCR020399 | HPR157 | 2020-03-01 | Subcontract | 182956382 | 158121683 | 162938663
MCR020400 | HPR157 | 2020-03-01 | Overhead | 39478188 | 34119376 | 25618730
MCR020401 | HPR157 | 2020-04-01 | Labor | 84914855 | 74619570 | 116770796
MCR020402 | HPR157 | 2020-04-01 | Material | 236235657 | 207593869 | 267584952
MCR020403 | HPR157 | 2020-04-01 | Equipment | 50975844 | 44795408 | 45230296
MCR020404 | HPR157 | 2020-04-01 | Subcontract | 183781805 | 161499650 | 178758345
MCR020405 | HPR157 | 2020-04-01 | Overhead | 39656297 | 34848271 | 25624615
MCR020406 | HPR157 | 2020-05-01 | Labor | 81354392 | 102559976 | 116824561
MCR020407 | HPR157 | 2020-05-01 | Material | 226330345 | 285324909 | 262675228
MCR020408 | HPR157 | 2020-05-01 | Equipment | 48838437 | 61568512 | 70067805
MCR020409 | HPR157 | 2020-05-01 | Subcontract | 176075872 | 221971261 | 220427946
MCR020410 | HPR157 | 2020-05-01 | Overhead | 37993517 | 47896789 | 24500833
MCR020411 | HPR157 | 2020-06-01 | Labor | 74207522 | 109887294 | 101291908
MCR020412 | HPR157 | 2020-06-01 | Material | 206447540 | 305709728 | 351275319
MCR020413 | HPR157 | 2020-06-01 | Equipment | 44548049 | 65967227 | 61639959
MCR020414 | HPR157 | 2020-06-01 | Subcontract | 160607852 | 237829827 | 265862410
MCR020415 | HPR157 | 2020-06-01 | Overhead | 34655839 | 51318738 | 26908995
MCR020416 | HPR157 | 2020-07-01 | Labor | 63896742 | 53646609 | 57804987
MCR020417 | HPR157 | 2020-07-01 | Material | 177762642 | 149246467 | 129655449
MCR020418 | HPR157 | 2020-07-01 | Equipment | 38358310 | 32204980 | 31931107
MCR020419 | HPR157 | 2020-07-01 | Subcontract | 138292160 | 116107726 | 115177167
MCR020420 | HPR157 | 2020-07-01 | Overhead | 29840576 | 25053636 | 24773133
MCR020421 | HPR157 | 2020-08-01 | Labor | 50945439 | 42170664 | 43643001
MCR020422 | HPR157 | 2020-08-01 | Material | 141731730 | 117320043 | 135702859
MCR020423 | HPR157 | 2020-08-01 | Equipment | 30583421 | 25315773 | 26851798
MCR020424 | HPR157 | 2020-08-01 | Subcontract | 110261564 | 91270258 | 104790292
MCR020425 | HPR157 | 2020-08-01 | Overhead | 23792156 | 19694226 | 24623106
MCR020426 | HPR157 | 2020-09-01 | Labor | 36045192 | 45352791 | 50790828
MCR020427 | HPR157 | 2020-09-01 | Material | 100278800 | 126172816 | 119026342
MCR020428 | HPR157 | 2020-09-01 | Equipment | 21638547 | 27226058 | 29265568
MCR020429 | HPR157 | 2020-09-01 | Subcontract | 78012858 | 98157358 | 139200816
MCR020430 | HPR157 | 2020-09-01 | Overhead | 16833555 | 21180319 | 25616162
MCR020431 | HPR157 | 2020-10-01 | Labor | 20221517 | 17008269 | 14199154
MCR020432 | HPR157 | 2020-10-01 | Material | 56256864 | 47317512 | 50451747
MCR020433 | HPR157 | 2020-10-01 | Equipment | 12139324 | 10210356 | 8069122
MCR020434 | HPR157 | 2020-10-01 | Subcontract | 43765569 | 36811114 | 90566770
MCR020435 | HPR157 | 2020-10-01 | Overhead | 9443701 | 7943074 | 24180975
MCR020436 | HPR157 | 2020-11-01 | Labor | 5515104 | 31965581 | 32903593
MCR020437 | HPR157 | 2020-11-01 | Material | 15343185 | 88929199 | 87005826
MCR020438 | HPR157 | 2020-11-01 | Equipment | 3310812 | 19189486 | 21920455
MCR020439 | HPR157 | 2020-11-01 | Subcontract | 11936379 | 69183327 | 86240580
MCR020440 | HPR157 | 2020-11-01 | Overhead | 2575623 | 14928325 | 25304979
MCR020441 | HPR157 | 2020-12-01 | Labor | 0 | 27698243 | 29223675
MCR020442 | HPR157 | 2020-12-01 | Material | 0 | 77057339 | 74777250
MCR020443 | HPR157 | 2020-12-01 | Equipment | 0 | 16627731 | 14710031
MCR020444 | HPR157 | 2020-12-01 | Subcontract | 0 | 59947499 | 106694283
MCR020445 | HPR157 | 2020-12-01 | Overhead | 0 | 12935425 | 26973190
MCR020446 | HPR157 | 2021-01-01 | Labor | 0 | 14783358 | 13850892
MCR020447 | HPR157 | 2021-01-01 | Material | 0 | 41127742 | 56126030
MCR020448 | HPR157 | 2021-01-01 | Equipment | 0 | 8874703 | 10263784
MCR020449 | HPR157 | 2021-01-01 | Subcontract | 0 | 31995723 | 41550498
MCR020450 | HPR157 | 2021-01-01 | Overhead | 0 | 6904013 | 25359058
MCR020451 | HPR157 | 2021-02-01 | Labor | 0 | 5378018 | 6304540
MCR020452 | HPR157 | 2021-02-01 | Material | 0 | 14961807 | 10211089
MCR020453 | HPR157 | 2021-02-01 | Equipment | 0 | 3228517 | 3479627
MCR020454 | HPR157 | 2021-02-01 | Subcontract | 0 | 11639682 | 37019589
MCR020455 | HPR157 | 2021-02-01 | Overhead | 0 | 2511602 | 26548715
MCR020456 | HPR158 | 2016-08-01 | Labor | 5939754 | 3050985 | 3379228
MCR020457 | HPR158 | 2016-08-01 | Material | 17498126 | 8988001 | 8173191
MCR020458 | HPR158 | 2016-08-01 | Equipment | 2763399 | 1419434 | 1617524
MCR020459 | HPR158 | 2016-08-01 | Subcontract | 33016477 | 16959079 | 17479809
MCR020460 | HPR158 | 2016-08-01 | Overhead | 5182021 | 2661771 | 21768588
MCR020461 | HPR158 | 2016-09-01 | Labor | 16488678 | 8876876 | 8551344
MCR020462 | HPR158 | 2016-09-01 | Material | 48574565 | 26150696 | 30356482
MCR020463 | HPR158 | 2016-09-01 | Equipment | 7671159 | 4129860 | 4215390
MCR020464 | HPR158 | 2016-09-01 | Subcontract | 91653297 | 49342644 | 49879987
MCR020465 | HPR158 | 2016-09-01 | Overhead | 14385222 | 7744456 | 22680577
MCR020466 | HPR158 | 2016-10-01 | Labor | 25088082 | 20355587 | 20119508
MCR020467 | HPR158 | 2016-10-01 | Material | 73907846 | 59966226 | 59497135
MCR020468 | HPR158 | 2016-10-01 | Equipment | 11671929 | 9470192 | 10991395
MCR020469 | HPR158 | 2016-10-01 | Subcontract | 139453598 | 113147742 | 125359439
MCR020470 | HPR158 | 2016-10-01 | Overhead | 21887603 | 17758831 | 24128825
MCR020471 | HPR158 | 2016-11-01 | Labor | 31803183 | 13590530 | 15811564
MCR020472 | HPR158 | 2016-11-01 | Material | 93690094 | 40036813 | 36972113
MCR020473 | HPR158 | 2016-11-01 | Equipment | 14796049 | 6322831 | 6184101
MCR020474 | HPR158 | 2016-11-01 | Subcontract | 176779885 | 75543773 | 76932182
MCR020475 | HPR158 | 2016-11-01 | Overhead | 27746060 | 11856791 | 21717730
MCR020476 | HPR158 | 2016-12-01 | Labor | 36704055 | 22246531 | 20993699
MCR020477 | HPR158 | 2016-12-01 | Material | 108127744 | 65536823 | 70104300
MCR020478 | HPR158 | 2016-12-01 | Equipment | 17076121 | 10349931 | 10069761
MCR020479 | HPR158 | 2016-12-01 | Subcontract | 204021678 | 123658666 | 135911079
MCR020480 | HPR158 | 2016-12-01 | Overhead | 32021730 | 19408548 | 23589481
MCR020481 | HPR158 | 2017-01-01 | Labor | 39866529 | 21829619 | 25402161
MCR020482 | HPR158 | 2017-01-01 | Material | 117444185 | 64308629 | 69665432
MCR020483 | HPR158 | 2017-01-01 | Equipment | 18547424 | 10155968 | 10076533
MCR020484 | HPR158 | 2017-01-01 | Subcontract | 221600478 | 121341240 | 129570883
MCR020485 | HPR158 | 2017-01-01 | Overhead | 34780768 | 19044822 | 23223180
MCR020486 | HPR158 | 2017-02-01 | Labor | 41373358 | 18469564 | 19736269
MCR020487 | HPR158 | 2017-02-01 | Material | 121883204 | 54410127 | 53452255
MCR020488 | HPR158 | 2017-02-01 | Equipment | 19248458 | 8592743 | 9904761
MCR020489 | HPR158 | 2017-02-01 | Subcontract | 229976277 | 102664174 | 119986817
MCR020490 | HPR158 | 2017-02-01 | Overhead | 36095372 | 16113408 | 22290232
MCR020491 | HPR158 | 2017-03-01 | Labor | 41315790 | 47885604 | 57875328
MCR020492 | HPR158 | 2017-03-01 | Material | 121713613 | 141067854 | 142314391
MCR020493 | HPR158 | 2017-03-01 | Equipment | 19221675 | 22278202 | 22615409
MCR020494 | HPR158 | 2017-03-01 | Subcontract | 229656282 | 266174983 | 294305592
MCR020495 | HPR158 | 2017-03-01 | Overhead | 36045148 | 41776852 | 23700330
MCR020496 | HPR158 | 2017-04-01 | Labor | 39795743 | 28672629 | 26833257
MCR020497 | HPR158 | 2017-04-01 | Material | 117235653 | 84467688 | 75784513
MCR020498 | HPR158 | 2017-04-01 | Equipment | 18514491 | 13339596 | 15213536
MCR020499 | HPR158 | 2017-04-01 | Subcontract | 221207009 | 159378517 | 139978148
MCR020500 | HPR158 | 2017-04-01 | Overhead | 34719012 | 25014871 | 22790983
MCR020501 | HPR158 | 2017-05-01 | Labor | 36928933 | 34134412 | 35213080
MCR020502 | HPR158 | 2017-05-01 | Material | 108790220 | 100557743 | 124642023
MCR020503 | HPR158 | 2017-05-01 | Equipment | 17180743 | 15880625 | 16036331
MCR020504 | HPR158 | 2017-05-01 | Subcontract | 205271677 | 189738163 | 224577718
MCR020505 | HPR158 | 2017-05-01 | Overhead | 32217921 | 29779896 | 23442272
MCR020506 | HPR158 | 2017-06-01 | Labor | 32849609 | 28978096 | 33530894
MCR020507 | HPR158 | 2017-06-01 | Material | 96772797 | 85367573 | 67559302
MCR020508 | HPR158 | 2017-06-01 | Equipment | 15282886 | 13481711 | 13452115
MCR020509 | HPR158 | 2017-06-01 | Subcontract | 182596508 | 161076471 | 189685844
MCR020510 | HPR158 | 2017-06-01 | Overhead | 28658994 | 25281369 | 22797566
MCR020511 | HPR158 | 2017-07-01 | Labor | 27718168 | 21323549 | 25089927
MCR020512 | HPR158 | 2017-07-01 | Material | 81655910 | 62817779 | 72892864
MCR020513 | HPR158 | 2017-07-01 | Equipment | 12895545 | 9920525 | 10976225
MCR020514 | HPR158 | 2017-07-01 | Subcontract | 154073091 | 118528217 | 118295643
MCR020515 | HPR158 | 2017-07-01 | Overhead | 24182170 | 18603310 | 20921034
MCR020516 | HPR158 | 2017-08-01 | Labor | 21734567 | 26611583 | 28839831
MCR020517 | HPR158 | 2017-08-01 | Material | 64028611 | 78395980 | 81286881
MCR020518 | HPR158 | 2017-08-01 | Equipment | 10111746 | 12380719 | 13873501
MCR020519 | HPR158 | 2017-08-01 | Subcontract | 120812886 | 147922068 | 182045632
MCR020520 | HPR158 | 2017-08-01 | Overhead | 18961895 | 23216751 | 20815998
MCR020521 | HPR158 | 2017-09-01 | Labor | 15165113 | 20127815 | 21077003
MCR020522 | HPR158 | 2017-09-01 | Material | 44675431 | 59295227 | 57550105
MCR020523 | HPR158 | 2017-09-01 | Equipment | 7055387 | 9364224 | 9456017
MCR020524 | HPR158 | 2017-09-01 | Subcontract | 84296186 | 111881662 | 110096779
MCR020525 | HPR158 | 2017-09-01 | Overhead | 13230505 | 17560116 | 23446313
MCR020526 | HPR158 | 2017-10-01 | Labor | 8408844 | 40382210 | 40190327
MCR020527 | HPR158 | 2017-10-01 | Material | 24771904 | 118963348 | 118114232
MCR020528 | HPR158 | 2017-10-01 | Equipment | 3912114 | 18787338 | 19566726
MCR020529 | HPR158 | 2017-10-01 | Subcontract | 46741060 | 224466923 | 337654912
MCR020530 | HPR158 | 2017-10-01 | Overhead | 7336130 | 35230664 | 22380103
MCR020531 | HPR158 | 2017-11-01 | Labor | 2272482 | 22207829 | 28994931
MCR020532 | HPR158 | 2017-11-01 | Material | 6694584 | 65422812 | 69800916
MCR020533 | HPR158 | 2017-11-01 | Equipment | 1057245 | 10331926 | 10502335
MCR020534 | HPR158 | 2017-11-01 | Subcontract | 12631729 | 123443543 | 151701755
MCR020535 | HPR158 | 2017-11-01 | Overhead | 1982583 | 19374784 | 24753165
MCR020536 | HPR158 | 2017-12-01 | Labor | 0 | 13643057 | 14088305
MCR020537 | HPR158 | 2017-12-01 | Material | 0 | 40191552 | 42141596
MCR020538 | HPR158 | 2017-12-01 | Equipment | 0 | 6347268 | 6707853
MCR020539 | HPR158 | 2017-12-01 | Subcontract | 0 | 75835743 | 139787253
MCR020540 | HPR158 | 2017-12-01 | Overhead | 0 | 11902616 | 22935012
MCR020541 | HPR158 | 2018-01-01 | Labor | 0 | 12412095 | 13573873
MCR020542 | HPR158 | 2018-01-01 | Material | 0 | 36565219 | 35220521
MCR020543 | HPR158 | 2018-01-01 | Equipment | 0 | 5774578 | 6604685
MCR020544 | HPR158 | 2018-01-01 | Subcontract | 0 | 68993370 | 127119441
MCR020545 | HPR158 | 2018-01-01 | Overhead | 0 | 10828688 | 24254380
MCR020546 | HPR158 | 2018-02-01 | Labor | 0 | 9629999 | 12241648
MCR020547 | HPR158 | 2018-02-01 | Material | 0 | 28369347 | 28819938
MCR020548 | HPR158 | 2018-02-01 | Equipment | 0 | 4480241 | 4862026
MCR020549 | HPR158 | 2018-02-01 | Subcontract | 0 | 53528923 | 90116365
MCR020550 | HPR158 | 2018-02-01 | Overhead | 0 | 8401503 | 24325729
MCR020551 | HPR158 | 2018-03-01 | Labor | 0 | 7545149 | 7627518
MCR020552 | HPR158 | 2018-03-01 | Material | 0 | 22227515 | 26493274
MCR020553 | HPR158 | 2018-03-01 | Equipment | 0 | 3510290 | 4455506
MCR020554 | HPR158 | 2018-03-01 | Subcontract | 0 | 41940160 | 88014505
MCR020555 | HPR158 | 2018-03-01 | Overhead | 0 | 6582617 | 23618059
MCR020556 | HPR158 | 2018-04-01 | Labor | 0 | 1479170 | 1680108
MCR020557 | HPR158 | 2018-04-01 | Material | 0 | 4357539 | 4335387
MCR020558 | HPR158 | 2018-04-01 | Equipment | 0 | 688166 | 670895
MCR020559 | HPR158 | 2018-04-01 | Subcontract | 0 | 8222056 | 61125093
MCR020560 | HPR158 | 2018-04-01 | Overhead | 0 | 1290473 | 22181113
MCR020561 | HPR159 | 2016-08-01 | Labor | 1860844 | 848669 | 1015885
MCR020562 | HPR159 | 2016-08-01 | Material | 5830116 | 2658922 | 2824999
MCR020563 | HPR159 | 2016-08-01 | Equipment | 2090849 | 953567 | 1001431
MCR020564 | HPR159 | 2016-08-01 | Subcontract | 5089424 | 2321117 | 2386377
MCR020565 | HPR159 | 2016-08-01 | Overhead | 1385908 | 632067 | 11914545
MCR020566 | HPR159 | 2016-09-01 | Labor | 5370839 | 4711610 | 4706401
MCR020567 | HPR159 | 2016-09-01 | Material | 16827104 | 14761708 | 13465867
MCR020568 | HPR159 | 2016-09-01 | Equipment | 6034689 | 5293978 | 5567145
MCR020569 | HPR159 | 2016-09-01 | Subcontract | 14689289 | 12886294 | 13790883
MCR020570 | HPR159 | 2016-09-01 | Overhead | 4000062 | 3509085 | 12042795
MCR020571 | HPR159 | 2016-10-01 | Labor | 8566922 | 6896656 | 9287083
MCR020572 | HPR159 | 2016-10-01 | Material | 26840593 | 21607566 | 20901058
MCR020573 | HPR159 | 2016-10-01 | Equipment | 9625818 | 7749102 | 9108139
MCR020574 | HPR159 | 2016-10-01 | Subcontract | 23430605 | 18862412 | 18500180
MCR020575 | HPR159 | 2016-10-01 | Overhead | 6380422 | 5136451 | 11919547
MCR020576 | HPR159 | 2016-11-01 | Labor | 11454059 | 6002173 | 6274135
MCR020577 | HPR159 | 2016-11-01 | Material | 35886137 | 18805107 | 19693302
MCR020578 | HPR159 | 2016-11-01 | Equipment | 12869813 | 6744059 | 6598190
MCR020579 | HPR159 | 2016-11-01 | Subcontract | 31326950 | 16415994 | 16857664
MCR020580 | HPR159 | 2016-11-01 | Overhead | 8530687 | 4470263 | 12198727
MCR020581 | HPR159 | 2016-12-01 | Labor | 14037382 | 8635338 | 9216409
MCR020582 | HPR159 | 2016-12-01 | Material | 43979816 | 27054944 | 30498728
MCR020583 | HPR159 | 2016-12-01 | Equipment | 15772442 | 9702690 | 8950229
MCR020584 | HPR159 | 2016-12-01 | Subcontract | 38392359 | 23617723 | 22930926
MCR020585 | HPR159 | 2016-12-01 | Overhead | 10454679 | 6431377 | 11359194
MCR020586 | HPR159 | 2017-01-01 | Labor | 16322205 | 7909187 | 9864359
MCR020587 | HPR159 | 2017-01-01 | Material | 51138279 | 24779876 | 24400718
MCR020588 | HPR159 | 2017-01-01 | Equipment | 18339675 | 8886785 | 8282847
MCR020589 | HPR159 | 2017-01-01 | Subcontract | 44641369 | 21631694 | 25223180
MCR020590 | HPR159 | 2017-01-01 | Overhead | 12156356 | 5890558 | 11578051
MCR020591 | HPR159 | 2017-02-01 | Labor | 18314039 | 8843362 | 9981417
MCR020592 | HPR159 | 2017-02-01 | Material | 57378793 | 27706692 | 24654866
MCR020593 | HPR159 | 2017-02-01 | Equipment | 20577705 | 9936426 | 9914253
MCR020594 | HPR159 | 2017-02-01 | Subcontract | 50089051 | 24186670 | 22410170
MCR020595 | HPR159 | 2017-02-01 | Overhead | 13639823 | 6586307 | 12202204
MCR020596 | HPR159 | 2017-03-01 | Labor | 20018608 | 11066592 | 13683190
MCR020597 | HPR159 | 2017-03-01 | Material | 62719294 | 34672182 | 41346716
MCR020598 | HPR159 | 2017-03-01 | Equipment | 22492964 | 12434454 | 13131803
MCR020599 | HPR159 | 2017-03-01 | Subcontract | 54751063 | 30267223 | 30353577
MCR020600 | HPR159 | 2017-03-01 | Overhead | 14909342 | 8242112 | 11239332
MCR020601 | HPR159 | 2017-04-01 | Labor | 21441872 | 10893009 | 12914461
MCR020602 | HPR159 | 2017-04-01 | Material | 67178451 | 34128340 | 32812417
MCR020603 | HPR159 | 2017-04-01 | Equipment | 24092148 | 12239416 | 13532226
MCR020604 | HPR159 | 2017-04-01 | Subcontract | 58643703 | 29792473 | 27607686
MCR020605 | HPR159 | 2017-04-01 | Overhead | 15969352 | 8112832 | 11904555
MCR020606 | HPR159 | 2017-05-01 | Labor | 22590045 | 12764004 | 13976612
MCR020607 | HPR159 | 2017-05-01 | Material | 70775734 | 39990260 | 41823295
MCR020608 | HPR159 | 2017-05-01 | Equipment | 25382238 | 14341671 | 13719375
MCR020609 | HPR159 | 2017-05-01 | Subcontract | 61783966 | 34909660 | 40264293
MCR020610 | HPR159 | 2017-05-01 | Overhead | 16824482 | 9506301 | 11567413
MCR020611 | HPR159 | 2017-06-01 | Labor | 23469623 | 18207933 | 20372483
MCR020612 | HPR159 | 2017-06-01 | Material | 73531496 | 57046360 | 59260503
MCR020613 | HPR159 | 2017-06-01 | Equipment | 26370535 | 20458485 | 23534440
MCR020614 | HPR159 | 2017-06-01 | Subcontract | 64189619 | 49798852 | 50235036
MCR020615 | HPR159 | 2017-06-01 | Overhead | 17479569 | 13560798 | 11292552
MCR020616 | HPR159 | 2017-07-01 | Labor | 24087414 | 11601964 | 13529254
MCR020617 | HPR159 | 2017-07-01 | Material | 75467066 | 36349531 | 36498229
MCR020618 | HPR159 | 2017-07-01 | Equipment | 27064686 | 13036000 | 13366915
MCR020619 | HPR159 | 2017-07-01 | Subcontract | 65879282 | 31731471 | 29167012
MCR020620 | HPR159 | 2017-07-01 | Overhead | 17939683 | 8640843 | 11341839
MCR020621 | HPR159 | 2017-08-01 | Labor | 24450572 | 14192683 | 19013797
MCR020622 | HPR159 | 2017-08-01 | Material | 76604857 | 44466380 | 44742680
MCR020623 | HPR159 | 2017-08-01 | Equipment | 27472731 | 15946938 | 17379056
MCR020624 | HPR159 | 2017-08-01 | Subcontract | 66872522 | 38817108 | 35538681
MCR020625 | HPR159 | 2017-08-01 | Overhead | 18210154 | 10570343 | 12535201
MCR020626 | HPR159 | 2017-09-01 | Labor | 24566638 | 14238218 | 14369736
MCR020627 | HPR159 | 2017-09-01 | Material | 76968498 | 44609044 | 52721016
MCR020628 | HPR159 | 2017-09-01 | Equipment | 27603144 | 15998102 | 16576130
MCR020629 | HPR159 | 2017-09-01 | Subcontract | 67189963 | 38941646 | 37379435
MCR020630 | HPR159 | 2017-09-01 | Overhead | 18296597 | 10604257 | 12190430
MCR020631 | HPR159 | 2017-10-01 | Labor | 24443591 | 17230878 | 20237667
MCR020632 | HPR159 | 2017-10-01 | Material | 76582984 | 53985196 | 58641420
MCR020633 | HPR159 | 2017-10-01 | Equipment | 27464887 | 19360663 | 22508206
MCR020634 | HPR159 | 2017-10-01 | Subcontract | 66853428 | 47126597 | 49490205
MCR020635 | HPR159 | 2017-10-01 | Overhead | 18204954 | 12833112 | 11535360
MCR020636 | HPR159 | 2017-11-01 | Labor | 24089903 | 13360648 | 16499697
MCR020637 | HPR159 | 2017-11-01 | Material | 75474863 | 41859573 | 41168777
MCR020638 | HPR159 | 2017-11-01 | Equipment | 27067483 | 15012061 | 14674789
MCR020639 | HPR159 | 2017-11-01 | Subcontract | 65886089 | 36541484 | 40942585
MCR020640 | HPR159 | 2017-11-01 | Overhead | 17941537 | 9950665 | 10820637
MCR020641 | HPR159 | 2017-12-01 | Labor | 23514615 | 12129527 | 15296574
MCR020642 | HPR159 | 2017-12-01 | Material | 73672457 | 38002411 | 39507656
MCR020643 | HPR159 | 2017-12-01 | Equipment | 26421087 | 13628771 | 16401198
MCR020644 | HPR159 | 2017-12-01 | Subcontract | 64312671 | 33174360 | 35051312
MCR020645 | HPR159 | 2017-12-01 | Overhead | 17513077 | 9033758 | 11917091
MCR020646 | HPR159 | 2018-01-01 | Labor | 22727420 | 18956573 | 22181279
MCR020647 | HPR159 | 2018-01-01 | Material | 71206135 | 59391884 | 61085172
MCR020648 | HPR159 | 2018-01-01 | Equipment | 25536593 | 21299658 | 21105419
MCR020649 | HPR159 | 2018-01-01 | Subcontract | 62159686 | 51846387 | 50190971
MCR020650 | HPR159 | 2018-01-01 | Overhead | 16926795 | 14118365 | 10432970
MCR020651 | HPR159 | 2018-02-01 | Labor | 21738775 | 11974755 | 15316873
MCR020652 | HPR159 | 2018-02-01 | Material | 68108663 | 37517503 | 38287733
MCR020653 | HPR159 | 2018-02-01 | Equipment | 24425749 | 13454869 | 13819097
MCR020654 | HPR159 | 2018-02-01 | Subcontract | 59455734 | 32751057 | 35416019
MCR020655 | HPR159 | 2018-02-01 | Overhead | 16190478 | 8918488 | 11489012
MCR020656 | HPR159 | 2018-03-01 | Labor | 20560041 | 31573597 | 34672754
MCR020657 | HPR159 | 2018-03-01 | Material | 64415630 | 98921649 | 112283701
MCR020658 | HPR159 | 2018-03-01 | Equipment | 23101320 | 35476183 | 31757076
MCR020659 | HPR159 | 2018-03-01 | Subcontract | 56231887 | 86354056 | 80658190
MCR020660 | HPR159 | 2018-03-01 | Overhead | 15312587 | 23515199 | 11172140
MCR020661 | HPR159 | 2018-04-01 | Labor | 19203660 | 22486381 | 56722871
MCR020662 | HPR159 | 2018-04-01 | Material | 60166021 | 70450949 | 88121538
MCR020663 | HPR159 | 2018-04-01 | Equipment | 21577286 | 25265761 | 32710444
MCR020664 | HPR159 | 2018-04-01 | Subcontract | 52522173 | 61500443 | 59016170
MCR020665 | HPR159 | 2018-04-01 | Overhead | 14302389 | 16747275 | 11711101
MCR020666 | HPR159 | 2018-05-01 | Labor | 17683394 | 42627874 | 65001267
MCR020667 | HPR159 | 2018-05-01 | Material | 55402952 | 133555248 | 171335580
MCR020668 | HPR159 | 2018-05-01 | Equipment | 19869111 | 47896799 | 43833769
MCR020669 | HPR159 | 2018-05-01 | Subcontract | 48364233 | 116587597 | 112630929
MCR020670 | HPR159 | 2018-05-01 | Overhead | 13170135 | 31748139 | 10745130
MCR020671 | HPR159 | 2018-06-01 | Labor | 16014649 | 21622274 | 24979271
MCR020672 | HPR159 | 2018-06-01 | Material | 50174692 | 67743659 | 69867897
MCR020673 | HPR159 | 2018-06-01 | Equipment | 17994105 | 24294848 | 29202347
MCR020674 | HPR159 | 2018-06-01 | Subcontract | 43800202 | 59137103 | 62519586
MCR020675 | HPR159 | 2018-06-01 | Overhead | 11927297 | 16103711 | 11648677
MCR020676 | HPR159 | 2018-07-01 | Labor | 14214929 | 15987368 | 19748549
MCR020677 | HPR159 | 2018-07-01 | Material | 44536078 | 50089218 | 54218051
MCR020678 | HPR159 | 2018-07-01 | Equipment | 15971934 | 17963451 | 16919825
MCR020679 | HPR159 | 2018-07-01 | Subcontract | 38877951 | 43725587 | 41780429
MCR020680 | HPR159 | 2018-07-01 | Overhead | 10586912 | 11906978 | 11751669
MCR020681 | HPR159 | 2018-08-01 | Labor | 12304494 | 18406827 | 22077501
MCR020682 | HPR159 | 2018-08-01 | Material | 38550590 | 57669504 | 66138469
MCR020683 | HPR159 | 2018-08-01 | Equipment | 13825364 | 20681963 | 24008909
MCR020684 | HPR159 | 2018-08-01 | Subcontract | 33652895 | 50342829 | 50773257
MCR020685 | HPR159 | 2018-08-01 | Overhead | 9164069 | 13708929 | 11239152
MCR020686 | HPR159 | 2018-09-01 | Labor | 10307380 | 7483552 | 9715934
MCR020687 | HPR159 | 2018-09-01 | Material | 32293535 | 23446341 | 23860275
MCR020688 | HPR159 | 2018-09-01 | Equipment | 11581402 | 8408540 | 6617693
MCR020689 | HPR159 | 2018-09-01 | Subcontract | 28190773 | 20467579 | 21931083
MCR020690 | HPR159 | 2018-09-01 | Overhead | 7676670 | 5573556 | 10643492
MCR020691 | HPR159 | 2018-10-01 | Labor | 8253062 | 7520433 | 8948960
MCR020692 | HPR159 | 2018-10-01 | Material | 25857253 | 23561889 | 26672723
MCR020693 | HPR159 | 2018-10-01 | Equipment | 9273163 | 8449979 | 9505538
MCR020694 | HPR159 | 2018-10-01 | Subcontract | 22572194 | 20568447 | 21245523
MCR020695 | HPR159 | 2018-10-01 | Overhead | 6146667 | 5601024 | 11176013
MCR020696 | HPR159 | 2018-11-01 | Labor | 6179424 | 16990996 | 18189545
MCR020697 | HPR159 | 2018-11-01 | Material | 19360441 | 53233633 | 56840632
MCR020698 | HPR159 | 2018-11-01 | Equipment | 6943218 | 19091130 | 17741505
MCR020699 | HPR159 | 2018-11-01 | Subcontract | 16900776 | 46470517 | 49024643
MCR020700 | HPR159 | 2018-11-01 | Overhead | 4602275 | 12654454 | 11904637
MCR020701 | HPR159 | 2018-12-01 | Labor | 4138828 | 12208753 | 16432690
MCR020702 | HPR159 | 2018-12-01 | Material | 12967153 | 38250629 | 41495147
MCR020703 | HPR159 | 2018-12-01 | Equipment | 4650398 | 13717789 | 14351033
MCR020704 | HPR159 | 2018-12-01 | Subcontract | 11319729 | 33391042 | 35057878
MCR020705 | HPR159 | 2018-12-01 | Overhead | 3082492 | 9092763 | 10864196
MCR020706 | HPR159 | 2019-01-01 | Labor | 2213459 | 14438029 | 16936268
MCR020707 | HPR159 | 2019-01-01 | Material | 6934876 | 45235061 | 51923633
MCR020708 | HPR159 | 2019-01-01 | Equipment | 2487048 | 16222610 | 18128827
MCR020709 | HPR159 | 2019-01-01 | Subcontract | 6053828 | 39488131 | 42288293
MCR020710 | HPR159 | 2019-01-01 | Overhead | 1648527 | 10753070 | 12399274
MCR020711 | HPR159 | 2019-02-01 | Labor | 580760 | 14168794 | 17793847
MCR020712 | HPR159 | 2019-02-01 | Material | 1819551 | 44391536 | 47119823
MCR020713 | HPR159 | 2019-02-01 | Equipment | 652544 | 15920097 | 15635796
MCR020714 | HPR159 | 2019-02-01 | Subcontract | 1588384 | 38751772 | 34395727
MCR020715 | HPR159 | 2019-02-01 | Overhead | 432535 | 10552552 | 11661388
MCR020716 | HPR159 | 2019-03-01 | Labor | 0 | 12804667 | 15058478
MCR020717 | HPR159 | 2019-03-01 | Material | 0 | 40117657 | 40994146
MCR020718 | HPR159 | 2019-03-01 | Equipment | 0 | 14387359 | 15667025
MCR020719 | HPR159 | 2019-03-01 | Subcontract | 0 | 35020872 | 32633754
MCR020720 | HPR159 | 2019-03-01 | Overhead | 0 | 9536585 | 12443479
MCR020721 | HPR159 | 2019-04-01 | Labor | 0 | 9351096 | 10478444
MCR020722 | HPR159 | 2019-04-01 | Material | 0 | 29297448 | 30923987
MCR020723 | HPR159 | 2019-04-01 | Equipment | 0 | 10506918 | 11850191
MCR020724 | HPR159 | 2019-04-01 | Subcontract | 0 | 25575326 | 24932469
MCR020725 | HPR159 | 2019-04-01 | Overhead | 0 | 6964454 | 11295418
MCR020726 | HPR159 | 2019-05-01 | Labor | 0 | 10791660 | 13756968
MCR020727 | HPR159 | 2019-05-01 | Material | 0 | 33810807 | 35221483
MCR020728 | HPR159 | 2019-05-01 | Equipment | 0 | 12125540 | 9491023
MCR020729 | HPR159 | 2019-05-01 | Subcontract | 0 | 29515282 | 27357153
MCR020730 | HPR159 | 2019-05-01 | Overhead | 0 | 8037350 | 11067589
MCR020731 | HPR159 | 2019-06-01 | Labor | 0 | 7030808 | 9562425
MCR020732 | HPR159 | 2019-06-01 | Material | 0 | 22027872 | 28341463
MCR020733 | HPR159 | 2019-06-01 | Equipment | 0 | 7899836 | 9914182
MCR020734 | HPR159 | 2019-06-01 | Subcontract | 0 | 19229320 | 17609274
MCR020735 | HPR159 | 2019-06-01 | Overhead | 0 | 5236364 | 11430116
MCR020736 | HPR159 | 2019-07-01 | Labor | 0 | 2684682 | 3147310
MCR020737 | HPR159 | 2019-07-01 | Material | 0 | 8411243 | 7271704
MCR020738 | HPR159 | 2019-07-01 | Equipment | 0 | 3016517 | 3953063
MCR020739 | HPR159 | 2019-07-01 | Subcontract | 0 | 7342629 | 9610238
MCR020740 | HPR159 | 2019-07-01 | Overhead | 0 | 1999482 | 11803804
MCR020741 | HPR159 | 2019-08-01 | Labor | 0 | 2104969 | 2487761
MCR020742 | HPR159 | 2019-08-01 | Material | 0 | 6594973 | 7717464
MCR020743 | HPR159 | 2019-08-01 | Equipment | 0 | 2365149 | 3194640
MCR020744 | HPR159 | 2019-08-01 | Subcontract | 0 | 5757109 | 6880316
MCR020745 | HPR159 | 2019-08-01 | Overhead | 0 | 1567727 | 11144350
MCR020746 | HPR159 | 2019-09-01 | Labor | 0 | 2085796 | 2921484
MCR020747 | HPR159 | 2019-09-01 | Material | 0 | 6534903 | 6595717
MCR020748 | HPR159 | 2019-09-01 | Equipment | 0 | 2343606 | 2312976
MCR020749 | HPR159 | 2019-09-01 | Subcontract | 0 | 5704670 | 5698039
MCR020750 | HPR159 | 2019-09-01 | Overhead | 0 | 1553447 | 11903024
MCR020751 | HPR159 | 2019-10-01 | Labor | 0 | 1629436 | 1878094
MCR020752 | HPR159 | 2019-10-01 | Material | 0 | 5105103 | 5442006
MCR020753 | HPR159 | 2019-10-01 | Equipment | 0 | 1830838 | 2362808
MCR020754 | HPR159 | 2019-10-01 | Subcontract | 0 | 4456520 | 4277160
MCR020755 | HPR159 | 2019-10-01 | Overhead | 0 | 1213561 | 11744453
MCR020756 | HPR159 | 2019-11-01 | Labor | 0 | 257675 | 295965
MCR020757 | HPR159 | 2019-11-01 | Material | 0 | 807310 | 1020131
MCR020758 | HPR159 | 2019-11-01 | Equipment | 0 | 289525 | 239178
MCR020759 | HPR159 | 2019-11-01 | Subcontract | 0 | 704744 | 688833
MCR020760 | HPR159 | 2019-11-01 | Overhead | 0 | 191910 | 12120657
MCR020761 | HPR160 | 2016-01-01 | Labor | 5292315 | 3125441 | 3297440
MCR020762 | HPR160 | 2016-01-01 | Material | 15308873 | 9040840 | 9423190
MCR020763 | HPR160 | 2016-01-01 | Equipment | 5151350 | 3042192 | 3505835
MCR020764 | HPR160 | 2016-01-01 | Subcontract | 11613934 | 6858749 | 6940197
MCR020765 | HPR160 | 2016-01-01 | Overhead | 4467778 | 2638500 | 25213258
MCR020766 | HPR160 | 2016-02-01 | Labor | 14980854 | 10127662 | 11594342
MCR020767 | HPR160 | 2016-02-01 | Material | 43334533 | 29295892 | 32503067
MCR020768 | HPR160 | 2016-02-01 | Equipment | 14581828 | 9857904 | 9499334
MCR020769 | HPR160 | 2016-02-01 | Subcontract | 32875340 | 22225056 | 23153010
MCR020770 | HPR160 | 2016-02-01 | Overhead | 12646852 | 8549782 | 25269709
MCR020771 | HPR160 | 2016-03-01 | Labor | 23348482 | 17070740 | 18087451
MCR020772 | HPR160 | 2016-03-01 | Material | 67539241 | 49379862 | 47399162
MCR020773 | HPR160 | 2016-03-01 | Equipment | 22726576 | 16616047 | 18809806
MCR020774 | HPR160 | 2016-03-01 | Subcontract | 51238018 | 37461573 | 36198123
MCR020775 | HPR160 | 2016-03-01 | Overhead | 19710811 | 14411135 | 27817997
MCR020776 | HPR160 | 2016-04-01 | Labor | 30427407 | 16185499 | 18236035
MCR020777 | HPR160 | 2016-04-01 | Material | 88016173 | 46819161 | 46402993
MCR020778 | HPR160 | 2016-04-01 | Equipment | 29616949 | 15754385 | 15570855
MCR020779 | HPR160 | 2016-04-01 | Subcontract | 66772652 | 35518921 | 33751224
MCR020780 | HPR160 | 2016-04-01 | Overhead | 25686847 | 13663814 | 25377485
MCR020781 | HPR160 | 2016-05-01 | Labor | 36251557 | 28280013 | 30669797
MCR020782 | HPR160 | 2016-05-01 | Material | 104863463 | 81804489 | 83375775
MCR020783 | HPR160 | 2016-05-01 | Equipment | 35285968 | 27526752 | 30390171
MCR020784 | HPR160 | 2016-05-01 | Subcontract | 79553692 | 62060215 | 59956701
MCR020785 | HPR160 | 2016-05-01 | Overhead | 30603600 | 23874015 | 25919813
MCR020786 | HPR160 | 2016-06-01 | Labor | 40856790 | 35176476 | 38017802
MCR020787 | HPR160 | 2016-06-01 | Material | 118184842 | 101753618 | 106307692
MCR020788 | HPR160 | 2016-06-01 | Equipment | 39768537 | 34239522 | 35663179
MCR020789 | HPR160 | 2016-06-01 | Subcontract | 89659832 | 77194436 | 70904202
MCR020790 | HPR160 | 2016-06-01 | Overhead | 34491343 | 29696016 | 25413486
MCR020791 | HPR160 | 2016-07-01 | Labor | 44281168 | 15577843 | 20288476
MCR020792 | HPR160 | 2016-07-01 | Material | 128090405 | 45061419 | 40700607
MCR020793 | HPR160 | 2016-07-01 | Equipment | 43101704 | 15162915 | 13703769
MCR020794 | HPR160 | 2016-07-01 | Subcontract | 97174595 | 34185426 | 42180682
MCR020795 | HPR160 | 2016-07-01 | Overhead | 37382206 | 13150831 | 24902734
MCR020796 | HPR160 | 2016-08-01 | Labor | 46565276 | 26410396 | 29971238
MCR020797 | HPR160 | 2016-08-01 | Material | 134697555 | 76396321 | 71164247
MCR020798 | HPR160 | 2016-08-01 | Equipment | 45324973 | 25706934 | 26022171
MCR020799 | HPR160 | 2016-08-01 | Subcontract | 102187048 | 57957359 | 62154479
MCR020800 | HPR160 | 2016-08-01 | Overhead | 39310452 | 22295682 | 26363017
MCR020801 | HPR160 | 2016-09-01 | Labor | 47752630 | 55417016 | 63443934
MCR020802 | HPR160 | 2016-09-01 | Material | 138132169 | 160302639 | 165990954
MCR020803 | HPR160 | 2016-09-01 | Equipment | 46480701 | 53940940 | 53944066
MCR020804 | HPR160 | 2016-09-01 | Subcontract | 104792686 | 121612107 | 109227696
MCR020805 | HPR160 | 2016-09-01 | Overhead | 40312818 | 46783100 | 25142896
MCR020806 | HPR160 | 2016-10-01 | Labor | 47890187 | 29800797 | 63767233
MCR020807 | HPR160 | 2016-10-01 | Material | 138530074 | 86203601 | 138290713
MCR020808 | HPR160 | 2016-10-01 | Equipment | 46614594 | 29007029 | 31364282
MCR020809 | HPR160 | 2016-10-01 | Subcontract | 105094553 | 65397561 | 66290396
MCR020810 | HPR160 | 2016-10-01 | Overhead | 40428943 | 25157862 | 26191009
MCR020811 | HPR160 | 2016-11-01 | Labor | 47028995 | 25044802 | 50668322
MCR020812 | HPR160 | 2016-11-01 | Material | 136038937 | 72446120 | 114076744
MCR020813 | HPR160 | 2016-11-01 | Equipment | 45776340 | 24377714 | 28379582
MCR020814 | HPR160 | 2016-11-01 | Subcontract | 103204675 | 54960576 | 44663060
MCR020815 | HPR160 | 2016-11-01 | Overhead | 39701924 | 21142846 | 23980096
MCR020816 | HPR160 | 2016-12-01 | Labor | 45225058 | 34554918 | 43450826
MCR020817 | HPR160 | 2016-12-01 | Material | 130820759 | 99955662 | 107926027
MCR020818 | HPR160 | 2016-12-01 | Equipment | 44020453 | 33634520 | 32627863
MCR020819 | HPR160 | 2016-12-01 | Subcontract | 99245953 | 75830434 | 90470067
MCR020820 | HPR160 | 2016-12-01 | Overhead | 38179039 | 29171296 | 26509686
MCR020821 | HPR160 | 2017-01-01 | Labor | 42540497 | 46382898 | 55840954
MCR020822 | HPR160 | 2017-01-01 | Material | 123055236 | 134169999 | 145691389
MCR020823 | HPR160 | 2017-01-01 | Equipment | 41407398 | 45147453 | 38789807
MCR020824 | HPR160 | 2017-01-01 | Subcontract | 93354711 | 101786822 | 101787590
MCR020825 | HPR160 | 2017-01-01 | Overhead | 35912730 | 39156489 | 27486094
MCR020826 | HPR160 | 2017-02-01 | Labor | 39045169 | 33211510 | 29849598
MCR020827 | HPR160 | 2017-02-01 | Material | 112944435 | 96069639 | 90414220
MCR020828 | HPR160 | 2017-02-01 | Equipment | 38005170 | 32326895 | 40638413
MCR020829 | HPR160 | 2017-02-01 | Subcontract | 85684246 | 72882339 | 71614231
MCR020830 | HPR160 | 2017-02-01 | Overhead | 32961970 | 28037190 | 26132055
MCR020831 | HPR160 | 2017-03-01 | Labor | 34819006 | 19149685 | 26552659
MCR020832 | HPR160 | 2017-03-01 | Material | 100719579 | 55393545 | 50692313
MCR020833 | HPR160 | 2017-03-01 | Equipment | 33891574 | 18639618 | 18651150
MCR020834 | HPR160 | 2017-03-01 | Subcontract | 76409973 | 42023798 | 35715130
MCR020835 | HPR160 | 2017-03-01 | Overhead | 29394239 | 16166183 | 25332547
MCR020836 | HPR160 | 2017-04-01 | Labor | 29955589 | 41491556 | 46073432
MCR020837 | HPR160 | 2017-04-01 | Material | 86651362 | 120021003 | 132635263
MCR020838 | HPR160 | 2017-04-01 | Equipment | 29157698 | 40386395 | 41696327
MCR020839 | HPR160 | 2017-04-01 | Subcontract | 65737250 | 91052818 | 75017464
MCR020840 | HPR160 | 2017-04-01 | Overhead | 25288538 | 35027212 | 26371895
MCR020841 | HPR160 | 2017-05-01 | Labor | 24567930 | 26760855 | 29521393
MCR020842 | HPR160 | 2017-05-01 | Material | 71066691 | 77410081 | 78052337
MCR020843 | HPR160 | 2017-05-01 | Equipment | 23913543 | 26048059 | 24653413
MCR020844 | HPR160 | 2017-05-01 | Subcontract | 53914084 | 58726438 | 64215405
MCR020845 | HPR160 | 2017-05-01 | Overhead | 20740271 | 22591540 | 26899179
MCR020846 | HPR160 | 2017-06-01 | Labor | 18798735 | 26754245 | 29677945
MCR020847 | HPR160 | 2017-06-01 | Material | 54378367 | 77390961 | 77362650
MCR020848 | HPR160 | 2017-06-01 | Equipment | 18298016 | 26041625 | 26818511
MCR020849 | HPR160 | 2017-06-01 | Subcontract | 41253642 | 58711933 | 63563569
MCR020850 | HPR160 | 2017-06-01 | Overhead | 15869911 | 22585960 | 27208710
MCR020851 | HPR160 | 2017-07-01 | Labor | 12841104 | 38250993 | 45088775
MCR020852 | HPR160 | 2017-07-01 | Material | 37144960 | 110647154 | 123630427
MCR020853 | HPR160 | 2017-07-01 | Equipment | 12499071 | 37232147 | 35521300
MCR020854 | HPR160 | 2017-07-01 | Subcontract | 28179679 | 83941435 | 100037925
MCR020855 | HPR160 | 2017-07-01 | Overhead | 10840473 | 32291526 | 27897290
MCR020856 | HPR160 | 2017-08-01 | Labor | 6990317 | 27780217 | 29985727
MCR020857 | HPR160 | 2017-08-01 | Material | 20220616 | 80358750 | 79152317
MCR020858 | HPR160 | 2017-08-01 | Equipment | 6804124 | 27040269 | 33620871
MCR020859 | HPR160 | 2017-08-01 | Subcontract | 15340182 | 60963419 | 88259022
MCR020860 | HPR160 | 2017-08-01 | Overhead | 5901232 | 23452087 | 24061092
MCR020861 | HPR160 | 2017-09-01 | Labor | 1861342 | 26179312 | 33821795
MCR020862 | HPR160 | 2017-09-01 | Material | 5384231 | 75727872 | 65245627
MCR020863 | HPR160 | 2017-09-01 | Equipment | 1811764 | 25482005 | 27833376
MCR020864 | HPR160 | 2017-09-01 | Subcontract | 4084697 | 57450247 | 81043127
MCR020865 | HPR160 | 2017-09-01 | Overhead | 1571347 | 22100601 | 25245138
MCR020866 | HPR160 | 2017-10-01 | Labor | 0 | 24835588 | 24214200
MCR020867 | HPR160 | 2017-10-01 | Material | 0 | 71840937 | 84736430
MCR020868 | HPR160 | 2017-10-01 | Equipment | 0 | 24174073 | 22308588
MCR020869 | HPR160 | 2017-10-01 | Subcontract | 0 | 54501459 | 79746777
MCR020870 | HPR160 | 2017-10-01 | Overhead | 0 | 20966228 | 24508841
MCR020871 | HPR160 | 2017-11-01 | Labor | 0 | 8734077 | 11988420
MCR020872 | HPR160 | 2017-11-01 | Material | 0 | 25264725 | 26095429
MCR020873 | HPR160 | 2017-11-01 | Equipment | 0 | 8501438 | 9044590
MCR020874 | HPR160 | 2017-11-01 | Subcontract | 0 | 19166849 | 55904032
MCR020875 | HPR160 | 2017-11-01 | Overhead | 0 | 7373317 | 22254099
MCR020876 | HPR160 | 2017-12-01 | Labor | 0 | 12036776 | 14612105
MCR020877 | HPR160 | 2017-12-01 | Material | 0 | 34818313 | 34595193
MCR020878 | HPR160 | 2017-12-01 | Equipment | 0 | 11716167 | 13462980
MCR020879 | HPR160 | 2017-12-01 | Subcontract | 0 | 26414590 | 66859426
MCR020880 | HPR160 | 2017-12-01 | Overhead | 0 | 10161459 | 25668029
MCR020881 | HPR160 | 2018-01-01 | Labor | 0 | 9115664 | 10291834
MCR020882 | HPR160 | 2018-01-01 | Material | 0 | 26368525 | 29159260
MCR020883 | HPR160 | 2018-01-01 | Equipment | 0 | 8872861 | 9362362
MCR020884 | HPR160 | 2018-01-01 | Subcontract | 0 | 20004236 | 45166992
MCR020885 | HPR160 | 2018-01-01 | Overhead | 0 | 7695452 | 24992625
MCR020886 | HPR160 | 2018-02-01 | Labor | 0 | 2668972 | 4200829
MCR020887 | HPR160 | 2018-02-01 | Material | 0 | 7720432 | 8196058
MCR020888 | HPR160 | 2018-02-01 | Equipment | 0 | 2597882 | 3482039
MCR020889 | HPR160 | 2018-02-01 | Subcontract | 0 | 5857034 | 40716325
MCR020890 | HPR160 | 2018-02-01 | Overhead | 0 | 2253149 | 25499374
MCR020891 | HPR160 | 2018-03-01 | Labor | 0 | 1196457 | 1051664
MCR020892 | HPR160 | 2018-03-01 | Material | 0 | 3460943 | 3294853
MCR020893 | HPR160 | 2018-03-01 | Equipment | 0 | 1164588 | 1420100
MCR020894 | HPR160 | 2018-03-01 | Subcontract | 0 | 2625612 | 14737250
MCR020895 | HPR160 | 2018-03-01 | Overhead | 0 | 1010050 | 28349650
MCR020896 | HPR161 | 2020-07-01 | Labor | 7111209 | 4605793 | 4840573
MCR020897 | HPR161 | 2020-07-01 | Material | 15892678 | 10293382 | 11186345
MCR020898 | HPR161 | 2020-07-01 | Equipment | 3329081 | 2156182 | 2370229
MCR020899 | HPR161 | 2020-07-01 | Subcontract | 20827012 | 13489255 | 14557287
MCR020900 | HPR161 | 2020-07-01 | Overhead | 4554228 | 2949686 | 19848009
MCR020901 | HPR161 | 2020-08-01 | Labor | 19740620 | 9327823 | 8653732
MCR020902 | HPR161 | 2020-08-01 | Material | 44117861 | 20846538 | 20344562
MCR020903 | HPR161 | 2020-08-01 | Equipment | 9241484 | 4366779 | 4778423
MCR020904 | HPR161 | 2020-08-01 | Subcontract | 57815508 | 27318939 | 23764985
MCR020905 | HPR161 | 2020-08-01 | Overhead | 12642476 | 5973813 | 20228091
MCR020906 | HPR161 | 2020-09-01 | Labor | 30036022 | 26817534 | 31000311
MCR020907 | HPR161 | 2020-09-01 | Material | 67126820 | 59933894 | 58529674
MCR020908 | HPR161 | 2020-09-01 | Equipment | 14061232 | 12554510 | 12950850
MCR020909 | HPR161 | 2020-09-01 | Subcontract | 87968254 | 78542079 | 72760378
MCR020910 | HPR161 | 2020-09-01 | Overhead | 19235955 | 17174741 | 19621642
MCR020911 | HPR161 | 2020-10-01 | Labor | 38075493 | 40526518 | 37530068
MCR020912 | HPR161 | 2020-10-01 | Material | 85094051 | 90571790 | 101657013
MCR020913 | HPR161 | 2020-10-01 | Equipment | 17824875 | 18972311 | 21933703
MCR020914 | HPR161 | 2020-10-01 | Subcontract | 111513924 | 118692383 | 122497719
MCR020915 | HPR161 | 2020-10-01 | Overhead | 24384670 | 25954379 | 20981710
MCR020916 | HPR161 | 2020-11-01 | Labor | 43942929 | 39496997 | 41161006
MCR020917 | HPR161 | 2020-11-01 | Material | 98207051 | 88270937 | 89222532
MCR020918 | HPR161 | 2020-11-01 | Equipment | 20571689 | 18490345 | 16344903
MCR020919 | HPR161 | 2020-11-01 | Subcontract | 128698228 | 115677165 | 106314340
MCR020920 | HPR161 | 2020-11-01 | Overhead | 28142350 | 25295043 | 20480694
MCR020921 | HPR161 | 2020-12-01 | Labor | 47729115 | 48511779 | 46373881
MCR020922 | HPR161 | 2020-12-01 | Material | 106668711 | 108417867 | 111370969
MCR020923 | HPR161 | 2020-12-01 | Equipment | 22344175 | 22710576 | 22731320
MCR020924 | HPR161 | 2020-12-01 | Subcontract | 139787051 | 142079284 | 129711347
MCR020925 | HPR161 | 2020-12-01 | Overhead | 30567135 | 31068376 | 19342338
MCR020926 | HPR161 | 2021-01-01 | Labor | 49533125 | 56709370 | 56603880
MCR020927 | HPR161 | 2021-01-01 | Material | 110700451 | 126738476 | 115021000
MCR020928 | HPR161 | 2021-01-01 | Equipment | 23188715 | 26548242 | 27479085
MCR020929 | HPR161 | 2021-01-01 | Subcontract | 145070560 | 166088047 | 177785002
MCR020930 | HPR161 | 2021-01-01 | Overhead | 31722476 | 36318355 | 21554169
MCR020931 | HPR161 | 2021-02-01 | Labor | 49464203 | 50130731 | 56263938
MCR020932 | HPR161 | 2021-02-01 | Material | 110546420 | 112036028 | 130347411
MCR020933 | HPR161 | 2021-02-01 | Equipment | 23156449 | 23468481 | 22064781
MCR020934 | HPR161 | 2021-02-01 | Subcontract | 144868706 | 146820805 | 125234263
MCR020935 | HPR161 | 2021-02-01 | Overhead | 31678337 | 32105201 | 20531919
MCR020936 | HPR161 | 2021-03-01 | Labor | 47644368 | 42214302 | 36438096
MCR020937 | HPR161 | 2021-03-01 | Material | 106479312 | 94343781 | 91672479
MCR020938 | HPR161 | 2021-03-01 | Equipment | 22304501 | 19762440 | 22579469
MCR020939 | HPR161 | 2021-03-01 | Subcontract | 139538848 | 123635496 | 139478088
MCR020940 | HPR161 | 2021-03-01 | Overhead | 30512861 | 27035286 | 21542408
MCR020941 | HPR161 | 2021-04-01 | Labor | 44212159 | 43430286 | 46911070
MCR020942 | HPR161 | 2021-04-01 | Material | 98808745 | 97061356 | 106416208
MCR020943 | HPR161 | 2021-04-01 | Equipment | 20697728 | 20331697 | 19444420
MCR020944 | HPR161 | 2021-04-01 | Subcontract | 129486735 | 127196819 | 120796524
MCR020945 | HPR161 | 2021-04-01 | Overhead | 28314772 | 27814038 | 20545245
MCR020946 | HPR161 | 2021-05-01 | Labor | 39328298 | 29500819 | 30930694
MCR020947 | HPR161 | 2021-05-01 | Material | 87893917 | 65930707 | 75658164
MCR020948 | HPR161 | 2021-05-01 | Equipment | 18411370 | 13810679 | 13315889
MCR020949 | HPR161 | 2021-05-01 | Subcontract | 115183088 | 86400773 | 86300923
MCR020950 | HPR161 | 2021-05-01 | Overhead | 25187004 | 18893196 | 21210457
MCR020951 | HPR161 | 2021-06-01 | Labor | 33184822 | 59435589 | 58315767
MCR020952 | HPR161 | 2021-06-01 | Material | 74164001 | 132831243 | 150808521
MCR020953 | HPR161 | 2021-06-01 | Equipment | 15535328 | 27824510 | 29736188
MCR020954 | HPR161 | 2021-06-01 | Subcontract | 97190328 | 174072487 | 166187620
MCR020955 | HPR161 | 2021-06-01 | Overhead | 21252540 | 38064307 | 21927512
MCR020956 | HPR161 | 2021-07-01 | Labor | 26021118 | 15781292 | 14909512
MCR020957 | HPR161 | 2021-07-01 | Material | 58154003 | 35269249 | 38945090
MCR020958 | HPR161 | 2021-07-01 | Equipment | 12181672 | 7387942 | 7432314
MCR020959 | HPR161 | 2021-07-01 | Subcontract | 76209570 | 46219592 | 54205141
MCR020960 | HPR161 | 2021-07-01 | Overhead | 16664692 | 10106805 | 19436134
MCR020961 | HPR161 | 2021-08-01 | Labor | 18156019 | 18178497 | 17773289
MCR020962 | HPR161 | 2021-08-01 | Material | 40576472 | 40626707 | 48147293
MCR020963 | HPR161 | 2021-08-01 | Equipment | 8499660 | 8510183 | 8330856
MCR020964 | HPR161 | 2021-08-01 | Subcontract | 53174593 | 53240426 | 53210294
MCR020965 | HPR161 | 2021-08-01 | Overhead | 11627650 | 11642046 | 20726144
MCR020966 | HPR161 | 2021-09-01 | Labor | 10067259 | 14777847 | 13217620
MCR020967 | HPR161 | 2021-09-01 | Material | 22499088 | 33026673 | 34668032
MCR020968 | HPR161 | 2021-09-01 | Equipment | 4712943 | 6918184 | 6846889
MCR020969 | HPR161 | 2021-09-01 | Subcontract | 29484571 | 43280745 | 43315989
MCR020970 | HPR161 | 2021-09-01 | Overhead | 6447370 | 9464170 | 20023434
MCR020971 | HPR161 | 2021-10-01 | Labor | 2720668 | 5509210 | 6060715
MCR020972 | HPR161 | 2021-10-01 | Material | 6080358 | 12312407 | 18029137
MCR020973 | HPR161 | 2021-10-01 | Equipment | 1273669 | 2579112 | 2467288
MCR020974 | HPR161 | 2021-10-01 | Subcontract | 7968178 | 16135144 | 13774250
MCR020975 | HPR161 | 2021-10-01 | Overhead | 1742396 | 3528260 | 20557230
MCR020976 | HPR161 | 2021-11-01 | Labor | 0 | 2013042 | 2031302
MCR020977 | HPR161 | 2021-11-01 | Material | 0 | 4498902 | 5928651
MCR020978 | HPR161 | 2021-11-01 | Equipment | 0 | 942397 | 1217409
MCR020979 | HPR161 | 2021-11-01 | Subcontract | 0 | 5895714 | 6172852
MCR020980 | HPR161 | 2021-11-01 | Overhead | 0 | 1289212 | 20251269
MCR020981 | HPR162 | 2016-07-01 | Labor | 4412167 | 3105806 | 3199966
MCR020982 | HPR162 | 2016-07-01 | Material | 9094399 | 6401716 | 6442568
MCR020983 | HPR162 | 2016-07-01 | Equipment | 2011389 | 1415854 | 1649456
MCR020984 | HPR162 | 2016-07-01 | Subcontract | 10609577 | 7468278 | 7373213
MCR020985 | HPR162 | 2016-07-01 | Overhead | 2756252 | 1940177 | 15381518
MCR020986 | HPR162 | 2016-08-01 | Labor | 12408576 | 5597742 | 6699030
MCR020987 | HPR162 | 2016-08-01 | Material | 25576671 | 11538117 | 11161684
MCR020988 | HPR162 | 2016-08-01 | Equipment | 5656740 | 2551862 | 2457887
MCR020989 | HPR162 | 2016-08-01 | Subcontract | 29837888 | 13460432 | 13468213
MCR020990 | HPR162 | 2016-08-01 | Overhead | 7751556 | 3496873 | 16119169
MCR020991 | HPR162 | 2016-09-01 | Labor | 19187004 | 16609042 | 15512286
MCR020992 | HPR162 | 2016-09-01 | Material | 39548429 | 34234711 | 36320437
MCR020993 | HPR162 | 2016-09-01 | Equipment | 8746845 | 7571621 | 7856674
MCR020994 | HPR162 | 2016-09-01 | Subcontract | 46137419 | 39938406 | 43846342
MCR020995 | HPR162 | 2016-09-01 | Overhead | 11985996 | 10375560 | 15004110
MCR020996 | HPR162 | 2016-10-01 | Labor | 24780763 | 18724659 | 22004429
MCR020997 | HPR162 | 2016-10-01 | Material | 51078337 | 38595440 | 41036694
MCR020998 | HPR162 | 2016-10-01 | Equipment | 11296890 | 8536074 | 9469554
MCR020999 | HPR162 | 2016-10-01 | Subcontract | 59588274 | 45025657 | 45843043
MCR021000 | HPR162 | 2016-10-01 | Overhead | 15480380 | 11697172 | 14797884
MCR021001 | HPR162 | 2016-11-01 | Labor | 29225166 | 10581207 | 10873018
MCR021002 | HPR162 | 2016-11-01 | Material | 60239182 | 21810081 | 22073826
MCR021003 | HPR162 | 2016-11-01 | Equipment | 13322976 | 4823691 | 4496926
MCR021004 | HPR162 | 2016-11-01 | Subcontract | 70275368 | 25443763 | 27817231
MCR021005 | HPR162 | 2016-11-01 | Overhead | 18256770 | 6610010 | 14474703
MCR021006 | HPR162 | 2016-12-01 | Labor | 32557823 | 22765024 | 25136399
MCR021007 | HPR162 | 2016-12-01 | Material | 67108485 | 46923477 | 41126315
MCR021008 | HPR162 | 2016-12-01 | Equipment | 14842245 | 10377969 | 11604686
MCR021009 | HPR162 | 2016-12-01 | Subcontract | 78289135 | 54741191 | 47746822
MCR021010 | HPR162 | 2016-12-01 | Overhead | 20338659 | 14221161 | 14542753
MCR021011 | HPR162 | 2017-01-01 | Labor | 34818997 | 25884226 | 27648430
MCR021012 | HPR162 | 2017-01-01 | Material | 71769238 | 53352804 | 56700845
MCR021013 | HPR162 | 2017-01-01 | Equipment | 15873055 | 11799930 | 11153058
MCR021014 | HPR162 | 2017-01-01 | Subcontract | 83726396 | 62241681 | 72048253
MCR021015 | HPR162 | 2017-01-01 | Overhead | 21751200 | 16169706 | 15046809
MCR021016 | HPR162 | 2017-02-01 | Labor | 36052066 | 35377625 | 29934419
MCR021017 | HPR162 | 2017-02-01 | Material | 74310852 | 72920688 | 80151982
MCR021018 | HPR162 | 2017-02-01 | Equipment | 16435178 | 16127718 | 15715476
MCR021019 | HPR162 | 2017-02-01 | Subcontract | 86691456 | 85069683 | 77366439
MCR021020 | HPR162 | 2017-02-01 | Overhead | 22521490 | 22100171 | 14596831
MCR021021 | HPR162 | 2017-03-01 | Labor | 36304106 | 21826235 | 28423125
MCR021022 | HPR162 | 2017-03-01 | Material | 74830357 | 44988437 | 37674232
MCR021023 | HPR162 | 2017-03-01 | Equipment | 16550076 | 9950000 | 12339831
MCR021024 | HPR162 | 2017-03-01 | Subcontract | 87297515 | 52483763 | 58322133
MCR021025 | HPR162 | 2017-03-01 | Overhead | 22678937 | 13634706 | 13528529
MCR021026 | HPR162 | 2017-04-01 | Labor | 35626657 | 45781186 | 44110427
MCR021027 | HPR162 | 2017-04-01 | Material | 73433995 | 94364602 | 97306229
MCR021028 | HPR162 | 2017-04-01 | Equipment | 16241245 | 20870425 | 22191584
MCR021029 | HPR162 | 2017-04-01 | Subcontract | 85668510 | 110086274 | 131643263
MCR021030 | HPR162 | 2017-04-01 | Overhead | 22255739 | 28599207 | 14045540
MCR021031 | HPR162 | 2017-05-01 | Labor | 34076765 | 30847140 | 37306266
MCR021032 | HPR162 | 2017-05-01 | Material | 70239342 | 63582409 | 74828753
MCR021033 | HPR162 | 2017-05-01 | Equipment | 15534691 | 14062390 | 15502797
MCR021034 | HPR162 | 2017-05-01 | Subcontract | 81941610 | 74175595 | 61290833
MCR021035 | HPR162 | 2017-05-01 | Overhead | 21287532 | 19270006 | 14843416
MCR021036 | HPR162 | 2017-06-01 | Labor | 31718411 | 28601693 | 33641246
MCR021037 | HPR162 | 2017-06-01 | Material | 65378281 | 58954074 | 56523186
MCR021038 | HPR162 | 2017-06-01 | Equipment | 14459580 | 13038751 | 13816373
MCR021039 | HPR162 | 2017-06-01 | Subcontract | 76270669 | 68776153 | 84575912
MCR021040 | HPR162 | 2017-06-01 | Overhead | 19814284 | 17867290 | 15103816
MCR021041 | HPR162 | 2017-07-01 | Labor | 28624597 | 13139299 | 9940201
MCR021042 | HPR162 | 2017-07-01 | Material | 59001282 | 27082843 | 28463757
MCR021043 | HPR162 | 2017-07-01 | Equipment | 13049192 | 5989857 | 4847137
MCR021044 | HPR162 | 2017-07-01 | Subcontract | 68831227 | 31594997 | 26391998
MCR021045 | HPR162 | 2017-07-01 | Overhead | 17881598 | 8208034 | 13745363
MCR021046 | HPR162 | 2017-08-01 | Labor | 24880496 | 17550088 | 18390926
MCR021047 | HPR162 | 2017-08-01 | Material | 51283908 | 36174404 | 42724282
MCR021048 | HPR162 | 2017-08-01 | Equipment | 11342356 | 8000618 | 8433299
MCR021049 | HPR162 | 2017-08-01 | Subcontract | 59828095 | 42201263 | 45067095
MCR021050 | HPR162 | 2017-08-01 | Overhead | 15542683 | 10963425 | 13898708
MCR021051 | HPR162 | 2017-09-01 | Labor | 20588566 | 27388294 | 27123072
MCR021052 | HPR162 | 2017-09-01 | Material | 42437342 | 56453004 | 59115605
MCR021053 | HPR162 | 2017-09-01 | Equipment | 9385779 | 12485595 | 12793872
MCR021054 | HPR162 | 2017-09-01 | Subcontract | 49507641 | 65858391 | 66156019
MCR021055 | HPR162 | 2017-09-01 | Overhead | 12861542 | 17109288 | 14000636
MCR021056 | HPR162 | 2017-10-01 | Labor | 15877571 | 33976688 | 40222310
MCR021057 | HPR162 | 2017-10-01 | Material | 32726996 | 70033064 | 71499623
MCR021058 | HPR162 | 2017-10-01 | Equipment | 7238162 | 15489068 | 16086932
MCR021059 | HPR162 | 2017-10-01 | Subcontract | 38179497 | 81700965 | 69272669
MCR021060 | HPR162 | 2017-10-01 | Overhead | 9918615 | 21225015 | 15001231
MCR021061 | HPR162 | 2017-11-01 | Labor | 10920746 | 18878757 | 21846389
MCR021062 | HPR162 | 2017-11-01 | Material | 22509943 | 38913068 | 42888375
MCR021063 | HPR162 | 2017-11-01 | Equipment | 4978478 | 8606323 | 7593557
MCR021064 | HPR162 | 2017-11-01 | Subcontract | 26260225 | 45396203 | 59703270
MCR021065 | HPR162 | 2017-11-01 | Overhead | 6822119 | 11793436 | 12719668
MCR021066 | HPR162 | 2017-12-01 | Labor | 5981064 | 19819245 | 20018232
MCR021067 | HPR162 | 2017-12-01 | Material | 12328224 | 40851611 | 39957460
MCR021068 | HPR162 | 2017-12-01 | Equipment | 2726608 | 9035067 | 8857429
MCR021069 | HPR162 | 2017-12-01 | Subcontract | 14382175 | 47657719 | 48822894
MCR021070 | HPR162 | 2017-12-01 | Overhead | 3736331 | 12380953 | 13891897
MCR021071 | HPR162 | 2018-01-01 | Labor | 1600476 | 16355661 | 18846908
MCR021072 | HPR162 | 2018-01-01 | Material | 3298917 | 33712439 | 36228726
MCR021073 | HPR162 | 2018-01-01 | Equipment | 729615 | 7456111 | 8071193
MCR021074 | HPR162 | 2018-01-01 | Subcontract | 3848535 | 39329121 | 37355385
MCR021075 | HPR162 | 2018-01-01 | Overhead | 999807 | 10217274 | 15472064
MCR021076 | HPR162 | 2018-02-01 | Labor | 0 | 13989531 | 13180466
MCR021077 | HPR162 | 2018-02-01 | Material | 0 | 28835351 | 32355275
MCR021078 | HPR162 | 2018-02-01 | Equipment | 0 | 6377455 | 6319861
MCR021079 | HPR162 | 2018-02-01 | Subcontract | 0 | 33639482 | 34628390
MCR021080 | HPR162 | 2018-02-01 | Overhead | 0 | 8739169 | 14080515
MCR021081 | HPR162 | 2018-03-01 | Labor | 0 | 7945429 | 10073099
MCR021082 | HPR162 | 2018-03-01 | Material | 0 | 16377191 | 16881198
MCR021083 | HPR162 | 2018-03-01 | Equipment | 0 | 3622110 | 3981538
MCR021084 | HPR162 | 2018-03-01 | Subcontract | 0 | 19105723 | 23008909
MCR021085 | HPR162 | 2018-03-01 | Overhead | 0 | 4963457 | 13804062
MCR021086 | HPR162 | 2018-04-01 | Labor | 0 | 3980272 | 4212254
MCR021087 | HPR162 | 2018-04-01 | Material | 0 | 8204172 | 9634484
MCR021088 | HPR162 | 2018-04-01 | Equipment | 0 | 1814500 | 1835693
MCR021089 | HPR162 | 2018-04-01 | Subcontract | 0 | 9571033 | 8531897
MCR021090 | HPR162 | 2018-04-01 | Overhead | 0 | 2486450 | 14480601
MCR021091 | HPR162 | 2018-05-01 | Labor | 0 | 917170 | 884956
MCR021092 | HPR162 | 2018-05-01 | Material | 0 | 1890479 | 1046910
MCR021093 | HPR162 | 2018-05-01 | Equipment | 0 | 418113 | 420970
MCR021094 | HPR162 | 2018-05-01 | Subcontract | 0 | 2205443 | 1838996
MCR021095 | HPR162 | 2018-05-01 | Overhead | 0 | 572950 | 15016432
MCR021096 | HPR163 | 2018-02-01 | Labor | 4504127 | 2778595 | 3074525
MCR021097 | HPR163 | 2018-02-01 | Material | 11071708 | 6830135 | 7166703
MCR021098 | HPR163 | 2018-02-01 | Equipment | 4833123 | 2981553 | 3568983
MCR021099 | HPR163 | 2018-02-01 | Subcontract | 9885867 | 6098591 | 6850351
MCR021100 | HPR163 | 2018-02-01 | Overhead | 4020859 | 2480468 | 27193625
MCR021101 | HPR163 | 2018-03-01 | Labor | 12874373 | 7984063 | 8399874
MCR021102 | HPR163 | 2018-03-01 | Material | 31646823 | 19625827 | 22620330
MCR021103 | HPR163 | 2018-03-01 | Equipment | 13814761 | 8567245 | 9175105
MCR021104 | HPR163 | 2018-03-01 | Subcontract | 28257276 | 17523793 | 17516158
MCR021105 | HPR163 | 2018-03-01 | Overhead | 11493025 | 7127417 | 27768856
MCR021106 | HPR163 | 2018-04-01 | Labor | 20301335 | 5667036 | 7867523
MCR021107 | HPR163 | 2018-04-01 | Material | 49903225 | 13930285 | 11982924
MCR021108 | HPR163 | 2018-04-01 | Equipment | 21784212 | 6080975 | 6032669
MCR021109 | HPR163 | 2018-04-01 | Subcontract | 44558317 | 12438275 | 14389339
MCR021110 | HPR163 | 2018-04-01 | Overhead | 18123115 | 5058995 | 27031573
MCR021111 | HPR163 | 2018-05-01 | Labor | 26803914 | 13207915 | 15995162
MCR021112 | HPR163 | 2018-05-01 | Material | 65887380 | 32466709 | 33948344
MCR021113 | HPR163 | 2018-05-01 | Equipment | 28761762 | 14172665 | 15525409
MCR021114 | HPR163 | 2018-05-01 | Subcontract | 58830481 | 28989347 | 30448726
MCR021115 | HPR163 | 2018-05-01 | Overhead | 23928004 | 11790779 | 27398128
MCR021116 | HPR163 | 2018-06-01 | Labor | 32401834 | 12087214 | 15030646
MCR021117 | HPR163 | 2018-06-01 | Material | 79647770 | 29711887 | 24296013
MCR021118 | HPR163 | 2018-06-01 | Equipment | 34768573 | 12970105 | 11799508
MCR021119 | HPR163 | 2018-06-01 | Subcontract | 71117058 | 26529581 | 26016590
MCR021120 | HPR163 | 2018-06-01 | Overhead | 28925299 | 10790324 | 28978324
MCR021121 | HPR163 | 2018-07-01 | Labor | 37115723 | 10383672 | 12615942
MCR021122 | HPR163 | 2018-07-01 | Material | 91235099 | 25524367 | 27776148
MCR021123 | HPR163 | 2018-07-01 | Equipment | 39826780 | 11142130 | 12917322
MCR021124 | HPR163 | 2018-07-01 | Subcontract | 81463321 | 22790568 | 27828129
MCR021125 | HPR163 | 2018-07-01 | Overhead | 33133414 | 9269562 | 28389727
MCR021126 | HPR163 | 2018-08-01 | Labor | 40967209 | 16094021 | 16520118
MCR021127 | HPR163 | 2018-08-01 | Material | 100702533 | 39561121 | 43855094
MCR021128 | HPR163 | 2018-08-01 | Equipment | 43959591 | 17269583 | 16315492
MCR021129 | HPR163 | 2018-08-01 | Subcontract | 89916741 | 35323909 | 37301169
MCR021130 | HPR163 | 2018-08-01 | Overhead | 36571657 | 14367223 | 26870145
MCR021131 | HPR163 | 2018-09-01 | Labor | 43979039 | 38825250 | 49516719
MCR021132 | HPR163 | 2018-09-01 | Material | 108105991 | 95437332 | 89401564
MCR021133 | HPR163 | 2018-09-01 | Equipment | 47191417 | 41661177 | 45389234
MCR021134 | HPR163 | 2018-09-01 | Subcontract | 96527248 | 85215472 | 103922922
MCR021135 | HPR163 | 2018-09-01 | Overhead | 39260335 | 34659519 | 26485990
MCR021136 | HPR163 | 2018-10-01 | Labor | 46175219 | 24726737 | 27900391
MCR021137 | HPR163 | 2018-10-01 | Material | 113504476 | 60781418 | 69594287
MCR021138 | HPR163 | 2018-10-01 | Equipment | 49548013 | 26532861 | 30351420
MCR021139 | HPR163 | 2018-10-01 | Subcontract | 101347526 | 54271396 | 44117929
MCR021140 | HPR163 | 2018-10-01 | Overhead | 41220877 | 22073696 | 27926605
MCR021141 | HPR163 | 2018-11-01 | Labor | 47581173 | 37738208 | 49007818
MCR021142 | HPR163 | 2018-11-01 | Material | 116960486 | 92765245 | 100762620
MCR021143 | HPR163 | 2018-11-01 | Equipment | 51056662 | 40494734 | 46561616
MCR021144 | HPR163 | 2018-11-01 | Subcontract | 104433378 | 82829580 | 101079053
MCR021145 | HPR163 | 2018-11-01 | Overhead | 42475979 | 33689110 | 27417463
MCR021146 | HPR163 | 2018-12-01 | Labor | 48223944 | 36205071 | 39582176
MCR021147 | HPR163 | 2018-12-01 | Material | 118540498 | 88996602 | 77745163
MCR021148 | HPR163 | 2018-12-01 | Equipment | 51746383 | 38849611 | 36550183
MCR021149 | HPR163 | 2018-12-01 | Subcontract | 105844163 | 79464579 | 95301737
MCR021150 | HPR163 | 2018-12-01 | Overhead | 43049785 | 32320470 | 27649670
MCR021151 | HPR163 | 2019-01-01 | Labor | 48132442 | 22086419 | 32597248
MCR021152 | HPR163 | 2019-01-01 | Material | 118315576 | 54291187 | 60268217
MCR021153 | HPR163 | 2019-01-01 | Equipment | 51648198 | 23699686 | 27407545
MCR021154 | HPR163 | 2019-01-01 | Subcontract | 105643331 | 48476304 | 37159359
MCR021155 | HPR163 | 2019-01-01 | Overhead | 42968101 | 19716670 | 27494028
MCR021156 | HPR163 | 2019-02-01 | Labor | 47337747 | 23413032 | 28297243
MCR021157 | HPR163 | 2019-02-01 | Material | 116362114 | 57552166 | 54462043
MCR021158 | HPR163 | 2019-02-01 | Equipment | 50795455 | 25123198 | 26485032
MCR021159 | HPR163 | 2019-02-01 | Subcontract | 103899096 | 51388015 | 61786641
MCR021160 | HPR163 | 2019-02-01 | Overhead | 42258672 | 20900945 | 29107817
MCR021161 | HPR163 | 2019-03-01 | Labor | 45873489 | 35681239 | 45314957
MCR021162 | HPR163 | 2019-03-01 | Material | 112762787 | 87708957 | 90752246
MCR021163 | HPR163 | 2019-03-01 | Equipment | 49224244 | 38287517 | 40063689
MCR021164 | HPR163 | 2019-03-01 | Subcontract | 100685275 | 78314848 | 87068489
MCR021165 | HPR163 | 2019-03-01 | Overhead | 40951521 | 31852842 | 29502516
MCR021166 | HPR163 | 2019-04-01 | Labor | 43776354 | 32174375 | 35533871
MCR021167 | HPR163 | 2019-04-01 | Material | 107607766 | 79088647 | 75164130
MCR021168 | HPR163 | 2019-04-01 | Equipment | 46973927 | 34524500 | 40153843
MCR021169 | HPR163 | 2019-04-01 | Subcontract | 96082386 | 70617820 | 73945095
MCR021170 | HPR163 | 2019-04-01 | Overhead | 39079397 | 28722245 | 26984696
MCR021171 | HPR163 | 2019-05-01 | Labor | 41086731 | 25109145 | 34928853
MCR021172 | HPR163 | 2019-05-01 | Material | 100996334 | 61721426 | 59983834
MCR021173 | HPR163 | 2019-05-01 | Equipment | 44087844 | 26943202 | 30093323
MCR021174 | HPR163 | 2019-05-01 | Subcontract | 90179075 | 55110724 | 61528180
MCR021175 | HPR163 | 2019-05-01 | Overhead | 36678355 | 22415075 | 26036347
MCR021176 | HPR163 | 2019-06-01 | Labor | 37849600 | 30032872 | 36738313
MCR021177 | HPR163 | 2019-06-01 | Material | 93039062 | 73824563 | 79736218
MCR021178 | HPR163 | 2019-06-01 | Equipment | 40614263 | 32226574 | 32577353
MCR021179 | HPR163 | 2019-06-01 | Subcontract | 83074070 | 65917549 | 74903144
MCR021180 | HPR163 | 2019-06-01 | Overhead | 33788550 | 26810513 | 26685525
MCR021181 | HPR163 | 2019-07-01 | Labor | 34115776 | 41049938 | 71955234
MCR021182 | HPR163 | 2019-07-01 | Material | 83860852 | 100905893 | 149208965
MCR021183 | HPR163 | 2019-07-01 | Equipment | 36607707 | 44048364 | 48262447
MCR021184 | HPR163 | 2019-07-01 | Subcontract | 74878896 | 90098320 | 99107952
MCR021185 | HPR163 | 2019-07-01 | Overhead | 30455344 | 36645510 | 28199035
MCR021186 | HPR163 | 2019-08-01 | Labor | 29943701 | 26557114 | 77583943
MCR021187 | HPR163 | 2019-08-01 | Material | 73605370 | 65280716 | 116642911
MCR021188 | HPR163 | 2019-08-01 | Equipment | 32130890 | 28496936 | 28761832
MCR021189 | HPR163 | 2019-08-01 | Subcontract | 65721833 | 58288794 | 59977668
MCR021190 | HPR163 | 2019-08-01 | Overhead | 26730910 | 23707685 | 26294958
MCR021191 | HPR163 | 2019-09-01 | Labor | 25402205 | 37296590 | 46839626
MCR021192 | HPR163 | 2019-09-01 | Material | 62441805 | 91679693 | 95626249
MCR021193 | HPR163 | 2019-09-01 | Equipment | 27257668 | 40020859 | 50523187
MCR021194 | HPR163 | 2019-09-01 | Subcontract | 55753946 | 81860296 | 101224798
MCR021195 | HPR163 | 2019-09-01 | Overhead | 22676691 | 33294875 | 27718095
MCR021196 | HPR163 | 2019-10-01 | Labor | 20574986 | 45898019 | 60037337
MCR021197 | HPR163 | 2019-10-01 | Material | 50575893 | 112823082 | 127484518
MCR021198 | HPR163 | 2019-10-01 | Equipment | 22077852 | 49250564 | 44567648
MCR021199 | HPR163 | 2019-10-01 | Subcontract | 45158939 | 100739113 | 88667865
MCR021200 | HPR163 | 2019-10-01 | Overhead | 18367405 | 40973418 | 28091946
MCR021201 | HPR163 | 2019-11-01 | Labor | 15568591 | 25257377 | 30124626
MCR021202 | HPR163 | 2019-11-01 | Material | 38269549 | 62085798 | 55132396
MCR021203 | HPR163 | 2019-11-01 | Equipment | 16705774 | 27102261 | 34375798
MCR021204 | HPR163 | 2019-11-01 | Subcontract | 34170671 | 55436069 | 60173863
MCR021205 | HPR163 | 2019-11-01 | Overhead | 13898169 | 22547402 | 26919583
MCR021206 | HPR163 | 2019-12-01 | Labor | 10528613 | 25493385 | 35787860
MCR021207 | HPR163 | 2019-12-01 | Material | 25880650 | 62665935 | 66030925
MCR021208 | HPR163 | 2019-12-01 | Equipment | 11297658 | 27355507 | 25824945
MCR021209 | HPR163 | 2019-12-01 | Subcontract | 23108691 | 55954070 | 71677236
MCR021210 | HPR163 | 2019-12-01 | Overhead | 9398952 | 22758087 | 27306938
MCR021211 | HPR163 | 2020-01-01 | Labor | 5680408 | 36035893 | 41809892
MCR021212 | HPR163 | 2020-01-01 | Material | 13963156 | 88580742 | 83530855
MCR021213 | HPR163 | 2020-01-01 | Equipment | 6095325 | 38668076 | 36575343
MCR021214 | HPR163 | 2020-01-01 | Subcontract | 12467626 | 79093260 | 84894652
MCR021215 | HPR163 | 2020-01-01 | Overhead | 5070932 | 32169444 | 26706475
MCR021216 | HPR163 | 2020-02-01 | Labor | 1501423 | 32530133 | 44336869
MCR021217 | HPR163 | 2020-02-01 | Material | 3690687 | 79963145 | 77909552
MCR021218 | HPR163 | 2020-02-01 | Equipment | 1611092 | 34906244 | 41125459
MCR021219 | HPR163 | 2020-02-01 | Subcontract | 3295394 | 71398655 | 100450746
MCR021220 | HPR163 | 2020-02-01 | Overhead | 1340329 | 29039832 | 28058412
MCR021221 | HPR163 | 2020-03-01 | Labor | 0 | 20327701 | 26150962
MCR021222 | HPR163 | 2020-03-01 | Material | 0 | 49968036 | 52811923
MCR021223 | HPR163 | 2020-03-01 | Equipment | 0 | 21812504 | 20159906
MCR021224 | HPR163 | 2020-03-01 | Subcontract | 0 | 44616186 | 88447473
MCR021225 | HPR163 | 2020-03-01 | Overhead | 0 | 18146652 | 27240095
MCR021226 | HPR163 | 2020-04-01 | Labor | 0 | 30031215 | 35698379
MCR021227 | HPR163 | 2020-04-01 | Material | 0 | 73820490 | 71305173
MCR021228 | HPR163 | 2020-04-01 | Equipment | 0 | 32224796 | 34004240
MCR021229 | HPR163 | 2020-04-01 | Subcontract | 0 | 65913912 | 100668004
MCR021230 | HPR163 | 2020-04-01 | Overhead | 0 | 26809034 | 27093457
MCR021231 | HPR163 | 2020-05-01 | Labor | 0 | 21713270 | 31802089
MCR021232 | HPR163 | 2020-05-01 | Material | 0 | 53373940 | 59027750
MCR021233 | HPR163 | 2020-05-01 | Equipment | 0 | 23299281 | 28775284
MCR021234 | HPR163 | 2020-05-01 | Subcontract | 0 | 47657299 | 93857182
MCR021235 | HPR163 | 2020-05-01 | Overhead | 0 | 19383558 | 26880036
MCR021236 | HPR163 | 2020-06-01 | Labor | 0 | 9919139 | 15328541
MCR021237 | HPR163 | 2020-06-01 | Material | 0 | 24382487 | 24547094
MCR021238 | HPR163 | 2020-06-01 | Equipment | 0 | 10643666 | 10540605
MCR021239 | HPR163 | 2020-06-01 | Subcontract | 0 | 21770990 | 53413581
MCR021240 | HPR163 | 2020-06-01 | Overhead | 0 | 8854871 | 26572730
MCR021241 | HPR163 | 2020-07-01 | Labor | 0 | 7465625 | 7242930
MCR021242 | HPR163 | 2020-07-01 | Material | 0 | 18351441 | 17493854
MCR021243 | HPR163 | 2020-07-01 | Equipment | 0 | 8010939 | 10903170
MCR021244 | HPR163 | 2020-07-01 | Subcontract | 0 | 16385902 | 63984025
MCR021245 | HPR163 | 2020-07-01 | Overhead | 0 | 6664605 | 27069862
MCR021246 | HPR163 | 2020-08-01 | Labor | 0 | 4706309 | 6731151
MCR021247 | HPR163 | 2020-08-01 | Material | 0 | 11568698 | 13698857
MCR021248 | HPR163 | 2020-08-01 | Equipment | 0 | 5050074 | 4402624
MCR021249 | HPR163 | 2020-08-01 | Subcontract | 0 | 10329627 | 49313552
MCR021250 | HPR163 | 2020-08-01 | Overhead | 0 | 4201349 | 27335887
MCR021251 | HPR163 | 2020-09-01 | Labor | 0 | 9518602 | 13632545
MCR021252 | HPR163 | 2020-09-01 | Material | 0 | 23397918 | 23305896
MCR021253 | HPR163 | 2020-09-01 | Equipment | 0 | 10213873 | 11519764
MCR021254 | HPR163 | 2020-09-01 | Subcontract | 0 | 20891873 | 57797570
MCR021255 | HPR163 | 2020-09-01 | Overhead | 0 | 8497310 | 27597572
MCR021256 | HPR163 | 2020-10-01 | Labor | 0 | 5896078 | 7232976
MCR021257 | HPR163 | 2020-10-01 | Material | 0 | 14493300 | 17597806
MCR021258 | HPR163 | 2020-10-01 | Equipment | 0 | 6326748 | 7928672
MCR021259 | HPR163 | 2020-10-01 | Subcontract | 0 | 12940988 | 58248667
MCR021260 | HPR163 | 2020-10-01 | Overhead | 0 | 5263462 | 30044471
MCR021261 | HPR163 | 2020-11-01 | Labor | 0 | 10879218 | 14525980
MCR021262 | HPR163 | 2020-11-01 | Material | 0 | 26742481 | 28292472
MCR021263 | HPR163 | 2020-11-01 | Equipment | 0 | 11673873 | 16050727
MCR021264 | HPR163 | 2020-11-01 | Subcontract | 0 | 23878215 | 53174886
MCR021265 | HPR163 | 2020-11-01 | Overhead | 0 | 9711939 | 28530155
MCR021266 | HPR163 | 2020-12-01 | Labor | 0 | 2812914 | 3968739
MCR021267 | HPR163 | 2020-12-01 | Material | 0 | 6914495 | 5335294
MCR021268 | HPR163 | 2020-12-01 | Equipment | 0 | 3018378 | 3186635
MCR021269 | HPR163 | 2020-12-01 | Subcontract | 0 | 6173914 | 24785440
MCR021270 | HPR163 | 2020-12-01 | Overhead | 0 | 2511104 | 27176353
MCR021271 | HPR163 | 2021-01-01 | Labor | 0 | 716574 | 970823
MCR021272 | HPR163 | 2021-01-01 | Material | 0 | 1761429 | 2190021
MCR021273 | HPR163 | 2021-01-01 | Equipment | 0 | 768915 | 1007730
MCR021274 | HPR163 | 2021-01-01 | Subcontract | 0 | 1572770 | 39690234
MCR021275 | HPR163 | 2021-01-01 | Overhead | 0 | 639690 | 26500652
MCR021276 | HPR164 | 2017-07-01 | Labor | 6684902 | 2675828 | 2755937
MCR021277 | HPR164 | 2017-07-01 | Material | 17367755 | 6951953 | 7405574
MCR021278 | HPR164 | 2017-07-01 | Equipment | 3636748 | 1455715 | 1632332
MCR021279 | HPR164 | 2017-07-01 | Subcontract | 36075833 | 14440410 | 16957219
MCR021280 | HPR164 | 2017-07-01 | Overhead | 5299602 | 2121321 | 28034972
MCR021281 | HPR164 | 2017-08-01 | Labor | 18864712 | 10527570 | 10682027
MCR021282 | HPR164 | 2017-08-01 | Material | 49011594 | 27351225 | 25966235
MCR021283 | HPR164 | 2017-08-01 | Equipment | 10262858 | 5727252 | 5812738
MCR021284 | HPR164 | 2017-08-01 | Subcontract | 101805563 | 56813228 | 56769240
MCR021285 | HPR164 | 2017-08-01 | Overhead | 14955411 | 8345960 | 28564121
MCR021286 | HPR164 | 2017-09-01 | Labor | 29292036 | 25772068 | 26452940
MCR021287 | HPR164 | 2017-09-01 | Material | 76102376 | 66957298 | 70368741
MCR021288 | HPR164 | 2017-09-01 | Equipment | 15935574 | 14020626 | 15047276
MCR021289 | HPR164 | 2017-09-01 | Subcontract | 158077807 | 139081899 | 136880526
MCR021290 | HPR164 | 2017-09-01 | Overhead | 23221900 | 20431369 | 30383076
MCR021291 | HPR164 | 2017-10-01 | Labor | 38012060 | 21501347 | 24308880
MCR021292 | HPR164 | 2017-10-01 | Material | 98757492 | 55861722 | 51639399
MCR021293 | HPR164 | 2017-10-01 | Equipment | 20679476 | 11697251 | 13847222
MCR021294 | HPR164 | 2017-10-01 | Subcontract | 205136405 | 116034465 | 128013168
MCR021295 | HPR164 | 2017-10-01 | Overhead | 30134888 | 17045661 | 27202832
MCR021296 | HPR164 | 2017-11-01 | Labor | 45072516 | 21085003 | 22301407
MCR021297 | HPR164 | 2017-11-01 | Material | 117100960 | 54780038 | 58275372
MCR021298 | HPR164 | 2017-11-01 | Equipment | 24520535 | 11470750 | 10600842
MCR021299 | HPR164 | 2017-11-01 | Subcontract | 243238962 | 113787620 | 98842749
MCR021300 | HPR164 | 2017-11-01 | Overhead | 35732219 | 16715596 | 29074358
MCR021301 | HPR164 | 2017-12-01 | Labor | 50524040 | 29009020 | 29723554
MCR021302 | HPR164 | 2017-12-01 | Material | 131264328 | 75367084 | 75885304
MCR021303 | HPR164 | 2017-12-01 | Equipment | 27486295 | 15781606 | 15972813
MCR021304 | HPR164 | 2017-12-01 | Subcontract | 272658730 | 156550478 | 135157755
MCR021305 | HPR164 | 2017-12-01 | Overhead | 40054033 | 22997533 | 30642579
MCR021306 | HPR164 | 2018-01-01 | Labor | 54420590 | 57553049 | 58884662
MCR021307 | HPR164 | 2018-01-01 | Material | 141387787 | 149526092 | 162474045
MCR021308 | HPR164 | 2018-01-01 | Equipment | 29606112 | 31310245 | 31387948
MCR021309 | HPR164 | 2018-01-01 | Subcontract | 293686907 | 310591575 | 354564547
MCR021310 | HPR164 | 2018-01-01 | Overhead | 43143108 | 45626433 | 30516127
MCR021311 | HPR164 | 2018-02-01 | Labor | 56819980 | 44203644 | 47874769
MCR021312 | HPR164 | 2018-02-01 | Material | 147621539 | 114843580 | 108577891
MCR021313 | HPR164 | 2018-02-01 | Equipment | 30911438 | 24047848 | 25474450
MCR021314 | HPR164 | 2018-02-01 | Subcontract | 306635488 | 238549995 | 225511610
MCR021315 | HPR164 | 2018-02-01 | Overhead | 45045277 | 35043402 | 27829702
MCR021316 | HPR164 | 2018-03-01 | Labor | 57784543 | 39308835 | 69991444
MCR021317 | HPR164 | 2018-03-01 | Material | 150127528 | 102126587 | 159524739
MCR021318 | HPR164 | 2018-03-01 | Equipment | 31436184 | 21384953 | 24330623
MCR021319 | HPR164 | 2018-03-01 | Subcontract | 311840860 | 212134598 | 208059319
MCR021320 | HPR164 | 2018-03-01 | Overhead | 45809955 | 31162935 | 27047603
MCR021321 | HPR164 | 2018-04-01 | Labor | 57381987 | 30738315 | 56654140
MCR021322 | HPR164 | 2018-04-01 | Material | 149081664 | 79859891 | 136186684
MCR021323 | HPR164 | 2018-04-01 | Equipment | 31217184 | 16722384 | 18386808
MCR021324 | HPR164 | 2018-04-01 | Subcontract | 309668421 | 165882816 | 165260091
MCR021325 | HPR164 | 2018-04-01 | Overhead | 45490820 | 24368469 | 31824457
MCR021326 | HPR164 | 2018-05-01 | Labor | 55686520 | 52546013 | 56103234
MCR021327 | HPR164 | 2018-05-01 | Material | 144676746 | 136517529 | 130234856
MCR021328 | HPR164 | 2018-05-01 | Equipment | 30294809 | 28586297 | 33662097
MCR021329 | HPR164 | 2018-05-01 | Subcontract | 300518644 | 283570537 | 265174364
MCR021330 | HPR164 | 2018-05-01 | Overhead | 44146702 | 41656996 | 30418192
MCR021331 | HPR164 | 2018-06-01 | Labor | 52780366 | 42019691 | 44081219
MCR021332 | HPR164 | 2018-06-01 | Material | 137126391 | 109169546 | 113525754
MCR021333 | HPR164 | 2018-06-01 | Equipment | 28713791 | 22859724 | 20571996
MCR021334 | HPR164 | 2018-06-01 | Subcontract | 284835249 | 226764043 | 223693791
MCR021335 | HPR164 | 2018-06-01 | Overhead | 41842785 | 33312025 | 28445377
MCR021336 | HPR164 | 2018-07-01 | Labor | 48755867 | 36258820 | 41360270
MCR021337 | HPR164 | 2018-07-01 | Material | 126670515 | 94202476 | 111521014
MCR021338 | HPR164 | 2018-07-01 | Equipment | 26524367 | 19725672 | 20647923
MCR021339 | HPR164 | 2018-07-01 | Subcontract | 263116585 | 195674848 | 217592261
MCR021340 | HPR164 | 2018-07-01 | Overhead | 38652276 | 28744969 | 29423924
MCR021341 | HPR164 | 2018-08-01 | Labor | 43718542 | 36151309 | 33710680
MCR021342 | HPR164 | 2018-08-01 | Material | 113583258 | 93923157 | 91197893
MCR021343 | HPR164 | 2018-08-01 | Equipment | 23783940 | 19667183 | 17556042
MCR021344 | HPR164 | 2018-08-01 | Subcontract | 235932088 | 195094654 | 160865220
MCR021345 | HPR164 | 2018-08-01 | Overhead | 34658827 | 28659738 | 29878530
MCR021346 | HPR164 | 2018-09-01 | Labor | 37791717 | 52166417 | 52532887
MCR021347 | HPR164 | 2018-09-01 | Material | 98185028 | 135531317 | 143375653
MCR021348 | HPR164 | 2018-09-01 | Equipment | 20559604 | 28379788 | 29955901
MCR021349 | HPR164 | 2018-09-01 | Subcontract | 203947299 | 281522005 | 306556877
MCR021350 | HPR164 | 2018-09-01 | Overhead | 29960207 | 41356064 | 30917775
MCR021351 | HPR164 | 2018-10-01 | Labor | 31124039 | 52261197 | 53563737
MCR021352 | HPR164 | 2018-10-01 | Material | 80862023 | 135777561 | 148575666
MCR021353 | HPR164 | 2018-10-01 | Equipment | 16932227 | 28431351 | 31236033
MCR021354 | HPR164 | 2018-10-01 | Subcontract | 167964419 | 282033496 | 286104833
MCR021355 | HPR164 | 2018-10-01 | Overhead | 24674260 | 41431202 | 29046748
MCR021356 | HPR164 | 2018-11-01 | Labor | 23902785 | 33504894 | 38944745
MCR021357 | HPR164 | 2018-11-01 | Material | 62100794 | 87047620 | 89640194
MCR021358 | HPR164 | 2018-11-01 | Equipment | 13003691 | 18227470 | 16686271
MCR021359 | HPR164 | 2018-11-01 | Subcontract | 128994098 | 180812974 | 180825050
MCR021360 | HPR164 | 2018-11-01 | Overhead | 18949453 | 26561735 | 31655499
MCR021361 | HPR164 | 2018-12-01 | Labor | 16380651 | 58539682 | 63019739
MCR021362 | HPR164 | 2018-12-01 | Material | 42557862 | 152089422 | 156603947
MCR021363 | HPR164 | 2018-12-01 | Equipment | 8911469 | 31846998 | 33081870
MCR021364 | HPR164 | 2018-12-01 | Subcontract | 88400045 | 315916054 | 459276371
MCR021365 | HPR164 | 2018-12-01 | Overhead | 12986118 | 46408608 | 25865150
MCR021366 | HPR164 | 2019-01-01 | Labor | 8942688 | 21079907 | 25025224
MCR021367 | HPR164 | 2019-01-01 | Material | 23233611 | 54766798 | 60971353
MCR021368 | HPR164 | 2019-01-01 | Equipment | 4865038 | 11467978 | 11931693
MCR021369 | HPR164 | 2019-01-01 | Subcontract | 48260232 | 113760119 | 139847845
MCR021370 | HPR164 | 2019-01-01 | Overhead | 7089510 | 16711556 | 31771422
MCR021371 | HPR164 | 2019-02-01 | Labor | 2386774 | 20919838 | 20983376
MCR021372 | HPR164 | 2019-02-01 | Material | 6200975 | 54350929 | 45300834
MCR021373 | HPR164 | 2019-02-01 | Equipment | 1298463 | 11380896 | 11325652
MCR021374 | HPR164 | 2019-02-01 | Subcontract | 12880499 | 112896286 | 198858414
MCR021375 | HPR164 | 2019-02-01 | Overhead | 1892167 | 16584657 | 31291485
MCR021376 | HPR164 | 2019-03-01 | Labor | 0 | 21365588 | 21604318
MCR021377 | HPR164 | 2019-03-01 | Material | 0 | 55509013 | 64264768
MCR021378 | HPR164 | 2019-03-01 | Equipment | 0 | 11623395 | 11823741
MCR021379 | HPR164 | 2019-03-01 | Subcontract | 0 | 115301827 | 214557353
MCR021380 | HPR164 | 2019-03-01 | Overhead | 0 | 16938035 | 31059026
MCR021381 | HPR164 | 2019-04-01 | Labor | 0 | 11199908 | 11023884
MCR021382 | HPR164 | 2019-04-01 | Material | 0 | 29097999 | 29517984
MCR021383 | HPR164 | 2019-04-01 | Equipment | 0 | 6093020 | 6611051
MCR021384 | HPR164 | 2019-04-01 | Subcontract | 0 | 60441580 | 102593368
MCR021385 | HPR164 | 2019-04-01 | Overhead | 0 | 8878971 | 29088859
MCR021386 | HPR164 | 2019-05-01 | Labor | 0 | 9513938 | 10231291
MCR021387 | HPR164 | 2019-05-01 | Material | 0 | 24717753 | 24252070
MCR021388 | HPR164 | 2019-05-01 | Equipment | 0 | 5175812 | 5373710
MCR021389 | HPR164 | 2019-05-01 | Subcontract | 0 | 51343051 | 106118100
MCR021390 | HPR164 | 2019-05-01 | Overhead | 0 | 7542382 | 28195381
MCR021391 | HPR164 | 2019-06-01 | Labor | 0 | 5457447 | 6529349
MCR021392 | HPR164 | 2019-06-01 | Material | 0 | 14178758 | 16648753
MCR021393 | HPR164 | 2019-06-01 | Equipment | 0 | 2968983 | 3392896
MCR021394 | HPR164 | 2019-06-01 | Subcontract | 0 | 29451734 | 91585232
MCR021395 | HPR164 | 2019-06-01 | Overhead | 0 | 4326510 | 29297709
MCR021396 | HPR164 | 2019-07-01 | Labor | 0 | 967985 | 997837
MCR021397 | HPR164 | 2019-07-01 | Material | 0 | 2514881 | 3136708
MCR021398 | HPR164 | 2019-07-01 | Equipment | 0 | 526607 | 725771
MCR021399 | HPR164 | 2019-07-01 | Subcontract | 0 | 5223842 | 74396588
MCR021400 | HPR164 | 2019-07-01 | Overhead | 0 | 767391 | 29812337
MCR021401 | HPR165 | 2020-05-01 | Labor | 3175012 | 2582144 | 2618673
MCR021402 | HPR165 | 2020-05-01 | Material | 6935169 | 5640169 | 6430009
MCR021403 | HPR165 | 2020-05-01 | Equipment | 1651773 | 1343339 | 1342454
MCR021404 | HPR165 | 2020-05-01 | Subcontract | 10304646 | 8380466 | 8050485
MCR021405 | HPR165 | 2020-05-01 | Overhead | 2104801 | 1711773 | 12505813
MCR021406 | HPR165 | 2020-06-01 | Labor | 8959846 | 9031480 | 9401476
MCR021407 | HPR165 | 2020-06-01 | Material | 19570962 | 19727432 | 18558737
MCR021408 | HPR165 | 2020-06-01 | Equipment | 4661284 | 4698551 | 4900812
MCR021409 | HPR165 | 2020-06-01 | Subcontract | 29079586 | 29312077 | 28636307
MCR021410 | HPR165 | 2020-06-01 | Overhead | 5939723 | 5987211 | 10902686
MCR021411 | HPR165 | 2020-07-01 | Labor | 13912332 | 5844276 | 6118791
MCR021412 | HPR165 | 2020-07-01 | Material | 30388661 | 12765634 | 13348036
MCR021413 | HPR165 | 2020-07-01 | Equipment | 7237773 | 3040435 | 2833011
MCR021414 | HPR165 | 2020-07-01 | Subcontract | 45153104 | 18967864 | 18631726
MCR021415 | HPR165 | 2020-07-01 | Overhead | 9222860 | 3874328 | 11294646
MCR021416 | HPR165 | 2020-08-01 | Labor | 18053930 | 8866519 | 7777938
MCR021417 | HPR165 | 2020-08-01 | Material | 39435142 | 19367108 | 17909258
MCR021418 | HPR165 | 2020-08-01 | Equipment | 9392405 | 4612731 | 4584891
MCR021419 | HPR165 | 2020-08-01 | Subcontract | 58594850 | 28776689 | 30530553
MCR021420 | HPR165 | 2020-08-01 | Overhead | 11968437 | 5877854 | 11867599
MCR021421 | HPR165 | 2020-09-01 | Labor | 21407313 | 22725100 | 23066696
MCR021422 | HPR165 | 2020-09-01 | Material | 46759925 | 49638362 | 49227455
MCR021423 | HPR165 | 2020-09-01 | Equipment | 11136974 | 11822541 | 12587058
MCR021424 | HPR165 | 2020-09-01 | Subcontract | 69478407 | 73755343 | 75435561
MCR021425 | HPR165 | 2020-09-01 | Overhead | 14191485 | 15065081 | 12122293
MCR021426 | HPR165 | 2020-10-01 | Labor | 23996529 | 15586731 | 13347004
MCR021427 | HPR165 | 2020-10-01 | Material | 52415541 | 34046046 | 32395912
MCR021428 | HPR165 | 2020-10-01 | Equipment | 12483991 | 8108865 | 8065096
MCR021429 | HPR165 | 2020-10-01 | Subcontract | 77881825 | 50587443 | 62165164
MCR021430 | HPR165 | 2020-10-01 | Overhead | 15907946 | 10332864 | 12363322
MCR021431 | HPR165 | 2020-11-01 | Labor | 25847206 | 20634338 | 22368014
MCR021432 | HPR165 | 2020-11-01 | Material | 56457969 | 45071518 | 49268067
MCR021433 | HPR165 | 2020-11-01 | Equipment | 13446791 | 10734840 | 8981521
MCR021434 | HPR165 | 2020-11-01 | Subcontract | 83888281 | 66969681 | 59679855
MCR021435 | HPR165 | 2020-11-01 | Overhead | 17134810 | 13679059 | 11536520
MCR021436 | HPR165 | 2020-12-01 | Labor | 26986803 | 23499697 | 24311936
MCR021437 | HPR165 | 2020-12-01 | Material | 58947186 | 51330312 | 52828353
MCR021438 | HPR165 | 2020-12-01 | Equipment | 14039656 | 12225519 | 13020623
MCR021439 | HPR165 | 2020-12-01 | Subcontract | 87586894 | 76269334 | 75193542
MCR021440 | HPR165 | 2020-12-01 | Overhead | 17890279 | 15578582 | 11559861
MCR021441 | HPR165 | 2021-01-01 | Labor | 27444925 | 27659042 | 25565113
MCR021442 | HPR165 | 2021-01-01 | Material | 59947860 | 60415556 | 61878252
MCR021443 | HPR165 | 2021-01-01 | Equipment | 14277990 | 14389383 | 16188935
MCR021444 | HPR165 | 2021-01-01 | Subcontract | 89073748 | 89768676 | 106854917
MCR021445 | HPR165 | 2021-01-01 | Overhead | 18193980 | 18335924 | 10264347
MCR021446 | HPR165 | 2021-02-01 | Labor | 27253730 | 23286423 | 23299595
MCR021447 | HPR165 | 2021-02-01 | Material | 59530233 | 50864459 | 51932733
MCR021448 | HPR165 | 2021-02-01 | Equipment | 14178522 | 12114565 | 10474282
MCR021449 | HPR165 | 2021-02-01 | Subcontract | 88453216 | 75577143 | 61419468
MCR021450 | HPR165 | 2021-02-01 | Overhead | 18067232 | 15437197 | 10858319
MCR021451 | HPR165 | 2021-03-01 | Labor | 26448463 | 13477184 | 14075446
MCR021452 | HPR165 | 2021-03-01 | Material | 57771293 | 29438170 | 32670764
MCR021453 | HPR165 | 2021-03-01 | Equipment | 13759589 | 7011391 | 8440666
MCR021454 | HPR165 | 2021-03-01 | Subcontract | 85839688 | 43740813 | 52550556
MCR021455 | HPR165 | 2021-03-01 | Overhead | 17533399 | 8934389 | 11353428
MCR021456 | HPR165 | 2021-04-01 | Labor | 25068177 | 22091466 | 23810788
MCR021457 | HPR165 | 2021-04-01 | Material | 54756338 | 48254317 | 51938936
MCR021458 | HPR165 | 2021-04-01 | Equipment | 13041507 | 11492898 | 10360880
MCR021459 | HPR165 | 2021-04-01 | Subcontract | 81359907 | 71698855 | 85591232
MCR021460 | HPR165 | 2021-04-01 | Overhead | 16618370 | 14645028 | 11620018
MCR021461 | HPR165 | 2021-05-01 | Labor | 23156731 | 30079514 | 27527044
MCR021462 | HPR165 | 2021-05-01 | Material | 50581172 | 65702586 | 72914834
MCR021463 | HPR165 | 2021-05-01 | Equipment | 12047093 | 15648613 | 16320826
MCR021464 | HPR165 | 2021-05-01 | Subcontract | 75156221 | 97624429 | 95470936
MCR021465 | HPR165 | 2021-05-01 | Overhead | 15351221 | 19940521 | 12186578
MCR021466 | HPR165 | 2021-06-01 | Labor | 20764240 | 34360673 | 33261880
MCR021467 | HPR165 | 2021-06-01 | Material | 45355261 | 75053906 | 81643750
MCR021468 | HPR165 | 2021-06-01 | Equipment | 10802420 | 17875849 | 18006242
MCR021469 | HPR165 | 2021-06-01 | Subcontract | 67391282 | 111519122 | 114434248
MCR021470 | HPR165 | 2021-06-01 | Overhead | 13765174 | 22778616 | 10970209
MCR021471 | HPR165 | 2021-07-01 | Labor | 17949278 | 14076091 | 12968871
MCR021472 | HPR165 | 2021-07-01 | Material | 39206549 | 30746360 | 40889928
MCR021473 | HPR165 | 2021-07-01 | Equipment | 9337960 | 7322967 | 6197831
MCR021474 | HPR165 | 2021-07-01 | Subcontract | 58255196 | 45684592 | 43043614
MCR021475 | HPR165 | 2021-07-01 | Overhead | 11899060 | 9331420 | 12256801
MCR021476 | HPR165 | 2021-08-01 | Labor | 14782447 | 16054686 | 17636422
MCR021477 | HPR165 | 2021-08-01 | Material | 32289250 | 35068199 | 37847119
MCR021478 | HPR165 | 2021-08-01 | Equipment | 7690443 | 8352315 | 8312881
MCR021479 | HPR165 | 2021-08-01 | Subcontract | 47977101 | 52106213 | 59039605
MCR021480 | HPR165 | 2021-08-01 | Overhead | 9799682 | 10643084 | 11653936
MCR021481 | HPR165 | 2021-09-01 | Labor | 11352692 | 14387641 | 15721047
MCR021482 | HPR165 | 2021-09-01 | Material | 24797649 | 31426877 | 34914375
MCR021483 | HPR165 | 2021-09-01 | Equipment | 5906142 | 7485048 | 7322753
MCR021484 | HPR165 | 2021-09-01 | Subcontract | 36845678 | 46695741 | 43599431
MCR021485 | HPR165 | 2021-09-01 | Overhead | 7526006 | 9537955 | 11793870
MCR021486 | HPR165 | 2021-10-01 | Labor | 7780034 | 8381114 | 6094064
MCR021487 | HPR165 | 2021-10-01 | Material | 16993904 | 18306840 | 25954971
MCR021488 | HPR165 | 2021-10-01 | Equipment | 4047497 | 4360204 | 4167941
MCR021489 | HPR165 | 2021-10-01 | Subcontract | 25250454 | 27201286 | 25555123
MCR021490 | HPR165 | 2021-10-01 | Overhead | 5157594 | 5556066 | 10873690
MCR021491 | HPR165 | 2021-11-01 | Labor | 4247354 | 10609265 | 11776469
MCR021492 | HPR165 | 2021-11-01 | Material | 9277481 | 23173783 | 27479679
MCR021493 | HPR165 | 2021-11-01 | Equipment | 2209650 | 5519380 | 6130065
MCR021494 | HPR165 | 2021-11-01 | Subcontract | 13784979 | 34432850 | 42073067
MCR021495 | HPR165 | 2021-11-01 | Overhead | 2815685 | 7033167 | 12872746
MCR021496 | HPR165 | 2021-12-01 | Labor | 1133605 | 14938892 | 14920920
MCR021497 | HPR165 | 2021-12-01 | Material | 2476130 | 32630974 | 43824082
MCR021498 | HPR165 | 2021-12-01 | Equipment | 589748 | 7771832 | 7789972
MCR021499 | HPR165 | 2021-12-01 | Subcontract | 3679166 | 48484853 | 46586730
MCR021500 | HPR165 | 2021-12-01 | Overhead | 751497 | 9903394 | 11568363
MCR021501 | HPR165 | 2022-01-01 | Labor | 0 | 8928511 | 8061264
MCR021502 | HPR165 | 2022-01-01 | Material | 0 | 19502517 | 23877083
MCR021503 | HPR165 | 2022-01-01 | Equipment | 0 | 4644982 | 4192798
MCR021504 | HPR165 | 2022-01-01 | Subcontract | 0 | 28977887 | 34422438
MCR021505 | HPR165 | 2022-01-01 | Overhead | 0 | 5918950 | 10785621
MCR021506 | HPR165 | 2022-02-01 | Labor | 0 | 1856192 | 2570929
MCR021507 | HPR165 | 2022-02-01 | Material | 0 | 4054475 | 3883172
MCR021508 | HPR165 | 2022-02-01 | Equipment | 0 | 965668 | 1286696
MCR021509 | HPR165 | 2022-02-01 | Subcontract | 0 | 6024356 | 4460604
MCR021510 | HPR165 | 2022-02-01 | Overhead | 0 | 1230520 | 11228212
MCR021511 | HPR165 | 2022-03-01 | Labor | 0 | 763668 | 1043969
MCR021512 | HPR165 | 2022-03-01 | Material | 0 | 1668077 | 2020331
MCR021513 | HPR165 | 2022-03-01 | Equipment | 0 | 397292 | 425565
MCR021514 | HPR165 | 2022-03-01 | Subcontract | 0 | 2478519 | 3333590
MCR021515 | HPR165 | 2022-03-01 | Overhead | 0 | 506256 | 11773368
MCR021516 | HPR166 | 2020-06-01 | Labor | 16832492 | 11802800 | 13605840
MCR021517 | HPR166 | 2020-06-01 | Material | 39781328 | 27894327 | 29004327
MCR021518 | HPR166 | 2020-06-01 | Equipment | 8275049 | 5802394 | 5481461
MCR021519 | HPR166 | 2020-06-01 | Subcontract | 98136590 | 68812538 | 67227471
MCR021520 | HPR166 | 2020-06-01 | Overhead | 14358792 | 10068262 | 42406878
MCR021521 | HPR166 | 2020-07-01 | Labor | 44341010 | 18486767 | 21013479
MCR021522 | HPR166 | 2020-07-01 | Material | 104794004 | 43690984 | 44503556
MCR021523 | HPR166 | 2020-07-01 | Equipment | 21798557 | 9088310 | 10455872
MCR021524 | HPR166 | 2020-07-01 | Subcontract | 258516413 | 107781324 | 119034719
MCR021525 | HPR166 | 2020-07-01 | Overhead | 37824662 | 15769955 | 40132130
MCR021526 | HPR166 | 2020-08-01 | Labor | 62980534 | 34347539 | 40737603
MCR021527 | HPR166 | 2020-08-01 | Material | 148846007 | 81175782 | 90976369
MCR021528 | HPR166 | 2020-08-01 | Equipment | 30961964 | 16885650 | 16700201
MCR021529 | HPR166 | 2020-08-01 | Subcontract | 367188333 | 200252601 | 187657063
MCR021530 | HPR166 | 2020-08-01 | Overhead | 53724924 | 29299830 | 40802901
MCR021531 | HPR166 | 2020-09-01 | Labor | 73287060 | 33099278 | 38320682
MCR021532 | HPR166 | 2020-09-01 | Material | 173204092 | 78225684 | 71095608
MCR021533 | HPR166 | 2020-09-01 | Equipment | 36028772 | 16271990 | 19304197
MCR021534 | HPR166 | 2020-09-01 | Subcontract | 427277313 | 192975002 | 200610254
MCR021535 | HPR166 | 2020-09-01 | Overhead | 62516804 | 28235013 | 41819904
MCR021536 | HPR166 | 2020-10-01 | Labor | 75873544 | 46881354 | 54671128
MCR021537 | HPR166 | 2020-10-01 | Material | 179316900 | 110797765 | 109276700
MCR021538 | HPR166 | 2020-10-01 | Equipment | 37300318 | 23047420 | 21811582
MCR021539 | HPR166 | 2020-10-01 | Subcontract | 442357004 | 273327095 | 229326432
MCR021540 | HPR166 | 2020-10-01 | Overhead | 64723179 | 39991677 | 40479884
MCR021541 | HPR166 | 2020-11-01 | Labor | 71459712 | 37415083 | 42050084
MCR021542 | HPR166 | 2020-11-01 | Material | 168885402 | 88425508 | 94672837
MCR021543 | HPR166 | 2020-11-01 | Equipment | 35130427 | 18393691 | 18270554
MCR021544 | HPR166 | 2020-11-01 | Subcontract | 416623535 | 218136958 | 253635507
MCR021545 | HPR166 | 2020-11-01 | Overhead | 60958003 | 31916568 | 43007492
MCR021546 | HPR166 | 2020-12-01 | Labor | 60923614 | 100333301 | 122654254
MCR021547 | HPR166 | 2020-12-01 | Material | 143984754 | 237124239 | 241711859
MCR021548 | HPR166 | 2020-12-01 | Equipment | 29950758 | 49325019 | 48201167
MCR021549 | HPR166 | 2020-12-01 | Subcontract | 355196104 | 584961976 | 593313459
MCR021550 | HPR166 | 2020-12-01 | Overhead | 51970288 | 85588333 | 42081118
MCR021551 | HPR166 | 2021-01-01 | Labor | 45402798 | 60433050 | 70008359
MCR021552 | HPR166 | 2021-01-01 | Material | 107303395 | 142825371 | 140216826
MCR021553 | HPR166 | 2021-01-01 | Equipment | 22320544 | 29709591 | 35253892
MCR021554 | HPR166 | 2021-01-01 | Subcontract | 264706832 | 352336023 | 343152852
MCR021555 | HPR166 | 2021-01-01 | Overhead | 38730409 | 51551817 | 39988342
MCR021556 | HPR166 | 2021-02-01 | Labor | 26539369 | 42823232 | 49602648
MCR021557 | HPR166 | 2021-02-01 | Material | 62722223 | 101206941 | 109292271
MCR021558 | HPR166 | 2021-02-01 | Equipment | 13047063 | 21052400 | 18774990
MCR021559 | HPR166 | 2021-02-01 | Subcontract | 154729503 | 249667483 | 305443600
MCR021560 | HPR166 | 2021-02-01 | Overhead | 22639147 | 36529936 | 40414098
MCR021561 | HPR166 | 2021-03-01 | Labor | 7464030 | 61593007 | 71430960
MCR021562 | HPR166 | 2021-03-01 | Material | 17640229 | 145566775 | 147850504
MCR021563 | HPR166 | 2021-03-01 | Equipment | 3669404 | 30279840 | 31919083
MCR021564 | HPR166 | 2021-03-01 | Subcontract | 43516696 | 359098794 | 435261066
MCR021565 | HPR166 | 2021-03-01 | Overhead | 6367117 | 52541308 | 39712404
MCR021566 | HPR166 | 2021-04-01 | Labor | 0 | 21537589 | 21124906
MCR021567 | HPR166 | 2021-04-01 | Material | 0 | 50901190 | 62523410
MCR021568 | HPR166 | 2021-04-01 | Equipment | 0 | 10588129 | 10380708
MCR021569 | HPR166 | 2021-04-01 | Subcontract | 0 | 125568186 | 124537782
MCR021570 | HPR166 | 2021-04-01 | Overhead | 0 | 18372428 | 40664867
MCR021571 | HPR166 | 2021-05-01 | Labor | 0 | 11776388 | 14078028
MCR021572 | HPR166 | 2021-05-01 | Material | 0 | 27831908 | 31668138
MCR021573 | HPR166 | 2021-05-01 | Equipment | 0 | 5789410 | 6629692
MCR021574 | HPR166 | 2021-05-01 | Subcontract | 0 | 68658555 | 132788687
MCR021575 | HPR166 | 2021-05-01 | Overhead | 0 | 10045732 | 40125199
MCR021576 | HPR166 | 2021-06-01 | Labor | 0 | 4574774 | 5983369
MCR021577 | HPR166 | 2021-06-01 | Material | 0 | 10811861 | 10767507
MCR021578 | HPR166 | 2021-06-01 | Equipment | 0 | 2249012 | 2620036
MCR021579 | HPR166 | 2021-06-01 | Subcontract | 0 | 26671788 | 101774754
MCR021580 | HPR166 | 2021-06-01 | Overhead | 0 | 3902465 | 41275675
MCR021581 | HPR167 | 2019-04-01 | Labor | 3476723 | 2416672 | 2369746
MCR021582 | HPR167 | 2019-04-01 | Material | 14035054 | 9755772 | 10047659
MCR021583 | HPR167 | 2019-04-01 | Equipment | 2891324 | 2009761 | 1891843
MCR021584 | HPR167 | 2019-04-01 | Subcontract | 10394429 | 7225172 | 7846846
MCR021585 | HPR167 | 2019-04-01 | Overhead | 2736068 | 1901842 | 11349666
MCR021586 | HPR167 | 2019-05-01 | Labor | 9597551 | 6329164 | 6408591
MCR021587 | HPR167 | 2019-05-01 | Material | 38743995 | 25549967 | 24373215
MCR021588 | HPR167 | 2019-05-01 | Equipment | 7981548 | 5263481 | 4953041
MCR021589 | HPR167 | 2019-05-01 | Subcontract | 28693992 | 18922430 | 19731906
MCR021590 | HPR167 | 2019-05-01 | Overhead | 7552959 | 4980846 | 11280706
MCR021591 | HPR167 | 2019-06-01 | Labor | 14500605 | 12215645 | 11298012
MCR021592 | HPR167 | 2019-06-01 | Material | 58536952 | 49312882 | 49834984
MCR021593 | HPR167 | 2019-06-01 | Equipment | 12059042 | 10158816 | 9522722
MCR021594 | HPR167 | 2019-06-01 | Subcontract | 43352751 | 36521360 | 37597957
MCR021595 | HPR167 | 2019-06-01 | Overhead | 11411503 | 9613314 | 11472539
MCR021596 | HPR167 | 2019-07-01 | Labor | 18229896 | 12259164 | 12104534
MCR021597 | HPR167 | 2019-07-01 | Material | 73591589 | 49488565 | 56477231
MCR021598 | HPR167 | 2019-07-01 | Equipment | 15160408 | 10195008 | 12759409
MCR021599 | HPR167 | 2019-07-01 | Subcontract | 54502289 | 36651472 | 38132193
MCR021600 | HPR167 | 2019-07-01 | Overhead | 14346333 | 9647563 | 10368370
MCR021601 | HPR167 | 2019-08-01 | Labor | 20833000 | 16234701 | 19415194
MCR021602 | HPR167 | 2019-08-01 | Material | 84099963 | 65537262 | 67154595
MCR021603 | HPR167 | 2019-08-01 | Equipment | 17325211 | 13501158 | 12034796
MCR021604 | HPR167 | 2019-08-01 | Subcontract | 62284841 | 48537215 | 51520868
MCR021605 | HPR167 | 2019-08-01 | Overhead | 16394891 | 12776180 | 11981907
MCR021606 | HPR167 | 2019-09-01 | Labor | 22361776 | 25444018 | 26406559
MCR021607 | HPR167 | 2019-09-01 | Material | 90271421 | 102714009 | 95816098
MCR021608 | HPR167 | 2019-09-01 | Equipment | 18596576 | 21159841 | 23378563
MCR021609 | HPR167 | 2019-09-01 | Subcontract | 66855453 | 76070495 | 85159301
MCR021610 | HPR167 | 2019-09-01 | Overhead | 17597988 | 20023612 | 10684580
MCR021611 | HPR167 | 2019-10-01 | Labor | 22873329 | 22294461 | 21669334
MCR021612 | HPR167 | 2019-10-01 | Material | 92336494 | 89999682 | 105485022
MCR021613 | HPR167 | 2019-10-01 | Equipment | 19021997 | 18540596 | 19691286
MCR021614 | HPR167 | 2019-10-01 | Subcontract | 68384856 | 66654202 | 63488053
MCR021615 | HPR167 | 2019-10-01 | Overhead | 18000564 | 17545014 | 10412635
MCR021616 | HPR167 | 2019-11-01 | Labor | 22431347 | 13190408 | 14677140
MCR021617 | HPR167 | 2019-11-01 | Material | 90552271 | 53247870 | 55048206
MCR021618 | HPR167 | 2019-11-01 | Equipment | 18654434 | 10969453 | 10792835
MCR021619 | HPR167 | 2019-11-01 | Subcontract | 67063453 | 39435631 | 43309704
MCR021620 | HPR167 | 2019-11-01 | Overhead | 17652739 | 10380421 | 12061121
MCR021621 | HPR167 | 2019-12-01 | Labor | 21108009 | 16302595 | 16630901
MCR021622 | HPR167 | 2019-12-01 | Material | 85210137 | 65811340 | 56996010
MCR021623 | HPR167 | 2019-12-01 | Equipment | 17553915 | 13557620 | 13098626
MCR021624 | HPR167 | 2019-12-01 | Subcontract | 63107042 | 48740199 | 52946155
MCR021625 | HPR167 | 2019-12-01 | Overhead | 16611315 | 12829611 | 10350149
MCR021626 | HPR167 | 2020-01-01 | Labor | 18986879 | 19029243 | 21661172
MCR021627 | HPR167 | 2020-01-01 | Material | 76647427 | 76818446 | 79602388
MCR021628 | HPR167 | 2020-01-01 | Equipment | 15789933 | 15825165 | 16379259
MCR021629 | HPR167 | 2020-01-01 | Subcontract | 56765457 | 56892115 | 65165860
MCR021630 | HPR167 | 2020-01-01 | Overhead | 14942055 | 14975394 | 10772354
MCR021631 | HPR167 | 2020-02-01 | Labor | 16167551 | 16339300 | 15523135
MCR021632 | HPR167 | 2020-02-01 | Material | 65266187 | 65959514 | 71071512
MCR021633 | HPR167 | 2020-02-01 | Equipment | 13445314 | 13588145 | 12751808
MCR021634 | HPR167 | 2020-02-01 | Subcontract | 48336456 | 48849937 | 41951853
MCR021635 | HPR167 | 2020-02-01 | Overhead | 12723336 | 12858497 | 11035643
MCR021636 | HPR167 | 2020-03-01 | Labor | 12773802 | 14621454 | 12956536
MCR021637 | HPR167 | 2020-03-01 | Material | 51566086 | 59024805 | 60339634
MCR021638 | HPR167 | 2020-03-01 | Equipment | 10622993 | 12159544 | 12657854
MCR021639 | HPR167 | 2020-03-01 | Subcontract | 38190094 | 43714058 | 45936508
MCR021640 | HPR167 | 2020-03-01 | Overhead | 10052565 | 11506608 | 11216899
MCR021641 | HPR167 | 2020-04-01 | Labor | 8969853 | 9473940 | 10299073
MCR021642 | HPR167 | 2020-04-01 | Material | 36210067 | 38244996 | 42079470
MCR021643 | HPR167 | 2020-04-01 | Equipment | 7459540 | 7878750 | 8912854
MCR021644 | HPR167 | 2020-04-01 | Subcontract | 26817352 | 28324430 | 30321329
MCR021645 | HPR167 | 2020-04-01 | Overhead | 7058982 | 7455682 | 11670217
MCR021646 | HPR167 | 2020-05-01 | Labor | 5000547 | 13623419 | 14760819
MCR021647 | HPR167 | 2020-05-01 | Material | 20186521 | 54995873 | 66143896
MCR021648 | HPR167 | 2020-05-01 | Equipment | 4158572 | 11329554 | 11308574
MCR021649 | HPR167 | 2020-05-01 | Subcontract | 14950236 | 40730211 | 37901063
MCR021650 | HPR167 | 2020-05-01 | Overhead | 3935267 | 10721186 | 11876259
MCR021651 | HPR167 | 2020-06-01 | Labor | 1357145 | 6912640 | 5945863
MCR021652 | HPR167 | 2020-06-01 | Material | 5478606 | 27905378 | 25290936
MCR021653 | HPR167 | 2020-06-01 | Equipment | 1128633 | 5748713 | 6449930
MCR021654 | HPR167 | 2020-06-01 | Subcontract | 4057482 | 20666858 | 24030860
MCR021655 | HPR167 | 2020-06-01 | Overhead | 1068028 | 5440022 | 11371251
MCR021656 | HPR167 | 2020-07-01 | Labor | 0 | 7721022 | 7236913
MCR021657 | HPR167 | 2020-07-01 | Material | 0 | 31168707 | 28127612
MCR021658 | HPR167 | 2020-07-01 | Equipment | 0 | 6420983 | 6269485
MCR021659 | HPR167 | 2020-07-01 | Subcontract | 0 | 23083696 | 23883687
MCR021660 | HPR167 | 2020-07-01 | Overhead | 0 | 6076193 | 11397398
MCR021661 | HPR167 | 2020-08-01 | Labor | 0 | 2519598 | 3563344
MCR021662 | HPR167 | 2020-08-01 | Material | 0 | 10171272 | 12207396
MCR021663 | HPR167 | 2020-08-01 | Equipment | 0 | 2095357 | 2103042
MCR021664 | HPR167 | 2020-08-01 | Subcontract | 0 | 7532894 | 7842125
MCR021665 | HPR167 | 2020-08-01 | Overhead | 0 | 1982842 | 13442217
MCR021666 | HPR167 | 2020-09-01 | Labor | 0 | 1740567 | 1579974
MCR021667 | HPR167 | 2020-09-01 | Material | 0 | 7026430 | 6506753
MCR021668 | HPR167 | 2020-09-01 | Equipment | 0 | 1447496 | 1691554
MCR021669 | HPR167 | 2020-09-01 | Subcontract | 0 | 5203809 | 4850579
MCR021670 | HPR167 | 2020-09-01 | Overhead | 0 | 1369769 | 10413489
MCR021671 | HPR168 | 2019-10-01 | Labor | 7772995 | 6748376 | 7697822
MCR021672 | HPR168 | 2019-10-01 | Material | 19387232 | 16831652 | 15147769
MCR021673 | HPR168 | 2019-10-01 | Equipment | 4966348 | 4311695 | 5015212
MCR021674 | HPR168 | 2019-10-01 | Subcontract | 22265870 | 19330834 | 17338219
MCR021675 | HPR168 | 2019-10-01 | Overhead | 5862819 | 5089996 | 27245920
MCR021676 | HPR168 | 2019-11-01 | Labor | 21683391 | 14859569 | 18273936
MCR021677 | HPR168 | 2019-11-01 | Material | 54082235 | 37062410 | 39046677
MCR021678 | HPR168 | 2019-11-01 | Equipment | 13854024 | 9494125 | 8262813
MCR021679 | HPR168 | 2019-11-01 | Subcontract | 62112425 | 42565477 | 41781564
MCR021680 | HPR168 | 2019-11-01 | Overhead | 16354802 | 11207902 | 26109402
MCR021681 | HPR168 | 2019-12-01 | Labor | 33193709 | 21461252 | 18912240
MCR021682 | HPR168 | 2019-12-01 | Material | 82791015 | 53528180 | 59577415
MCR021683 | HPR168 | 2019-12-01 | Equipment | 21208234 | 13712094 | 13957989
MCR021684 | HPR168 | 2019-12-01 | Subcontract | 95083916 | 61476103 | 66079686
MCR021685 | HPR168 | 2019-12-01 | Overhead | 25036515 | 16187253 | 25030857
MCR021686 | HPR168 | 2020-01-01 | Labor | 42378678 | 28966385 | 32702635
MCR021687 | HPR168 | 2020-01-01 | Material | 105699964 | 72247319 | 70558736
MCR021688 | HPR168 | 2020-01-01 | Equipment | 27076725 | 18507299 | 20189750
MCR021689 | HPR168 | 2020-01-01 | Subcontract | 121394410 | 82974680 | 86545038
MCR021690 | HPR168 | 2020-01-01 | Overhead | 31964322 | 21848036 | 26339310
MCR021691 | HPR168 | 2020-02-01 | Labor | 49318185 | 49342730 | 58613108
MCR021692 | HPR168 | 2020-02-01 | Material | 123008330 | 123069549 | 128850699
MCR021693 | HPR168 | 2020-02-01 | Equipment | 31510539 | 31526221 | 29260040
MCR021694 | HPR168 | 2020-02-01 | Subcontract | 141272741 | 141343051 | 135311467
MCR021695 | HPR168 | 2020-02-01 | Overhead | 37198479 | 37216993 | 25585098
MCR021696 | HPR168 | 2020-03-01 | Labor | 54098146 | 18696129 | 17674295
MCR021697 | HPR168 | 2020-03-01 | Material | 134930401 | 46631474 | 45703639
MCR021698 | HPR168 | 2020-03-01 | Equipment | 34564567 | 11945393 | 14381988
MCR021699 | HPR168 | 2020-03-01 | Subcontract | 154965015 | 53555366 | 55377429
MCR021700 | HPR168 | 2020-03-01 | Overhead | 40803788 | 14101646 | 27172324
MCR021701 | HPR168 | 2020-04-01 | Labor | 56811622 | 38576539 | 48445012
MCR021702 | HPR168 | 2020-04-01 | Material | 141698295 | 96216751 | 92559250
MCR021703 | HPR168 | 2020-04-01 | Equipment | 36298270 | 24647450 | 24561718
MCR021704 | HPR168 | 2020-04-01 | Subcontract | 162737813 | 110503120 | 99164650
MCR021705 | HPR168 | 2020-04-01 | Overhead | 42850440 | 29096540 | 27398568
MCR021706 | HPR168 | 2020-05-01 | Labor | 57560290 | 61773348 | 63710983
MCR021707 | HPR168 | 2020-05-01 | Material | 143565606 | 154073721 | 171775826
MCR021708 | HPR168 | 2020-05-01 | Equipment | 36776612 | 39468432 | 41864870
MCR021709 | HPR168 | 2020-05-01 | Subcontract | 164882385 | 176950756 | 174592685
MCR021710 | HPR168 | 2020-05-01 | Overhead | 43415127 | 46592846 | 26545776
MCR021711 | HPR168 | 2020-06-01 | Labor | 56456406 | 77552061 | 85570810
MCR021712 | HPR168 | 2020-06-01 | Material | 140812323 | 193428639 | 181554923
MCR021713 | HPR168 | 2020-06-01 | Equipment | 36071314 | 49549820 | 43589162
MCR021714 | HPR168 | 2020-06-01 | Subcontract | 161720291 | 222149135 | 211931188
MCR021715 | HPR168 | 2020-06-01 | Overhead | 42582517 | 58494016 | 27014867
MCR021716 | HPR168 | 2020-07-01 | Labor | 53625536 | 33625287 | 39038163
MCR021717 | HPR168 | 2020-07-01 | Material | 133751628 | 83867448 | 94101476
MCR021718 | HPR168 | 2020-07-01 | Equipment | 34262605 | 21483980 | 26785513
MCR021719 | HPR168 | 2020-07-01 | Subcontract | 153611216 | 96320179 | 94699124
MCR021720 | HPR168 | 2020-07-01 | Overhead | 40447319 | 25362035 | 29218029
MCR021721 | HPR168 | 2020-08-01 | Labor | 49210488 | 27369374 | 34383875
MCR021722 | HPR168 | 2020-08-01 | Material | 122739714 | 68264089 | 66164691
MCR021723 | HPR168 | 2020-08-01 | Equipment | 31441728 | 17486931 | 17662360
MCR021724 | HPR168 | 2020-08-01 | Subcontract | 140964240 | 78400016 | 83041531
MCR021725 | HPR168 | 2020-08-01 | Overhead | 37117248 | 20643483 | 28069429
MCR021726 | HPR168 | 2020-09-01 | Labor | 43377271 | 56211481 | 63388200
MCR021727 | HPR168 | 2020-09-01 | Material | 108190633 | 140201435 | 132962617
MCR021728 | HPR168 | 2020-09-01 | Equipment | 27714750 | 35914826 | 30901109
MCR021729 | HPR168 | 2020-09-01 | Subcontract | 124254896 | 161018698 | 159294220
MCR021730 | HPR168 | 2020-09-01 | Overhead | 32717516 | 42397781 | 27963985
MCR021731 | HPR168 | 2020-10-01 | Labor | 36324703 | 44633072 | 47547740
MCR021732 | HPR168 | 2020-10-01 | Material | 90600272 | 111322823 | 124224090
MCR021733 | HPR168 | 2020-10-01 | Equipment | 23208700 | 28517110 | 35328767
MCR021734 | HPR168 | 2020-10-01 | Subcontract | 104052700 | 127852158 | 115551129
MCR021735 | HPR168 | 2020-10-01 | Overhead | 27398082 | 33664710 | 26007340
MCR021736 | HPR168 | 2020-11-01 | Labor | 28301342 | 40285514 | 51748294
MCR021737 | HPR168 | 2020-11-01 | Material | 70588582 | 100479241 | 95055581
MCR021738 | HPR168 | 2020-11-01 | Equipment | 18082387 | 25739354 | 26377871
MCR021739 | HPR168 | 2020-11-01 | Subcontract | 81069651 | 115398509 | 113381729
MCR021740 | HPR168 | 2020-11-01 | Overhead | 21346423 | 30385544 | 27307441
MCR021741 | HPR168 | 2020-12-01 | Labor | 19639416 | 39581377 | 42573010
MCR021742 | HPR168 | 2020-12-01 | Material | 48984198 | 98722997 | 112923883
MCR021743 | HPR168 | 2020-12-01 | Equipment | 12548081 | 25289465 | 31478472
MCR021744 | HPR168 | 2020-12-01 | Subcontract | 56257425 | 113381496 | 156962839
MCR021745 | HPR168 | 2020-12-01 | Overhead | 14813124 | 29854445 | 29402739
MCR021746 | HPR168 | 2021-01-01 | Labor | 10839055 | 21391606 | 27012968
MCR021747 | HPR168 | 2021-01-01 | Material | 27034533 | 53354471 | 49714719
MCR021748 | HPR168 | 2021-01-01 | Equipment | 6925325 | 13667596 | 10053941
MCR021749 | HPR168 | 2021-01-01 | Subcontract | 31048650 | 61276602 | 67453326
MCR021750 | HPR168 | 2021-01-01 | Overhead | 8175410 | 16134722 | 26524524
MCR021751 | HPR168 | 2021-02-01 | Labor | 2918395 | 21086760 | 20888446
MCR021752 | HPR168 | 2021-02-01 | Material | 7278995 | 52594133 | 54427970
MCR021753 | HPR168 | 2021-02-01 | Equipment | 1864630 | 13472823 | 14343408
MCR021754 | HPR168 | 2021-02-01 | Subcontract | 8359788 | 60403367 | 98476467
MCR021755 | HPR168 | 2021-02-01 | Overhead | 2201213 | 15904791 | 28707073
MCR021756 | HPR168 | 2021-03-01 | Labor | 0 | 11679761 | 14256936
MCR021757 | HPR168 | 2021-03-01 | Material | 0 | 29131403 | 35774793
MCR021758 | HPR168 | 2021-03-01 | Equipment | 0 | 7462472 | 8706894
MCR021759 | HPR168 | 2021-03-01 | Subcontract | 0 | 33456866 | 54951198
MCR021760 | HPR168 | 2021-03-01 | Overhead | 0 | 8809516 | 26477088
MCR021761 | HPR168 | 2021-04-01 | Labor | 0 | 7064329 | 8666238
MCR021762 | HPR168 | 2021-04-01 | Material | 0 | 17619694 | 15935429
MCR021763 | HPR168 | 2021-04-01 | Equipment | 0 | 4513565 | 4215236
MCR021764 | HPR168 | 2021-04-01 | Subcontract | 0 | 20235885 | 64352861
MCR021765 | HPR168 | 2021-04-01 | Overhead | 0 | 5328304 | 25478062
MCR021766 | HPR168 | 2021-05-01 | Labor | 0 | 2604676 | 2694384
MCR021767 | HPR168 | 2021-05-01 | Material | 0 | 6496526 | 7863563
MCR021768 | HPR168 | 2021-05-01 | Equipment | 0 | 1664188 | 1946072
MCR021769 | HPR168 | 2021-05-01 | Subcontract | 0 | 7461137 | 41469769
MCR021770 | HPR168 | 2021-05-01 | Overhead | 0 | 1964590 | 32256620
MCR021771 | HPR169 | 2018-08-01 | Labor | 7553222 | 2858348 | 3252572
MCR021772 | HPR169 | 2018-08-01 | Material | 13232474 | 5007535 | 5159449
MCR021773 | HPR169 | 2018-08-01 | Equipment | 3126675 | 1183220 | 1143994
MCR021774 | HPR169 | 2018-08-01 | Subcontract | 17046427 | 6450841 | 5778363
MCR021775 | HPR169 | 2018-08-01 | Overhead | 3678539 | 1392061 | 20297759
MCR021776 | HPR169 | 2018-09-01 | Labor | 21315099 | 21291475 | 24479985
MCR021777 | HPR169 | 2018-09-01 | Material | 37341881 | 37300494 | 41703962
MCR021778 | HPR169 | 2018-09-01 | Equipment | 8823438 | 8813659 | 7349007
MCR021779 | HPR169 | 2018-09-01 | Subcontract | 48104811 | 48051496 | 47199633
MCR021780 | HPR169 | 2018-09-01 | Overhead | 10380793 | 10369287 | 21002271
MCR021781 | HPR169 | 2018-10-01 | Labor | 33096857 | 16934782 | 17395135
MCR021782 | HPR169 | 2018-10-01 | Material | 57982319 | 29668012 | 29424818
MCR021783 | HPR169 | 2018-10-01 | Equipment | 13700525 | 7010195 | 8162679
MCR021784 | HPR169 | 2018-10-01 | Subcontract | 74694376 | 38219128 | 42953714
MCR021785 | HPR169 | 2018-10-01 | Overhead | 16118696 | 8247508 | 20799179
MCR021786 | HPR169 | 2018-11-01 | Labor | 42949547 | 47705368 | 48072722
MCR021787 | HPR169 | 2018-11-01 | Material | 75243227 | 83574941 | 88785355
MCR021788 | HPR169 | 2018-11-01 | Equipment | 17779071 | 19747755 | 21093579
MCR021789 | HPR169 | 2018-11-01 | Subcontract | 96930342 | 107663479 | 102686223
MCR021790 | HPR169 | 2018-11-01 | Overhead | 20917113 | 23233273 | 20527868
MCR021791 | HPR169 | 2018-12-01 | Labor | 50927105 | 48303276 | 56059737
MCR021792 | HPR169 | 2018-12-01 | Material | 89219096 | 84622414 | 83835028
MCR021793 | HPR169 | 2018-12-01 | Equipment | 21081401 | 19995260 | 20046513
MCR021794 | HPR169 | 2018-12-01 | Subcontract | 114934430 | 109012862 | 96641326
MCR021795 | HPR169 | 2018-12-01 | Overhead | 24802311 | 23524464 | 19888881
MCR021796 | HPR169 | 2019-01-01 | Labor | 57086742 | 54976201 | 55329064
MCR021797 | HPR169 | 2019-01-01 | Material | 100010151 | 96312699 | 97003659
MCR021798 | HPR169 | 2019-01-01 | Equipment | 23631197 | 22757534 | 24844106
MCR021799 | HPR169 | 2019-01-01 | Subcontract | 128835756 | 124072599 | 125129969
MCR021800 | HPR169 | 2019-01-01 | Overhead | 27802152 | 26774285 | 19960974
MCR021801 | HPR169 | 2019-02-01 | Labor | 61489425 | 34934258 | 37410920
MCR021802 | HPR169 | 2019-02-01 | Material | 107723204 | 61201257 | 66629582
MCR021803 | HPR169 | 2019-02-01 | Equipment | 25453699 | 14461122 | 14007860
MCR021804 | HPR169 | 2019-02-01 | Subcontract | 138771918 | 78841100 | 85675004
MCR021805 | HPR169 | 2019-02-01 | Overhead | 29946329 | 17013539 | 21314991
MCR021806 | HPR169 | 2019-03-01 | Labor | 64200479 | 73349102 | 71773947
MCR021807 | HPR169 | 2019-03-01 | Material | 112472692 | 128500148 | 134940610
MCR021808 | HPR169 | 2019-03-01 | Equipment | 26575946 | 30363041 | 29349338
MCR021809 | HPR169 | 2019-03-01 | Subcontract | 144890336 | 165537334 | 135842283
MCR021810 | HPR169 | 2019-03-01 | Overhead | 31266655 | 35722180 | 21522713
MCR021811 | HPR169 | 2019-04-01 | Labor | 65290331 | 63173177 | 71564861
MCR021812 | HPR169 | 2019-04-01 | Material | 114382003 | 110672965 | 110014589
MCR021813 | HPR169 | 2019-04-01 | Equipment | 27027093 | 26150692 | 27940076
MCR021814 | HPR169 | 2019-04-01 | Subcontract | 147349960 | 142571878 | 150520038
MCR021815 | HPR169 | 2019-04-01 | Overhead | 31797430 | 30766342 | 20047600
MCR021816 | HPR169 | 2019-05-01 | Labor | 64835486 | 54454026 | 56604394
MCR021817 | HPR169 | 2019-05-01 | Material | 113585160 | 95397902 | 102338775
MCR021818 | HPR169 | 2019-05-01 | Equipment | 26838809 | 22541378 | 24070146
MCR021819 | HPR169 | 2019-05-01 | Subcontract | 146323447 | 122894133 | 111646333
MCR021820 | HPR169 | 2019-05-01 | Overhead | 31575913 | 26519977 | 21055235
MCR021821 | HPR169 | 2019-06-01 | Labor | 62919791 | 61038353 | 69534553
MCR021822 | HPR169 | 2019-06-01 | Material | 110229058 | 106932971 | 107585631
MCR021823 | HPR169 | 2019-06-01 | Equipment | 26045802 | 25266976 | 24429595
MCR021824 | HPR169 | 2019-06-01 | Subcontract | 142000026 | 137753918 | 141022713
MCR021825 | HPR169 | 2019-06-01 | Overhead | 30642939 | 29726649 | 20864828
MCR021826 | HPR169 | 2019-07-01 | Labor | 59636148 | 31500220 | 32465906
MCR021827 | HPR169 | 2019-07-01 | Material | 104476450 | 55185174 | 53827275
MCR021828 | HPR169 | 2019-07-01 | Equipment | 24686530 | 13039594 | 13522836
MCR021829 | HPR169 | 2019-07-01 | Subcontract | 134589363 | 71091019 | 77375107
MCR021830 | HPR169 | 2019-07-01 | Overhead | 29043753 | 15341108 | 21271686
MCR021831 | HPR169 | 2019-08-01 | Labor | 55088896 | 49164275 | 56316704
MCR021832 | HPR169 | 2019-08-01 | Material | 96510130 | 86130798 | 91859527
MCR021833 | HPR169 | 2019-08-01 | Equipment | 22804184 | 20351673 | 20434253
MCR021834 | HPR169 | 2019-08-01 | Subcontract | 124326935 | 110956001 | 114206843
MCR021835 | HPR169 | 2019-08-01 | Overhead | 26829169 | 23943784 | 21558250
MCR021836 | HPR169 | 2019-09-01 | Labor | 49397260 | 31502979 | 65570465
MCR021837 | HPR169 | 2019-09-01 | Material | 86538963 | 55190006 | 81594920
MCR021838 | HPR169 | 2019-09-01 | Equipment | 20448117 | 13040736 | 10441782
MCR021839 | HPR169 | 2019-09-01 | Subcontract | 111481811 | 71097245 | 60002199
MCR021840 | HPR169 | 2019-09-01 | Overhead | 24057252 | 15342452 | 20100535
MCR021841 | HPR169 | 2019-10-01 | Labor | 42700583 | 72134520 | 114512853
MCR021842 | HPR169 | 2019-10-01 | Material | 74807068 | 126372324 | 166999028
MCR021843 | HPR169 | 2019-10-01 | Equipment | 17676012 | 29860262 | 27534404
MCR021844 | HPR169 | 2019-10-01 | Subcontract | 96368469 | 162796214 | 172328695
MCR021845 | HPR169 | 2019-10-01 | Overhead | 20795863 | 35130659 | 19391536
MCR021846 | HPR169 | 2019-11-01 | Labor | 35166823 | 29942599 | 37085491
MCR021847 | HPR169 | 2019-11-01 | Material | 61608689 | 52456381 | 58559570
MCR021848 | HPR169 | 2019-11-01 | Equipment | 14557393 | 12394813 | 14560055
MCR021849 | HPR169 | 2019-11-01 | Subcontract | 79365964 | 67575716 | 58131792
MCR021850 | HPR169 | 2019-11-01 | Overhead | 17126803 | 14582522 | 19020775
MCR021851 | HPR169 | 2019-12-01 | Labor | 27007581 | 48476192 | 49914073
MCR021852 | HPR169 | 2019-12-01 | Material | 47314529 | 84925346 | 99955816
MCR021853 | HPR169 | 2019-12-01 | Equipment | 11179855 | 20066839 | 19380301
MCR021854 | HPR169 | 2019-12-01 | Subcontract | 60951843 | 109403107 | 116817857
MCR021855 | HPR169 | 2019-12-01 | Overhead | 13153122 | 23608677 | 21406946
MCR021856 | HPR169 | 2020-01-01 | Labor | 18508377 | 25556136 | 25910549
MCR021857 | HPR169 | 2020-01-01 | Material | 32424789 | 44771745 | 40499469
MCR021858 | HPR169 | 2020-01-01 | Equipment | 7661588 | 10579026 | 12484425
MCR021859 | HPR169 | 2020-01-01 | Subcontract | 41770483 | 57676162 | 53196506
MCR021860 | HPR169 | 2020-01-01 | Overhead | 9013874 | 12446245 | 19274305
MCR021861 | HPR169 | 2020-02-01 | Labor | 10104277 | 15262842 | 18403701
MCR021862 | HPR169 | 2020-02-01 | Material | 17701663 | 26738942 | 27788993
MCR021863 | HPR169 | 2020-02-01 | Equipment | 4182690 | 6318091 | 5999682
MCR021864 | HPR169 | 2020-02-01 | Subcontract | 22803757 | 34445822 | 36676200
MCR021865 | HPR169 | 2020-02-01 | Overhead | 4920944 | 7433247 | 19989551
MCR021866 | HPR169 | 2020-03-01 | Labor | 2696799 | 27041263 | 26404796
MCR021867 | HPR169 | 2020-03-01 | Material | 4724517 | 47373535 | 55590655
MCR021868 | HPR169 | 2020-03-01 | Equipment | 1116347 | 11193797 | 13416909
MCR021869 | HPR169 | 2020-03-01 | Subcontract | 6086249 | 61027857 | 53944964
MCR021870 | HPR169 | 2020-03-01 | Overhead | 1313384 | 13169525 | 21239258
MCR021871 | HPR169 | 2020-04-01 | Labor | 0 | 15347831 | 17342398
MCR021872 | HPR169 | 2020-04-01 | Material | 0 | 26887835 | 26742771
MCR021873 | HPR169 | 2020-04-01 | Equipment | 0 | 6353272 | 4701069
MCR021874 | HPR169 | 2020-04-01 | Subcontract | 0 | 34637629 | 38397605
MCR021875 | HPR169 | 2020-04-01 | Overhead | 0 | 7474638 | 20411373
MCR021876 | HPR169 | 2020-05-01 | Labor | 0 | 4782456 | 5006549
MCR021877 | HPR169 | 2020-05-01 | Material | 0 | 8378375 | 8968144
MCR021878 | HPR169 | 2020-05-01 | Equipment | 0 | 1979709 | 2705532
MCR021879 | HPR169 | 2020-05-01 | Subcontract | 0 | 10793247 | 7787874
MCR021880 | HPR169 | 2020-05-01 | Overhead | 0 | 2329132 | 20360524
MCR021881 | HPR169 | 2020-06-01 | Labor | 0 | 2241149 | 2042133
MCR021882 | HPR169 | 2020-06-01 | Material | 0 | 3926264 | 5017856
MCR021883 | HPR169 | 2020-06-01 | Equipment | 0 | 927729 | 1106792
MCR021884 | HPR169 | 2020-06-01 | Subcontract | 0 | 5057918 | 5669491
MCR021885 | HPR169 | 2020-06-01 | Overhead | 0 | 1091475 | 21297354
MCR021886 | HPR170 | 2017-10-01 | Labor | 3593400 | 1931366 | 2053628
MCR021887 | HPR170 | 2017-10-01 | Material | 8702811 | 4677552 | 4818835
MCR021888 | HPR170 | 2017-10-01 | Equipment | 2772393 | 1490095 | 1841106
MCR021889 | HPR170 | 2017-10-01 | Subcontract | 10097938 | 5427399 | 5607079
MCR021890 | HPR170 | 2017-10-01 | Overhead | 2790881 | 1500032 | 19693974
MCR021891 | HPR170 | 2017-11-01 | Labor | 10309648 | 6415903 | 6488184
MCR021892 | HPR170 | 2017-11-01 | Material | 24968806 | 15538594 | 14465432
MCR021893 | HPR170 | 2017-11-01 | Equipment | 7954138 | 4950021 | 4316623
MCR021894 | HPR170 | 2017-11-01 | Subcontract | 28971497 | 18029549 | 16374449
MCR021895 | HPR170 | 2017-11-01 | Overhead | 8007181 | 4983031 | 21910191
MCR021896 | HPR170 | 2017-12-01 | Labor | 16329395 | 6712520 | 7128141
MCR021897 | HPR170 | 2017-12-01 | Material | 39547957 | 16256967 | 16677848
MCR021898 | HPR170 | 2017-12-01 | Equipment | 12598516 | 5178868 | 5592552
MCR021899 | HPR170 | 2017-12-01 | Subcontract | 45887796 | 18863083 | 19219372
MCR021900 | HPR170 | 2017-12-01 | Overhead | 12682530 | 5213404 | 19759577
MCR021901 | HPR170 | 2018-01-01 | Labor | 21665459 | 13445052 | 13918781
MCR021902 | HPR170 | 2018-01-01 | Material | 52471302 | 32562402 | 31347678
MCR021903 | HPR170 | 2018-01-01 | Equipment | 16715415 | 10373177 | 11754569
MCR021904 | HPR170 | 2018-01-01 | Subcontract | 60882852 | 37782404 | 40772185
MCR021905 | HPR170 | 2018-01-01 | Overhead | 16826883 | 10442351 | 21187492
MCR021906 | HPR170 | 2018-02-01 | Labor | 26331163 | 11138190 | 13099467
MCR021907 | HPR170 | 2018-02-01 | Material | 63771112 | 26975443 | 33863452
MCR021908 | HPR170 | 2018-02-01 | Equipment | 20315117 | 8593378 | 8488236
MCR021909 | HPR170 | 2018-02-01 | Subcontract | 73994108 | 31299812 | 25500347
MCR021910 | HPR170 | 2018-02-01 | Overhead | 20450589 | 8650683 | 21662261
MCR021911 | HPR170 | 2018-03-01 | Labor | 30340389 | 12434198 | 12149672
MCR021912 | HPR170 | 2018-03-01 | Material | 73481005 | 30114228 | 31574532
MCR021913 | HPR170 | 2018-03-01 | Equipment | 23408329 | 9593279 | 10733022
MCR021914 | HPR170 | 2018-03-01 | Subcontract | 85260571 | 34941769 | 37247816
MCR021915 | HPR170 | 2018-03-01 | Overhead | 23564429 | 9657252 | 19121130
MCR021916 | HPR170 | 2018-04-01 | Labor | 33707627 | 12349745 | 12635097
MCR021917 | HPR170 | 2018-04-01 | Material | 81636077 | 29909692 | 31824048
MCR021918 | HPR170 | 2018-04-01 | Equipment | 26006234 | 9528121 | 9692064
MCR021919 | HPR170 | 2018-04-01 | Subcontract | 94722964 | 34704444 | 32651345
MCR021920 | HPR170 | 2018-04-01 | Overhead | 26179658 | 9591660 | 19911853
MCR021921 | HPR170 | 2018-05-01 | Labor | 36448045 | 25652473 | 28816655
MCR021922 | HPR170 | 2018-05-01 | Material | 88273061 | 62127401 | 62582226
MCR021923 | HPR170 | 2018-05-01 | Equipment | 28120531 | 19791491 | 22959532
MCR021924 | HPR170 | 2018-05-01 | Subcontract | 102423907 | 72086898 | 74529753
MCR021925 | HPR170 | 2018-05-01 | Overhead | 28308055 | 19923472 | 20761550
MCR021926 | HPR170 | 2018-06-01 | Labor | 38577558 | 21522197 | 22413307
MCR021927 | HPR170 | 2018-06-01 | Material | 93430502 | 52124337 | 54977835
MCR021928 | HPR170 | 2018-06-01 | Equipment | 29763501 | 16604885 | 13761162
MCR021929 | HPR170 | 2018-06-01 | Subcontract | 108408125 | 60480266 | 55993640
MCR021930 | HPR170 | 2018-06-01 | Overhead | 29961981 | 16715616 | 20867460
MCR021931 | HPR170 | 2018-07-01 | Labor | 40112919 | 19648897 | 24951950
MCR021932 | HPR170 | 2018-07-01 | Material | 97148972 | 47587417 | 48169080
MCR021933 | HPR170 | 2018-07-01 | Equipment | 30948068 | 15159590 | 17167293
MCR021934 | HPR170 | 2018-07-01 | Subcontract | 112722695 | 55216043 | 49851471
MCR021935 | HPR170 | 2018-07-01 | Overhead | 31154447 | 15260683 | 18594734
MCR021936 | HPR170 | 2018-08-01 | Labor | 41071820 | 25595744 | 25516066
MCR021937 | HPR170 | 2018-08-01 | Material | 99471322 | 61990010 | 62516899
MCR021938 | HPR170 | 2018-08-01 | Equipment | 31687883 | 19747724 | 18333683
MCR021939 | HPR170 | 2018-08-01 | Subcontract | 115417335 | 71927483 | 78792491
MCR021940 | HPR170 | 2018-08-01 | Overhead | 31899195 | 19879413 | 20604674
MCR021941 | HPR170 | 2018-09-01 | Labor | 41473018 | 47935635 | 44448153
MCR021942 | HPR170 | 2018-09-01 | Material | 100442980 | 116094709 | 117523331
MCR021943 | HPR170 | 2018-09-01 | Equipment | 31997417 | 36983479 | 38526994
MCR021944 | HPR170 | 2018-09-01 | Subcontract | 116544757 | 134705578 | 121676988
MCR021945 | HPR170 | 2018-09-01 | Overhead | 32210794 | 37230105 | 20702131
MCR021946 | HPR170 | 2018-10-01 | Labor | 41336488 | 32398800 | 38964302
MCR021947 | HPR170 | 2018-10-01 | Material | 100112319 | 78466246 | 99038339
MCR021948 | HPR170 | 2018-10-01 | Equipment | 31892081 | 24996443 | 25097367
MCR021949 | HPR170 | 2018-10-01 | Subcontract | 116161089 | 91044985 | 87025686
MCR021950 | HPR170 | 2018-10-01 | Overhead | 32104755 | 25163133 | 22958396
MCR021951 | HPR170 | 2018-11-01 | Labor | 40683604 | 28273217 | 31738965
MCR021952 | HPR170 | 2018-11-01 | Material | 98531107 | 68474547 | 54900488
MCR021953 | HPR170 | 2018-11-01 | Equipment | 31388365 | 21813457 | 20112276
MCR021954 | HPR170 | 2018-11-01 | Subcontract | 114326396 | 79451541 | 90169778
MCR021955 | HPR170 | 2018-11-01 | Overhead | 31597680 | 21958922 | 20123109
MCR021956 | HPR170 | 2018-12-01 | Labor | 39537371 | 37393760 | 37652625
MCR021957 | HPR170 | 2018-12-01 | Material | 95755061 | 90563476 | 101966806
MCR021958 | HPR170 | 2018-12-01 | Equipment | 30504019 | 28850172 | 31995724
MCR021959 | HPR170 | 2018-12-01 | Subcontract | 111105329 | 105081493 | 108161237
MCR021960 | HPR170 | 2018-12-01 | Overhead | 30707437 | 29042562 | 21524566
MCR021961 | HPR170 | 2019-01-01 | Labor | 37922721 | 20230302 | 20654896
MCR021962 | HPR170 | 2019-01-01 | Material | 91844561 | 48995513 | 50831740
MCR021963 | HPR170 | 2019-01-01 | Equipment | 29258279 | 15608158 | 16704849
MCR021964 | HPR170 | 2019-01-01 | Subcontract | 106567945 | 56849868 | 49991439
MCR021965 | HPR170 | 2019-01-01 | Overhead | 29453389 | 15712242 | 22082363
MCR021966 | HPR170 | 2019-02-01 | Labor | 35866886 | 45515108 | 51631534
MCR021967 | HPR170 | 2019-02-01 | Material | 86865559 | 110232465 | 124290968
MCR021968 | HPR170 | 2019-02-01 | Equipment | 27672153 | 35115985 | 34010334
MCR021969 | HPR170 | 2019-02-01 | Subcontract | 100790772 | 127903572 | 139430885
MCR021970 | HPR170 | 2019-02-01 | Overhead | 27856687 | 35350158 | 19081541
MCR021971 | HPR170 | 2019-03-01 | Labor | 33399898 | 35589904 | 37840719
MCR021972 | HPR170 | 2019-03-01 | Material | 80890791 | 86194741 | 97337675
MCR021973 | HPR170 | 2019-03-01 | Equipment | 25768813 | 27458455 | 29189953
MCR021974 | HPR170 | 2019-03-01 | Subcontract | 93858203 | 100012416 | 95130478
MCR021975 | HPR170 | 2019-03-01 | Overhead | 25940654 | 27641563 | 21715725
MCR021976 | HPR170 | 2019-04-01 | Labor | 30555263 | 41880709 | 43465699
MCR021977 | HPR170 | 2019-04-01 | Material | 74001407 | 101430361 | 95273202
MCR021978 | HPR170 | 2019-04-01 | Equipment | 23574110 | 32311960 | 32253510
MCR021979 | HPR170 | 2019-04-01 | Subcontract | 85864398 | 117690423 | 123690140
MCR021980 | HPR170 | 2019-04-01 | Overhead | 23731316 | 32527434 | 20772284
MCR021981 | HPR170 | 2019-05-01 | Labor | 27370911 | 49463738 | 55439552
MCR021982 | HPR170 | 2019-05-01 | Material | 66289265 | 119795603 | 122986065
MCR021983 | HPR170 | 2019-05-01 | Equipment | 21117307 | 38162447 | 42253128
MCR021984 | HPR170 | 2019-05-01 | Subcontract | 76915941 | 138999753 | 125558283
MCR021985 | HPR170 | 2019-05-01 | Overhead | 21258129 | 38416935 | 22130735
MCR021986 | HPR170 | 2019-06-01 | Labor | 23890567 | 34503146 | 37439199
MCR021987 | HPR170 | 2019-06-01 | Material | 57860264 | 83562734 | 90140624
MCR021988 | HPR170 | 2019-06-01 | Equipment | 18432139 | 26619995 | 28074593
MCR021989 | HPR170 | 2019-06-01 | Subcontract | 67135706 | 96958479 | 98030141
MCR021990 | HPR170 | 2019-06-01 | Overhead | 18555055 | 26797512 | 19726284
MCR021991 | HPR170 | 2019-07-01 | Labor | 20165860 | 16481389 | 18109616
MCR021992 | HPR170 | 2019-07-01 | Material | 48839443 | 39916068 | 40674338
MCR021993 | HPR170 | 2019-07-01 | Equipment | 15558439 | 12715782 | 12035926
MCR021994 | HPR170 | 2019-07-01 | Subcontract | 56668779 | 46314918 | 44366143
MCR021995 | HPR170 | 2019-07-01 | Overhead | 15662192 | 12800578 | 18297858
MCR021996 | HPR170 | 2019-08-01 | Labor | 16259763 | 24687389 | 24453430
MCR021997 | HPR170 | 2019-08-01 | Material | 39379314 | 59790075 | 58682683
MCR021998 | HPR170 | 2019-08-01 | Equipment | 12544792 | 19046906 | 15305739
MCR021999 | HPR170 | 2019-08-01 | Subcontract | 45692119 | 69374881 | 77555179
MCR022000 | HPR170 | 2019-08-01 | Overhead | 12628448 | 19173921 | 22223028
MCR022001 | HPR170 | 2019-09-01 | Labor | 12252722 | 22626161 | 28234850
MCR022002 | HPR170 | 2019-09-01 | Material | 29674713 | 54798015 | 66655137
MCR022003 | HPR170 | 2019-09-01 | Equipment | 9453265 | 17456620 | 20862590
MCR022004 | HPR170 | 2019-09-01 | Subcontract | 34431796 | 63582555 | 51816857
MCR022005 | HPR170 | 2019-09-01 | Overhead | 9516305 | 17573030 | 19765526
MCR022006 | HPR170 | 2019-10-01 | Labor | 8255123 | 14878601 | 13990971
MCR022007 | HPR170 | 2019-10-01 | Material | 19992979 | 36034296 | 40100467
MCR022008 | HPR170 | 2019-10-01 | Equipment | 6369023 | 11479193 | 12794943
MCR022009 | HPR170 | 2019-10-01 | Subcontract | 23198006 | 41810869 | 45725947
MCR022010 | HPR170 | 2019-10-01 | Overhead | 6411495 | 11555743 | 19340871
MCR022011 | HPR170 | 2019-11-01 | Labor | 4438708 | 19409950 | 23272759
MCR022012 | HPR170 | 2019-11-01 | Material | 10750050 | 47008714 | 51377440
MCR022013 | HPR170 | 2019-11-01 | Equipment | 3424568 | 14975237 | 14716565
MCR022014 | HPR170 | 2019-11-01 | Subcontract | 12473365 | 54544570 | 57827495
MCR022015 | HPR170 | 2019-11-01 | Overhead | 3447405 | 15075100 | 21573363
MCR022016 | HPR170 | 2019-12-01 | Labor | 1169901 | 12322446 | 13561009
MCR022017 | HPR170 | 2019-12-01 | Material | 2833369 | 29843577 | 25433596
MCR022018 | HPR170 | 2019-12-01 | Equipment | 902606 | 9507059 | 10392460
MCR022019 | HPR170 | 2019-12-01 | Subcontract | 3287580 | 34627730 | 28617799
MCR022020 | HPR170 | 2019-12-01 | Overhead | 908626 | 9570458 | 18591174
MCR022021 | HPR170 | 2020-01-01 | Labor | 0 | 18007740 | 21337749
MCR022022 | HPR170 | 2020-01-01 | Material | 0 | 43612719 | 41487079
MCR022023 | HPR170 | 2020-01-01 | Equipment | 0 | 13893399 | 15621721
MCR022024 | HPR170 | 2020-01-01 | Subcontract | 0 | 50604172 | 50012260
MCR022025 | HPR170 | 2020-01-01 | Overhead | 0 | 13986048 | 20971806
MCR022026 | HPR170 | 2020-02-01 | Labor | 0 | 14870180 | 16283484
MCR022027 | HPR170 | 2020-02-01 | Material | 0 | 36013902 | 43458504
MCR022028 | HPR170 | 2020-02-01 | Equipment | 0 | 11472697 | 11850096
MCR022029 | HPR170 | 2020-02-01 | Subcontract | 0 | 41787206 | 42919266
MCR022030 | HPR170 | 2020-02-01 | Overhead | 0 | 11549203 | 21800142
MCR022031 | HPR170 | 2020-03-01 | Labor | 0 | 13960500 | 12934026
MCR022032 | HPR170 | 2020-03-01 | Material | 0 | 33810760 | 34763268
MCR022033 | HPR170 | 2020-03-01 | Equipment | 0 | 10770857 | 10601012
MCR022034 | HPR170 | 2020-03-01 | Subcontract | 0 | 39230883 | 35183885
MCR022035 | HPR170 | 2020-03-01 | Overhead | 0 | 10842683 | 20135572
MCR022036 | HPR170 | 2020-04-01 | Labor | 0 | 9519561 | 12432228
MCR022037 | HPR170 | 2020-04-01 | Material | 0 | 23055305 | 26947350
MCR022038 | HPR170 | 2020-04-01 | Equipment | 0 | 7344567 | 8457425
MCR022039 | HPR170 | 2020-04-01 | Subcontract | 0 | 26751246 | 30535827
MCR022040 | HPR170 | 2020-04-01 | Overhead | 0 | 7393545 | 19895724
MCR022041 | HPR170 | 2020-05-01 | Labor | 0 | 7163334 | 8283504
MCR022042 | HPR170 | 2020-05-01 | Material | 0 | 17348787 | 16505532
MCR022043 | HPR170 | 2020-05-01 | Equipment | 0 | 5526682 | 5462753
MCR022044 | HPR170 | 2020-05-01 | Subcontract | 0 | 20129930 | 18989459
MCR022045 | HPR170 | 2020-05-01 | Overhead | 0 | 5563537 | 20113575
MCR022046 | HPR170 | 2020-06-01 | Labor | 0 | 6862218 | 7922498
MCR022047 | HPR170 | 2020-06-01 | Material | 0 | 16619519 | 18984880
MCR022048 | HPR170 | 2020-06-01 | Equipment | 0 | 5294364 | 6007678
MCR022049 | HPR170 | 2020-06-01 | Subcontract | 0 | 19283755 | 20525313
MCR022050 | HPR170 | 2020-06-01 | Overhead | 0 | 5329670 | 20036150
MCR022051 | HPR170 | 2020-07-01 | Labor | 0 | 1789050 | 1954767
MCR022052 | HPR170 | 2020-07-01 | Material | 0 | 4332878 | 4777896
MCR022053 | HPR170 | 2020-07-01 | Equipment | 0 | 1380295 | 1752774
MCR022054 | HPR170 | 2020-07-01 | Subcontract | 0 | 5027471 | 5264874
MCR022055 | HPR170 | 2020-07-01 | Overhead | 0 | 1389499 | 20486468
MCR022056 | HPR170 | 2020-08-01 | Labor | 0 | 457104 | 549776
MCR022057 | HPR170 | 2020-08-01 | Material | 0 | 1107054 | 1173812
MCR022058 | HPR170 | 2020-08-01 | Equipment | 0 | 352666 | 420829
MCR022059 | HPR170 | 2020-08-01 | Subcontract | 0 | 1284523 | 521971
MCR022060 | HPR170 | 2020-08-01 | Overhead | 0 | 355018 | 20918445
MCR022061 | HPR171 | 2017-05-01 | Labor | 12870103 | 10843408 | 10951558
MCR022062 | HPR171 | 2017-05-01 | Material | 28910768 | 24358102 | 23187625
MCR022063 | HPR171 | 2017-05-01 | Equipment | 6592003 | 5553940 | 5837048
MCR022064 | HPR171 | 2017-05-01 | Subcontract | 38232442 | 32211863 | 34733905
MCR022065 | HPR171 | 2017-05-01 | Overhead | 6146265 | 5178394 | 17376583
MCR022066 | HPR171 | 2017-06-01 | Labor | 33903081 | 28366888 | 26030481
MCR022067 | HPR171 | 2017-06-01 | Material | 76158221 | 63721989 | 61655471
MCR022068 | HPR171 | 2017-06-01 | Equipment | 17364990 | 14529379 | 13203284
MCR022069 | HPR171 | 2017-06-01 | Subcontract | 100713849 | 84267813 | 85365718
MCR022070 | HPR171 | 2017-06-01 | Overhead | 16190806 | 13546934 | 17711785
MCR022071 | HPR171 | 2017-07-01 | Labor | 48154837 | 21849784 | 23940593
MCR022072 | HPR171 | 2017-07-01 | Material | 108172668 | 49082284 | 46183857
MCR022073 | HPR171 | 2017-07-01 | Equipment | 24664668 | 11191351 | 13095430
MCR022074 | HPR171 | 2017-07-01 | Subcontract | 143050687 | 64907842 | 63064283
MCR022075 | HPR171 | 2017-07-01 | Overhead | 22996896 | 10434615 | 16452600
MCR022076 | HPR171 | 2017-08-01 | Labor | 56035194 | 43489907 | 47845215
MCR022077 | HPR171 | 2017-08-01 | Material | 125874716 | 97693598 | 109399285
MCR022078 | HPR171 | 2017-08-01 | Equipment | 28700948 | 22275314 | 22136473
MCR022079 | HPR171 | 2017-08-01 | Subcontract | 166460390 | 129192858 | 131393832
MCR022080 | HPR171 | 2017-08-01 | Overhead | 26760251 | 20769105 | 17469384
MCR022081 | HPR171 | 2017-09-01 | Labor | 58012817 | 59058442 | 63133245
MCR022082 | HPR171 | 2017-09-01 | Material | 130317151 | 132665992 | 153543896
MCR022083 | HPR171 | 2017-09-01 | Equipment | 29713876 | 30249440 | 29692065
MCR022084 | HPR171 | 2017-09-01 | Subcontract | 172335195 | 175441371 | 178954923
MCR022085 | HPR171 | 2017-09-01 | Overhead | 27704688 | 28204038 | 17640974
MCR022086 | HPR171 | 2017-10-01 | Labor | 54638007 | 60883962 | 73223446
MCR022087 | HPR171 | 2017-10-01 | Material | 122736142 | 136766750 | 120225264
MCR022088 | HPR171 | 2017-10-01 | Equipment | 27985315 | 31184463 | 29245633
MCR022089 | HPR171 | 2017-10-01 | Subcontract | 162309848 | 180864333 | 169372483
MCR022090 | HPR171 | 2017-10-01 | Overhead | 26093008 | 29075836 | 16821103
MCR022091 | HPR171 | 2017-11-01 | Labor | 46582119 | 46088332 | 46489866
MCR022092 | HPR171 | 2017-11-01 | Material | 104639791 | 103530571 | 107174975
MCR022093 | HPR171 | 2017-11-01 | Equipment | 23859130 | 23606214 | 27344397
MCR022094 | HPR171 | 2017-11-01 | Subcontract | 138378706 | 136911841 | 154335779
MCR022095 | HPR171 | 2017-11-01 | Overhead | 22245826 | 22010012 | 18079656
MCR022096 | HPR171 | 2017-12-01 | Labor | 34714922 | 42055157 | 44772958
MCR022097 | HPR171 | 2017-12-01 | Material | 77981901 | 94470644 | 93556609
MCR022098 | HPR171 | 2017-12-01 | Equipment | 17780811 | 21540442 | 20199610
MCR022099 | HPR171 | 2017-12-01 | Subcontract | 103125537 | 124930731 | 125171292
MCR022100 | HPR171 | 2017-12-01 | Overhead | 16578510 | 20083923 | 17020035
MCR022101 | HPR171 | 2018-01-01 | Labor | 20291968 | 28751735 | 31920289
MCR022102 | HPR171 | 2018-01-01 | Material | 45582884 | 64586490 | 73943162
MCR022103 | HPR171 | 2018-01-01 | Equipment | 10393445 | 14726496 | 15702527
MCR022104 | HPR171 | 2018-01-01 | Subcontract | 60280133 | 85411055 | 79844968
MCR022105 | HPR171 | 2018-01-01 | Overhead | 9690663 | 13730722 | 16016786
MCR022106 | HPR171 | 2018-02-01 | Labor | 5706988 | 24515298 | 27808367
MCR022107 | HPR171 | 2018-02-01 | Material | 12819898 | 55069964 | 57913475
MCR022108 | HPR171 | 2018-02-01 | Equipment | 2923091 | 12556614 | 12534188
MCR022109 | HPR171 | 2018-02-01 | Subcontract | 16953407 | 72826124 | 75642227
MCR022110 | HPR171 | 2018-02-01 | Overhead | 2725438 | 11707562 | 17255774
MCR022111 | HPR171 | 2018-03-01 | Labor | 0 | 5007124 | 4493673
MCR022112 | HPR171 | 2018-03-01 | Material | 0 | 11247759 | 8775954
MCR022113 | HPR171 | 2018-03-01 | Equipment | 0 | 2564624 | 2263524
MCR022114 | HPR171 | 2018-03-01 | Subcontract | 0 | 14874364 | 9637496
MCR022115 | HPR171 | 2018-03-01 | Overhead | 0 | 2391210 | 16039376
MCR022116 | HPR172 | 2019-02-01 | Labor | 2269798 | 1455769 | 1471215
MCR022117 | HPR172 | 2019-02-01 | Material | 7186317 | 4609051 | 4402000
MCR022118 | HPR172 | 2019-02-01 | Equipment | 1994392 | 1279133 | 1406653
MCR022119 | HPR172 | 2019-02-01 | Subcontract | 9034788 | 5794595 | 5803176
MCR022120 | HPR172 | 2019-02-01 | Overhead | 1738148 | 1114787 | 10815717
MCR022121 | HPR172 | 2019-03-01 | Labor | 6442968 | 2694098 | 2325901
MCR022122 | HPR172 | 2019-03-01 | Material | 20398823 | 8529676 | 8913948
MCR022123 | HPR172 | 2019-03-01 | Equipment | 5661209 | 2367209 | 2715271
MCR022124 | HPR172 | 2019-03-01 | Subcontract | 25645827 | 10723686 | 10334386
MCR022125 | HPR172 | 2019-03-01 | Overhead | 4933845 | 2063065 | 10957462
MCR022126 | HPR172 | 2019-04-01 | Labor | 10075532 | 7629734 | 8883297
MCR022127 | HPR172 | 2019-04-01 | Material | 31899739 | 24156196 | 24057206
MCR022128 | HPR172 | 2019-04-01 | Equipment | 8853016 | 6703979 | 7056812
MCR022129 | HPR172 | 2019-04-01 | Subcontract | 40105020 | 30369675 | 25688706
MCR022130 | HPR172 | 2019-04-01 | Overhead | 7715562 | 5842638 | 10242540
MCR022131 | HPR172 | 2019-05-01 | Labor | 13179996 | 7001333 | 6956643
MCR022132 | HPR172 | 2019-05-01 | Material | 41728658 | 22166641 | 22162261
MCR022133 | HPR172 | 2019-05-01 | Equipment | 11580799 | 6151825 | 5999599
MCR022134 | HPR172 | 2019-05-01 | Subcontract | 52462142 | 27868364 | 28098680
MCR022135 | HPR172 | 2019-05-01 | Overhead | 10092874 | 5361426 | 9353971
MCR022136 | HPR172 | 2019-06-01 | Labor | 15769494 | 7729306 | 6660653
MCR022137 | HPR172 | 2019-06-01 | Material | 49927164 | 24471447 | 24009707
MCR022138 | HPR172 | 2019-06-01 | Equipment | 13856100 | 6791470 | 7225073
MCR022139 | HPR172 | 2019-06-01 | Subcontract | 62769475 | 30766014 | 36313923
MCR022140 | HPR172 | 2019-06-01 | Overhead | 12075839 | 5918887 | 10541947
MCR022141 | HPR172 | 2019-07-01 | Labor | 17857866 | 7413741 | 8223193
MCR022142 | HPR172 | 2019-07-01 | Material | 56539078 | 23472350 | 23270205
MCR022143 | HPR172 | 2019-07-01 | Equipment | 15691080 | 6514194 | 6175991
MCR022144 | HPR172 | 2019-07-01 | Subcontract | 71082111 | 29509930 | 26367230
MCR022145 | HPR172 | 2019-07-01 | Overhead | 13675057 | 5677237 | 10835002
MCR022146 | HPR172 | 2019-08-01 | Labor | 19459751 | 11242134 | 13168831
MCR022147 | HPR172 | 2019-08-01 | Material | 61610742 | 35593271 | 38805599
MCR022148 | HPR172 | 2019-08-01 | Equipment | 17098600 | 9878068 | 10849581
MCR022149 | HPR172 | 2019-08-01 | Subcontract | 77458313 | 44748605 | 52530326
MCR022150 | HPR172 | 2019-08-01 | Overhead | 14901736 | 8608913 | 9576214
MCR022151 | HPR172 | 2019-09-01 | Labor | 20590693 | 13506343 | 14213021
MCR022152 | HPR172 | 2019-09-01 | Material | 65191372 | 42761894 | 41473213
MCR022153 | HPR172 | 2019-09-01 | Equipment | 18092319 | 11867549 | 11684932
MCR022154 | HPR172 | 2019-09-01 | Subcontract | 81959956 | 53761148 | 45656109
MCR022155 | HPR172 | 2019-09-01 | Overhead | 15767780 | 10342782 | 9860572
MCR022156 | HPR172 | 2019-10-01 | Labor | 21267279 | 13272213 | 13518107
MCR022157 | HPR172 | 2019-10-01 | Material | 67333484 | 42020624 | 40903680
MCR022158 | HPR172 | 2019-10-01 | Equipment | 18686811 | 11661827 | 11321575
MCR022159 | HPR172 | 2019-10-01 | Subcontract | 84653064 | 52829207 | 53180647
MCR022160 | HPR172 | 2019-10-01 | Overhead | 16285890 | 10163491 | 9946513
MCR022161 | HPR172 | 2019-11-01 | Labor | 21507306 | 10604541 | 10768620
MCR022162 | HPR172 | 2019-11-01 | Material | 68093421 | 33574613 | 37307931
MCR022163 | HPR172 | 2019-11-01 | Equipment | 18897714 | 9317837 | 9163644
MCR022164 | HPR172 | 2019-11-01 | Subcontract | 85608473 | 42210706 | 48338041
MCR022165 | HPR172 | 2019-11-01 | Overhead | 16469696 | 8120662 | 10963027
MCR022166 | HPR172 | 2019-12-01 | Labor | 21329990 | 17310564 | 17860112
MCR022167 | HPR172 | 2019-12-01 | Material | 67532029 | 54806284 | 58446076
MCR022168 | HPR172 | 2019-12-01 | Equipment | 18741913 | 15210184 | 17737178
MCR022169 | HPR172 | 2019-12-01 | Subcontract | 84902680 | 68903606 | 61213807
MCR022170 | HPR172 | 2019-12-01 | Overhead | 16333912 | 13255948 | 10578935
MCR022171 | HPR172 | 2020-01-01 | Labor | 20756243 | 26681152 | 29739979
MCR022172 | HPR172 | 2020-01-01 | Material | 65715513 | 84474130 | 81615553
MCR022173 | HPR172 | 2020-01-01 | Equipment | 18237782 | 23443791 | 22168677
MCR022174 | HPR172 | 2020-01-01 | Subcontract | 82618917 | 106202643 | 113923761
MCR022175 | HPR172 | 2020-01-01 | Overhead | 15894553 | 20431684 | 10839452
MCR022176 | HPR172 | 2020-02-01 | Labor | 19809028 | 19973928 | 21768383
MCR022177 | HPR172 | 2020-02-01 | Material | 62716571 | 63238656 | 56731949
MCR022178 | HPR172 | 2020-02-01 | Equipment | 17405497 | 17550389 | 21634426
MCR022179 | HPR172 | 2020-02-01 | Subcontract | 78848585 | 79504961 | 71351098
MCR022180 | HPR172 | 2020-02-01 | Overhead | 15169202 | 15295478 | 10917070
MCR022181 | HPR172 | 2020-03-01 | Labor | 18513841 | 19206801 | 22065693
MCR022182 | HPR172 | 2020-03-01 | Material | 58615931 | 60809884 | 67606337
MCR022183 | HPR172 | 2020-03-01 | Equipment | 16267461 | 16876341 | 16169344
MCR022184 | HPR172 | 2020-03-01 | Subcontract | 73693175 | 76451458 | 84788275
MCR022185 | HPR172 | 2020-03-01 | Overhead | 14177384 | 14708033 | 11375104
MCR022186 | HPR172 | 2020-04-01 | Labor | 16899388 | 17917152 | 19289734
MCR022187 | HPR172 | 2020-04-01 | Material | 53504478 | 56726780 | 54588179
MCR022188 | HPR172 | 2020-04-01 | Equipment | 14848899 | 15743172 | 15982630
MCR022189 | HPR172 | 2020-04-01 | Subcontract | 67266949 | 71318095 | 62739149
MCR022190 | HPR172 | 2020-04-01 | Overhead | 12941081 | 13720456 | 11093877
MCR022191 | HPR172 | 2020-05-01 | Labor | 14998564 | 12746006 | 12589700
MCR022192 | HPR172 | 2020-05-01 | Material | 47486353 | 40354620 | 40713407
MCR022193 | HPR172 | 2020-05-01 | Equipment | 13178711 | 11199468 | 11577756
MCR022194 | HPR172 | 2020-05-01 | Subcontract | 59700836 | 50734673 | 54203420
MCR022195 | HPR172 | 2020-05-01 | Overhead | 11485482 | 9760537 | 11148680
MCR022196 | HPR172 | 2020-06-01 | Labor | 12849936 | 14584109 | 15767060
MCR022197 | HPR172 | 2020-06-01 | Material | 40683668 | 46174165 | 46500473
MCR022198 | HPR172 | 2020-06-01 | Equipment | 11290787 | 12814544 | 14322315
MCR022199 | HPR172 | 2020-06-01 | Subcontract | 51148358 | 58051126 | 64320903
MCR022200 | HPR172 | 2020-06-01 | Overhead | 9840123 | 11168105 | 11199788
MCR022201 | HPR172 | 2020-07-01 | Labor | 10500168 | 9500769 | 11464441
MCR022202 | HPR172 | 2020-07-01 | Material | 33244164 | 30080005 | 32472948
MCR022203 | HPR172 | 2020-07-01 | Equipment | 9226129 | 8347992 | 10696218
MCR022204 | HPR172 | 2020-07-01 | Subcontract | 41795258 | 37817211 | 32599777
MCR022205 | HPR172 | 2020-07-01 | Overhead | 8040737 | 7275424 | 10921613
MCR022206 | HPR172 | 2020-08-01 | Labor | 8008316 | 9858800 | 11419747
MCR022207 | HPR172 | 2020-08-01 | Material | 25354810 | 31213552 | 36037537
MCR022208 | HPR172 | 2020-08-01 | Equipment | 7036626 | 8662581 | 7337027
MCR022209 | HPR172 | 2020-08-01 | Subcontract | 31876597 | 39242330 | 42410112
MCR022210 | HPR172 | 2020-08-01 | Overhead | 6132545 | 7549594 | 10614379
MCR022211 | HPR172 | 2020-09-01 | Labor | 5454497 | 14821335 | 17716106
MCR022212 | HPR172 | 2020-09-01 | Material | 17269266 | 46925238 | 44677145
MCR022213 | HPR172 | 2020-09-01 | Equipment | 4792675 | 13022987 | 13431749
MCR022214 | HPR172 | 2020-09-01 | Subcontract | 21711282 | 58995390 | 55561003
MCR022215 | HPR172 | 2020-09-01 | Overhead | 4176902 | 11349766 | 10407706
MCR022216 | HPR172 | 2020-10-01 | Labor | 2961635 | 16169445 | 17192661
MCR022217 | HPR172 | 2020-10-01 | Material | 9376713 | 51193433 | 52027508
MCR022218 | HPR172 | 2020-10-01 | Equipment | 2602284 | 14207523 | 13768059
MCR022219 | HPR172 | 2020-10-01 | Subcontract | 11788599 | 64361455 | 67351783
MCR022220 | HPR172 | 2020-10-01 | Overhead | 2267937 | 12382111 | 10439984
MCR022221 | HPR172 | 2020-11-01 | Labor | 786944 | 8849232 | 9791641
MCR022222 | HPR172 | 2020-11-01 | Material | 2491513 | 28017199 | 27758864
MCR022223 | HPR172 | 2020-11-01 | Equipment | 691460 | 7775509 | 7043504
MCR022224 | HPR172 | 2020-11-01 | Subcontract | 3132383 | 35223808 | 32408033
MCR022225 | HPR172 | 2020-11-01 | Overhead | 602620 | 6776495 | 10254632
MCR022226 | HPR172 | 2020-12-01 | Labor | 0 | 7531171 | 9287848
MCR022227 | HPR172 | 2020-12-01 | Material | 0 | 23844139 | 28395688
MCR022228 | HPR172 | 2020-12-01 | Equipment | 0 | 6617375 | 7452020
MCR022229 | HPR172 | 2020-12-01 | Subcontract | 0 | 29977351 | 28075362
MCR022230 | HPR172 | 2020-12-01 | Overhead | 0 | 5767161 | 9926173
MCR022231 | HPR172 | 2021-01-01 | Labor | 0 | 7122450 | 7325125
MCR022232 | HPR172 | 2021-01-01 | Material | 0 | 22550105 | 22769123
MCR022233 | HPR172 | 2021-01-01 | Equipment | 0 | 6258247 | 6717178
MCR022234 | HPR172 | 2021-01-01 | Subcontract | 0 | 28350464 | 30877300
MCR022235 | HPR172 | 2021-01-01 | Overhead | 0 | 5454174 | 10386797
MCR022236 | HPR172 | 2021-02-01 | Labor | 0 | 5594803 | 5504278
MCR022237 | HPR172 | 2021-02-01 | Material | 0 | 17713483 | 19392743
MCR022238 | HPR172 | 2021-02-01 | Equipment | 0 | 4915957 | 5624568
MCR022239 | HPR172 | 2021-02-01 | Subcontract | 0 | 22269762 | 23118060
MCR022240 | HPR172 | 2021-02-01 | Overhead | 0 | 4284345 | 10555305
MCR022241 | HPR172 | 2021-03-01 | Labor | 0 | 5285451 | 6227544
MCR022242 | HPR172 | 2021-03-01 | Material | 0 | 16734054 | 19068541
MCR022243 | HPR172 | 2021-03-01 | Equipment | 0 | 4644140 | 5012595
MCR022244 | HPR172 | 2021-03-01 | Subcontract | 0 | 21038403 | 18657656
MCR022245 | HPR172 | 2021-03-01 | Overhead | 0 | 4047451 | 10562626
MCR022246 | HPR172 | 2021-04-01 | Labor | 0 | 3948821 | 4491143
MCR022247 | HPR172 | 2021-04-01 | Material | 0 | 12502204 | 13447733
MCR022248 | HPR172 | 2021-04-01 | Equipment | 0 | 3469690 | 4905403
MCR022249 | HPR172 | 2021-04-01 | Subcontract | 0 | 15718033 | 16112096
MCR022250 | HPR172 | 2021-04-01 | Overhead | 0 | 3023897 | 10379022
MCR022251 | HPR172 | 2021-05-01 | Labor | 0 | 1176530 | 1396219
MCR022252 | HPR172 | 2021-05-01 | Material | 0 | 3724964 | 3260615
MCR022253 | HPR172 | 2021-05-01 | Equipment | 0 | 1033776 | 759648
MCR022254 | HPR172 | 2021-05-01 | Subcontract | 0 | 4683103 | 4489382
MCR022255 | HPR172 | 2021-05-01 | Overhead | 0 | 900954 | 9583491
MCR022256 | HPR172 | 2021-06-01 | Labor | 0 | 461503 | 485537
MCR022257 | HPR172 | 2021-06-01 | Material | 0 | 1461148 | 1156123
MCR022258 | HPR172 | 2021-06-01 | Equipment | 0 | 405507 | 501604
MCR022259 | HPR172 | 2021-06-01 | Subcontract | 0 | 1836986 | 2314017
MCR022260 | HPR172 | 2021-06-01 | Overhead | 0 | 353407 | 9767792
MCR022261 | HPR173 | 2023-03-01 | Labor | 18051838 | 20356376 | 21975945
MCR022262 | HPR173 | 2023-03-01 | Material | 32785493 | 36970962 | 39453028
MCR022263 | HPR173 | 2023-03-01 | Equipment | 6305229 | 7110168 | 6895336
MCR022264 | HPR173 | 2023-03-01 | Subcontract | 28901116 | 32590697 | 34185102
MCR022265 | HPR173 | 2023-03-01 | Overhead | 9501934 | 10714972 | 42776818
MCR022266 | HPR173 | 2023-04-01 | Labor | 50357047 | 23832113 | 26755957
MCR022267 | HPR173 | 2023-04-01 | Material | 91457756 | 43283546 | 38648846
MCR022268 | HPR173 | 2023-04-01 | Equipment | 17588940 | 8324190 | 9365626
MCR022269 | HPR173 | 2023-04-01 | Subcontract | 80621976 | 38155376 | 36853260
MCR022270 | HPR173 | 2023-04-01 | Overhead | 26506406 | 12544494 | 43550978
MCR022271 | HPR173 | 2023-05-01 | Labor | 77088364 | 50316495 | 51356940
MCR022272 | HPR173 | 2023-05-01 | Material | 140006796 | 91384106 | 84125234
MCR022273 | HPR173 | 2023-05-01 | Equipment | 26925777 | 17574776 | 16740528
MCR022274 | HPR173 | 2023-05-01 | Subcontract | 123418998 | 80557052 | 76961034
MCR022275 | HPR173 | 2023-05-01 | Overhead | 40576952 | 26485061 | 45182656
MCR022276 | HPR173 | 2023-06-01 | Labor | 98419343 | 104083447 | 106672724
MCR022277 | HPR173 | 2023-06-01 | Material | 178747816 | 189034883 | 199853369
MCR022278 | HPR173 | 2023-06-01 | Equipment | 34376359 | 36354743 | 38184498
MCR022279 | HPR173 | 2023-06-01 | Subcontract | 157570039 | 166638309 | 174928600
MCR022280 | HPR173 | 2023-06-01 | Overhead | 51804925 | 54786336 | 40435618
MCR022281 | HPR173 | 2023-07-01 | Labor | 114535507 | 55549173 | 54144211
MCR022282 | HPR173 | 2023-07-01 | Material | 208017766 | 100887621 | 71055966
MCR022283 | HPR173 | 2023-07-01 | Equipment | 40005487 | 19402469 | 23532045
MCR022284 | HPR173 | 2023-07-01 | Subcontract | 183372129 | 88934605 | 81397696
MCR022285 | HPR173 | 2023-07-01 | Overhead | 60287980 | 29239382 | 43244901
MCR022286 | HPR173 | 2023-08-01 | Labor | 125636386 | 70885570 | 74302773
MCR022287 | HPR173 | 2023-08-01 | Material | 228179025 | 128741368 | 118188159
MCR022288 | HPR173 | 2023-08-01 | Equipment | 43882852 | 24759236 | 23551397
MCR022289 | HPR173 | 2023-08-01 | Subcontract | 201144711 | 113488281 | 103798533
MCR022290 | HPR173 | 2023-08-01 | Overhead | 66131143 | 37311991 | 45392384
MCR022291 | HPR173 | 2023-09-01 | Labor | 131938106 | 172521716 | 182470301
MCR022292 | HPR173 | 2023-09-01 | Material | 239624120 | 313331498 | 294747492
MCR022293 | HPR173 | 2023-09-01 | Equipment | 46083946 | 60259175 | 54652851
MCR022294 | HPR173 | 2023-09-01 | Subcontract | 211233809 | 276208446 | 296133300
MCR022295 | HPR173 | 2023-09-01 | Overhead | 69448175 | 90810144 | 43435982
MCR022296 | HPR173 | 2023-10-01 | Labor | 133676797 | 120071848 | 140406486
MCR022297 | HPR173 | 2023-10-01 | Material | 242781906 | 218072790 | 216422370
MCR022298 | HPR173 | 2023-10-01 | Equipment | 46691244 | 41939245 | 43048300
MCR022299 | HPR173 | 2023-10-01 | Subcontract | 214017465 | 192235848 | 201441310
MCR022300 | HPR173 | 2023-10-01 | Overhead | 70363369 | 63202140 | 45776758
MCR022301 | HPR173 | 2023-11-01 | Labor | 131113160 | 127659972 | 122527010
MCR022302 | HPR173 | 2023-11-01 | Material | 238125865 | 231854234 | 221810073
MCR022303 | HPR173 | 2023-11-01 | Equipment | 45795805 | 44589660 | 41719838
MCR022304 | HPR173 | 2023-11-01 | Subcontract | 209913065 | 204384487 | 151974767
MCR022305 | HPR173 | 2023-11-01 | Overhead | 69013949 | 67196297 | 44029751
MCR022306 | HPR173 | 2023-12-01 | Labor | 124538807 | 87463231 | 96274090
MCR022307 | HPR173 | 2023-12-01 | Material | 226185617 | 158849481 | 126527434
MCR022308 | HPR173 | 2023-12-01 | Equipment | 43499485 | 30549558 | 29388326
MCR022309 | HPR173 | 2023-12-01 | Subcontract | 199387479 | 140029230 | 146617794
MCR022310 | HPR173 | 2023-12-01 | Overhead | 65553411 | 46037964 | 44916231
MCR022311 | HPR173 | 2024-01-01 | Labor | 114285393 | 240035871 | 214538155
MCR022312 | HPR173 | 2024-01-01 | Material | 207563513 | 435949749 | 475555222
MCR022313 | HPR173 | 2024-01-01 | Equipment | 39918126 | 83840828 | 92178876
MCR022314 | HPR173 | 2024-01-01 | Subcontract | 182971695 | 384299067 | 417484583
MCR022315 | HPR173 | 2024-01-01 | Overhead | 60156328 | 126347525 | 43161927
MCR022316 | HPR173 | 2024-02-01 | Labor | 100738454 | 54517748 | 76711920
MCR022317 | HPR173 | 2024-02-01 | Material | 182959754 | 99014362 | 47264203
MCR022318 | HPR173 | 2024-02-01 | Equipment | 35186389 | 19042209 | 17556188
MCR022319 | HPR173 | 2024-02-01 | Subcontract | 161282953 | 87283287 | 55708782
MCR022320 | HPR173 | 2024-02-01 | Overhead | 53025635 | 28696472 | 49528316
MCR022321 | HPR173 | 2024-03-01 | Labor | 84359719 | 70940917 | 77894689
MCR022322 | HPR173 | 2024-03-01 | Material | 153212927 | 128841889 | 130084170
MCR022323 | HPR173 | 2024-03-01 | Equipment | 29465549 | 24778568 | 24653025
MCR022324 | HPR173 | 2024-03-01 | Subcontract | 135060486 | 113576892 | 138557024
MCR022325 | HPR173 | 2024-03-01 | Overhead | 44404370 | 37341124 | 43067348
MCR022326 | HPR173 | 2024-04-01 | Labor | 65726435 | 120929874 | 124868804
MCR022327 | HPR173 | 2024-04-01 | Material | 119371421 | 219631125 | 224195733
MCR022328 | HPR173 | 2024-04-01 | Equipment | 22957230 | 42238940 | 46259711
MCR022329 | HPR173 | 2024-04-01 | Subcontract | 105228471 | 193609554 | 226113520
MCR022330 | HPR173 | 2024-04-01 | Overhead | 34596381 | 63653779 | 47081076
MCR022331 | HPR173 | 2024-05-01 | Labor | 45610163 | 60288559 | 62961443
MCR022332 | HPR173 | 2024-05-01 | Material | 82836532 | 109495226 | 88509358
MCR022333 | HPR173 | 2024-05-01 | Equipment | 15930927 | 21057864 | 17088769
MCR022334 | HPR173 | 2024-05-01 | Subcontract | 73022182 | 96522394 | 139559426
MCR022335 | HPR173 | 2024-05-01 | Overhead | 24007792 | 31734049 | 42831955
MCR022336 | HPR173 | 2024-06-01 | Labor | 25172392 | 30676676 | 29885299
MCR022337 | HPR173 | 2024-06-01 | Material | 45717743 | 55714545 | 57691007
MCR022338 | HPR173 | 2024-06-01 | Equipment | 8792329 | 10714890 | 11900790
MCR022339 | HPR173 | 2024-06-01 | Subcontract | 40301172 | 49113568 | 99331140
MCR022340 | HPR173 | 2024-06-01 | Overhead | 13249976 | 16147262 | 44157916
MCR022341 | HPR173 | 2024-07-01 | Labor | 6777617 | 19066527 | 19125120
MCR022342 | HPR173 | 2024-07-01 | Material | 12309413 | 34628357 | 33929952
MCR022343 | HPR173 | 2024-07-01 | Equipment | 2367317 | 6659644 | 6854042
MCR022344 | HPR173 | 2024-07-01 | Subcontract | 10851012 | 30525641 | 74339855
MCR022345 | HPR173 | 2024-07-01 | Overhead | 3567530 | 10036036 | 44677437
MCR022346 | HPR173 | 2024-08-01 | Labor | 0 | 12265920 | 10816953
MCR022347 | HPR173 | 2024-08-01 | Material | 0 | 22277191 | 17935018
MCR022348 | HPR173 | 2024-08-01 | Equipment | 0 | 4284297 | 4268007
MCR022349 | HPR173 | 2024-08-01 | Subcontract | 0 | 19637822 | 55555939
MCR022350 | HPR173 | 2024-08-01 | Overhead | 0 | 6456405 | 46396664
MCR022351 | HPR173 | 2024-09-01 | Labor | 0 | 6563497 | 6450061
MCR022352 | HPR173 | 2024-09-01 | Material | 0 | 11920531 | 11459027
MCR022353 | HPR173 | 2024-09-01 | Equipment | 0 | 2292528 | 2339509
MCR022354 | HPR173 | 2024-09-01 | Subcontract | 0 | 10508204 | 58707830
MCR022355 | HPR173 | 2024-09-01 | Overhead | 0 | 3454824 | 47504052
MCR022356 | HPR174 | 2017-10-01 | Labor | 11463666 | 10033325 | 10340224
MCR022357 | HPR174 | 2017-10-01 | Material | 22152688 | 19388659 | 17945857
MCR022358 | HPR174 | 2017-10-01 | Equipment | 5129954 | 4489881 | 4245533
MCR022359 | HPR174 | 2017-10-01 | Subcontract | 23465614 | 20537769 | 19365135
MCR022360 | HPR174 | 2017-10-01 | Overhead | 6144872 | 5378166 | 27147283
MCR022361 | HPR174 | 2017-11-01 | Labor | 31645637 | 21865746 | 20925310
MCR022362 | HPR174 | 2017-11-01 | Material | 61152855 | 42253939 | 42416537
MCR022363 | HPR174 | 2017-11-01 | Equipment | 14161321 | 9784851 | 10627057
MCR022364 | HPR174 | 2017-11-01 | Subcontract | 64777209 | 44758209 | 42812443
MCR022365 | HPR174 | 2017-11-01 | Overhead | 16963020 | 11720702 | 27155433
MCR022366 | HPR174 | 2017-12-01 | Labor | 47812289 | 28798871 | 25723700
MCR022367 | HPR174 | 2017-12-01 | Material | 92393717 | 55651691 | 55030219
MCR022368 | HPR174 | 2017-12-01 | Equipment | 21395846 | 12887403 | 12245517
MCR022369 | HPR174 | 2017-12-01 | Subcontract | 97869626 | 58950006 | 61311310
MCR022370 | HPR174 | 2017-12-01 | Overhead | 25628835 | 15437067 | 24682950
MCR022371 | HPR174 | 2018-01-01 | Labor | 60108739 | 58029795 | 64204439
MCR022372 | HPR174 | 2018-01-01 | Material | 116155697 | 112138291 | 106246562
MCR022373 | HPR174 | 2018-01-01 | Equipment | 26898468 | 25968147 | 27279317
MCR022374 | HPR174 | 2018-01-01 | Subcontract | 123039910 | 118784405 | 103637969
MCR022375 | HPR174 | 2018-01-01 | Overhead | 32220105 | 31105728 | 26040083
MCR022376 | HPR174 | 2018-02-01 | Labor | 68691854 | 85066009 | 91855185
MCR022377 | HPR174 | 2018-02-01 | Material | 132741933 | 164383777 | 189561036
MCR022378 | HPR174 | 2018-02-01 | Equipment | 30739384 | 38066766 | 35016821
MCR022379 | HPR174 | 2018-02-01 | Subcontract | 140609165 | 174126330 | 173131383
MCR022380 | HPR174 | 2018-02-01 | Overhead | 36820915 | 45597957 | 26597559
MCR022381 | HPR174 | 2018-03-01 | Labor | 73732628 | 76746901 | 70126555
MCR022382 | HPR174 | 2018-03-01 | Material | 142482856 | 148307716 | 143942113
MCR022383 | HPR174 | 2018-03-01 | Equipment | 32995115 | 34343992 | 31707667
MCR022384 | HPR174 | 2018-03-01 | Subcontract | 150927405 | 157097487 | 170413626
MCR022385 | HPR174 | 2018-03-01 | Overhead | 39522922 | 41138664 | 25675049
MCR022386 | HPR174 | 2018-04-01 | Labor | 75419355 | 62305767 | 70202917
MCR022387 | HPR174 | 2018-04-01 | Material | 145742332 | 120401292 | 120019672
MCR022388 | HPR174 | 2018-04-01 | Equipment | 33749920 | 27881631 | 31049717
MCR022389 | HPR174 | 2018-04-01 | Subcontract | 154380060 | 127537130 | 95951170
MCR022390 | HPR174 | 2018-04-01 | Overhead | 40427059 | 33397779 | 25004973
MCR022391 | HPR174 | 2018-05-01 | Labor | 73962024 | 65572478 | 64745798
MCR022392 | HPR174 | 2018-05-01 | Material | 142926146 | 126713969 | 116792000
MCR022393 | HPR174 | 2018-05-01 | Equipment | 33097768 | 29343474 | 26607175
MCR022394 | HPR174 | 2018-05-01 | Subcontract | 151396967 | 134223941 | 149158292
MCR022395 | HPR174 | 2018-05-01 | Overhead | 39645885 | 35148835 | 25950249
MCR022396 | HPR174 | 2018-06-01 | Labor | 69598631 | 54814600 | 57489357
MCR022397 | HPR174 | 2018-06-01 | Material | 134494213 | 105925166 | 132789411
MCR022398 | HPR174 | 2018-06-01 | Equipment | 31145164 | 24529358 | 29733990
MCR022399 | HPR174 | 2018-06-01 | Subcontract | 142465298 | 112203045 | 101992352
MCR022400 | HPR174 | 2018-06-01 | Overhead | 37306975 | 29382286 | 27881279
MCR022401 | HPR174 | 2018-07-01 | Labor | 62604711 | 57429882 | 65338192
MCR022402 | HPR174 | 2018-07-01 | Material | 120978978 | 110979005 | 100830631
MCR022403 | HPR174 | 2018-07-01 | Equipment | 28015407 | 25699688 | 24863450
MCR022404 | HPR174 | 2018-07-01 | Subcontract | 128149054 | 117556411 | 116751171
MCR022405 | HPR174 | 2018-07-01 | Overhead | 33558021 | 30784157 | 26051176
MCR022406 | HPR174 | 2018-08-01 | Labor | 53308649 | 59280970 | 55069359
MCR022407 | HPR174 | 2018-08-01 | Material | 103015026 | 114556094 | 118613223
MCR022408 | HPR174 | 2018-08-01 | Equipment | 23855450 | 26528044 | 26650882
MCR022409 | HPR174 | 2018-08-01 | Subcontract | 109120430 | 121345504 | 153806062
MCR022410 | HPR174 | 2018-08-01 | Overhead | 28575051 | 31776395 | 26604009
MCR022411 | HPR174 | 2018-09-01 | Labor | 42118569 | 64532498 | 62864117
MCR022412 | HPR174 | 2018-09-01 | Material | 81391022 | 124704285 | 119970312
MCR022413 | HPR174 | 2018-09-01 | Equipment | 18847924 | 28878086 | 27747920
MCR022414 | HPR174 | 2018-09-01 | Subcontract | 86214833 | 132095149 | 153621205
MCR022415 | HPR174 | 2018-09-01 | Overhead | 22576829 | 34591374 | 24470271
MCR022416 | HPR174 | 2018-10-01 | Labor | 29575954 | 31655962 | 38998648
MCR022417 | HPR174 | 2018-10-01 | Material | 57153347 | 61172807 | 79111172
MCR022418 | HPR174 | 2018-10-01 | Equipment | 13235145 | 14165941 | 12670767
MCR022419 | HPR174 | 2018-10-01 | Subcontract | 60540661 | 64798343 | 68119564
MCR022420 | HPR174 | 2018-10-01 | Overhead | 15853608 | 16968554 | 23822844
MCR022421 | HPR174 | 2018-11-01 | Labor | 16488112 | 21347077 | 21009176
MCR022422 | HPR174 | 2018-11-01 | Material | 31862057 | 41251649 | 41983730
MCR022423 | HPR174 | 2018-11-01 | Equipment | 7378377 | 9552748 | 11989943
MCR022424 | HPR174 | 2018-11-01 | Subcontract | 33750430 | 43696516 | 57638541
MCR022425 | HPR174 | 2018-11-01 | Overhead | 8838127 | 11442680 | 27153894
MCR022426 | HPR174 | 2018-12-01 | Labor | 4474861 | 20430121 | 24928478
MCR022427 | HPR174 | 2018-12-01 | Material | 8647338 | 39479700 | 35549530
MCR022428 | HPR174 | 2018-12-01 | Equipment | 2002486 | 9142414 | 7632167
MCR022429 | HPR174 | 2018-12-01 | Subcontract | 9159841 | 41819548 | 79193639
MCR022430 | HPR174 | 2018-12-01 | Overhead | 2398661 | 10951164 | 25110117
MCR022431 | HPR174 | 2019-01-01 | Labor | 0 | 3095676 | 2012992
MCR022432 | HPR174 | 2019-01-01 | Material | 0 | 5982165 | 9973275
MCR022433 | HPR174 | 2019-01-01 | Equipment | 0 | 1385305 | 1905865
MCR022434 | HPR174 | 2019-01-01 | Subcontract | 0 | 6336710 | 33091068
MCR022435 | HPR174 | 2019-01-01 | Overhead | 0 | 1659376 | 25496784
MCR022436 | HPR175 | 2017-10-01 | Labor | 1997499 | 1644211 | 1516587
MCR022437 | HPR175 | 2017-10-01 | Material | 4838235 | 3982519 | 3700645
MCR022438 | HPR175 | 2017-10-01 | Equipment | 1405032 | 1156531 | 1267709
MCR022439 | HPR175 | 2017-10-01 | Subcontract | 6329898 | 5210359 | 5038493
MCR022440 | HPR175 | 2017-10-01 | Overhead | 1399298 | 1151811 | 8241587
MCR022441 | HPR175 | 2017-11-01 | Labor | 5654283 | 4602607 | 4942648
MCR022442 | HPR175 | 2017-11-01 | Material | 13695498 | 11148185 | 12041617
MCR022443 | HPR175 | 2017-11-01 | Equipment | 3977198 | 3237454 | 3097653
MCR022444 | HPR175 | 2017-11-01 | Subcontract | 17917920 | 14585252 | 15148872
MCR022445 | HPR175 | 2017-11-01 | Overhead | 3960965 | 3224240 | 8961115
MCR022446 | HPR175 | 2017-12-01 | Labor | 8812510 | 8697503 | 9586812
MCR022447 | HPR175 | 2017-12-01 | Material | 21345184 | 21066621 | 22345511
MCR022448 | HPR175 | 2017-12-01 | Equipment | 6198681 | 6117786 | 5929238
MCR022449 | HPR175 | 2017-12-01 | Subcontract | 27926059 | 27561613 | 26381848
MCR022450 | HPR175 | 2017-12-01 | Overhead | 6173381 | 6092816 | 8022288
MCR022451 | HPR175 | 2018-01-01 | Labor | 11484337 | 6673423 | 6800676
MCR022452 | HPR175 | 2018-01-01 | Material | 27816738 | 16164004 | 15647712
MCR022453 | HPR175 | 2018-01-01 | Equipment | 8078033 | 4694057 | 5190761
MCR022454 | HPR175 | 2018-01-01 | Subcontract | 36392841 | 21147485 | 22730968
MCR022455 | HPR175 | 2018-01-01 | Overhead | 8045062 | 4674898 | 8021907
MCR022456 | HPR175 | 2018-02-01 | Labor | 13682569 | 14275648 | 13235799
MCR022457 | HPR175 | 2018-02-01 | Material | 33141176 | 34577700 | 29892857
MCR022458 | HPR175 | 2018-02-01 | Equipment | 9624259 | 10041429 | 10389949
MCR022459 | HPR175 | 2018-02-01 | Subcontract | 43358842 | 45238257 | 41300184
MCR022460 | HPR175 | 2018-02-01 | Overhead | 9584978 | 10000445 | 8620909
MCR022461 | HPR175 | 2018-03-01 | Labor | 15420740 | 9767077 | 11175968
MCR022462 | HPR175 | 2018-03-01 | Material | 37351281 | 23657286 | 24960633
MCR022463 | HPR175 | 2018-03-01 | Equipment | 10846882 | 6870120 | 6970678
MCR022464 | HPR175 | 2018-03-01 | Subcontract | 48866953 | 30950999 | 33017273
MCR022465 | HPR175 | 2018-03-01 | Overhead | 10802610 | 6842080 | 8242948
MCR022466 | HPR175 | 2018-04-01 | Labor | 16713216 | 9378635 | 10491339
MCR022467 | HPR175 | 2018-04-01 | Material | 40481847 | 22716422 | 25957178
MCR022468 | HPR175 | 2018-04-01 | Equipment | 11756004 | 6596891 | 7034412
MCR022469 | HPR175 | 2018-04-01 | Subcontract | 52962695 | 29720061 | 28638885
MCR022470 | HPR175 | 2018-04-01 | Overhead | 11708022 | 6569966 | 7832819
MCR022471 | HPR175 | 2018-05-01 | Labor | 17575316 | 15526529 | 16982515
MCR022472 | HPR175 | 2018-05-01 | Material | 42569978 | 37607517 | 40059179
MCR022473 | HPR175 | 2018-05-01 | Equipment | 12362401 | 10921293 | 9568091
MCR022474 | HPR175 | 2018-05-01 | Subcontract | 55694613 | 49202189 | 50146187
MCR022475 | HPR175 | 2018-05-01 | Overhead | 12311944 | 10876718 | 7907588
MCR022476 | HPR175 | 2018-06-01 | Labor | 18023464 | 12659481 | 11389653
MCR022477 | HPR175 | 2018-06-01 | Material | 43655458 | 30663108 | 31640784
MCR022478 | HPR175 | 2018-06-01 | Equipment | 12677627 | 8904624 | 10067599
MCR022479 | HPR175 | 2018-06-01 | Subcontract | 57114754 | 40116767 | 45523793
MCR022480 | HPR175 | 2018-06-01 | Overhead | 12625883 | 8868280 | 8131574
MCR022481 | HPR175 | 2018-07-01 | Labor | 18075383 | 16972796 | 18776774
MCR022482 | HPR175 | 2018-07-01 | Material | 43781212 | 41110587 | 40187610
MCR022483 | HPR175 | 2018-07-01 | Equipment | 12714146 | 11938591 | 10269444
MCR022484 | HPR175 | 2018-07-01 | Subcontract | 57279279 | 53785280 | 54541468
MCR022485 | HPR175 | 2018-07-01 | Overhead | 12662253 | 11889864 | 7704805
MCR022486 | HPR175 | 2018-08-01 | Labor | 17750340 | 13586073 | 12392190
MCR022487 | HPR175 | 2018-08-01 | Material | 42993910 | 32907450 | 33936436
MCR022488 | HPR175 | 2018-08-01 | Equipment | 12485512 | 9556385 | 11552577
MCR022489 | HPR175 | 2018-08-01 | Subcontract | 56249246 | 43053057 | 45587025
MCR022490 | HPR175 | 2018-08-01 | Overhead | 12434553 | 9517381 | 7717163
MCR022491 | HPR175 | 2018-09-01 | Labor | 17069473 | 10333713 | 10348572
MCR022492 | HPR175 | 2018-09-01 | Material | 41344751 | 25029758 | 21871104
MCR022493 | HPR175 | 2018-09-01 | Equipment | 12006593 | 7268689 | 6315060
MCR022494 | HPR175 | 2018-09-01 | Subcontract | 54091639 | 32746615 | 29764452
MCR022495 | HPR175 | 2018-09-01 | Overhead | 11957588 | 7239022 | 8124545
MCR022496 | HPR175 | 2018-10-01 | Labor | 16056228 | 19331669 | 20424407
MCR022497 | HPR175 | 2018-10-01 | Material | 38890526 | 46824122 | 44899701
MCR022498 | HPR175 | 2018-10-01 | Equipment | 11293881 | 13597812 | 14245003
MCR022499 | HPR175 | 2018-10-01 | Subcontract | 50880758 | 61260339 | 61241060
MCR022500 | HPR175 | 2018-10-01 | Overhead | 11247786 | 13542313 | 7575042
MCR022501 | HPR175 | 2018-11-01 | Labor | 14736973 | 13669182 | 13357231
MCR022502 | HPR175 | 2018-11-01 | Material | 35695096 | 33108752 | 34249238
MCR022503 | HPR175 | 2018-11-01 | Equipment | 10365923 | 9614843 | 10581928
MCR022504 | HPR175 | 2018-11-01 | Subcontract | 46700154 | 43316421 | 41597931
MCR022505 | HPR175 | 2018-11-01 | Overhead | 10323614 | 9575600 | 7833700
MCR022506 | HPR175 | 2018-12-01 | Labor | 13141875 | 16756434 | 16065820
MCR022507 | HPR175 | 2018-12-01 | Material | 31831538 | 40586525 | 49843673
MCR022508 | HPR175 | 2018-12-01 | Equipment | 9243938 | 11786403 | 12004441
MCR022509 | HPR175 | 2018-12-01 | Subcontract | 41645433 | 53099647 | 56875751
MCR022510 | HPR175 | 2018-12-01 | Overhead | 9206209 | 11738297 | 8110300
MCR022511 | HPR175 | 2019-01-01 | Labor | 11306256 | 10124298 | 10949648
MCR022512 | HPR175 | 2019-01-01 | Material | 27385402 | 24522525 | 18640884
MCR022513 | HPR175 | 2019-01-01 | Equipment | 7952772 | 7121387 | 6831512
MCR022514 | HPR175 | 2019-01-01 | Subcontract | 35828520 | 32082998 | 27010524
MCR022515 | HPR175 | 2019-01-01 | Overhead | 7920313 | 7092321 | 7949653
MCR022516 | HPR175 | 2019-02-01 | Labor | 9272771 | 9734269 | 10046299
MCR022517 | HPR175 | 2019-02-01 | Material | 22460003 | 23577818 | 22879706
MCR022518 | HPR175 | 2019-02-01 | Equipment | 6522427 | 6847042 | 9003924
MCR022519 | HPR175 | 2019-02-01 | Subcontract | 29384586 | 30847031 | 36433041
MCR022520 | HPR175 | 2019-02-01 | Overhead | 6495806 | 6819096 | 8066418
MCR022521 | HPR175 | 2019-03-01 | Labor | 7095281 | 8454129 | 6530941
MCR022522 | HPR175 | 2019-03-01 | Material | 17185805 | 20477133 | 22006287
MCR022523 | HPR175 | 2019-03-01 | Equipment | 4990790 | 5946598 | 5839750
MCR022524 | HPR175 | 2019-03-01 | Subcontract | 22484314 | 26790382 | 27644856
MCR022525 | HPR175 | 2019-03-01 | Overhead | 4970420 | 5922327 | 8406032
MCR022526 | HPR175 | 2019-04-01 | Labor | 4846669 | 9759571 | 8693106
MCR022527 | HPR175 | 2019-04-01 | Material | 11739338 | 23639105 | 25244470
MCR022528 | HPR175 | 2019-04-01 | Equipment | 3409126 | 6864840 | 7017131
MCR022529 | HPR175 | 2019-04-01 | Subcontract | 15358662 | 30927213 | 32317349
MCR022530 | HPR175 | 2019-04-01 | Overhead | 3395211 | 6836821 | 8465938
MCR022531 | HPR175 | 2019-05-01 | Labor | 2638383 | 9443557 | 9824651
MCR022532 | HPR175 | 2019-05-01 | Material | 6390548 | 22873671 | 23290660
MCR022533 | HPR175 | 2019-05-01 | Equipment | 1855827 | 6642557 | 7855803
MCR022534 | HPR175 | 2019-05-01 | Subcontract | 8360800 | 29925790 | 29018800
MCR022535 | HPR175 | 2019-05-01 | Overhead | 1848253 | 6615445 | 6987573
MCR022536 | HPR175 | 2019-06-01 | Labor | 702534 | 8268731 | 8276949
MCR022537 | HPR175 | 2019-06-01 | Material | 1701639 | 20028073 | 19913793
MCR022538 | HPR175 | 2019-06-01 | Equipment | 494159 | 5816190 | 5988429
MCR022539 | HPR175 | 2019-06-01 | Subcontract | 2226267 | 26202874 | 27364686
MCR022540 | HPR175 | 2019-06-01 | Overhead | 492142 | 5792451 | 8087940
MCR022541 | HPR175 | 2019-07-01 | Labor | 0 | 6034854 | 6319108
MCR022542 | HPR175 | 2019-07-01 | Material | 0 | 14617296 | 14687268
MCR022543 | HPR175 | 2019-07-01 | Equipment | 0 | 4244890 | 4552352
MCR022544 | HPR175 | 2019-07-01 | Subcontract | 0 | 19123915 | 20293981
MCR022545 | HPR175 | 2019-07-01 | Overhead | 0 | 4227565 | 7816433
MCR022546 | HPR175 | 2019-08-01 | Labor | 0 | 2194433 | 2189232
MCR022547 | HPR175 | 2019-08-01 | Material | 0 | 5315237 | 6570493
MCR022548 | HPR175 | 2019-08-01 | Equipment | 0 | 1543555 | 1429979
MCR022549 | HPR175 | 2019-08-01 | Subcontract | 0 | 6953963 | 5874201
MCR022550 | HPR175 | 2019-08-01 | Overhead | 0 | 1537255 | 7410183
MCR022551 | HPR175 | 2019-09-01 | Labor | 0 | 2347613 | 2372177
MCR022552 | HPR175 | 2019-09-01 | Material | 0 | 5686260 | 4981331
MCR022553 | HPR175 | 2019-09-01 | Equipment | 0 | 1651301 | 1685511
MCR022554 | HPR175 | 2019-09-01 | Subcontract | 0 | 7439375 | 7910670
MCR022555 | HPR175 | 2019-09-01 | Overhead | 0 | 1644561 | 8069124
MCR022556 | HPR175 | 2019-10-01 | Labor | 0 | 1261175 | 1231901
MCR022557 | HPR175 | 2019-10-01 | Material | 0 | 3054749 | 2783539
MCR022558 | HPR175 | 2019-10-01 | Equipment | 0 | 887105 | 1013910
MCR022559 | HPR175 | 2019-10-01 | Subcontract | 0 | 3996551 | 3931034
MCR022560 | HPR175 | 2019-10-01 | Overhead | 0 | 883484 | 9113662
MCR022561 | HPR175 | 2019-11-01 | Labor | 0 | 558489 | 530996
MCR022562 | HPR175 | 2019-11-01 | Material | 0 | 1352741 | 1696186
MCR022563 | HPR175 | 2019-11-01 | Equipment | 0 | 392838 | 449180
MCR022564 | HPR175 | 2019-11-01 | Subcontract | 0 | 1769801 | 2042191
MCR022565 | HPR175 | 2019-11-01 | Overhead | 0 | 391235 | 7644581
MCR022566 | HPR176 | 2022-06-01 | Labor | 8584707 | 5707029 | 6238478
MCR022567 | HPR176 | 2022-06-01 | Material | 20920376 | 13907663 | 13138752
MCR022568 | HPR176 | 2022-06-01 | Equipment | 4518213 | 3003664 | 2722425
MCR022569 | HPR176 | 2022-06-01 | Subcontract | 29659366 | 19717258 | 20117464
MCR022570 | HPR176 | 2022-06-01 | Overhead | 7193465 | 4782146 | 37406554
MCR022571 | HPR176 | 2022-07-01 | Labor | 24051072 | 9945971 | 9598392
MCR022572 | HPR176 | 2022-07-01 | Material | 58610911 | 24237689 | 26832200
MCR022573 | HPR176 | 2022-07-01 | Equipment | 12658310 | 5234660 | 5913857
MCR022574 | HPR176 | 2022-07-01 | Subcontract | 83094227 | 34362408 | 31183333
MCR022575 | HPR176 | 2022-07-01 | Overhead | 20153345 | 8334123 | 33189720
MCR022576 | HPR176 | 2022-08-01 | Labor | 37015016 | 18418948 | 20381746
MCR022577 | HPR176 | 2022-08-01 | Material | 90203208 | 44885788 | 43186163
MCR022578 | HPR176 | 2022-08-01 | Equipment | 19481358 | 9694069 | 10200579
MCR022579 | HPR176 | 2022-08-01 | Subcontract | 127883454 | 63635759 | 60913785
MCR022580 | HPR176 | 2022-08-01 | Overhead | 31016347 | 15433966 | 37220831
MCR022581 | HPR176 | 2022-09-01 | Labor | 47549412 | 25830793 | 27713411
MCR022582 | HPR176 | 2022-09-01 | Material | 115874852 | 62947978 | 65086913
MCR022583 | HPR176 | 2022-09-01 | Equipment | 25025712 | 13594995 | 14474004
MCR022584 | HPR176 | 2022-09-01 | Subcontract | 164278817 | 89243000 | 90570214
MCR022585 | HPR176 | 2022-09-01 | Overhead | 39843535 | 21644644 | 37742266
MCR022586 | HPR176 | 2022-10-01 | Labor | 55731814 | 51808717 | 60404882
MCR022587 | HPR176 | 2022-10-01 | Material | 135814837 | 126254503 | 128679967
MCR022588 | HPR176 | 2022-10-01 | Equipment | 29332189 | 27267425 | 25815766
MCR022589 | HPR176 | 2022-10-01 | Subcontract | 192548256 | 178994321 | 179671183
MCR022590 | HPR176 | 2022-10-01 | Overhead | 46699893 | 43412575 | 33456036
MCR022591 | HPR176 | 2022-11-01 | Labor | 61645189 | 47367581 | 47187267
MCR022592 | HPR176 | 2022-11-01 | Material | 150225351 | 115431741 | 107771786
MCR022593 | HPR176 | 2022-11-01 | Equipment | 32444455 | 24930013 | 26070538
MCR022594 | HPR176 | 2022-11-01 | Subcontract | 212978420 | 163650608 | 167657874
MCR022595 | HPR176 | 2022-11-01 | Overhead | 51654944 | 39691171 | 37240183
MCR022596 | HPR176 | 2022-12-01 | Labor | 65378846 | 58909462 | 67516293
MCR022597 | HPR176 | 2022-12-01 | Material | 159324032 | 143558561 | 152351993
MCR022598 | HPR176 | 2022-12-01 | Equipment | 34409514 | 31004615 | 30405839
MCR022599 | HPR176 | 2022-12-01 | Subcontract | 225877859 | 203526738 | 188102186
MCR022600 | HPR176 | 2022-12-01 | Overhead | 54783523 | 49362570 | 34144723
MCR022601 | HPR176 | 2023-01-01 | Labor | 67029616 | 45722324 | 49277438
MCR022602 | HPR176 | 2023-01-01 | Material | 163346853 | 111422355 | 98651184
MCR022603 | HPR176 | 2023-01-01 | Equipment | 35278330 | 24064098 | 25278411
MCR022604 | HPR176 | 2023-01-01 | Subcontract | 231581118 | 157966396 | 168846306
MCR022605 | HPR176 | 2023-01-01 | Overhead | 56166769 | 38312545 | 37310925
MCR022606 | HPR176 | 2023-02-01 | Labor | 66703407 | 62978320 | 65628484
MCR022607 | HPR176 | 2023-02-01 | Material | 162551903 | 153474105 | 164324792
MCR022608 | HPR176 | 2023-02-01 | Equipment | 35106644 | 33146094 | 34532060
MCR022609 | HPR176 | 2023-02-01 | Subcontract | 230454097 | 217584264 | 212815101
MCR022610 | HPR176 | 2023-02-01 | Overhead | 55893426 | 52772027 | 30736370
MCR022611 | HPR176 | 2023-03-01 | Labor | 64517293 | 47172294 | 54423800
MCR022612 | HPR176 | 2023-03-01 | Material | 157224482 | 114955839 | 103637715
MCR022613 | HPR176 | 2023-03-01 | Equipment | 33956071 | 24827231 | 24232042
MCR022614 | HPR176 | 2023-03-01 | Subcontract | 222901273 | 162975908 | 162741944
MCR022615 | HPR176 | 2023-03-01 | Overhead | 54061594 | 39527533 | 34705623
MCR022616 | HPR176 | 2023-04-01 | Labor | 60602410 | 58657227 | 57307343
MCR022617 | HPR176 | 2023-04-01 | Material | 147684166 | 142943881 | 160660969
MCR022618 | HPR176 | 2023-04-01 | Equipment | 31895630 | 30871862 | 39880233
MCR022619 | HPR176 | 2023-04-01 | Subcontract | 209375716 | 202655290 | 179336451
MCR022620 | HPR176 | 2023-04-01 | Overhead | 50781158 | 49151213 | 32705707
MCR022621 | HPR176 | 2023-05-01 | Labor | 55108148 | 48337946 | 56471902
MCR022622 | HPR176 | 2023-05-01 | Material | 134295005 | 117796458 | 121097467
MCR022623 | HPR176 | 2023-05-01 | Equipment | 29003948 | 25440725 | 19759809
MCR022624 | HPR176 | 2023-05-01 | Subcontract | 190393551 | 167003129 | 155732570
MCR022625 | HPR176 | 2023-05-01 | Overhead | 46177299 | 40504279 | 34837318
MCR022626 | HPR176 | 2023-06-01 | Labor | 48208494 | 55880651 | 61160157
MCR022627 | HPR176 | 2023-06-01 | Material | 117480992 | 136177545 | 105331588
MCR022628 | HPR176 | 2023-06-01 | Equipment | 25372593 | 29410523 | 31361201
MCR022629 | HPR176 | 2023-06-01 | Subcontract | 166555884 | 193062477 | 183196446
MCR022630 | HPR176 | 2023-06-01 | Overhead | 40395806 | 46824610 | 33925565
MCR022631 | HPR176 | 2023-07-01 | Labor | 40112288 | 28349697 | 34504291
MCR022632 | HPR176 | 2023-07-01 | Material | 97751059 | 69086384 | 84615246
MCR022633 | HPR176 | 2023-07-01 | Equipment | 21111482 | 14920718 | 16494537
MCR022634 | HPR176 | 2023-07-01 | Subcontract | 138584241 | 97945578 | 93203604
MCR022635 | HPR176 | 2023-07-01 | Overhead | 33611674 | 23755333 | 32328210
MCR022636 | HPR176 | 2023-08-01 | Labor | 31081328 | 24366574 | 27268350
MCR022637 | HPR176 | 2023-08-01 | Material | 75743191 | 59379771 | 60500251
MCR022638 | HPR176 | 2023-08-01 | Equipment | 16358401 | 12824362 | 12309160
MCR022639 | HPR176 | 2023-08-01 | Subcontract | 107383109 | 84184259 | 92527704
MCR022640 | HPR176 | 2023-08-01 | Overhead | 26044275 | 20417717 | 36669494
MCR022641 | HPR176 | 2023-09-01 | Labor | 21466713 | 37794210 | 35673369
MCR022642 | HPR176 | 2023-09-01 | Material | 52312996 | 92102053 | 89727807
MCR022643 | HPR176 | 2023-09-01 | Equipment | 11298137 | 19891455 | 24018412
MCR022644 | HPR176 | 2023-09-01 | Subcontract | 74165506 | 130575496 | 179285057
MCR022645 | HPR176 | 2023-09-01 | Overhead | 17987809 | 31669265 | 37865315
MCR022646 | HPR176 | 2023-10-01 | Labor | 11799274 | 43686028 | 55310670
MCR022647 | HPR176 | 2023-10-01 | Material | 28754071 | 106460034 | 116752471
MCR022648 | HPR176 | 2023-10-01 | Equipment | 6210071 | 22992376 | 22447195
MCR022649 | HPR176 | 2023-10-01 | Subcontract | 40765401 | 150931183 | 229905491
MCR022650 | HPR176 | 2023-10-01 | Overhead | 9887079 | 36606252 | 34689199
MCR022651 | HPR176 | 2023-11-01 | Labor | 3166558 | 20622282 | 20075368
MCR022652 | HPR176 | 2023-11-01 | Material | 7716697 | 50255172 | 46553218
MCR022653 | HPR176 | 2023-11-01 | Equipment | 1666590 | 10853705 | 10770218
MCR022654 | HPR176 | 2023-11-01 | Subcontract | 10940164 | 71248075 | 83989581
MCR022655 | HPR176 | 2023-11-01 | Overhead | 2653384 | 17280226 | 35421469
MCR022656 | HPR176 | 2023-12-01 | Labor | 0 | 18015587 | 21841600
MCR022657 | HPR176 | 2023-12-01 | Material | 0 | 43902824 | 32200175
MCR022658 | HPR176 | 2023-12-01 | Equipment | 0 | 9481776 | 10838927
MCR022659 | HPR176 | 2023-12-01 | Subcontract | 0 | 62242185 | 96899352
MCR022660 | HPR176 | 2023-12-01 | Overhead | 0 | 15095973 | 33013365
MCR022661 | HPR176 | 2024-01-01 | Labor | 0 | 34665545 | 39849834
MCR022662 | HPR176 | 2024-01-01 | Material | 0 | 84477697 | 86695066
MCR022663 | HPR176 | 2024-01-01 | Equipment | 0 | 18244809 | 19029787
MCR022664 | HPR176 | 2024-01-01 | Subcontract | 0 | 119766248 | 174672300
MCR022665 | HPR176 | 2024-01-01 | Overhead | 0 | 29047632 | 37931262
MCR022666 | HPR176 | 2024-02-01 | Labor | 0 | 17679974 | 22262249
MCR022667 | HPR176 | 2024-02-01 | Material | 0 | 43084956 | 43622025
MCR022668 | HPR176 | 2024-02-01 | Equipment | 0 | 9305140 | 9864545
MCR022669 | HPR176 | 2024-02-01 | Subcontract | 0 | 61082672 | 107905642
MCR022670 | HPR176 | 2024-02-01 | Overhead | 0 | 14814750 | 34139520
MCR022671 | HPR176 | 2024-03-01 | Labor | 0 | 4929214 | 5473977
MCR022672 | HPR176 | 2024-03-01 | Material | 0 | 12012177 | 11530126
MCR022673 | HPR176 | 2024-03-01 | Equipment | 0 | 2594293 | 2848418
MCR022674 | HPR176 | 2024-03-01 | Subcontract | 0 | 17029978 | 55305537
MCR022675 | HPR176 | 2024-03-01 | Overhead | 0 | 4130384 | 36949679
MCR022676 | HPR176 | 2024-04-01 | Labor | 0 | 2905210 | 2986497
MCR022677 | HPR176 | 2024-04-01 | Material | 0 | 7079808 | 6857554
MCR022678 | HPR176 | 2024-04-01 | Equipment | 0 | 1529040 | 1992216
MCR022679 | HPR176 | 2024-04-01 | Subcontract | 0 | 10037230 | 44281257
MCR022680 | HPR176 | 2024-04-01 | Overhead | 0 | 2434390 | 34063680
MCR022681 | HPR177 | 2018-08-01 | Labor | 2965941 | 904099 | 873651
MCR022682 | HPR177 | 2018-08-01 | Material | 6913321 | 2107367 | 2136433
MCR022683 | HPR177 | 2018-08-01 | Equipment | 2420317 | 737778 | 698945
MCR022684 | HPR177 | 2018-08-01 | Subcontract | 8769909 | 2673304 | 2512598
MCR022685 | HPR177 | 2018-08-01 | Overhead | 1928903 | 587982 | 11700514
MCR022686 | HPR177 | 2018-09-01 | Labor | 8440318 | 5219026 | 5389044
MCR022687 | HPR177 | 2018-09-01 | Material | 19673561 | 12165044 | 13561719
MCR022688 | HPR177 | 2018-09-01 | Equipment | 6887610 | 4258918 | 4701369
MCR022689 | HPR177 | 2018-09-01 | Subcontract | 24956938 | 15431992 | 18091706
MCR022690 | HPR177 | 2018-09-01 | Overhead | 5489169 | 3394199 | 11726601
MCR022691 | HPR177 | 2018-10-01 | Labor | 13239189 | 9089308 | 9911088
MCR022692 | HPR177 | 2018-10-01 | Material | 30859266 | 21186295 | 20996644
MCR022693 | HPR177 | 2018-10-01 | Equipment | 10803666 | 7417210 | 6519073
MCR022694 | HPR177 | 2018-10-01 | Subcontract | 39146588 | 26875920 | 26127232
MCR022695 | HPR177 | 2018-10-01 | Overhead | 8610120 | 5911241 | 12528992
MCR022696 | HPR177 | 2018-11-01 | Labor | 17377418 | 15668810 | 14382379
MCR022697 | HPR177 | 2018-11-01 | Material | 40505076 | 36522475 | 32569603
MCR022698 | HPR177 | 2018-11-01 | Equipment | 14180613 | 12786326 | 15729115
MCR022699 | HPR177 | 2018-11-01 | Subcontract | 51382801 | 46330665 | 46019444
MCR022700 | HPR177 | 2018-11-01 | Overhead | 11301422 | 10190227 | 12071195
MCR022701 | HPR177 | 2018-12-01 | Labor | 20870575 | 21329954 | 24614085
MCR022702 | HPR177 | 2018-12-01 | Material | 48647286 | 49718054 | 57984071
MCR022703 | HPR177 | 2018-12-01 | Equipment | 17031158 | 17406028 | 18468552
MCR022704 | HPR177 | 2018-12-01 | Subcontract | 61711619 | 63069944 | 74303413
MCR022705 | HPR177 | 2018-12-01 | Overhead | 13573200 | 13871958 | 12011505
MCR022706 | HPR177 | 2019-01-01 | Labor | 23735023 | 12073167 | 13400341
MCR022707 | HPR177 | 2019-01-01 | Material | 55324036 | 28141380 | 26854171
MCR022708 | HPR177 | 2019-01-01 | Equipment | 19368653 | 9852149 | 8612504
MCR022709 | HPR177 | 2019-01-01 | Subcontract | 70181425 | 35698808 | 36315678
MCR022710 | HPR177 | 2019-01-01 | Overhead | 15436097 | 7851796 | 11976956
MCR022711 | HPR177 | 2019-02-01 | Labor | 25988012 | 22675606 | 21600820
MCR022712 | HPR177 | 2019-02-01 | Material | 60575534 | 52854638 | 58273233
MCR022713 | HPR177 | 2019-02-01 | Equipment | 21207175 | 18504130 | 16578625
MCR022714 | HPR177 | 2019-02-01 | Subcontract | 76843224 | 67048864 | 73806316
MCR022715 | HPR177 | 2019-02-01 | Overhead | 16901330 | 14747104 | 12574140
MCR022716 | HPR177 | 2019-03-01 | Labor | 27647795 | 19989989 | 22776675
MCR022717 | HPR177 | 2019-03-01 | Material | 64444327 | 46594725 | 40463355
MCR022718 | HPR177 | 2019-03-01 | Equipment | 22561618 | 16312567 | 17871709
MCR022719 | HPR177 | 2019-03-01 | Subcontract | 81750989 | 59107838 | 60910265
MCR022720 | HPR177 | 2019-03-01 | Overhead | 17980771 | 13000510 | 12212361
MCR022721 | HPR177 | 2019-04-01 | Labor | 28733766 | 26809678 | 28126800
MCR022722 | HPR177 | 2019-04-01 | Material | 66975621 | 62490757 | 63121707
MCR022723 | HPR177 | 2019-04-01 | Equipment | 23447811 | 21877684 | 23581599
MCR022724 | HPR177 | 2019-04-01 | Subcontract | 84962068 | 79272785 | 82425126
MCR022725 | HPR177 | 2019-04-01 | Overhead | 18687034 | 17435701 | 12625016
MCR022726 | HPR177 | 2019-05-01 | Labor | 29266635 | 21587067 | 24361664
MCR022727 | HPR177 | 2019-05-01 | Material | 68217686 | 50317359 | 55224406
MCR022728 | HPR177 | 2019-05-01 | Equipment | 23882652 | 17615842 | 18235762
MCR022729 | HPR177 | 2019-05-01 | Subcontract | 86537692 | 63830194 | 71311566
MCR022730 | HPR177 | 2019-05-01 | Overhead | 19033586 | 14039171 | 12941693
MCR022731 | HPR177 | 2019-06-01 | Labor | 29268633 | 21234233 | 19098182
MCR022732 | HPR177 | 2019-06-01 | Material | 68222344 | 49494938 | 47323095
MCR022733 | HPR177 | 2019-06-01 | Equipment | 23884282 | 17327916 | 17776398
MCR022734 | HPR177 | 2019-06-01 | Subcontract | 86543601 | 62786910 | 68301533
MCR022735 | HPR177 | 2019-06-01 | Overhead | 19034885 | 13809705 | 13005729
MCR022736 | HPR177 | 2019-07-01 | Labor | 28763788 | 33122220 | 39812834
MCR022737 | HPR177 | 2019-07-01 | Material | 67045598 | 77204680 | 77734601
MCR022738 | HPR177 | 2019-07-01 | Equipment | 23472310 | 27028951 | 25239962
MCR022739 | HPR177 | 2019-07-01 | Subcontract | 85050838 | 97938163 | 115233922
MCR022740 | HPR177 | 2019-07-01 | Overhead | 18706559 | 21541069 | 13136269
MCR022741 | HPR177 | 2019-08-01 | Labor | 27778264 | 21362937 | 21686749
MCR022742 | HPR177 | 2019-08-01 | Material | 64748437 | 49794932 | 53755756
MCR022743 | HPR177 | 2019-08-01 | Equipment | 22668086 | 17432943 | 19824684
MCR022744 | HPR177 | 2019-08-01 | Subcontract | 82136769 | 63167468 | 65554484
MCR022745 | HPR177 | 2019-08-01 | Overhead | 18065622 | 13893408 | 13381657
MCR022746 | HPR177 | 2019-09-01 | Labor | 26340818 | 17213258 | 21765186
MCR022747 | HPR177 | 2019-09-01 | Material | 61397891 | 40122435 | 39219291
MCR022748 | HPR177 | 2019-09-01 | Equipment | 21495078 | 14046653 | 12688243
MCR022749 | HPR177 | 2019-09-01 | Subcontract | 77886427 | 50897401 | 53414294
MCR022750 | HPR177 | 2019-09-01 | Overhead | 17130778 | 11194660 | 11810542
MCR022751 | HPR177 | 2019-10-01 | Labor | 24483417 | 19801369 | 22709006
MCR022752 | HPR177 | 2019-10-01 | Material | 57068469 | 46155070 | 46991078
MCR022753 | HPR177 | 2019-10-01 | Equipment | 19979370 | 16158646 | 15046733
MCR022754 | HPR177 | 2019-10-01 | Subcontract | 72394329 | 58550113 | 60405883
MCR022755 | HPR177 | 2019-10-01 | Overhead | 15922815 | 12877840 | 13904987
MCR022756 | HPR177 | 2019-11-01 | Labor | 22242090 | 17729557 | 20916346
MCR022757 | HPR177 | 2019-11-01 | Material | 51844153 | 41325877 | 46613544
MCR022758 | HPR177 | 2019-11-01 | Equipment | 18150364 | 14467971 | 15255586
MCR022759 | HPR177 | 2019-11-01 | Subcontract | 65767011 | 52424030 | 58990953
MCR022760 | HPR177 | 2019-11-01 | Overhead | 14465166 | 11530436 | 10573261
MCR022761 | HPR177 | 2019-12-01 | Labor | 19658176 | 23627700 | 25978059
MCR022762 | HPR177 | 2019-12-01 | Material | 45821300 | 55073877 | 55968399
MCR022763 | HPR177 | 2019-12-01 | Equipment | 16041795 | 19281073 | 19398324
MCR022764 | HPR177 | 2019-12-01 | Subcontract | 58126708 | 69864085 | 69351932
MCR022765 | HPR177 | 2019-12-01 | Overhead | 12784715 | 15366299 | 13136827
MCR022766 | HPR177 | 2020-01-01 | Labor | 16780221 | 17440217 | 18216024
MCR022767 | HPR177 | 2020-01-01 | Material | 39113067 | 40651453 | 35426172
MCR022768 | HPR177 | 2020-01-01 | Equipment | 13693278 | 14231859 | 16003594
MCR022769 | HPR177 | 2020-01-01 | Subcontract | 49616965 | 51568488 | 60071537
MCR022770 | HPR177 | 2020-01-01 | Overhead | 10913034 | 11342263 | 12734483
MCR022771 | HPR177 | 2020-02-01 | Labor | 13667064 | 20461006 | 21451795
MCR022772 | HPR177 | 2020-02-01 | Material | 31856600 | 47692619 | 48075485
MCR022773 | HPR177 | 2020-02-01 | Equipment | 11152827 | 16696934 | 17755834
MCR022774 | HPR177 | 2020-02-01 | Subcontract | 40411758 | 60500575 | 67084609
MCR022775 | HPR177 | 2020-02-01 | Overhead | 8888389 | 13306836 | 12861904
MCR022776 | HPR177 | 2020-03-01 | Labor | 10393321 | 13512237 | 15014767
MCR022777 | HPR177 | 2020-03-01 | Material | 24225822 | 31495712 | 35982875
MCR022778 | HPR177 | 2020-03-01 | Equipment | 8481332 | 11026483 | 10765924
MCR022779 | HPR177 | 2020-03-01 | Subcontract | 30731718 | 39953954 | 78439898
MCR022780 | HPR177 | 2020-03-01 | Overhead | 6759307 | 8787697 | 12101523
MCR022781 | HPR177 | 2020-04-01 | Labor | 7060476 | 14463366 | 16727829
MCR022782 | HPR177 | 2020-04-01 | Material | 16457284 | 33712704 | 34290068
MCR022783 | HPR177 | 2020-04-01 | Equipment | 5761608 | 11802640 | 12105985
MCR022784 | HPR177 | 2020-04-01 | Subcontract | 20876923 | 42766323 | 59199797
MCR022785 | HPR177 | 2020-04-01 | Overhead | 4591788 | 9406265 | 11264148
MCR022786 | HPR177 | 2020-05-01 | Labor | 3824721 | 27596818 | 31134346
MCR022787 | HPR177 | 2020-05-01 | Material | 8915054 | 64325505 | 67138268
MCR022788 | HPR177 | 2020-05-01 | Equipment | 3121113 | 22520020 | 24717940
MCR022789 | HPR177 | 2020-05-01 | Subcontract | 11309210 | 81600257 | 114475654
MCR022790 | HPR177 | 2020-05-01 | Overhead | 2487411 | 17947619 | 12514452
MCR022791 | HPR177 | 2020-06-01 | Labor | 1014331 | 8940050 | 8432802
MCR022792 | HPR177 | 2020-06-01 | Material | 2364306 | 20838389 | 22797785
MCR022793 | HPR177 | 2020-06-01 | Equipment | 827731 | 7295410 | 7485410
MCR022794 | HPR177 | 2020-06-01 | Subcontract | 2999246 | 26434583 | 52891837
MCR022795 | HPR177 | 2020-06-01 | Overhead | 659671 | 5814171 | 11973043
MCR022796 | HPR177 | 2020-07-01 | Labor | 0 | 5956377 | 7128212
MCR022797 | HPR177 | 2020-07-01 | Material | 0 | 13883737 | 13114829
MCR022798 | HPR177 | 2020-07-01 | Equipment | 0 | 4860623 | 4845694
MCR022799 | HPR177 | 2020-07-01 | Subcontract | 0 | 17612244 | 40432012
MCR022800 | HPR177 | 2020-07-01 | Overhead | 0 | 3873736 | 11669825
MCR022801 | HPR177 | 2020-08-01 | Labor | 0 | 3629973 | 3738055
MCR022802 | HPR177 | 2020-08-01 | Material | 0 | 8461116 | 8816119
MCR022803 | HPR177 | 2020-08-01 | Equipment | 0 | 2962192 | 3137347
MCR022804 | HPR177 | 2020-08-01 | Subcontract | 0 | 10733367 | 41449255
MCR022805 | HPR177 | 2020-08-01 | Overhead | 0 | 2360757 | 12794534
MCR022806 | HPR177 | 2020-09-01 | Labor | 0 | 5441011 | 6368342
MCR022807 | HPR177 | 2020-09-01 | Material | 0 | 12682469 | 13338913
MCR022808 | HPR177 | 2020-09-01 | Equipment | 0 | 4440065 | 4934768
MCR022809 | HPR177 | 2020-09-01 | Subcontract | 0 | 16088373 | 37565775
MCR022810 | HPR177 | 2020-09-01 | Overhead | 0 | 3538567 | 12649554
MCR022811 | HPR177 | 2020-10-01 | Labor | 0 | 1968948 | 1962223
MCR022812 | HPR177 | 2020-10-01 | Material | 0 | 4589426 | 4410555
MCR022813 | HPR177 | 2020-10-01 | Equipment | 0 | 1606734 | 1605044
MCR022814 | HPR177 | 2020-10-01 | Subcontract | 0 | 5821926 | 25826091
MCR022815 | HPR177 | 2020-10-01 | Overhead | 0 | 1280507 | 10486883
MCR022816 | HPR177 | 2020-11-01 | Labor | 0 | 692008 | 790990
MCR022817 | HPR177 | 2020-11-01 | Material | 0 | 1613005 | 1616467
MCR022818 | HPR177 | 2020-11-01 | Equipment | 0 | 564704 | 786129
MCR022819 | HPR177 | 2020-11-01 | Subcontract | 0 | 2046180 | 17585964
MCR022820 | HPR177 | 2020-11-01 | Overhead | 0 | 450048 | 11397424
MCR022821 | HPR178 | 2022-01-01 | Labor | 8377681 | 4898785 | 4855463
MCR022822 | HPR178 | 2022-01-01 | Material | 15574095 | 9106833 | 9991316
MCR022823 | HPR178 | 2022-01-01 | Equipment | 2829968 | 1654802 | 1535057
MCR022824 | HPR178 | 2022-01-01 | Subcontract | 18323578 | 10714572 | 12122490
MCR022825 | HPR178 | 2022-01-01 | Overhead | 4520145 | 2643120 | 29880419
MCR022826 | HPR178 | 2022-02-01 | Labor | 23840757 | 13825738 | 15116031
MCR022827 | HPR178 | 2022-02-01 | Material | 44319928 | 25702023 | 26993828
MCR022828 | HPR178 | 2022-02-01 | Equipment | 8053371 | 4670313 | 5120440
MCR022829 | HPR178 | 2022-02-01 | Subcontract | 52144260 | 30239512 | 29780480
MCR022830 | HPR178 | 2022-02-01 | Overhead | 12863188 | 7459623 | 31282905
MCR022831 | HPR178 | 2022-03-01 | Labor | 37395785 | 19457098 | 18898546
MCR022832 | HPR178 | 2022-03-01 | Material | 69518701 | 36170713 | 36318801
MCR022833 | HPR178 | 2022-03-01 | Equipment | 12632239 | 6572578 | 5687827
MCR022834 | HPR178 | 2022-03-01 | Subcontract | 81791678 | 42556366 | 47111570
MCR022835 | HPR178 | 2022-03-01 | Overhead | 20176751 | 10498002 | 30755079
MCR022836 | HPR178 | 2022-04-01 | Labor | 49084742 | 53800553 | 57967344
MCR022837 | HPR178 | 2022-04-01 | Material | 91248453 | 100015137 | 109333221
MCR022838 | HPR178 | 2022-04-01 | Equipment | 16580751 | 18173745 | 20136269
MCR022839 | HPR178 | 2022-04-01 | Subcontract | 107357646 | 117672018 | 133420958
MCR022840 | HPR178 | 2022-04-01 | Overhead | 26483482 | 29027879 | 26062638
MCR022841 | HPR178 | 2022-05-01 | Labor | 58951611 | 38915789 | 39556668
MCR022842 | HPR178 | 2022-05-01 | Material | 109590946 | 72344386 | 72699174
MCR022843 | HPR178 | 2022-05-01 | Equipment | 19913764 | 13145694 | 12165081
MCR022844 | HPR178 | 2022-05-01 | Subcontract | 128938361 | 85116215 | 84183307
MCR022845 | HPR178 | 2022-05-01 | Overhead | 31807113 | 20996863 | 27434870
MCR022846 | HPR178 | 2022-06-01 | Labor | 67042611 | 53460378 | 58721461
MCR022847 | HPR178 | 2022-06-01 | Material | 124632101 | 99382752 | 113354841
MCR022848 | HPR178 | 2022-06-01 | Equipment | 22646892 | 18058834 | 21142187
MCR022849 | HPR178 | 2022-06-01 | Subcontract | 146634913 | 116927991 | 108380475
MCR022850 | HPR178 | 2022-06-01 | Overhead | 36172580 | 28844339 | 29013646
MCR022851 | HPR178 | 2022-07-01 | Labor | 73406466 | 38387455 | 40774707
MCR022852 | HPR178 | 2022-07-01 | Material | 136462497 | 71362214 | 67992603
MCR022853 | HPR178 | 2022-07-01 | Equipment | 24796592 | 12967224 | 11479615
MCR022854 | HPR178 | 2022-07-01 | Subcontract | 160553872 | 83960648 | 81507835
MCR022855 | HPR178 | 2022-07-01 | Overhead | 39606174 | 20711802 | 28270738
MCR022856 | HPR178 | 2022-08-01 | Labor | 78094735 | 40893184 | 47349126
MCR022857 | HPR178 | 2022-08-01 | Material | 145177981 | 76020360 | 74489624
MCR022858 | HPR178 | 2022-08-01 | Equipment | 26380282 | 13813655 | 12198234
MCR022859 | HPR178 | 2022-08-01 | Subcontract | 170808005 | 89441153 | 106610319
MCR022860 | HPR178 | 2022-08-01 | Overhead | 42135711 | 22063758 | 30316765
MCR022861 | HPR178 | 2022-09-01 | Labor | 81162201 | 96284375 | 108295478
MCR022862 | HPR178 | 2022-09-01 | Material | 150880394 | 178992491 | 206481412
MCR022863 | HPR178 | 2022-09-01 | Equipment | 27416468 | 32524715 | 35539721
MCR022864 | HPR178 | 2022-09-01 | Subcontract | 177517134 | 210592200 | 226552637
MCR022865 | HPR178 | 2022-09-01 | Overhead | 43790750 | 51949861 | 28362918
MCR022866 | HPR178 | 2022-10-01 | Labor | 82667356 | 79062604 | 67144691
MCR022867 | HPR178 | 2022-10-01 | Material | 153678475 | 146977248 | 149778789
MCR022868 | HPR178 | 2022-10-01 | Equipment | 27924907 | 26707227 | 27783305
MCR022869 | HPR178 | 2022-10-01 | Subcontract | 180809194 | 172924919 | 185229773
MCR022870 | HPR178 | 2022-10-01 | Overhead | 44602851 | 42657921 | 27552479
MCR022871 | HPR178 | 2022-11-01 | Labor | 82673001 | 103680993 | 116719980
MCR022872 | HPR178 | 2022-11-01 | Material | 153688969 | 192742791 | 221410898
MCR022873 | HPR178 | 2022-11-01 | Equipment | 27926813 | 35023281 | 37585482
MCR022874 | HPR178 | 2022-11-01 | Subcontract | 180821541 | 226770007 | 237043782
MCR022875 | HPR178 | 2022-11-01 | Overhead | 44605896 | 55940677 | 30917530
MCR022876 | HPR178 | 2022-12-01 | Labor | 81247000 | 44835156 | 45524759
MCR022877 | HPR178 | 2022-12-01 | Material | 151038037 | 83348479 | 75679852
MCR022878 | HPR178 | 2022-12-01 | Equipment | 27445113 | 15145247 | 16226434
MCR022879 | HPR178 | 2022-12-01 | Subcontract | 177702608 | 98062994 | 92206076
MCR022880 | HPR178 | 2022-12-01 | Overhead | 43836503 | 24190634 | 28827809
MCR022881 | HPR178 | 2023-01-01 | Labor | 78463261 | 128625176 | 119447799
MCR022882 | HPR178 | 2023-01-01 | Material | 145863070 | 239113985 | 250323214
MCR022883 | HPR178 | 2023-01-01 | Equipment | 26504770 | 43449388 | 43026965
MCR022884 | HPR178 | 2023-01-01 | Subcontract | 171614041 | 281327668 | 254314179
MCR022885 | HPR178 | 2023-01-01 | Overhead | 42334548 | 69399214 | 27956880
MCR022886 | HPR178 | 2023-02-01 | Labor | 74403013 | 98614810 | 113317749
MCR022887 | HPR178 | 2023-02-01 | Material | 138315075 | 183324765 | 195152479
MCR022888 | HPR178 | 2023-02-01 | Equipment | 25133224 | 33311932 | 32206582
MCR022889 | HPR178 | 2023-02-01 | Subcontract | 162733507 | 215689303 | 279350136
MCR022890 | HPR178 | 2023-02-01 | Overhead | 40143856 | 53207238 | 27244017
MCR022891 | HPR178 | 2023-03-01 | Labor | 69156545 | 81400494 | 83963889
MCR022892 | HPR178 | 2023-03-01 | Material | 128561900 | 151323381 | 147122581
MCR022893 | HPR178 | 2023-03-01 | Equipment | 23360975 | 27496963 | 27679217
MCR022894 | HPR178 | 2023-03-01 | Subcontract | 151258487 | 178038327 | 173567336
MCR022895 | HPR178 | 2023-03-01 | Overhead | 37313145 | 43919320 | 29009057
MCR022896 | HPR178 | 2023-04-01 | Labor | 62825629 | 77147970 | 84118213
MCR022897 | HPR178 | 2023-04-01 | Material | 116792738 | 143417946 | 120171502
MCR022898 | HPR178 | 2023-04-01 | Equipment | 21222402 | 26060467 | 24335537
MCR022899 | HPR178 | 2023-04-01 | Subcontract | 137411573 | 168737250 | 169342033
MCR022900 | HPR178 | 2023-04-01 | Overhead | 33897324 | 41624888 | 29701070
MCR022901 | HPR178 | 2023-05-01 | Labor | 55527033 | 35197477 | 37420666
MCR022902 | HPR178 | 2023-05-01 | Material | 103224661 | 65432051 | 74429535
MCR022903 | HPR178 | 2023-05-01 | Equipment | 18756947 | 11889654 | 12525803
MCR022904 | HPR178 | 2023-05-01 | Subcontract | 121448159 | 76983562 | 79067865
MCR022905 | HPR178 | 2023-05-01 | Overhead | 29959395 | 18990662 | 28235710
MCR022906 | HPR178 | 2023-06-01 | Labor | 47397882 | 54860631 | 64423216
MCR022907 | HPR178 | 2023-06-01 | Material | 88112582 | 101985821 | 107145010
MCR022908 | HPR178 | 2023-06-01 | Equipment | 16010932 | 18531838 | 15006644
MCR022909 | HPR178 | 2023-06-01 | Subcontract | 103668162 | 119990611 | 134542949
MCR022910 | HPR178 | 2023-06-01 | Overhead | 25573343 | 29599841 | 31785474
MCR022911 | HPR178 | 2023-07-01 | Labor | 38604371 | 23810479 | 22927033
MCR022912 | HPR178 | 2023-07-01 | Material | 71765461 | 44263640 | 39534875
MCR022913 | HPR178 | 2023-07-01 | Equipment | 13040498 | 8043143 | 11540384
MCR022914 | HPR178 | 2023-07-01 | Subcontract | 84435086 | 52078035 | 42308279
MCR022915 | HPR178 | 2023-07-01 | Overhead | 20828839 | 12846851 | 29363200
MCR022916 | HPR178 | 2023-08-01 | Labor | 29357264 | 28117312 | 30867370
MCR022917 | HPR178 | 2023-08-01 | Material | 54575105 | 52270035 | 45239647
MCR022918 | HPR178 | 2023-08-01 | Equipment | 9916839 | 9497985 | 8525484
MCR022919 | HPR178 | 2023-08-01 | Subcontract | 64209908 | 61497896 | 62994934
MCR022920 | HPR178 | 2023-08-01 | Overhead | 15839598 | 15170586 | 28424373
MCR022921 | HPR178 | 2023-09-01 | Labor | 19943218 | 45162083 | 51603075
MCR022922 | HPR178 | 2023-09-01 | Material | 37074408 | 83956235 | 85241465
MCR022923 | HPR178 | 2023-09-01 | Equipment | 6736789 | 15255683 | 16157104
MCR022924 | HPR178 | 2023-09-01 | Subcontract | 43619602 | 98778045 | 108656116
MCR022925 | HPR178 | 2023-09-01 | Overhead | 10760286 | 24367026 | 28942956
MCR022926 | HPR178 | 2023-10-01 | Labor | 10803414 | 26007420 | 31889612
MCR022927 | HPR178 | 2023-10-01 | Material | 20083529 | 48347750 | 41138232
MCR022928 | HPR178 | 2023-10-01 | Equipment | 3649377 | 8785267 | 8952224
MCR022929 | HPR178 | 2023-10-01 | Subcontract | 23629117 | 56883163 | 54601002
MCR022930 | HPR178 | 2023-10-01 | Overhead | 5828940 | 14032202 | 29571186
MCR022931 | HPR178 | 2023-11-01 | Labor | 2865107 | 14906849 | 15404433
MCR022932 | HPR178 | 2023-11-01 | Material | 5326229 | 27711807 | 29560212
MCR022933 | HPR178 | 2023-11-01 | Equipment | 967829 | 5035511 | 5207606
MCR022934 | HPR178 | 2023-11-01 | Subcontract | 6266532 | 32604108 | 34323285
MCR022935 | HPR178 | 2023-11-01 | Overhead | 1545857 | 8042933 | 28631565
MCR022936 | HPR178 | 2023-12-01 | Labor | 0 | 9600414 | 11082392
MCR022937 | HPR178 | 2023-12-01 | Material | 0 | 17847153 | 19509793
MCR022938 | HPR178 | 2023-12-01 | Equipment | 0 | 3243005 | 2749768
MCR022939 | HPR178 | 2023-12-01 | Subcontract | 0 | 20997927 | 22420024
MCR022940 | HPR178 | 2023-12-01 | Overhead | 0 | 5179866 | 29384204
MCR022941 | HPR178 | 2024-01-01 | Labor | 0 | 2337462 | 2940851
MCR022942 | HPR178 | 2024-01-01 | Material | 0 | 4345338 | 3404544
MCR022943 | HPR178 | 2024-01-01 | Equipment | 0 | 789591 | 919637
MCR022944 | HPR178 | 2024-01-01 | Subcontract | 0 | 5112473 | 5175365
MCR022945 | HPR178 | 2024-01-01 | Overhead | 0 | 1261169 | 29592487
MCR022946 | HPR179 | 2022-11-01 | Labor | 3562342 | 1661024 | 2099733
MCR022947 | HPR179 | 2022-11-01 | Material | 11889683 | 5543837 | 5107210
MCR022948 | HPR179 | 2022-11-01 | Equipment | 2954775 | 1377732 | 1538356
MCR022949 | HPR179 | 2022-11-01 | Subcontract | 10258156 | 4783101 | 3941802
MCR022950 | HPR179 | 2022-11-01 | Overhead | 2631154 | 1226836 | 9979754
MCR022951 | HPR179 | 2022-12-01 | Labor | 9770620 | 5756702 | 5974463
MCR022952 | HPR179 | 2022-12-01 | Material | 32610447 | 19213584 | 22775377
MCR022953 | HPR179 | 2022-12-01 | Equipment | 8104213 | 4774880 | 4828995
MCR022954 | HPR179 | 2022-12-01 | Subcontract | 28135575 | 16577057 | 15590980
MCR022955 | HPR179 | 2022-12-01 | Overhead | 7216603 | 4251914 | 10803972
MCR022956 | HPR179 | 2023-01-01 | Labor | 14641317 | 10946190 | 10888954
MCR022957 | HPR179 | 2023-01-01 | Material | 48866897 | 36534031 | 30574415
MCR022958 | HPR179 | 2023-01-01 | Equipment | 12144199 | 9079286 | 9129465
MCR022959 | HPR179 | 2023-01-01 | Subcontract | 42161282 | 31520757 | 31499036
MCR022960 | HPR179 | 2023-01-01 | Overhead | 10814111 | 8084881 | 10618118
MCR022961 | HPR179 | 2023-02-01 | Labor | 18226998 | 8104841 | 8723334
MCR022962 | HPR179 | 2023-02-01 | Material | 60834475 | 27050739 | 23727178
MCR022963 | HPR179 | 2023-02-01 | Equipment | 15118332 | 6722538 | 7195367
MCR022964 | HPR179 | 2023-02-01 | Subcontract | 52486645 | 23338782 | 21715916
MCR022965 | HPR179 | 2023-02-01 | Overhead | 13462503 | 5986255 | 9710207
MCR022966 | HPR179 | 2023-03-01 | Labor | 20584892 | 16003349 | 16805663
MCR022967 | HPR179 | 2023-03-01 | Material | 68704188 | 53412816 | 55094552
MCR022968 | HPR179 | 2023-03-01 | Equipment | 17074080 | 13273932 | 13342355
MCR022969 | HPR179 | 2023-03-01 | Subcontract | 59276459 | 46083401 | 42077867
MCR022970 | HPR179 | 2023-03-01 | Overhead | 15204049 | 11820110 | 9707227
MCR022971 | HPR179 | 2023-04-01 | Labor | 21777931 | 17440036 | 22394575
MCR022972 | HPR179 | 2023-04-01 | Material | 72686075 | 58207908 | 53706948
MCR022973 | HPR179 | 2023-04-01 | Equipment | 18063642 | 14465588 | 17757451
MCR022974 | HPR179 | 2023-04-01 | Subcontract | 62711944 | 50220500 | 47043931
MCR022975 | HPR179 | 2023-04-01 | Overhead | 16085230 | 12881251 | 10519686
MCR022976 | HPR179 | 2023-05-01 | Labor | 21876183 | 21819773 | 20676912
MCR022977 | HPR179 | 2023-05-01 | Material | 73014004 | 72825729 | 67119258
MCR022978 | HPR179 | 2023-05-01 | Equipment | 18145138 | 18098349 | 19089099
MCR022979 | HPR179 | 2023-05-01 | Subcontract | 62994874 | 62832434 | 60965586
MCR022980 | HPR179 | 2023-05-01 | Overhead | 16157799 | 16116135 | 9707826
MCR022981 | HPR179 | 2023-06-01 | Labor | 20958920 | 20104736 | 22283969
MCR022982 | HPR179 | 2023-06-01 | Material | 69952542 | 67101617 | 67524237
MCR022983 | HPR179 | 2023-06-01 | Equipment | 17384316 | 16675816 | 13880927
MCR022984 | HPR179 | 2023-06-01 | Subcontract | 60353512 | 57893796 | 56119995
MCR022985 | HPR179 | 2023-06-01 | Overhead | 15480306 | 14849404 | 10445053
MCR022986 | HPR179 | 2023-07-01 | Labor | 19117708 | 17291283 | 18938291
MCR022987 | HPR179 | 2023-07-01 | Material | 63807309 | 57711431 | 50911397
MCR022988 | HPR179 | 2023-07-01 | Equipment | 15857128 | 14342206 | 16719298
MCR022989 | HPR179 | 2023-07-01 | Subcontract | 55051540 | 49792151 | 48209323
MCR022990 | HPR179 | 2023-07-01 | Overhead | 14120383 | 12771382 | 10354195
MCR022991 | HPR179 | 2023-08-01 | Labor | 16461394 | 19081183 | 21553090
MCR022992 | HPR179 | 2023-08-01 | Material | 54941589 | 63685403 | 60331887
MCR022993 | HPR179 | 2023-08-01 | Equipment | 13653856 | 15826833 | 15381812
MCR022994 | HPR179 | 2023-08-01 | Subcontract | 47402392 | 54946362 | 52047456
MCR022995 | HPR179 | 2023-08-01 | Overhead | 12158423 | 14093406 | 10655277
MCR022996 | HPR179 | 2023-09-01 | Labor | 13124815 | 16845386 | 19189909
MCR022997 | HPR179 | 2023-09-01 | Material | 43805416 | 56223204 | 45097641
MCR022998 | HPR179 | 2023-09-01 | Equipment | 10886340 | 13972358 | 13574078
MCR022999 | HPR179 | 2023-09-01 | Subcontract | 37794347 | 48508141 | 44975006
MCR023000 | HPR179 | 2023-09-01 | Overhead | 9694019 | 12442041 | 9170113
MCR023001 | HPR179 | 2023-10-01 | Labor | 9286140 | 9697247 | 10473950
MCR023002 | HPR179 | 2023-10-01 | Material | 30993444 | 32365557 | 34445866
MCR023003 | HPR179 | 2023-10-01 | Equipment | 7702362 | 8043354 | 8824746
MCR023004 | HPR179 | 2023-10-01 | Subcontract | 26740461 | 27924289 | 27249116
MCR023005 | HPR179 | 2023-10-01 | Overhead | 6858764 | 7162409 | 9743541
MCR023006 | HPR179 | 2023-11-01 | Labor | 5209567 | 14825111 | 16761225
MCR023007 | HPR179 | 2023-11-01 | Material | 17387464 | 49480327 | 45226399
MCR023008 | HPR179 | 2023-11-01 | Equipment | 4321060 | 12296646 | 10964624
MCR023009 | HPR179 | 2023-11-01 | Subcontract | 15001521 | 42690536 | 43286389
MCR023010 | HPR179 | 2023-11-01 | Overhead | 3847798 | 10949861 | 10022516
MCR023011 | HPR179 | 2023-12-01 | Labor | 1420828 | 7541558 | 6796492
MCR023012 | HPR179 | 2023-12-01 | Material | 4742160 | 25170723 | 25431689
MCR023013 | HPR179 | 2023-12-01 | Equipment | 1178502 | 6255324 | 7410404
MCR023014 | HPR179 | 2023-12-01 | Subcontract | 4091431 | 21716745 | 15151925
MCR023015 | HPR179 | 2023-12-01 | Overhead | 1049427 | 5570212 | 10738341
MCR023016 | HPR179 | 2024-01-01 | Labor | 0 | 3599683 | 4544601
MCR023017 | HPR179 | 2024-01-01 | Material | 0 | 12014312 | 9510902
MCR023018 | HPR179 | 2024-01-01 | Equipment | 0 | 2985747 | 2697931
MCR023019 | HPR179 | 2024-01-01 | Subcontract | 0 | 10365684 | 10560952
MCR023020 | HPR179 | 2024-01-01 | Overhead | 0 | 2658734 | 9224265
MCR023021 | HPR179 | 2024-02-01 | Labor | 0 | 3960474 | 4438316
MCR023022 | HPR179 | 2024-02-01 | Material | 0 | 13218487 | 13493060
MCR023023 | HPR179 | 2024-02-01 | Equipment | 0 | 3285004 | 3691091
MCR023024 | HPR179 | 2024-02-01 | Subcontract | 0 | 11404620 | 10472213
MCR023025 | HPR179 | 2024-02-01 | Overhead | 0 | 2925215 | 9290877
MCR023026 | HPR179 | 2024-03-01 | Labor | 0 | 1341078 | 1299179
MCR023027 | HPR179 | 2024-03-01 | Material | 0 | 4475986 | 4838854
MCR023028 | HPR179 | 2024-03-01 | Equipment | 0 | 1112353 | 1061836
MCR023029 | HPR179 | 2024-03-01 | Subcontract | 0 | 3861782 | 3646275
MCR023030 | HPR179 | 2024-03-01 | Overhead | 0 | 990523 | 10223979
MCR023031 | HPR180 | 2018-11-01 | Labor | 1181400 | 531309 | 533120
MCR023032 | HPR180 | 2018-11-01 | Material | 5267148 | 2368784 | 2167744
MCR023033 | HPR180 | 2018-11-01 | Equipment | 2364613 | 1063433 | 1117784
MCR023034 | HPR180 | 2018-11-01 | Subcontract | 2751765 | 1237546 | 1433469
MCR023035 | HPR180 | 2018-11-01 | Overhead | 1066924 | 479826 | 4911988
MCR023036 | HPR180 | 2018-12-01 | Labor | 3295609 | 2500187 | 2369768
MCR023037 | HPR180 | 2018-12-01 | Material | 14693130 | 11146820 | 10117044
MCR023038 | HPR180 | 2018-12-01 | Equipment | 6596278 | 5004211 | 5085628
MCR023039 | HPR180 | 2018-12-01 | Subcontract | 7676270 | 5823538 | 5437162
MCR023040 | HPR180 | 2018-12-01 | Overhead | 2976271 | 2257923 | 5087309
MCR023041 | HPR180 | 2019-01-01 | Labor | 5045037 | 2276197 | 2521461
MCR023042 | HPR180 | 2019-01-01 | Material | 22492767 | 10148186 | 10279534
MCR023043 | HPR180 | 2019-01-01 | Equipment | 10097818 | 4555888 | 4802795
MCR023044 | HPR180 | 2019-01-01 | Subcontract | 11751107 | 5301812 | 6605390
MCR023045 | HPR180 | 2019-01-01 | Overhead | 4556181 | 2055637 | 4905848
MCR023046 | HPR180 | 2019-02-01 | Labor | 6441039 | 2698473 | 2900362
MCR023047 | HPR180 | 2019-02-01 | Material | 28716699 | 12030857 | 13534125
MCR023048 | HPR180 | 2019-02-01 | Equipment | 12891966 | 5401087 | 5696630
MCR023049 | HPR180 | 2019-02-01 | Subcontract | 15002734 | 6285394 | 6383585
MCR023050 | HPR180 | 2019-02-01 | Overhead | 5816914 | 2436995 | 4626111
MCR023051 | HPR180 | 2019-03-01 | Labor | 7495759 | 9321865 | 8512165
MCR023052 | HPR180 | 2019-03-01 | Material | 33419058 | 41560561 | 45883521
MCR023053 | HPR180 | 2019-03-01 | Equipment | 15003025 | 18658041 | 20056325
MCR023054 | HPR180 | 2019-03-01 | Subcontract | 17459432 | 21712873 | 26081631
MCR023055 | HPR180 | 2019-03-01 | Overhead | 6769433 | 8418592 | 5189835
MCR023056 | HPR180 | 2019-04-01 | Labor | 8222255 | 3352944 | 3719717
MCR023057 | HPR180 | 2019-04-01 | Material | 36658061 | 14948752 | 13662349
MCR023058 | HPR180 | 2019-04-01 | Equipment | 16457131 | 6711036 | 6788727
MCR023059 | HPR180 | 2019-04-01 | Subcontract | 19151615 | 7809817 | 7239314
MCR023060 | HPR180 | 2019-04-01 | Overhead | 7425532 | 3028050 | 5345210
MCR023061 | HPR180 | 2019-05-01 | Labor | 8634670 | 4514009 | 4779680
MCR023062 | HPR180 | 2019-05-01 | Material | 38496771 | 20125237 | 20361228
MCR023063 | HPR180 | 2019-05-01 | Equipment | 17282594 | 9034948 | 11314070
MCR023064 | HPR180 | 2019-05-01 | Subcontract | 20112229 | 10514216 | 12022124
MCR023065 | HPR180 | 2019-05-01 | Overhead | 7797985 | 4076609 | 5035830
MCR023066 | HPR180 | 2019-06-01 | Labor | 8748458 | 7203872 | 6718738
MCR023067 | HPR180 | 2019-06-01 | Material | 39004084 | 32117708 | 33334210
MCR023068 | HPR180 | 2019-06-01 | Equipment | 17510346 | 14418802 | 13560968
MCR023069 | HPR180 | 2019-06-01 | Subcontract | 20377270 | 16779555 | 17832144
MCR023070 | HPR180 | 2019-06-01 | Overhead | 7900747 | 6505829 | 5379259
MCR023071 | HPR180 | 2019-07-01 | Labor | 8580681 | 2774353 | 3238756
MCR023072 | HPR180 | 2019-07-01 | Material | 38256069 | 12369163 | 10953695
MCR023073 | HPR180 | 2019-07-01 | Equipment | 17174535 | 5552965 | 6129189
MCR023074 | HPR180 | 2019-07-01 | Subcontract | 19986477 | 6462138 | 7931470
MCR023075 | HPR180 | 2019-07-01 | Overhead | 7749228 | 2505523 | 5234498
MCR023076 | HPR180 | 2019-08-01 | Labor | 8150424 | 3669036 | 4072153
MCR023077 | HPR180 | 2019-08-01 | Material | 36337810 | 16358012 | 17885170
MCR023078 | HPR180 | 2019-08-01 | Equipment | 16313359 | 7343704 | 7345197
MCR023079 | HPR180 | 2019-08-01 | Subcontract | 18984303 | 8546070 | 8156444
MCR023080 | HPR180 | 2019-08-01 | Overhead | 7360661 | 3313512 | 4936675
MCR023081 | HPR180 | 2019-09-01 | Labor | 7479391 | 4040628 | 3669274
MCR023082 | HPR180 | 2019-09-01 | Material | 33346080 | 18014718 | 18163924
MCR023083 | HPR180 | 2019-09-01 | Equipment | 14970263 | 8087459 | 8880126
MCR023084 | HPR180 | 2019-09-01 | Subcontract | 17421305 | 9411598 | 12237436
MCR023085 | HPR180 | 2019-09-01 | Overhead | 6754650 | 3649098 | 4665555
MCR023086 | HPR180 | 2019-10-01 | Labor | 6592813 | 9653858 | 10491190
MCR023087 | HPR180 | 2019-10-01 | Material | 29393367 | 43040714 | 49747992
MCR023088 | HPR180 | 2019-10-01 | Equipment | 13195747 | 19322535 | 21299682
MCR023089 | HPR180 | 2019-10-01 | Subcontract | 15356252 | 22486164 | 24237853
MCR023090 | HPR180 | 2019-10-01 | Overhead | 5953981 | 8718415 | 4515351
MCR023091 | HPR180 | 2019-11-01 | Labor | 5520909 | 6945742 | 7150359
MCR023092 | HPR180 | 2019-11-01 | Material | 24614396 | 30966864 | 28306875
MCR023093 | HPR180 | 2019-11-01 | Equipment | 11050294 | 13902146 | 12241869
MCR023094 | HPR180 | 2019-11-01 | Subcontract | 12859530 | 16178309 | 18866827
MCR023095 | HPR180 | 2019-11-01 | Overhead | 4985943 | 6272711 | 4526630
MCR023096 | HPR180 | 2019-12-01 | Labor | 4301457 | 7025917 | 7118182
MCR023097 | HPR180 | 2019-12-01 | Material | 19177595 | 31324317 | 34329747
MCR023098 | HPR180 | 2019-12-01 | Equipment | 8609517 | 14062620 | 17566884
MCR023099 | HPR180 | 2019-12-01 | Subcontract | 10019131 | 16365057 | 21682563
MCR023100 | HPR180 | 2019-12-01 | Overhead | 3884653 | 6345118 | 4965855
MCR023101 | HPR180 | 2020-01-01 | Labor | 2984950 | 4467812 | 4678143
MCR023102 | HPR180 | 2020-01-01 | Material | 13308088 | 19919270 | 18150605
MCR023103 | HPR180 | 2020-01-01 | Equipment | 5974483 | 8942482 | 7515283
MCR023104 | HPR180 | 2020-01-01 | Subcontract | 6952669 | 10406611 | 9409448
MCR023105 | HPR180 | 2020-01-01 | Overhead | 2695714 | 4034888 | 5052324
MCR023106 | HPR180 | 2020-02-01 | Labor | 1647403 | 3631257 | 3102695
MCR023107 | HPR180 | 2020-02-01 | Material | 7344776 | 16189579 | 16254976
MCR023108 | HPR180 | 2020-02-01 | Equipment | 3297336 | 7268088 | 8380892
MCR023109 | HPR180 | 2020-02-01 | Subcontract | 3837200 | 8458074 | 8124341
MCR023110 | HPR180 | 2020-02-01 | Overhead | 1487773 | 3279394 | 5289067
MCR023111 | HPR180 | 2020-03-01 | Labor | 443560 | 4927227 | 5207355
MCR023112 | HPR180 | 2020-03-01 | Material | 1977567 | 21967526 | 22889962
MCR023113 | HPR180 | 2020-03-01 | Equipment | 887801 | 9862018 | 10147780
MCR023114 | HPR180 | 2020-03-01 | Subcontract | 1033159 | 11476701 | 14348135
MCR023115 | HPR180 | 2020-03-01 | Overhead | 400580 | 4449787 | 5031882
MCR023116 | HPR180 | 2020-04-01 | Labor | 0 | 3803125 | 3553342
MCR023117 | HPR180 | 2020-04-01 | Material | 0 | 16955832 | 15691128
MCR023118 | HPR180 | 2020-04-01 | Equipment | 0 | 7612087 | 8379659
MCR023119 | HPR180 | 2020-04-01 | Subcontract | 0 | 8858395 | 10217972
MCR023120 | HPR180 | 2020-04-01 | Overhead | 0 | 3434608 | 5152891
MCR023121 | HPR180 | 2020-05-01 | Labor | 0 | 3712520 | 3791482
MCR023122 | HPR180 | 2020-05-01 | Material | 0 | 16551880 | 19698034
MCR023123 | HPR180 | 2020-05-01 | Equipment | 0 | 7430738 | 8674781
MCR023124 | HPR180 | 2020-05-01 | Subcontract | 0 | 8647354 | 8716402
MCR023125 | HPR180 | 2020-05-01 | Overhead | 0 | 3352783 | 4760730
MCR023126 | HPR180 | 2020-06-01 | Labor | 0 | 3702362 | 4688598
MCR023127 | HPR180 | 2020-06-01 | Material | 0 | 16506593 | 13298625
MCR023128 | HPR180 | 2020-06-01 | Equipment | 0 | 7410407 | 7844762
MCR023129 | HPR180 | 2020-06-01 | Subcontract | 0 | 8623694 | 10190550
MCR023130 | HPR180 | 2020-06-01 | Overhead | 0 | 3343609 | 4586013
MCR023131 | HPR180 | 2020-07-01 | Labor | 0 | 1434517 | 989671
MCR023132 | HPR180 | 2020-07-01 | Material | 0 | 6395643 | 8783732
MCR023133 | HPR180 | 2020-07-01 | Equipment | 0 | 2871236 | 3670113
MCR023134 | HPR180 | 2020-07-01 | Subcontract | 0 | 3341336 | 3243870
MCR023135 | HPR180 | 2020-07-01 | Overhead | 0 | 1295515 | 5608367
MCR023136 | HPR180 | 2020-08-01 | Labor | 0 | 1966582 | 2093974
MCR023137 | HPR180 | 2020-08-01 | Material | 0 | 8767801 | 9355405
MCR023138 | HPR180 | 2020-08-01 | Equipment | 0 | 3936183 | 5215850
MCR023139 | HPR180 | 2020-08-01 | Subcontract | 0 | 4580644 | 5476314
MCR023140 | HPR180 | 2020-08-01 | Overhead | 0 | 1776024 | 5057499
MCR023141 | HPR180 | 2020-09-01 | Labor | 0 | 416894 | 552184
MCR023142 | HPR180 | 2020-09-01 | Material | 0 | 1858677 | 1408500
MCR023143 | HPR180 | 2020-09-01 | Equipment | 0 | 834428 | 715528
MCR023144 | HPR180 | 2020-09-01 | Subcontract | 0 | 971046 | 924761
MCR023145 | HPR180 | 2020-09-01 | Overhead | 0 | 376497 | 5120192
MCR023146 | HPR180 | 2020-10-01 | Labor | 0 | 195131 | 192565
MCR023147 | HPR180 | 2020-10-01 | Material | 0 | 869971 | 782168
MCR023148 | HPR180 | 2020-10-01 | Equipment | 0 | 390561 | 597835
MCR023149 | HPR180 | 2020-10-01 | Subcontract | 0 | 454507 | 489392
MCR023150 | HPR180 | 2020-10-01 | Overhead | 0 | 176223 | 4617121
MCR023151 | HPR181 | 2020-03-01 | Labor | 10541535 | 8299341 | 8859054
MCR023152 | HPR181 | 2020-03-01 | Material | 20980416 | 16517862 | 17407106
MCR023153 | HPR181 | 2020-03-01 | Equipment | 4617284 | 3635183 | 3695998
MCR023154 | HPR181 | 2020-03-01 | Subcontract | 23335021 | 18371640 | 19477899
MCR023155 | HPR181 | 2020-03-01 | Overhead | 6204430 | 4884742 | 26820865
MCR023156 | HPR181 | 2020-04-01 | Labor | 29263161 | 24480059 | 25790899
MCR023157 | HPR181 | 2020-04-01 | Material | 58241353 | 48721727 | 52307251
MCR023158 | HPR181 | 2020-04-01 | Equipment | 12817518 | 10722478 | 10698131
MCR023159 | HPR181 | 2020-04-01 | Subcontract | 64777705 | 54189704 | 51646344
MCR023160 | HPR181 | 2020-04-01 | Overhead | 17223413 | 14408224 | 28248653
MCR023161 | HPR181 | 2020-05-01 | Labor | 44524891 | 45511015 | 48732435
MCR023162 | HPR181 | 2020-05-01 | Material | 88616193 | 90578837 | 101197053
MCR023163 | HPR181 | 2020-05-01 | Equipment | 19502288 | 19934218 | 19413579
MCR023164 | HPR181 | 2020-05-01 | Subcontract | 98561474 | 100744382 | 95452498
MCR023165 | HPR181 | 2020-05-01 | Overhead | 26206007 | 26786410 | 27393585
MCR023166 | HPR181 | 2020-06-01 | Labor | 56442468 | 47545025 | 52281397
MCR023167 | HPR181 | 2020-06-01 | Material | 112335291 | 94627049 | 82807206
MCR023168 | HPR181 | 2020-06-01 | Equipment | 24722289 | 20825132 | 24529379
MCR023169 | HPR181 | 2020-06-01 | Subcontract | 124942535 | 105246921 | 109294000
MCR023170 | HPR181 | 2020-06-01 | Overhead | 33220333 | 27983567 | 26998149
MCR023171 | HPR181 | 2020-07-01 | Labor | 65140256 | 64131177 | 64578098
MCR023172 | HPR181 | 2020-07-01 | Material | 129646167 | 127637835 | 146316537
MCR023173 | HPR181 | 2020-07-01 | Equipment | 28531996 | 28090010 | 27589285
MCR023174 | HPR181 | 2020-07-01 | Subcontract | 144196189 | 141962464 | 156948251
MCR023175 | HPR181 | 2020-07-01 | Overhead | 38339589 | 37745675 | 25508148
MCR023176 | HPR181 | 2020-08-01 | Labor | 70752834 | 43478817 | 43856376
MCR023177 | HPR181 | 2020-08-01 | Material | 140816666 | 86534232 | 73595875
MCR023178 | HPR181 | 2020-08-01 | Equipment | 30990353 | 19044098 | 15937683
MCR023179 | HPR181 | 2020-08-01 | Subcontract | 156620339 | 96245857 | 88718709
MCR023180 | HPR181 | 2020-08-01 | Overhead | 41642983 | 25590320 | 28001358
MCR023181 | HPR181 | 2020-09-01 | Labor | 73427068 | 81500004 | 83123224
MCR023182 | HPR181 | 2020-09-01 | Material | 146139092 | 162206349 | 185975617
MCR023183 | HPR181 | 2020-09-01 | Equipment | 32161691 | 35697707 | 34023529
MCR023184 | HPR181 | 2020-09-01 | Subcontract | 162540093 | 180410558 | 190544318
MCR023185 | HPR181 | 2020-09-01 | Overhead | 43216956 | 47968443 | 29319476
MCR023186 | HPR181 | 2020-10-01 | Labor | 73324899 | 98912111 | 107051445
MCR023187 | HPR181 | 2020-10-01 | Material | 145935750 | 196861002 | 211421081
MCR023188 | HPR181 | 2020-10-01 | Equipment | 32116940 | 43324361 | 41879696
MCR023189 | HPR181 | 2020-10-01 | Subcontract | 162313931 | 218954458 | 178811682
MCR023190 | HPR181 | 2020-10-01 | Overhead | 43156823 | 58216683 | 27704310
MCR023191 | HPR181 | 2020-11-01 | Labor | 70627207 | 78869409 | 91836303
MCR023192 | HPR181 | 2020-11-01 | Material | 140566635 | 156970777 | 148948613
MCR023193 | HPR181 | 2020-11-01 | Equipment | 30935328 | 34545484 | 38436854
MCR023194 | HPR181 | 2020-11-01 | Subcontract | 156342247 | 174587404 | 183873374
MCR023195 | HPR181 | 2020-11-01 | Overhead | 41569042 | 46420154 | 28588878
MCR023196 | HPR181 | 2020-12-01 | Labor | 65539357 | 60848640 | 71025524
MCR023197 | HPR181 | 2020-12-01 | Material | 130440482 | 121104726 | 126428047
MCR023198 | HPR181 | 2020-12-01 | Equipment | 28706805 | 26652231 | 25508068
MCR023199 | HPR181 | 2020-12-01 | Subcontract | 145079649 | 134696153 | 148666911
MCR023200 | HPR181 | 2020-12-01 | Overhead | 38574488 | 35813673 | 28054411
MCR023201 | HPR181 | 2021-01-01 | Labor | 58299605 | 47371307 | 47783533
MCR023202 | HPR181 | 2021-01-01 | Material | 116031480 | 94281305 | 91246237
MCR023203 | HPR181 | 2021-01-01 | Equipment | 25535731 | 20749042 | 20739867
MCR023204 | HPR181 | 2021-01-01 | Subcontract | 129053543 | 104862374 | 88155513
MCR023205 | HPR181 | 2021-01-01 | Overhead | 34313388 | 27881322 | 27415988
MCR023206 | HPR181 | 2021-02-01 | Labor | 49192619 | 43663574 | 53213786
MCR023207 | HPR181 | 2021-02-01 | Material | 97906192 | 86901946 | 91726520
MCR023208 | HPR181 | 2021-02-01 | Equipment | 21546793 | 19125023 | 16408769
MCR023209 | HPR181 | 2021-02-01 | Subcontract | 108894078 | 96654839 | 97020363
MCR023210 | HPR181 | 2021-02-01 | Overhead | 28953291 | 25699062 | 27637729
MCR023211 | HPR181 | 2021-03-01 | Labor | 38573265 | 50650356 | 60372214
MCR023212 | HPR181 | 2021-03-01 | Material | 76770898 | 100807471 | 99349736
MCR023213 | HPR181 | 2021-03-01 | Equipment | 16895424 | 22185294 | 22155884
MCR023214 | HPR181 | 2021-03-01 | Subcontract | 85386797 | 112120963 | 115469629
MCR023215 | HPR181 | 2021-03-01 | Overhead | 22703060 | 29811271 | 27363292
MCR023216 | HPR181 | 2021-04-01 | Labor | 26914175 | 33922083 | 34630870
MCR023217 | HPR181 | 2021-04-01 | Material | 53566256 | 67513827 | 80586612
MCR023218 | HPR181 | 2021-04-01 | Equipment | 11788642 | 14858166 | 16246694
MCR023219 | HPR181 | 2021-04-01 | Subcontract | 59577928 | 75090817 | 80480832
MCR023220 | HPR181 | 2021-04-01 | Overhead | 15840871 | 19965514 | 30169243
MCR023221 | HPR181 | 2021-05-01 | Labor | 14923535 | 16228941 | 16258985
MCR023222 | HPR181 | 2021-05-01 | Material | 29701742 | 32299843 | 38474021
MCR023223 | HPR181 | 2021-05-01 | Equipment | 6536637 | 7108417 | 7462681
MCR023224 | HPR181 | 2021-05-01 | Subcontract | 33035130 | 35924812 | 34882039
MCR023225 | HPR181 | 2021-05-01 | Overhead | 8783542 | 9551865 | 29384889
MCR023226 | HPR181 | 2021-06-01 | Labor | 4033072 | 6108089 | 8351919
MCR023227 | HPR181 | 2021-06-01 | Material | 8026869 | 12156696 | 13369560
MCR023228 | HPR181 | 2021-06-01 | Equipment | 1766520 | 2675396 | 2728207
MCR023229 | HPR181 | 2021-06-01 | Subcontract | 8927714 | 13521026 | 9748814
MCR023230 | HPR181 | 2021-06-01 | Overhead | 2373744 | 3595037 | 26723743
MCR023231 | HPR182 | 2018-05-01 | Labor | 3758594 | 2865709 | 2797920
MCR023232 | HPR182 | 2018-05-01 | Material | 10414910 | 7940762 | 8004371
MCR023233 | HPR182 | 2018-05-01 | Equipment | 2525607 | 1925628 | 1910198
MCR023234 | HPR182 | 2018-05-01 | Subcontract | 10676954 | 8140556 | 7503904
MCR023235 | HPR182 | 2018-05-01 | Overhead | 2264360 | 1726442 | 14801422
MCR023236 | HPR182 | 2018-06-01 | Labor | 10720702 | 8030932 | 7855404
MCR023237 | HPR182 | 2018-06-01 | Material | 29706624 | 22253383 | 22309508
MCR023238 | HPR182 | 2018-06-01 | Equipment | 7203831 | 5396426 | 5704397
MCR023239 | HPR182 | 2018-06-01 | Subcontract | 30454058 | 22813289 | 22910156
MCR023240 | HPR182 | 2018-06-01 | Overhead | 6458672 | 4838223 | 13588661
MCR023241 | HPR182 | 2018-07-01 | Labor | 16862659 | 7347734 | 7684036
MCR023242 | HPR182 | 2018-07-01 | Material | 46725736 | 20360269 | 21503413
MCR023243 | HPR182 | 2018-07-01 | Equipment | 11330950 | 4937347 | 4903880
MCR023244 | HPR182 | 2018-07-01 | Subcontract | 47901379 | 20872543 | 19886303
MCR023245 | HPR182 | 2018-07-01 | Overhead | 10158885 | 4426632 | 14508846
MCR023246 | HPR182 | 2018-08-01 | Labor | 22201669 | 14645600 | 15106103
MCR023247 | HPR182 | 2018-08-01 | Material | 61519913 | 40582356 | 40290149
MCR023248 | HPR182 | 2018-08-01 | Equipment | 14918525 | 9841186 | 10305469
MCR023249 | HPR182 | 2018-08-01 | Subcontract | 63067785 | 41603428 | 44161000
MCR023250 | HPR182 | 2018-08-01 | Overhead | 13375364 | 8823221 | 15058625
MCR023251 | HPR182 | 2018-09-01 | Labor | 26755715 | 22777702 | 22179481
MCR023252 | HPR182 | 2018-09-01 | Material | 74138987 | 63116076 | 66398289
MCR023253 | HPR182 | 2018-09-01 | Equipment | 17978640 | 15305594 | 16530253
MCR023254 | HPR182 | 2018-09-01 | Subcontract | 76004361 | 64704108 | 62893872
MCR023255 | HPR182 | 2018-09-01 | Overhead | 16118942 | 13722394 | 13946569
MCR023256 | HPR182 | 2018-10-01 | Labor | 30543648 | 18488339 | 16347348
MCR023257 | HPR182 | 2018-10-01 | Material | 84635194 | 51230428 | 54075307
MCR023258 | HPR182 | 2018-10-01 | Equipment | 20523961 | 12423334 | 12845551
MCR023259 | HPR182 | 2018-10-01 | Subcontract | 86764658 | 52519412 | 53051785
MCR023260 | HPR182 | 2018-10-01 | Overhead | 18400977 | 11138274 | 15774553
MCR023261 | HPR182 | 2018-11-01 | Labor | 33585285 | 38421523 | 39457791
MCR023262 | HPR182 | 2018-11-01 | Material | 93063446 | 106464462 | 117527341
MCR023263 | HPR182 | 2018-11-01 | Equipment | 22567805 | 25817539 | 24655653
MCR023264 | HPR182 | 2018-11-01 | Subcontract | 95404969 | 109143161 | 108309626
MCR023265 | HPR182 | 2018-11-01 | Overhead | 20233407 | 23146992 | 14298420
MCR023266 | HPR182 | 2018-12-01 | Labor | 35901529 | 21459888 | 24456781
MCR023267 | HPR182 | 2018-12-01 | Material | 99481662 | 59464469 | 48711088
MCR023268 | HPR182 | 2018-12-01 | Equipment | 24124217 | 14420082 | 13650618
MCR023269 | HPR182 | 2018-12-01 | Subcontract | 101984671 | 60960625 | 65748591
MCR023270 | HPR182 | 2018-12-01 | Overhead | 21628825 | 12928479 | 15828728
MCR023271 | HPR182 | 2019-01-01 | Labor | 37514507 | 29273072 | 26616972
MCR023272 | HPR182 | 2019-01-01 | Material | 103951159 | 81114481 | 94166601
MCR023273 | HPR182 | 2019-01-01 | Equipment | 25208066 | 19670191 | 22972773
MCR023274 | HPR182 | 2019-01-01 | Subcontract | 106566622 | 83155362 | 74218392
MCR023275 | HPR182 | 2019-01-01 | Overhead | 22600561 | 17635521 | 15386598
MCR023276 | HPR182 | 2019-02-01 | Labor | 38447746 | 28485822 | 33751241
MCR023277 | HPR182 | 2019-02-01 | Material | 106537125 | 78933043 | 80366324
MCR023278 | HPR182 | 2019-02-01 | Equipment | 25835160 | 19141194 | 20983958
MCR023279 | HPR182 | 2019-02-01 | Subcontract | 109217652 | 80919038 | 75621619
MCR023280 | HPR182 | 2019-02-01 | Overhead | 23162790 | 17161243 | 15835263
MCR023281 | HPR182 | 2019-03-01 | Labor | 38726378 | 18665553 | 15230922
MCR023282 | HPR182 | 2019-03-01 | Material | 107309203 | 51721481 | 52962023
MCR023283 | HPR182 | 2019-03-01 | Equipment | 26022388 | 12542414 | 11685670
MCR023284 | HPR182 | 2019-03-01 | Subcontract | 110009156 | 53022819 | 60986369
MCR023285 | HPR182 | 2019-03-01 | Overhead | 23330651 | 11245036 | 16245843
MCR023286 | HPR182 | 2019-04-01 | Labor | 38377405 | 49014782 | 55902306
MCR023287 | HPR182 | 2019-04-01 | Material | 106342214 | 135817949 | 145173455
MCR023288 | HPR182 | 2019-04-01 | Equipment | 25787895 | 32935735 | 32361806
MCR023289 | HPR182 | 2019-04-01 | Subcontract | 109017838 | 139235197 | 133232620
MCR023290 | HPR182 | 2019-04-01 | Overhead | 23120413 | 29528886 | 15652581
MCR023291 | HPR182 | 2019-05-01 | Labor | 37430029 | 32162440 | 26536297
MCR023292 | HPR182 | 2019-05-01 | Material | 103717073 | 89120800 | 87362208
MCR023293 | HPR182 | 2019-05-01 | Equipment | 25151300 | 21611717 | 23058638
MCR023294 | HPR182 | 2019-05-01 | Subcontract | 106326647 | 91363124 | 95646147
MCR023295 | HPR182 | 2019-05-01 | Overhead | 22549668 | 19376216 | 14749116
MCR023296 | HPR182 | 2019-06-01 | Labor | 35916074 | 54339321 | 54073041
MCR023297 | HPR182 | 2019-06-01 | Material | 99521965 | 150572028 | 142092882
MCR023298 | HPR182 | 2019-06-01 | Equipment | 24133990 | 36513586 | 34565132
MCR023299 | HPR182 | 2019-06-01 | Subcontract | 102025988 | 154360496 | 135521710
MCR023300 | HPR182 | 2019-06-01 | Overhead | 21637587 | 32736647 | 14830603
MCR023301 | HPR182 | 2019-07-01 | Labor | 33870550 | 29248993 | 33767908
MCR023302 | HPR182 | 2019-07-01 | Material | 93853902 | 81047759 | 84326965
MCR023303 | HPR182 | 2019-07-01 | Equipment | 22759490 | 19654011 | 20957159
MCR023304 | HPR182 | 2019-07-01 | Subcontract | 96215314 | 83086962 | 101562934
MCR023305 | HPR182 | 2019-07-01 | Overhead | 20405264 | 17621014 | 14871730
MCR023306 | HPR182 | 2019-08-01 | Labor | 31332410 | 23223963 | 19492515
MCR023307 | HPR182 | 2019-08-01 | Material | 86820821 | 64352648 | 73434894
MCR023308 | HPR182 | 2019-08-01 | Equipment | 21053974 | 15605461 | 15570674
MCR023309 | HPR182 | 2019-08-01 | Subcontract | 89005277 | 65971793 | 59972971
MCR023310 | HPR182 | 2019-08-01 | Overhead | 18876166 | 13991243 | 14589627
MCR023311 | HPR182 | 2019-09-01 | Labor | 28345610 | 34787382 | 36131745
MCR023312 | HPR182 | 2019-09-01 | Material | 78544522 | 96394406 | 96022705
MCR023313 | HPR182 | 2019-09-01 | Equipment | 19046978 | 23375560 | 26702490
MCR023314 | HPR182 | 2019-09-01 | Subcontract | 80520741 | 98819738 | 102231593
MCR023315 | HPR182 | 2019-09-01 | Overhead | 17076772 | 20957609 | 13519262
MCR023316 | HPR182 | 2019-10-01 | Labor | 24960647 | 27431259 | 29322278
MCR023317 | HPR182 | 2019-10-01 | Material | 69164927 | 76010892 | 71313574
MCR023318 | HPR182 | 2019-10-01 | Equipment | 16772435 | 18432575 | 17630384
MCR023319 | HPR182 | 2019-10-01 | Subcontract | 70905151 | 77923364 | 71477816
MCR023320 | HPR182 | 2019-10-01 | Overhead | 15037506 | 16525923 | 15894682
MCR023321 | HPR182 | 2019-11-01 | Labor | 21236905 | 21536780 | 19576324
MCR023322 | HPR182 | 2019-11-01 | Material | 58846591 | 59677534 | 64350430
MCR023323 | HPR182 | 2019-11-01 | Equipment | 14270247 | 14471750 | 13368063
MCR023324 | HPR182 | 2019-11-01 | Subcontract | 60327201 | 61179051 | 59236765
MCR023325 | HPR182 | 2019-11-01 | Overhead | 12794143 | 12974803 | 15216293
MCR023326 | HPR182 | 2019-12-01 | Labor | 17246483 | 24910721 | 23180405
MCR023327 | HPR182 | 2019-12-01 | Material | 47789295 | 69026585 | 68512550
MCR023328 | HPR182 | 2019-12-01 | Equipment | 11588862 | 16738887 | 17360580
MCR023329 | HPR182 | 2019-12-01 | Subcontract | 48991698 | 70763329 | 76633773
MCR023330 | HPR182 | 2019-12-01 | Overhead | 10390119 | 15007428 | 14142147
MCR023331 | HPR182 | 2020-01-01 | Labor | 13080990 | 20848813 | 17870830
MCR023332 | HPR182 | 2020-01-01 | Material | 36246887 | 57771205 | 46625265
MCR023333 | HPR182 | 2020-01-01 | Equipment | 8789839 | 14009467 | 16011751
MCR023334 | HPR182 | 2020-01-01 | Subcontract | 37158877 | 59224758 | 51457782
MCR023335 | HPR182 | 2020-01-01 | Overhead | 7880624 | 12560338 | 15940702
MCR023336 | HPR182 | 2020-02-01 | Labor | 8865325 | 20625090 | 20873890
MCR023337 | HPR182 | 2020-02-01 | Material | 24565451 | 57151276 | 61317860
MCR023338 | HPR182 | 2020-02-01 | Equipment | 5957100 | 13859135 | 13527492
MCR023339 | HPR182 | 2020-02-01 | Subcontract | 25183530 | 58589231 | 55153521
MCR023340 | HPR182 | 2020-02-01 | Overhead | 5340902 | 12425556 | 14717886
MCR023341 | HPR182 | 2020-03-01 | Labor | 4792275 | 7621562 | 6407224
MCR023342 | HPR182 | 2020-03-01 | Material | 13279196 | 21119036 | 24294438
MCR023343 | HPR182 | 2020-03-01 | Equipment | 3220193 | 5121348 | 4763550
MCR023344 | HPR182 | 2020-03-01 | Subcontract | 13613307 | 21650402 | 27836124
MCR023345 | HPR182 | 2020-03-01 | Overhead | 2887099 | 4591599 | 14975212
MCR023346 | HPR182 | 2020-04-01 | Labor | 1268708 | 13798491 | 12151374
MCR023347 | HPR182 | 2020-04-01 | Material | 3515536 | 38235051 | 32139611
MCR023348 | HPR182 | 2020-04-01 | Equipment | 852515 | 9271967 | 10662310
MCR023349 | HPR182 | 2020-04-01 | Subcontract | 3603989 | 39197064 | 39418055
MCR023350 | HPR182 | 2020-04-01 | Overhead | 764331 | 8312881 | 14164656
MCR023351 | HPR182 | 2020-05-01 | Labor | 0 | 9555696 | 10304348
MCR023352 | HPR182 | 2020-05-01 | Material | 0 | 26478441 | 31060728
MCR023353 | HPR182 | 2020-05-01 | Equipment | 0 | 6420999 | 6237264
MCR023354 | HPR182 | 2020-05-01 | Subcontract | 0 | 27144652 | 27713900
MCR023355 | HPR182 | 2020-05-01 | Overhead | 0 | 5756815 | 14847615
MCR023356 | HPR182 | 2020-06-01 | Labor | 0 | 9629169 | 7594836
MCR023357 | HPR182 | 2020-06-01 | Material | 0 | 26682031 | 27842866
MCR023358 | HPR182 | 2020-06-01 | Equipment | 0 | 6470369 | 6897294
MCR023359 | HPR182 | 2020-06-01 | Subcontract | 0 | 27353365 | 24965865
MCR023360 | HPR182 | 2020-06-01 | Overhead | 0 | 5801079 | 15625511
MCR023361 | HPR182 | 2020-07-01 | Labor | 0 | 2128851 | 2509585
MCR023362 | HPR182 | 2020-07-01 | Material | 0 | 5898958 | 4704246
MCR023363 | HPR182 | 2020-07-01 | Equipment | 0 | 1430492 | 1506811
MCR023364 | HPR182 | 2020-07-01 | Subcontract | 0 | 6047379 | 6524234
MCR023365 | HPR182 | 2020-07-01 | Overhead | 0 | 1282523 | 14678578
MCR023366 | HPR182 | 2020-08-01 | Labor | 0 | 416653 | 344200
MCR023367 | HPR182 | 2020-08-01 | Material | 0 | 1154529 | 1205164
MCR023368 | HPR182 | 2020-08-01 | Equipment | 0 | 279972 | 347725
MCR023369 | HPR182 | 2020-08-01 | Subcontract | 0 | 1183578 | 987731
MCR023370 | HPR182 | 2020-08-01 | Overhead | 0 | 251012 | 14037169
MCR023371 | HPR183 | 2020-11-01 | Labor | 1286680 | 687122 | 760888
MCR023372 | HPR183 | 2020-11-01 | Material | 3746678 | 2000828 | 1953754
MCR023373 | HPR183 | 2020-11-01 | Equipment | 1004441 | 536399 | 530822
MCR023374 | HPR183 | 2020-11-01 | Subcontract | 3334980 | 1780970 | 1848399
MCR023375 | HPR183 | 2020-11-01 | Overhead | 797829 | 426063 | 5321684
MCR023376 | HPR183 | 2020-12-01 | Labor | 3677784 | 2545945 | 2401708
MCR023377 | HPR183 | 2020-12-01 | Material | 10709320 | 7413525 | 8122444
MCR023378 | HPR183 | 2020-12-01 | Equipment | 2871044 | 1987480 | 1949258
MCR023379 | HPR183 | 2020-12-01 | Subcontract | 9532543 | 6598901 | 6709806
MCR023380 | HPR183 | 2020-12-01 | Overhead | 2280476 | 1578659 | 5184598
MCR023381 | HPR183 | 2021-01-01 | Labor | 5799421 | 3082459 | 3335162
MCR023382 | HPR183 | 2021-01-01 | Material | 16887307 | 8975798 | 7777750
MCR023383 | HPR183 | 2021-01-01 | Equipment | 4527291 | 2406307 | 2760525
MCR023384 | HPR183 | 2021-01-01 | Subcontract | 15031672 | 7989507 | 7712564
MCR023385 | HPR183 | 2021-01-01 | Overhead | 3596036 | 1911334 | 5825831
MCR023386 | HPR183 | 2021-02-01 | Labor | 7656994 | 6580968 | 7938810
MCR023387 | HPR183 | 2021-02-01 | Material | 22296363 | 19163088 | 20390827
MCR023388 | HPR183 | 2021-02-01 | Equipment | 5977396 | 5137401 | 4772494
MCR023389 | HPR183 | 2021-02-01 | Subcontract | 19846362 | 17057382 | 18699596
MCR023390 | HPR183 | 2021-02-01 | Overhead | 4747857 | 4080648 | 5645841
MCR023391 | HPR183 | 2021-03-01 | Labor | 9256135 | 7727111 | 7429002
MCR023392 | HPR183 | 2021-03-01 | Material | 26952894 | 22500539 | 24624492
MCR023393 | HPR183 | 2021-03-01 | Equipment | 7225758 | 6032133 | 6555111
MCR023394 | HPR183 | 2021-03-01 | Subcontract | 23991218 | 20028102 | 20135657
MCR023395 | HPR183 | 2021-03-01 | Overhead | 5739434 | 4791335 | 5594179
MCR023396 | HPR183 | 2021-04-01 | Labor | 10602737 | 6360458 | 6825093
MCR023397 | HPR183 | 2021-04-01 | Material | 30874059 | 18520988 | 17715962
MCR023398 | HPR183 | 2021-04-01 | Equipment | 8276976 | 4965262 | 5084306
MCR023399 | HPR183 | 2021-04-01 | Subcontract | 27481511 | 16485838 | 19758573
MCR023400 | HPR183 | 2021-04-01 | Overhead | 6574419 | 3943917 | 5577442
MCR023401 | HPR183 | 2021-05-01 | Labor | 11702980 | 10108392 | 12372600
MCR023402 | HPR183 | 2021-05-01 | Material | 34077850 | 29434578 | 35197973
MCR023403 | HPR183 | 2021-05-01 | Equipment | 9135875 | 7891068 | 9248287
MCR023404 | HPR183 | 2021-05-01 | Subcontract | 30333258 | 26200205 | 26741696
MCR023405 | HPR183 | 2021-05-01 | Overhead | 7256644 | 6267891 | 5492463
MCR023406 | HPR183 | 2021-06-01 | Labor | 12563360 | 9641427 | 10664204
MCR023407 | HPR183 | 2021-06-01 | Material | 36583188 | 28074826 | 24402997
MCR023408 | HPR183 | 2021-06-01 | Equipment | 9807527 | 7526534 | 7383294
MCR023409 | HPR183 | 2021-06-01 | Subcontract | 32563302 | 24989867 | 27142774
MCR023410 | HPR183 | 2021-06-01 | Overhead | 7790138 | 5978341 | 5273405
MCR023411 | HPR183 | 2021-07-01 | Labor | 13190736 | 8039707 | 7720775
MCR023412 | HPR183 | 2021-07-01 | Material | 38410042 | 23410783 | 26142537
MCR023413 | HPR183 | 2021-07-01 | Equipment | 10297286 | 6276159 | 6094027
MCR023414 | HPR183 | 2021-07-01 | Subcontract | 34189414 | 20838326 | 22450985
MCR023415 | HPR183 | 2021-07-01 | Overhead | 8179154 | 4985165 | 5450754
MCR023416 | HPR183 | 2021-08-01 | Labor | 13592371 | 6872422 | 6696440
MCR023417 | HPR183 | 2021-08-01 | Material | 39579559 | 20011773 | 17517327
MCR023418 | HPR183 | 2021-08-01 | Equipment | 10610820 | 5364924 | 5455723
MCR023419 | HPR183 | 2021-08-01 | Subcontract | 35230421 | 17812810 | 17757493
MCR023420 | HPR183 | 2021-08-01 | Overhead | 8428195 | 4261369 | 5123277
MCR023421 | HPR183 | 2021-09-01 | Labor | 13775989 | 10932817 | 11491945
MCR023422 | HPR183 | 2021-09-01 | Material | 40114237 | 31835216 | 38986264
MCR023423 | HPR183 | 2021-09-01 | Equipment | 10754160 | 8534651 | 8429273
MCR023424 | HPR183 | 2021-09-01 | Subcontract | 35706347 | 28337053 | 30830345
MCR023425 | HPR183 | 2021-09-01 | Overhead | 8542051 | 6779090 | 5555730
MCR023426 | HPR183 | 2021-10-01 | Labor | 13749850 | 5372730 | 6225313
MCR023427 | HPR183 | 2021-10-01 | Material | 40038123 | 15644827 | 14952714
MCR023428 | HPR183 | 2021-10-01 | Equipment | 10733755 | 4194196 | 3899552
MCR023429 | HPR183 | 2021-10-01 | Subcontract | 35638596 | 13925720 | 12896296
MCR023430 | HPR183 | 2021-10-01 | Overhead | 8525843 | 3331458 | 5378413
MCR023431 | HPR183 | 2021-11-01 | Labor | 13522832 | 10975740 | 11269416
MCR023432 | HPR183 | 2021-11-01 | Material | 39377070 | 31960205 | 30347871
MCR023433 | HPR183 | 2021-11-01 | Equipment | 10556534 | 8568159 | 10717515
MCR023434 | HPR183 | 2021-11-01 | Subcontract | 35050182 | 28448308 | 30566357
MCR023435 | HPR183 | 2021-11-01 | Overhead | 8385076 | 6805706 | 4659970
MCR023436 | HPR183 | 2021-12-01 | Labor | 13104542 | 14536551 | 16243051
MCR023437 | HPR183 | 2021-12-01 | Material | 38159053 | 42328913 | 46723668
MCR023438 | HPR183 | 2021-12-01 | Equipment | 10229998 | 11347889 | 11700542
MCR023439 | HPR183 | 2021-12-01 | Subcontract | 33966005 | 37677666 | 40001232
MCR023440 | HPR183 | 2021-12-01 | Overhead | 8125708 | 9013651 | 5217917
MCR023441 | HPR183 | 2022-01-01 | Labor | 12505460 | 11406139 | 10483412
MCR023442 | HPR183 | 2022-01-01 | Material | 36414588 | 33213482 | 31927234
MCR023443 | HPR183 | 2022-01-01 | Equipment | 9762328 | 8904148 | 9589545
MCR023444 | HPR183 | 2022-01-01 | Subcontract | 32413228 | 29563870 | 34945430
MCR023445 | HPR183 | 2022-01-01 | Overhead | 7754236 | 7072583 | 5624470
MCR023446 | HPR183 | 2022-02-01 | Labor | 11737123 | 9969603 | 11828438
MCR023447 | HPR183 | 2022-02-01 | Material | 34177272 | 29030439 | 27853766
MCR023448 | HPR183 | 2022-02-01 | Equipment | 9162529 | 7782723 | 7553683
MCR023449 | HPR183 | 2022-02-01 | Subcontract | 30421756 | 25840474 | 22684080
MCR023450 | HPR183 | 2022-02-01 | Overhead | 7277815 | 6181832 | 5040247
MCR023451 | HPR183 | 2022-03-01 | Labor | 10812382 | 15609931 | 16670887
MCR023452 | HPR183 | 2022-03-01 | Material | 31484523 | 45454483 | 52440837
MCR023453 | HPR183 | 2022-03-01 | Equipment | 8440634 | 12185818 | 12580909
MCR023454 | HPR183 | 2022-03-01 | Subcontract | 28024895 | 40459787 | 42248048
MCR023455 | HPR183 | 2022-03-01 | Overhead | 6704413 | 9679220 | 5461482
MCR023456 | HPR183 | 2022-04-01 | Labor | 9745751 | 8961625 | 10255196
MCR023457 | HPR183 | 2022-04-01 | Material | 28378606 | 26095313 | 27914804
MCR023458 | HPR183 | 2022-04-01 | Equipment | 7607974 | 6995850 | 8428453
MCR023459 | HPR183 | 2022-04-01 | Subcontract | 25260267 | 23227870 | 23515242
MCR023460 | HPR183 | 2022-04-01 | Overhead | 6043029 | 5556817 | 5352090
MCR023461 | HPR183 | 2022-05-01 | Labor | 8553927 | 7049780 | 7067031
MCR023462 | HPR183 | 2022-05-01 | Material | 24908140 | 20528221 | 22709130
MCR023463 | HPR183 | 2022-05-01 | Equipment | 6677583 | 5503377 | 4603883
MCR023464 | HPR183 | 2022-05-01 | Subcontract | 22171147 | 18272510 | 20179731
MCR023465 | HPR183 | 2022-05-01 | Overhead | 5304017 | 4371344 | 5454321
MCR023466 | HPR183 | 2022-06-01 | Labor | 7256572 | 9593297 | 10972882
MCR023467 | HPR183 | 2022-06-01 | Material | 21130377 | 27934676 | 29456029
MCR023468 | HPR183 | 2022-06-01 | Equipment | 5664808 | 7488962 | 6500683
MCR023469 | HPR183 | 2022-06-01 | Subcontract | 18808498 | 24865118 | 23965028
MCR023470 | HPR183 | 2022-06-01 | Overhead | 4499568 | 5948497 | 5129623
MCR023471 | HPR183 | 2022-07-01 | Labor | 5877594 | 3629852 | 4353137
MCR023472 | HPR183 | 2022-07-01 | Material | 17114939 | 10569749 | 10238473
MCR023473 | HPR183 | 2022-07-01 | Equipment | 4588316 | 2833627 | 3784286
MCR023474 | HPR183 | 2022-07-01 | Subcontract | 15234290 | 9408308 | 12003589
MCR023475 | HPR183 | 2022-07-01 | Overhead | 3644509 | 2250755 | 5622521
MCR023476 | HPR183 | 2022-08-01 | Labor | 4447433 | 6692107 | 7290957
MCR023477 | HPR183 | 2022-08-01 | Material | 12950458 | 19486715 | 20076876
MCR023478 | HPR183 | 2022-08-01 | Equipment | 3471867 | 5224162 | 4631082
MCR023479 | HPR183 | 2022-08-01 | Subcontract | 11527417 | 17345448 | 24899228
MCR023480 | HPR183 | 2022-08-01 | Overhead | 2757711 | 4149562 | 5542234
MCR023481 | HPR183 | 2022-09-01 | Labor | 3007677 | 7483440 | 7804407
MCR023482 | HPR183 | 2022-09-01 | Material | 8758041 | 21790993 | 25699222
MCR023483 | HPR183 | 2022-09-01 | Equipment | 2347929 | 5841912 | 6447825
MCR023484 | HPR183 | 2022-09-01 | Subcontract | 7795677 | 19396524 | 32780347
MCR023485 | HPR183 | 2022-09-01 | Overhead | 1864965 | 4640242 | 5434974
MCR023486 | HPR183 | 2022-10-01 | Labor | 1622705 | 6672656 | 7789799
MCR023487 | HPR183 | 2022-10-01 | Material | 4725148 | 19430074 | 20151294
MCR023488 | HPR183 | 2022-10-01 | Equipment | 1266757 | 5208977 | 6309506
MCR023489 | HPR183 | 2022-10-01 | Subcontract | 4205932 | 17295031 | 23487722
MCR023490 | HPR183 | 2022-10-01 | Overhead | 1006188 | 4137501 | 5310164
MCR023491 | HPR183 | 2022-11-01 | Labor | 428907 | 4221514 | 4626314
MCR023492 | HPR183 | 2022-11-01 | Material | 1248932 | 12292607 | 11835899
MCR023493 | HPR183 | 2022-11-01 | Equipment | 334824 | 3295505 | 2814661
MCR023494 | HPR183 | 2022-11-01 | Subcontract | 1111695 | 10941853 | 21622931
MCR023495 | HPR183 | 2022-11-01 | Overhead | 265952 | 2617626 | 5505856
MCR023496 | HPR183 | 2022-12-01 | Labor | 0 | 4833282 | 4665342
MCR023497 | HPR183 | 2022-12-01 | Material | 0 | 14074012 | 17229195
MCR023498 | HPR183 | 2022-12-01 | Equipment | 0 | 3773079 | 3691274
MCR023499 | HPR183 | 2022-12-01 | Subcontract | 0 | 12527511 | 20855096
MCR023500 | HPR183 | 2022-12-01 | Overhead | 0 | 2996964 | 5497849
MCR023501 | HPR183 | 2023-01-01 | Labor | 0 | 7952644 | 7943460
MCR023502 | HPR183 | 2023-01-01 | Material | 0 | 23157267 | 19144417
MCR023503 | HPR183 | 2023-01-01 | Equipment | 0 | 6208194 | 7273046
MCR023504 | HPR183 | 2023-01-01 | Subcontract | 0 | 20612667 | 30901956
MCR023505 | HPR183 | 2023-01-01 | Overhead | 0 | 4931181 | 6113383
MCR023506 | HPR183 | 2023-02-01 | Labor | 0 | 4481518 | 5420672
MCR023507 | HPR183 | 2023-02-01 | Material | 0 | 13049711 | 14706798
MCR023508 | HPR183 | 2023-02-01 | Equipment | 0 | 3498476 | 3739761
MCR023509 | HPR183 | 2023-02-01 | Subcontract | 0 | 11615764 | 26936624
MCR023510 | HPR183 | 2023-02-01 | Overhead | 0 | 2778846 | 5088256
MCR023511 | HPR183 | 2023-03-01 | Labor | 0 | 3610434 | 3885169
MCR023512 | HPR183 | 2023-03-01 | Material | 0 | 10513205 | 10664765
MCR023513 | HPR183 | 2023-03-01 | Equipment | 0 | 2818468 | 3746681
MCR023514 | HPR183 | 2023-03-01 | Subcontract | 0 | 9357977 | 14001291
MCR023515 | HPR183 | 2023-03-01 | Overhead | 0 | 2238715 | 5311813
MCR023516 | HPR183 | 2023-04-01 | Labor | 0 | 2508816 | 3068572
MCR023517 | HPR183 | 2023-04-01 | Material | 0 | 7305410 | 9047448
MCR023518 | HPR183 | 2023-04-01 | Equipment | 0 | 1958495 | 1772432
MCR023519 | HPR183 | 2023-04-01 | Subcontract | 0 | 6502666 | 17691379
MCR023520 | HPR183 | 2023-04-01 | Overhead | 0 | 1555637 | 5523240
MCR023521 | HPR183 | 2023-05-01 | Labor | 0 | 1134505 | 1228341
MCR023522 | HPR183 | 2023-05-01 | Material | 0 | 3303560 | 2793963
MCR023523 | HPR183 | 2023-05-01 | Equipment | 0 | 885646 | 907146
MCR023524 | HPR183 | 2023-05-01 | Subcontract | 0 | 2940554 | 16430996
MCR023525 | HPR183 | 2023-05-01 | Overhead | 0 | 703470 | 4996614
MCR023526 | HPR183 | 2023-06-01 | Labor | 0 | 202949 | 250839
MCR023527 | HPR183 | 2023-06-01 | Material | 0 | 590965 | 636482
MCR023528 | HPR183 | 2023-06-01 | Equipment | 0 | 158431 | 217887
MCR023529 | HPR183 | 2023-06-01 | Subcontract | 0 | 526028 | 10164611
MCR023530 | HPR183 | 2023-06-01 | Overhead | 0 | 125842 | 5535196
MCR023531 | HPR184 | 2018-07-01 | Labor | 2005442 | 401657 | 384984
MCR023532 | HPR184 | 2018-07-01 | Material | 7829576 | 1568134 | 1560111
MCR023533 | HPR184 | 2018-07-01 | Equipment | 4572036 | 915703 | 1049574
MCR023534 | HPR184 | 2018-07-01 | Subcontract | 4226390 | 846475 | 793104
MCR023535 | HPR184 | 2018-07-01 | Overhead | 2070008 | 414588 | 12809726
MCR023536 | HPR184 | 2018-08-01 | Labor | 5692576 | 1477352 | 1372605
MCR023537 | HPR184 | 2018-08-01 | Material | 22224755 | 5767825 | 6118821
MCR023538 | HPR184 | 2018-08-01 | Equipment | 12978019 | 3368088 | 3509248
MCR023539 | HPR184 | 2018-08-01 | Subcontract | 11996880 | 3113461 | 3222918
MCR023540 | HPR184 | 2018-08-01 | Overhead | 5875851 | 1524916 | 12856204
MCR023541 | HPR184 | 2018-09-01 | Labor | 8902068 | 5001044 | 4725090
MCR023542 | HPR184 | 2018-09-01 | Material | 34755138 | 19524900 | 21313016
MCR023543 | HPR184 | 2018-09-01 | Equipment | 20295065 | 11401454 | 11704588
MCR023544 | HPR184 | 2018-09-01 | Subcontract | 18760756 | 10539503 | 11240930
MCR023545 | HPR184 | 2018-09-01 | Overhead | 9188673 | 5162054 | 12892567
MCR023546 | HPR184 | 2018-10-01 | Labor | 11644965 | 6926095 | 7303499
MCR023547 | HPR184 | 2018-10-01 | Material | 45463860 | 27040615 | 27009841
MCR023548 | HPR184 | 2018-10-01 | Equipment | 26548362 | 15790213 | 15126728
MCR023549 | HPR184 | 2018-10-01 | Subcontract | 24541304 | 14596472 | 12087643
MCR023550 | HPR184 | 2018-10-01 | Overhead | 12019878 | 7149083 | 12482461
MCR023551 | HPR184 | 2018-11-01 | Labor | 13932873 | 5227464 | 5167377
MCR023552 | HPR184 | 2018-11-01 | Material | 54396228 | 20408879 | 19856569
MCR023553 | HPR184 | 2018-11-01 | Equipment | 31764367 | 11917649 | 15809970
MCR023554 | HPR184 | 2018-11-01 | Subcontract | 29362979 | 11016674 | 11896841
MCR023555 | HPR184 | 2018-11-01 | Overhead | 14381446 | 5395764 | 12546148
MCR023556 | HPR184 | 2018-12-01 | Labor | 15778020 | 7661953 | 7991860
MCR023557 | HPR184 | 2018-12-01 | Material | 61599984 | 29913526 | 30180014
MCR023558 | HPR184 | 2018-12-01 | Equipment | 35970960 | 17467833 | 16460510
MCR023559 | HPR184 | 2018-12-01 | Subcontract | 33251553 | 16147264 | 16463287
MCR023560 | HPR184 | 2018-12-01 | Overhead | 16285997 | 7908632 | 12529921
MCR023561 | HPR184 | 2019-01-01 | Labor | 17193338 | 16101397 | 16225922
MCR023562 | HPR184 | 2019-01-01 | Material | 67125621 | 62862503 | 66238487
MCR023563 | HPR184 | 2019-01-01 | Equipment | 39197624 | 36708200 | 34432626
MCR023564 | HPR184 | 2019-01-01 | Subcontract | 36234281 | 33933058 | 34663899
MCR023565 | HPR184 | 2019-01-01 | Overhead | 17746883 | 16619786 | 12606460
MCR023566 | HPR184 | 2019-02-01 | Labor | 18192563 | 9761812 | 9867524
MCR023567 | HPR184 | 2019-02-01 | Material | 71026760 | 38111720 | 36513085
MCR023568 | HPR184 | 2019-02-01 | Equipment | 41475672 | 22255122 | 24792140
MCR023569 | HPR184 | 2019-02-01 | Subcontract | 38340108 | 20572633 | 19209289
MCR023570 | HPR184 | 2019-02-01 | Overhead | 18778278 | 10076096 | 11937366
MCR023571 | HPR184 | 2019-03-01 | Labor | 18790349 | 7542642 | 8141664
MCR023572 | HPR184 | 2019-03-01 | Material | 73360616 | 29447714 | 25953455
MCR023573 | HPR184 | 2019-03-01 | Equipment | 42838514 | 17195825 | 18310311
MCR023574 | HPR184 | 2019-03-01 | Subcontract | 39599919 | 15895819 | 16476458
MCR023575 | HPR184 | 2019-03-01 | Overhead | 19395310 | 7785479 | 13166932
MCR023576 | HPR184 | 2019-04-01 | Labor | 19002421 | 12521167 | 12032321
MCR023577 | HPR184 | 2019-04-01 | Material | 74188576 | 48884696 | 51137257
MCR023578 | HPR184 | 2019-04-01 | Equipment | 43321997 | 28545940 | 29905685
MCR023579 | HPR184 | 2019-04-01 | Subcontract | 40046850 | 26387865 | 22261149
MCR023580 | HPR184 | 2019-04-01 | Overhead | 19614209 | 12924289 | 13347015
MCR023581 | HPR184 | 2019-05-01 | Labor | 18845756 | 11356917 | 11388760
MCR023582 | HPR184 | 2019-05-01 | Material | 73576933 | 44339274 | 53073708
MCR023583 | HPR184 | 2019-05-01 | Equipment | 42964831 | 25891666 | 32725826
MCR023584 | HPR184 | 2019-05-01 | Subcontract | 39716687 | 23934254 | 24063543
MCR023585 | HPR184 | 2019-05-01 | Overhead | 19452501 | 11722556 | 13234534
MCR023586 | HPR184 | 2019-06-01 | Labor | 18338832 | 14876607 | 15376105
MCR023587 | HPR184 | 2019-06-01 | Material | 71597817 | 58080723 | 54017214
MCR023588 | HPR184 | 2019-06-01 | Equipment | 41809137 | 33915907 | 29881616
MCR023589 | HPR184 | 2019-06-01 | Subcontract | 38648364 | 31351862 | 30854411
MCR023590 | HPR184 | 2019-06-01 | Overhead | 18929256 | 15355564 | 11855995
MCR023591 | HPR184 | 2019-07-01 | Labor | 17501935 | 6204284 | 5729739
MCR023592 | HPR184 | 2019-07-01 | Material | 68330436 | 24222547 | 25750247
MCR023593 | HPR184 | 2019-07-01 | Equipment | 39901169 | 14144618 | 14220630
MCR023594 | HPR184 | 2019-07-01 | Subcontract | 36884637 | 13075284 | 13497368
MCR023595 | HPR184 | 2019-07-01 | Overhead | 18065415 | 6404033 | 12852300
MCR023596 | HPR184 | 2019-08-01 | Labor | 16357595 | 14113973 | 14366661
MCR023597 | HPR184 | 2019-08-01 | Material | 63862740 | 55103272 | 51650583
MCR023598 | HPR184 | 2019-08-01 | Equipment | 37292283 | 32177242 | 35919557
MCR023599 | HPR184 | 2019-08-01 | Subcontract | 34472984 | 29744640 | 28197395
MCR023600 | HPR184 | 2019-08-01 | Overhead | 16884232 | 14568376 | 12657781
MCR023601 | HPR184 | 2019-09-01 | Labor | 14931172 | 14727700 | 16185812
MCR023602 | HPR184 | 2019-09-01 | Material | 58293753 | 57499362 | 58305472
MCR023603 | HPR184 | 2019-09-01 | Equipment | 34040305 | 33576425 | 35778363
MCR023604 | HPR184 | 2019-09-01 | Subcontract | 31466855 | 31038045 | 32585966
MCR023605 | HPR184 | 2019-09-01 | Overhead | 15411885 | 15201862 | 12352296
MCR023606 | HPR184 | 2019-10-01 | Labor | 13251730 | 21010942 | 19465801
MCR023607 | HPR184 | 2019-10-01 | Material | 51736935 | 82030176 | 86077220
MCR023608 | HPR184 | 2019-10-01 | Equipment | 30211489 | 47901054 | 50206265
MCR023609 | HPR184 | 2019-10-01 | Subcontract | 27927498 | 44279731 | 38287349
MCR023610 | HPR184 | 2019-10-01 | Overhead | 13678374 | 21687396 | 12342854
MCR023611 | HPR184 | 2019-11-01 | Labor | 11353346 | 15925589 | 16796196
MCR023612 | HPR184 | 2019-11-01 | Material | 44325330 | 62176120 | 63558698
MCR023613 | HPR184 | 2019-11-01 | Equipment | 25883524 | 36307391 | 38269382
MCR023614 | HPR184 | 2019-11-01 | Subcontract | 23926728 | 33562550 | 36898740
MCR023615 | HPR184 | 2019-11-01 | Overhead | 11718870 | 16438318 | 12076294
MCR023616 | HPR184 | 2019-12-01 | Labor | 9277248 | 8224027 | 8004062
MCR023617 | HPR184 | 2019-12-01 | Material | 36219904 | 32107955 | 30409487
MCR023618 | HPR184 | 2019-12-01 | Equipment | 21150407 | 18749257 | 20312920
MCR023619 | HPR184 | 2019-12-01 | Subcontract | 19551434 | 17331812 | 15719178
MCR023620 | HPR184 | 2019-12-01 | Overhead | 9575932 | 8488802 | 13092361
MCR023621 | HPR184 | 2020-01-01 | Labor | 7075614 | 15964132 | 16236391
MCR023622 | HPR184 | 2020-01-01 | Material | 27624361 | 62326598 | 62506115
MCR023623 | HPR184 | 2020-01-01 | Equipment | 16131088 | 36395262 | 37037589
MCR023624 | HPR184 | 2020-01-01 | Subcontract | 14911577 | 33643777 | 34320514
MCR023625 | HPR184 | 2020-01-01 | Overhead | 7303415 | 16478102 | 12127951
MCR023626 | HPR184 | 2020-02-01 | Labor | 4819230 | 11180378 | 11915320
MCR023627 | HPR184 | 2020-02-01 | Material | 18815067 | 43650034 | 50969578
MCR023628 | HPR184 | 2020-02-01 | Equipment | 10986951 | 25489189 | 26205662
MCR023629 | HPR184 | 2020-02-01 | Subcontract | 10156337 | 23562204 | 21931863
MCR023630 | HPR184 | 2020-02-01 | Overhead | 4974386 | 11540333 | 12561673
MCR023631 | HPR184 | 2020-03-01 | Labor | 2616703 | 8512973 | 7981550
MCR023632 | HPR184 | 2020-03-01 | Material | 10216038 | 33236048 | 36128163
MCR023633 | HPR184 | 2020-03-01 | Equipment | 5965597 | 19408001 | 19157253
MCR023634 | HPR184 | 2020-03-01 | Subcontract | 5514598 | 17940754 | 30832127
MCR023635 | HPR184 | 2020-03-01 | Overhead | 2700948 | 8787051 | 12488227
MCR023636 | HPR184 | 2020-04-01 | Labor | 695292 | 17467879 | 13642155
MCR023637 | HPR184 | 2020-04-01 | Material | 2714533 | 68197475 | 64625710
MCR023638 | HPR184 | 2020-04-01 | Equipment | 1585136 | 39823527 | 42302785
MCR023639 | HPR184 | 2020-04-01 | Subcontract | 1465300 | 36812866 | 53043950
MCR023640 | HPR184 | 2020-04-01 | Overhead | 717677 | 18030263 | 11813387
MCR023641 | HPR184 | 2020-05-01 | Labor | 0 | 8535921 | 10218283
MCR023642 | HPR184 | 2020-05-01 | Material | 0 | 33325640 | 39658934
MCR023643 | HPR184 | 2020-05-01 | Equipment | 0 | 19460318 | 21285759
MCR023644 | HPR184 | 2020-05-01 | Subcontract | 0 | 17989116 | 25233980
MCR023645 | HPR184 | 2020-05-01 | Overhead | 0 | 8810737 | 11659857
MCR023646 | HPR184 | 2020-06-01 | Labor | 0 | 7220769 | 7559817
MCR023647 | HPR184 | 2020-06-01 | Material | 0 | 28191071 | 23912447
MCR023648 | HPR184 | 2020-06-01 | Equipment | 0 | 16462015 | 16898486
MCR023649 | HPR184 | 2020-06-01 | Subcontract | 0 | 15217486 | 25480189
MCR023650 | HPR184 | 2020-06-01 | Overhead | 0 | 7453244 | 12442114
MCR023651 | HPR184 | 2020-07-01 | Labor | 0 | 4686345 | 4616030
MCR023652 | HPR184 | 2020-07-01 | Material | 0 | 18296260 | 20024426
MCR023653 | HPR184 | 2020-07-01 | Equipment | 0 | 10683997 | 12165187
MCR023654 | HPR184 | 2020-07-01 | Subcontract | 0 | 9876286 | 21946470
MCR023655 | HPR184 | 2020-07-01 | Overhead | 0 | 4837223 | 13276318
MCR023656 | HPR184 | 2020-08-01 | Labor | 0 | 3831641 | 3428225
MCR023657 | HPR184 | 2020-08-01 | Material | 0 | 14959357 | 14799565
MCR023658 | HPR184 | 2020-08-01 | Equipment | 0 | 8735431 | 9511671
MCR023659 | HPR184 | 2020-08-01 | Subcontract | 0 | 8075032 | 23464081
MCR023660 | HPR184 | 2020-08-01 | Overhead | 0 | 3955002 | 11596430
MCR023661 | HPR184 | 2020-09-01 | Labor | 0 | 3211916 | 3511178
MCR023662 | HPR184 | 2020-09-01 | Material | 0 | 12539847 | 13430752
MCR023663 | HPR184 | 2020-09-01 | Equipment | 0 | 7322572 | 8842540
MCR023664 | HPR184 | 2020-09-01 | Subcontract | 0 | 6768985 | 11085970
MCR023665 | HPR184 | 2020-09-01 | Overhead | 0 | 3315324 | 12172312
MCR023666 | HPR184 | 2020-10-01 | Labor | 0 | 3003752 | 2938943
MCR023667 | HPR184 | 2020-10-01 | Material | 0 | 11727142 | 10850124
MCR023668 | HPR184 | 2020-10-01 | Equipment | 0 | 6847997 | 7726912
MCR023669 | HPR184 | 2020-10-01 | Subcontract | 0 | 6330288 | 23786239
MCR023670 | HPR184 | 2020-10-01 | Overhead | 0 | 3100459 | 13194565
MCR023671 | HPR184 | 2020-11-01 | Labor | 0 | 2008129 | 2024141
MCR023672 | HPR184 | 2020-11-01 | Material | 0 | 7840067 | 7942070
MCR023673 | HPR184 | 2020-11-01 | Equipment | 0 | 4578163 | 5552958
MCR023674 | HPR184 | 2020-11-01 | Subcontract | 0 | 4232053 | 17959027
MCR023675 | HPR184 | 2020-11-01 | Overhead | 0 | 2072782 | 13314618
MCR023676 | HPR184 | 2020-12-01 | Labor | 0 | 1118004 | 953269
MCR023677 | HPR184 | 2020-12-01 | Material | 0 | 4364870 | 4096099
MCR023678 | HPR184 | 2020-12-01 | Equipment | 0 | 2548841 | 3046334
MCR023679 | HPR184 | 2020-12-01 | Subcontract | 0 | 2356148 | 7952504
MCR023680 | HPR184 | 2020-12-01 | Overhead | 0 | 1153998 | 12407626
MCR023681 | HPR184 | 2021-01-01 | Labor | 0 | 394607 | 444151
MCR023682 | HPR184 | 2021-01-01 | Material | 0 | 1540611 | 2070512
MCR023683 | HPR184 | 2021-01-01 | Equipment | 0 | 899631 | 1322592
MCR023684 | HPR184 | 2021-01-01 | Subcontract | 0 | 831619 | 12240350
MCR023685 | HPR184 | 2021-01-01 | Overhead | 0 | 407312 | 13227827
MCR023686 | HPR185 | 2022-10-01 | Labor | 8724756 | 7581091 | 7901112
MCR023687 | HPR185 | 2022-10-01 | Material | 17298775 | 15031204 | 15060246
MCR023688 | HPR185 | 2022-10-01 | Equipment | 3779662 | 3284214 | 3413794
MCR023689 | HPR185 | 2022-10-01 | Subcontract | 23276437 | 20225298 | 19612698
MCR023690 | HPR185 | 2022-10-01 | Overhead | 4762573 | 4138282 | 28161188
MCR023691 | HPR185 | 2022-11-01 | Labor | 24828445 | 15507540 | 14909474
MCR023692 | HPR185 | 2022-11-01 | Material | 49227931 | 30747158 | 26532047
MCR023693 | HPR185 | 2022-11-01 | Equipment | 10755961 | 6718040 | 6439469
MCR023694 | HPR185 | 2022-11-01 | Subcontract | 66238842 | 41371962 | 40511250
MCR023695 | HPR185 | 2022-11-01 | Overhead | 13553075 | 8465084 | 29346512
MCR023696 | HPR185 | 2022-12-01 | Labor | 38945037 | 17517342 | 17925343
MCR023697 | HPR185 | 2022-12-01 | Material | 77217226 | 34732039 | 38958543
MCR023698 | HPR185 | 2022-12-01 | Equipment | 16871427 | 7588709 | 7835808
MCR023699 | HPR185 | 2022-12-01 | Subcontract | 103899950 | 46733836 | 50168756
MCR023700 | HPR185 | 2022-12-01 | Overhead | 21258884 | 9562172 | 29223310
MCR023701 | HPR185 | 2023-01-01 | Labor | 51118251 | 32351107 | 35360049
MCR023702 | HPR185 | 2023-01-01 | Material | 101353337 | 64143287 | 65715212
MCR023703 | HPR185 | 2023-01-01 | Equipment | 22145000 | 14014862 | 13765567
MCR023704 | HPR185 | 2023-01-01 | Subcontract | 136376392 | 86308259 | 81144405
MCR023705 | HPR185 | 2023-01-01 | Overhead | 27903863 | 17659463 | 29378005
MCR023706 | HPR185 | 2023-02-01 | Labor | 61393890 | 31881556 | 30946308
MCR023707 | HPR185 | 2023-02-01 | Material | 121727084 | 63212298 | 57049558
MCR023708 | HPR185 | 2023-02-01 | Equipment | 26596522 | 13811448 | 16679719
MCR023709 | HPR185 | 2023-02-01 | Subcontract | 163790370 | 85055563 | 93272895
MCR023710 | HPR185 | 2023-02-01 | Overhead | 33513014 | 17403150 | 29586528
MCR023711 | HPR185 | 2023-03-01 | Labor | 69820088 | 56581753 | 67072617
MCR023712 | HPR185 | 2023-03-01 | Material | 138433902 | 112185950 | 102526193
MCR023713 | HPR185 | 2023-03-01 | Equipment | 30246845 | 24511850 | 21045074
MCR023714 | HPR185 | 2023-03-01 | Subcontract | 186270296 | 150952258 | 133893185
MCR023715 | HPR185 | 2023-03-01 | Overhead | 38112614 | 30886219 | 28697098
MCR023716 | HPR185 | 2023-04-01 | Labor | 76447588 | 36838116 | 35059365
MCR023717 | HPR185 | 2023-04-01 | Material | 151574400 | 73039783 | 76140968
MCR023718 | HPR185 | 2023-04-01 | Equipment | 33117953 | 15958685 | 18901529
MCR023719 | HPR185 | 2023-04-01 | Subcontract | 203951546 | 98278976 | 101101217
MCR023720 | HPR185 | 2023-04-01 | Overhead | 41730360 | 20108781 | 28665297
MCR023721 | HPR185 | 2023-05-01 | Labor | 81330085 | 99807242 | 101567409
MCR023722 | HPR185 | 2023-05-01 | Material | 161255039 | 197890126 | 222240216
MCR023723 | HPR185 | 2023-05-01 | Equipment | 35233105 | 43237617 | 43898823
MCR023724 | HPR185 | 2023-05-01 | Subcontract | 216977369 | 266271859 | 264762365
MCR023725 | HPR185 | 2023-05-01 | Overhead | 44395563 | 54481668 | 29685427
MCR023726 | HPR185 | 2023-06-01 | Labor | 84524631 | 54589921 | 63612339
MCR023727 | HPR185 | 2023-06-01 | Material | 167588940 | 108236699 | 97255031
MCR023728 | HPR185 | 2023-06-01 | Equipment | 36617019 | 23648966 | 27552267
MCR023729 | HPR185 | 2023-06-01 | Subcontract | 225499975 | 145638327 | 158753282
MCR023730 | HPR185 | 2023-06-01 | Overhead | 46139366 | 29798940 | 30137164
MCR023731 | HPR185 | 2023-07-01 | Labor | 86092143 | 49519742 | 47402410
MCR023732 | HPR185 | 2023-07-01 | Material | 170696881 | 98183937 | 109528977
MCR023733 | HPR185 | 2023-07-01 | Equipment | 37296082 | 21452508 | 19897809
MCR023734 | HPR185 | 2023-07-01 | Subcontract | 229681878 | 132111793 | 135709758
MCR023735 | HPR185 | 2023-07-01 | Overhead | 46995022 | 27031286 | 31242293
MCR023736 | HPR185 | 2023-08-01 | Labor | 86098021 | 39635481 | 42913559
MCR023737 | HPR185 | 2023-08-01 | Material | 170708537 | 78586184 | 70137730
MCR023738 | HPR185 | 2023-08-01 | Equipment | 37298629 | 17170535 | 16738076
MCR023739 | HPR185 | 2023-08-01 | Subcontract | 229697561 | 105741958 | 107551883
MCR023740 | HPR185 | 2023-08-01 | Overhead | 46998231 | 21635776 | 30348713
MCR023741 | HPR185 | 2023-09-01 | Labor | 84612944 | 81253290 | 88591808
MCR023742 | HPR185 | 2023-09-01 | Material | 167764040 | 161102777 | 183554718
MCR023743 | HPR185 | 2023-09-01 | Equipment | 36655277 | 35199837 | 38564867
MCR023744 | HPR185 | 2023-09-01 | Subcontract | 225735581 | 216772492 | 234248296
MCR023745 | HPR185 | 2023-09-01 | Overhead | 46187574 | 44353643 | 30105257
MCR023746 | HPR185 | 2023-10-01 | Labor | 81713878 | 77537531 | 72025370
MCR023747 | HPR185 | 2023-10-01 | Material | 162015995 | 153735454 | 146123882
MCR023748 | HPR185 | 2023-10-01 | Equipment | 35399369 | 33590128 | 34727033
MCR023749 | HPR185 | 2023-10-01 | Subcontract | 218001277 | 206859361 | 183209262
MCR023750 | HPR185 | 2023-10-01 | Overhead | 44605064 | 42325326 | 28479995
MCR023751 | HPR185 | 2023-11-01 | Labor | 77485420 | 56911515 | 70725275
MCR023752 | HPR185 | 2023-11-01 | Material | 153632133 | 112839777 | 103726310
MCR023753 | HPR185 | 2023-11-01 | Equipment | 33567553 | 24654707 | 26780237
MCR023754 | HPR185 | 2023-11-01 | Subcontract | 206720337 | 151832018 | 153209582
MCR023755 | HPR185 | 2023-11-01 | Overhead | 42296880 | 31066226 | 29231420
MCR023756 | HPR185 | 2023-12-01 | Labor | 72021598 | 83787472 | 87384373
MCR023757 | HPR185 | 2023-12-01 | Material | 142798888 | 166127357 | 170912925
MCR023758 | HPR185 | 2023-12-01 | Equipment | 31200565 | 36297673 | 33514009
MCR023759 | HPR185 | 2023-12-01 | Subcontract | 192143621 | 223533336 | 203635324
MCR023760 | HPR185 | 2023-12-01 | Overhead | 39314350 | 45736974 | 26394833
MCR023761 | HPR185 | 2024-01-01 | Labor | 65428402 | 45925976 | 47380896
MCR023762 | HPR185 | 2024-01-01 | Material | 129726405 | 91058494 | 95512800
MCR023763 | HPR185 | 2024-01-01 | Equipment | 28344318 | 19895648 | 24103026
MCR023764 | HPR185 | 2024-01-01 | Subcontract | 174553889 | 122524125 | 151733371
MCR023765 | HPR185 | 2024-01-01 | Overhead | 35715329 | 25069561 | 28471153
MCR023766 | HPR185 | 2024-02-01 | Labor | 57827437 | 99808706 | 116428462
MCR023767 | HPR185 | 2024-02-01 | Material | 114655795 | 197893028 | 212859193
MCR023768 | HPR185 | 2024-02-01 | Equipment | 25051494 | 43238251 | 48034606
MCR023769 | HPR185 | 2024-02-01 | Subcontract | 154275568 | 266275764 | 235362741
MCR023770 | HPR185 | 2024-02-01 | Overhead | 31566198 | 54482467 | 28876026
MCR023771 | HPR185 | 2024-03-01 | Labor | 49361506 | 63147394 | 63162216
MCR023772 | HPR185 | 2024-03-01 | Material | 97870199 | 125203798 | 101042270
MCR023773 | HPR185 | 2024-03-01 | Equipment | 21383958 | 27356160 | 27368523
MCR023774 | HPR185 | 2024-03-01 | Subcontract | 131689642 | 168468477 | 182950065
MCR023775 | HPR185 | 2024-03-01 | Overhead | 26944910 | 34470198 | 28440115
MCR023776 | HPR185 | 2024-04-01 | Labor | 40203694 | 68612307 | 62229843
MCR023777 | HPR185 | 2024-04-01 | Material | 79712793 | 136039206 | 134016418
MCR023778 | HPR185 | 2024-04-01 | Equipment | 17416691 | 29723621 | 24909939
MCR023779 | HPR185 | 2024-04-01 | Subcontract | 107257870 | 183048104 | 253335494
MCR023780 | HPR185 | 2024-04-01 | Overhead | 21945946 | 37453323 | 30993878
MCR023781 | HPR185 | 2024-05-01 | Labor | 30573492 | 57802001 | 61344897
MCR023782 | HPR185 | 2024-05-01 | Material | 60618770 | 114605363 | 125317037
MCR023783 | HPR185 | 2024-05-01 | Equipment | 13244780 | 25040475 | 25785759
MCR023784 | HPR185 | 2024-05-01 | Subcontract | 81565831 | 154207709 | 219723366
MCR023785 | HPR185 | 2024-05-01 | Overhead | 16689118 | 31552314 | 30563638
MCR023786 | HPR185 | 2024-06-01 | Labor | 20769436 | 44212343 | 46132544
MCR023787 | HPR185 | 2024-06-01 | Material | 41180041 | 87660835 | 87360937
MCR023788 | HPR185 | 2024-06-01 | Equipment | 8997553 | 19153283 | 22109275
MCR023789 | HPR185 | 2024-06-01 | Subcontract | 55409970 | 117952391 | 196283834
MCR023790 | HPR185 | 2024-06-01 | Overhead | 11337389 | 24134143 | 27151616
MCR023791 | HPR185 | 2024-07-01 | Labor | 11250984 | 36564054 | 37969375
MCR023792 | HPR185 | 2024-07-01 | Material | 22307585 | 72496395 | 69380433
MCR023793 | HPR185 | 2024-07-01 | Equipment | 4874052 | 15839959 | 13490037
MCR023794 | HPR185 | 2024-07-01 | Subcontract | 30016062 | 97547818 | 176940516
MCR023795 | HPR185 | 2024-07-01 | Overhead | 6141562 | 19959180 | 30934148
MCR023796 | HPR185 | 2024-08-01 | Labor | 2983804 | 20151026 | 17460023
MCR023797 | HPR185 | 2024-08-01 | Material | 5916057 | 39953906 | 43311752
MCR023798 | HPR185 | 2024-08-01 | Equipment | 1292617 | 8729651 | 9818423
MCR023799 | HPR185 | 2024-08-01 | Subcontract | 7960375 | 53760139 | 128551548
MCR023800 | HPR185 | 2024-08-01 | Overhead | 1628766 | 10999818 | 32961871
MCR023801 | HPR185 | 2024-09-01 | Labor | 0 | 26093514 | 28950973
MCR023802 | HPR185 | 2024-09-01 | Material | 0 | 51736214 | 50463391
MCR023803 | HPR185 | 2024-09-01 | Equipment | 0 | 11304003 | 10846123
MCR023804 | HPR185 | 2024-09-01 | Subcontract | 0 | 69613872 | 108734106
MCR023805 | HPR185 | 2024-09-01 | Overhead | 0 | 14243638 | 30882665
MCR023806 | HPR185 | 2024-10-01 | Labor | 0 | 25306900 | 27358293
MCR023807 | HPR185 | 2024-10-01 | Material | 0 | 50176576 | 57059023
MCR023808 | HPR185 | 2024-10-01 | Equipment | 0 | 10963233 | 12677770
MCR023809 | HPR185 | 2024-10-01 | Subcontract | 0 | 67515295 | 128430518
MCR023810 | HPR185 | 2024-10-01 | Overhead | 0 | 13814249 | 30531218
MCR023811 | HPR185 | 2024-11-01 | Labor | 0 | 14327420 | 14683481
MCR023812 | HPR185 | 2024-11-01 | Material | 0 | 28407306 | 27800323
MCR023813 | HPR185 | 2024-11-01 | Equipment | 0 | 6206799 | 6925500
MCR023814 | HPR185 | 2024-11-01 | Subcontract | 0 | 38223565 | 61271191
MCR023815 | HPR185 | 2024-11-01 | Overhead | 0 | 7820893 | 30300366
MCR023816 | HPR185 | 2024-12-01 | Labor | 0 | 12723169 | 13888478
MCR023817 | HPR185 | 2024-12-01 | Material | 0 | 25226521 | 21617657
MCR023818 | HPR185 | 2024-12-01 | Equipment | 0 | 5511820 | 6625404
MCR023819 | HPR185 | 2024-12-01 | Subcontract | 0 | 33943647 | 127491175
MCR023820 | HPR185 | 2024-12-01 | Overhead | 0 | 6945182 | 30539959
MCR023821 | HPR185 | 2025-01-01 | Labor | 0 | 6148859 | 5929611
MCR023822 | HPR185 | 2025-01-01 | Material | 0 | 12191485 | 12728145
MCR023823 | HPR185 | 2025-01-01 | Equipment | 0 | 2663755 | 3027559
MCR023824 | HPR185 | 2025-01-01 | Subcontract | 0 | 16404302 | 110702853
MCR023825 | HPR185 | 2025-01-01 | Overhead | 0 | 3356471 | 29785604
MCR023826 | HPR185 | 2025-02-01 | Labor | 0 | 1431160 | 1535623
MCR023827 | HPR185 | 2025-02-01 | Material | 0 | 2837593 | 2304230
MCR023828 | HPR185 | 2025-02-01 | Equipment | 0 | 619994 | 621829
MCR023829 | HPR185 | 2025-02-01 | Subcontract | 0 | 3818135 | 103061839
MCR023830 | HPR185 | 2025-02-01 | Overhead | 0 | 781225 | 30836612
MCR023831 | HPR186 | 2018-07-01 | Labor | 1192116 | 762038 | 920309
MCR023832 | HPR186 | 2018-07-01 | Material | 4746439 | 3034074 | 2994525
MCR023833 | HPR186 | 2018-07-01 | Equipment | 2803073 | 1791813 | 1781528
MCR023834 | HPR186 | 2018-07-01 | Subcontract | 2509541 | 1604178 | 1616979
MCR023835 | HPR186 | 2018-07-01 | Overhead | 972146 | 621426 | 6833695
MCR023836 | HPR186 | 2018-08-01 | Labor | 3414114 | 1619345 | 1828161
MCR023837 | HPR186 | 2018-08-01 | Material | 13593377 | 6447461 | 6085070
MCR023838 | HPR186 | 2018-08-01 | Equipment | 8027751 | 3807634 | 3761051
MCR023839 | HPR186 | 2018-08-01 | Subcontract | 7187101 | 3408906 | 3846642
MCR023840 | HPR186 | 2018-08-01 | Overhead | 2784139 | 1320542 | 7341632
MCR023841 | HPR186 | 2018-09-01 | Labor | 5396108 | 3665171 | 3685471
MCR023842 | HPR186 | 2018-09-01 | Material | 21484734 | 14592964 | 16398424
MCR023843 | HPR186 | 2018-09-01 | Equipment | 12688098 | 8618070 | 8802470
MCR023844 | HPR186 | 2018-09-01 | Subcontract | 11359425 | 7715603 | 8587356
MCR023845 | HPR186 | 2018-09-01 | Overhead | 4400414 | 2988870 | 7117715
MCR023846 | HPR186 | 2018-10-01 | Labor | 7142704 | 6205714 | 7048121
MCR023847 | HPR186 | 2018-10-01 | Material | 28438844 | 24708199 | 24247848
MCR023848 | HPR186 | 2018-10-01 | Equipment | 16794940 | 14591758 | 14301140
MCR023849 | HPR186 | 2018-10-01 | Subcontract | 15036207 | 13063738 | 12996706
MCR023850 | HPR186 | 2018-10-01 | Overhead | 5824726 | 5060630 | 6858133
MCR023851 | HPR186 | 2018-11-01 | Labor | 8658695 | 6450676 | 7068058
MCR023852 | HPR186 | 2018-11-01 | Material | 34474799 | 25683522 | 26617769
MCR023853 | HPR186 | 2018-11-01 | Equipment | 20359555 | 15167748 | 14966788
MCR023854 | HPR186 | 2018-11-01 | Subcontract | 18227542 | 13579411 | 15767562
MCR023855 | HPR186 | 2018-11-01 | Overhead | 7060985 | 5260392 | 7420763
MCR023856 | HPR186 | 2018-12-01 | Labor | 9949087 | 6959188 | 8141679
MCR023857 | HPR186 | 2018-12-01 | Material | 39612527 | 27708173 | 26732189
MCR023858 | HPR186 | 2018-12-01 | Equipment | 23393709 | 16363433 | 19075467
MCR023859 | HPR186 | 2018-12-01 | Subcontract | 20943966 | 14649887 | 18146852
MCR023860 | HPR186 | 2018-12-01 | Overhead | 8113273 | 5675073 | 7171185
MCR023861 | HPR186 | 2019-01-01 | Labor | 11019117 | 9424872 | 9910294
MCR023862 | HPR186 | 2019-01-01 | Material | 43872875 | 37525354 | 37510166
MCR023863 | HPR186 | 2019-01-01 | Equipment | 25909714 | 22161100 | 22171878
MCR023864 | HPR186 | 2019-01-01 | Subcontract | 23196500 | 19840434 | 21314489
MCR023865 | HPR186 | 2019-01-01 | Overhead | 8985859 | 7685787 | 6507345
MCR023866 | HPR186 | 2019-02-01 | Labor | 11874276 | 6488420 | 8353164
MCR023867 | HPR186 | 2019-02-01 | Material | 47277711 | 25833797 | 27447633
MCR023868 | HPR186 | 2019-02-01 | Equipment | 27920486 | 15256495 | 14833642
MCR023869 | HPR186 | 2019-02-01 | Subcontract | 24996708 | 13658865 | 13012968
MCR023870 | HPR186 | 2019-02-01 | Overhead | 9683224 | 5291171 | 6435429
MCR023871 | HPR186 | 2019-03-01 | Labor | 12520344 | 9796234 | 10069223
MCR023872 | HPR186 | 2019-03-01 | Material | 49850045 | 39003939 | 39214253
MCR023873 | HPR186 | 2019-03-01 | Equipment | 29439612 | 23034299 | 21247047
MCR023874 | HPR186 | 2019-03-01 | Subcontract | 26356754 | 20622193 | 23681919
MCR023875 | HPR186 | 2019-03-01 | Overhead | 10210079 | 7988624 | 6671067
MCR023876 | HPR186 | 2019-04-01 | Labor | 12963421 | 10537764 | 12675877
MCR023877 | HPR186 | 2019-04-01 | Material | 51614168 | 41956357 | 47754144
MCR023878 | HPR186 | 2019-04-01 | Equipment | 30481439 | 24777889 | 32207464
MCR023879 | HPR186 | 2019-04-01 | Subcontract | 27289483 | 22183197 | 23742906
MCR023880 | HPR186 | 2019-04-01 | Overhead | 10571399 | 8593326 | 7153913
MCR023881 | HPR186 | 2019-05-01 | Labor | 13209973 | 13891840 | 17687672
MCR023882 | HPR186 | 2019-05-01 | Material | 52595821 | 55310691 | 51839161
MCR023883 | HPR186 | 2019-05-01 | Equipment | 31061167 | 32664470 | 30967189
MCR023884 | HPR186 | 2019-05-01 | Subcontract | 27808503 | 29243911 | 29438227
MCR023885 | HPR186 | 2019-05-01 | Overhead | 10772457 | 11328505 | 6948380
MCR023886 | HPR186 | 2019-06-01 | Labor | 13266880 | 13169222 | 15381368
MCR023887 | HPR186 | 2019-06-01 | Material | 52822397 | 52433569 | 52973248
MCR023888 | HPR186 | 2019-06-01 | Equipment | 31194975 | 30965347 | 30828830
MCR023889 | HPR186 | 2019-06-01 | Subcontract | 27928298 | 27722717 | 31856642
MCR023890 | HPR186 | 2019-06-01 | Overhead | 10818863 | 10739225 | 7259880
MCR023891 | HPR186 | 2019-07-01 | Labor | 13141501 | 7533180 | 10451438
MCR023892 | HPR186 | 2019-07-01 | Material | 52323198 | 29993536 | 32913390
MCR023893 | HPR186 | 2019-07-01 | Equipment | 30900166 | 17713085 | 19483380
MCR023894 | HPR186 | 2019-07-01 | Subcontract | 27664362 | 15858206 | 17251765
MCR023895 | HPR186 | 2019-07-01 | Overhead | 10716619 | 6143151 | 7254265
MCR023896 | HPR186 | 2019-08-01 | Labor | 12841752 | 5991732 | 6799829
MCR023897 | HPR186 | 2019-08-01 | Material | 51129743 | 23856224 | 24916230
MCR023898 | HPR186 | 2019-08-01 | Equipment | 30195355 | 14088613 | 13031884
MCR023899 | HPR186 | 2019-08-01 | Subcontract | 27033357 | 12613281 | 13275136
MCR023900 | HPR186 | 2019-08-01 | Overhead | 10472181 | 4886132 | 6789726
MCR023901 | HPR186 | 2019-09-01 | Labor | 12376207 | 11130702 | 12648908
MCR023902 | HPR186 | 2019-09-01 | Material | 49276162 | 44317154 | 46992995
MCR023903 | HPR186 | 2019-09-01 | Equipment | 29100698 | 26172089 | 25677250
MCR023904 | HPR186 | 2019-09-01 | Subcontract | 26053330 | 23431400 | 24505989
MCR023905 | HPR186 | 2019-09-01 | Overhead | 10092538 | 9076855 | 7098454
MCR023906 | HPR186 | 2019-10-01 | Labor | 11754222 | 12551967 | 13215175
MCR023907 | HPR186 | 2019-10-01 | Material | 46799713 | 49975955 | 44212814
MCR023908 | HPR186 | 2019-10-01 | Equipment | 27638197 | 29513970 | 30202155
MCR023909 | HPR186 | 2019-10-01 | Subcontract | 24743980 | 26423325 | 28981660
MCR023910 | HPR186 | 2019-10-01 | Overhead | 9585322 | 10235867 | 7169279
MCR023911 | HPR186 | 2019-11-01 | Labor | 10986108 | 10691110 | 14394735
MCR023912 | HPR186 | 2019-11-01 | Material | 43741449 | 42566910 | 52368850
MCR023913 | HPR186 | 2019-11-01 | Equipment | 25832099 | 25138459 | 26943750
MCR023914 | HPR186 | 2019-11-01 | Subcontract | 23127012 | 22506009 | 21839352
MCR023915 | HPR186 | 2019-11-01 | Overhead | 8958941 | 8718377 | 6806470
MCR023916 | HPR186 | 2019-12-01 | Labor | 10083359 | 6361586 | 6817834
MCR023917 | HPR186 | 2019-12-01 | Material | 40147133 | 25328805 | 20516299
MCR023918 | HPR186 | 2019-12-01 | Equipment | 23709427 | 14958265 | 14949490
MCR023919 | HPR186 | 2019-12-01 | Subcontract | 21226623 | 13391865 | 15730869
MCR023920 | HPR186 | 2019-12-01 | Overhead | 8222768 | 5187740 | 6957565
MCR023921 | HPR186 | 2020-01-01 | Labor | 9058973 | 10393303 | 11738853
MCR023922 | HPR186 | 2020-01-01 | Material | 36068515 | 41381184 | 32693634
MCR023923 | HPR186 | 2020-01-01 | Equipment | 21300745 | 24438213 | 25051397
MCR023924 | HPR186 | 2020-01-01 | Subcontract | 19070173 | 21879091 | 22513653
MCR023925 | HPR186 | 2020-01-01 | Overhead | 7387403 | 8475522 | 6710002
MCR023926 | HPR186 | 2020-02-01 | Labor | 7927917 | 7220443 | 8967812
MCR023927 | HPR186 | 2020-02-01 | Material | 31565188 | 28748367 | 35583659
MCR023928 | HPR186 | 2020-02-01 | Equipment | 18641245 | 16977733 | 16182853
MCR023929 | HPR186 | 2020-02-01 | Subcontract | 16689171 | 15199858 | 17533390
MCR023930 | HPR186 | 2020-02-01 | Overhead | 6465050 | 5888121 | 7184224
MCR023931 | HPR186 | 2020-03-01 | Labor | 6707840 | 10494032 | 10643890
MCR023932 | HPR186 | 2020-03-01 | Material | 26707426 | 41782236 | 43599865
MCR023933 | HPR186 | 2020-03-01 | Equipment | 15772428 | 24675059 | 24876440
MCR023934 | HPR186 | 2020-03-01 | Subcontract | 14120771 | 22091136 | 23208060
MCR023935 | HPR186 | 2020-03-01 | Overhead | 5470104 | 8557664 | 6820507
MCR023936 | HPR186 | 2020-04-01 | Labor | 5420240 | 6950881 | 20476697
MCR023937 | HPR186 | 2020-04-01 | Material | 21580814 | 27675099 | 42261137
MCR023938 | HPR186 | 2020-04-01 | Equipment | 12744839 | 16343900 | 18717505
MCR023939 | HPR186 | 2020-04-01 | Subcontract | 11410224 | 14632399 | 24766618
MCR023940 | HPR186 | 2020-04-01 | Overhead | 4420092 | 5668298 | 7609173
MCR023941 | HPR186 | 2020-05-01 | Labor | 4092529 | 12221375 | 22703777
MCR023942 | HPR186 | 2020-05-01 | Material | 16294503 | 48659693 | 57403923
MCR023943 | HPR186 | 2020-05-01 | Equipment | 9622937 | 28736634 | 27887524
MCR023944 | HPR186 | 2020-05-01 | Subcontract | 8615242 | 25727390 | 40567652
MCR023945 | HPR186 | 2020-05-01 | Overhead | 3337372 | 9966276 | 6995375
MCR023946 | HPR186 | 2020-06-01 | Labor | 2762248 | 6770217 | 6824906
MCR023947 | HPR186 | 2020-06-01 | Material | 10997956 | 26955781 | 25278268
MCR023948 | HPR186 | 2020-06-01 | Equipment | 6494990 | 15919098 | 18172991
MCR023949 | HPR186 | 2020-06-01 | Subcontract | 5814848 | 14252081 | 22598103
MCR023950 | HPR186 | 2020-06-01 | Overhead | 2252556 | 5520971 | 6827405
MCR023951 | HPR186 | 2020-07-01 | Labor | 1487656 | 3527681 | 5558324
MCR023952 | HPR186 | 2020-07-01 | Material | 5923138 | 14045547 | 15200146
MCR023953 | HPR186 | 2020-07-01 | Equipment | 3497989 | 8294786 | 8149739
MCR023954 | HPR186 | 2020-07-01 | Subcontract | 3131686 | 7426173 | 19134731
MCR023955 | HPR186 | 2020-07-01 | Overhead | 1213152 | 2876750 | 6960020
MCR023956 | HPR186 | 2020-08-01 | Labor | 392632 | 3826457 | 4206562
MCR023957 | HPR186 | 2020-08-01 | Material | 1563274 | 15235131 | 17477719
MCR023958 | HPR186 | 2020-08-01 | Equipment | 923213 | 8997310 | 8757197
MCR023959 | HPR186 | 2020-08-01 | Subcontract | 826536 | 8055130 | 19113291
MCR023960 | HPR186 | 2020-08-01 | Overhead | 320183 | 3120396 | 7255176
MCR023961 | HPR186 | 2020-09-01 | Labor | 0 | 4755599 | 5819110
MCR023962 | HPR186 | 2020-09-01 | Material | 0 | 18934531 | 18290349
MCR023963 | HPR186 | 2020-09-01 | Equipment | 0 | 11182041 | 11136072
MCR023964 | HPR186 | 2020-09-01 | Subcontract | 0 | 10011080 | 22440097
MCR023965 | HPR186 | 2020-09-01 | Overhead | 0 | 3878092 | 6862458
MCR023966 | HPR186 | 2020-10-01 | Labor | 0 | 5004319 | 5281374
MCR023967 | HPR186 | 2020-10-01 | Material | 0 | 19924813 | 19391605
MCR023968 | HPR186 | 2020-10-01 | Equipment | 0 | 11766866 | 11199418
MCR023969 | HPR186 | 2020-10-01 | Subcontract | 0 | 10534663 | 17534644
MCR023970 | HPR186 | 2020-10-01 | Overhead | 0 | 4080917 | 6535230
MCR023971 | HPR186 | 2020-11-01 | Labor | 0 | 2156867 | 2868069
MCR023972 | HPR186 | 2020-11-01 | Material | 0 | 8587616 | 9391134
MCR023973 | HPR186 | 2020-11-01 | Equipment | 0 | 5071532 | 6386298
MCR023974 | HPR186 | 2020-11-01 | Subcontract | 0 | 4540451 | 12926147
MCR023975 | HPR186 | 2020-11-01 | Overhead | 0 | 1758880 | 7533457
MCR023976 | HPR186 | 2020-12-01 | Labor | 0 | 1533966 | 2037907
MCR023977 | HPR186 | 2020-12-01 | Material | 0 | 6107523 | 6358618
MCR023978 | HPR186 | 2020-12-01 | Equipment | 0 | 3606879 | 3608107
MCR023979 | HPR186 | 2020-12-01 | Subcontract | 0 | 3229174 | 14602204
MCR023980 | HPR186 | 2020-12-01 | Overhead | 0 | 1250917 | 7571974
MCR023981 | HPR186 | 2021-01-01 | Labor | 0 | 948345 | 1070447
MCR023982 | HPR186 | 2021-01-01 | Material | 0 | 3775858 | 3943528
MCR023983 | HPR186 | 2021-01-01 | Equipment | 0 | 2229884 | 3001607
MCR023984 | HPR186 | 2021-01-01 | Subcontract | 0 | 1996375 | 10995516
MCR023985 | HPR186 | 2021-01-01 | Overhead | 0 | 773356 | 6864713
MCR023986 | HPR186 | 2021-02-01 | Labor | 0 | 605770 | 723780
MCR023987 | HPR186 | 2021-02-01 | Material | 0 | 2411886 | 2649167
MCR023988 | HPR186 | 2021-02-01 | Equipment | 0 | 1424372 | 1628055
MCR023989 | HPR186 | 2021-02-01 | Subcontract | 0 | 1275214 | 9509992
MCR023990 | HPR186 | 2021-02-01 | Overhead | 0 | 493993 | 6479895
MCR023991 | HPR187 | 2018-10-01 | Labor | 1151962 | 1000393 | 1185626
MCR023992 | HPR187 | 2018-10-01 | Material | 2796657 | 2428689 | 2475564
MCR023993 | HPR187 | 2018-10-01 | Equipment | 799272 | 694108 | 766136
MCR023994 | HPR187 | 2018-10-01 | Subcontract | 3976289 | 3453113 | 3788973
MCR023995 | HPR187 | 2018-10-01 | Overhead | 879820 | 764058 | 7560885
MCR023996 | HPR187 | 2018-11-01 | Labor | 3324835 | 2366328 | 2227391
MCR023997 | HPR187 | 2018-11-01 | Material | 8071818 | 5744817 | 6258744
MCR023998 | HPR187 | 2018-11-01 | Equipment | 2306888 | 1641842 | 1910758
MCR023999 | HPR187 | 2018-11-01 | Subcontract | 11476518 | 8167986 | 7712290
MCR024000 | HPR187 | 2018-11-01 | Overhead | 2539369 | 1807302 | 6844664
MCR024001 | HPR187 | 2018-12-01 | Labor | 5303382 | 2850785 | 2947791
MCR024002 | HPR187 | 2018-12-01 | Material | 12875203 | 6920950 | 7013106
MCR024003 | HPR187 | 2018-12-01 | Equipment | 3679673 | 1977975 | 1576885
MCR024004 | HPR187 | 2018-12-01 | Subcontract | 18305976 | 9840213 | 10331761
MCR024005 | HPR187 | 2018-12-01 | Overhead | 4050499 | 2177309 | 7666888
MCR024006 | HPR187 | 2019-01-01 | Labor | 7090673 | 5188026 | 5980708
MCR024007 | HPR187 | 2019-01-01 | Material | 17214274 | 12595149 | 10636454
MCR024008 | HPR187 | 2019-01-01 | Equipment | 4919759 | 3599635 | 4324924
MCR024009 | HPR187 | 2019-01-01 | Subcontract | 24475270 | 17907795 | 18904933
MCR024010 | HPR187 | 2019-01-01 | Overhead | 5415557 | 3962395 | 7219398
MCR024011 | HPR187 | 2019-02-01 | Labor | 8689888 | 3445846 | 3205615
MCR024012 | HPR187 | 2019-02-01 | Material | 21096742 | 8365601 | 9952038
MCR024013 | HPR187 | 2019-02-01 | Equipment | 6029351 | 2390850 | 2165234
MCR024014 | HPR187 | 2019-02-01 | Subcontract | 29995367 | 11894219 | 11769938
MCR024015 | HPR187 | 2019-02-01 | Overhead | 6636970 | 2631792 | 6771275
MCR024016 | HPR187 | 2019-03-01 | Labor | 10104315 | 7278724 | 7654203
MCR024017 | HPR187 | 2019-03-01 | Material | 24530596 | 17670809 | 17639289
MCR024018 | HPR187 | 2019-03-01 | Equipment | 7010730 | 5050235 | 5388336
MCR024019 | HPR187 | 2019-03-01 | Subcontract | 34877624 | 25124373 | 26199544
MCR024020 | HPR187 | 2019-03-01 | Overhead | 7717249 | 5559182 | 6950153
MCR024021 | HPR187 | 2019-04-01 | Labor | 11337366 | 6721255 | 7994622
MCR024022 | HPR187 | 2019-04-01 | Material | 27524117 | 16317423 | 14686680
MCR024023 | HPR187 | 2019-04-01 | Equipment | 7866264 | 4663444 | 4435770
MCR024024 | HPR187 | 2019-04-01 | Subcontract | 39133815 | 23200127 | 23767880
MCR024025 | HPR187 | 2019-04-01 | Overhead | 8659002 | 5133411 | 7920367
MCR024026 | HPR187 | 2019-05-01 | Labor | 12392586 | 10490421 | 12277326
MCR024027 | HPR187 | 2019-05-01 | Material | 30085910 | 25467958 | 28376628
MCR024028 | HPR187 | 2019-05-01 | Equipment | 8598413 | 7278624 | 6640097
MCR024029 | HPR187 | 2019-05-01 | Subcontract | 42776174 | 36210366 | 36445605
MCR024030 | HPR187 | 2019-05-01 | Overhead | 9464934 | 8012140 | 7497342
MCR024031 | HPR187 | 2019-06-01 | Labor | 13273662 | 11992583 | 12969015
MCR024032 | HPR187 | 2019-06-01 | Material | 32224929 | 29114810 | 28724835
MCR024033 | HPR187 | 2019-06-01 | Equipment | 9209735 | 8320877 | 8653168
MCR024034 | HPR187 | 2019-06-01 | Subcontract | 45817434 | 41395463 | 41836346
MCR024035 | HPR187 | 2019-06-01 | Overhead | 10137863 | 9159429 | 7150595
MCR024036 | HPR187 | 2019-07-01 | Labor | 13984443 | 6028093 | 5940959
MCR024037 | HPR187 | 2019-07-01 | Material | 33950515 | 14634610 | 16094154
MCR024038 | HPR187 | 2019-07-01 | Equipment | 9702899 | 4182503 | 4351738
MCR024039 | HPR187 | 2019-07-01 | Subcontract | 48270874 | 20807502 | 22371931
MCR024040 | HPR187 | 2019-07-01 | Overhead | 10680727 | 4604003 | 7526697
MCR024041 | HPR187 | 2019-08-01 | Labor | 14528948 | 8402054 | 9540828
MCR024042 | HPR187 | 2019-08-01 | Material | 35272431 | 20397958 | 18604788
MCR024043 | HPR187 | 2019-08-01 | Equipment | 10080696 | 5829641 | 5819391
MCR024044 | HPR187 | 2019-08-01 | Subcontract | 50150375 | 29001835 | 28826534
MCR024045 | HPR187 | 2019-08-01 | Overhead | 11096597 | 6417134 | 7499116
MCR024046 | HPR187 | 2019-09-01 | Labor | 14911394 | 8257689 | 8834435
MCR024047 | HPR187 | 2019-09-01 | Material | 36200907 | 20047478 | 20980511
MCR024048 | HPR187 | 2019-09-01 | Equipment | 10346051 | 5729476 | 6089546
MCR024049 | HPR187 | 2019-09-01 | Subcontract | 51470483 | 28503523 | 30148462
MCR024050 | HPR187 | 2019-09-01 | Overhead | 11388693 | 6306874 | 7326934
MCR024051 | HPR187 | 2019-10-01 | Labor | 15136208 | 15960463 | 16767085
MCR024052 | HPR187 | 2019-10-01 | Material | 36746696 | 38747770 | 42645724
MCR024053 | HPR187 | 2019-10-01 | Equipment | 10502034 | 11073932 | 13693476
MCR024054 | HPR187 | 2019-10-01 | Subcontract | 52246486 | 55091615 | 52900239
MCR024055 | HPR187 | 2019-10-01 | Overhead | 11560396 | 12189928 | 7236473
MCR024056 | HPR187 | 2019-11-01 | Labor | 15208059 | 11019743 | 13744031
MCR024057 | HPR187 | 2019-11-01 | Material | 36921131 | 26753011 | 29885178
MCR024058 | HPR187 | 2019-11-01 | Equipment | 10551887 | 7645886 | 6471624
MCR024059 | HPR187 | 2019-11-01 | Subcontract | 52494498 | 38037456 | 32393602
MCR024060 | HPR187 | 2019-11-01 | Overhead | 11615273 | 8416414 | 7684681
MCR024061 | HPR187 | 2019-12-01 | Labor | 15131886 | 7717031 | 8094947
MCR024062 | HPR187 | 2019-12-01 | Material | 36736203 | 18734904 | 18652847
MCR024063 | HPR187 | 2019-12-01 | Equipment | 10499036 | 5354348 | 5260813
MCR024064 | HPR187 | 2019-12-01 | Subcontract | 52231568 | 26637304 | 34122555
MCR024065 | HPR187 | 2019-12-01 | Overhead | 11557096 | 5893943 | 8292225
MCR024066 | HPR187 | 2020-01-01 | Labor | 14912934 | 9311057 | 9180827
MCR024067 | HPR187 | 2020-01-01 | Material | 36204647 | 22604776 | 24014775
MCR024068 | HPR187 | 2020-01-01 | Equipment | 10347120 | 6460340 | 5877007
MCR024069 | HPR187 | 2020-01-01 | Subcontract | 51475801 | 32139492 | 29457030
MCR024070 | HPR187 | 2020-01-01 | Overhead | 11389870 | 7111392 | 7232063
MCR024071 | HPR187 | 2020-02-01 | Labor | 14556800 | 13250177 | 14189341
MCR024072 | HPR187 | 2020-02-01 | Material | 35340048 | 32167915 | 32411260
MCR024073 | HPR187 | 2020-02-01 | Equipment | 10100021 | 9193440 | 10606488
MCR024074 | HPR187 | 2020-02-01 | Subcontract | 50246513 | 45736371 | 42955446
MCR024075 | HPR187 | 2020-02-01 | Overhead | 11117869 | 10119926 | 7841148
MCR024076 | HPR187 | 2020-03-01 | Labor | 14069485 | 18603883 | 19827820
MCR024077 | HPR187 | 2020-03-01 | Material | 34156975 | 45165290 | 48240634
MCR024078 | HPR187 | 2020-03-01 | Equipment | 9761904 | 12908029 | 13170957
MCR024079 | HPR187 | 2020-03-01 | Subcontract | 48564419 | 64216051 | 69047777
MCR024080 | HPR187 | 2020-03-01 | Overhead | 10745678 | 14208860 | 7867222
MCR024081 | HPR187 | 2020-04-01 | Labor | 13457461 | 19054487 | 21004294
MCR024082 | HPR187 | 2020-04-01 | Material | 32671144 | 46259239 | 47099150
MCR024083 | HPR187 | 2020-04-01 | Equipment | 9337261 | 13220675 | 13701046
MCR024084 | HPR187 | 2020-04-01 | Subcontract | 46451863 | 65771429 | 69050251
MCR024085 | HPR187 | 2020-04-01 | Overhead | 10278240 | 14553013 | 7123548
MCR024086 | HPR187 | 2020-05-01 | Labor | 12727762 | 16635612 | 17363201
MCR024087 | HPR187 | 2020-05-01 | Material | 30899628 | 40386852 | 40056915
MCR024088 | HPR187 | 2020-05-01 | Equipment | 8830970 | 11542374 | 11480435
MCR024089 | HPR187 | 2020-05-01 | Subcontract | 43933119 | 57422064 | 48570902
MCR024090 | HPR187 | 2020-05-01 | Overhead | 9720927 | 12705578 | 7408632
MCR024091 | HPR187 | 2020-06-01 | Labor | 11888089 | 17134637 | 19053328
MCR024092 | HPR187 | 2020-06-01 | Material | 28861126 | 41598351 | 44833228
MCR024093 | HPR187 | 2020-06-01 | Equipment | 8248375 | 11888615 | 13077191
MCR024094 | HPR187 | 2020-06-01 | Subcontract | 41034776 | 59144575 | 71777278
MCR024095 | HPR187 | 2020-06-01 | Overhead | 9079621 | 13086712 | 7721807
MCR024096 | HPR187 | 2020-07-01 | Labor | 10946964 | 8674737 | 8653580
MCR024097 | HPR187 | 2020-07-01 | Material | 26576323 | 21059958 | 22009630
MCR024098 | HPR187 | 2020-07-01 | Equipment | 7595389 | 6018838 | 6347653
MCR024099 | HPR187 | 2020-07-01 | Subcontract | 37786241 | 29943068 | 24523110
MCR024100 | HPR187 | 2020-07-01 | Overhead | 8360829 | 6625398 | 7186653
MCR024101 | HPR187 | 2020-08-01 | Labor | 9913922 | 6983592 | 7430989
MCR024102 | HPR187 | 2020-08-01 | Material | 24068371 | 16954307 | 16464531
MCR024103 | HPR187 | 2020-08-01 | Equipment | 6878628 | 4845462 | 4572846
MCR024104 | HPR187 | 2020-08-01 | Subcontract | 34220433 | 24105650 | 28676452
MCR024105 | HPR187 | 2020-08-01 | Overhead | 7571835 | 5333772 | 7574007
MCR024106 | HPR187 | 2020-09-01 | Labor | 8799799 | 11108000 | 13434950
MCR024107 | HPR187 | 2020-09-01 | Material | 21363576 | 26967277 | 28704120
MCR024108 | HPR187 | 2020-09-01 | Equipment | 6105611 | 7707122 | 8755218
MCR024109 | HPR187 | 2020-09-01 | Subcontract | 30374753 | 38342099 | 36082649
MCR024110 | HPR187 | 2020-09-01 | Overhead | 6720915 | 8483822 | 7212280
MCR024111 | HPR187 | 2020-10-01 | Labor | 7617138 | 11337057 | 11706332
MCR024112 | HPR187 | 2020-10-01 | Material | 18492389 | 27523367 | 28074425
MCR024113 | HPR187 | 2020-10-01 | Equipment | 5285039 | 7866050 | 8454930
MCR024114 | HPR187 | 2020-10-01 | Subcontract | 26292496 | 39132748 | 42465252
MCR024115 | HPR187 | 2020-10-01 | Overhead | 5817648 | 8658766 | 7098777
MCR024116 | HPR187 | 2020-11-01 | Labor | 6380818 | 7988461 | 8606670
MCR024117 | HPR187 | 2020-11-01 | Material | 15490933 | 19393863 | 22640489
MCR024118 | HPR187 | 2020-11-01 | Equipment | 4427236 | 5542676 | 6163469
MCR024119 | HPR187 | 2020-11-01 | Subcontract | 22025023 | 27574212 | 23866417
MCR024120 | HPR187 | 2020-11-01 | Overhead | 4873399 | 6101249 | 7637940
MCR024121 | HPR187 | 2020-12-01 | Labor | 5109085 | 12869213 | 15230153
MCR024122 | HPR187 | 2020-12-01 | Material | 12403503 | 31243034 | 31556420
MCR024123 | HPR187 | 2020-12-01 | Equipment | 3544863 | 8929114 | 7726809
MCR024124 | HPR187 | 2020-12-01 | Subcontract | 17635313 | 44421374 | 42865315
MCR024125 | HPR187 | 2020-12-01 | Overhead | 3902104 | 9828961 | 7716337
MCR024126 | HPR187 | 2021-01-01 | Labor | 3825393 | 6162334 | 6724601
MCR024127 | HPR187 | 2021-01-01 | Material | 9287038 | 14960511 | 18463900
MCR024128 | HPR187 | 2021-01-01 | Equipment | 2654192 | 4275644 | 4416268
MCR024129 | HPR187 | 2021-01-01 | Subcontract | 13204320 | 21270868 | 25597416
MCR024130 | HPR187 | 2021-01-01 | Overhead | 2921673 | 4706530 | 6513472
MCR024131 | HPR187 | 2021-02-01 | Labor | 2562155 | 4752322 | 4831905
MCR024132 | HPR187 | 2021-02-01 | Material | 6220233 | 11537377 | 13402871
MCR024133 | HPR187 | 2021-02-01 | Equipment | 1777713 | 3297329 | 3835989
MCR024134 | HPR187 | 2021-02-01 | Subcontract | 8843932 | 16403853 | 15733045
MCR024135 | HPR187 | 2021-02-01 | Overhead | 1956866 | 3629623 | 7164767
MCR024136 | HPR187 | 2021-03-01 | Labor | 1370249 | 4505886 | 4932139
MCR024137 | HPR187 | 2021-03-01 | Material | 3326601 | 10939095 | 9582381
MCR024138 | HPR187 | 2021-03-01 | Equipment | 950727 | 3126342 | 2877533
MCR024139 | HPR187 | 2021-03-01 | Subcontract | 4729764 | 15553215 | 15504041
MCR024140 | HPR187 | 2021-03-01 | Overhead | 1046538 | 3441405 | 7651637
MCR024141 | HPR187 | 2021-04-01 | Labor | 359522 | 6146314 | 6472299
MCR024142 | HPR187 | 2021-04-01 | Material | 872823 | 14921618 | 19855060
MCR024143 | HPR187 | 2021-04-01 | Equipment | 249449 | 4264529 | 4369247
MCR024144 | HPR187 | 2021-04-01 | Subcontract | 1240980 | 21215571 | 23640180
MCR024145 | HPR187 | 2021-04-01 | Overhead | 274587 | 4694295 | 7417035
MCR024146 | HPR187 | 2021-05-01 | Labor | 0 | 5334478 | 6956632
MCR024147 | HPR187 | 2021-05-01 | Material | 0 | 12950697 | 14524907
MCR024148 | HPR187 | 2021-05-01 | Equipment | 0 | 3701249 | 3402545
MCR024149 | HPR187 | 2021-05-01 | Subcontract | 0 | 18413313 | 19567892
MCR024150 | HPR187 | 2021-05-01 | Overhead | 0 | 4074249 | 6823431
MCR024151 | HPR187 | 2021-06-01 | Labor | 0 | 5213389 | 5922872
MCR024152 | HPR187 | 2021-06-01 | Material | 0 | 12656724 | 15293479
MCR024153 | HPR187 | 2021-06-01 | Equipment | 0 | 3617233 | 3711762
MCR024154 | HPR187 | 2021-06-01 | Subcontract | 0 | 17995342 | 18809468
MCR024155 | HPR187 | 2021-06-01 | Overhead | 0 | 3981766 | 7726790
MCR024156 | HPR187 | 2021-07-01 | Labor | 0 | 2086914 | 2195098
MCR024157 | HPR187 | 2021-07-01 | Material | 0 | 5066474 | 5258184
MCR024158 | HPR187 | 2021-07-01 | Equipment | 0 | 1447975 | 1611478
MCR024159 | HPR187 | 2021-07-01 | Subcontract | 0 | 7203517 | 7560422
MCR024160 | HPR187 | 2021-07-01 | Overhead | 0 | 1593897 | 6984281
MCR024161 | HPR187 | 2021-08-01 | Labor | 0 | 1963612 | 2412597
MCR024162 | HPR187 | 2021-08-01 | Material | 0 | 4767130 | 5434803
MCR024163 | HPR187 | 2021-08-01 | Equipment | 0 | 1362424 | 1407861
MCR024164 | HPR187 | 2021-08-01 | Subcontract | 0 | 6777910 | 6419331
MCR024165 | HPR187 | 2021-08-01 | Overhead | 0 | 1499724 | 6962266
MCR024166 | HPR187 | 2021-09-01 | Labor | 0 | 1026357 | 1193737
MCR024167 | HPR187 | 2021-09-01 | Material | 0 | 2491724 | 2762349
MCR024168 | HPR187 | 2021-09-01 | Equipment | 0 | 712123 | 829490
MCR024169 | HPR187 | 2021-09-01 | Subcontract | 0 | 3542735 | 3598343
MCR024170 | HPR187 | 2021-09-01 | Overhead | 0 | 783889 | 7271672
MCR024171 | HPR187 | 2021-10-01 | Labor | 0 | 929268 | 1227045
MCR024172 | HPR187 | 2021-10-01 | Material | 0 | 2256017 | 2964672
MCR024173 | HPR187 | 2021-10-01 | Equipment | 0 | 644759 | 729091
MCR024174 | HPR187 | 2021-10-01 | Subcontract | 0 | 3207607 | 3005525
MCR024175 | HPR187 | 2021-10-01 | Overhead | 0 | 709736 | 7675823
MCR024176 | HPR187 | 2021-11-01 | Labor | 0 | 275959 | 348180
MCR024177 | HPR187 | 2021-11-01 | Material | 0 | 669956 | 654198
MCR024178 | HPR187 | 2021-11-01 | Equipment | 0 | 191470 | 236218
MCR024179 | HPR187 | 2021-11-01 | Subcontract | 0 | 952544 | 1205225
MCR024180 | HPR187 | 2021-11-01 | Overhead | 0 | 210766 | 7191199
MCR024181 | HPR188 | 2020-01-01 | Labor | 5580045 | 3079306 | 3019290
MCR024182 | HPR188 | 2020-01-01 | Material | 10804122 | 5962175 | 6562304
MCR024183 | HPR188 | 2020-01-01 | Equipment | 3202062 | 1767034 | 1799558
MCR024184 | HPR188 | 2020-01-01 | Subcontract | 16762683 | 9250362 | 8820098
MCR024185 | HPR188 | 2020-01-01 | Overhead | 3236361 | 1785962 | 18951570
MCR024186 | HPR188 | 2020-02-01 | Labor | 15795325 | 12594114 | 13177291
MCR024187 | HPR188 | 2020-02-01 | Material | 30583022 | 24384814 | 22557954
MCR024188 | HPR188 | 2020-02-01 | Equipment | 9064014 | 7227026 | 7941674
MCR024189 | HPR188 | 2020-02-01 | Subcontract | 47449805 | 37833236 | 44052638
MCR024190 | HPR188 | 2020-02-01 | Overhead | 9161105 | 7304440 | 17740349
MCR024191 | HPR188 | 2020-03-01 | Labor | 24617879 | 22034457 | 21731757
MCR024192 | HPR188 | 2020-03-01 | Material | 47665314 | 42663274 | 46238696
MCR024193 | HPR188 | 2020-03-01 | Equipment | 14126763 | 12644288 | 13500693
MCR024194 | HPR188 | 2020-03-01 | Subcontract | 73953119 | 66192413 | 63856703
MCR024195 | HPR188 | 2020-03-01 | Overhead | 14278084 | 12779729 | 18945566
MCR024196 | HPR188 | 2020-04-01 | Labor | 32081668 | 24275953 | 25628607
MCR024197 | HPR188 | 2020-04-01 | Material | 62116755 | 47003275 | 44712430
MCR024198 | HPR188 | 2020-04-01 | Equipment | 18409795 | 13930552 | 12853056
MCR024199 | HPR188 | 2020-04-01 | Subcontract | 96374647 | 72925960 | 80168855
MCR024200 | HPR188 | 2020-04-01 | Overhead | 18606995 | 14079771 | 20232274
MCR024201 | HPR188 | 2020-05-01 | Labor | 38222462 | 46096404 | 46895741
MCR024202 | HPR188 | 2020-05-01 | Material | 74006604 | 89252188 | 90078555
MCR024203 | HPR188 | 2020-05-01 | Equipment | 21933638 | 26452034 | 26378307
MCR024204 | HPR188 | 2020-05-01 | Subcontract | 114821843 | 138475489 | 132630688
MCR024205 | HPR188 | 2020-05-01 | Overhead | 22168584 | 26735379 | 19002678
MCR024206 | HPR188 | 2020-06-01 | Labor | 43078070 | 44369724 | 43241288
MCR024207 | HPR188 | 2020-06-01 | Material | 83408067 | 85908977 | 94606527
MCR024208 | HPR188 | 2020-06-01 | Equipment | 24719988 | 25461193 | 26907323
MCR024209 | HPR188 | 2020-06-01 | Subcontract | 129408289 | 133288470 | 145907328
MCR024210 | HPR188 | 2020-06-01 | Overhead | 24984780 | 25733924 | 19388331
MCR024211 | HPR188 | 2020-07-01 | Labor | 46688622 | 29811008 | 31123516
MCR024212 | HPR188 | 2020-07-01 | Material | 90398844 | 57720287 | 56298181
MCR024213 | HPR188 | 2020-07-01 | Equipment | 26791873 | 17106796 | 21754579
MCR024214 | HPR188 | 2020-07-01 | Subcontract | 140254536 | 89553490 | 101410720
MCR024215 | HPR188 | 2020-07-01 | Overhead | 27078858 | 17290038 | 17236144
MCR024216 | HPR188 | 2020-08-01 | Labor | 49096911 | 21113738 | 22979917
MCR024217 | HPR188 | 2020-08-01 | Material | 95061791 | 40880570 | 40187537
MCR024218 | HPR188 | 2020-08-01 | Equipment | 28173849 | 12115941 | 10625979
MCR024219 | HPR188 | 2020-08-01 | Subcontract | 147489135 | 63426534 | 65356721
MCR024220 | HPR188 | 2020-08-01 | Overhead | 28475638 | 12245723 | 16482464
MCR024221 | HPR188 | 2020-09-01 | Labor | 50348819 | 40442547 | 41366922
MCR024222 | HPR188 | 2020-09-01 | Material | 97485745 | 78305150 | 83018030
MCR024223 | HPR188 | 2020-09-01 | Equipment | 28892246 | 23207615 | 24741259
MCR024224 | HPR188 | 2020-09-01 | Subcontract | 151249918 | 121491072 | 126678312
MCR024225 | HPR188 | 2020-09-01 | Overhead | 29201730 | 23456208 | 18058658
MCR024226 | HPR188 | 2020-10-01 | Labor | 50493854 | 34166154 | 36007923
MCR024227 | HPR188 | 2020-10-01 | Material | 97766563 | 66152753 | 60005378
MCR024228 | HPR188 | 2020-10-01 | Equipment | 28975473 | 19605960 | 21025865
MCR024229 | HPR188 | 2020-10-01 | Subcontract | 151685610 | 102636529 | 104507798
MCR024230 | HPR188 | 2020-10-01 | Overhead | 29285849 | 19815973 | 20111527
MCR024231 | HPR188 | 2020-11-01 | Labor | 49585841 | 35568968 | 36331146
MCR024232 | HPR188 | 2020-11-01 | Material | 96008461 | 68868891 | 73122365
MCR024233 | HPR188 | 2020-11-01 | Equipment | 28454418 | 20410953 | 20148528
MCR024234 | HPR188 | 2020-11-01 | Subcontract | 148957901 | 106850639 | 104992499
MCR024235 | HPR188 | 2020-11-01 | Overhead | 28759212 | 20629588 | 18711734
MCR024236 | HPR188 | 2020-12-01 | Labor | 47683829 | 37474203 | 42785335
MCR024237 | HPR188 | 2020-12-01 | Material | 92325772 | 72557821 | 66842544
MCR024238 | HPR188 | 2020-12-01 | Equipment | 27362964 | 21504256 | 22620204
MCR024239 | HPR188 | 2020-12-01 | Subcontract | 143244179 | 112574044 | 134118143
MCR024240 | HPR188 | 2020-12-01 | Overhead | 27656067 | 21734603 | 19036573
MCR024241 | HPR188 | 2021-01-01 | Labor | 44853316 | 30574414 | 55127619
MCR024242 | HPR188 | 2021-01-01 | Material | 86845311 | 59198399 | 84275133
MCR024243 | HPR188 | 2021-01-01 | Equipment | 25738698 | 17544870 | 17306208
MCR024244 | HPR188 | 2021-01-01 | Subcontract | 134741201 | 91846793 | 90342920
MCR024245 | HPR188 | 2021-01-01 | Overhead | 26014402 | 17732805 | 19730260
MCR024246 | HPR188 | 2021-02-01 | Labor | 41167955 | 45248148 | 81833154
MCR024247 | HPR188 | 2021-02-01 | Material | 79709690 | 87609788 | 95196952
MCR024248 | HPR188 | 2021-02-01 | Equipment | 23623885 | 25965269 | 25418813
MCR024249 | HPR188 | 2021-02-01 | Subcontract | 123670226 | 135927292 | 151279255
MCR024250 | HPR188 | 2021-02-01 | Overhead | 23876936 | 26243400 | 19351325
MCR024251 | HPR188 | 2021-03-01 | Labor | 36712027 | 40509531 | 41362077
MCR024252 | HPR188 | 2021-03-01 | Material | 71082089 | 78434844 | 99382359
MCR024253 | HPR188 | 2021-03-01 | Equipment | 21066888 | 23246053 | 26573421
MCR024254 | HPR188 | 2021-03-01 | Subcontract | 110284434 | 121692292 | 125579572
MCR024255 | HPR188 | 2021-03-01 | Overhead | 21292549 | 23495057 | 16437435
MCR024256 | HPR188 | 2021-04-01 | Labor | 31584198 | 54801191 | 63366158
MCR024257 | HPR188 | 2021-04-01 | Material | 61153550 | 106106458 | 107792560
MCR024258 | HPR188 | 2021-04-01 | Equipment | 18124326 | 31447202 | 29864687
MCR024259 | HPR188 | 2021-04-01 | Subcontract | 94880226 | 164625025 | 179378723
MCR024260 | HPR188 | 2021-04-01 | Overhead | 18318468 | 31784054 | 20956769
MCR024261 | HPR188 | 2021-05-01 | Labor | 25903625 | 59121354 | 58100373
MCR024262 | HPR188 | 2021-05-01 | Material | 50154785 | 114471190 | 130070574
MCR024263 | HPR188 | 2021-05-01 | Equipment | 14864577 | 33926292 | 38368017
MCR024264 | HPR188 | 2021-05-01 | Subcontract | 77815553 | 177602974 | 235078031
MCR024265 | HPR188 | 2021-05-01 | Overhead | 15023802 | 34289699 | 19330688
MCR024266 | HPR188 | 2021-06-01 | Labor | 19820774 | 23602784 | 30249646
MCR024267 | HPR188 | 2021-06-01 | Material | 38377125 | 45699880 | 56376429
MCR024268 | HPR188 | 2021-06-01 | Equipment | 11373985 | 13544259 | 12540192
MCR024269 | HPR188 | 2021-06-01 | Subcontract | 59542419 | 70903732 | 92310957
MCR024270 | HPR188 | 2021-06-01 | Overhead | 11495819 | 13689341 | 18989075
MCR024271 | HPR188 | 2021-07-01 | Labor | 13539242 | 22123385 | 22931000
MCR024272 | HPR188 | 2021-07-01 | Material | 26214777 | 42835458 | 44465096
MCR024273 | HPR188 | 2021-07-01 | Equipment | 7769380 | 12695319 | 12587293
MCR024274 | HPR188 | 2021-07-01 | Subcontract | 40672438 | 66459558 | 100406874
MCR024275 | HPR188 | 2021-07-01 | Overhead | 7852603 | 12831307 | 18954272
MCR024276 | HPR188 | 2021-08-01 | Labor | 7370362 | 16214612 | 17008849
MCR024277 | HPR188 | 2021-08-01 | Material | 14270548 | 31394849 | 38393854
MCR024278 | HPR188 | 2021-08-01 | Equipment | 4229420 | 9304619 | 10394693
MCR024279 | HPR188 | 2021-08-01 | Subcontract | 22140871 | 48709361 | 84566065
MCR024280 | HPR188 | 2021-08-01 | Overhead | 4274724 | 9404287 | 19315694
MCR024281 | HPR188 | 2021-09-01 | Labor | 1962538 | 14921272 | 15992090
MCR024282 | HPR188 | 2021-09-01 | Material | 3799881 | 28890673 | 40648949
MCR024283 | HPR188 | 2021-09-01 | Equipment | 1126186 | 8562446 | 8288266
MCR024284 | HPR188 | 2021-09-01 | Subcontract | 5895546 | 44824113 | 100160923
MCR024285 | HPR188 | 2021-09-01 | Overhead | 1138250 | 8654164 | 18141347
MCR024286 | HPR188 | 2021-10-01 | Labor | 0 | 11734501 | 15104864
MCR024287 | HPR188 | 2021-10-01 | Material | 0 | 22720425 | 23478189
MCR024288 | HPR188 | 2021-10-01 | Equipment | 0 | 6733745 | 6235453
MCR024289 | HPR188 | 2021-10-01 | Subcontract | 0 | 35250922 | 57627083
MCR024290 | HPR188 | 2021-10-01 | Overhead | 0 | 6805874 | 18178655
MCR024291 | HPR188 | 2021-11-01 | Labor | 0 | 5088130 | 4715714
MCR024292 | HPR188 | 2021-11-01 | Material | 0 | 9851674 | 12019926
MCR024293 | HPR188 | 2021-11-01 | Equipment | 0 | 2919781 | 3594534
MCR024294 | HPR188 | 2021-11-01 | Subcontract | 0 | 15284952 | 52845772
MCR024295 | HPR188 | 2021-11-01 | Overhead | 0 | 2951056 | 19665038
MCR024296 | HPR188 | 2021-12-01 | Labor | 0 | 1221463 | 1378734
MCR024297 | HPR188 | 2021-12-01 | Material | 0 | 2365006 | 3218249
MCR024298 | HPR188 | 2021-12-01 | Equipment | 0 | 700927 | 590549
MCR024299 | HPR188 | 2021-12-01 | Subcontract | 0 | 3669326 | 57691091
MCR024300 | HPR188 | 2021-12-01 | Overhead | 0 | 708435 | 19601013
MCR024301 | HPR189 | 2021-03-01 | Labor | 6559867 | 2610808 | 2585042
MCR024302 | HPR189 | 2021-03-01 | Material | 15438082 | 6144311 | 6411821
MCR024303 | HPR189 | 2021-03-01 | Equipment | 2885778 | 1148531 | 1264557
MCR024304 | HPR189 | 2021-03-01 | Subcontract | 17657775 | 7027743 | 6767772
MCR024305 | HPR189 | 2021-03-01 | Overhead | 3728251 | 1483833 | 20346488
MCR024306 | HPR189 | 2021-04-01 | Labor | 18448670 | 13390948 | 13624857
MCR024307 | HPR189 | 2021-04-01 | Material | 43417354 | 31514443 | 34290308
MCR024308 | HPR189 | 2021-04-01 | Equipment | 8115829 | 5890867 | 6021471
MCR024309 | HPR189 | 2021-04-01 | Subcontract | 49659918 | 36045602 | 35198554
MCR024310 | HPR189 | 2021-04-01 | Overhead | 10485164 | 7610646 | 19327665
MCR024311 | HPR189 | 2021-05-01 | Labor | 28526617 | 24300462 | 24069562
MCR024312 | HPR189 | 2021-05-01 | Material | 67134934 | 57189043 | 62928801
MCR024313 | HPR189 | 2021-05-01 | Equipment | 12549260 | 10690115 | 10785850
MCR024314 | HPR189 | 2021-05-01 | Subcontract | 76787622 | 65411707 | 61145958
MCR024315 | HPR189 | 2021-05-01 | Overhead | 16212890 | 13810986 | 18893741
MCR024316 | HPR189 | 2021-06-01 | Labor | 36843237 | 21522246 | 23158754
MCR024317 | HPR189 | 2021-06-01 | Material | 86707382 | 50650750 | 50367183
MCR024318 | HPR189 | 2021-06-01 | Equipment | 16207858 | 9467939 | 10823436
MCR024319 | HPR189 | 2021-06-01 | Subcontract | 99174205 | 57933335 | 62209117
MCR024320 | HPR189 | 2021-06-01 | Overhead | 20939578 | 12232007 | 20189302
MCR024321 | HPR189 | 2021-07-01 | Labor | 43451032 | 23482605 | 23065162
MCR024322 | HPR189 | 2021-07-01 | Material | 102258260 | 55264286 | 55980664
MCR024323 | HPR189 | 2021-07-01 | Equipment | 19114720 | 10330328 | 10593329
MCR024324 | HPR189 | 2021-07-01 | Subcontract | 116960994 | 63210207 | 57593239
MCR024325 | HPR189 | 2021-07-01 | Overhead | 24695070 | 13346163 | 20756175
MCR024326 | HPR189 | 2021-08-01 | Labor | 48405919 | 28039912 | 29112945
MCR024327 | HPR189 | 2021-08-01 | Material | 113919158 | 65989516 | 60913651
MCR024328 | HPR189 | 2021-08-01 | Equipment | 21294445 | 12335152 | 13261094
MCR024329 | HPR189 | 2021-08-01 | Subcontract | 130298500 | 75477515 | 72498022
MCR024330 | HPR189 | 2021-08-01 | Overhead | 27511142 | 15936274 | 19906754
MCR024331 | HPR189 | 2021-09-01 | Labor | 51767759 | 61170301 | 56842882
MCR024332 | HPR189 | 2021-09-01 | Material | 121830960 | 143959030 | 161414161
MCR024333 | HPR189 | 2021-09-01 | Equipment | 22773366 | 26909676 | 29874676
MCR024334 | HPR189 | 2021-09-01 | Subcontract | 139347865 | 164657518 | 164611786
MCR024335 | HPR189 | 2021-09-01 | Overhead | 29421819 | 34765683 | 19517454
MCR024336 | HPR189 | 2021-10-01 | Labor | 53601047 | 44029320 | 56484650
MCR024337 | HPR189 | 2021-10-01 | Material | 126145443 | 103619210 | 96224842
MCR024338 | HPR189 | 2021-10-01 | Equipment | 23579854 | 19369117 | 18149545
MCR024339 | HPR189 | 2021-10-01 | Subcontract | 144282686 | 118517621 | 114040273
MCR024340 | HPR189 | 2021-10-01 | Overhead | 30463755 | 25023735 | 20338079
MCR024341 | HPR189 | 2021-11-01 | Labor | 53975771 | 19645350 | 16934102
MCR024342 | HPR189 | 2021-11-01 | Material | 127027324 | 46233639 | 56481534
MCR024343 | HPR189 | 2021-11-01 | Equipment | 23744701 | 8642266 | 8477412
MCR024344 | HPR189 | 2021-11-01 | Subcontract | 145291364 | 52881130 | 41551609
MCR024345 | HPR189 | 2021-11-01 | Overhead | 30676726 | 11165288 | 21037897
MCR024346 | HPR189 | 2021-12-01 | Labor | 52968562 | 41411903 | 48182010
MCR024347 | HPR189 | 2021-12-01 | Material | 124656946 | 97459344 | 83609566
MCR024348 | HPR189 | 2021-12-01 | Equipment | 23301616 | 18217679 | 17783620
MCR024349 | HPR189 | 2021-12-01 | Subcontract | 142580172 | 111472088 | 86260168
MCR024350 | HPR189 | 2021-12-01 | Overhead | 30104287 | 23536146 | 19636747
MCR024351 | HPR189 | 2022-01-01 | Labor | 50664232 | 47055808 | 53385306
MCR024352 | HPR189 | 2022-01-01 | Material | 119233904 | 110741789 | 137828521
MCR024353 | HPR189 | 2022-01-01 | Equipment | 22287908 | 20700512 | 19584415
MCR024354 | HPR189 | 2022-01-01 | Subcontract | 136377403 | 126664288 | 133366883
MCR024355 | HPR189 | 2022-01-01 | Overhead | 28794638 | 26743817 | 19168399
MCR024356 | HPR189 | 2022-02-01 | Labor | 47157908 | 44378416 | 45685334
MCR024357 | HPR189 | 2022-02-01 | Material | 110982072 | 104440778 | 104578922
MCR024358 | HPR189 | 2022-02-01 | Equipment | 20745427 | 19522690 | 23330867
MCR024359 | HPR189 | 2022-02-01 | Subcontract | 126939119 | 119457315 | 122654028
MCR024360 | HPR189 | 2022-02-01 | Overhead | 26801845 | 25222141 | 18266619
MCR024361 | HPR189 | 2022-03-01 | Labor | 42558125 | 46977494 | 52220090
MCR024362 | HPR189 | 2022-03-01 | Material | 100156878 | 110557483 | 99949516
MCR024363 | HPR189 | 2022-03-01 | Equipment | 18721918 | 20666060 | 21013391
MCR024364 | HPR189 | 2022-03-01 | Subcontract | 114557475 | 126453483 | 117872334
MCR024365 | HPR189 | 2022-03-01 | Overhead | 24187592 | 26699308 | 19870989
MCR024366 | HPR189 | 2022-04-01 | Labor | 36991517 | 47452249 | 57170418
MCR024367 | HPR189 | 2022-04-01 | Material | 87056348 | 111674779 | 134791228
MCR024368 | HPR189 | 2022-04-01 | Equipment | 16273089 | 20874912 | 21466028
MCR024369 | HPR189 | 2022-04-01 | Subcontract | 99573345 | 127731424 | 115247304
MCR024370 | HPR189 | 2022-04-01 | Overhead | 21023853 | 26969132 | 20288919
MCR024371 | HPR189 | 2022-05-01 | Labor | 30610414 | 60615506 | 63288729
MCR024372 | HPR189 | 2022-05-01 | Material | 72038971 | 142653369 | 128698490
MCR024373 | HPR189 | 2022-05-01 | Equipment | 13465952 | 26665614 | 30820384
MCR024374 | HPR189 | 2022-05-01 | Subcontract | 82396764 | 163164128 | 163780613
MCR024375 | HPR189 | 2022-05-01 | Overhead | 17397200 | 34450370 | 20290589
MCR024376 | HPR189 | 2022-06-01 | Labor | 23606260 | 35213102 | 37300844
MCR024377 | HPR189 | 2022-06-01 | Material | 55555297 | 82871002 | 90076713
MCR024378 | HPR189 | 2022-06-01 | Equipment | 10384726 | 15490739 | 13736705
MCR024379 | HPR189 | 2022-06-01 | Subcontract | 63543060 | 94786228 | 93011908
MCR024380 | HPR189 | 2022-06-01 | Overhead | 13416441 | 20013104 | 18662386
MCR024381 | HPR189 | 2022-07-01 | Labor | 16236612 | 16110978 | 20529184
MCR024382 | HPR189 | 2022-07-01 | Material | 38211468 | 37915797 | 47818081
MCR024383 | HPR189 | 2022-07-01 | Equipment | 7142714 | 7087446 | 8054483
MCR024384 | HPR189 | 2022-07-01 | Subcontract | 43705528 | 43367346 | 41342541
MCR024385 | HPR189 | 2022-07-01 | Overhead | 9227957 | 9156554 | 20080068
MCR024386 | HPR189 | 2022-08-01 | Labor | 8892452 | 9667339 | 10069409
MCR024387 | HPR189 | 2022-08-01 | Material | 20927620 | 22751248 | 22076740
MCR024388 | HPR189 | 2022-08-01 | Equipment | 3911915 | 4252798 | 4946192
MCR024389 | HPR189 | 2022-08-01 | Subcontract | 23936601 | 26022432 | 18483818
MCR024390 | HPR189 | 2022-08-01 | Overhead | 5053959 | 5494360 | 19531558
MCR024391 | HPR189 | 2022-09-01 | Labor | 2379536 | 28138985 | 31865986
MCR024392 | HPR189 | 2022-09-01 | Material | 5600034 | 66222676 | 78675623
MCR024393 | HPR189 | 2022-09-01 | Equipment | 1046792 | 12378735 | 13299973
MCR024394 | HPR189 | 2022-09-01 | Subcontract | 6405209 | 75744199 | 85095419
MCR024395 | HPR189 | 2022-09-01 | Overhead | 1352392 | 15992582 | 19911917
MCR024396 | HPR189 | 2022-10-01 | Labor | 0 | 18914286 | 21166105
MCR024397 | HPR189 | 2022-10-01 | Material | 0 | 44513143 | 39407999
MCR024398 | HPR189 | 2022-10-01 | Equipment | 0 | 8320661 | 8181208
MCR024399 | HPR189 | 2022-10-01 | Subcontract | 0 | 50913260 | 44214478
MCR024400 | HPR189 | 2022-10-01 | Overhead | 0 | 10749793 | 18294836
MCR024401 | HPR189 | 2022-11-01 | Labor | 0 | 8242393 | 8688689
MCR024402 | HPR189 | 2022-11-01 | Material | 0 | 19397761 | 19870872
MCR024403 | HPR189 | 2022-11-01 | Equipment | 0 | 3625945 | 3684652
MCR024404 | HPR189 | 2022-11-01 | Subcontract | 0 | 22186779 | 17402495
MCR024405 | HPR189 | 2022-11-01 | Overhead | 0 | 4684502 | 18552501
MCR024406 | HPR189 | 2022-12-01 | Labor | 0 | 6649014 | 6688526
MCR024407 | HPR189 | 2022-12-01 | Material | 0 | 15647882 | 16657342
MCR024408 | HPR189 | 2022-12-01 | Equipment | 0 | 2924995 | 3279486
MCR024409 | HPR189 | 2022-12-01 | Subcontract | 0 | 17897741 | 18332761
MCR024410 | HPR189 | 2022-12-01 | Overhead | 0 | 3778918 | 20403255
MCR024411 | HPR189 | 2023-01-01 | Labor | 0 | 3091413 | 3973319
MCR024412 | HPR189 | 2023-01-01 | Material | 0 | 7275374 | 8006926
MCR024413 | HPR189 | 2023-01-01 | Equipment | 0 | 1359956 | 1495601
MCR024414 | HPR189 | 2023-01-01 | Subcontract | 0 | 8321430 | 6409050
MCR024415 | HPR189 | 2023-01-01 | Overhead | 0 | 1756981 | 19178693
MCR024416 | HPR189 | 2023-02-01 | Labor | 0 | 1534699 | 1212113
MCR024417 | HPR189 | 2023-02-01 | Material | 0 | 3611783 | 3491360
MCR024418 | HPR189 | 2023-02-01 | Equipment | 0 | 675136 | 778215
MCR024419 | HPR189 | 2023-02-01 | Subcontract | 0 | 4131087 | 4324182
MCR024420 | HPR189 | 2023-02-01 | Overhead | 0 | 872235 | 20312322
MCR024421 | HPR190 | 2018-05-01 | Labor | 2006432 | 2410279 | 2376733
MCR024422 | HPR190 | 2018-05-01 | Material | 7236318 | 8692816 | 7872737
MCR024423 | HPR190 | 2018-05-01 | Equipment | 3646229 | 4380127 | 4569557
MCR024424 | HPR190 | 2018-05-01 | Subcontract | 4160243 | 4997600 | 5536133
MCR024425 | HPR190 | 2018-05-01 | Overhead | 1796967 | 2158653 | 10650274
MCR024426 | HPR190 | 2018-06-01 | Labor | 5695387 | 4898449 | 5890852
MCR024427 | HPR190 | 2018-06-01 | Material | 20540756 | 17666553 | 18589128
MCR024428 | HPR190 | 2018-06-01 | Equipment | 10350055 | 8901805 | 9541329
MCR024429 | HPR190 | 2018-06-01 | Subcontract | 11809117 | 10156705 | 9557211
MCR024430 | HPR190 | 2018-06-01 | Overhead | 5100806 | 4387067 | 11593096
MCR024431 | HPR190 | 2018-07-01 | Labor | 8906463 | 9613898 | 9611244
MCR024432 | HPR190 | 2018-07-01 | Material | 32121695 | 34673104 | 39576342
MCR024433 | HPR190 | 2018-07-01 | Equipment | 16185447 | 17471048 | 15923447
MCR024434 | HPR190 | 2018-07-01 | Subcontract | 18467132 | 19933967 | 21242449
MCR024435 | HPR190 | 2018-07-01 | Overhead | 7976656 | 8610238 | 11324729
MCR024436 | HPR190 | 2018-08-01 | Labor | 11650714 | 5653094 | 5610690
MCR024437 | HPR190 | 2018-08-01 | Material | 42019003 | 20388226 | 17023967
MCR024438 | HPR190 | 2018-08-01 | Equipment | 21172492 | 10273199 | 11319066
MCR024439 | HPR190 | 2018-08-01 | Subcontract | 24157208 | 11721426 | 12622307
MCR024440 | HPR190 | 2018-08-01 | Overhead | 10434416 | 5062929 | 11494492
MCR024441 | HPR190 | 2018-09-01 | Labor | 13939751 | 9655437 | 10144480
MCR024442 | HPR190 | 2018-09-01 | Material | 50274553 | 34822917 | 30998622
MCR024443 | HPR190 | 2018-09-01 | Equipment | 25332290 | 17546536 | 15428960
MCR024444 | HPR190 | 2018-09-01 | Subcontract | 28903419 | 20020096 | 19695356
MCR024445 | HPR190 | 2018-09-01 | Overhead | 12484485 | 8647440 | 10424502
MCR024446 | HPR190 | 2018-10-01 | Labor | 15785808 | 14519444 | 16520856
MCR024447 | HPR190 | 2018-10-01 | Material | 56932472 | 52365251 | 48727649
MCR024448 | HPR190 | 2018-10-01 | Equipment | 28687076 | 26385749 | 29518007
MCR024449 | HPR190 | 2018-10-01 | Subcontract | 32731133 | 30105385 | 31851821
MCR024450 | HPR190 | 2018-10-01 | Overhead | 14137821 | 13003660 | 10305212
MCR024451 | HPR190 | 2018-11-01 | Labor | 17201826 | 14179673 | 13804761
MCR024452 | HPR190 | 2018-11-01 | Material | 62039424 | 51139849 | 58631369
MCR024453 | HPR190 | 2018-11-01 | Equipment | 31260362 | 25768295 | 28453020
MCR024454 | HPR190 | 2018-11-01 | Subcontract | 35667179 | 29400888 | 28047990
MCR024455 | HPR190 | 2018-11-01 | Overhead | 15406010 | 12699361 | 10402048
MCR024456 | HPR190 | 2018-12-01 | Labor | 18201544 | 12319605 | 12539256
MCR024457 | HPR190 | 2018-12-01 | Material | 65644968 | 44431399 | 39529055
MCR024458 | HPR190 | 2018-12-01 | Equipment | 33077119 | 22388048 | 17824083
MCR024459 | HPR190 | 2018-12-01 | Subcontract | 37740048 | 25544123 | 27137442
MCR024460 | HPR190 | 2018-12-01 | Overhead | 16301361 | 11033477 | 11146165
MCR024461 | HPR190 | 2019-01-01 | Labor | 18799625 | 18872899 | 20345285
MCR024462 | HPR190 | 2019-01-01 | Material | 67801984 | 68066252 | 79940446
MCR024463 | HPR190 | 2019-01-01 | Equipment | 34163995 | 34297153 | 36079234
MCR024464 | HPR190 | 2019-01-01 | Subcontract | 38980141 | 39132072 | 41372727
MCR024465 | HPR190 | 2019-01-01 | Overhead | 16837005 | 16902629 | 11837128
MCR024466 | HPR190 | 2019-02-01 | Labor | 19011801 | 24154375 | 25547549
MCR024467 | HPR190 | 2019-02-01 | Material | 68567209 | 87114214 | 68250077
MCR024468 | HPR190 | 2019-02-01 | Equipment | 34549575 | 43895021 | 47949347
MCR024469 | HPR190 | 2019-02-01 | Subcontract | 39420078 | 50082964 | 47740118
MCR024470 | HPR190 | 2019-02-01 | Overhead | 17027030 | 21632736 | 10897898
MCR024471 | HPR190 | 2019-03-01 | Labor | 18855060 | 19888768 | 24139900
MCR024472 | HPR190 | 2019-03-01 | Material | 68001911 | 71730042 | 87177071
MCR024473 | HPR190 | 2019-03-01 | Equipment | 34264734 | 36143260 | 30829685
MCR024474 | HPR190 | 2019-03-01 | Subcontract | 39095081 | 41238427 | 42652681
MCR024475 | HPR190 | 2019-03-01 | Overhead | 16886652 | 17812444 | 11128207
MCR024476 | HPR190 | 2019-04-01 | Labor | 18347885 | 14565586 | 15117008
MCR024477 | HPR190 | 2019-04-01 | Material | 66172755 | 52531665 | 48773759
MCR024478 | HPR190 | 2019-04-01 | Equipment | 33343060 | 26469602 | 27995971
MCR024479 | HPR190 | 2019-04-01 | Subcontract | 38043479 | 30201059 | 33051142
MCR024480 | HPR190 | 2019-04-01 | Overhead | 16432424 | 13044985 | 11689509
MCR024481 | HPR190 | 2019-05-01 | Labor | 17510575 | 19780485 | 17674206
MCR024482 | HPR190 | 2019-05-01 | Material | 63152948 | 71339515 | 74760275
MCR024483 | HPR190 | 2019-05-01 | Equipment | 31821443 | 35946482 | 38009667
MCR024484 | HPR190 | 2019-05-01 | Subcontract | 36307357 | 41013909 | 41185157
MCR024485 | HPR190 | 2019-05-01 | Overhead | 15682527 | 17715466 | 11368432
MCR024486 | HPR190 | 2019-06-01 | Labor | 16365670 | 19737572 | 32370803
MCR024487 | HPR190 | 2019-06-01 | Material | 59023776 | 71184746 | 84528750
MCR024488 | HPR190 | 2019-06-01 | Equipment | 29740840 | 35868497 | 31226762
MCR024489 | HPR190 | 2019-06-01 | Subcontract | 33933448 | 40924930 | 41459034
MCR024490 | HPR190 | 2019-06-01 | Overhead | 14657146 | 17677033 | 11079593
MCR024491 | HPR190 | 2019-07-01 | Labor | 14938543 | 10352455 | 27096015
MCR024492 | HPR190 | 2019-07-01 | Material | 53876758 | 37336753 | 64214448
MCR024493 | HPR190 | 2019-07-01 | Equipment | 27147366 | 18813205 | 22022356
MCR024494 | HPR190 | 2019-07-01 | Subcontract | 30974368 | 21465329 | 22445258
MCR024495 | HPR190 | 2019-07-01 | Overhead | 13379007 | 9271691 | 10946970
MCR024496 | HPR190 | 2019-08-01 | Labor | 13258272 | 7737877 | 8099852
MCR024497 | HPR190 | 2019-08-01 | Material | 47816759 | 27907122 | 24894808
MCR024498 | HPR190 | 2019-08-01 | Equipment | 24093860 | 14061812 | 13393983
MCR024499 | HPR190 | 2019-08-01 | Subcontract | 27490405 | 16044126 | 13316940
MCR024500 | HPR190 | 2019-08-01 | Overhead | 11874151 | 6930068 | 10811933
MCR024501 | HPR190 | 2019-09-01 | Labor | 11358951 | 19740168 | 21443742
MCR024502 | HPR190 | 2019-09-01 | Material | 40966741 | 71194106 | 68960983
MCR024503 | HPR190 | 2019-09-01 | Equipment | 20642280 | 35873214 | 36459552
MCR024504 | HPR190 | 2019-09-01 | Subcontract | 23552251 | 40930311 | 41630899
MCR024505 | HPR190 | 2019-09-01 | Overhead | 10173112 | 17679357 | 10780606
MCR024506 | HPR190 | 2019-10-01 | Labor | 9281828 | 8415460 | 9805058
MCR024507 | HPR190 | 2019-10-01 | Material | 33475474 | 30350864 | 32184788
MCR024508 | HPR190 | 2019-10-01 | Equipment | 16867588 | 15293162 | 17223307
MCR024509 | HPR190 | 2019-10-01 | Subcontract | 19245435 | 17449061 | 17807112
MCR024510 | HPR190 | 2019-10-01 | Overhead | 8312835 | 7536913 | 11428080
MCR024511 | HPR190 | 2019-11-01 | Labor | 7079107 | 13761897 | 15013976
MCR024512 | HPR190 | 2019-11-01 | Material | 25531226 | 49633111 | 45335207
MCR024513 | HPR190 | 2019-11-01 | Equipment | 12864648 | 25009081 | 27229204
MCR024514 | HPR190 | 2019-11-01 | Subcontract | 14678196 | 28534647 | 33388359
MCR024515 | HPR190 | 2019-11-01 | Overhead | 6340071 | 12325199 | 10712816
MCR024516 | HPR190 | 2019-12-01 | Labor | 4821609 | 7823188 | 9327571
MCR024517 | HPR190 | 2019-12-01 | Material | 17389424 | 28214799 | 31861497
MCR024518 | HPR190 | 2019-12-01 | Equipment | 8762165 | 14216844 | 14010888
MCR024519 | HPR190 | 2019-12-01 | Subcontract | 9997380 | 16221013 | 14125852
MCR024520 | HPR190 | 2019-12-01 | Overhead | 4318248 | 7006472 | 10461570
MCR024521 | HPR190 | 2020-01-01 | Labor | 2617994 | 4980380 | 5578358
MCR024522 | HPR190 | 2020-01-01 | Material | 9441955 | 17962041 | 18938218
MCR024523 | HPR190 | 2020-01-01 | Equipment | 4757603 | 9050695 | 9447133
MCR024524 | HPR190 | 2020-01-01 | Subcontract | 5428289 | 10326584 | 9952363
MCR024525 | HPR190 | 2020-01-01 | Overhead | 2344684 | 4460444 | 10975300
MCR024526 | HPR190 | 2020-02-01 | Labor | 695635 | 2760738 | 2999309
MCR024527 | HPR190 | 2020-02-01 | Material | 2508849 | 9956768 | 8886981
MCR024528 | HPR190 | 2020-02-01 | Equipment | 1264156 | 5017006 | 4121554
MCR024529 | HPR190 | 2020-02-01 | Subcontract | 1442366 | 5724260 | 5369678
MCR024530 | HPR190 | 2020-02-01 | Overhead | 623013 | 2472526 | 11608596
MCR024531 | HPR190 | 2020-03-01 | Labor | 0 | 508753 | 785103
MCR024532 | HPR190 | 2020-03-01 | Material | 0 | 1834847 | 2171147
MCR024533 | HPR190 | 2020-03-01 | Equipment | 0 | 924541 | 1029657
MCR024534 | HPR190 | 2020-03-01 | Subcontract | 0 | 1054874 | 796978
MCR024535 | HPR190 | 2020-03-01 | Overhead | 0 | 455640 | 11432466
MCR024536 | HPR191 | 2017-10-01 | Labor | 7609569 | 4991614 | 5194470
MCR024537 | HPR191 | 2017-10-01 | Material | 20556219 | 13484166 | 13510816
MCR024538 | HPR191 | 2017-10-01 | Equipment | 6177246 | 4052059 | 4075575
MCR024539 | HPR191 | 2017-10-01 | Subcontract | 20586371 | 13503945 | 11384622
MCR024540 | HPR191 | 2017-10-01 | Overhead | 5035865 | 3303353 | 34156438
MCR024541 | HPR191 | 2017-11-01 | Labor | 21750818 | 14724096 | 12583379
MCR024542 | HPR191 | 2017-11-01 | Material | 58756882 | 39775145 | 44987504
MCR024543 | HPR191 | 2017-11-01 | Equipment | 17656736 | 11952629 | 11031858
MCR024544 | HPR191 | 2017-11-01 | Subcontract | 58843068 | 39833488 | 43815550
MCR024545 | HPR191 | 2017-11-01 | Overhead | 14394269 | 9744120 | 32418334
MCR024546 | HPR191 | 2017-12-01 | Labor | 34298418 | 30048317 | 36272246
MCR024547 | HPR191 | 2017-12-01 | Material | 92652519 | 81171449 | 72456617
MCR024548 | HPR191 | 2017-12-01 | Equipment | 27842543 | 24392424 | 24087469
MCR024549 | HPR191 | 2017-12-01 | Subcontract | 92788423 | 81290512 | 73220270
MCR024550 | HPR191 | 2017-12-01 | Overhead | 22698026 | 19885392 | 35071314
MCR024551 | HPR191 | 2018-01-01 | Labor | 45284305 | 27739830 | 28664304
MCR024552 | HPR191 | 2018-01-01 | Material | 122329403 | 74935385 | 75582912
MCR024553 | HPR191 | 2018-01-01 | Equipment | 36760595 | 22518456 | 23988100
MCR024554 | HPR191 | 2018-01-01 | Subcontract | 122508838 | 75045302 | 81238770
MCR024555 | HPR191 | 2018-01-01 | Overhead | 29968273 | 18357680 | 36234732
MCR024556 | HPR191 | 2018-02-01 | Labor | 54741802 | 27529279 | 22753294
MCR024557 | HPR191 | 2018-02-01 | Material | 147877548 | 74366611 | 83408824
MCR024558 | HPR191 | 2018-02-01 | Equipment | 44437939 | 22347537 | 22943176
MCR024559 | HPR191 | 2018-02-01 | Subcontract | 148094457 | 74475693 | 65321778
MCR024560 | HPR191 | 2018-02-01 | Overhead | 36227061 | 18218342 | 37390697
MCR024561 | HPR191 | 2018-03-01 | Labor | 62705757 | 42315696 | 47495914
MCR024562 | HPR191 | 2018-03-01 | Material | 169391091 | 114310109 | 102069419
MCR024563 | HPR191 | 2018-03-01 | Equipment | 50902866 | 34350757 | 36858477
MCR024564 | HPR191 | 2018-03-01 | Subcontract | 169639557 | 114477781 | 118978325
MCR024565 | HPR191 | 2018-03-01 | Overhead | 41497451 | 28003705 | 35135525
MCR024566 | HPR191 | 2018-04-01 | Labor | 69212712 | 41846370 | 47557328
MCR024567 | HPR191 | 2018-04-01 | Material | 186968746 | 113042288 | 124937623
MCR024568 | HPR191 | 2018-04-01 | Equipment | 56185039 | 33969770 | 28236067
MCR024569 | HPR191 | 2018-04-01 | Subcontract | 187242995 | 113208100 | 126390169
MCR024570 | HPR191 | 2018-04-01 | Overhead | 45803627 | 27693114 | 34827038
MCR024571 | HPR191 | 2018-05-01 | Labor | 74301098 | 44456465 | 39315933
MCR024572 | HPR191 | 2018-05-01 | Material | 200714331 | 120093106 | 114545949
MCR024573 | HPR191 | 2018-05-01 | Equipment | 60315656 | 36088576 | 41854983
MCR024574 | HPR191 | 2018-05-01 | Subcontract | 201008742 | 120269261 | 108197945
MCR024575 | HPR191 | 2018-05-01 | Overhead | 49171022 | 29420424 | 33011451
MCR024576 | HPR191 | 2018-06-01 | Labor | 78011470 | 64545687 | 66968269
MCR024577 | HPR191 | 2018-06-01 | Material | 210737396 | 174361411 | 186970087
MCR024578 | HPR191 | 2018-06-01 | Equipment | 63327637 | 52396472 | 55401011
MCR024579 | HPR191 | 2018-06-01 | Subcontract | 211046509 | 174617167 | 201746330
MCR024580 | HPR191 | 2018-06-01 | Overhead | 51626474 | 42715081 | 34108806
MCR024581 | HPR191 | 2018-07-01 | Labor | 80386780 | 57573171 | 60436768
MCR024582 | HPR191 | 2018-07-01 | Material | 217153975 | 155526107 | 175975295
MCR024583 | HPR191 | 2018-07-01 | Equipment | 65255850 | 46736369 | 41344666
MCR024584 | HPR191 | 2018-07-01 | Subcontract | 217472500 | 155754235 | 155124030
MCR024585 | HPR191 | 2018-07-01 | Overhead | 53198408 | 38100805 | 35482343
MCR024586 | HPR191 | 2018-08-01 | Labor | 81472721 | 46734335 | 42124572
MCR024587 | HPR191 | 2018-08-01 | Material | 220087496 | 126246463 | 121119117
MCR024588 | HPR191 | 2018-08-01 | Equipment | 66137388 | 37937690 | 38925912
MCR024589 | HPR191 | 2018-08-01 | Subcontract | 220410323 | 126431643 | 114299572
MCR024590 | HPR191 | 2018-08-01 | Overhead | 53917063 | 30927874 | 35734197
MCR024591 | HPR191 | 2018-09-01 | Labor | 81318132 | 78643732 | 87606086
MCR024592 | HPR191 | 2018-09-01 | Material | 219669895 | 212445366 | 230966692
MCR024593 | HPR191 | 2018-09-01 | Equipment | 66011897 | 63840890 | 73177908
MCR024594 | HPR191 | 2018-09-01 | Subcontract | 219992111 | 212756984 | 204925677
MCR024595 | HPR191 | 2018-09-01 | Overhead | 53814759 | 52044893 | 35498234
MCR024596 | HPR191 | 2018-10-01 | Labor | 79975520 | 76517492 | 80950823
MCR024597 | HPR191 | 2018-10-01 | Material | 216043012 | 206701617 | 229919429
MCR024598 | HPR191 | 2018-10-01 | Equipment | 64922001 | 62114865 | 61510704
MCR024599 | HPR191 | 2018-10-01 | Subcontract | 216359908 | 207004810 | 210208145
MCR024600 | HPR191 | 2018-10-01 | Overhead | 52926245 | 50637788 | 32810546
MCR024601 | HPR191 | 2018-11-01 | Labor | 77501707 | 68759697 | 82255028
MCR024602 | HPR191 | 2018-11-01 | Material | 209360342 | 185744987 | 168610261
MCR024603 | HPR191 | 2018-11-01 | Equipment | 62913825 | 55817293 | 59481903
MCR024604 | HPR191 | 2018-11-01 | Subcontract | 209667435 | 186017441 | 167672082
MCR024605 | HPR191 | 2018-11-01 | Overhead | 51289123 | 45503831 | 34569124
MCR024606 | HPR191 | 2018-12-01 | Labor | 73958669 | 71572139 | 60906072
MCR024607 | HPR191 | 2018-12-01 | Material | 199789304 | 193342417 | 221269545
MCR024608 | HPR191 | 2018-12-01 | Equipment | 60037680 | 58100359 | 56997429
MCR024609 | HPR191 | 2018-12-01 | Subcontract | 200082358 | 193626015 | 193957627
MCR024610 | HPR191 | 2018-12-01 | Overhead | 48944409 | 47365050 | 31340790
MCR024611 | HPR191 | 2019-01-01 | Labor | 69414641 | 68222625 | 82338461
MCR024612 | HPR191 | 2019-01-01 | Material | 187514230 | 184294162 | 184839171
MCR024613 | HPR191 | 2019-01-01 | Equipment | 56348959 | 55381313 | 58601238
MCR024614 | HPR191 | 2019-01-01 | Subcontract | 187789279 | 184564487 | 207463368
MCR024615 | HPR191 | 2019-01-01 | Overhead | 45937260 | 45148407 | 35781740
MCR024616 | HPR191 | 2019-02-01 | Labor | 63945619 | 42893179 | 47545647
MCR024617 | HPR191 | 2019-02-01 | Material | 172740409 | 115870099 | 107297844
MCR024618 | HPR191 | 2019-02-01 | Equipment | 51909353 | 34819542 | 41973385
MCR024619 | HPR191 | 2019-02-01 | Subcontract | 172993787 | 116040059 | 109371314
MCR024620 | HPR191 | 2019-02-01 | Overhead | 42317967 | 28385872 | 32436597
MCR024621 | HPR191 | 2019-03-01 | Labor | 57637448 | 71698582 | 74366082
MCR024622 | HPR191 | 2019-03-01 | Material | 155699742 | 193683987 | 223913021
MCR024623 | HPR191 | 2019-03-01 | Equipment | 46788547 | 58203002 | 50868121
MCR024624 | HPR191 | 2019-03-01 | Subcontract | 155928125 | 193968086 | 189823163
MCR024625 | HPR191 | 2019-03-01 | Overhead | 38143343 | 47448728 | 35440441
MCR024626 | HPR191 | 2019-04-01 | Labor | 50588869 | 60494743 | 57631239
MCR024627 | HPR191 | 2019-04-01 | Material | 136658963 | 163418337 | 181680496
MCR024628 | HPR191 | 2019-04-01 | Equipment | 41066699 | 49108024 | 58131041
MCR024629 | HPR191 | 2019-04-01 | Subcontract | 136859417 | 163658041 | 151209246
MCR024630 | HPR191 | 2019-04-01 | Overhead | 33478730 | 40034245 | 33395616
MCR024631 | HPR191 | 2019-05-01 | Labor | 42916166 | 65586054 | 77987268
MCR024632 | HPR191 | 2019-05-01 | Material | 115932197 | 177171822 | 191157459
MCR024633 | HPR191 | 2019-05-01 | Equipment | 34838202 | 53241014 | 51233826
MCR024634 | HPR191 | 2019-05-01 | Subcontract | 116102249 | 177431700 | 182244534
MCR024635 | HPR191 | 2019-05-01 | Overhead | 28401084 | 43403575 | 32505121
MCR024636 | HPR191 | 2019-06-01 | Labor | 34760742 | 43480240 | 47493179
MCR024637 | HPR191 | 2019-06-01 | Material | 93901425 | 117455966 | 118594297
MCR024638 | HPR191 | 2019-06-01 | Equipment | 28217846 | 35296102 | 35914349
MCR024639 | HPR191 | 2019-06-01 | Subcontract | 94039161 | 117628252 | 112839550
MCR024640 | HPR191 | 2019-06-01 | Overhead | 23003983 | 28774378 | 35688644
MCR024641 | HPR191 | 2019-07-01 | Labor | 26302608 | 19927690 | 20140887
MCR024642 | HPR191 | 2019-07-01 | Material | 71052925 | 53831949 | 59512491
MCR024643 | HPR191 | 2019-07-01 | Equipment | 21351758 | 16176769 | 15042796
MCR024644 | HPR191 | 2019-07-01 | Subcontract | 71157147 | 53910911 | 64067999
MCR024645 | HPR191 | 2019-07-01 | Overhead | 17406555 | 13187758 | 35975642
MCR024646 | HPR191 | 2019-08-01 | Labor | 17787735 | 32083067 | 34613231
MCR024647 | HPR191 | 2019-08-01 | Material | 48051151 | 86668050 | 88298193
MCR024648 | HPR191 | 2019-08-01 | Equipment | 14439610 | 26044180 | 29100998
MCR024649 | HPR191 | 2019-08-01 | Subcontract | 48121633 | 86795176 | 85284410
MCR024650 | HPR191 | 2019-08-01 | Overhead | 11771577 | 21231950 | 35121901
MCR024651 | HPR191 | 2019-09-01 | Labor | 9596858 | 45690277 | 55947959
MCR024652 | HPR191 | 2019-09-01 | Material | 25924609 | 123426080 | 140160409
MCR024653 | HPR191 | 2019-09-01 | Equipment | 7790474 | 37090151 | 43880136
MCR024654 | HPR191 | 2019-09-01 | Subcontract | 25962635 | 123607123 | 121913614
MCR024655 | HPR191 | 2019-09-01 | Overhead | 6351014 | 30236937 | 35491696
MCR024656 | HPR191 | 2019-10-01 | Labor | 2536604 | 50933580 | 62490134
MCR024657 | HPR191 | 2019-10-01 | Material | 6852291 | 137590154 | 145991537
MCR024658 | HPR191 | 2019-10-01 | Equipment | 2059148 | 41346526 | 32812827
MCR024659 | HPR191 | 2019-10-01 | Subcontract | 6862342 | 137791973 | 146096380
MCR024660 | HPR191 | 2019-10-01 | Overhead | 1678675 | 33706853 | 36097048
MCR024661 | HPR191 | 2019-11-01 | Labor | 0 | 20694634 | 20120821
MCR024662 | HPR191 | 2019-11-01 | Material | 0 | 55903744 | 54722590
MCR024663 | HPR191 | 2019-11-01 | Equipment | 0 | 16799353 | 22310469
MCR024664 | HPR191 | 2019-11-01 | Subcontract | 0 | 55985744 | 56770693
MCR024665 | HPR191 | 2019-11-01 | Overhead | 0 | 13695306 | 32060168
MCR024666 | HPR191 | 2019-12-01 | Labor | 0 | 22338338 | 24339300
MCR024667 | HPR191 | 2019-12-01 | Material | 0 | 60343989 | 61838978
MCR024668 | HPR191 | 2019-12-01 | Equipment | 0 | 18133669 | 17692724
MCR024669 | HPR191 | 2019-12-01 | Subcontract | 0 | 60432502 | 53498225
MCR024670 | HPR191 | 2019-12-01 | Overhead | 0 | 14783078 | 33562971
MCR024671 | HPR191 | 2020-01-01 | Labor | 0 | 14799665 | 17726773
MCR024672 | HPR191 | 2020-01-01 | Material | 0 | 39979286 | 46439750
MCR024673 | HPR191 | 2020-01-01 | Equipment | 0 | 12013975 | 12944647
MCR024674 | HPR191 | 2020-01-01 | Subcontract | 0 | 40037929 | 41516560
MCR024675 | HPR191 | 2020-01-01 | Overhead | 0 | 9794131 | 32901814
MCR024676 | HPR191 | 2020-02-01 | Labor | 0 | 19647382 | 22773326
MCR024677 | HPR191 | 2020-02-01 | Material | 0 | 53074735 | 56518844
MCR024678 | HPR191 | 2020-02-01 | Equipment | 0 | 15949222 | 20654848
MCR024679 | HPR191 | 2020-02-01 | Subcontract | 0 | 53152586 | 52380585
MCR024680 | HPR191 | 2020-02-01 | Overhead | 0 | 13002255 | 35047310
MCR024681 | HPR191 | 2020-03-01 | Labor | 0 | 14768481 | 16980544
MCR024682 | HPR191 | 2020-03-01 | Material | 0 | 39895046 | 47962247
MCR024683 | HPR191 | 2020-03-01 | Equipment | 0 | 11988660 | 11421462
MCR024684 | HPR191 | 2020-03-01 | Subcontract | 0 | 39953565 | 45319200
MCR024685 | HPR191 | 2020-03-01 | Overhead | 0 | 9773493 | 35930751
MCR024686 | HPR191 | 2020-04-01 | Labor | 0 | 5290341 | 7008383
MCR024687 | HPR191 | 2020-04-01 | Material | 0 | 14291138 | 8796077
MCR024688 | HPR191 | 2020-04-01 | Equipment | 0 | 4294558 | 5223966
MCR024689 | HPR191 | 2020-04-01 | Subcontract | 0 | 14312101 | 13153908
MCR024690 | HPR191 | 2020-04-01 | Overhead | 0 | 3501045 | 36219568
MCR024691 | HPR191 | 2020-05-01 | Labor | 0 | 1469974 | 1409235
MCR024692 | HPR191 | 2020-05-01 | Material | 0 | 3970934 | 6482193
MCR024693 | HPR191 | 2020-05-01 | Equipment | 0 | 1193286 | 1519608
MCR024694 | HPR191 | 2020-05-01 | Subcontract | 0 | 3976759 | 3563220
MCR024695 | HPR191 | 2020-05-01 | Overhead | 0 | 972800 | 32948605
MCR024696 | HPR192 | 2018-07-01 | Labor | 2908407 | 1717704 | 1770354
MCR024697 | HPR192 | 2018-07-01 | Material | 11393540 | 6729020 | 6513248
MCR024698 | HPR192 | 2018-07-01 | Equipment | 5566797 | 3287748 | 3580877
MCR024699 | HPR192 | 2018-07-01 | Subcontract | 6394119 | 3776364 | 3169176
MCR024700 | HPR192 | 2018-07-01 | Overhead | 2381447 | 1406482 | 11008703
MCR024701 | HPR192 | 2018-08-01 | Labor | 8113233 | 4742273 | 4778219
MCR024702 | HPR192 | 2018-08-01 | Material | 31783190 | 18577622 | 18710828
MCR024703 | HPR192 | 2018-08-01 | Equipment | 15529025 | 9076885 | 8073334
MCR024704 | HPR192 | 2018-08-01 | Subcontract | 17836906 | 10425866 | 11612511
MCR024705 | HPR192 | 2018-08-01 | Overhead | 6643238 | 3883045 | 11290930
MCR024706 | HPR192 | 2018-09-01 | Labor | 12420026 | 10352684 | 11983556
MCR024707 | HPR192 | 2018-09-01 | Material | 48654842 | 40556131 | 43854438
MCR024708 | HPR192 | 2018-09-01 | Equipment | 23772385 | 19815417 | 20472233
MCR024709 | HPR192 | 2018-09-01 | Subcontract | 27305372 | 22760329 | 22022614
MCR024710 | HPR192 | 2018-09-01 | Overhead | 10169706 | 8476935 | 11534967
MCR024711 | HPR192 | 2018-10-01 | Labor | 15856749 | 11436725 | 10936469
MCR024712 | HPR192 | 2018-10-01 | Material | 62118032 | 44802809 | 37376683
MCR024713 | HPR192 | 2018-10-01 | Equipment | 30350398 | 21890311 | 23083735
MCR024714 | HPR192 | 2018-10-01 | Subcontract | 34860990 | 25143589 | 25727361
MCR024715 | HPR192 | 2018-10-01 | Overhead | 12983746 | 9364564 | 11660167
MCR024716 | HPR192 | 2018-11-01 | Labor | 18453291 | 13703989 | 14706661
MCR024717 | HPR192 | 2018-11-01 | Material | 72289858 | 53684703 | 58708787
MCR024718 | HPR192 | 2018-11-01 | Equipment | 35320275 | 26229938 | 24383926
MCR024719 | HPR192 | 2018-11-01 | Subcontract | 40569477 | 30128158 | 31253268
MCR024720 | HPR192 | 2018-11-01 | Overhead | 15109835 | 11221034 | 11410207
MCR024721 | HPR192 | 2018-12-01 | Labor | 20241799 | 22920764 | 23186941
MCR024722 | HPR192 | 2018-12-01 | Material | 79296253 | 89790965 | 97528695
MCR024723 | HPR192 | 2018-12-01 | Equipment | 38743546 | 43871183 | 40239449
MCR024724 | HPR192 | 2018-12-01 | Subcontract | 44501505 | 50391196 | 48038460
MCR024725 | HPR192 | 2018-12-01 | Overhead | 16574293 | 18767869 | 11308675
MCR024726 | HPR192 | 2019-01-01 | Labor | 21257096 | 10490378 | 11233880
MCR024727 | HPR192 | 2019-01-01 | Material | 83273626 | 41095541 | 36935795
MCR024728 | HPR192 | 2019-01-01 | Equipment | 40686860 | 20078969 | 22552321
MCR024729 | HPR192 | 2019-01-01 | Subcontract | 46733629 | 23063049 | 25661819
MCR024730 | HPR192 | 2019-01-01 | Overhead | 17405633 | 8589681 | 12075141
MCR024731 | HPR192 | 2019-02-01 | Labor | 21537223 | 15907759 | 16343317
MCR024732 | HPR192 | 2019-02-01 | Material | 84371013 | 62317865 | 59393800
MCR024733 | HPR192 | 2019-02-01 | Equipment | 41223035 | 30448035 | 31585502
MCR024734 | HPR192 | 2019-02-01 | Subcontract | 47349489 | 34973137 | 38851849
MCR024735 | HPR192 | 2019-02-01 | Overhead | 17635005 | 13025515 | 10523036
MCR024736 | HPR192 | 2019-03-01 | Labor | 21124185 | 23227911 | 24773219
MCR024737 | HPR192 | 2019-03-01 | Material | 82752956 | 90994199 | 92975257
MCR024738 | HPR192 | 2019-03-01 | Equipment | 40432465 | 44459073 | 49468888
MCR024739 | HPR192 | 2019-03-01 | Subcontract | 46441426 | 51066458 | 48205694
MCR024740 | HPR192 | 2019-03-01 | Overhead | 17296803 | 19019366 | 11294109
MCR024741 | HPR192 | 2019-04-01 | Labor | 20064964 | 21691156 | 26048082
MCR024742 | HPR192 | 2019-04-01 | Material | 78603508 | 84974038 | 86609872
MCR024743 | HPR192 | 2019-04-01 | Equipment | 38405076 | 41517668 | 37321132
MCR024744 | HPR192 | 2019-04-01 | Subcontract | 44112732 | 47687910 | 50529280
MCR024745 | HPR192 | 2019-04-01 | Overhead | 16429497 | 17761048 | 11433973
MCR024746 | HPR192 | 2019-05-01 | Labor | 18412994 | 15928985 | 14936894
MCR024747 | HPR192 | 2019-05-01 | Material | 72131997 | 62401015 | 57076728
MCR024748 | HPR192 | 2019-05-01 | Equipment | 35243145 | 30488661 | 35558196
MCR024749 | HPR192 | 2019-05-01 | Subcontract | 40480884 | 35019802 | 35297284
MCR024750 | HPR192 | 2019-05-01 | Overhead | 15076839 | 13042895 | 11204382
MCR024751 | HPR192 | 2019-06-01 | Labor | 16230390 | 20537236 | 21074456
MCR024752 | HPR192 | 2019-06-01 | Material | 63581755 | 80453613 | 96472191
MCR024753 | HPR192 | 2019-06-01 | Equipment | 31065562 | 39309023 | 40741135
MCR024754 | HPR192 | 2019-06-01 | Subcontract | 35682440 | 45151022 | 44572835
MCR024755 | HPR192 | 2019-06-01 | Overhead | 13289690 | 16816201 | 10386487
MCR024756 | HPR192 | 2019-07-01 | Labor | 13591544 | 11342079 | 13014516
MCR024757 | HPR192 | 2019-07-01 | Material | 53244206 | 44432036 | 39474959
MCR024758 | HPR192 | 2019-07-01 | Equipment | 26014714 | 21709155 | 23576068
MCR024759 | HPR192 | 2019-07-01 | Subcontract | 29880949 | 24935509 | 27174574
MCR024760 | HPR192 | 2019-07-01 | Overhead | 11128963 | 9287066 | 11088950
MCR024761 | HPR192 | 2019-08-01 | Labor | 10589459 | 10690443 | 21607613
MCR024762 | HPR192 | 2019-08-01 | Material | 41483683 | 41879284 | 62891252
MCR024763 | HPR192 | 2019-08-01 | Equipment | 20268612 | 20461899 | 19143439
MCR024764 | HPR192 | 2019-08-01 | Subcontract | 23280877 | 23502890 | 22532834
MCR024765 | HPR192 | 2019-08-01 | Overhead | 8670809 | 8753497 | 11109688
MCR024766 | HPR192 | 2019-09-01 | Labor | 7348443 | 11585882 | 19456195
MCR024767 | HPR192 | 2019-09-01 | Material | 28787162 | 45387123 | 59930739
MCR024768 | HPR192 | 2019-09-01 | Equipment | 14065188 | 22175803 | 23932789
MCR024769 | HPR192 | 2019-09-01 | Subcontract | 16155518 | 25471510 | 25670650
MCR024770 | HPR192 | 2019-09-01 | Overhead | 6017016 | 9486696 | 11705235
MCR024771 | HPR192 | 2019-10-01 | Labor | 4055629 | 10255295 | 8514561
MCR024772 | HPR192 | 2019-10-01 | Material | 15887725 | 40174615 | 40216652
MCR024773 | HPR192 | 2019-10-01 | Equipment | 7762622 | 19629011 | 19139214
MCR024774 | HPR192 | 2019-10-01 | Subcontract | 8916281 | 22546220 | 22188251
MCR024775 | HPR192 | 2019-10-01 | Overhead | 3320810 | 8397191 | 10938438
MCR024776 | HPR192 | 2019-11-01 | Labor | 1091970 | 9040285 | 9707162
MCR024777 | HPR192 | 2019-11-01 | Material | 4277739 | 35414873 | 37152531
MCR024778 | HPR192 | 2019-11-01 | Equipment | 2090071 | 17303437 | 19964481
MCR024779 | HPR192 | 2019-11-01 | Subcontract | 2400691 | 19875026 | 20065922
MCR024780 | HPR192 | 2019-11-01 | Overhead | 894122 | 7402323 | 12442697
MCR024781 | HPR192 | 2019-12-01 | Labor | 0 | 4087129 | 4986560
MCR024782 | HPR192 | 2019-12-01 | Material | 0 | 16011126 | 17149356
MCR024783 | HPR192 | 2019-12-01 | Equipment | 0 | 7822914 | 7651698
MCR024784 | HPR192 | 2019-12-01 | Subcontract | 0 | 8985534 | 8603638
MCR024785 | HPR192 | 2019-12-01 | Overhead | 0 | 3346603 | 11013418
MCR024786 | HPR192 | 2020-01-01 | Labor | 0 | 2262512 | 2349558
MCR024787 | HPR192 | 2020-01-01 | Material | 0 | 8863280 | 8785016
MCR024788 | HPR192 | 2020-01-01 | Equipment | 0 | 4330531 | 4048214
MCR024789 | HPR192 | 2020-01-01 | Subcontract | 0 | 4974123 | 4877789
MCR024790 | HPR192 | 2020-01-01 | Overhead | 0 | 1852579 | 10920841
MCR024791 | HPR192 | 2020-02-01 | Labor | 0 | 1376209 | 1466910
MCR024792 | HPR192 | 2020-02-01 | Material | 0 | 5391232 | 5737252
MCR024793 | HPR192 | 2020-02-01 | Equipment | 0 | 2634115 | 2913512
MCR024794 | HPR192 | 2020-02-01 | Subcontract | 0 | 3025590 | 3491286
MCR024795 | HPR192 | 2020-02-01 | Overhead | 0 | 1126861 | 11477185
MCR024796 | HPR193 | 2020-12-01 | Labor | 16505525 | 14443284 | 13246801
MCR024797 | HPR193 | 2020-12-01 | Material | 43478647 | 38046318 | 33463925
MCR024798 | HPR193 | 2020-12-01 | Equipment | 8662004 | 7579752 | 7220704
MCR024799 | HPR193 | 2020-12-01 | Subcontract | 89596750 | 78402312 | 75175934
MCR024800 | HPR193 | 2020-12-01 | Overhead | 15407361 | 13482328 | 46588990
MCR024801 | HPR193 | 2021-01-01 | Labor | 43479696 | 46407279 | 51239374
MCR024802 | HPR193 | 2021-01-01 | Material | 114533671 | 122245476 | 125205724
MCR024803 | HPR193 | 2021-01-01 | Equipment | 22817892 | 24354271 | 23333410
MCR024804 | HPR193 | 2021-01-01 | Subcontract | 236020333 | 251912101 | 263965543
MCR024805 | HPR193 | 2021-01-01 | Overhead | 40586858 | 43319660 | 45232709
MCR024806 | HPR193 | 2021-02-01 | Labor | 61757150 | 44852229 | 42654087
MCR024807 | HPR193 | 2021-02-01 | Material | 162679914 | 118149181 | 118722209
MCR024808 | HPR193 | 2021-02-01 | Equipment | 32409794 | 23538189 | 25842042
MCR024809 | HPR193 | 2021-02-01 | Subcontract | 335235629 | 243470837 | 301473025
MCR024810 | HPR193 | 2021-02-01 | Overhead | 57648257 | 41868072 | 45582919
MCR024811 | HPR193 | 2021-03-01 | Labor | 71863474 | 75527151 | 81515516
MCR024812 | HPR193 | 2021-03-01 | Material | 189301866 | 198952678 | 207472880
MCR024813 | HPR193 | 2021-03-01 | Equipment | 37713534 | 39636211 | 40510853
MCR024814 | HPR193 | 2021-03-01 | Subcontract | 390095670 | 409983167 | 430669489
MCR024815 | HPR193 | 2021-03-01 | Overhead | 67082176 | 70502098 | 42138071
MCR024816 | HPR193 | 2021-04-01 | Labor | 74399717 | 56686274 | 49573625
MCR024817 | HPR193 | 2021-04-01 | Material | 195982804 | 149322276 | 159297224
MCR024818 | HPR193 | 2021-04-01 | Equipment | 39044540 | 29748628 | 30132499
MCR024819 | HPR193 | 2021-04-01 | Subcontract | 403863127 | 307709452 | 330260495
MCR024820 | HPR193 | 2021-04-01 | Overhead | 69449675 | 52914762 | 47903887
MCR024821 | HPR193 | 2021-05-01 | Labor | 70071622 | 52654481 | 49409980
MCR024822 | HPR193 | 2021-05-01 | Material | 184581793 | 138701777 | 132254044
MCR024823 | HPR193 | 2021-05-01 | Equipment | 36773181 | 27632766 | 32455838
MCR024824 | HPR193 | 2021-05-01 | Subcontract | 380368983 | 285823716 | 339407444
MCR024825 | HPR193 | 2021-05-01 | Overhead | 65409542 | 49151217 | 49901550
MCR024826 | HPR193 | 2021-06-01 | Labor | 59740186 | 55473429 | 58181946
MCR024827 | HPR193 | 2021-06-01 | Material | 157366851 | 146127414 | 152915889
MCR024828 | HPR193 | 2021-06-01 | Equipment | 31351303 | 29112134 | 25834759
MCR024829 | HPR193 | 2021-06-01 | Subcontract | 324286963 | 301125778 | 292781290
MCR024830 | HPR193 | 2021-06-01 | Overhead | 55765487 | 51782611 | 43095073
MCR024831 | HPR193 | 2021-07-01 | Labor | 44520858 | 31855525 | 30281099
MCR024832 | HPR193 | 2021-07-01 | Material | 117276288 | 83913426 | 83353051
MCR024833 | HPR193 | 2021-07-01 | Equipment | 23364288 | 16717595 | 20054564
MCR024834 | HPR193 | 2021-07-01 | Subcontract | 241672061 | 172920980 | 166006583
MCR024835 | HPR193 | 2021-07-01 | Overhead | 41558748 | 29736079 | 44757940
MCR024836 | HPR193 | 2021-08-01 | Labor | 26023847 | 49702939 | 50203254
MCR024837 | HPR193 | 2021-08-01 | Material | 68551694 | 130926860 | 145374643
MCR024838 | HPR193 | 2021-08-01 | Equipment | 13657164 | 26083814 | 25909931
MCR024839 | HPR193 | 2021-08-01 | Subcontract | 141264952 | 269801890 | 334847523
MCR024840 | HPR193 | 2021-08-01 | Overhead | 24292401 | 46396049 | 44514641
MCR024841 | HPR193 | 2021-09-01 | Labor | 7319043 | 21558286 | 19556626
MCR024842 | HPR193 | 2021-09-01 | Material | 19279731 | 56788569 | 58564125
MCR024843 | HPR193 | 2021-09-01 | Equipment | 3840991 | 11313664 | 11503199
MCR024844 | HPR193 | 2021-09-01 | Subcontract | 39729876 | 117024598 | 177576623
MCR024845 | HPR193 | 2021-09-01 | Overhead | 6832084 | 20123947 | 42192176
MCR024846 | HPR193 | 2021-10-01 | Labor | 0 | 21136028 | 27395016
MCR024847 | HPR193 | 2021-10-01 | Material | 0 | 55676261 | 50379917
MCR024848 | HPR193 | 2021-10-01 | Equipment | 0 | 11092065 | 12272756
MCR024849 | HPR193 | 2021-10-01 | Subcontract | 0 | 114732459 | 191468129
MCR024850 | HPR193 | 2021-10-01 | Overhead | 0 | 19729783 | 45896138
MCR024851 | HPR193 | 2021-11-01 | Labor | 0 | 5384212 | 2489218
MCR024852 | HPR193 | 2021-11-01 | Material | 0 | 14183023 | 16983561
MCR024853 | HPR193 | 2021-11-01 | Equipment | 0 | 2825603 | 2414705
MCR024854 | HPR193 | 2021-11-01 | Subcontract | 0 | 29227054 | 91474213
MCR024855 | HPR193 | 2021-11-01 | Overhead | 0 | 5025983 | 43303985
MCR024856 | HPR194 | 2020-12-01 | Labor | 3563105 | 2447034 | 2282911
MCR024857 | HPR194 | 2020-12-01 | Material | 8291071 | 5694059 | 6329833
MCR024858 | HPR194 | 2020-12-01 | Equipment | 2182753 | 1499049 | 1629835
MCR024859 | HPR194 | 2020-12-01 | Subcontract | 21089797 | 14483841 | 15292530
MCR024860 | HPR194 | 2020-12-01 | Overhead | 3374914 | 2317790 | 24497461
MCR024861 | HPR194 | 2021-01-01 | Labor | 10204415 | 13387984 | 12508172
MCR024862 | HPR194 | 2021-01-01 | Material | 23744888 | 31152808 | 29305187
MCR024863 | HPR194 | 2021-01-01 | Equipment | 6251209 | 8201459 | 8447871
MCR024864 | HPR194 | 2021-01-01 | Subcontract | 60399298 | 79242645 | 83619424
MCR024865 | HPR194 | 2021-01-01 | Overhead | 9665453 | 12680877 | 24275046
MCR024866 | HPR194 | 2021-02-01 | Labor | 16128380 | 22073668 | 23093950
MCR024867 | HPR194 | 2021-02-01 | Material | 37529498 | 51363727 | 52942250
MCR024868 | HPR194 | 2021-02-01 | Equipment | 9880221 | 13522295 | 12582271
MCR024869 | HPR194 | 2021-02-01 | Subcontract | 95462877 | 130652669 | 112064499
MCR024870 | HPR194 | 2021-02-01 | Overhead | 15276535 | 20907814 | 22859541
MCR024871 | HPR194 | 2021-03-01 | Labor | 21348762 | 17744844 | 19517169
MCR024872 | HPR194 | 2021-03-01 | Material | 49676926 | 41290887 | 42531346
MCR024873 | HPR194 | 2021-03-01 | Equipment | 13078219 | 10870465 | 10491590
MCR024874 | HPR194 | 2021-03-01 | Subcontract | 126361995 | 105030631 | 109095519
MCR024875 | HPR194 | 2021-03-01 | Overhead | 20221194 | 16807623 | 23446135
MCR024876 | HPR194 | 2021-04-01 | Labor | 25879895 | 18934939 | 18824026
MCR024877 | HPR194 | 2021-04-01 | Material | 60220523 | 44060147 | 42391584
MCR024878 | HPR194 | 2021-04-01 | Equipment | 15853984 | 11599515 | 12125706
MCR024879 | HPR194 | 2021-04-01 | Subcontract | 153181487 | 112074729 | 122361754
MCR024880 | HPR194 | 2021-04-01 | Overhead | 24513008 | 17934862 | 26069292
MCR024881 | HPR194 | 2021-05-01 | Labor | 29736736 | 37756902 | 37871608
MCR024882 | HPR194 | 2021-05-01 | Material | 69195097 | 87857406 | 93861351
MCR024883 | HPR194 | 2021-05-01 | Equipment | 18216680 | 23129821 | 23539901
MCR024884 | HPR194 | 2021-05-01 | Subcontract | 176009895 | 223480759 | 183491143
MCR024885 | HPR194 | 2021-05-01 | Overhead | 28166145 | 35762714 | 23185062
MCR024886 | HPR194 | 2021-06-01 | Labor | 32934938 | 16661251 | 19049862
MCR024887 | HPR194 | 2021-06-01 | Material | 76637065 | 38769448 | 35337055
MCR024888 | HPR194 | 2021-06-01 | Equipment | 20175893 | 10206657 | 9525948
MCR024889 | HPR194 | 2021-06-01 | Subcontract | 194939849 | 98616908 | 99158859
MCR024890 | HPR194 | 2021-06-01 | Overhead | 31195428 | 15781261 | 24307559
MCR024891 | HPR194 | 2021-07-01 | Labor | 35490915 | 19575161 | 21946345
MCR024892 | HPR194 | 2021-07-01 | Material | 82584627 | 45549892 | 51227262
MCR024893 | HPR194 | 2021-07-01 | Equipment | 21741680 | 11991714 | 14111614
MCR024894 | HPR194 | 2021-07-01 | Subcontract | 210068519 | 115864160 | 103507077
MCR024895 | HPR194 | 2021-07-01 | Overhead | 33616408 | 18541269 | 24619097
MCR024896 | HPR194 | 2021-08-01 | Labor | 37421941 | 29141963 | 27780382
MCR024897 | HPR194 | 2021-08-01 | Material | 87077977 | 67811105 | 68727705
MCR024898 | HPR194 | 2021-08-01 | Equipment | 22924624 | 17852322 | 19759417
MCR024899 | HPR194 | 2021-08-01 | Subcontract | 221498144 | 172489468 | 171598562
MCR024900 | HPR194 | 2021-08-01 | Overhead | 35445444 | 27602786 | 25311057
MCR024901 | HPR194 | 2021-09-01 | Labor | 38746251 | 33136100 | 35570889
MCR024902 | HPR194 | 2021-09-01 | Material | 90159544 | 77105155 | 84490731
MCR024903 | HPR194 | 2021-09-01 | Equipment | 23735894 | 20299125 | 20515934
MCR024904 | HPR194 | 2021-09-01 | Subcontract | 229336652 | 196130517 | 176654412
MCR024905 | HPR194 | 2021-09-01 | Overhead | 36699809 | 31385966 | 27027470
MCR024906 | HPR194 | 2021-10-01 | Labor | 39483168 | 36502364 | 60621866
MCR024907 | HPR194 | 2021-10-01 | Material | 91874293 | 84938191 | 134648034
MCR024908 | HPR194 | 2021-10-01 | Equipment | 24187329 | 22361292 | 22936058
MCR024909 | HPR194 | 2021-10-01 | Subcontract | 233698417 | 216055222 | 222952169
MCR024910 | HPR194 | 2021-10-01 | Overhead | 37397804 | 34574435 | 23672473
MCR024911 | HPR194 | 2021-11-01 | Labor | 39653257 | 30529481 | 54725511
MCR024912 | HPR194 | 2021-11-01 | Material | 92270076 | 71039754 | 119235525
MCR024913 | HPR194 | 2021-11-01 | Equipment | 24291525 | 18702314 | 16597608
MCR024914 | HPR194 | 2021-11-01 | Subcontract | 234705161 | 180702103 | 158126279
MCR024915 | HPR194 | 2021-11-01 | Overhead | 37558909 | 28917020 | 22000808
MCR024916 | HPR194 | 2021-12-01 | Labor | 39278513 | 18688532 | 22629491
MCR024917 | HPR194 | 2021-12-01 | Material | 91398077 | 43486776 | 38383082
MCR024918 | HPR194 | 2021-12-01 | Equipment | 24061957 | 11448566 | 12223523
MCR024919 | HPR194 | 2021-12-01 | Subcontract | 232487077 | 110616260 | 113928080
MCR024920 | HPR194 | 2021-12-01 | Overhead | 37203958 | 17701469 | 26030859
MCR024921 | HPR194 | 2022-01-01 | Labor | 38382597 | 40212300 | 47001669
MCR024922 | HPR194 | 2022-01-01 | Material | 89313350 | 93570927 | 98534051
MCR024923 | HPR194 | 2022-01-01 | Equipment | 23513121 | 24633994 | 22627325
MCR024924 | HPR194 | 2022-01-01 | Subcontract | 227184208 | 238014103 | 211738275
MCR024925 | HPR194 | 2022-01-01 | Overhead | 36355362 | 38088426 | 26117148
MCR024926 | HPR194 | 2022-02-01 | Labor | 36991132 | 33110000 | 34204266
MCR024927 | HPR194 | 2022-02-01 | Material | 86075519 | 77044422 | 92214129
MCR024928 | HPR194 | 2022-02-01 | Equipment | 22660712 | 20283136 | 20968826
MCR024929 | HPR194 | 2022-02-01 | Subcontract | 218948214 | 195976032 | 203366285
MCR024930 | HPR194 | 2022-02-01 | Overhead | 35037389 | 31361245 | 23327026
MCR024931 | HPR194 | 2022-03-01 | Labor | 35132086 | 32143463 | 36911045
MCR024932 | HPR194 | 2022-03-01 | Material | 81749661 | 74795365 | 79260417
MCR024933 | HPR194 | 2022-03-01 | Equipment | 21521863 | 19691037 | 19549226
MCR024934 | HPR194 | 2022-03-01 | Subcontract | 207944635 | 190255160 | 199364099
MCR024935 | HPR194 | 2022-03-01 | Overhead | 33276531 | 30445757 | 27295939
MCR024936 | HPR194 | 2022-04-01 | Labor | 32836277 | 43514487 | 46945653
MCR024937 | HPR194 | 2022-04-01 | Material | 76407490 | 101254863 | 107942303
MCR024938 | HPR194 | 2022-04-01 | Equipment | 20115454 | 26656909 | 30041948
MCR024939 | HPR194 | 2022-04-01 | Subcontract | 194355885 | 257559546 | 216982738
MCR024940 | HPR194 | 2022-04-01 | Overhead | 31101979 | 41216203 | 25309349
MCR024941 | HPR194 | 2022-05-01 | Labor | 30138060 | 42527876 | 44942320
MCR024942 | HPR194 | 2022-05-01 | Material | 70128946 | 98959095 | 106829763
MCR024943 | HPR194 | 2022-05-01 | Equipment | 18462530 | 26052512 | 23222120
MCR024944 | HPR194 | 2022-05-01 | Subcontract | 178385302 | 251719856 | 255047655
MCR024945 | HPR194 | 2022-05-01 | Overhead | 28546272 | 40281701 | 24994439
MCR024946 | HPR194 | 2022-06-01 | Labor | 27076281 | 30601070 | 29607262
MCR024947 | HPR194 | 2022-06-01 | Material | 63004423 | 71206335 | 76849135
MCR024948 | HPR194 | 2022-06-01 | Equipment | 16586889 | 18746169 | 20238444
MCR024949 | HPR194 | 2022-06-01 | Subcontract | 160262827 | 181125831 | 170825332
MCR024950 | HPR194 | 2022-06-01 | Overhead | 25646206 | 28984828 | 21921254
MCR024951 | HPR194 | 2022-07-01 | Labor | 23695678 | 20006274 | 25067452
MCR024952 | HPR194 | 2022-07-01 | Material | 55138019 | 46553061 | 52525446
MCR024953 | HPR194 | 2022-07-01 | Equipment | 14515936 | 12255813 | 12521667
MCR024954 | HPR194 | 2022-07-01 | Subcontract | 140253245 | 118415895 | 127191673
MCR024955 | HPR194 | 2022-07-01 | Overhead | 22444155 | 18949612 | 22096659
MCR024956 | HPR194 | 2022-08-01 | Labor | 20049003 | 19010578 | 21878085
MCR024957 | HPR194 | 2022-08-01 | Material | 46652488 | 44236152 | 45254001
MCR024958 | HPR194 | 2022-08-01 | Equipment | 12281989 | 11645851 | 12292561
MCR024959 | HPR194 | 2022-08-01 | Subcontract | 118668804 | 112522429 | 96823569
MCR024960 | HPR194 | 2022-08-01 | Overhead | 18990084 | 18006505 | 23447824
MCR024961 | HPR194 | 2022-09-01 | Labor | 16200506 | 17685399 | 20753574
MCR024962 | HPR194 | 2022-09-01 | Material | 37697330 | 41152561 | 43771916
MCR024963 | HPR194 | 2022-09-01 | Equipment | 9924405 | 10834048 | 10992735
MCR024964 | HPR194 | 2022-09-01 | Subcontract | 95889786 | 104678775 | 121446681
MCR024965 | HPR194 | 2022-09-01 | Overhead | 15344851 | 16751317 | 24579559
MCR024966 | HPR194 | 2022-10-01 | Labor | 12232124 | 19740023 | 19082034
MCR024967 | HPR194 | 2022-10-01 | Material | 28463210 | 45933515 | 52927880
MCR024968 | HPR194 | 2022-10-01 | Equipment | 7493380 | 12092708 | 12524766
MCR024969 | HPR194 | 2022-10-01 | Subcontract | 72401179 | 116839971 | 84127289
MCR024970 | HPR194 | 2022-10-01 | Overhead | 11586065 | 18697424 | 22572150
MCR024971 | HPR194 | 2022-11-01 | Labor | 8256058 | 16872830 | 19445177
MCR024972 | HPR194 | 2022-11-01 | Material | 19211212 | 39261776 | 39760951
MCR024973 | HPR194 | 2022-11-01 | Equipment | 5057649 | 10336270 | 10982305
MCR024974 | HPR194 | 2022-11-01 | Subcontract | 48867095 | 99869230 | 107295266
MCR024975 | HPR194 | 2022-11-01 | Overhead | 7820002 | 15981665 | 25579266
MCR024976 | HPR194 | 2022-12-01 | Labor | 4446442 | 17719930 | 20241762
MCR024977 | HPR194 | 2022-12-01 | Material | 10346528 | 41232913 | 51206872
MCR024978 | HPR194 | 2022-12-01 | Equipment | 2723883 | 10855202 | 10045879
MCR024979 | HPR194 | 2022-12-01 | Subcontract | 26318213 | 104883162 | 98482400
MCR024980 | HPR194 | 2022-12-01 | Overhead | 4211596 | 16784024 | 22368981
MCR024981 | HPR194 | 2023-01-01 | Labor | 1173535 | 10329834 | 9396390
MCR024982 | HPR194 | 2023-01-01 | Material | 2730725 | 24036729 | 23180882
MCR024983 | HPR194 | 2023-01-01 | Equipment | 718906 | 6328041 | 8047203
MCR024984 | HPR194 | 2023-01-01 | Subcontract | 6946079 | 61141646 | 56504841
MCR024985 | HPR194 | 2023-01-01 | Overhead | 1111553 | 9784248 | 23959416
MCR024986 | HPR194 | 2023-02-01 | Labor | 0 | 7238010 | 7998403
MCR024987 | HPR194 | 2023-02-01 | Material | 0 | 16842293 | 16665601
MCR024988 | HPR194 | 2023-02-01 | Equipment | 0 | 4433994 | 4146265
MCR024989 | HPR194 | 2023-02-01 | Subcontract | 0 | 42841334 | 37456270
MCR024990 | HPR194 | 2023-02-01 | Overhead | 0 | 6855724 | 22652882
MCR024991 | HPR194 | 2023-03-01 | Labor | 0 | 5644587 | 6128253
MCR024992 | HPR194 | 2023-03-01 | Material | 0 | 13134520 | 12348016
MCR024993 | HPR194 | 2023-03-01 | Equipment | 0 | 3457866 | 3665709
MCR024994 | HPR194 | 2023-03-01 | Subcontract | 0 | 33409961 | 34829361
MCR024995 | HPR194 | 2023-03-01 | Overhead | 0 | 5346460 | 23399967
MCR024996 | HPR194 | 2023-04-01 | Labor | 0 | 2734131 | 2779561
MCR024997 | HPR194 | 2023-04-01 | Material | 0 | 6362113 | 7353215
MCR024998 | HPR194 | 2023-04-01 | Equipment | 0 | 1674925 | 1576372
MCR024999 | HPR194 | 2023-04-01 | Subcontract | 0 | 16183153 | 16213764
MCR025000 | HPR194 | 2023-04-01 | Overhead | 0 | 2589724 | 24704702
MCR025001 | HPR194 | 2023-05-01 | Labor | 0 | 809038 | 987947
MCR025002 | HPR194 | 2023-05-01 | Material | 0 | 1882570 | 1679651
MCR025003 | HPR194 | 2023-05-01 | Equipment | 0 | 495616 | 644552
MCR025004 | HPR194 | 2023-05-01 | Subcontract | 0 | 4788648 | 4954296
MCR025005 | HPR194 | 2023-05-01 | Overhead | 0 | 766308 | 25309364
MCR025006 | HPR195 | 2022-04-01 | Labor | 28932004 | 42005335 | 37193513
MCR025007 | HPR195 | 2022-04-01 | Material | 58114310 | 84374073 | 91180779
MCR025008 | HPR195 | 2022-04-01 | Equipment | 11197676 | 16257502 | 18778297
MCR025009 | HPR195 | 2022-04-01 | Subcontract | 60109672 | 87271068 | 93975188
MCR025010 | HPR195 | 2022-04-01 | Overhead | 15864193 | 23032650 | 41735261
MCR025011 | HPR195 | 2022-05-01 | Labor | 76214162 | 81719293 | 84921268
MCR025012 | HPR195 | 2022-05-01 | Material | 153087680 | 164145568 | 165870625
MCR025013 | HPR195 | 2022-05-01 | Equipment | 29497489 | 31628163 | 31252025
MCR025014 | HPR195 | 2022-05-01 | Subcontract | 158343966 | 169781528 | 162153316
MCR025015 | HPR195 | 2022-05-01 | Overhead | 41790266 | 44808876 | 48973876
MCR025016 | HPR195 | 2022-06-01 | Labor | 108252125 | 63841263 | 61329267
MCR025017 | HPR195 | 2022-06-01 | Material | 217440778 | 128234839 | 111360041
MCR025018 | HPR195 | 2022-06-01 | Equipment | 41897277 | 24708754 | 20562236
MCR025019 | HPR195 | 2022-06-01 | Subcontract | 224906636 | 132637799 | 122448643
MCR025020 | HPR195 | 2022-06-01 | Overhead | 59357539 | 35005874 | 46887564
MCR025021 | HPR195 | 2022-07-01 | Labor | 125967175 | 112740476 | 108905174
MCR025022 | HPR195 | 2022-07-01 | Material | 253024138 | 226456310 | 251490943
MCR025023 | HPR195 | 2022-07-01 | Equipment | 48753608 | 43634423 | 48626569
MCR025024 | HPR195 | 2022-07-01 | Subcontract | 261711755 | 234231717 | 255244044
MCR025025 | HPR195 | 2022-07-01 | Overhead | 69071175 | 61818622 | 48023618
MCR025026 | HPR195 | 2022-08-01 | Labor | 130412874 | 128712947 | 124857053
MCR025027 | HPR195 | 2022-08-01 | Material | 261953996 | 258539437 | 251539036
MCR025028 | HPR195 | 2022-08-01 | Equipment | 50474246 | 49816316 | 43379577
MCR025029 | HPR195 | 2022-08-01 | Subcontract | 270948221 | 267416422 | 269978874
MCR025030 | HPR195 | 2022-08-01 | Overhead | 71508871 | 70576756 | 43694911
MCR025031 | HPR195 | 2022-09-01 | Labor | 122826296 | 78960978 | 81228578
MCR025032 | HPR195 | 2022-09-01 | Material | 246715207 | 158605076 | 159651259
MCR025033 | HPR195 | 2022-09-01 | Equipment | 47537980 | 30560601 | 33599513
MCR025034 | HPR195 | 2022-09-01 | Subcontract | 255186206 | 164050803 | 164493202
MCR025035 | HPR195 | 2022-09-01 | Overhead | 67348947 | 43296419 | 47347525
MCR025036 | HPR195 | 2022-10-01 | Labor | 104716653 | 103292870 | 105387642
MCR025037 | HPR195 | 2022-10-01 | Material | 210339246 | 207479365 | 238885753
MCR025038 | HPR195 | 2022-10-01 | Equipment | 40528929 | 39977876 | 41965503
MCR025039 | HPR195 | 2022-10-01 | Subcontract | 217561272 | 214603196 | 198113625
MCR025040 | HPR195 | 2022-10-01 | Overhead | 57418945 | 56638247 | 46493493
MCR025041 | HPR195 | 2022-11-01 | Labor | 78039182 | 81689799 | 76212192
MCR025042 | HPR195 | 2022-11-01 | Material | 156753509 | 164086326 | 175135058
MCR025043 | HPR195 | 2022-11-01 | Equipment | 30203834 | 31616748 | 31773511
MCR025044 | HPR195 | 2022-11-01 | Subcontract | 162135661 | 169720252 | 162333454
MCR025045 | HPR195 | 2022-11-01 | Overhead | 42790973 | 44792704 | 47016801
MCR025046 | HPR195 | 2022-12-01 | Labor | 45616366 | 91498989 | 95125648
MCR025047 | HPR195 | 2022-12-01 | Material | 91627376 | 183789569 | 163769049
MCR025048 | HPR195 | 2022-12-01 | Equipment | 17655095 | 35413240 | 37340551
MCR025049 | HPR195 | 2022-12-01 | Subcontract | 94773414 | 190100008 | 183235295
MCR025050 | HPR195 | 2022-12-01 | Overhead | 25012675 | 50171346 | 44731585
MCR025051 | HPR195 | 2023-01-01 | Labor | 12829315 | 41352405 | 37830011
MCR025052 | HPR195 | 2023-01-01 | Material | 25769621 | 83062565 | 87508803
MCR025053 | HPR195 | 2023-01-01 | Equipment | 4965384 | 16004796 | 12892043
MCR025054 | HPR195 | 2023-01-01 | Subcontract | 26654424 | 85914529 | 96880251
MCR025055 | HPR195 | 2023-01-01 | Overhead | 7034657 | 22674631 | 45509706
MCR025056 | HPR195 | 2023-02-01 | Labor | 0 | 7991797 | 8993980
MCR025057 | HPR195 | 2023-02-01 | Material | 0 | 16052734 | 14465260
MCR025058 | HPR195 | 2023-02-01 | Equipment | 0 | 3093099 | 4140443
MCR025059 | HPR195 | 2023-02-01 | Subcontract | 0 | 16603906 | 18136946
MCR025060 | HPR195 | 2023-02-01 | Overhead | 0 | 4382116 | 43894635
MCR025061 | HPR196 | 2018-09-01 | Labor | 3825255 | 3063346 | 3145568
MCR025062 | HPR196 | 2018-09-01 | Material | 11529664 | 9233201 | 9557190
MCR025063 | HPR196 | 2018-09-01 | Equipment | 2357911 | 1888266 | 2114419
MCR025064 | HPR196 | 2018-09-01 | Subcontract | 23871680 | 19116950 | 19578808
MCR025065 | HPR196 | 2018-09-01 | Overhead | 3166231 | 2535585 | 15317670
MCR025066 | HPR196 | 2018-10-01 | Labor | 10670854 | 5572056 | 6044728
MCR025067 | HPR196 | 2018-10-01 | Material | 32162920 | 16794681 | 15512689
MCR025068 | HPR196 | 2018-10-01 | Equipment | 6577583 | 3434651 | 3462572
MCR025069 | HPR196 | 2018-10-01 | Subcontract | 66591960 | 34772675 | 32956536
MCR025070 | HPR196 | 2018-10-01 | Overhead | 8832454 | 4612089 | 15421902
MCR025071 | HPR196 | 2018-11-01 | Labor | 16335324 | 13347162 | 14361795
MCR025072 | HPR196 | 2018-11-01 | Material | 49236146 | 40229555 | 40318761
MCR025073 | HPR196 | 2018-11-01 | Equipment | 10069198 | 8227276 | 7601559
MCR025074 | HPR196 | 2018-11-01 | Subcontract | 101941349 | 83293586 | 84106716
MCR025075 | HPR196 | 2018-11-01 | Overhead | 13521035 | 11047681 | 15070781
MCR025076 | HPR196 | 2018-12-01 | Labor | 20855441 | 16475543 | 18217958
MCR025077 | HPR196 | 2018-12-01 | Material | 62860188 | 49658779 | 58999496
MCR025078 | HPR196 | 2018-12-01 | Equipment | 12855428 | 10155630 | 10653008
MCR025079 | HPR196 | 2018-12-01 | Subcontract | 130149350 | 102816393 | 100273389
MCR025080 | HPR196 | 2018-12-01 | Overhead | 17262416 | 13637097 | 14976828
MCR025081 | HPR196 | 2019-01-01 | Labor | 24270519 | 9670081 | 9247172
MCR025082 | HPR196 | 2019-01-01 | Material | 73153542 | 29146500 | 22872422
MCR025083 | HPR196 | 2019-01-01 | Equipment | 14960503 | 5960700 | 6696143
MCR025084 | HPR196 | 2019-01-01 | Subcontract | 151461302 | 60346591 | 69404635
MCR025085 | HPR196 | 2019-01-01 | Overhead | 20089136 | 8004096 | 15102287
MCR025086 | HPR196 | 2019-02-01 | Labor | 26622838 | 23145411 | 27567900
MCR025087 | HPR196 | 2019-02-01 | Material | 80243646 | 69762365 | 66971460
MCR025088 | HPR196 | 2019-02-01 | Equipment | 16410488 | 14266980 | 14833737
MCR025089 | HPR196 | 2019-02-01 | Subcontract | 166141060 | 144440013 | 139316250
MCR025090 | HPR196 | 2019-02-01 | Overhead | 22036192 | 19157864 | 15544292
MCR025091 | HPR196 | 2019-03-01 | Labor | 27958197 | 17946484 | 17175545
MCR025092 | HPR196 | 2019-03-01 | Material | 84268539 | 54092329 | 57077727
MCR025093 | HPR196 | 2019-03-01 | Equipment | 17233612 | 11062328 | 11142912
MCR025094 | HPR196 | 2019-03-01 | Subcontract | 174474431 | 111995871 | 116220303
MCR025095 | HPR196 | 2019-03-01 | Overhead | 23141492 | 14854621 | 14195620
MCR025096 | HPR196 | 2019-04-01 | Labor | 28326633 | 18456525 | 20044498
MCR025097 | HPR196 | 2019-04-01 | Material | 85379036 | 55629638 | 57695899
MCR025098 | HPR196 | 2019-04-01 | Equipment | 17460718 | 11376720 | 11291356
MCR025099 | HPR196 | 2019-04-01 | Subcontract | 176773669 | 115178803 | 120405985
MCR025100 | HPR196 | 2019-04-01 | Overhead | 23446452 | 15276791 | 15006146
MCR025101 | HPR196 | 2019-05-01 | Labor | 27783388 | 34093340 | 40454658
MCR025102 | HPR196 | 2019-05-01 | Material | 83741648 | 102760414 | 117682792
MCR025103 | HPR196 | 2019-05-01 | Equipment | 17125858 | 21015353 | 20360634
MCR025104 | HPR196 | 2019-05-01 | Subcontract | 173383525 | 212761074 | 243018153
MCR025105 | HPR196 | 2019-05-01 | Overhead | 22996799 | 28219657 | 13884129
MCR025106 | HPR196 | 2019-06-01 | Labor | 26390257 | 27780135 | 31153640
MCR025107 | HPR196 | 2019-06-01 | Material | 79542624 | 83731842 | 76652850
MCR025108 | HPR196 | 2019-06-01 | Equipment | 16267123 | 17123853 | 18013381
MCR025109 | HPR196 | 2019-06-01 | Subcontract | 164689626 | 173363222 | 122205622
MCR025110 | HPR196 | 2019-06-01 | Overhead | 21843680 | 22994106 | 16183268
MCR025111 | HPR196 | 2019-07-01 | Labor | 24217519 | 11929386 | 11378335
MCR025112 | HPR196 | 2019-07-01 | Material | 72993795 | 35956251 | 38130729
MCR025113 | HPR196 | 2019-07-01 | Equipment | 14927834 | 7353350 | 9379180
MCR025114 | HPR196 | 2019-07-01 | Subcontract | 151130553 | 74445890 | 83611135
MCR025115 | HPR196 | 2019-07-01 | Overhead | 20045267 | 9874163 | 16485539
MCR025116 | HPR196 | 2019-08-01 | Labor | 21346870 | 18941099 | 18500176
MCR025117 | HPR196 | 2019-08-01 | Material | 64341399 | 57090189 | 55976656
MCR025118 | HPR196 | 2019-08-01 | Equipment | 13158347 | 11675415 | 10554995
MCR025119 | HPR196 | 2019-08-01 | Subcontract | 133216134 | 118202813 | 117151541
MCR025120 | HPR196 | 2019-08-01 | Overhead | 17669180 | 15677881 | 14452801
MCR025121 | HPR196 | 2019-09-01 | Labor | 17876152 | 11718282 | 15237830
MCR025122 | HPR196 | 2019-09-01 | Material | 53880342 | 35319963 | 37145802
MCR025123 | HPR196 | 2019-09-01 | Equipment | 11018975 | 7223224 | 9585065
MCR025124 | HPR196 | 2019-09-01 | Subcontract | 111556959 | 73128484 | 74292650
MCR025125 | HPR196 | 2019-09-01 | Overhead | 14796406 | 9699428 | 15824225
MCR025126 | HPR196 | 2019-10-01 | Labor | 13927687 | 18538659 | 18295374
MCR025127 | HPR196 | 2019-10-01 | Material | 41979310 | 55877199 | 54538802
MCR025128 | HPR196 | 2019-10-01 | Equipment | 8585115 | 11427349 | 11128338
MCR025129 | HPR196 | 2019-10-01 | Subcontract | 86916378 | 115691367 | 112505461
MCR025130 | HPR196 | 2019-10-01 | Overhead | 11528192 | 15344775 | 14367523
MCR025131 | HPR196 | 2019-11-01 | Labor | 9664971 | 11968925 | 15781368
MCR025132 | HPR196 | 2019-11-01 | Material | 29131097 | 36075424 | 43666663
MCR025133 | HPR196 | 2019-11-01 | Equipment | 5957550 | 7377722 | 7736861
MCR025134 | HPR196 | 2019-11-01 | Subcontract | 60314699 | 74692633 | 76709831
MCR025135 | HPR196 | 2019-11-01 | Overhead | 7999866 | 9906890 | 15413673
MCR025136 | HPR196 | 2019-12-01 | Labor | 5334128 | 16972112 | 20139206
MCR025137 | HPR196 | 2019-12-01 | Material | 16077544 | 51155484 | 45901448
MCR025138 | HPR196 | 2019-12-01 | Equipment | 3287991 | 10461719 | 10969227
MCR025139 | HPR196 | 2019-12-01 | Subcontract | 33287872 | 105915258 | 109625968
MCR025140 | HPR196 | 2019-12-01 | Overhead | 4415151 | 14048116 | 15099471
MCR025141 | HPR196 | 2020-01-01 | Labor | 1436203 | 8656879 | 8741758
MCR025142 | HPR196 | 2020-01-01 | Material | 4328847 | 26092616 | 24968894
MCR025143 | HPR196 | 2020-01-01 | Equipment | 885285 | 5336155 | 6166666
MCR025144 | HPR196 | 2020-01-01 | Subcontract | 8962695 | 54023654 | 62631187
MCR025145 | HPR196 | 2020-01-01 | Overhead | 1188771 | 7165451 | 15066829
MCR025146 | HPR196 | 2020-02-01 | Labor | 0 | 20635367 | 21207502
MCR025147 | HPR196 | 2020-02-01 | Material | 0 | 62196866 | 66850451
MCR025148 | HPR196 | 2020-02-01 | Equipment | 0 | 12719773 | 15291845
MCR025149 | HPR196 | 2020-02-01 | Subcontract | 0 | 128775970 | 116782413
MCR025150 | HPR196 | 2020-02-01 | Overhead | 0 | 17080257 | 15528518
MCR025151 | HPR196 | 2020-03-01 | Labor | 0 | 7611020 | 10035211
MCR025152 | HPR196 | 2020-03-01 | Material | 0 | 22940304 | 22294924
MCR025153 | HPR196 | 2020-03-01 | Equipment | 0 | 4691482 | 4150748
MCR025154 | HPR196 | 2020-03-01 | Subcontract | 0 | 47496925 | 61685317
MCR025155 | HPR196 | 2020-03-01 | Overhead | 0 | 6299775 | 14884106
MCR025156 | HPR196 | 2020-04-01 | Labor | 0 | 7134671 | 7834296
MCR025157 | HPR196 | 2020-04-01 | Material | 0 | 21504543 | 25478199
MCR025158 | HPR196 | 2020-04-01 | Equipment | 0 | 4397857 | 4474093
MCR025159 | HPR196 | 2020-04-01 | Subcontract | 0 | 44524244 | 36238626
MCR025160 | HPR196 | 2020-04-01 | Overhead | 0 | 5905492 | 15088550
MCR025161 | HPR196 | 2020-05-01 | Labor | 0 | 2399791 | 3009084
MCR025162 | HPR196 | 2020-05-01 | Material | 0 | 7233188 | 5035137
MCR025163 | HPR196 | 2020-05-01 | Equipment | 0 | 1479247 | 1635848
MCR025164 | HPR196 | 2020-05-01 | Subcontract | 0 | 14976009 | 14848982
MCR025165 | HPR196 | 2020-05-01 | Overhead | 0 | 1986349 | 14607690
MCR025166 | HPR196 | 2020-06-01 | Labor | 0 | 785960 | 830633
MCR025167 | HPR196 | 2020-06-01 | Material | 0 | 2368954 | 2897340
MCR025168 | HPR196 | 2020-06-01 | Equipment | 0 | 484471 | 700741
MCR025169 | HPR196 | 2020-06-01 | Subcontract | 0 | 4904818 | 5929611
MCR025170 | HPR196 | 2020-06-01 | Overhead | 0 | 650553 | 15410800
MCR025171 | HPR197 | 2020-07-01 | Labor | 1904094 | 1413168 | 1450616
MCR025172 | HPR197 | 2020-07-01 | Material | 3822976 | 2837312 | 2844498
MCR025173 | HPR197 | 2020-07-01 | Equipment | 739682 | 548972 | 469341
MCR025174 | HPR197 | 2020-07-01 | Subcontract | 3236255 | 2401863 | 2202961
MCR025175 | HPR197 | 2020-07-01 | Overhead | 984866 | 730941 | 7564354
MCR025176 | HPR197 | 2020-08-01 | Labor | 5472018 | 2976062 | 2601281
MCR025177 | HPR197 | 2020-08-01 | Material | 10986532 | 5975236 | 5878529
MCR025178 | HPR197 | 2020-08-01 | Equipment | 2125709 | 1156108 | 1201179
MCR025179 | HPR197 | 2020-08-01 | Subcontract | 9300405 | 5058204 | 4190371
MCR025180 | HPR197 | 2020-08-01 | Overhead | 2830324 | 1539326 | 7397107
MCR025181 | HPR197 | 2020-09-01 | Labor | 8684128 | 5430819 | 5895692
MCR025182 | HPR197 | 2020-09-01 | Material | 17435699 | 10903814 | 11174720
MCR025183 | HPR197 | 2020-09-01 | Equipment | 3373514 | 2109705 | 2460024
MCR025184 | HPR197 | 2020-09-01 | Subcontract | 14759804 | 9230382 | 9137626
MCR025185 | HPR197 | 2020-09-01 | Overhead | 4491742 | 2809014 | 8051523
MCR025186 | HPR197 | 2020-10-01 | Labor | 11546715 | 9441327 | 10145094
MCR025187 | HPR197 | 2020-10-01 | Material | 23183104 | 18955976 | 20264046
MCR025188 | HPR197 | 2020-10-01 | Equipment | 4485541 | 3667663 | 2970113
MCR025189 | HPR197 | 2020-10-01 | Subcontract | 19625143 | 16046761 | 15584607
MCR025190 | HPR197 | 2020-10-01 | Overhead | 5972375 | 4883393 | 7659205
MCR025191 | HPR197 | 2020-11-01 | Labor | 14066309 | 12834075 | 13314484
MCR025192 | HPR197 | 2020-11-01 | Material | 28241859 | 25767821 | 26260284
MCR025193 | HPR197 | 2020-11-01 | Equipment | 5464325 | 4985640 | 5188036
MCR025194 | HPR197 | 2020-11-01 | Subcontract | 23907519 | 21813178 | 21243251
MCR025195 | HPR197 | 2020-11-01 | Overhead | 7275599 | 6638244 | 7744049
MCR025196 | HPR197 | 2020-12-01 | Labor | 16249699 | 12365034 | 11823507
MCR025197 | HPR197 | 2020-12-01 | Material | 32625595 | 24826097 | 25424346
MCR025198 | HPR197 | 2020-12-01 | Equipment | 6312504 | 4803432 | 5093932
MCR025199 | HPR197 | 2020-12-01 | Subcontract | 27618474 | 21015982 | 16628592
MCR025200 | HPR197 | 2020-12-01 | Overhead | 8404927 | 6395639 | 7990233
MCR025201 | HPR197 | 2021-01-01 | Labor | 18103961 | 14832905 | 17643244
MCR025202 | HPR197 | 2021-01-01 | Material | 36348519 | 29781005 | 28652113
MCR025203 | HPR197 | 2021-01-01 | Equipment | 7032827 | 5762124 | 5099082
MCR025204 | HPR197 | 2021-01-01 | Subcontract | 30770033 | 25210449 | 28141529
MCR025205 | HPR197 | 2021-01-01 | Overhead | 9364017 | 7672110 | 7887312
MCR025206 | HPR197 | 2021-02-01 | Labor | 19636484 | 11134054 | 10041200
MCR025207 | HPR197 | 2021-02-01 | Material | 39425468 | 22354577 | 22042743
MCR025208 | HPR197 | 2021-02-01 | Equipment | 7628165 | 4325235 | 5365733
MCR025209 | HPR197 | 2021-02-01 | Subcontract | 33374756 | 18923772 | 17773665
MCR025210 | HPR197 | 2021-02-01 | Overhead | 10156693 | 5758932 | 7573282
MCR025211 | HPR197 | 2021-03-01 | Labor | 20855005 | 13490134 | 14419976
MCR025212 | HPR197 | 2021-03-01 | Material | 41871973 | 27085035 | 25331235
MCR025213 | HPR197 | 2021-03-01 | Equipment | 8101523 | 5240499 | 5216641
MCR025214 | HPR197 | 2021-03-01 | Subcontract | 35445791 | 22928236 | 19894835
MCR025215 | HPR197 | 2021-03-01 | Overhead | 10786956 | 6977581 | 8303786
MCR025216 | HPR197 | 2021-04-01 | Labor | 21767646 | 20731313 | 21895703
MCR025217 | HPR197 | 2021-04-01 | Material | 43704342 | 41623629 | 50098963
MCR025218 | HPR197 | 2021-04-01 | Equipment | 8456055 | 8053472 | 7926167
MCR025219 | HPR197 | 2021-04-01 | Subcontract | 36996941 | 35235560 | 39295169
MCR025220 | HPR197 | 2021-04-01 | Overhead | 11259006 | 10722978 | 8077516
MCR025221 | HPR197 | 2021-05-01 | Labor | 22382957 | 20558321 | 22540793
MCR025222 | HPR197 | 2021-05-01 | Material | 44939743 | 41276300 | 42835388
MCR025223 | HPR197 | 2021-05-01 | Equipment | 8695084 | 7986270 | 8368953
MCR025224 | HPR197 | 2021-05-01 | Subcontract | 38042743 | 34941537 | 29664477
MCR025225 | HPR197 | 2021-05-01 | Overhead | 11577267 | 10633500 | 7574065
MCR025226 | HPR197 | 2021-06-01 | Labor | 22709974 | 24970483 | 26106079
MCR025227 | HPR197 | 2021-06-01 | Material | 45596317 | 50134891 | 52735505
MCR025228 | HPR197 | 2021-06-01 | Equipment | 8822121 | 9700258 | 10623613
MCR025229 | HPR197 | 2021-06-01 | Subcontract | 38598551 | 42440580 | 41357796
MCR025230 | HPR197 | 2021-06-01 | Overhead | 11746413 | 12915629 | 7844107
MCR025231 | HPR197 | 2021-07-01 | Labor | 22758282 | 8747198 | 9492749
MCR025232 | HPR197 | 2021-07-01 | Material | 45693308 | 17562328 | 25765361
MCR025233 | HPR197 | 2021-07-01 | Equipment | 8840887 | 3398015 | 2498642
MCR025234 | HPR197 | 2021-07-01 | Subcontract | 38680656 | 14866999 | 12824551
MCR025235 | HPR197 | 2021-07-01 | Overhead | 11771399 | 4524364 | 7095410
MCR025236 | HPR197 | 2021-08-01 | Labor | 22538089 | 10000037 | 10608545
MCR025237 | HPR197 | 2021-08-01 | Material | 45251213 | 20077735 | 24592535
MCR025238 | HPR197 | 2021-08-01 | Equipment | 8755349 | 3884704 | 4576757
MCR025239 | HPR197 | 2021-08-01 | Subcontract | 38306411 | 16996361 | 16134262
MCR025240 | HPR197 | 2021-08-01 | Overhead | 11657508 | 5172377 | 7604209
MCR025241 | HPR197 | 2021-09-01 | Labor | 22060329 | 15236652 | 14600213
MCR025242 | HPR197 | 2021-09-01 | Material | 44291982 | 30591633 | 32910425
MCR025243 | HPR197 | 2021-09-01 | Equipment | 8569754 | 5918967 | 6201836
MCR025244 | HPR197 | 2021-09-01 | Subcontract | 37494395 | 25896669 | 23663034
MCR025245 | HPR197 | 2021-09-01 | Overhead | 11410393 | 7880942 | 7991440
MCR025246 | HPR197 | 2021-10-01 | Labor | 21336775 | 17462869 | 20179600
MCR025247 | HPR197 | 2021-10-01 | Material | 42839254 | 35061357 | 41573477
MCR025248 | HPR197 | 2021-10-01 | Equipment | 8288675 | 6783783 | 6499063
MCR025249 | HPR197 | 2021-10-01 | Subcontract | 36264620 | 29680415 | 24298482
MCR025250 | HPR197 | 2021-10-01 | Overhead | 11036144 | 9032422 | 7889237
MCR025251 | HPR197 | 2021-11-01 | Labor | 20380192 | 12562740 | 14065008
MCR025252 | HPR197 | 2021-11-01 | Material | 40918660 | 25223044 | 32631276
MCR025253 | HPR197 | 2021-11-01 | Equipment | 7917073 | 4880235 | 5026186
MCR025254 | HPR197 | 2021-11-01 | Subcontract | 34638784 | 21352009 | 20902716
MCR025255 | HPR197 | 2021-11-01 | Overhead | 10541366 | 6497899 | 7532931
MCR025256 | HPR197 | 2021-12-01 | Labor | 19204537 | 16143141 | 15531801
MCR025257 | HPR197 | 2021-12-01 | Material | 38558218 | 32411652 | 35178561
MCR025258 | HPR197 | 2021-12-01 | Equipment | 7460367 | 6271110 | 6137131
MCR025259 | HPR197 | 2021-12-01 | Subcontract | 32640605 | 27437365 | 27322436
MCR025260 | HPR197 | 2021-12-01 | Overhead | 9933275 | 8349811 | 7613698
MCR025261 | HPR197 | 2022-01-01 | Labor | 17825210 | 34687036 | 37835258
MCR025262 | HPR197 | 2022-01-01 | Material | 35788853 | 69643457 | 92425055
MCR025263 | HPR197 | 2022-01-01 | Equipment | 6924541 | 13474838 | 15003095
MCR025264 | HPR197 | 2022-01-01 | Subcontract | 30296260 | 58955124 | 55500430
MCR025265 | HPR197 | 2022-01-01 | Overhead | 9219837 | 17941378 | 7221185
MCR025266 | HPR197 | 2022-02-01 | Labor | 16259410 | 17623661 | 18227001
MCR025267 | HPR197 | 2022-02-01 | Material | 32645094 | 35384190 | 41007321
MCR025268 | HPR197 | 2022-02-01 | Equipment | 6316277 | 6846246 | 6607599
MCR025269 | HPR197 | 2022-02-01 | Subcontract | 27634980 | 29953701 | 31080403
MCR025270 | HPR197 | 2022-02-01 | Overhead | 8409950 | 9115589 | 7426225
MCR025271 | HPR197 | 2022-03-01 | Labor | 14526625 | 18231226 | 19298297
MCR025272 | HPR197 | 2022-03-01 | Material | 29166066 | 36604038 | 45597411
MCR025273 | HPR197 | 2022-03-01 | Equipment | 5643143 | 7082266 | 7603222
MCR025274 | HPR197 | 2022-03-01 | Subcontract | 24689887 | 30986337 | 30611740
MCR025275 | HPR197 | 2022-03-01 | Overhead | 7513691 | 9429843 | 7056930
MCR025276 | HPR197 | 2022-04-01 | Labor | 12649344 | 13219771 | 14263305
MCR025277 | HPR197 | 2022-04-01 | Material | 25396925 | 26542209 | 34469948
MCR025278 | HPR197 | 2022-04-01 | Equipment | 4913878 | 5135471 | 4458842
MCR025279 | HPR197 | 2022-04-01 | Subcontract | 21499204 | 22468719 | 21002450
MCR025280 | HPR197 | 2022-04-01 | Overhead | 6542694 | 6837739 | 7490874
MCR025281 | HPR197 | 2022-05-01 | Labor | 10654155 | 14630842 | 16175797
MCR025282 | HPR197 | 2022-05-01 | Material | 21391053 | 29375308 | 37272711
MCR025283 | HPR197 | 2022-05-01 | Equipment | 4138809 | 5683628 | 6009728
MCR025284 | HPR197 | 2022-05-01 | Subcontract | 18108121 | 24867016 | 46800932
MCR025285 | HPR197 | 2022-05-01 | Overhead | 5510711 | 7567596 | 7617615
MCR025286 | HPR197 | 2022-06-01 | Labor | 8573533 | 12421365 | 13663346
MCR025287 | HPR197 | 2022-06-01 | Material | 17213650 | 24939197 | 27121681
MCR025288 | HPR197 | 2022-06-01 | Equipment | 3330552 | 4825315 | 4869557
MCR025289 | HPR197 | 2022-06-01 | Subcontract | 14571834 | 21111724 | 32176833
MCR025290 | HPR197 | 2022-06-01 | Overhead | 4434539 | 6424775 | 7586865
MCR025291 | HPR197 | 2022-07-01 | Labor | 6449034 | 13999314 | 15464062
MCR025292 | HPR197 | 2022-07-01 | Material | 12948152 | 28107349 | 36419454
MCR025293 | HPR197 | 2022-07-01 | Equipment | 2505250 | 5438299 | 5985727
MCR025294 | HPR197 | 2022-07-01 | Subcontract | 10960971 | 23793653 | 29134464
MCR025295 | HPR197 | 2022-07-01 | Overhead | 3335671 | 7240947 | 7279134
MCR025296 | HPR197 | 2022-08-01 | Labor | 4337787 | 6586582 | 5834439
MCR025297 | HPR197 | 2022-08-01 | Material | 8709262 | 13224317 | 16144643
MCR025298 | HPR197 | 2022-08-01 | Equipment | 1685096 | 2558683 | 2760075
MCR025299 | HPR197 | 2022-08-01 | Subcontract | 7372633 | 11194752 | 17466427
MCR025300 | HPR197 | 2022-08-01 | Overhead | 2243659 | 3406816 | 7238212
MCR025301 | HPR197 | 2022-09-01 | Labor | 2328889 | 18876709 | 20644299
MCR025302 | HPR197 | 2022-09-01 | Material | 4675865 | 37900017 | 46838823
MCR025303 | HPR197 | 2022-09-01 | Equipment | 904701 | 7333016 | 7821697
MCR025304 | HPR197 | 2022-09-01 | Subcontract | 3958250 | 32083419 | 40298502
MCR025305 | HPR197 | 2022-09-01 | Overhead | 1204585 | 9763710 | 7626225
MCR025306 | HPR197 | 2022-10-01 | Labor | 613048 | 8628726 | 8186954
MCR025307 | HPR197 | 2022-10-01 | Material | 1230858 | 17324463 | 24145781
MCR025308 | HPR197 | 2022-10-01 | Equipment | 238150 | 3351992 | 3393141
MCR025309 | HPR197 | 2022-10-01 | Subcontract | 1041955 | 14665640 | 23157756
MCR025310 | HPR197 | 2022-10-01 | Overhead | 317091 | 4463086 | 7641122
MCR025311 | HPR197 | 2022-11-01 | Labor | 0 | 7907711 | 9293949
MCR025312 | HPR197 | 2022-11-01 | Material | 0 | 15876835 | 22405562
MCR025313 | HPR197 | 2022-11-01 | Equipment | 0 | 3071901 | 2859356
MCR025314 | HPR197 | 2022-11-01 | Subcontract | 0 | 13440183 | 35555956
MCR025315 | HPR197 | 2022-11-01 | Overhead | 0 | 4090152 | 8077125
MCR025316 | HPR197 | 2022-12-01 | Labor | 0 | 5272355 | 4674656
MCR025317 | HPR197 | 2022-12-01 | Material | 0 | 10585655 | 10181046
MCR025318 | HPR197 | 2022-12-01 | Equipment | 0 | 2048146 | 2225975
MCR025319 | HPR197 | 2022-12-01 | Subcontract | 0 | 8961052 | 16895076
MCR025320 | HPR197 | 2022-12-01 | Overhead | 0 | 2727051 | 7797115
MCR025321 | HPR197 | 2023-01-01 | Labor | 0 | 1772351 | 2093518
MCR025322 | HPR197 | 2023-01-01 | Material | 0 | 3558466 | 4521258
MCR025323 | HPR197 | 2023-01-01 | Equipment | 0 | 688503 | 720812
MCR025324 | HPR197 | 2023-01-01 | Subcontract | 0 | 3012340 | 19823534
MCR025325 | HPR197 | 2023-01-01 | Overhead | 0 | 916723 | 7586323
MCR025326 | HPR197 | 2023-02-01 | Labor | 0 | 1208673 | 1409441
MCR025327 | HPR197 | 2023-02-01 | Material | 0 | 2426733 | 3587492
MCR025328 | HPR197 | 2023-02-01 | Equipment | 0 | 469532 | 515906
MCR025329 | HPR197 | 2023-02-01 | Subcontract | 0 | 2054297 | 20003817
MCR025330 | HPR197 | 2023-02-01 | Overhead | 0 | 625169 | 7224713
MCR025331 | HPR197 | 2023-03-01 | Labor | 0 | 477576 | 475766
MCR025332 | HPR197 | 2023-03-01 | Material | 0 | 958861 | 921636
MCR025333 | HPR197 | 2023-03-01 | Equipment | 0 | 185523 | 191823
MCR025334 | HPR197 | 2023-03-01 | Subcontract | 0 | 811703 | 20592018
MCR025335 | HPR197 | 2023-03-01 | Overhead | 0 | 247019 | 7588243
MCR025336 | HPR198 | 2022-12-01 | Labor | 5142230 | 4137112 | 4916508
MCR025337 | HPR198 | 2022-12-01 | Material | 11164228 | 8982030 | 8503010
MCR025338 | HPR198 | 2022-12-01 | Equipment | 2415434 | 1943305 | 2134036
MCR025339 | HPR198 | 2022-12-01 | Subcontract | 11841477 | 9526902 | 10315099
MCR025340 | HPR198 | 2022-12-01 | Overhead | 3450653 | 2776176 | 19109600
MCR025341 | HPR198 | 2023-01-01 | Labor | 14596550 | 7714362 | 7870976
MCR025342 | HPR198 | 2023-01-01 | Material | 31690380 | 16748552 | 14779376
MCR025343 | HPR198 | 2023-01-01 | Equipment | 6856365 | 3623629 | 3544517
MCR025344 | HPR198 | 2023-01-01 | Subcontract | 33612795 | 17764560 | 18727937
MCR025345 | HPR198 | 2023-01-01 | Overhead | 9794900 | 5176662 | 20717071
MCR025346 | HPR198 | 2023-02-01 | Labor | 22826128 | 9638126 | 10168464
MCR025347 | HPR198 | 2023-02-01 | Material | 49557511 | 20925210 | 22377820
MCR025348 | HPR198 | 2023-02-01 | Equipment | 10722003 | 4527269 | 5104500
MCR025349 | HPR198 | 2023-02-01 | Subcontract | 52563789 | 22194584 | 22591401
MCR025350 | HPR198 | 2023-02-01 | Overhead | 15317294 | 6467588 | 19524265
MCR025351 | HPR198 | 2023-03-01 | Labor | 29859293 | 14292133 | 16221697
MCR025352 | HPR198 | 2023-03-01 | Material | 64827126 | 31029465 | 29566559
MCR025353 | HPR198 | 2023-03-01 | Equipment | 14025657 | 6713372 | 6206087
MCR025354 | HPR198 | 2023-03-01 | Subcontract | 68759696 | 32911787 | 37657657
MCR025355 | HPR198 | 2023-03-01 | Overhead | 20036844 | 9590623 | 19651886
MCR025356 | HPR198 | 2023-04-01 | Labor | 35725803 | 23267226 | 25647992
MCR025357 | HPR198 | 2023-04-01 | Material | 77563831 | 50515173 | 44936778
MCR025358 | HPR198 | 2023-04-01 | Equipment | 16781304 | 10929198 | 12062580
MCR025359 | HPR198 | 2023-04-01 | Subcontract | 82269040 | 53579545 | 51999088
MCR025360 | HPR198 | 2023-04-01 | Overhead | 23973520 | 15613289 | 21060605
MCR025361 | HPR198 | 2023-05-01 | Labor | 40457014 | 26801961 | 33427314
MCR025362 | HPR198 | 2023-05-01 | Material | 87835700 | 58189391 | 54146268
MCR025363 | HPR198 | 2023-05-01 | Equipment | 19003671 | 12589552 | 12619945
MCR025364 | HPR198 | 2023-05-01 | Subcontract | 93164026 | 61719300 | 68153522
MCR025365 | HPR198 | 2023-05-01 | Overhead | 27148361 | 17985245 | 20662112
MCR025366 | HPR198 | 2023-06-01 | Labor | 44086086 | 31257980 | 35851242
MCR025367 | HPR198 | 2023-06-01 | Material | 95714732 | 67863796 | 70257446
MCR025368 | HPR198 | 2023-06-01 | Equipment | 20708337 | 14682655 | 16239571
MCR025369 | HPR198 | 2023-06-01 | Subcontract | 101521018 | 71980578 | 68550737
MCR025370 | HPR198 | 2023-06-01 | Overhead | 29583622 | 20975422 | 21258950
MCR025371 | HPR198 | 2023-07-01 | Labor | 46648236 | 30564006 | 31706406
MCR025372 | HPR198 | 2023-07-01 | Material | 101277383 | 66357118 | 66254768
MCR025373 | HPR198 | 2023-07-01 | Equipment | 21911843 | 14356678 | 14711819
MCR025374 | HPR198 | 2023-07-01 | Subcontract | 107421114 | 70382501 | 72199923
MCR025375 | HPR198 | 2023-07-01 | Overhead | 31302932 | 20509736 | 21562063
MCR025376 | HPR198 | 2023-08-01 | Labor | 48181042 | 29357687 | 31649159
MCR025377 | HPR198 | 2023-08-01 | Material | 104605238 | 63738096 | 64791694
MCR025378 | HPR198 | 2023-08-01 | Equipment | 22631841 | 13790040 | 13533724
MCR025379 | HPR198 | 2023-08-01 | Subcontract | 110950845 | 67604603 | 72388806
MCR025380 | HPR198 | 2023-08-01 | Overhead | 32331510 | 19700246 | 22000839
MCR025381 | HPR198 | 2023-09-01 | Labor | 48724822 | 57859217 | 65335513
MCR025382 | HPR198 | 2023-09-01 | Material | 105785832 | 125617399 | 133115079
MCR025383 | HPR198 | 2023-09-01 | Equipment | 22887268 | 27177922 | 29478490
MCR025384 | HPR198 | 2023-09-01 | Subcontract | 112203056 | 133237654 | 102205438
MCR025385 | HPR198 | 2023-09-01 | Overhead | 32696409 | 38825973 | 21350119
MCR025386 | HPR198 | 2023-10-01 | Labor | 48323113 | 68329216 | 79774377
MCR025387 | HPR198 | 2023-10-01 | Material | 104913687 | 148348679 | 146086401
MCR025388 | HPR198 | 2023-10-01 | Equipment | 22698575 | 32095942 | 30584045
MCR025389 | HPR198 | 2023-10-01 | Subcontract | 111278004 | 157347868 | 168811616
MCR025390 | HPR198 | 2023-10-01 | Overhead | 32426845 | 45851784 | 19389967
MCR025391 | HPR198 | 2023-11-01 | Labor | 47023289 | 36723366 | 46365720
MCR025392 | HPR198 | 2023-11-01 | Material | 102091656 | 79729626 | 66075856
MCR025393 | HPR198 | 2023-11-01 | Equipment | 22088015 | 17249884 | 16251180
MCR025394 | HPR198 | 2023-11-01 | Subcontract | 108284782 | 84566217 | 93398750
MCR025395 | HPR198 | 2023-11-01 | Overhead | 31554609 | 24642926 | 19792421
MCR025396 | HPR198 | 2023-12-01 | Labor | 44877372 | 51567924 | 62569764
MCR025397 | HPR198 | 2023-12-01 | Material | 97432682 | 111958453 | 124057742
MCR025398 | HPR198 | 2023-12-01 | Equipment | 21080024 | 24222744 | 25985218
MCR025399 | HPR198 | 2023-12-01 | Subcontract | 103343184 | 118750123 | 99797342
MCR025400 | HPR198 | 2023-12-01 | Overhead | 30114608 | 34604250 | 19386955
MCR025401 | HPR198 | 2024-01-01 | Labor | 41943124 | 30433188 | 35614294
MCR025402 | HPR198 | 2024-01-01 | Material | 91062175 | 66073101 | 57263118
MCR025403 | HPR198 | 2024-01-01 | Equipment | 19701735 | 14295230 | 15873533
MCR025404 | HPR198 | 2024-01-01 | Subcontract | 96586226 | 70081255 | 82653890
MCR025405 | HPR198 | 2024-01-01 | Overhead | 28145604 | 20421952 | 19295995
MCR025406 | HPR198 | 2024-02-01 | Labor | 38285580 | 46671093 | 41631947
MCR025407 | HPR198 | 2024-02-01 | Material | 83121329 | 101327008 | 113609244
MCR025408 | HPR198 | 2024-02-01 | Equipment | 17983695 | 21922580 | 21114345
MCR025409 | HPR198 | 2024-02-01 | Subcontract | 88163670 | 107473749 | 112571004
MCR025410 | HPR198 | 2024-02-01 | Overhead | 25691238 | 31318271 | 21205933
MCR025411 | HPR198 | 2024-03-01 | Labor | 33979260 | 29324583 | 38875819
MCR025412 | HPR198 | 2024-03-01 | Material | 73771934 | 63666224 | 59188647
MCR025413 | HPR198 | 2024-03-01 | Equipment | 15960909 | 13774490 | 15293252
MCR025414 | HPR198 | 2024-03-01 | Subcontract | 78247117 | 67528370 | 65139133
MCR025415 | HPR198 | 2024-03-01 | Overhead | 22801516 | 19678031 | 20637465
MCR025416 | HPR198 | 2024-04-01 | Labor | 29111542 | 28955858 | 26266223
MCR025417 | HPR198 | 2024-04-01 | Material | 63203692 | 62865689 | 56304616
MCR025418 | HPR198 | 2024-04-01 | Equipment | 13674419 | 13601291 | 14314456
MCR025419 | HPR198 | 2024-04-01 | Subcontract | 67037781 | 66679274 | 71812843
MCR025420 | HPR198 | 2024-04-01 | Overhead | 19535071 | 19430601 | 22833428
MCR025421 | HPR198 | 2024-05-01 | Labor | 23788142 | 29587343 | 31927246
MCR025422 | HPR198 | 2024-05-01 | Material | 51646127 | 64236698 | 51762671
MCR025423 | HPR198 | 2024-05-01 | Equipment | 11173885 | 13897915 | 14664904
MCR025424 | HPR198 | 2024-05-01 | Subcontract | 54779106 | 68133451 | 94685351
MCR025425 | HPR198 | 2024-05-01 | Overhead | 15962846 | 19854354 | 22557439
MCR025426 | HPR198 | 2024-06-01 | Labor | 18142848 | 20570616 | 29052494
MCR025427 | HPR198 | 2024-06-01 | Material | 39389702 | 44660599 | 56368341
MCR025428 | HPR198 | 2024-06-01 | Equipment | 8522149 | 9662533 | 8412555
MCR025429 | HPR198 | 2024-06-01 | Subcontract | 41779177 | 47369819 | 73056963
MCR025430 | HPR198 | 2024-06-01 | Overhead | 12174615 | 13803750 | 19749153
MCR025431 | HPR198 | 2024-07-01 | Labor | 12357169 | 14204609 | 13264254
MCR025432 | HPR198 | 2024-07-01 | Material | 26828490 | 30839444 | 30839668
MCR025433 | HPR198 | 2024-07-01 | Equipment | 5804471 | 6672260 | 7424452
MCR025434 | HPR198 | 2024-07-01 | Subcontract | 28455971 | 32710239 | 56617126
MCR025435 | HPR198 | 2024-07-01 | Overhead | 8292181 | 9531891 | 20309365
MCR025436 | HPR198 | 2024-08-01 | Labor | 6709586 | 14838428 | 18097913
MCR025437 | HPR198 | 2024-08-01 | Material | 14567095 | 32215520 | 29301968
MCR025438 | HPR198 | 2024-08-01 | Equipment | 3151660 | 6969981 | 6612642
MCR025439 | HPR198 | 2024-08-01 | Subcontract | 15450770 | 34169791 | 71175253
MCR025440 | HPR198 | 2024-08-01 | Overhead | 4502415 | 9957211 | 20663394
MCR025441 | HPR198 | 2024-09-01 | Labor | 1782823 | 18188118 | 20106931
MCR025442 | HPR198 | 2024-09-01 | Material | 3870665 | 39487989 | 42294926
MCR025443 | HPR198 | 2024-09-01 | Equipment | 837437 | 8543414 | 8882607
MCR025444 | HPR198 | 2024-09-01 | Subcontract | 4105469 | 41883426 | 63851092
MCR025445 | HPR198 | 2024-09-01 | Overhead | 1196350 | 12204994 | 20735557
MCR025446 | HPR198 | 2024-10-01 | Labor | 0 | 22986787 | 24642198
MCR025447 | HPR198 | 2024-10-01 | Material | 0 | 49906317 | 45550062
MCR025448 | HPR198 | 2024-10-01 | Equipment | 0 | 10797469 | 11024811
MCR025449 | HPR198 | 2024-10-01 | Subcontract | 0 | 52933754 | 89279971
MCR025450 | HPR198 | 2024-10-01 | Overhead | 0 | 15425103 | 20444097
MCR025451 | HPR198 | 2024-11-01 | Labor | 0 | 9463451 | 10966746
MCR025452 | HPR198 | 2024-11-01 | Material | 0 | 20545977 | 20171941
MCR025453 | HPR198 | 2024-11-01 | Equipment | 0 | 4445220 | 4646544
MCR025454 | HPR198 | 2024-11-01 | Subcontract | 0 | 21792345 | 64990689
MCR025455 | HPR198 | 2024-11-01 | Overhead | 0 | 6350375 | 20937858
MCR025456 | HPR198 | 2024-12-01 | Labor | 0 | 19335489 | 18502371
MCR025457 | HPR198 | 2024-12-01 | Material | 0 | 41979030 | 42028215
MCR025458 | HPR198 | 2024-12-01 | Equipment | 0 | 9082363 | 9986543
MCR025459 | HPR198 | 2024-12-01 | Subcontract | 0 | 44525579 | 69821237
MCR025460 | HPR198 | 2024-12-01 | Overhead | 0 | 12974928 | 20786277
MCR025461 | HPR198 | 2025-01-01 | Labor | 0 | 5298331 | 7073106
MCR025462 | HPR198 | 2025-01-01 | Material | 0 | 11503138 | 12859230
MCR025463 | HPR198 | 2025-01-01 | Equipment | 0 | 2488759 | 2695630
MCR025464 | HPR198 | 2025-01-01 | Subcontract | 0 | 12200946 | 32328653
MCR025465 | HPR198 | 2025-01-01 | Overhead | 0 | 3555403 | 19654446
MCR025466 | HPR198 | 2025-02-01 | Labor | 0 | 1202842 | 1930998
MCR025467 | HPR198 | 2025-02-01 | Material | 0 | 2611474 | 2038959
MCR025468 | HPR198 | 2025-02-01 | Equipment | 0 | 565005 | 776074
MCR025469 | HPR198 | 2025-02-01 | Subcontract | 0 | 2769892 | 29014531
MCR025470 | HPR198 | 2025-02-01 | Overhead | 0 | 807157 | 21290108
MCR025471 | HPR199 | 2019-11-01 | Labor | 3413617 | 1234998 | 1302618
MCR025472 | HPR199 | 2019-11-01 | Material | 8869157 | 3208736 | 3334912
MCR025473 | HPR199 | 2019-11-01 | Equipment | 1718934 | 621886 | 657107
MCR025474 | HPR199 | 2019-11-01 | Subcontract | 17086223 | 6181554 | 6363658
MCR025475 | HPR199 | 2019-11-01 | Overhead | 2906676 | 1051594 | 19339213
MCR025476 | HPR199 | 2019-12-01 | Labor | 9793839 | 7561959 | 7209121
MCR025477 | HPR199 | 2019-12-01 | Material | 25446062 | 19647257 | 21131034
MCR025478 | HPR199 | 2019-12-01 | Equipment | 4931710 | 3807841 | 3850644
MCR025479 | HPR199 | 2019-12-01 | Subcontract | 49021243 | 37849981 | 41446531
MCR025480 | HPR199 | 2019-12-01 | Overhead | 8339401 | 6438967 | 22508139
MCR025481 | HPR199 | 2020-01-01 | Labor | 15512409 | 14684933 | 13672921
MCR025482 | HPR199 | 2020-01-01 | Material | 40303880 | 38153956 | 41421964
MCR025483 | HPR199 | 2020-01-01 | Equipment | 7811308 | 7394631 | 7973617
MCR025484 | HPR199 | 2020-01-01 | Subcontract | 77644480 | 73502702 | 66965223
MCR025485 | HPR199 | 2020-01-01 | Overhead | 13208732 | 12504141 | 23278864
MCR025486 | HPR199 | 2020-02-01 | Labor | 20581501 | 17123055 | 19984672
MCR025487 | HPR199 | 2020-02-01 | Material | 53474243 | 44488613 | 37606508
MCR025488 | HPR199 | 2020-02-01 | Equipment | 10363860 | 8622353 | 9124497
MCR025489 | HPR199 | 2020-02-01 | Subcontract | 103016875 | 85706270 | 82203748
MCR025490 | HPR199 | 2020-02-01 | Overhead | 17525036 | 14580188 | 21437409
MCR025491 | HPR199 | 2020-03-01 | Labor | 25013772 | 12391782 | 13690400
MCR025492 | HPR199 | 2020-03-01 | Material | 64990039 | 32195959 | 37508782
MCR025493 | HPR199 | 2020-03-01 | Equipment | 12595741 | 6239909 | 6239870
MCR025494 | HPR199 | 2020-03-01 | Subcontract | 125201786 | 62024761 | 76801509
MCR025495 | HPR199 | 2020-03-01 | Overhead | 21299091 | 10551535 | 21320356
MCR025496 | HPR199 | 2020-04-01 | Labor | 28822409 | 10814044 | 11684592
MCR025497 | HPR199 | 2020-04-01 | Material | 74885527 | 28096728 | 26016458
MCR025498 | HPR199 | 2020-04-01 | Equipment | 14513588 | 5445436 | 5519553
MCR025499 | HPR199 | 2020-04-01 | Subcontract | 144265212 | 54127688 | 46952221
MCR025500 | HPR199 | 2020-04-01 | Overhead | 24542125 | 9208100 | 21374442
MCR025501 | HPR199 | 2020-05-01 | Labor | 32021179 | 22997223 | 20334075
MCR025502 | HPR199 | 2020-05-01 | Material | 83196476 | 59750701 | 64192172
MCR025503 | HPR199 | 2020-05-01 | Equipment | 16124336 | 11580303 | 11259458
MCR025504 | HPR199 | 2020-05-01 | Subcontract | 160276061 | 115108325 | 129974843
MCR025505 | HPR199 | 2020-05-01 | Overhead | 27265860 | 19582010 | 21595401
MCR025506 | HPR199 | 2020-06-01 | Labor | 34624490 | 26121478 | 31277029
MCR025507 | HPR199 | 2020-06-01 | Material | 89960320 | 67868048 | 72690912
MCR025508 | HPR199 | 2020-06-01 | Equipment | 17435239 | 13153529 | 15039519
MCR025509 | HPR199 | 2020-06-01 | Subcontract | 173306447 | 130746204 | 141573363
MCR025510 | HPR199 | 2020-06-01 | Overhead | 29482565 | 22242297 | 20753397
MCR025511 | HPR199 | 2020-07-01 | Labor | 36647460 | 18687768 | 18472280
MCR025512 | HPR199 | 2020-07-01 | Material | 95216341 | 48554004 | 49230304
MCR025513 | HPR199 | 2020-07-01 | Equipment | 18453910 | 9410267 | 10273414
MCR025514 | HPR199 | 2020-07-01 | Subcontract | 183432048 | 93538151 | 95220062
MCR025515 | HPR199 | 2020-07-01 | Overhead | 31205113 | 15912533 | 21749809
MCR025516 | HPR199 | 2020-08-01 | Labor | 38106004 | 23854058 | 23155151
MCR025517 | HPR199 | 2020-08-01 | Material | 99005886 | 61976903 | 63740233
MCR025518 | HPR199 | 2020-08-01 | Equipment | 19188363 | 12011764 | 12793669
MCR025519 | HPR199 | 2020-08-01 | Subcontract | 190732519 | 119397051 | 113392138
MCR025520 | HPR199 | 2020-08-01 | Overhead | 32447055 | 20311600 | 20836058
MCR025521 | HPR199 | 2020-09-01 | Labor | 39016929 | 33970199 | 34549323
MCR025522 | HPR199 | 2020-09-01 | Material | 101372626 | 88260361 | 79761652
MCR025523 | HPR199 | 2020-09-01 | Equipment | 19647062 | 17105769 | 17521381
MCR025524 | HPR199 | 2020-09-01 | Subcontract | 195291987 | 170031516 | 181084949
MCR025525 | HPR199 | 2020-09-01 | Overhead | 33222703 | 28925440 | 23198332
MCR025526 | HPR199 | 2020-10-01 | Labor | 39398055 | 24156668 | 25307541
MCR025527 | HPR199 | 2020-10-01 | Material | 102362856 | 62763136 | 67978775
MCR025528 | HPR199 | 2020-10-01 | Equipment | 19838978 | 12164144 | 11572085
MCR025529 | HPR199 | 2020-10-01 | Subcontract | 197199642 | 120911711 | 138169835
MCR025530 | HPR199 | 2020-10-01 | Overhead | 33547230 | 20569271 | 22236130
MCR025531 | HPR199 | 2020-11-01 | Labor | 39268356 | 28394652 | 28873102
MCR025532 | HPR199 | 2020-11-01 | Material | 102025875 | 73774141 | 73412074
MCR025533 | HPR199 | 2020-11-01 | Equipment | 19773668 | 14298190 | 14388072
MCR025534 | HPR199 | 2020-11-01 | Subcontract | 196550456 | 142124153 | 151717578
MCR025535 | HPR199 | 2020-11-01 | Overhead | 33436792 | 24177892 | 22601368
MCR025536 | HPR199 | 2020-12-01 | Labor | 38648136 | 44545271 | 40157039
MCR025537 | HPR199 | 2020-12-01 | Material | 100414439 | 115736198 | 118145447
MCR025538 | HPR199 | 2020-12-01 | Equipment | 19461355 | 22430870 | 26783787
MCR025539 | HPR199 | 2020-12-01 | Subcontract | 193446062 | 222963072 | 230282886
MCR025540 | HPR199 | 2020-12-01 | Overhead | 32908678 | 37930056 | 21871346
MCR025541 | HPR199 | 2021-01-01 | Labor | 37559252 | 24691482 | 28477259
MCR025542 | HPR199 | 2021-01-01 | Material | 97585331 | 64152674 | 78855000
MCR025543 | HPR199 | 2021-01-01 | Equipment | 18913045 | 12433451 | 9804076
MCR025544 | HPR199 | 2021-01-01 | Subcontract | 187995853 | 123588624 | 138896168
MCR025545 | HPR199 | 2021-01-01 | Overhead | 31981499 | 21024663 | 23358485
MCR025546 | HPR199 | 2021-02-01 | Labor | 36025386 | 32495106 | 32530759
MCR025547 | HPR199 | 2021-02-01 | Material | 93600086 | 84427818 | 73199898
MCR025548 | HPR199 | 2021-02-01 | Equipment | 18140663 | 16362983 | 16153686
MCR025549 | HPR199 | 2021-02-01 | Subcontract | 180318371 | 162648212 | 172535358
MCR025550 | HPR199 | 2021-02-01 | Overhead | 30675420 | 27669406 | 22784716
MCR025551 | HPR199 | 2021-03-01 | Labor | 34072407 | 31457554 | 35812369
MCR025552 | HPR199 | 2021-03-01 | Material | 88525915 | 81732082 | 87836126
MCR025553 | HPR199 | 2021-03-01 | Equipment | 17157236 | 15840521 | 15573158
MCR025554 | HPR199 | 2021-03-01 | Subcontract | 170543101 | 157454941 | 163001893
MCR025555 | HPR199 | 2021-03-01 | Overhead | 29012470 | 26785937 | 21391825
MCR025556 | HPR199 | 2021-04-01 | Labor | 31728846 | 33549302 | 32667729
MCR025557 | HPR199 | 2021-04-01 | Material | 82436945 | 87166798 | 90252954
MCR025558 | HPR199 | 2021-04-01 | Equipment | 15977131 | 16893825 | 20461947
MCR025559 | HPR199 | 2021-04-01 | Subcontract | 158812842 | 167924793 | 182130835
MCR025560 | HPR199 | 2021-04-01 | Overhead | 27016940 | 28567048 | 19488914
MCR025561 | HPR199 | 2021-05-01 | Labor | 29026534 | 16226202 | 16551365
MCR025562 | HPR199 | 2021-05-01 | Material | 75415877 | 42158435 | 49242201
MCR025563 | HPR199 | 2021-05-01 | Equipment | 14616376 | 8170740 | 7495100
MCR025564 | HPR199 | 2021-05-01 | Subcontract | 145286918 | 81217236 | 83668742
MCR025565 | HPR199 | 2021-05-01 | Overhead | 24715936 | 13816523 | 21816414
MCR025566 | HPR199 | 2021-06-01 | Labor | 26001500 | 20050621 | 22071587
MCR025567 | HPR199 | 2021-06-01 | Material | 67556324 | 52094926 | 54362495
MCR025568 | HPR199 | 2021-06-01 | Equipment | 13093113 | 10096535 | 9824362
MCR025569 | HPR199 | 2021-06-01 | Subcontract | 130145674 | 100359654 | 107754711
MCR025570 | HPR199 | 2021-06-01 | Overhead | 22140136 | 17072994 | 22075212
MCR025571 | HPR199 | 2021-07-01 | Labor | 22695283 | 34685000 | 34194364
MCR025572 | HPR199 | 2021-07-01 | Material | 58966210 | 90117535 | 98549035
MCR025573 | HPR199 | 2021-07-01 | Equipment | 11428260 | 17465709 | 20117872
MCR025574 | HPR199 | 2021-07-01 | Subcontract | 113597021 | 173609319 | 184303721
MCR025575 | HPR199 | 2021-07-01 | Overhead | 19324910 | 29534089 | 21528376
MCR025576 | HPR199 | 2021-08-01 | Labor | 19156929 | 14853418 | 14483842
MCR025577 | HPR199 | 2021-08-01 | Material | 49772964 | 38591708 | 34165325
MCR025578 | HPR199 | 2021-08-01 | Equipment | 9646514 | 7479471 | 6246107
MCR025579 | HPR199 | 2021-08-01 | Subcontract | 95886449 | 74346021 | 83400271
MCR025580 | HPR199 | 2021-08-01 | Overhead | 16312021 | 12647604 | 22228832
MCR025581 | HPR199 | 2021-09-01 | Labor | 15446260 | 30394244 | 31372334
MCR025582 | HPR199 | 2021-09-01 | Material | 40132014 | 78969421 | 95611598
MCR025583 | HPR199 | 2021-09-01 | Equipment | 7777999 | 15305089 | 16618665
MCR025584 | HPR199 | 2021-09-01 | Subcontract | 77313384 | 152132739 | 171109009
MCR025585 | HPR199 | 2021-09-01 | Overhead | 13152407 | 25880534 | 21354717
MCR025586 | HPR199 | 2021-10-01 | Labor | 11639698 | 21086119 | 24896999
MCR025587 | HPR199 | 2021-10-01 | Material | 30241918 | 54785327 | 46956374
MCR025588 | HPR199 | 2021-10-01 | Equipment | 5861196 | 10617962 | 10553104
MCR025589 | HPR199 | 2021-10-01 | Subcontract | 58260346 | 105542648 | 111868597
MCR025590 | HPR199 | 2021-10-01 | Overhead | 9911140 | 17954716 | 22013258
MCR025591 | HPR199 | 2021-11-01 | Labor | 7842106 | 12752263 | 11144324
MCR025592 | HPR199 | 2021-11-01 | Material | 20375126 | 33132551 | 35112728
MCR025593 | HPR199 | 2021-11-01 | Equipment | 3948910 | 6421431 | 6435834
MCR025594 | HPR199 | 2021-11-01 | Subcontract | 39252203 | 63829083 | 57718787
MCR025595 | HPR199 | 2021-11-01 | Overhead | 6677510 | 10858483 | 21362984
MCR025596 | HPR199 | 2021-12-01 | Labor | 4216632 | 35714730 | 34330161
MCR025597 | HPR199 | 2021-12-01 | Material | 10955527 | 92792948 | 97518819
MCR025598 | HPR199 | 2021-12-01 | Equipment | 2123294 | 17984231 | 19366934
MCR025599 | HPR199 | 2021-12-01 | Subcontract | 21105567 | 178763439 | 218494878
MCR025600 | HPR199 | 2021-12-01 | Overhead | 3590439 | 30410898 | 20301482
MCR025601 | HPR199 | 2022-01-01 | Labor | 1111369 | 31425904 | 34712539
MCR025602 | HPR199 | 2022-01-01 | Material | 2887526 | 81649850 | 74486659
MCR025603 | HPR199 | 2022-01-01 | Equipment | 559632 | 15824584 | 15504896
MCR025604 | HPR199 | 2022-01-01 | Subcontract | 5562751 | 157296521 | 148902281
MCR025605 | HPR199 | 2022-01-01 | Overhead | 946325 | 26758987 | 19946104
MCR025606 | HPR199 | 2022-02-01 | Labor | 0 | 13053189 | 13307073
MCR025607 | HPR199 | 2022-02-01 | Material | 0 | 33914408 | 40336663
MCR025608 | HPR199 | 2022-02-01 | Equipment | 0 | 6572962 | 8414700
MCR025609 | HPR199 | 2022-02-01 | Subcontract | 0 | 65335312 | 65769254
MCR025610 | HPR199 | 2022-02-01 | Overhead | 0 | 11114720 | 23005786
MCR025611 | HPR199 | 2022-03-01 | Labor | 0 | 10450249 | 11418289
MCR025612 | HPR199 | 2022-03-01 | Material | 0 | 27151527 | 32745647
MCR025613 | HPR199 | 2022-03-01 | Equipment | 0 | 5262246 | 5515143
MCR025614 | HPR199 | 2022-03-01 | Subcontract | 0 | 52306780 | 62984544
MCR025615 | HPR199 | 2022-03-01 | Overhead | 0 | 8898330 | 20929071
MCR025616 | HPR199 | 2022-04-01 | Labor | 0 | 7698674 | 7201163
MCR025617 | HPR199 | 2022-04-01 | Material | 0 | 20002467 | 20833634
MCR025618 | HPR199 | 2022-04-01 | Equipment | 0 | 3876685 | 3977495
MCR025619 | HPR199 | 2022-04-01 | Subcontract | 0 | 38534283 | 37845648
MCR025620 | HPR199 | 2022-04-01 | Overhead | 0 | 6555379 | 20987759
MCR025621 | HPR199 | 2022-05-01 | Labor | 0 | 7958751 | 9002455
MCR025622 | HPR199 | 2022-05-01 | Material | 0 | 20678190 | 18117716
MCR025623 | HPR199 | 2022-05-01 | Equipment | 0 | 4007647 | 3957774
MCR025624 | HPR199 | 2022-05-01 | Subcontract | 0 | 39836048 | 39550028
MCR025625 | HPR199 | 2022-05-01 | Overhead | 0 | 6776833 | 22275535
MCR025626 | HPR199 | 2022-06-01 | Labor | 0 | 7192617 | 7282617
MCR025627 | HPR199 | 2022-06-01 | Material | 0 | 18687644 | 20474113
MCR025628 | HPR199 | 2022-06-01 | Equipment | 0 | 3621858 | 4399858
MCR025629 | HPR199 | 2022-06-01 | Subcontract | 0 | 36001309 | 40721965
MCR025630 | HPR199 | 2022-06-01 | Overhead | 0 | 6124474 | 20417600
MCR025631 | HPR199 | 2022-07-01 | Labor | 0 | 2837318 | 2832985
MCR025632 | HPR199 | 2022-07-01 | Material | 0 | 7371834 | 7644706
MCR025633 | HPR199 | 2022-07-01 | Equipment | 0 | 1428738 | 1517504
MCR025634 | HPR199 | 2022-07-01 | Subcontract | 0 | 14201666 | 12698513
MCR025635 | HPR199 | 2022-07-01 | Overhead | 0 | 2415961 | 19971463
MCR025636 | HPR199 | 2022-08-01 | Labor | 0 | 1328604 | 1545773
MCR025637 | HPR199 | 2022-08-01 | Material | 0 | 3451938 | 3887791
MCR025638 | HPR199 | 2022-08-01 | Equipment | 0 | 669021 | 904382
MCR025639 | HPR199 | 2022-08-01 | Subcontract | 0 | 6650078 | 8541886
MCR025640 | HPR199 | 2022-08-01 | Overhead | 0 | 1131299 | 22547635
MCR025641 | HPR199 | 2022-09-01 | Labor | 0 | 950925 | 1105148
MCR025642 | HPR199 | 2022-09-01 | Material | 0 | 2470665 | 2238750
MCR025643 | HPR199 | 2022-09-01 | Equipment | 0 | 478840 | 502183
MCR025644 | HPR199 | 2022-09-01 | Subcontract | 0 | 4759678 | 4528196
MCR025645 | HPR199 | 2022-09-01 | Overhead | 0 | 809707 | 22086469
MCR025646 | HPR200 | 2016-11-01 | Labor | 18468151 | 8518720 | 9165513
MCR025647 | HPR200 | 2016-11-01 | Material | 36632157 | 16897149 | 16051042
MCR025648 | HPR200 | 2016-11-01 | Equipment | 9016387 | 4158948 | 4110736
MCR025649 | HPR200 | 2016-11-01 | Subcontract | 63709176 | 29386843 | 30165936
MCR025650 | HPR200 | 2016-11-01 | Overhead | 14395325 | 6640066 | 48604764
MCR025651 | HPR200 | 2016-12-01 | Labor | 48649745 | 27994073 | 29697856
MCR025652 | HPR200 | 2016-12-01 | Material | 96498297 | 55527122 | 56710585
MCR025653 | HPR200 | 2016-12-01 | Equipment | 23751426 | 13667064 | 16134006
MCR025654 | HPR200 | 2016-12-01 | Subcontract | 167825964 | 96570542 | 94458501
MCR025655 | HPR200 | 2016-12-01 | Overhead | 37920899 | 21820472 | 39447610
MCR025656 | HPR200 | 2017-01-01 | Labor | 69100521 | 49528532 | 43468917
MCR025657 | HPR200 | 2017-01-01 | Material | 137063052 | 98241399 | 97796495
MCR025658 | HPR200 | 2017-01-01 | Equipment | 33735756 | 24180461 | 22895633
MCR025659 | HPR200 | 2017-01-01 | Subcontract | 238374559 | 170857497 | 159129436
MCR025660 | HPR200 | 2017-01-01 | Overhead | 53861615 | 38605885 | 38153276
MCR025661 | HPR200 | 2017-02-01 | Labor | 80408559 | 70903827 | 83692409
MCR025662 | HPR200 | 2017-02-01 | Material | 159492902 | 140639967 | 147674255
MCR025663 | HPR200 | 2017-02-01 | Equipment | 39256485 | 34616153 | 36888189
MCR025664 | HPR200 | 2017-02-01 | Subcontract | 277383653 | 244595385 | 272649638
MCR025665 | HPR200 | 2017-02-01 | Overhead | 62675865 | 55267234 | 40241635
MCR025666 | HPR200 | 2017-03-01 | Labor | 83246379 | 64243516 | 58276804
MCR025667 | HPR200 | 2017-03-01 | Material | 165121807 | 127429031 | 117627337
MCR025668 | HPR200 | 2017-03-01 | Equipment | 40641945 | 31364504 | 35657504
MCR025669 | HPR200 | 2017-03-01 | Subcontract | 287173219 | 221619456 | 221137419
MCR025670 | HPR200 | 2017-03-01 | Overhead | 64887853 | 50075738 | 48142797
MCR025671 | HPR200 | 2017-04-01 | Labor | 78403644 | 50772595 | 54132734
MCR025672 | HPR200 | 2017-04-01 | Material | 155516088 | 100709036 | 110794414
MCR025673 | HPR200 | 2017-04-01 | Equipment | 38277659 | 24787829 | 23914252
MCR025674 | HPR200 | 2017-04-01 | Subcontract | 270467339 | 175149114 | 168876349
MCR025675 | HPR200 | 2017-04-01 | Overhead | 61113098 | 39575592 | 39763113
MCR025676 | HPR200 | 2017-05-01 | Labor | 66843724 | 53008081 | 64264155
MCR025677 | HPR200 | 2017-05-01 | Material | 132586626 | 105143192 | 103442331
MCR025678 | HPR200 | 2017-05-01 | Equipment | 32633959 | 25879221 | 32062162
MCR025679 | HPR200 | 2017-05-01 | Subcontract | 230589338 | 182860820 | 199247665
MCR025680 | HPR200 | 2017-05-01 | Overhead | 52102516 | 41318080 | 42296411
MCR025681 | HPR200 | 2017-06-01 | Labor | 49814709 | 51609291 | 51489317
MCR025682 | HPR200 | 2017-06-01 | Material | 98809039 | 102368648 | 107121628
MCR025683 | HPR200 | 2017-06-01 | Equipment | 24320177 | 25196314 | 22800330
MCR025684 | HPR200 | 2017-06-01 | Subcontract | 171844715 | 178035444 | 192198344
MCR025685 | HPR200 | 2017-06-01 | Overhead | 38828950 | 40227769 | 41190731
MCR025686 | HPR200 | 2017-07-01 | Labor | 29118271 | 32243531 | 33061926
MCR025687 | HPR200 | 2017-07-01 | Material | 57757004 | 63956056 | 66707895
MCR025688 | HPR200 | 2017-07-01 | Equipment | 14215911 | 15741703 | 16832190
MCR025689 | HPR200 | 2017-07-01 | Subcontract | 100448662 | 111229805 | 110259255
MCR025690 | HPR200 | 2017-07-01 | Overhead | 22696748 | 25132787 | 41481844
MCR025691 | HPR200 | 2017-08-01 | Labor | 8189330 | 33030858 | 36501957
MCR025692 | HPR200 | 2017-08-01 | Material | 16243793 | 65517743 | 69930525
MCR025693 | HPR200 | 2017-08-01 | Equipment | 3998135 | 16126086 | 18639270
MCR025694 | HPR200 | 2017-08-01 | Subcontract | 28250552 | 113945829 | 118378750
MCR025695 | HPR200 | 2017-08-01 | Overhead | 6383317 | 25746482 | 41828193
MCR025696 | HPR200 | 2017-09-01 | Labor | 0 | 50351650 | 60020516
MCR025697 | HPR200 | 2017-09-01 | Material | 0 | 99874079 | 93002287
MCR025698 | HPR200 | 2017-09-01 | Equipment | 0 | 24582318 | 22603332
MCR025699 | HPR200 | 2017-09-01 | Subcontract | 0 | 173696990 | 179246549
MCR025700 | HPR200 | 2017-09-01 | Overhead | 0 | 39247479 | 44966998
MCR025701 | HPR200 | 2017-10-01 | Labor | 0 | 25246957 | 24570528
MCR025702 | HPR200 | 2017-10-01 | Material | 0 | 50078133 | 53056393
MCR025703 | HPR200 | 2017-10-01 | Equipment | 0 | 12325887 | 13622334
MCR025704 | HPR200 | 2017-10-01 | Subcontract | 0 | 87093878 | 84012520
MCR025705 | HPR200 | 2017-10-01 | Overhead | 0 | 19679185 | 41807335
MCR025706 | HPR200 | 2017-11-01 | Labor | 0 | 11910518 | 10907384
MCR025707 | HPR200 | 2017-11-01 | Material | 0 | 23624885 | 23497253
MCR025708 | HPR200 | 2017-11-01 | Equipment | 0 | 5814867 | 7798011
MCR025709 | HPR200 | 2017-11-01 | Subcontract | 0 | 41087452 | 46386656
MCR025710 | HPR200 | 2017-11-01 | Overhead | 0 | 9283862 | 40866867
MCR025711 | HPR200 | 2017-12-01 | Labor | 0 | 2880884 | 3799111
MCR025712 | HPR200 | 2017-12-01 | Material | 0 | 5714324 | 5966172
MCR025713 | HPR200 | 2017-12-01 | Equipment | 0 | 1406484 | 1594517
MCR025714 | HPR200 | 2017-12-01 | Subcontract | 0 | 9938123 | 8063799
MCR025715 | HPR200 | 2017-12-01 | Overhead | 0 | 2245556 | 39330838
MCR025716 | HPR201 | 2019-12-01 | Labor | 29089958 | 17972240 | 18320836
MCR025717 | HPR201 | 2019-12-01 | Material | 80992554 | 50038493 | 47407226
MCR025718 | HPR201 | 2019-12-01 | Equipment | 21821764 | 13481834 | 16163725
MCR025719 | HPR201 | 2019-12-01 | Subcontract | 75282022 | 46510435 | 46093492
MCR025720 | HPR201 | 2019-12-01 | Overhead | 18999754 | 11738352 | 65126545
MCR025721 | HPR201 | 2020-01-01 | Labor | 79786531 | 65870503 | 68829381
MCR025722 | HPR201 | 2020-01-01 | Material | 222142464 | 183397318 | 206813143
MCR025723 | HPR201 | 2020-01-01 | Equipment | 59851680 | 49412604 | 51875304
MCR025724 | HPR201 | 2020-01-01 | Subcontract | 206479894 | 170466547 | 169996259
MCR025725 | HPR201 | 2020-01-01 | Overhead | 52111609 | 43022523 | 76194724
MCR025726 | HPR201 | 2020-02-01 | Labor | 119560466 | 150069024 | 164994436
MCR025727 | HPR201 | 2020-02-01 | Material | 332881453 | 417823688 | 385626868
MCR025728 | HPR201 | 2020-02-01 | Equipment | 89688004 | 112573927 | 134493054
MCR025729 | HPR201 | 2020-02-01 | Subcontract | 309411023 | 388364247 | 433505569
MCR025730 | HPR201 | 2020-02-01 | Overhead | 78089473 | 98015770 | 79446648
MCR025731 | HPR201 | 2020-03-01 | Labor | 148841008 | 99637178 | 108691501
MCR025732 | HPR201 | 2020-03-01 | Material | 414404633 | 277410835 | 299178549
MCR025733 | HPR201 | 2020-03-01 | Equipment | 111652734 | 74742596 | 64708892
MCR025734 | HPR201 | 2020-03-01 | Subcontract | 385186259 | 257851465 | 235786894
MCR025735 | HPR201 | 2020-03-01 | Overhead | 97213706 | 65076819 | 74163873
MCR025736 | HPR201 | 2020-04-01 | Labor | 168095484 | 140110505 | 147487976
MCR025737 | HPR201 | 2020-04-01 | Material | 468013139 | 390097078 | 429923304
MCR025738 | HPR201 | 2020-04-01 | Equipment | 126096434 | 105103567 | 109810498
MCR025739 | HPR201 | 2020-04-01 | Subcontract | 435014997 | 362592553 | 375049952
MCR025740 | HPR201 | 2020-04-01 | Overhead | 109789534 | 91511483 | 82005868
MCR025741 | HPR201 | 2020-05-01 | Labor | 177837790 | 128558606 | 137823540
MCR025742 | HPR201 | 2020-05-01 | Material | 495137767 | 357934165 | 333101103
MCR025743 | HPR201 | 2020-05-01 | Equipment | 133404602 | 96437937 | 94163536
MCR025744 | HPR201 | 2020-05-01 | Subcontract | 460227152 | 332697347 | 348465049
MCR025745 | HPR201 | 2020-05-01 | Overhead | 116152604 | 83966500 | 79327626
MCR025746 | HPR201 | 2020-06-01 | Labor | 178640120 | 127384235 | 191082093
MCR025747 | HPR201 | 2020-06-01 | Material | 497371620 | 354664469 | 481593360
MCR025748 | HPR201 | 2020-06-01 | Equipment | 134006468 | 95556985 | 104172364
MCR025749 | HPR201 | 2020-06-01 | Subcontract | 462303503 | 329658187 | 299254371
MCR025750 | HPR201 | 2020-06-01 | Overhead | 116676635 | 83199473 | 69470219
MCR025751 | HPR201 | 2020-07-01 | Labor | 171149777 | 79086576 | 164286274
MCR025752 | HPR201 | 2020-07-01 | Material | 476516932 | 220193642 | 310620110
MCR025753 | HPR201 | 2020-07-01 | Equipment | 128387604 | 59326610 | 56586600
MCR025754 | HPR201 | 2020-07-01 | Subcontract | 442919214 | 204668477 | 208927314
MCR025755 | HPR201 | 2020-07-01 | Overhead | 111784408 | 51654441 | 73639455
MCR025756 | HPR201 | 2020-08-01 | Labor | 156114507 | 111310782 | 110216947
MCR025757 | HPR201 | 2020-08-01 | Material | 434655584 | 309912600 | 337007309
MCR025758 | HPR201 | 2020-08-01 | Equipment | 117108932 | 83499523 | 96818632
MCR025759 | HPR201 | 2020-08-01 | Subcontract | 404009378 | 288061632 | 284795145
MCR025760 | HPR201 | 2020-08-01 | Overhead | 101964304 | 72701292 | 72408975
MCR025761 | HPR201 | 2020-09-01 | Labor | 134423144 | 100558795 | 113769540
MCR025762 | HPR201 | 2020-09-01 | Material | 374262271 | 279976809 | 313440097
MCR025763 | HPR201 | 2020-09-01 | Equipment | 100837207 | 75433944 | 79877955
MCR025764 | HPR201 | 2020-09-01 | Subcontract | 347874209 | 260236520 | 276539858
MCR025765 | HPR201 | 2020-09-01 | Overhead | 87796852 | 65678762 | 71805975
MCR025766 | HPR201 | 2020-10-01 | Labor | 107176764 | 80108136 | 92339658
MCR025767 | HPR201 | 2020-10-01 | Material | 298402625 | 223037879 | 247626962
MCR025768 | HPR201 | 2020-10-01 | Equipment | 80398399 | 60092931 | 63012571
MCR025769 | HPR201 | 2020-10-01 | Subcontract | 277363190 | 207312176 | 231379683
MCR025770 | HPR201 | 2020-10-01 | Overhead | 70001208 | 52321661 | 74519400
MCR025771 | HPR201 | 2020-11-01 | Labor | 75830283 | 123200621 | 131014738
MCR025772 | HPR201 | 2020-11-01 | Material | 211127438 | 343016409 | 350545724
MCR025773 | HPR201 | 2020-11-01 | Equipment | 56883909 | 92418657 | 93513923
MCR025774 | HPR201 | 2020-11-01 | Subcontract | 196241503 | 318831395 | 300505943
MCR025775 | HPR201 | 2020-11-01 | Overhead | 49527633 | 80466997 | 71807504
MCR025776 | HPR201 | 2020-12-01 | Labor | 42541135 | 165621833 | 181228352
MCR025777 | HPR201 | 2020-12-01 | Material | 118443456 | 461125976 | 449975624
MCR025778 | HPR201 | 2020-12-01 | Equipment | 31912133 | 124240830 | 134160867
MCR025779 | HPR201 | 2020-12-01 | Subcontract | 110092379 | 428613426 | 456517573
MCR025780 | HPR201 | 2020-12-01 | Overhead | 27785228 | 108173899 | 73474717
MCR025781 | HPR201 | 2021-01-01 | Labor | 11602433 | 87298994 | 100078159
MCR025782 | HPR201 | 2021-01-01 | Material | 32303611 | 243058737 | 228843264
MCR025783 | HPR201 | 2021-01-01 | Equipment | 8703538 | 65487136 | 68348313
MCR025784 | HPR201 | 2021-01-01 | Subcontract | 30025984 | 225921426 | 221638496
MCR025785 | HPR201 | 2021-01-01 | Overhead | 7577989 | 57018283 | 67740516
MCR025786 | HPR201 | 2021-02-01 | Labor | 0 | 42808674 | 46859414
MCR025787 | HPR201 | 2021-02-01 | Material | 0 | 119188341 | 131540290
MCR025788 | HPR201 | 2021-02-01 | Equipment | 0 | 32112827 | 30355291
MCR025789 | HPR201 | 2021-02-01 | Subcontract | 0 | 110784744 | 79978430
MCR025790 | HPR201 | 2021-02-01 | Overhead | 0 | 27959968 | 76504134
MCR025791 | HPR201 | 2021-03-01 | Labor | 0 | 46517533 | 43648148
MCR025792 | HPR201 | 2021-03-01 | Material | 0 | 129514584 | 129318317
MCR025793 | HPR201 | 2021-03-01 | Equipment | 0 | 34895018 | 40086238
MCR025794 | HPR201 | 2021-03-01 | Subcontract | 0 | 120382916 | 136352935
MCR025795 | HPR201 | 2021-03-01 | Overhead | 0 | 30382365 | 68705860
MCR025796 | HPR201 | 2021-04-01 | Labor | 0 | 25384317 | 34491308
MCR025797 | HPR201 | 2021-04-01 | Material | 0 | 70675271 | 87807453
MCR025798 | HPR201 | 2021-04-01 | Equipment | 0 | 19041986 | 18569865
MCR025799 | HPR201 | 2021-04-01 | Subcontract | 0 | 65692178 | 63974704
MCR025800 | HPR201 | 2021-04-01 | Overhead | 0 | 16579460 | 78091331
MCR025801 | HPR201 | 2021-05-01 | Labor | 0 | 9190849 | 8588775
MCR025802 | HPR201 | 2021-05-01 | Material | 0 | 25589254 | 27917672
MCR025803 | HPR201 | 2021-05-01 | Equipment | 0 | 6894494 | 9217309
MCR025804 | HPR201 | 2021-05-01 | Subcontract | 0 | 23785036 | 24290322
MCR025805 | HPR201 | 2021-05-01 | Overhead | 0 | 6002892 | 77693196
MCR025806 | HPR202 | 2016-08-01 | Labor | 12368735 | 4398665 | 3999803
MCR025807 | HPR202 | 2016-08-01 | Material | 35617919 | 12666718 | 11413286
MCR025808 | HPR202 | 2016-08-01 | Equipment | 8225558 | 2925236 | 2556212
MCR025809 | HPR202 | 2016-08-01 | Subcontract | 38952861 | 13852715 | 15589236
MCR025810 | HPR202 | 2016-08-01 | Overhead | 6815639 | 2423830 | 38809721
MCR025811 | HPR202 | 2016-09-01 | Labor | 35011941 | 11282247 | 12953984
MCR025812 | HPR202 | 2016-09-01 | Material | 100822960 | 32489187 | 35378177
MCR025813 | HPR202 | 2016-09-01 | Equipment | 23283930 | 7503013 | 8033838
MCR025814 | HPR202 | 2016-09-01 | Subcontract | 110263115 | 35531182 | 39174778
MCR025815 | HPR202 | 2016-09-01 | Overhead | 19292899 | 6216943 | 38933167
MCR025816 | HPR202 | 2016-10-01 | Labor | 54568027 | 60643444 | 63668116
MCR025817 | HPR202 | 2016-10-01 | Material | 157138102 | 174633319 | 176929670
MCR025818 | HPR202 | 2016-10-01 | Equipment | 36289280 | 40329604 | 46179919
MCR025819 | HPR202 | 2016-10-01 | Subcontract | 171851101 | 190984412 | 185140112
MCR025820 | HPR202 | 2016-10-01 | Overhead | 30069039 | 33416822 | 43811013
MCR025821 | HPR202 | 2016-11-01 | Labor | 71112272 | 28825410 | 29331727
MCR025822 | HPR202 | 2016-11-01 | Material | 204780128 | 83007771 | 87172443
MCR025823 | HPR202 | 2016-11-01 | Equipment | 47291670 | 19169712 | 19528035
MCR025824 | HPR202 | 2016-11-01 | Subcontract | 223953897 | 90779872 | 99107462
MCR025825 | HPR202 | 2016-11-01 | Overhead | 39185541 | 15883887 | 37759081
MCR025826 | HPR202 | 2016-12-01 | Labor | 84723965 | 63714992 | 71459998
MCR025827 | HPR202 | 2016-12-01 | Material | 243977358 | 183478375 | 182596039
MCR025828 | HPR202 | 2016-12-01 | Equipment | 56343830 | 42372270 | 51257875
MCR025829 | HPR202 | 2016-12-01 | Subcontract | 266821203 | 200657639 | 198623605
MCR025830 | HPR202 | 2016-12-01 | Overhead | 46686097 | 35109361 | 42511917
MCR025831 | HPR202 | 2017-01-01 | Labor | 95486913 | 73369136 | 82554870
MCR025832 | HPR202 | 2017-01-01 | Material | 274971134 | 211279159 | 198141133
MCR025833 | HPR202 | 2017-01-01 | Equipment | 63501495 | 48792549 | 48882969
MCR025834 | HPR202 | 2017-01-01 | Subcontract | 300716958 | 231061439 | 265075298
MCR025835 | HPR202 | 2017-01-01 | Overhead | 52616886 | 40429158 | 37824967
MCR025836 | HPR202 | 2017-02-01 | Labor | 103490068 | 48391257 | 50685915
MCR025837 | HPR202 | 2017-02-01 | Material | 298017608 | 139351022 | 160531027
MCR025838 | HPR202 | 2017-02-01 | Equipment | 68823819 | 32181553 | 32777999
MCR025839 | HPR202 | 2017-02-01 | Subcontract | 325921296 | 152398598 | 168975156
MCR025840 | HPR202 | 2017-02-01 | Overhead | 57026926 | 26665406 | 39074760
MCR025841 | HPR202 | 2017-03-01 | Labor | 108828285 | 91190034 | 94747560
MCR025842 | HPR202 | 2017-03-01 | Material | 313389931 | 262597527 | 259032690
MCR025843 | HPR202 | 2017-03-01 | Equipment | 72373884 | 60643949 | 64312941
MCR025844 | HPR202 | 2017-03-01 | Subcontract | 342732945 | 287184797 | 260331179
MCR025845 | HPR202 | 2017-03-01 | Overhead | 59968485 | 50249145 | 39752493
MCR025846 | HPR202 | 2017-04-01 | Labor | 111603267 | 51581817 | 60095382
MCR025847 | HPR202 | 2017-04-01 | Material | 321380972 | 148538792 | 140433637
MCR025848 | HPR202 | 2017-04-01 | Equipment | 74219326 | 34303366 | 33850454
MCR025849 | HPR202 | 2017-04-01 | Subcontract | 351472195 | 162446628 | 187400445
MCR025850 | HPR202 | 2017-04-01 | Overhead | 61497605 | 28423524 | 39148633
MCR025851 | HPR202 | 2017-05-01 | Labor | 111924752 | 73262694 | 71502950
MCR025852 | HPR202 | 2017-05-01 | Material | 322306744 | 210972641 | 234579140
MCR025853 | HPR202 | 2017-05-01 | Equipment | 74433122 | 48721762 | 44485997
MCR025854 | HPR202 | 2017-05-01 | Subcontract | 352484648 | 230726222 | 237470992
MCR025855 | HPR202 | 2017-05-01 | Overhead | 61674755 | 40370505 | 38807838
MCR025856 | HPR202 | 2017-06-01 | Labor | 109912049 | 94648691 | 108135931
MCR025857 | HPR202 | 2017-06-01 | Material | 316510816 | 272557330 | 276709026
MCR025858 | HPR202 | 2017-06-01 | Equipment | 73094618 | 62944054 | 76684828
MCR025859 | HPR202 | 2017-06-01 | Subcontract | 346146042 | 298077147 | 277266337
MCR025860 | HPR202 | 2017-06-01 | Overhead | 60565680 | 52154995 | 37681196
MCR025861 | HPR202 | 2017-07-01 | Labor | 105696045 | 56511054 | 152608945
MCR025862 | HPR202 | 2017-07-01 | Material | 304370103 | 162733385 | 286017106
MCR025863 | HPR202 | 2017-07-01 | Equipment | 70290857 | 37581447 | 30202037
MCR025864 | HPR202 | 2017-07-01 | Subcontract | 332868582 | 177970275 | 227961594
MCR025865 | HPR202 | 2017-07-01 | Overhead | 58242503 | 31139720 | 39301006
MCR025866 | HPR202 | 2017-08-01 | Labor | 99421926 | 68291442 | 169517510
MCR025867 | HPR202 | 2017-08-01 | Material | 286302687 | 196657058 | 330226873
MCR025868 | HPR202 | 2017-08-01 | Equipment | 66118390 | 45415739 | 51110420
MCR025869 | HPR202 | 2017-08-01 | Subcontract | 313109495 | 215070255 | 212455045
MCR025870 | HPR202 | 2017-08-01 | Overhead | 54785227 | 37631157 | 41727494
MCR025871 | HPR202 | 2017-09-01 | Labor | 91252950 | 93528680 | 118700633
MCR025872 | HPR202 | 2017-09-01 | Material | 262778703 | 269332064 | 260805730
MCR025873 | HPR202 | 2017-09-01 | Equipment | 60685790 | 62199215 | 65760994
MCR025874 | HPR202 | 2017-09-01 | Subcontract | 287382936 | 294549895 | 300079533
MCR025875 | HPR202 | 2017-09-01 | Overhead | 50283813 | 51537826 | 38740823
MCR025876 | HPR202 | 2017-10-01 | Labor | 81375932 | 104138718 | 105150425
MCR025877 | HPR202 | 2017-10-01 | Material | 234336118 | 299885507 | 297581028
MCR025878 | HPR202 | 2017-10-01 | Equipment | 54117294 | 69255189 | 73481959
MCR025879 | HPR202 | 2017-10-01 | Subcontract | 256277244 | 327964088 | 351093658
MCR025880 | HPR202 | 2017-10-01 | Overhead | 44841205 | 57384357 | 38845789
MCR025881 | HPR202 | 2017-11-01 | Labor | 70009579 | 53605497 | 70811307
MCR025882 | HPR202 | 2017-11-01 | Material | 201604732 | 154366329 | 170553178
MCR025883 | HPR202 | 2017-11-01 | Equipment | 46558348 | 35649170 | 36593023
MCR025884 | HPR202 | 2017-11-01 | Subcontract | 220481185 | 168819803 | 182416153
MCR025885 | HPR202 | 2017-11-01 | Overhead | 38577916 | 29538648 | 39671289
MCR025886 | HPR202 | 2017-12-01 | Labor | 57418014 | 99575900 | 131177792
MCR025887 | HPR202 | 2017-12-01 | Material | 165345135 | 286746082 | 261268034
MCR025888 | HPR202 | 2017-12-01 | Equipment | 38184602 | 66220787 | 65582742
MCR025889 | HPR202 | 2017-12-01 | Subcontract | 180826566 | 313594405 | 358590084
MCR025890 | HPR202 | 2017-12-01 | Overhead | 31639489 | 54870072 | 41300526
MCR025891 | HPR202 | 2018-01-01 | Labor | 43934757 | 101179078 | 111550807
MCR025892 | HPR202 | 2018-01-01 | Material | 126517758 | 291362711 | 257805909
MCR025893 | HPR202 | 2018-01-01 | Equipment | 29217855 | 67286945 | 68856450
MCR025894 | HPR202 | 2018-01-01 | Subcontract | 138363742 | 318643294 | 281339246
MCR025895 | HPR202 | 2018-01-01 | Overhead | 24209707 | 55753484 | 36912734
MCR025896 | HPR202 | 2018-02-01 | Labor | 30011104 | 77584714 | 94141950
MCR025897 | HPR202 | 2018-02-01 | Material | 86422181 | 223418645 | 266621336
MCR025898 | HPR202 | 2018-02-01 | Equipment | 19958232 | 51596027 | 54721652
MCR025899 | HPR202 | 2018-02-01 | Subcontract | 94513976 | 244337557 | 341285245
MCR025900 | HPR202 | 2018-02-01 | Overhead | 16537249 | 42752100 | 36081825
MCR025901 | HPR202 | 2018-03-01 | Labor | 16337156 | 66127698 | 69451987
MCR025902 | HPR202 | 2018-03-01 | Material | 47045675 | 190426181 | 210435278
MCR025903 | HPR202 | 2018-03-01 | Equipment | 10864670 | 43976788 | 46897832
MCR025904 | HPR202 | 2018-03-01 | Subcontract | 51450609 | 208255976 | 366708018
MCR025905 | HPR202 | 2018-03-01 | Overhead | 9002388 | 36438853 | 38568414
MCR025906 | HPR202 | 2018-04-01 | Labor | 4350166 | 50382028 | 61948406
MCR025907 | HPR202 | 2018-04-01 | Material | 12527057 | 145083792 | 156754085
MCR025908 | HPR202 | 2018-04-01 | Equipment | 2892983 | 33505472 | 37366981
MCR025909 | HPR202 | 2018-04-01 | Subcontract | 13699978 | 158668133 | 274941522
MCR025910 | HPR202 | 2018-04-01 | Overhead | 2397105 | 27762396 | 39833091
MCR025911 | HPR202 | 2018-05-01 | Labor | 0 | 42056056 | 46988337
MCR025912 | HPR202 | 2018-05-01 | Material | 0 | 121107710 | 103175505
MCR025913 | HPR202 | 2018-05-01 | Equipment | 0 | 27968465 | 29075306
MCR025914 | HPR202 | 2018-05-01 | Subcontract | 0 | 132447146 | 244668582
MCR025915 | HPR202 | 2018-05-01 | Overhead | 0 | 23174471 | 39190608
MCR025916 | HPR202 | 2018-06-01 | Labor | 0 | 41488935 | 49106738
MCR025917 | HPR202 | 2018-06-01 | Material | 0 | 119474587 | 112651214
MCR025918 | HPR202 | 2018-06-01 | Equipment | 0 | 27591314 | 30608256
MCR025919 | HPR202 | 2018-06-01 | Subcontract | 0 | 130661113 | 250329891
MCR025920 | HPR202 | 2018-06-01 | Overhead | 0 | 22861966 | 36680481
MCR025921 | HPR202 | 2018-07-01 | Labor | 0 | 19833189 | 18328616
MCR025922 | HPR202 | 2018-07-01 | Material | 0 | 57113109 | 72606021
MCR025923 | HPR202 | 2018-07-01 | Equipment | 0 | 13189631 | 12895111
MCR025924 | HPR202 | 2018-07-01 | Subcontract | 0 | 62460667 | 141475534
MCR025925 | HPR202 | 2018-07-01 | Overhead | 0 | 10928834 | 42152326
MCR025926 | HPR202 | 2018-08-01 | Labor | 0 | 11643946 | 18066671
MCR025927 | HPR202 | 2018-08-01 | Material | 0 | 33530763 | 27877310
MCR025928 | HPR202 | 2018-08-01 | Equipment | 0 | 7743553 | 9752538
MCR025929 | HPR202 | 2018-08-01 | Subcontract | 0 | 36670282 | 131018212
MCR025930 | HPR202 | 2018-08-01 | Overhead | 0 | 6416253 | 39062322
MCR025931 | HPR202 | 2018-09-01 | Labor | 0 | 9755367 | 9256789
MCR025932 | HPR202 | 2018-09-01 | Material | 0 | 28092273 | 30026305
MCR025933 | HPR202 | 2018-09-01 | Equipment | 0 | 6487595 | 7447370
MCR025934 | HPR202 | 2018-09-01 | Subcontract | 0 | 30722581 | 176776917
MCR025935 | HPR202 | 2018-09-01 | Overhead | 0 | 5375575 | 38908886
MCR025936 | HPR202 | 2018-10-01 | Labor | 0 | 1827214 | 3338532
MCR025937 | HPR202 | 2018-10-01 | Material | 0 | 5261781 | 6581961
MCR025938 | HPR202 | 2018-10-01 | Equipment | 0 | 1215149 | 1142216
MCR025939 | HPR202 | 2018-10-01 | Subcontract | 0 | 5754447 | 129954061
MCR025940 | HPR202 | 2018-10-01 | Overhead | 0 | 1006864 | 38522926
MCR025941 | HPR203 | 2017-10-01 | Labor | 1774705 | 968554 | 996228
MCR025942 | HPR203 | 2017-10-01 | Material | 8660132 | 4726312 | 4428987
MCR025943 | HPR203 | 2017-10-01 | Equipment | 3813308 | 2081133 | 2124865
MCR025944 | HPR203 | 2017-10-01 | Subcontract | 4408623 | 2406029 | 2881849
MCR025945 | HPR203 | 2017-10-01 | Overhead | 1913272 | 1044178 | 17727082
MCR025946 | HPR203 | 2017-11-01 | Labor | 5155432 | 2580293 | 3028543
MCR025947 | HPR203 | 2017-11-01 | Material | 25157264 | 12591207 | 12748317
MCR025948 | HPR203 | 2017-11-01 | Equipment | 11077475 | 5544275 | 5969470
MCR025949 | HPR203 | 2017-11-01 | Subcontract | 12806836 | 6409819 | 7125955
MCR025950 | HPR203 | 2017-11-01 | Overhead | 5557963 | 2781760 | 18997631
MCR025951 | HPR203 | 2017-12-01 | Labor | 8285538 | 4625176 | 5071796
MCR025952 | HPR203 | 2017-12-01 | Material | 40431426 | 22569740 | 23160094
MCR025953 | HPR203 | 2017-12-01 | Equipment | 17803132 | 9938113 | 11949531
MCR025954 | HPR203 | 2017-12-01 | Subcontract | 20582470 | 11489602 | 13703726
MCR025955 | HPR203 | 2017-12-01 | Overhead | 8932465 | 4986305 | 18698422
MCR025956 | HPR203 | 2018-01-01 | Labor | 11168296 | 6799379 | 6965990
MCR025957 | HPR203 | 2018-01-01 | Material | 54498588 | 33179325 | 32591112
MCR025958 | HPR203 | 2018-01-01 | Equipment | 23997313 | 14609822 | 14430749
MCR025959 | HPR203 | 2018-01-01 | Subcontract | 27743656 | 16890635 | 16300024
MCR025960 | HPR203 | 2018-01-01 | Overhead | 12040306 | 7330267 | 19406856
MCR025961 | HPR203 | 2018-02-01 | Labor | 13807071 | 7885099 | 10302009
MCR025962 | HPR203 | 2018-02-01 | Material | 67375169 | 38477381 | 39857915
MCR025963 | HPR203 | 2018-02-01 | Equipment | 29667246 | 16942710 | 14033922
MCR025964 | HPR203 | 2018-02-01 | Subcontract | 34298751 | 19587722 | 20459065
MCR025965 | HPR203 | 2018-02-01 | Overhead | 14885113 | 8500760 | 19466901
MCR025966 | HPR203 | 2018-03-01 | Labor | 16205322 | 11546485 | 12387382
MCR025967 | HPR203 | 2018-03-01 | Material | 79078058 | 56344058 | 52095457
MCR025968 | HPR203 | 2018-03-01 | Equipment | 34820368 | 24809927 | 31291688
MCR025969 | HPR203 | 2018-03-01 | Subcontract | 40256353 | 28683132 | 30886362
MCR025970 | HPR203 | 2018-03-01 | Overhead | 17470618 | 12448023 | 18650699
MCR025971 | HPR203 | 2018-04-01 | Labor | 18366616 | 7736840 | 7846894
MCR025972 | HPR203 | 2018-04-01 | Material | 89624650 | 37753909 | 39003752
MCR025973 | HPR203 | 2018-04-01 | Equipment | 39464340 | 16624144 | 17909775
MCR025974 | HPR203 | 2018-04-01 | Subcontract | 45625319 | 19219424 | 20792824
MCR025975 | HPR203 | 2018-04-01 | Overhead | 19800663 | 8340925 | 19655589
MCR025976 | HPR203 | 2018-05-01 | Labor | 20294628 | 18208861 | 21005012
MCR025977 | HPR203 | 2018-05-01 | Material | 99032881 | 88854845 | 85362028
MCR025978 | HPR203 | 2018-05-01 | Equipment | 43607057 | 39125372 | 42692509
MCR025979 | HPR203 | 2018-05-01 | Subcontract | 50414777 | 45233433 | 50292126
MCR025980 | HPR203 | 2018-05-01 | Overhead | 21879212 | 19630591 | 17593544
MCR025981 | HPR203 | 2018-06-01 | Labor | 21993152 | 9752836 | 9674782
MCR025982 | HPR203 | 2018-06-01 | Material | 107321268 | 47591485 | 55204713
MCR025983 | HPR203 | 2018-06-01 | Equipment | 47256675 | 20955915 | 21090159
MCR025984 | HPR203 | 2018-06-01 | Subcontract | 54634155 | 24227449 | 24595490
MCR025985 | HPR203 | 2018-06-01 | Overhead | 23710355 | 10514328 | 20416571
MCR025986 | HPR203 | 2018-07-01 | Labor | 23466110 | 13826267 | 17115217
MCR025987 | HPR203 | 2018-07-01 | Material | 114508950 | 67468841 | 74496133
MCR025988 | HPR203 | 2018-07-01 | Equipment | 50421621 | 29708493 | 29449284
MCR025989 | HPR203 | 2018-07-01 | Subcontract | 58293197 | 34346437 | 38248246
MCR025990 | HPR203 | 2018-07-01 | Overhead | 25298321 | 14905808 | 19412248
MCR025991 | HPR203 | 2018-08-01 | Labor | 24717564 | 7650363 | 7649504
MCR025992 | HPR203 | 2018-08-01 | Material | 120615740 | 37331924 | 32450463
MCR025993 | HPR203 | 2018-08-01 | Equipment | 53110618 | 16438332 | 17618562
MCR025994 | HPR203 | 2018-08-01 | Subcontract | 61401987 | 19004604 | 18976768
MCR025995 | HPR203 | 2018-08-01 | Overhead | 26647487 | 8247696 | 20582455
MCR025996 | HPR203 | 2018-09-01 | Labor | 25751721 | 17145589 | 18575928
MCR025997 | HPR203 | 2018-09-01 | Material | 125662178 | 83666333 | 93151252
MCR025998 | HPR203 | 2018-09-01 | Equipment | 55332711 | 36840719 | 46453594
MCR025999 | HPR203 | 2018-09-01 | Subcontract | 63970982 | 42592111 | 49358104
MCR026000 | HPR203 | 2018-09-01 | Overhead | 27762390 | 18484300 | 17346509
MCR026001 | HPR203 | 2018-10-01 | Labor | 26572953 | 10151074 | 12219510
MCR026002 | HPR203 | 2018-10-01 | Material | 129669593 | 49534790 | 43461925
MCR026003 | HPR203 | 2018-10-01 | Equipment | 57097292 | 21811609 | 20323488
MCR026004 | HPR203 | 2018-10-01 | Subcontract | 66011041 | 25216730 | 23045780
MCR026005 | HPR203 | 2018-10-01 | Overhead | 28647743 | 10943660 | 20278514
MCR026006 | HPR203 | 2018-11-01 | Labor | 27185808 | 12325692 | 12458706
MCR026007 | HPR203 | 2018-11-01 | Material | 132660174 | 60146401 | 68166151
MCR026008 | HPR203 | 2018-11-01 | Equipment | 58414133 | 26484209 | 22136407
MCR026009 | HPR203 | 2018-11-01 | Subcontract | 67533460 | 30618794 | 39063195
MCR026010 | HPR203 | 2018-11-01 | Overhead | 29308449 | 13288070 | 18432399
MCR026011 | HPR203 | 2018-12-01 | Labor | 27595024 | 12939848 | 14433465
MCR026012 | HPR203 | 2018-12-01 | Material | 134657053 | 63143333 | 64467659
MCR026013 | HPR203 | 2018-12-01 | Equipment | 59293416 | 27803846 | 33833503
MCR026014 | HPR203 | 2018-12-01 | Subcontract | 68550013 | 32144446 | 35023758
MCR026015 | HPR203 | 2018-12-01 | Overhead | 29749617 | 13950179 | 19981987
MCR026016 | HPR203 | 2019-01-01 | Labor | 27805554 | 29031485 | 34036917
MCR026017 | HPR203 | 2019-01-01 | Material | 135684389 | 141666633 | 137614890
MCR026018 | HPR203 | 2019-01-01 | Equipment | 59745782 | 62379938 | 60434456
MCR026019 | HPR203 | 2019-01-01 | Subcontract | 69073000 | 72118388 | 76586123
MCR026020 | HPR203 | 2019-01-01 | Overhead | 29976585 | 31298234 | 18630941
MCR026021 | HPR203 | 2019-02-01 | Labor | 27822582 | 17695689 | 19303814
MCR026022 | HPR203 | 2019-02-01 | Material | 135767482 | 86350686 | 102364404
MCR026023 | HPR203 | 2019-02-01 | Equipment | 59782370 | 38022718 | 50094365
MCR026024 | HPR203 | 2019-02-01 | Subcontract | 69115301 | 43958638 | 50546587
MCR026025 | HPR203 | 2019-02-01 | Overhead | 29994942 | 19077350 | 18403522
MCR026026 | HPR203 | 2019-03-01 | Labor | 27651552 | 20535088 | 23106546
MCR026027 | HPR203 | 2019-03-01 | Material | 134932894 | 100206271 | 91300094
MCR026028 | HPR203 | 2019-03-01 | Equipment | 59414877 | 44123735 | 42081726
MCR026029 | HPR203 | 2019-03-01 | Subcontract | 68690436 | 51012116 | 55139913
MCR026030 | HPR203 | 2019-03-01 | Overhead | 29810558 | 22138448 | 18756510
MCR026031 | HPR203 | 2019-04-01 | Labor | 27298193 | 14625893 | 17673649
MCR026032 | HPR203 | 2019-04-01 | Material | 133208590 | 71370827 | 79021239
MCR026033 | HPR203 | 2019-04-01 | Equipment | 58655616 | 31426651 | 38285335
MCR026034 | HPR203 | 2019-04-01 | Subcontract | 67812643 | 36332825 | 39220384
MCR026035 | HPR203 | 2019-04-01 | Overhead | 29429609 | 15767869 | 19460412
MCR026036 | HPR203 | 2019-05-01 | Labor | 26768561 | 19494945 | 26543816
MCR026037 | HPR203 | 2019-05-01 | Material | 130624112 | 95130621 | 104875005
MCR026038 | HPR203 | 2019-05-01 | Equipment | 57517595 | 41888779 | 43626337
MCR026039 | HPR203 | 2019-05-01 | Subcontract | 66496960 | 48428249 | 49713841
MCR026040 | HPR203 | 2019-05-01 | Overhead | 28858624 | 21017091 | 18919822
MCR026041 | HPR203 | 2019-06-01 | Labor | 26069073 | 36230438 | 41554526
MCR026042 | HPR203 | 2019-06-01 | Material | 127210782 | 176795785 | 168071663
MCR026043 | HPR203 | 2019-06-01 | Equipment | 56014606 | 77848325 | 84132769
MCR026044 | HPR203 | 2019-06-01 | Subcontract | 64759332 | 90001624 | 100017054
MCR026045 | HPR203 | 2019-06-01 | Overhead | 28104521 | 39059275 | 20370359
MCR026046 | HPR203 | 2019-07-01 | Labor | 25206564 | 14798765 | 18704662
MCR026047 | HPR203 | 2019-07-01 | Material | 123001942 | 72214398 | 78728985
MCR026048 | HPR203 | 2019-07-01 | Equipment | 54161332 | 31798099 | 35012931
MCR026049 | HPR203 | 2019-07-01 | Subcontract | 62616733 | 36762262 | 41757009
MCR026050 | HPR203 | 2019-07-01 | Overhead | 27174667 | 15954238 | 19359493
MCR026051 | HPR203 | 2019-08-01 | Labor | 24188340 | 8564161 | 10191503
MCR026052 | HPR203 | 2019-08-01 | Material | 118033255 | 41791036 | 45771847
MCR026053 | HPR203 | 2019-08-01 | Equipment | 51973475 | 18401809 | 20245559
MCR026054 | HPR203 | 2019-08-01 | Subcontract | 60087318 | 21274609 | 25240623
MCR026055 | HPR203 | 2019-08-01 | Overhead | 26076941 | 9232842 | 18232193
MCR026056 | HPR203 | 2019-09-01 | Labor | 23022261 | 17368208 | 24053303
MCR026057 | HPR203 | 2019-09-01 | Material | 112343071 | 84752658 | 80802301
MCR026058 | HPR203 | 2019-09-01 | Equipment | 49467921 | 37319060 | 40567290
MCR026059 | HPR203 | 2019-09-01 | Subcontract | 57190610 | 43145129 | 49216550
MCR026060 | HPR203 | 2019-09-01 | Overhead | 24819816 | 18724300 | 19547314
MCR026061 | HPR203 | 2019-10-01 | Labor | 21716830 | 21290271 | 26146634
MCR026062 | HPR203 | 2019-10-01 | Material | 105972884 | 103891381 | 128649509
MCR026063 | HPR203 | 2019-10-01 | Equipment | 46662942 | 45746396 | 52412747
MCR026064 | HPR203 | 2019-10-01 | Subcontract | 53947732 | 52888099 | 52511761
MCR026065 | HPR203 | 2019-10-01 | Overhead | 23412458 | 22952595 | 19023785
MCR026066 | HPR203 | 2019-11-01 | Labor | 20281314 | 19830050 | 24468973
MCR026067 | HPR203 | 2019-11-01 | Material | 98967913 | 96765852 | 88911620
MCR026068 | HPR203 | 2019-11-01 | Equipment | 43578450 | 42608819 | 41253727
MCR026069 | HPR203 | 2019-11-01 | Subcontract | 50381704 | 49260698 | 58698172
MCR026070 | HPR203 | 2019-11-01 | Overhead | 21864859 | 21378360 | 18891290
MCR026071 | HPR203 | 2019-12-01 | Labor | 18725899 | 26255579 | 32324957
MCR026072 | HPR203 | 2019-12-01 | Material | 91377865 | 128120885 | 132876923
MCR026073 | HPR203 | 2019-12-01 | Equipment | 40236331 | 56415351 | 69472726
MCR026074 | HPR203 | 2019-12-01 | Subcontract | 46517830 | 65222639 | 56305619
MCR026075 | HPR203 | 2019-12-01 | Overhead | 20187999 | 28305589 | 19214757
MCR026076 | HPR203 | 2020-01-01 | Labor | 17061896 | 17237663 | 21278904
MCR026077 | HPR203 | 2020-01-01 | Material | 83257931 | 84115633 | 92485712
MCR026078 | HPR203 | 2020-01-01 | Equipment | 36660888 | 37038559 | 30753523
MCR026079 | HPR203 | 2020-01-01 | Subcontract | 42384206 | 42820837 | 54135052
MCR026080 | HPR203 | 2020-01-01 | Overhead | 18394072 | 18583563 | 18601416
MCR026081 | HPR203 | 2020-02-01 | Labor | 15302019 | 15758587 | 19082553
MCR026082 | HPR203 | 2020-02-01 | Material | 74670157 | 76898096 | 70921317
MCR026083 | HPR203 | 2020-02-01 | Equipment | 32879442 | 33860468 | 41809078
MCR026084 | HPR203 | 2020-02-01 | Subcontract | 38012419 | 39146598 | 38796459
MCR026085 | HPR203 | 2020-02-01 | Overhead | 16496786 | 16989002 | 19215306
MCR026086 | HPR203 | 2020-03-01 | Labor | 13460783 | 19490211 | 27186305
MCR026087 | HPR203 | 2020-03-01 | Material | 65685367 | 95107521 | 91021240
MCR026088 | HPR203 | 2020-03-01 | Equipment | 28923177 | 41878607 | 41992607
MCR026089 | HPR203 | 2020-03-01 | Subcontract | 33438522 | 48416490 | 52723410
MCR026090 | HPR203 | 2020-03-01 | Overhead | 14511787 | 21011987 | 18362811
MCR026091 | HPR203 | 2020-04-01 | Labor | 11555076 | 24871825 | 30024439
MCR026092 | HPR203 | 2020-04-01 | Material | 56385978 | 121368498 | 134284477
MCR026093 | HPR203 | 2020-04-01 | Equipment | 24828386 | 53442079 | 44576895
MCR026094 | HPR203 | 2020-04-01 | Subcontract | 28704472 | 61785194 | 64512684
MCR026095 | HPR203 | 2020-04-01 | Overhead | 12457285 | 26813793 | 19389890
MCR026096 | HPR203 | 2020-05-01 | Labor | 9605052 | 17956746 | 54223308
MCR026097 | HPR203 | 2020-05-01 | Material | 46870335 | 87624581 | 126498977
MCR026098 | HPR203 | 2020-05-01 | Equipment | 20638372 | 38583651 | 45608284
MCR026099 | HPR203 | 2020-05-01 | Subcontract | 23860333 | 44607141 | 55525776
MCR026100 | HPR203 | 2020-05-01 | Overhead | 10355005 | 19358791 | 19204081
MCR026101 | HPR203 | 2020-06-01 | Labor | 7635589 | 19769246 | 54356392
MCR026102 | HPR203 | 2020-06-01 | Material | 37259832 | 96469147 | 168139670
MCR026103 | HPR203 | 2020-06-01 | Equipment | 16406588 | 42478171 | 44761528
MCR026104 | HPR203 | 2020-06-01 | Subcontract | 18967903 | 49109654 | 54707025
MCR026105 | HPR203 | 2020-06-01 | Overhead | 8231769 | 21312810 | 17848970
MCR026106 | HPR203 | 2020-07-01 | Labor | 5678907 | 14471693 | 16302624
MCR026107 | HPR203 | 2020-07-01 | Material | 27711693 | 70618364 | 90594853
MCR026108 | HPR203 | 2020-07-01 | Equipment | 12202264 | 31095319 | 33670083
MCR026109 | HPR203 | 2020-07-01 | Subcontract | 14107222 | 35949768 | 37680293
MCR026110 | HPR203 | 2020-07-01 | Overhead | 6122310 | 15601628 | 20616200
MCR026111 | HPR203 | 2020-08-01 | Labor | 3779926 | 9546266 | 12813482
MCR026112 | HPR203 | 2020-08-01 | Material | 18445128 | 46583473 | 47457336
MCR026113 | HPR203 | 2020-08-01 | Equipment | 8121926 | 20512058 | 26384900
MCR026114 | HPR203 | 2020-08-01 | Subcontract | 9389882 | 23714299 | 43480994
MCR026115 | HPR203 | 2020-08-01 | Overhead | 4075059 | 10291629 | 18240312
MCR026116 | HPR203 | 2020-09-01 | Labor | 2009895 | 14906214 | 20118127
MCR026117 | HPR203 | 2020-09-01 | Material | 9807800 | 72738721 | 75673757
MCR026118 | HPR203 | 2020-09-01 | Equipment | 4318660 | 32028974 | 29481037
MCR026119 | HPR203 | 2020-09-01 | Subcontract | 4992867 | 37029181 | 67562163
MCR026120 | HPR203 | 2020-09-01 | Overhead | 2166825 | 16070076 | 20030912
MCR026121 | HPR203 | 2020-10-01 | Labor | 524772 | 19498727 | 23838943
MCR026122 | HPR203 | 2020-10-01 | Material | 2560762 | 95149079 | 85401808
MCR026123 | HPR203 | 2020-10-01 | Equipment | 1127578 | 41896906 | 50352396
MCR026124 | HPR203 | 2020-10-01 | Subcontract | 1303610 | 48437646 | 83448987
MCR026125 | HPR203 | 2020-10-01 | Overhead | 565746 | 21021169 | 17882910
MCR026126 | HPR203 | 2020-11-01 | Labor | 0 | 7370364 | 9873640
MCR026127 | HPR203 | 2020-11-01 | Material | 0 | 35965598 | 42695592
MCR026128 | HPR203 | 2020-11-01 | Equipment | 0 | 15836699 | 15572710
MCR026129 | HPR203 | 2020-11-01 | Subcontract | 0 | 18309046 | 55671356
MCR026130 | HPR203 | 2020-11-01 | Overhead | 0 | 7945835 | 18459281
MCR026131 | HPR203 | 2020-12-01 | Labor | 0 | 7558868 | 9121936
MCR026132 | HPR203 | 2020-12-01 | Material | 0 | 36885452 | 40376970
MCR026133 | HPR203 | 2020-12-01 | Equipment | 0 | 16241737 | 17042778
MCR026134 | HPR203 | 2020-12-01 | Subcontract | 0 | 18777317 | 56866465
MCR026135 | HPR203 | 2020-12-01 | Overhead | 0 | 8149057 | 18154573
MCR026136 | HPR203 | 2021-01-01 | Labor | 0 | 11720967 | 15249214
MCR026137 | HPR203 | 2021-01-01 | Material | 0 | 57195487 | 57881909
MCR026138 | HPR203 | 2021-01-01 | Equipment | 0 | 25184836 | 32697243
MCR026139 | HPR203 | 2021-01-01 | Subcontract | 0 | 29116569 | 49392147
MCR026140 | HPR203 | 2021-01-01 | Overhead | 0 | 12636128 | 19107843
MCR026141 | HPR203 | 2021-02-01 | Labor | 0 | 10323407 | 14528213
MCR026142 | HPR203 | 2021-02-01 | Material | 0 | 50375734 | 53331675
MCR026143 | HPR203 | 2021-02-01 | Equipment | 0 | 22181901 | 22034110
MCR026144 | HPR203 | 2021-02-01 | Subcontract | 0 | 25644830 | 67138381
MCR026145 | HPR203 | 2021-02-01 | Overhead | 0 | 11129449 | 18502639
MCR026146 | HPR203 | 2021-03-01 | Labor | 0 | 3989974 | 4607007
MCR026147 | HPR203 | 2021-03-01 | Material | 0 | 19470110 | 20263351
MCR026148 | HPR203 | 2021-03-01 | Equipment | 0 | 8573256 | 8932248
MCR026149 | HPR203 | 2021-03-01 | Subcontract | 0 | 9911670 | 47161274
MCR026150 | HPR203 | 2021-03-01 | Overhead | 0 | 4301507 | 18956280
MCR026151 | HPR203 | 2021-04-01 | Labor | 0 | 7190814 | 9369940
MCR026152 | HPR203 | 2021-04-01 | Material | 0 | 35089433 | 35915559
MCR026153 | HPR203 | 2021-04-01 | Equipment | 0 | 15450898 | 17283064
MCR026154 | HPR203 | 2021-04-01 | Subcontract | 0 | 17863016 | 45932613
MCR026155 | HPR203 | 2021-04-01 | Overhead | 0 | 7752265 | 16986580
MCR026156 | HPR203 | 2021-05-01 | Labor | 0 | 13224057 | 18385173
MCR026157 | HPR203 | 2021-05-01 | Material | 0 | 64530202 | 66071150
MCR026158 | HPR203 | 2021-05-01 | Equipment | 0 | 28414525 | 30297842
MCR026159 | HPR203 | 2021-05-01 | Subcontract | 0 | 32850461 | 90844691
MCR026160 | HPR203 | 2021-05-01 | Overhead | 0 | 14256578 | 20819806
MCR026161 | HPR203 | 2021-06-01 | Labor | 0 | 5823472 | 7410333
MCR026162 | HPR203 | 2021-06-01 | Material | 0 | 28417138 | 32440927
MCR026163 | HPR203 | 2021-06-01 | Equipment | 0 | 12512892 | 16875706
MCR026164 | HPR203 | 2021-06-01 | Subcontract | 0 | 14466344 | 33088443
MCR026165 | HPR203 | 2021-06-01 | Overhead | 0 | 6278163 | 19338219
MCR026166 | HPR203 | 2021-07-01 | Labor | 0 | 4101595 | 4844879
MCR026167 | HPR203 | 2021-07-01 | Material | 0 | 20014791 | 25197980
MCR026168 | HPR203 | 2021-07-01 | Equipment | 0 | 8813094 | 11450200
MCR026169 | HPR203 | 2021-07-01 | Subcontract | 0 | 10188951 | 52520583
MCR026170 | HPR203 | 2021-07-01 | Overhead | 0 | 4421843 | 19380790
MCR026171 | HPR203 | 2021-08-01 | Labor | 0 | 5022609 | 7055550
MCR026172 | HPR203 | 2021-08-01 | Material | 0 | 24509120 | 24859150
MCR026173 | HPR203 | 2021-08-01 | Equipment | 0 | 10792078 | 13743122
MCR026174 | HPR203 | 2021-08-01 | Subcontract | 0 | 12476885 | 57174098
MCR026175 | HPR203 | 2021-08-01 | Overhead | 0 | 5414770 | 19034890
MCR026176 | HPR203 | 2021-09-01 | Labor | 0 | 8449391 | 9682901
MCR026177 | HPR203 | 2021-09-01 | Material | 0 | 41230986 | 48778781
MCR026178 | HPR203 | 2021-09-01 | Equipment | 0 | 18155202 | 22611877
MCR026179 | HPR203 | 2021-09-01 | Subcontract | 0 | 20989503 | 68622373
MCR026180 | HPR203 | 2021-09-01 | Overhead | 0 | 9109111 | 19738073
MCR026181 | HPR203 | 2021-10-01 | Labor | 0 | 2755465 | 5382789
MCR026182 | HPR203 | 2021-10-01 | Material | 0 | 13446003 | 10248178
MCR026183 | HPR203 | 2021-10-01 | Equipment | 0 | 5920666 | 6810518
MCR026184 | HPR203 | 2021-10-01 | Subcontract | 0 | 6844972 | 35213435
MCR026185 | HPR203 | 2021-10-01 | Overhead | 0 | 2970609 | 18718328
MCR026186 | HPR203 | 2021-11-01 | Labor | 0 | 2000861 | 1770311
MCR026187 | HPR203 | 2021-11-01 | Material | 0 | 9763717 | 10882417
MCR026188 | HPR203 | 2021-11-01 | Equipment | 0 | 4299249 | 5378949
MCR026189 | HPR203 | 2021-11-01 | Subcontract | 0 | 4970426 | 28656293
MCR026190 | HPR203 | 2021-11-01 | Overhead | 0 | 2157086 | 18971497
MCR026191 | HPR203 | 2021-12-01 | Labor | 0 | 1614084 | 2571309
MCR026192 | HPR203 | 2021-12-01 | Material | 0 | 7876342 | 9002239
MCR026193 | HPR203 | 2021-12-01 | Equipment | 0 | 3468182 | 4508951
MCR026194 | HPR203 | 2021-12-01 | Subcontract | 0 | 4009618 | 38911346
MCR026195 | HPR203 | 2021-12-01 | Overhead | 0 | 1740110 | 18250805
MCR026196 | HPR203 | 2022-01-01 | Labor | 0 | 737957 | 912526
MCR026197 | HPR203 | 2022-01-01 | Material | 0 | 3601050 | 3840108
MCR026198 | HPR203 | 2022-01-01 | Equipment | 0 | 1585647 | 1752967
MCR026199 | HPR203 | 2022-01-01 | Subcontract | 0 | 1833190 | 51906224
MCR026200 | HPR203 | 2022-01-01 | Overhead | 0 | 795576 | 20044255
MCR026201 | HPR203 | 2022-02-01 | Labor | 0 | 256588 | 342177
MCR026202 | HPR203 | 2022-02-01 | Material | 0 | 1252089 | 1296034
MCR026203 | HPR203 | 2022-02-01 | Equipment | 0 | 551331 | 924620
MCR026204 | HPR203 | 2022-02-01 | Subcontract | 0 | 637402 | 24077574
MCR026205 | HPR203 | 2022-02-01 | Overhead | 0 | 276622 | 20266142
MCR026206 | HPR204 | 2016-09-01 | Labor | 9903544 | 7552128 | 7418224
MCR026207 | HPR204 | 2016-09-01 | Material | 19864691 | 15148181 | 14491155
MCR026208 | HPR204 | 2016-09-01 | Equipment | 3824254 | 2916254 | 2799287
MCR026209 | HPR204 | 2016-09-01 | Subcontract | 19301822 | 14718956 | 13528710
MCR026210 | HPR204 | 2016-09-01 | Overhead | 5580860 | 4255787 | 21666638
MCR026211 | HPR204 | 2016-10-01 | Labor | 26958851 | 16690935 | 18297596
MCR026212 | HPR204 | 2016-10-01 | Material | 54074505 | 33478950 | 36053013
MCR026213 | HPR204 | 2016-10-01 | Equipment | 10410161 | 6445205 | 7340766
MCR026214 | HPR204 | 2016-10-01 | Subcontract | 52542297 | 32530320 | 31750057
MCR026215 | HPR204 | 2016-10-01 | Overhead | 15191893 | 9405701 | 21211759
MCR026216 | HPR204 | 2016-11-01 | Labor | 40007332 | 23936780 | 21604273
MCR026217 | HPR204 | 2016-11-01 | Material | 80247363 | 48012785 | 48617036
MCR026218 | HPR204 | 2016-11-01 | Equipment | 15448832 | 9243188 | 10218194
MCR026219 | HPR204 | 2016-11-01 | Subcontract | 77973543 | 46652337 | 41696608
MCR026220 | HPR204 | 2016-11-01 | Overhead | 22544994 | 13488891 | 18977217
MCR026221 | HPR204 | 2016-12-01 | Labor | 49221532 | 44940698 | 48364263
MCR026222 | HPR204 | 2016-12-01 | Material | 98729357 | 90142789 | 93223448
MCR026223 | HPR204 | 2016-12-01 | Equipment | 19006896 | 17353852 | 18334383
MCR026224 | HPR204 | 2016-12-01 | Subcontract | 95931848 | 87588582 | 86822389
MCR026225 | HPR204 | 2016-12-01 | Overhead | 27737394 | 25325052 | 21080432
MCR026226 | HPR204 | 2017-01-01 | Labor | 54790916 | 49783196 | 45782636
MCR026227 | HPR204 | 2017-01-01 | Material | 109900518 | 99855951 | 83279242
MCR026228 | HPR204 | 2017-01-01 | Equipment | 21157514 | 19223782 | 16687793
MCR026229 | HPR204 | 2017-01-01 | Subcontract | 106786473 | 97026520 | 92823833
MCR026230 | HPR204 | 2017-01-01 | Overhead | 30875862 | 28053904 | 18597483
MCR026231 | HPR204 | 2017-02-01 | Labor | 56926088 | 30651713 | 30756937
MCR026232 | HPR204 | 2017-02-01 | Material | 114183280 | 61481709 | 60871333
MCR026233 | HPR204 | 2017-02-01 | Equipment | 21982010 | 11836160 | 15092873
MCR026234 | HPR204 | 2017-02-01 | Subcontract | 110947882 | 59739617 | 60444283
MCR026235 | HPR204 | 2017-02-01 | Overhead | 32079077 | 17272901 | 19973951
MCR026236 | HPR204 | 2017-03-01 | Labor | 55864833 | 38041507 | 34030113
MCR026237 | HPR204 | 2017-03-01 | Material | 112054599 | 76304279 | 86755649
MCR026238 | HPR204 | 2017-03-01 | Equipment | 21572207 | 14689729 | 13646628
MCR026239 | HPR204 | 2017-03-01 | Subcontract | 108879518 | 74142188 | 69528178
MCR026240 | HPR204 | 2017-03-01 | Overhead | 31481037 | 21437209 | 19717864
MCR026241 | HPR204 | 2017-04-01 | Labor | 51881200 | 53157424 | 42640938
MCR026242 | HPR204 | 2017-04-01 | Material | 104064162 | 106624033 | 114850703
MCR026243 | HPR204 | 2017-04-01 | Equipment | 20033927 | 20526741 | 19325217
MCR026244 | HPR204 | 2017-04-01 | Subcontract | 101115491 | 103602827 | 102111929
MCR026245 | HPR204 | 2017-04-01 | Overhead | 29236174 | 29955354 | 19970527
MCR026246 | HPR204 | 2017-05-01 | Labor | 45300033 | 36757048 | 47122202
MCR026247 | HPR204 | 2017-05-01 | Material | 90863549 | 73727890 | 74217521
MCR026248 | HPR204 | 2017-05-01 | Equipment | 17492609 | 14193735 | 15238269
MCR026249 | HPR204 | 2017-05-01 | Subcontract | 88288919 | 71638801 | 75595680
MCR026250 | HPR204 | 2017-05-01 | Overhead | 25527545 | 20713389 | 22019318
MCR026251 | HPR204 | 2017-06-01 | Labor | 36522360 | 38397014 | 34623506
MCR026252 | HPR204 | 2017-06-01 | Material | 73257149 | 77017360 | 83379355
MCR026253 | HPR204 | 2017-06-01 | Equipment | 14103110 | 14827008 | 17458296
MCR026254 | HPR204 | 2017-06-01 | Subcontract | 71181399 | 74835063 | 64540399
MCR026255 | HPR204 | 2017-06-01 | Overhead | 20581137 | 21637545 | 20153969
MCR026256 | HPR204 | 2017-07-01 | Labor | 26075764 | 32002788 | 33324034
MCR026257 | HPR204 | 2017-07-01 | Material | 52303195 | 64191717 | 58065211
MCR026258 | HPR204 | 2017-07-01 | Equipment | 10069157 | 12357878 | 12902700
MCR026259 | HPR204 | 2017-07-01 | Subcontract | 50821177 | 62372837 | 58311680
MCR026260 | HPR204 | 2017-07-01 | Overhead | 14694255 | 18034261 | 20286212
MCR026261 | HPR204 | 2017-08-01 | Labor | 14737992 | 35960521 | 33813580
MCR026262 | HPR204 | 2017-08-01 | Material | 29561707 | 72130202 | 79344191
MCR026263 | HPR204 | 2017-08-01 | Equipment | 5691076 | 13886156 | 13592418
MCR026264 | HPR204 | 2017-08-01 | Subcontract | 28724072 | 70086383 | 69223792
MCR026265 | HPR204 | 2017-08-01 | Overhead | 8305176 | 20264528 | 20050916
MCR026266 | HPR204 | 2017-09-01 | Labor | 4042681 | 31217999 | 27447073
MCR026267 | HPR204 | 2017-09-01 | Material | 8108875 | 62617574 | 69629232
MCR026268 | HPR204 | 2017-09-01 | Equipment | 1561081 | 12054831 | 11780977
MCR026269 | HPR204 | 2017-09-01 | Subcontract | 7879109 | 60843297 | 60586654
MCR026270 | HPR204 | 2017-09-01 | Overhead | 2278138 | 17592015 | 18814228
MCR026271 | HPR204 | 2017-10-01 | Labor | 0 | 19344354 | 18423859
MCR026272 | HPR204 | 2017-10-01 | Material | 0 | 38801223 | 36188711
MCR026273 | HPR204 | 2017-10-01 | Equipment | 0 | 7469823 | 8507376
MCR026274 | HPR204 | 2017-10-01 | Subcontract | 0 | 37701785 | 36597903
MCR026275 | HPR204 | 2017-10-01 | Overhead | 0 | 10900960 | 20331307
MCR026276 | HPR204 | 2017-11-01 | Labor | 0 | 11476047 | 11501168
MCR026277 | HPR204 | 2017-11-01 | Material | 0 | 23018843 | 20932027
MCR026278 | HPR204 | 2017-11-01 | Equipment | 0 | 4431476 | 4210169
MCR026279 | HPR204 | 2017-11-01 | Subcontract | 0 | 22366602 | 21281490
MCR026280 | HPR204 | 2017-11-01 | Overhead | 0 | 6467000 | 21136406
MCR026281 | HPR204 | 2017-12-01 | Labor | 0 | 2322975 | 2564483
MCR026282 | HPR204 | 2017-12-01 | Material | 0 | 4659461 | 5040541
MCR026283 | HPR204 | 2017-12-01 | Equipment | 0 | 897017 | 1311987
MCR026284 | HPR204 | 2017-12-01 | Subcontract | 0 | 4527435 | 4925288
MCR026285 | HPR204 | 2017-12-01 | Overhead | 0 | 1309046 | 20569178
MCR026286 | HPR205 | 2016-04-01 | Labor | 1848459 | 1934581 | 2093450
MCR026287 | HPR205 | 2016-04-01 | Material | 4565988 | 4778724 | 4906875
MCR026288 | HPR205 | 2016-04-01 | Equipment | 912438 | 954950 | 944222
MCR026289 | HPR205 | 2016-04-01 | Subcontract | 9649279 | 10098853 | 10803544
MCR026290 | HPR205 | 2016-04-01 | Overhead | 1467532 | 1535907 | 9270315
MCR026291 | HPR205 | 2016-05-01 | Labor | 5260245 | 1741333 | 1958194
MCR026292 | HPR205 | 2016-05-01 | Material | 12993646 | 4301370 | 4412786
MCR026293 | HPR205 | 2016-05-01 | Equipment | 2596567 | 859558 | 963111
MCR026294 | HPR205 | 2016-05-01 | Subcontract | 27459404 | 9090064 | 8179841
MCR026295 | HPR205 | 2016-05-01 | Overhead | 4176225 | 1382483 | 9605157
MCR026296 | HPR205 | 2016-06-01 | Labor | 8251038 | 7970658 | 7367250
MCR026297 | HPR205 | 2016-06-01 | Material | 20381382 | 19688800 | 18961628
MCR026298 | HPR205 | 2016-06-01 | Equipment | 4072885 | 3934484 | 4644189
MCR026299 | HPR205 | 2016-06-01 | Subcontract | 43071868 | 41608238 | 44138761
MCR026300 | HPR205 | 2016-06-01 | Overhead | 6550681 | 6328082 | 8691940
MCR026301 | HPR205 | 2016-07-01 | Labor | 10830099 | 5335523 | 5887968
MCR026302 | HPR205 | 2016-07-01 | Material | 26752076 | 13179594 | 12793608
MCR026303 | HPR205 | 2016-07-01 | Equipment | 5345964 | 2633726 | 2727894
MCR026304 | HPR205 | 2016-07-01 | Subcontract | 56535023 | 27852366 | 30294373
MCR026305 | HPR205 | 2016-07-01 | Overhead | 8598255 | 4235989 | 9404052
MCR026306 | HPR205 | 2016-08-01 | Labor | 13007134 | 7643375 | 7428468
MCR026307 | HPR205 | 2016-08-01 | Material | 32129699 | 18880359 | 21425980
MCR026308 | HPR205 | 2016-08-01 | Equipment | 6420594 | 3772930 | 3563196
MCR026309 | HPR205 | 2016-08-01 | Subcontract | 67899525 | 39899764 | 39086125
MCR026310 | HPR205 | 2016-08-01 | Overhead | 10326651 | 6068245 | 8992564
MCR026311 | HPR205 | 2016-09-01 | Labor | 14792339 | 10506960 | 10897091
MCR026312 | HPR205 | 2016-09-01 | Material | 36539441 | 25953871 | 27250778
MCR026313 | HPR205 | 2016-09-01 | Equipment | 7301809 | 5186456 | 6028090
MCR026314 | HPR205 | 2016-09-01 | Subcontract | 77218609 | 54848180 | 48783650
MCR026315 | HPR205 | 2016-09-01 | Overhead | 11743965 | 8341708 | 8799890
MCR026316 | HPR205 | 2016-10-01 | Labor | 16196465 | 8301791 | 8320726
MCR026317 | HPR205 | 2016-10-01 | Material | 40007858 | 20506751 | 20099635
MCR026318 | HPR205 | 2016-10-01 | Equipment | 7994915 | 4097938 | 4707807
MCR026319 | HPR205 | 2016-10-01 | Subcontract | 84548396 | 43336810 | 51440549
MCR026320 | HPR205 | 2016-10-01 | Overhead | 12858732 | 6590976 | 8930077
MCR026321 | HPR205 | 2016-11-01 | Labor | 17230889 | 7393029 | 7513754
MCR026322 | HPR205 | 2016-11-01 | Material | 42563049 | 18261963 | 17820016
MCR026323 | HPR205 | 2016-11-01 | Equipment | 8505528 | 3649354 | 3614405
MCR026324 | HPR205 | 2016-11-01 | Subcontract | 89948269 | 38592910 | 36700604
MCR026325 | HPR205 | 2016-11-01 | Overhead | 13679983 | 5869489 | 8888081
MCR026326 | HPR205 | 2016-12-01 | Labor | 17907697 | 18206301 | 17092600
MCR026327 | HPR205 | 2016-12-01 | Material | 44234874 | 44972473 | 45485042
MCR026328 | HPR205 | 2016-12-01 | Equipment | 8839615 | 8987012 | 9289535
MCR026329 | HPR205 | 2016-12-01 | Subcontract | 93481327 | 95040091 | 93904688
MCR026330 | HPR205 | 2016-12-01 | Overhead | 14217317 | 14454385 | 8479208
MCR026331 | HPR205 | 2017-01-01 | Labor | 18239796 | 18309530 | 22554370
MCR026332 | HPR205 | 2017-01-01 | Material | 45055211 | 45227464 | 42974145
MCR026333 | HPR205 | 2017-01-01 | Equipment | 9003546 | 9037968 | 8559829
MCR026334 | HPR205 | 2017-01-01 | Subcontract | 95214941 | 95578963 | 97426636
MCR026335 | HPR205 | 2017-01-01 | Overhead | 14480977 | 14536340 | 8362224
MCR026336 | HPR205 | 2017-02-01 | Labor | 18241041 | 16026666 | 16700642
MCR026337 | HPR205 | 2017-02-01 | Material | 45058287 | 39588426 | 42921027
MCR026338 | HPR205 | 2017-02-01 | Equipment | 9004161 | 7911098 | 8323862
MCR026339 | HPR205 | 2017-02-01 | Subcontract | 95221442 | 83662013 | 78608742
MCR026340 | HPR205 | 2017-02-01 | Overhead | 14481966 | 12723924 | 8821346
MCR026341 | HPR205 | 2017-03-01 | Labor | 17926407 | 18363026 | 17133026
MCR026342 | HPR205 | 2017-03-01 | Material | 44281091 | 45359610 | 43418691
MCR026343 | HPR205 | 2017-03-01 | Equipment | 8848851 | 9064375 | 9403640
MCR026344 | HPR205 | 2017-03-01 | Subcontract | 93578998 | 95858226 | 90904570
MCR026345 | HPR205 | 2017-03-01 | Overhead | 14232171 | 14578813 | 8710843
MCR026346 | HPR205 | 2017-04-01 | Labor | 17312201 | 8885715 | 11438693
MCR026347 | HPR205 | 2017-04-01 | Material | 42763903 | 21949136 | 25531852
MCR026348 | HPR205 | 2017-04-01 | Equipment | 8545665 | 4386175 | 4178296
MCR026349 | HPR205 | 2017-04-01 | Subcontract | 90372732 | 46384994 | 57048689
MCR026350 | HPR205 | 2017-04-01 | Overhead | 13744539 | 7054565 | 9464691
MCR026351 | HPR205 | 2017-05-01 | Labor | 16416344 | 13574961 | 14477867
MCR026352 | HPR205 | 2017-05-01 | Material | 40550994 | 33532323 | 32727040
MCR026353 | HPR205 | 2017-05-01 | Equipment | 8103452 | 6700885 | 7117755
MCR026354 | HPR205 | 2017-05-01 | Subcontract | 85696202 | 70863682 | 76680932
MCR026355 | HPR205 | 2017-05-01 | Overhead | 13033298 | 10777461 | 9792025
MCR026356 | HPR205 | 2017-06-01 | Labor | 15258759 | 15113964 | 13970721
MCR026357 | HPR205 | 2017-06-01 | Material | 37691573 | 37333907 | 42109793
MCR026358 | HPR205 | 2017-06-01 | Equipment | 7532043 | 7460570 | 7278121
MCR026359 | HPR205 | 2017-06-01 | Subcontract | 79653404 | 78897551 | 71894306
MCR026360 | HPR205 | 2017-06-01 | Overhead | 12114266 | 11999310 | 8621642
MCR026361 | HPR205 | 2017-07-01 | Labor | 13861900 | 13372690 | 14238684
MCR026362 | HPR205 | 2017-07-01 | Material | 34241109 | 33032682 | 29935036
MCR026363 | HPR205 | 2017-07-01 | Equipment | 6842525 | 6601040 | 8445547
MCR026364 | HPR205 | 2017-07-01 | Subcontract | 72361557 | 69807793 | 66796042
MCR026365 | HPR205 | 2017-07-01 | Overhead | 11005269 | 10616874 | 9181491
MCR026366 | HPR205 | 2017-08-01 | Labor | 12251532 | 9859454 | 8339490
MCR026367 | HPR205 | 2017-08-01 | Material | 30263242 | 24354428 | 28769450
MCR026368 | HPR205 | 2017-08-01 | Equipment | 6047613 | 4866834 | 4517989
MCR026369 | HPR205 | 2017-08-01 | Subcontract | 63955151 | 51468086 | 55947557
MCR026370 | HPR205 | 2017-08-01 | Overhead | 9726762 | 7827639 | 9032499
MCR026371 | HPR205 | 2017-09-01 | Labor | 10457909 | 9430093 | 10040238
MCR026372 | HPR205 | 2017-09-01 | Material | 25832707 | 23293836 | 19364077
MCR026373 | HPR205 | 2017-09-01 | Equipment | 5162243 | 4654892 | 4274808
MCR026374 | HPR205 | 2017-09-01 | Subcontract | 54592124 | 49226742 | 42511741
MCR026375 | HPR205 | 2017-09-01 | Overhead | 8302765 | 7486759 | 9113254
MCR026376 | HPR205 | 2017-10-01 | Labor | 8517701 | 9829044 | 10267764
MCR026377 | HPR205 | 2017-10-01 | Material | 21040084 | 24279308 | 23683574
MCR026378 | HPR205 | 2017-10-01 | Equipment | 4204516 | 4851822 | 5269720
MCR026379 | HPR205 | 2017-10-01 | Subcontract | 44463899 | 51309335 | 49209536
MCR026380 | HPR205 | 2017-10-01 | Overhead | 6762391 | 7803495 | 9375346
MCR026381 | HPR205 | 2017-11-01 | Labor | 6477412 | 8892415 | 7353677
MCR026382 | HPR205 | 2017-11-01 | Material | 16000242 | 21965687 | 23827740
MCR026383 | HPR205 | 2017-11-01 | Equipment | 3197386 | 4389483 | 5188246
MCR026384 | HPR205 | 2017-11-01 | Subcontract | 33813228 | 46419972 | 55506557
MCR026385 | HPR205 | 2017-11-01 | Overhead | 5142560 | 7059885 | 9895185
MCR026386 | HPR205 | 2017-12-01 | Labor | 4400289 | 9987675 | 11161860
MCR026387 | HPR205 | 2017-12-01 | Material | 10869416 | 24671153 | 23630246
MCR026388 | HPR205 | 2017-12-01 | Equipment | 2172075 | 4930126 | 5075275
MCR026389 | HPR205 | 2017-12-01 | Subcontract | 22970280 | 52137418 | 50404097
MCR026390 | HPR205 | 2017-12-01 | Overhead | 3493486 | 7929436 | 8674926
MCR026391 | HPR205 | 2018-01-01 | Labor | 2383675 | 14679437 | 15173766
MCR026392 | HPR205 | 2018-01-01 | Material | 5888057 | 36260554 | 35892556
MCR026393 | HPR205 | 2018-01-01 | Equipment | 1176632 | 7246078 | 7112967
MCR026394 | HPR205 | 2018-01-01 | Subcontract | 12443200 | 76629239 | 70979023
MCR026395 | HPR205 | 2018-01-01 | Overhead | 1892452 | 11654329 | 9118761
MCR026396 | HPR205 | 2018-02-01 | Labor | 632160 | 7694842 | 6490896
MCR026397 | HPR205 | 2018-02-01 | Material | 1561535 | 19007491 | 19504718
MCR026398 | HPR205 | 2018-02-01 | Equipment | 312047 | 3798336 | 4132457
MCR026399 | HPR205 | 2018-02-01 | Subcontract | 3299984 | 40168430 | 39469188
MCR026400 | HPR205 | 2018-02-01 | Overhead | 501885 | 6109105 | 9157125
MCR026401 | HPR205 | 2018-03-01 | Labor | 0 | 7277319 | 7736086
MCR026402 | HPR205 | 2018-03-01 | Material | 0 | 17976140 | 19197432
MCR026403 | HPR205 | 2018-03-01 | Equipment | 0 | 3592237 | 4000407
MCR026404 | HPR205 | 2018-03-01 | Subcontract | 0 | 37988882 | 38247101
MCR026405 | HPR205 | 2018-03-01 | Overhead | 0 | 5777624 | 8866781
MCR026406 | HPR205 | 2018-04-01 | Labor | 0 | 5895750 | 5861136
MCR026407 | HPR205 | 2018-04-01 | Material | 0 | 14563444 | 13738896
MCR026408 | HPR205 | 2018-04-01 | Equipment | 0 | 2910266 | 3153443
MCR026409 | HPR205 | 2018-04-01 | Subcontract | 0 | 30776849 | 32462432
MCR026410 | HPR205 | 2018-04-01 | Overhead | 0 | 4680766 | 9069191
MCR026411 | HPR205 | 2018-05-01 | Labor | 0 | 4665274 | 4531690
MCR026412 | HPR205 | 2018-05-01 | Material | 0 | 11523972 | 11768033
MCR026413 | HPR205 | 2018-05-01 | Equipment | 0 | 2302877 | 2347785
MCR026414 | HPR205 | 2018-05-01 | Subcontract | 0 | 24353549 | 25953733
MCR026415 | HPR205 | 2018-05-01 | Overhead | 0 | 3703864 | 8881962
MCR026416 | HPR205 | 2018-06-01 | Labor | 0 | 3309345 | 3658315
MCR026417 | HPR205 | 2018-06-01 | Material | 0 | 8174612 | 8269544
MCR026418 | HPR205 | 2018-06-01 | Equipment | 0 | 1633562 | 2031272
MCR026419 | HPR205 | 2018-06-01 | Subcontract | 0 | 17275364 | 17373035
MCR026420 | HPR205 | 2018-06-01 | Overhead | 0 | 2627362 | 9380799
MCR026421 | HPR205 | 2018-07-01 | Labor | 0 | 2051605 | 1800341
MCR026422 | HPR205 | 2018-07-01 | Material | 0 | 5067791 | 5014618
MCR026423 | HPR205 | 2018-07-01 | Equipment | 0 | 1012715 | 1028443
MCR026424 | HPR205 | 2018-07-01 | Subcontract | 0 | 10709737 | 8862681
MCR026425 | HPR205 | 2018-07-01 | Overhead | 0 | 1628814 | 8948620
MCR026426 | HPR205 | 2018-08-01 | Labor | 0 | 993763 | 980410
MCR026427 | HPR205 | 2018-08-01 | Material | 0 | 2454754 | 2945383
MCR026428 | HPR205 | 2018-08-01 | Equipment | 0 | 490542 | 591901
MCR026429 | HPR205 | 2018-08-01 | Subcontract | 0 | 5187620 | 6390348
MCR026430 | HPR205 | 2018-08-01 | Overhead | 0 | 788971 | 9126318
MCR026431 | HPR205 | 2018-09-01 | Labor | 0 | 455372 | 501364
MCR026432 | HPR205 | 2018-09-01 | Material | 0 | 1124842 | 1081909
MCR026433 | HPR205 | 2018-09-01 | Equipment | 0 | 224781 | 253071
MCR026434 | HPR205 | 2018-09-01 | Subcontract | 0 | 2377122 | 2258324
MCR026435 | HPR205 | 2018-09-01 | Overhead | 0 | 361530 | 9160994
MCR026436 | HPR206 | 2017-02-01 | Labor | 54492290 | 48978054 | 45524788
MCR026437 | HPR206 | 2017-02-01 | Material | 96380041 | 86627060 | 83019919
MCR026438 | HPR206 | 2017-02-01 | Equipment | 23088116 | 20751761 | 19981438
MCR026439 | HPR206 | 2017-02-01 | Subcontract | 136801069 | 122957764 | 105390967
MCR026440 | HPR206 | 2017-02-01 | Overhead | 25614167 | 23022194 | 72089976
MCR026441 | HPR206 | 2017-03-01 | Labor | 143546372 | 97965756 | 105803715
MCR026442 | HPR206 | 2017-03-01 | Material | 253889224 | 173271183 | 173849132
MCR026443 | HPR206 | 2017-03-01 | Equipment | 60819893 | 41507610 | 39753410
MCR026444 | HPR206 | 2017-03-01 | Subcontract | 360368357 | 245939747 | 232491304
MCR026445 | HPR206 | 2017-03-01 | Overhead | 67474146 | 46048922 | 74991145
MCR026446 | HPR206 | 2017-04-01 | Labor | 203888614 | 127346635 | 131220621
MCR026447 | HPR206 | 2017-04-01 | Material | 360616023 | 225236889 | 219594734
MCR026448 | HPR206 | 2017-04-01 | Equipment | 86386605 | 53956144 | 58516343
MCR026449 | HPR206 | 2017-04-01 | Subcontract | 511855533 | 319699460 | 344696162
MCR026450 | HPR206 | 2017-04-01 | Overhead | 95838089 | 59859440 | 74717337
MCR026451 | HPR206 | 2017-05-01 | Labor | 237254213 | 166745341 | 144474204
MCR026452 | HPR206 | 2017-05-01 | Material | 419629469 | 294921039 | 327930399
MCR026453 | HPR206 | 2017-05-01 | Equipment | 100523446 | 70649183 | 72260621
MCR026454 | HPR206 | 2017-05-01 | Subcontract | 595618752 | 418608592 | 396710699
MCR026455 | HPR206 | 2017-05-01 | Overhead | 111521630 | 78378849 | 76898937
MCR026456 | HPR206 | 2017-06-01 | Labor | 245627511 | 246566069 | 252558039
MCR026457 | HPR206 | 2017-06-01 | Material | 434439248 | 436099267 | 376143100
MCR026458 | HPR206 | 2017-06-01 | Equipment | 104071171 | 104468833 | 114299226
MCR026459 | HPR206 | 2017-06-01 | Subcontract | 616639635 | 618995853 | 518042639
MCR026460 | HPR206 | 2017-06-01 | Overhead | 115457508 | 115898679 | 74758440
MCR026461 | HPR206 | 2017-07-01 | Labor | 231338491 | 210843927 | 191058410
MCR026462 | HPR206 | 2017-07-01 | Material | 409166383 | 372917825 | 438560561
MCR026463 | HPR206 | 2017-07-01 | Equipment | 98016983 | 89333537 | 90744619
MCR026464 | HPR206 | 2017-07-01 | Subcontract | 580767530 | 529316613 | 584278163
MCR026465 | HPR206 | 2017-07-01 | Overhead | 108740937 | 99107443 | 69382549
MCR026466 | HPR206 | 2017-08-01 | Labor | 197229691 | 133638083 | 160414630
MCR026467 | HPR206 | 2017-08-01 | Material | 348838443 | 236364519 | 193183418
MCR026468 | HPR206 | 2017-08-01 | Equipment | 83565252 | 56621800 | 49795230
MCR026469 | HPR206 | 2017-08-01 | Subcontract | 495138529 | 335493930 | 355181300
MCR026470 | HPR206 | 2017-08-01 | Overhead | 92708054 | 62816743 | 71604015
MCR026471 | HPR206 | 2017-09-01 | Labor | 146983725 | 210022218 | 179704561
MCR026472 | HPR206 | 2017-09-01 | Material | 259968840 | 371464476 | 400514206
MCR026473 | HPR206 | 2017-09-01 | Equipment | 62276283 | 88985383 | 99371581
MCR026474 | HPR206 | 2017-09-01 | Subcontract | 368997717 | 527253740 | 490597864
MCR026475 | HPR206 | 2017-09-01 | Overhead | 69089878 | 98721197 | 75711946
MCR026476 | HPR206 | 2017-10-01 | Labor | 85916629 | 123100888 | 137444081
MCR026477 | HPR206 | 2017-10-01 | Material | 151959997 | 217727473 | 209652350
MCR026478 | HPR206 | 2017-10-01 | Equipment | 36402454 | 52157242 | 43866513
MCR026479 | HPR206 | 2017-10-01 | Subcontract | 215690818 | 309040655 | 290796943
MCR026480 | HPR206 | 2017-10-01 | Overhead | 40385215 | 57863721 | 70822374
MCR026481 | HPR206 | 2017-11-01 | Labor | 24163510 | 116155091 | 95557705
MCR026482 | HPR206 | 2017-11-01 | Material | 42737790 | 205442502 | 214187066
MCR026483 | HPR206 | 2017-11-01 | Equipment | 10237960 | 49214342 | 43705745
MCR026484 | HPR206 | 2017-11-01 | Subcontract | 60661681 | 291603463 | 296020820
MCR026485 | HPR206 | 2017-11-01 | Overhead | 11358087 | 54598841 | 76655533
MCR026486 | HPR206 | 2017-12-01 | Labor | 0 | 78980419 | 87175706
MCR026487 | HPR206 | 2017-12-01 | Material | 0 | 139691982 | 133997706
MCR026488 | HPR206 | 2017-12-01 | Equipment | 0 | 33463616 | 38138498
MCR026489 | HPR206 | 2017-12-01 | Subcontract | 0 | 198277695 | 156794045
MCR026490 | HPR206 | 2017-12-01 | Overhead | 0 | 37124841 | 72446176
MCR026491 | HPR206 | 2018-01-01 | Labor | 0 | 10098565 | 8635556
MCR026492 | HPR206 | 2018-01-01 | Material | 0 | 17861244 | 24221279
MCR026493 | HPR206 | 2018-01-01 | Equipment | 0 | 4278712 | 7395907
MCR026494 | HPR206 | 2018-01-01 | Subcontract | 0 | 25352108 | 37345929
MCR026495 | HPR206 | 2018-01-01 | Overhead | 0 | 4746843 | 74226091
MCR026496 | HPR207 | 2022-05-01 | Labor | 2332424 | 1363555 | 1389876
MCR026497 | HPR207 | 2022-05-01 | Material | 5623579 | 3287592 | 2891456
MCR026498 | HPR207 | 2022-05-01 | Equipment | 1208138 | 706288 | 701996
MCR026499 | HPR207 | 2022-05-01 | Subcontract | 7704968 | 4504390 | 4782119
MCR026500 | HPR207 | 2022-05-01 | Overhead | 1741857 | 1018305 | 10792929
MCR026501 | HPR207 | 2022-06-01 | Labor | 6620737 | 5037323 | 5718728
MCR026502 | HPR207 | 2022-06-01 | Material | 15962890 | 12145209 | 12021414
MCR026503 | HPR207 | 2022-06-01 | Equipment | 3429378 | 2609209 | 2854273
MCR026504 | HPR207 | 2022-06-01 | Subcontract | 21871049 | 16640375 | 15764678
MCR026505 | HPR207 | 2022-06-01 | Overhead | 4944374 | 3761879 | 11346667
MCR026506 | HPR207 | 2022-07-01 | Labor | 10353527 | 3963060 | 3859779
MCR026507 | HPR207 | 2022-07-01 | Material | 24962815 | 9555113 | 10298188
MCR026508 | HPR207 | 2022-07-01 | Equipment | 5362871 | 2052767 | 2210092
MCR026509 | HPR207 | 2022-07-01 | Subcontract | 34202011 | 13091636 | 14953617
MCR026510 | HPR207 | 2022-07-01 | Overhead | 7732027 | 2959618 | 10978351
MCR026511 | HPR207 | 2022-08-01 | Labor | 13543647 | 6510893 | 6838513
MCR026512 | HPR207 | 2022-08-01 | Material | 32654335 | 15698053 | 16895171
MCR026513 | HPR207 | 2022-08-01 | Equipment | 7015274 | 3372482 | 3425899
MCR026514 | HPR207 | 2022-08-01 | Subcontract | 44740304 | 21508190 | 19571260
MCR026515 | HPR207 | 2022-08-01 | Overhead | 10114413 | 4862343 | 10393415
MCR026516 | HPR207 | 2022-09-01 | Labor | 16204592 | 7931628 | 8106042
MCR026517 | HPR207 | 2022-09-01 | Material | 39069992 | 19123508 | 18883288
MCR026518 | HPR207 | 2022-09-01 | Equipment | 8393578 | 4108387 | 4490923
MCR026519 | HPR207 | 2022-09-01 | Subcontract | 53530514 | 26201470 | 23159057
MCR026520 | HPR207 | 2022-09-01 | Overhead | 12101610 | 5923350 | 9426349
MCR026521 | HPR207 | 2022-10-01 | Labor | 18350585 | 15142981 | 14555389
MCR026522 | HPR207 | 2022-10-01 | Material | 44244077 | 36510400 | 34258701
MCR026523 | HPR207 | 2022-10-01 | Equipment | 9505150 | 7843690 | 8025810
MCR026524 | HPR207 | 2022-10-01 | Subcontract | 60619623 | 50023570 | 54573123
MCR026525 | HPR207 | 2022-10-01 | Overhead | 13704240 | 11308797 | 10575726
MCR026526 | HPR207 | 2022-11-01 | Labor | 19996668 | 13812080 | 14797297
MCR026527 | HPR207 | 2022-11-01 | Material | 48212856 | 33301538 | 38081110
MCR026528 | HPR207 | 2022-11-01 | Equipment | 10357780 | 7154316 | 6854700
MCR026529 | HPR207 | 2022-11-01 | Subcontract | 66057320 | 45627049 | 45527961
MCR026530 | HPR207 | 2022-11-01 | Overhead | 14933537 | 10314878 | 9823521
MCR026531 | HPR207 | 2022-12-01 | Labor | 21158814 | 20079335 | 20856888
MCR026532 | HPR207 | 2022-12-01 | Material | 51014841 | 48412170 | 46554880
MCR026533 | HPR207 | 2022-12-01 | Equipment | 10959743 | 10400599 | 11283832
MCR026534 | HPR207 | 2022-12-01 | Subcontract | 69896372 | 66330404 | 71552252
MCR026535 | HPR207 | 2022-12-01 | Overhead | 15801429 | 14995273 | 10671373
MCR026536 | HPR207 | 2023-01-01 | Labor | 21854068 | 10829924 | 12051138
MCR026537 | HPR207 | 2023-01-01 | Material | 52691129 | 26111429 | 25975669
MCR026538 | HPR207 | 2023-01-01 | Equipment | 11319867 | 5609633 | 6380458
MCR026539 | HPR207 | 2023-01-01 | Subcontract | 72193084 | 35775748 | 28807451
MCR026540 | HPR207 | 2023-01-01 | Overhead | 16320645 | 8087801 | 10114826
MCR026541 | HPR207 | 2023-02-01 | Labor | 22100717 | 16378509 | 16249724
MCR026542 | HPR207 | 2023-02-01 | Material | 53285810 | 39489314 | 38568328
MCR026543 | HPR207 | 2023-02-01 | Equipment | 11447625 | 8483663 | 8277668
MCR026544 | HPR207 | 2023-02-01 | Subcontract | 73007868 | 54105035 | 47234297
MCR026545 | HPR207 | 2023-02-01 | Overhead | 16504843 | 12231491 | 10407026
MCR026546 | HPR207 | 2023-03-01 | Labor | 21918509 | 22422916 | 21349116
MCR026547 | HPR207 | 2023-03-01 | Material | 52846499 | 54062647 | 54093278
MCR026548 | HPR207 | 2023-03-01 | Equipment | 11353246 | 11614516 | 12377536
MCR026549 | HPR207 | 2023-03-01 | Subcontract | 72405959 | 74072227 | 85567163
MCR026550 | HPR207 | 2023-03-01 | Overhead | 16368770 | 16745462 | 11340043
MCR026551 | HPR207 | 2023-04-01 | Labor | 21328932 | 12003358 | 12965238
MCR026552 | HPR207 | 2023-04-01 | Material | 51425002 | 28940629 | 32404071
MCR026553 | HPR207 | 2023-04-01 | Equipment | 11047859 | 6217443 | 6701315
MCR026554 | HPR207 | 2023-04-01 | Subcontract | 70458341 | 39652089 | 38997993
MCR026555 | HPR207 | 2023-04-01 | Overhead | 15928473 | 8964123 | 9828927
MCR026556 | HPR207 | 2023-05-01 | Labor | 20355581 | 19803054 | 20289143
MCR026557 | HPR207 | 2023-05-01 | Material | 49078211 | 47746042 | 48271632
MCR026558 | HPR207 | 2023-05-01 | Equipment | 10543688 | 10257492 | 10896678
MCR026559 | HPR207 | 2023-05-01 | Subcontract | 67242960 | 65417730 | 63009109
MCR026560 | HPR207 | 2023-05-01 | Overhead | 15201574 | 14788945 | 9473726
MCR026561 | HPR207 | 2023-06-01 | Labor | 19024659 | 21997334 | 21859701
MCR026562 | HPR207 | 2023-06-01 | Material | 45869297 | 53036549 | 50914477
MCR026563 | HPR207 | 2023-06-01 | Equipment | 9854303 | 11394075 | 11705962
MCR026564 | HPR207 | 2023-06-01 | Subcontract | 62846368 | 72666351 | 66309695
MCR026565 | HPR207 | 2023-06-01 | Overhead | 14207639 | 16427637 | 11053531
MCR026566 | HPR207 | 2023-07-01 | Labor | 17365662 | 11148201 | 11484125
MCR026567 | HPR207 | 2023-07-01 | Material | 41869382 | 26878809 | 25310910
MCR026568 | HPR207 | 2023-07-01 | Equipment | 8994983 | 5774493 | 6031452
MCR026569 | HPR207 | 2023-07-01 | Subcontract | 57366010 | 36827151 | 37891220
MCR026570 | HPR207 | 2023-07-01 | Overhead | 12968698 | 8325491 | 10983564
MCR026571 | HPR207 | 2023-08-01 | Labor | 15412391 | 14457733 | 15044520
MCR026572 | HPR207 | 2023-08-01 | Material | 37159960 | 34858236 | 36194255
MCR026573 | HPR207 | 2023-08-01 | Equipment | 7983238 | 7488748 | 6991898
MCR026574 | HPR207 | 2023-08-01 | Subcontract | 50913544 | 47759910 | 49054285
MCR026575 | HPR207 | 2023-08-01 | Overhead | 11509993 | 10797053 | 10352413
MCR026576 | HPR207 | 2023-09-01 | Labor | 13204480 | 18576190 | 16187607
MCR026577 | HPR207 | 2023-09-01 | Material | 31836588 | 44788021 | 41328539
MCR026578 | HPR207 | 2023-09-01 | Equipment | 6839594 | 9622007 | 9384331
MCR026579 | HPR207 | 2023-09-01 | Subcontract | 43619895 | 61364891 | 48378970
MCR026580 | HPR207 | 2023-09-01 | Overhead | 9861122 | 13872722 | 11126067
MCR026581 | HPR207 | 2023-10-01 | Labor | 10789880 | 17444580 | 19179189
MCR026582 | HPR207 | 2023-10-01 | Material | 26014880 | 42059659 | 42339245
MCR026583 | HPR207 | 2023-10-01 | Equipment | 5588891 | 9035861 | 9026675
MCR026584 | HPR207 | 2023-10-01 | Subcontract | 35643466 | 57626711 | 64127422
MCR026585 | HPR207 | 2023-10-01 | Overhead | 8057896 | 13027635 | 10672494
MCR026586 | HPR207 | 2023-11-01 | Labor | 8229275 | 12533206 | 14325256
MCR026587 | HPR207 | 2023-11-01 | Material | 19841147 | 30218116 | 28047835
MCR026588 | HPR207 | 2023-11-01 | Equipment | 4262561 | 6491891 | 8281996
MCR026589 | HPR207 | 2023-11-01 | Subcontract | 27184720 | 41402397 | 41278500
MCR026590 | HPR207 | 2023-11-01 | Overhead | 6145633 | 9359814 | 10429829
MCR026591 | HPR207 | 2023-12-01 | Labor | 5604993 | 11725781 | 11436910
MCR026592 | HPR207 | 2023-12-01 | Material | 13513887 | 28271380 | 25395114
MCR026593 | HPR207 | 2023-12-01 | Equipment | 2903248 | 6073665 | 5268292
MCR026594 | HPR207 | 2023-12-01 | Subcontract | 18515626 | 38735137 | 42643301
MCR026595 | HPR207 | 2023-12-01 | Overhead | 4185816 | 8756828 | 10443932
MCR026596 | HPR207 | 2024-01-01 | Labor | 3043349 | 11530941 | 11318230
MCR026597 | HPR207 | 2024-01-01 | Material | 7337651 | 27801612 | 33123151
MCR026598 | HPR207 | 2024-01-01 | Equipment | 1576380 | 5972742 | 6564267
MCR026599 | HPR207 | 2024-01-01 | Subcontract | 10053450 | 38091499 | 37748302
MCR026600 | HPR207 | 2024-01-01 | Overhead | 2272777 | 8611321 | 10523155
MCR026601 | HPR207 | 2024-02-01 | Labor | 808657 | 9293775 | 9182426
MCR026602 | HPR207 | 2024-02-01 | Material | 1949708 | 22407705 | 20126242
MCR026603 | HPR207 | 2024-02-01 | Equipment | 418864 | 4813946 | 4500832
MCR026604 | HPR207 | 2024-02-01 | Subcontract | 2671331 | 30701209 | 31187365
MCR026605 | HPR207 | 2024-02-01 | Overhead | 603906 | 6940603 | 10844028
MCR026606 | HPR207 | 2024-03-01 | Labor | 0 | 7292619 | 7707430
MCR026607 | HPR207 | 2024-03-01 | Material | 0 | 17582827 | 19432660
MCR026608 | HPR207 | 2024-03-01 | Equipment | 0 | 3777396 | 4634536
MCR026609 | HPR207 | 2024-03-01 | Subcontract | 0 | 24090555 | 23084609
MCR026610 | HPR207 | 2024-03-01 | Overhead | 0 | 5446137 | 10337596
MCR026611 | HPR207 | 2024-04-01 | Labor | 0 | 6500806 | 5583728
MCR026612 | HPR207 | 2024-04-01 | Material | 0 | 15673732 | 14332374
MCR026613 | HPR207 | 2024-04-01 | Equipment | 0 | 3367257 | 3008668
MCR026614 | HPR207 | 2024-04-01 | Subcontract | 0 | 21474868 | 22495304
MCR026615 | HPR207 | 2024-04-01 | Overhead | 0 | 4854810 | 10058913
MCR026616 | HPR207 | 2024-05-01 | Labor | 0 | 5641123 | 6037513
MCR026617 | HPR207 | 2024-05-01 | Material | 0 | 13600998 | 11786631
MCR026618 | HPR207 | 2024-05-01 | Equipment | 0 | 2921962 | 3635663
MCR026619 | HPR207 | 2024-05-01 | Subcontract | 0 | 18634977 | 17162877
MCR026620 | HPR207 | 2024-05-01 | Overhead | 0 | 4212798 | 9484881
MCR026621 | HPR207 | 2024-06-01 | Labor | 0 | 3435596 | 3550869
MCR026622 | HPR207 | 2024-06-01 | Material | 0 | 8283373 | 7269285
MCR026623 | HPR207 | 2024-06-01 | Equipment | 0 | 1779554 | 1736347
MCR026624 | HPR207 | 2024-06-01 | Subcontract | 0 | 11349202 | 10577278
MCR026625 | HPR207 | 2024-06-01 | Overhead | 0 | 2565707 | 10025670
MCR026626 | HPR207 | 2024-07-01 | Labor | 0 | 1352753 | 1392921
MCR026627 | HPR207 | 2024-07-01 | Material | 0 | 3261547 | 4722179
MCR026628 | HPR207 | 2024-07-01 | Equipment | 0 | 700692 | 864384
MCR026629 | HPR207 | 2024-07-01 | Subcontract | 0 | 4468705 | 4688677
MCR026630 | HPR207 | 2024-07-01 | Overhead | 0 | 1010237 | 9771175
MCR026631 | HPR207 | 2024-08-01 | Labor | 0 | 946130 | 909343
MCR026632 | HPR207 | 2024-08-01 | Material | 0 | 2281161 | 2366551
MCR026633 | HPR207 | 2024-08-01 | Equipment | 0 | 490072 | 660860
MCR026634 | HPR207 | 2024-08-01 | Subcontract | 0 | 3125461 | 3344073
MCR026635 | HPR207 | 2024-08-01 | Overhead | 0 | 706571 | 9861553
MCR026636 | HPR207 | 2024-09-01 | Labor | 0 | 446764 | 396746
MCR026637 | HPR207 | 2024-09-01 | Material | 0 | 1077167 | 773086
MCR026638 | HPR207 | 2024-09-01 | Equipment | 0 | 231413 | 325587
MCR026639 | HPR207 | 2024-09-01 | Subcontract | 0 | 1475847 | 1596934
MCR026640 | HPR207 | 2024-09-01 | Overhead | 0 | 333644 | 11037604
MCR026641 | HPR208 | 2020-03-01 | Labor | 5823685 | 3562962 | 3913941
MCR026642 | HPR208 | 2020-03-01 | Material | 13673000 | 8365214 | 8487645
MCR026643 | HPR208 | 2020-03-01 | Equipment | 2928193 | 1791484 | 1893001
MCR026644 | HPR208 | 2020-03-01 | Subcontract | 17112550 | 10469549 | 12930539
MCR026645 | HPR208 | 2020-03-01 | Overhead | 3297114 | 2017192 | 11747403
MCR026646 | HPR208 | 2020-04-01 | Labor | 15972923 | 10443424 | 9997028
MCR026647 | HPR208 | 2020-04-01 | Material | 37501643 | 24519341 | 25048499
MCR026648 | HPR208 | 2020-04-01 | Equipment | 8031307 | 5251033 | 5913738
MCR026649 | HPR208 | 2020-04-01 | Subcontract | 46935476 | 30687374 | 32541516
MCR026650 | HPR208 | 2020-04-01 | Overhead | 9043165 | 5912606 | 13185427
MCR026651 | HPR208 | 2020-05-01 | Labor | 23935495 | 19782474 | 24227418
MCR026652 | HPR208 | 2020-05-01 | Material | 56196376 | 46445806 | 49650473
MCR026653 | HPR208 | 2020-05-01 | Equipment | 12034948 | 9946778 | 9886619
MCR026654 | HPR208 | 2020-05-01 | Subcontract | 70333016 | 58129614 | 59089638
MCR026655 | HPR208 | 2020-05-01 | Overhead | 13551223 | 11199965 | 13626778
MCR026656 | HPR208 | 2020-06-01 | Labor | 29797335 | 20853224 | 16045775
MCR026657 | HPR208 | 2020-06-01 | Material | 69958954 | 48959740 | 50324505
MCR026658 | HPR208 | 2020-06-01 | Equipment | 14982326 | 10485159 | 8613087
MCR026659 | HPR208 | 2020-06-01 | Subcontract | 87557679 | 61275948 | 66914212
MCR026660 | HPR208 | 2020-06-01 | Overhead | 16869938 | 11806177 | 12532407
MCR026661 | HPR208 | 2020-07-01 | Labor | 33651999 | 25476295 | 26996859
MCR026662 | HPR208 | 2020-07-01 | Material | 79009034 | 59813905 | 61670291
MCR026663 | HPR208 | 2020-07-01 | Equipment | 16920480 | 12809674 | 14694102
MCR026664 | HPR208 | 2020-07-01 | Subcontract | 98884378 | 74860563 | 79131735
MCR026665 | HPR208 | 2020-07-01 | Overhead | 19052279 | 14423556 | 12332030
MCR026666 | HPR208 | 2020-08-01 | Labor | 35602367 | 24236683 | 26555858
MCR026667 | HPR208 | 2020-08-01 | Material | 83588159 | 56903512 | 45223358
MCR026668 | HPR208 | 2020-08-01 | Equipment | 17901140 | 12186388 | 11792347
MCR026669 | HPR208 | 2020-08-01 | Subcontract | 104615418 | 71218037 | 81979917
MCR026670 | HPR208 | 2020-08-01 | Overhead | 20156491 | 13721742 | 12473321
MCR026671 | HPR208 | 2020-09-01 | Labor | 35762990 | 27361623 | 25811961
MCR026672 | HPR208 | 2020-09-01 | Material | 83965274 | 64240328 | 74964089
MCR026673 | HPR208 | 2020-09-01 | Equipment | 17981902 | 13757632 | 12339531
MCR026674 | HPR208 | 2020-09-01 | Subcontract | 105087399 | 80400487 | 88868442
MCR026675 | HPR208 | 2020-09-01 | Overhead | 20247429 | 15490946 | 13426456
MCR026676 | HPR208 | 2020-10-01 | Labor | 34263455 | 29449643 | 29788310
MCR026677 | HPR208 | 2020-10-01 | Material | 80444627 | 69142635 | 64385604
MCR026678 | HPR208 | 2020-10-01 | Equipment | 17227925 | 14807504 | 15307397
MCR026679 | HPR208 | 2020-10-01 | Subcontract | 100681106 | 86536009 | 103624912
MCR026680 | HPR208 | 2020-10-01 | Overhead | 19398459 | 16673090 | 13578154
MCR026681 | HPR208 | 2020-11-01 | Labor | 31253458 | 18248193 | 15311661
MCR026682 | HPR208 | 2020-11-01 | Material | 73377679 | 42843581 | 40289453
MCR026683 | HPR208 | 2020-11-01 | Equipment | 15714476 | 9175330 | 9208602
MCR026684 | HPR208 | 2020-11-01 | Subcontract | 91836411 | 53621220 | 57404199
MCR026685 | HPR208 | 2020-11-01 | Overhead | 17694331 | 10331323 | 12579392
MCR026686 | HPR208 | 2020-12-01 | Labor | 26910940 | 34416430 | 35582862
MCR026687 | HPR208 | 2020-12-01 | Material | 63182202 | 80803786 | 84919462
MCR026688 | HPR208 | 2020-12-01 | Equipment | 13531025 | 17304842 | 17822523
MCR026689 | HPR208 | 2020-12-01 | Subcontract | 79076181 | 101130614 | 106601202
MCR026690 | HPR208 | 2020-12-01 | Overhead | 15235788 | 19485066 | 12794650
MCR026691 | HPR208 | 2021-01-01 | Labor | 21456331 | 32266506 | 31102542
MCR026692 | HPR208 | 2021-01-01 | Material | 50375729 | 75756139 | 75003483
MCR026693 | HPR208 | 2021-01-01 | Equipment | 10788406 | 16223844 | 17168590
MCR026694 | HPR208 | 2021-01-01 | Subcontract | 63048140 | 94813192 | 126795501
MCR026695 | HPR208 | 2021-01-01 | Overhead | 12147629 | 18267874 | 13394761
MCR026696 | HPR208 | 2021-02-01 | Labor | 15180899 | 23119661 | 23296528
MCR026697 | HPR208 | 2021-02-01 | Material | 35642108 | 54280940 | 63373768
MCR026698 | HPR208 | 2021-02-01 | Equipment | 7633071 | 11624741 | 10864892
MCR026699 | HPR208 | 2021-02-01 | Subcontract | 44608161 | 67935737 | 51815152
MCR026700 | HPR208 | 2021-02-01 | Overhead | 8594756 | 13089334 | 13259181
MCR026701 | HPR208 | 2021-03-01 | Labor | 8516554 | 13974965 | 14370459
MCR026702 | HPR208 | 2021-03-01 | Material | 19995385 | 32810786 | 33700867
MCR026703 | HPR208 | 2021-03-01 | Equipment | 4282188 | 7026719 | 7733939
MCR026704 | HPR208 | 2021-03-01 | Subcontract | 25025382 | 41064597 | 55669172
MCR026705 | HPR208 | 2021-03-01 | Overhead | 4821697 | 7912010 | 12382960
MCR026706 | HPR208 | 2021-04-01 | Labor | 2322758 | 15523283 | 14619949
MCR026707 | HPR208 | 2021-04-01 | Material | 5453430 | 36445965 | 33035136
MCR026708 | HPR208 | 2021-04-01 | Equipment | 1167900 | 7805224 | 7892400
MCR026709 | HPR208 | 2021-04-01 | Subcontract | 6825284 | 45614234 | 49575256
MCR026710 | HPR208 | 2021-04-01 | Overhead | 1315043 | 8788599 | 12738948
MCR026711 | HPR208 | 2021-05-01 | Labor | 0 | 11570415 | 10276227
MCR026712 | HPR208 | 2021-05-01 | Material | 0 | 27165319 | 27925379
MCR026713 | HPR208 | 2021-05-01 | Equipment | 0 | 5817692 | 5871072
MCR026714 | HPR208 | 2021-05-01 | Subcontract | 0 | 33998969 | 40932906
MCR026715 | HPR208 | 2021-05-01 | Overhead | 0 | 6550659 | 13819985
MCR026716 | HPR208 | 2021-06-01 | Labor | 0 | 8760873 | 9121978
MCR026717 | HPR208 | 2021-06-01 | Material | 0 | 20569005 | 24393624
MCR026718 | HPR208 | 2021-06-01 | Equipment | 0 | 4405033 | 5098412
MCR026719 | HPR208 | 2021-06-01 | Subcontract | 0 | 25743300 | 28176050
MCR026720 | HPR208 | 2021-06-01 | Overhead | 0 | 4960020 | 13551491
MCR026721 | HPR208 | 2021-07-01 | Labor | 0 | 1404533 | 1588734
MCR026722 | HPR208 | 2021-07-01 | Material | 0 | 3297600 | 1860624
MCR026723 | HPR208 | 2021-07-01 | Equipment | 0 | 706210 | 602748
MCR026724 | HPR208 | 2021-07-01 | Subcontract | 0 | 4127137 | 4553044
MCR026725 | HPR208 | 2021-07-01 | Overhead | 0 | 795185 | 12853215
MCR026726 | HPR209 | 2021-01-01 | Labor | 4401484 | 1470798 | 1504908
MCR026727 | HPR209 | 2021-01-01 | Material | 12445596 | 4158816 | 3520260
MCR026728 | HPR209 | 2021-01-01 | Equipment | 2246388 | 750652 | 792062
MCR026729 | HPR209 | 2021-01-01 | Subcontract | 24745020 | 8268787 | 9470979
MCR026730 | HPR209 | 2021-01-01 | Overhead | 3978146 | 1329336 | 20869124
MCR026731 | HPR209 | 2021-02-01 | Labor | 12378533 | 5792654 | 6445188
MCR026732 | HPR209 | 2021-02-01 | Material | 35001423 | 16379254 | 18393546
MCR026733 | HPR209 | 2021-02-01 | Equipment | 6317639 | 2956400 | 3141109
MCR026734 | HPR209 | 2021-02-01 | Subcontract | 69591760 | 32566136 | 38803249
MCR026735 | HPR209 | 2021-02-01 | Overhead | 11187956 | 5235512 | 21471350
MCR026736 | HPR209 | 2021-03-01 | Labor | 19140549 | 8461411 | 9449980
MCR026737 | HPR209 | 2021-03-01 | Material | 54121637 | 23925407 | 23293544
MCR026738 | HPR209 | 2021-03-01 | Equipment | 9768773 | 4318455 | 4928942
MCR026739 | HPR209 | 2021-03-01 | Subcontract | 107607623 | 47569814 | 46739645
MCR026740 | HPR209 | 2021-03-01 | Overhead | 17299596 | 7647586 | 21328272
MCR026741 | HPR209 | 2021-04-01 | Labor | 24720765 | 12366674 | 14993524
MCR026742 | HPR209 | 2021-04-01 | Material | 69900202 | 34967891 | 33127716
MCR026743 | HPR209 | 2021-04-01 | Equipment | 12616751 | 6311586 | 6469661
MCR026744 | HPR209 | 2021-04-01 | Subcontract | 138979436 | 69525089 | 71468780
MCR026745 | HPR209 | 2021-04-01 | Overhead | 22343102 | 11177237 | 18570813
MCR026746 | HPR209 | 2021-05-01 | Labor | 29154408 | 16282018 | 17067622
MCR026747 | HPR209 | 2021-05-01 | Material | 82436730 | 46038882 | 50857698
MCR026748 | HPR209 | 2021-05-01 | Equipment | 14879552 | 8309863 | 9351044
MCR026749 | HPR209 | 2021-05-01 | Subcontract | 163905252 | 91537043 | 98827234
MCR026750 | HPR209 | 2021-05-01 | Overhead | 26350313 | 14716001 | 21155075
MCR026751 | HPR209 | 2021-06-01 | Labor | 32478996 | 20453948 | 23405756
MCR026752 | HPR209 | 2021-06-01 | Material | 91837303 | 57835391 | 58119147
MCR026753 | HPR209 | 2021-06-01 | Equipment | 16576323 | 10439093 | 10177339
MCR026754 | HPR209 | 2021-06-01 | Subcontract | 182595990 | 114991513 | 118009254
MCR026755 | HPR209 | 2021-06-01 | Overhead | 29355140 | 18486671 | 20783988
MCR026756 | HPR209 | 2021-07-01 | Labor | 34734695 | 18576541 | 23465948
MCR026757 | HPR209 | 2021-07-01 | Material | 98215498 | 52526853 | 47857359
MCR026758 | HPR209 | 2021-07-01 | Equipment | 17727566 | 9480920 | 9409187
MCR026759 | HPR209 | 2021-07-01 | Subcontract | 195277469 | 104436785 | 125389709
MCR026760 | HPR209 | 2021-07-01 | Overhead | 31393884 | 16789834 | 21293829
MCR026761 | HPR209 | 2021-08-01 | Labor | 35964779 | 17346218 | 20134607
MCR026762 | HPR209 | 2021-08-01 | Material | 101693671 | 49048003 | 61382655
MCR026763 | HPR209 | 2021-08-01 | Equipment | 18355364 | 8852999 | 9864670
MCR026764 | HPR209 | 2021-08-01 | Subcontract | 202192964 | 97519943 | 105750769
MCR026765 | HPR209 | 2021-08-01 | Overhead | 32505657 | 15677845 | 23071446
MCR026766 | HPR209 | 2021-09-01 | Labor | 36216208 | 30644358 | 34649344
MCR026767 | HPR209 | 2021-09-01 | Material | 102404610 | 86649698 | 79174395
MCR026768 | HPR209 | 2021-09-01 | Equipment | 18483686 | 15639978 | 17593816
MCR026769 | HPR209 | 2021-09-01 | Subcontract | 203606491 | 172281707 | 172005455
MCR026770 | HPR209 | 2021-09-01 | Overhead | 32732904 | 27696959 | 21148170
MCR026771 | HPR209 | 2021-10-01 | Labor | 35540400 | 20347248 | 22486040
MCR026772 | HPR209 | 2021-10-01 | Material | 100493701 | 57533686 | 62527014
MCR026773 | HPR209 | 2021-10-01 | Equipment | 18138774 | 10384636 | 9720142
MCR026774 | HPR209 | 2021-10-01 | Subcontract | 199807117 | 114391648 | 135556954
MCR026775 | HPR209 | 2021-10-01 | Overhead | 32122096 | 18390233 | 21764103
MCR026776 | HPR209 | 2021-11-01 | Labor | 33994260 | 21428797 | 23273695
MCR026777 | HPR209 | 2021-11-01 | Material | 96121850 | 60591865 | 69130077
MCR026778 | HPR209 | 2021-11-01 | Equipment | 17349669 | 10936627 | 12435737
MCR026779 | HPR209 | 2021-11-01 | Subcontract | 191114762 | 120472086 | 125342604
MCR026780 | HPR209 | 2021-11-01 | Overhead | 30724665 | 19367758 | 21936408
MCR026781 | HPR209 | 2021-12-01 | Labor | 31641616 | 26046900 | 28940152
MCR026782 | HPR209 | 2021-12-01 | Material | 89469536 | 73649970 | 73698124
MCR026783 | HPR209 | 2021-12-01 | Equipment | 16148949 | 13293571 | 15046580
MCR026784 | HPR209 | 2021-12-01 | Subcontract | 177888264 | 146434932 | 166211601
MCR026785 | HPR209 | 2021-12-01 | Overhead | 28598300 | 23541688 | 20634784
MCR026786 | HPR209 | 2022-01-01 | Labor | 28555292 | 21106193 | 24646570
MCR026787 | HPR209 | 2022-01-01 | Material | 80742676 | 59679673 | 67389168
MCR026788 | HPR209 | 2022-01-01 | Equipment | 14573780 | 10771980 | 8922295
MCR026789 | HPR209 | 2022-01-01 | Subcontract | 160537040 | 118658417 | 107450006
MCR026790 | HPR209 | 2022-01-01 | Overhead | 25808821 | 19076182 | 23387039
MCR026791 | HPR209 | 2022-02-01 | Labor | 24820257 | 34648816 | 40322802
MCR026792 | HPR209 | 2022-02-01 | Material | 70181525 | 97972668 | 114729783
MCR026793 | HPR209 | 2022-02-01 | Equipment | 12667528 | 17683736 | 19300400
MCR026794 | HPR209 | 2022-02-01 | Subcontract | 139538778 | 194794660 | 234992086
MCR026795 | HPR209 | 2022-02-01 | Overhead | 22433025 | 31316265 | 19718345
MCR026796 | HPR209 | 2022-03-01 | Labor | 20538718 | 25408384 | 27058076
MCR026797 | HPR209 | 2022-03-01 | Material | 58075086 | 71844508 | 76793913
MCR026798 | HPR209 | 2022-03-01 | Equipment | 10482357 | 12967691 | 12023828
MCR026799 | HPR209 | 2022-03-01 | Subcontract | 115468088 | 142845212 | 148120647
MCR026800 | HPR209 | 2022-03-01 | Overhead | 18563287 | 22964585 | 21603141
MCR026801 | HPR209 | 2022-04-01 | Labor | 15839129 | 16142279 | 19688352
MCR026802 | HPR209 | 2022-04-01 | Material | 44786573 | 45643757 | 48880060
MCR026803 | HPR209 | 2022-04-01 | Equipment | 8083825 | 8238544 | 8751850
MCR026804 | HPR209 | 2022-04-01 | Subcontract | 89047134 | 90751433 | 84795282
MCR026805 | HPR209 | 2022-04-01 | Overhead | 14315709 | 14589702 | 21381927
MCR026806 | HPR209 | 2022-05-01 | Labor | 10894305 | 35726972 | 40337770
MCR026807 | HPR209 | 2022-05-01 | Material | 30804636 | 101021250 | 113134453
MCR026808 | HPR209 | 2022-05-01 | Equipment | 5560133 | 18233995 | 20029087
MCR026809 | HPR209 | 2022-05-01 | Subcontract | 61247475 | 200856018 | 234075450
MCR026810 | HPR209 | 2022-05-01 | Overhead | 9846482 | 32290723 | 19362837
MCR026811 | HPR209 | 2022-06-01 | Labor | 5966583 | 21825874 | 26084313
MCR026812 | HPR209 | 2022-06-01 | Material | 16871053 | 61714637 | 51964878
MCR026813 | HPR209 | 2022-06-01 | Equipment | 3045168 | 11139284 | 9853334
MCR026814 | HPR209 | 2022-06-01 | Subcontract | 33543958 | 122704444 | 162902900
MCR026815 | HPR209 | 2022-06-01 | Overhead | 5392712 | 19726644 | 20229375
MCR026816 | HPR209 | 2022-07-01 | Labor | 1596601 | 9640266 | 10948309
MCR026817 | HPR209 | 2022-07-01 | Material | 4514535 | 27258726 | 34824549
MCR026818 | HPR209 | 2022-07-01 | Equipment | 814858 | 4920108 | 5943349
MCR026819 | HPR209 | 2022-07-01 | Subcontract | 8976047 | 54197302 | 83493264
MCR026820 | HPR209 | 2022-07-01 | Overhead | 1443039 | 8713058 | 20478908
MCR026821 | HPR209 | 2022-08-01 | Labor | 0 | 19686386 | 22443512
MCR026822 | HPR209 | 2022-08-01 | Material | 0 | 55665040 | 58449477
MCR026823 | HPR209 | 2022-08-01 | Equipment | 0 | 10047352 | 10547096
MCR026824 | HPR209 | 2022-08-01 | Subcontract | 0 | 110676301 | 173402642
MCR026825 | HPR209 | 2022-08-01 | Overhead | 0 | 17792933 | 21022789
MCR026826 | HPR209 | 2022-09-01 | Labor | 0 | 10948448 | 13410588
MCR026827 | HPR209 | 2022-09-01 | Material | 0 | 30957728 | 36317984
MCR026828 | HPR209 | 2022-09-01 | Equipment | 0 | 5587765 | 5980341
MCR026829 | HPR209 | 2022-09-01 | Subcontract | 0 | 61551861 | 80748360
MCR026830 | HPR209 | 2022-09-01 | Overhead | 0 | 9895417 | 20598114
MCR026831 | HPR209 | 2022-10-01 | Labor | 0 | 14680262 | 16866422
MCR026832 | HPR209 | 2022-10-01 | Material | 0 | 41509770 | 41278203
MCR026833 | HPR209 | 2022-10-01 | Equipment | 0 | 7492373 | 9849108
MCR026834 | HPR209 | 2022-10-01 | Subcontract | 0 | 82532014 | 150935399
MCR026835 | HPR209 | 2022-10-01 | Overhead | 0 | 13268302 | 21797536
MCR026836 | HPR209 | 2022-11-01 | Labor | 0 | 6436399 | 7450274
MCR026837 | HPR209 | 2022-11-01 | Material | 0 | 18199501 | 21741547
MCR026838 | HPR209 | 2022-11-01 | Equipment | 0 | 3284949 | 3513286
MCR026839 | HPR209 | 2022-11-01 | Subcontract | 0 | 36185252 | 76341286
MCR026840 | HPR209 | 2022-11-01 | Overhead | 0 | 5817341 | 22268892
MCR026841 | HPR209 | 2022-12-01 | Labor | 0 | 8270938 | 10004039
MCR026842 | HPR209 | 2022-12-01 | Material | 0 | 23386827 | 23515135
MCR026843 | HPR209 | 2022-12-01 | Equipment | 0 | 4221243 | 4848951
MCR026844 | HPR209 | 2022-12-01 | Subcontract | 0 | 46498979 | 126994557
MCR026845 | HPR209 | 2022-12-01 | Overhead | 0 | 7475433 | 20957763
MCR026846 | HPR209 | 2023-01-01 | Labor | 0 | 4826874 | 4941307
MCR026847 | HPR209 | 2023-01-01 | Material | 0 | 13648423 | 14377580
MCR026848 | HPR209 | 2023-01-01 | Equipment | 0 | 2463494 | 3238952
MCR026849 | HPR209 | 2023-01-01 | Subcontract | 0 | 27136547 | 84123570
MCR026850 | HPR209 | 2023-01-01 | Overhead | 0 | 4362621 | 21020119
MCR026851 | HPR209 | 2023-02-01 | Labor | 0 | 4857057 | 5578607
MCR026852 | HPR209 | 2023-02-01 | Material | 0 | 13733768 | 14476458
MCR026853 | HPR209 | 2023-02-01 | Equipment | 0 | 2478899 | 3156200
MCR026854 | HPR209 | 2023-02-01 | Subcontract | 0 | 27306235 | 78113012
MCR026855 | HPR209 | 2023-02-01 | Overhead | 0 | 4389901 | 21607041
MCR026856 | HPR209 | 2023-03-01 | Labor | 0 | 4488660 | 5189588
MCR026857 | HPR209 | 2023-03-01 | Material | 0 | 12692094 | 12522250
MCR026858 | HPR209 | 2023-03-01 | Equipment | 0 | 2290880 | 2877134
MCR026859 | HPR209 | 2023-03-01 | Subcontract | 0 | 25235121 | 88555683
MCR026860 | HPR209 | 2023-03-01 | Overhead | 0 | 4056937 | 21011709
MCR026861 | HPR209 | 2023-04-01 | Labor | 0 | 666205 | 864872
MCR026862 | HPR209 | 2023-04-01 | Material | 0 | 1883756 | 2244787
MCR026863 | HPR209 | 2023-04-01 | Equipment | 0 | 340012 | 356515
MCR026864 | HPR209 | 2023-04-01 | Subcontract | 0 | 3745387 | 74093370
MCR026865 | HPR209 | 2023-04-01 | Overhead | 0 | 602129 | 22025994
MCR026866 | HPR210 | 2020-05-01 | Labor | 3177153 | 2891860 | 3111428
MCR026867 | HPR210 | 2020-05-01 | Material | 9557252 | 8699057 | 9228848
MCR026868 | HPR210 | 2020-05-01 | Equipment | 2465608 | 2244209 | 2206753
MCR026869 | HPR210 | 2020-05-01 | Subcontract | 7904580 | 7194787 | 7489676
MCR026870 | HPR210 | 2020-05-01 | Overhead | 2053564 | 1869164 | 15123409
MCR026871 | HPR210 | 2020-06-01 | Labor | 9115413 | 8586974 | 8715391
MCR026872 | HPR210 | 2020-06-01 | Material | 27420242 | 25830635 | 25020067
MCR026873 | HPR210 | 2020-06-01 | Equipment | 7073956 | 6663865 | 7303365
MCR026874 | HPR210 | 2020-06-01 | Subcontract | 22678643 | 21363916 | 21532817
MCR026875 | HPR210 | 2020-06-01 | Overhead | 5891780 | 5550221 | 14724286
MCR026876 | HPR210 | 2020-07-01 | Labor | 14437853 | 15503165 | 15056732
MCR026877 | HPR210 | 2020-07-01 | Material | 43430773 | 46635357 | 48051802
MCR026878 | HPR210 | 2020-07-01 | Equipment | 11204401 | 12031129 | 12076660
MCR026879 | HPR210 | 2020-07-01 | Subcontract | 35920579 | 38571016 | 38373631
MCR026880 | HPR210 | 2020-07-01 | Overhead | 9331958 | 10020526 | 16247407
MCR026881 | HPR210 | 2020-08-01 | Labor | 19155805 | 10781851 | 12955832
MCR026882 | HPR210 | 2020-08-01 | Material | 57622931 | 32433085 | 33022420
MCR026883 | HPR210 | 2020-08-01 | Equipment | 14865736 | 8367184 | 8449078
MCR026884 | HPR210 | 2020-08-01 | Subcontract | 47658582 | 26824648 | 22928364
MCR026885 | HPR210 | 2020-08-01 | Overhead | 12381423 | 6968888 | 16140486
MCR026886 | HPR210 | 2020-09-01 | Labor | 23281050 | 21449351 | 25004075
MCR026887 | HPR210 | 2020-09-01 | Material | 70032155 | 64522188 | 63453770
MCR026888 | HPR210 | 2020-09-01 | Equipment | 18067105 | 16645627 | 14400091
MCR026889 | HPR210 | 2020-09-01 | Subcontract | 57921962 | 53364797 | 56530774
MCR026890 | HPR210 | 2020-09-01 | Overhead | 15047789 | 13863864 | 16378360
MCR026891 | HPR210 | 2020-10-01 | Labor | 26825860 | 18674639 | 18205841
MCR026892 | HPR210 | 2020-10-01 | Material | 80695365 | 56175527 | 64140257
MCR026893 | HPR210 | 2020-10-01 | Equipment | 20818032 | 14492330 | 17306729
MCR026894 | HPR210 | 2020-10-01 | Subcontract | 66741254 | 46461468 | 42442311
MCR026895 | HPR210 | 2020-10-01 | Overhead | 17338990 | 12070419 | 15767789
MCR026896 | HPR210 | 2020-11-01 | Labor | 29803049 | 18933386 | 19669432
MCR026897 | HPR210 | 2020-11-01 | Material | 89651102 | 56953867 | 54930789
MCR026898 | HPR210 | 2020-11-01 | Equipment | 23128459 | 14693129 | 13737897
MCR026899 | HPR210 | 2020-11-01 | Subcontract | 74148335 | 47105215 | 47807596
MCR026900 | HPR210 | 2020-11-01 | Overhead | 19263307 | 12237661 | 15586110
MCR026901 | HPR210 | 2020-12-01 | Labor | 32226026 | 26433297 | 27958212
MCR026902 | HPR210 | 2020-12-01 | Material | 96939704 | 79514487 | 75388656
MCR026903 | HPR210 | 2020-12-01 | Equipment | 25008795 | 20513385 | 22618075
MCR026904 | HPR210 | 2020-12-01 | Subcontract | 80176568 | 65764577 | 61836781
MCR026905 | HPR210 | 2020-12-01 | Overhead | 20829407 | 17085255 | 15066673
MCR026906 | HPR210 | 2021-01-01 | Labor | 34108864 | 23465802 | 22421232
MCR026907 | HPR210 | 2021-01-01 | Material | 102603502 | 70587912 | 71614414
MCR026908 | HPR210 | 2021-01-01 | Equipment | 26469958 | 18210481 | 18005466
MCR026909 | HPR210 | 2021-01-01 | Subcontract | 84860963 | 58381615 | 63636953
MCR026910 | HPR210 | 2021-01-01 | Overhead | 22046385 | 15167205 | 15074804
MCR026911 | HPR210 | 2021-02-01 | Labor | 35466373 | 24387784 | 25204515
MCR026912 | HPR210 | 2021-02-01 | Material | 106687052 | 73361343 | 84428356
MCR026913 | HPR210 | 2021-02-01 | Equipment | 27523445 | 18925979 | 19065851
MCR026914 | HPR210 | 2021-02-01 | Subcontract | 88238372 | 60675455 | 59628023
MCR026915 | HPR210 | 2021-02-01 | Overhead | 22923816 | 15763131 | 14381936
MCR026916 | HPR210 | 2021-03-01 | Labor | 36314198 | 47798903 | 53093125
MCR026917 | HPR210 | 2021-03-01 | Material | 109237410 | 143784763 | 155208991
MCR026918 | HPR210 | 2021-03-01 | Equipment | 28181394 | 37094023 | 34994534
MCR026919 | HPR210 | 2021-03-01 | Subcontract | 90347713 | 118921023 | 122836176
MCR026920 | HPR210 | 2021-03-01 | Overhead | 23471811 | 30894991 | 15669769
MCR026921 | HPR210 | 2021-04-01 | Labor | 36668923 | 38320256 | 42861543
MCR026922 | HPR210 | 2021-04-01 | Material | 110304465 | 115271870 | 105731869
MCR026923 | HPR210 | 2021-04-01 | Equipment | 28456676 | 29738182 | 32474204
MCR026924 | HPR210 | 2021-04-01 | Subcontract | 91230250 | 95338674 | 88594228
MCR026925 | HPR210 | 2021-04-01 | Overhead | 23701089 | 24768434 | 15187106
MCR026926 | HPR210 | 2021-05-01 | Labor | 36548208 | 43651201 | 42130091
MCR026927 | HPR210 | 2021-05-01 | Material | 109941340 | 131307983 | 144231544
MCR026928 | HPR210 | 2021-05-01 | Equipment | 28362996 | 33875226 | 29213765
MCR026929 | HPR210 | 2021-05-01 | Subcontract | 90929918 | 108601770 | 107155889
MCR026930 | HPR210 | 2021-05-01 | Overhead | 23623064 | 28214109 | 15368182
MCR026931 | HPR210 | 2021-06-01 | Labor | 35970952 | 39053345 | 37750496
MCR026932 | HPR210 | 2021-06-01 | Material | 108204884 | 117477089 | 146079738
MCR026933 | HPR210 | 2021-06-01 | Equipment | 27915020 | 30307091 | 35247579
MCR026934 | HPR210 | 2021-06-01 | Subcontract | 89493735 | 97162560 | 82056816
MCR026935 | HPR210 | 2021-06-01 | Overhead | 23249953 | 25242269 | 13550924
MCR026936 | HPR210 | 2021-07-01 | Labor | 34957495 | 40116626 | 45556374
MCR026937 | HPR210 | 2021-07-01 | Material | 105156286 | 120675564 | 117108569
MCR026938 | HPR210 | 2021-07-01 | Equipment | 27128533 | 31132243 | 28367616
MCR026939 | HPR210 | 2021-07-01 | Subcontract | 86972311 | 99807944 | 93469295
MCR026940 | HPR210 | 2021-07-01 | Overhead | 22594901 | 25929524 | 13943237
MCR026941 | HPR210 | 2021-08-01 | Labor | 33529881 | 10913359 | 11190348
MCR026942 | HPR210 | 2021-08-01 | Material | 100861853 | 32828677 | 48167800
MCR026943 | HPR210 | 2021-08-01 | Equipment | 26020643 | 8469240 | 9396396
MCR026944 | HPR210 | 2021-08-01 | Subcontract | 83420486 | 27151833 | 28718062
MCR026945 | HPR210 | 2021-08-01 | Overhead | 21672158 | 7053888 | 14927052
MCR026946 | HPR210 | 2021-09-01 | Labor | 31712187 | 35991856 | 38067851
MCR026947 | HPR210 | 2021-09-01 | Material | 95394014 | 108267767 | 125377809
MCR026948 | HPR210 | 2021-09-01 | Equipment | 24610033 | 27931242 | 29892296
MCR026949 | HPR210 | 2021-09-01 | Subcontract | 78898164 | 89545744 | 84728497
MCR026950 | HPR210 | 2021-09-01 | Overhead | 20497285 | 23263464 | 14738843
MCR026951 | HPR210 | 2021-10-01 | Labor | 29530966 | 24658568 | 26700160
MCR026952 | HPR210 | 2021-10-01 | Material | 88832644 | 74175895 | 92966325
MCR026953 | HPR210 | 2021-10-01 | Equipment | 22917311 | 19136119 | 16045611
MCR026954 | HPR210 | 2021-10-01 | Subcontract | 73471407 | 61349152 | 64668255
MCR026955 | HPR210 | 2021-10-01 | Overhead | 19087445 | 15938153 | 14917989
MCR026956 | HPR210 | 2021-11-01 | Labor | 27015844 | 23703249 | 25365955
MCR026957 | HPR210 | 2021-11-01 | Material | 81266860 | 71302182 | 94856428
MCR026958 | HPR210 | 2021-11-01 | Equipment | 20965468 | 18394750 | 20138808
MCR026959 | HPR210 | 2021-11-01 | Subcontract | 67213924 | 58972371 | 55971095
MCR026960 | HPR210 | 2021-11-01 | Overhead | 17461787 | 15320680 | 16499931
MCR026961 | HPR210 | 2021-12-01 | Labor | 24200357 | 33441275 | 37565591
MCR026962 | HPR210 | 2021-12-01 | Material | 72797541 | 100595317 | 123204544
MCR026963 | HPR210 | 2021-12-01 | Equipment | 18780527 | 25951881 | 23914830
MCR026964 | HPR210 | 2021-12-01 | Subcontract | 60209148 | 83200040 | 71901200
MCR026965 | HPR210 | 2021-12-01 | Overhead | 15641987 | 21614887 | 16074724
MCR026966 | HPR210 | 2022-01-01 | Labor | 21123164 | 32239849 | 33463230
MCR026967 | HPR210 | 2022-01-01 | Material | 63540980 | 96981285 | 99619866
MCR026968 | HPR210 | 2022-01-01 | Equipment | 16392492 | 25019522 | 21930871
MCR026969 | HPR210 | 2022-01-01 | Subcontract | 52553263 | 80210958 | 90255668
MCR026970 | HPR210 | 2022-01-01 | Overhead | 13653032 | 20838341 | 16236003
MCR026971 | HPR210 | 2022-02-01 | Labor | 17829915 | 20723562 | 22606948
MCR026972 | HPR210 | 2022-02-01 | Material | 53634496 | 62338930 | 92548266
MCR026973 | HPR210 | 2022-02-01 | Equipment | 13836788 | 16082384 | 17879019
MCR026974 | HPR210 | 2022-02-01 | Subcontract | 44359841 | 51559075 | 45725519
MCR026975 | HPR210 | 2022-02-01 | Overhead | 11524429 | 13394748 | 15248880
MCR026976 | HPR210 | 2022-03-01 | Labor | 14376286 | 22679632 | 21411722
MCR026977 | HPR210 | 2022-03-01 | Material | 43245572 | 68223018 | 92369429
MCR026978 | HPR210 | 2022-03-01 | Equipment | 11156622 | 17600378 | 18601369
MCR026979 | HPR210 | 2022-03-01 | Subcontract | 35767404 | 56425667 | 62491936
MCR026980 | HPR210 | 2022-03-01 | Overhead | 9292164 | 14659061 | 15350370
MCR026981 | HPR210 | 2022-04-01 | Labor | 10833408 | 14138842 | 16549667
MCR026982 | HPR210 | 2022-04-01 | Material | 32588174 | 42531312 | 47958014
MCR026983 | HPR210 | 2022-04-01 | Equipment | 8407195 | 10972355 | 10374963
MCR026984 | HPR210 | 2022-04-01 | Subcontract | 26952919 | 35176656 | 26233383
MCR026985 | HPR210 | 2022-04-01 | Overhead | 7002212 | 9138691 | 15688539
MCR026986 | HPR210 | 2022-05-01 | Labor | 7298877 | 11285937 | 12249127
MCR026987 | HPR210 | 2022-05-01 | Material | 21955888 | 33949435 | 42296503
MCR026988 | HPR210 | 2022-05-01 | Equipment | 5664246 | 8758377 | 8982653
MCR026989 | HPR210 | 2022-05-01 | Subcontract | 18159203 | 28078786 | 29316043
MCR026990 | HPR210 | 2022-05-01 | Overhead | 4717655 | 7294706 | 16015611
MCR026991 | HPR210 | 2022-06-01 | Labor | 3924543 | 12390971 | 10164718
MCR026992 | HPR210 | 2022-06-01 | Material | 11805489 | 37273509 | 50167540
MCR026993 | HPR210 | 2022-06-01 | Equipment | 3045615 | 9615931 | 9564544
MCR026994 | HPR210 | 2022-06-01 | Subcontract | 9764045 | 30828049 | 24000691
MCR026995 | HPR210 | 2022-06-01 | Overhead | 2536642 | 8008948 | 15257841
MCR026996 | HPR210 | 2022-07-01 | Labor | 1034384 | 4531396 | 6653952
MCR026997 | HPR210 | 2022-07-01 | Material | 3111549 | 13630975 | 17731069
MCR026998 | HPR210 | 2022-07-01 | Equipment | 802727 | 3516560 | 3216304
MCR026999 | HPR210 | 2022-07-01 | Subcontract | 2573489 | 11273862 | 14027885
MCR027000 | HPR210 | 2022-07-01 | Overhead | 668578 | 2928884 | 16741628
MCR027001 | HPR210 | 2022-08-01 | Labor | 0 | 2662128 | 2543975
MCR027002 | HPR210 | 2022-08-01 | Material | 0 | 8007995 | 8537856
MCR027003 | HPR210 | 2022-08-01 | Equipment | 0 | 2065927 | 1815799
MCR027004 | HPR210 | 2022-08-01 | Subcontract | 0 | 6623226 | 6451010
MCR027005 | HPR210 | 2022-08-01 | Overhead | 0 | 1720676 | 13527116
MCR027006 | HPR210 | 2022-09-01 | Labor | 0 | 1057970 | 1184008
MCR027007 | HPR210 | 2022-09-01 | Material | 0 | 3182498 | 4284591
MCR027008 | HPR210 | 2022-09-01 | Equipment | 0 | 821030 | 1052816
MCR027009 | HPR210 | 2022-09-01 | Subcontract | 0 | 2632170 | 2228487
MCR027010 | HPR210 | 2022-09-01 | Overhead | 0 | 683822 | 13999777
MCR027011 | HPR211 | 2017-05-01 | Labor | 1514002 | 1000637 | 1020085
MCR027012 | HPR211 | 2017-05-01 | Material | 4081600 | 2697618 | 2822082
MCR027013 | HPR211 | 2017-05-01 | Equipment | 1523750 | 1007080 | 1070521
MCR027014 | HPR211 | 2017-05-01 | Subcontract | 3013530 | 1991708 | 1924300
MCR027015 | HPR211 | 2017-05-01 | Overhead | 992913 | 656238 | 8495749
MCR027016 | HPR211 | 2017-06-01 | Labor | 4389754 | 2636793 | 2965523
MCR027017 | HPR211 | 2017-06-01 | Material | 11834343 | 7108535 | 6962979
MCR027018 | HPR211 | 2017-06-01 | Equipment | 4418018 | 2653771 | 3093618
MCR027019 | HPR211 | 2017-06-01 | Subcontract | 8737541 | 5248379 | 6031197
MCR027020 | HPR211 | 2017-06-01 | Overhead | 2878888 | 1729262 | 9616175
MCR027021 | HPR211 | 2017-07-01 | Labor | 7039427 | 3963997 | 4632801
MCR027022 | HPR211 | 2017-07-01 | Material | 18977599 | 10686544 | 13086104
MCR027023 | HPR211 | 2017-07-01 | Equipment | 7084751 | 3989520 | 4125208
MCR027024 | HPR211 | 2017-07-01 | Subcontract | 14011556 | 7890098 | 7165976
MCR027025 | HPR211 | 2017-07-01 | Overhead | 4616596 | 2599668 | 9058824
MCR027026 | HPR211 | 2017-08-01 | Labor | 9466155 | 4315889 | 4580171
MCR027027 | HPR211 | 2017-08-01 | Material | 25519818 | 11635211 | 11010506
MCR027028 | HPR211 | 2017-08-01 | Equipment | 9527104 | 4343678 | 4586905
MCR027029 | HPR211 | 2017-08-01 | Subcontract | 18841812 | 8590518 | 9117231
MCR027030 | HPR211 | 2017-08-01 | Overhead | 6208093 | 2830446 | 10062079
MCR027031 | HPR211 | 2017-09-01 | Labor | 11673165 | 8985484 | 11297157
MCR027032 | HPR211 | 2017-09-01 | Material | 31469701 | 24223978 | 24542295
MCR027033 | HPR211 | 2017-09-01 | Equipment | 11748325 | 9043338 | 8840827
MCR027034 | HPR211 | 2017-09-01 | Subcontract | 23234734 | 17885066 | 16793463
MCR027035 | HPR211 | 2017-09-01 | Overhead | 7655494 | 5892859 | 9836512
MCR027036 | HPR211 | 2017-10-01 | Labor | 13663785 | 18017889 | 20292965
MCR027037 | HPR211 | 2017-10-01 | Material | 36836215 | 48574451 | 51718343
MCR027038 | HPR211 | 2017-10-01 | Equipment | 13751761 | 18133901 | 18899006
MCR027039 | HPR211 | 2017-10-01 | Subcontract | 27196943 | 35863526 | 40056950
MCR027040 | HPR211 | 2017-10-01 | Overhead | 8960982 | 11816490 | 9623651
MCR027041 | HPR211 | 2017-11-01 | Labor | 15441446 | 11420184 | 12747268
MCR027042 | HPR211 | 2017-11-01 | Material | 41628616 | 30787689 | 27909792
MCR027043 | HPR211 | 2017-11-01 | Equipment | 15540869 | 11493715 | 11976842
MCR027044 | HPR211 | 2017-11-01 | Subcontract | 30735271 | 22731190 | 22978178
MCR027045 | HPR211 | 2017-11-01 | Overhead | 10126808 | 7489584 | 9077101
MCR027046 | HPR211 | 2017-12-01 | Labor | 17009697 | 21450266 | 21982546
MCR027047 | HPR211 | 2017-12-01 | Material | 45856465 | 57827800 | 53954313
MCR027048 | HPR211 | 2017-12-01 | Equipment | 17119217 | 21588377 | 25314015
MCR027049 | HPR211 | 2017-12-01 | Subcontract | 33856781 | 42695466 | 48886463
MCR027050 | HPR211 | 2017-12-01 | Overhead | 11155298 | 14067512 | 9804943
MCR027051 | HPR211 | 2018-01-01 | Labor | 18372208 | 11756937 | 16153227
MCR027052 | HPR211 | 2018-01-01 | Material | 49529659 | 31695543 | 37020978
MCR027053 | HPR211 | 2018-01-01 | Equipment | 18490501 | 11832637 | 10329734
MCR027054 | HPR211 | 2018-01-01 | Subcontract | 36568776 | 23401478 | 24157011
MCR027055 | HPR211 | 2018-01-01 | Overhead | 12048860 | 7710434 | 9923792
MCR027056 | HPR211 | 2018-02-01 | Labor | 19532782 | 13285847 | 15985912
MCR027057 | HPR211 | 2018-02-01 | Material | 52658452 | 35817332 | 38607200
MCR027058 | HPR211 | 2018-02-01 | Equipment | 19658547 | 13371390 | 15516371
MCR027059 | HPR211 | 2018-02-01 | Subcontract | 38878829 | 26444680 | 25975213
MCR027060 | HPR211 | 2018-02-01 | Overhead | 12809987 | 8713123 | 10247068
MCR027061 | HPR211 | 2018-03-01 | Labor | 20495367 | 17002182 | 18638512
MCR027062 | HPR211 | 2018-03-01 | Material | 55253487 | 45836204 | 49423635
MCR027063 | HPR211 | 2018-03-01 | Equipment | 20627330 | 17111653 | 17445344
MCR027064 | HPR211 | 2018-03-01 | Subcontract | 40794797 | 33841821 | 38233839
MCR027065 | HPR211 | 2018-03-01 | Overhead | 13441270 | 11150369 | 9141217
MCR027066 | HPR211 | 2018-04-01 | Labor | 21264069 | 20127203 | 25521539
MCR027067 | HPR211 | 2018-04-01 | Material | 57325832 | 54260953 | 51937151
MCR027068 | HPR211 | 2018-04-01 | Equipment | 21400982 | 20256796 | 18516686
MCR027069 | HPR211 | 2018-04-01 | Subcontract | 42324852 | 40061988 | 42675258
MCR027070 | HPR211 | 2018-04-01 | Overhead | 13945400 | 13199820 | 8965950
MCR027071 | HPR211 | 2018-05-01 | Labor | 21843166 | 18291659 | 20046192
MCR027072 | HPR211 | 2018-05-01 | Material | 58887018 | 49312508 | 50150510
MCR027073 | HPR211 | 2018-05-01 | Equipment | 21983807 | 18409433 | 20836980
MCR027074 | HPR211 | 2018-05-01 | Subcontract | 43477508 | 36408449 | 34410934
MCR027075 | HPR211 | 2018-05-01 | Overhead | 14325183 | 11996034 | 9371013
MCR027076 | HPR211 | 2018-06-01 | Labor | 22237122 | 16393540 | 17073305
MCR027077 | HPR211 | 2018-06-01 | Material | 59949085 | 44195367 | 48140265
MCR027078 | HPR211 | 2018-06-01 | Equipment | 22380299 | 16499093 | 14257969
MCR027079 | HPR211 | 2018-06-01 | Subcontract | 44261655 | 32630357 | 36412801
MCR027080 | HPR211 | 2018-06-01 | Overhead | 14583547 | 10751210 | 8890558
MCR027081 | HPR211 | 2018-07-01 | Labor | 22450611 | 9900654 | 12709346
MCR027082 | HPR211 | 2018-07-01 | Material | 60524632 | 26691186 | 27294166
MCR027083 | HPR211 | 2018-07-01 | Equipment | 22595164 | 9964401 | 11970519
MCR027084 | HPR211 | 2018-07-01 | Subcontract | 44686593 | 19706657 | 20760191
MCR027085 | HPR211 | 2018-07-01 | Overhead | 14723558 | 6493046 | 10137815
MCR027086 | HPR211 | 2018-08-01 | Labor | 22488538 | 11130870 | 14236319
MCR027087 | HPR211 | 2018-08-01 | Material | 60626880 | 30007726 | 31206813
MCR027088 | HPR211 | 2018-08-01 | Equipment | 22633335 | 11202538 | 10864347
MCR027089 | HPR211 | 2018-08-01 | Subcontract | 44762084 | 22155327 | 23501507
MCR027090 | HPR211 | 2018-08-01 | Overhead | 14748431 | 7299846 | 9245094
MCR027091 | HPR211 | 2018-09-01 | Labor | 22356063 | 20607491 | 47197823
MCR027092 | HPR211 | 2018-09-01 | Material | 60269739 | 55555762 | 63758834
MCR027093 | HPR211 | 2018-09-01 | Equipment | 22500006 | 20740176 | 21648963
MCR027094 | HPR211 | 2018-09-01 | Subcontract | 44498400 | 41017973 | 42663965
MCR027095 | HPR211 | 2018-09-01 | Overhead | 14661551 | 13514803 | 9040023
MCR027096 | HPR211 | 2018-10-01 | Labor | 22058632 | 15567264 | 47095470
MCR027097 | HPR211 | 2018-10-01 | Material | 59467894 | 41967807 | 90174303
MCR027098 | HPR211 | 2018-10-01 | Equipment | 22200660 | 15667496 | 16543848
MCR027099 | HPR211 | 2018-10-01 | Subcontract | 43906381 | 30985703 | 29311767
MCR027100 | HPR211 | 2018-10-01 | Overhead | 14466490 | 10209322 | 9358512
MCR027101 | HPR211 | 2018-11-01 | Labor | 21602016 | 8413605 | 9375670
MCR027102 | HPR211 | 2018-11-01 | Material | 58236904 | 22682248 | 16372385
MCR027103 | HPR211 | 2018-11-01 | Equipment | 21741105 | 8467777 | 7264256
MCR027104 | HPR211 | 2018-11-01 | Subcontract | 42997516 | 16746775 | 19473140
MCR027105 | HPR211 | 2018-11-01 | Overhead | 14167032 | 5517809 | 9748946
MCR027106 | HPR211 | 2018-12-01 | Labor | 20992356 | 20795857 | 24351561
MCR027107 | HPR211 | 2018-12-01 | Material | 56593319 | 56063577 | 59200188
MCR027108 | HPR211 | 2018-12-01 | Equipment | 21127519 | 20929755 | 27804039
MCR027109 | HPR211 | 2018-12-01 | Subcontract | 41784023 | 41392903 | 41405269
MCR027110 | HPR211 | 2018-12-01 | Overhead | 13767205 | 13638337 | 9908599
MCR027111 | HPR211 | 2019-01-01 | Labor | 20236211 | 20947337 | 25506697
MCR027112 | HPR211 | 2019-01-01 | Material | 54554827 | 56471953 | 62000898
MCR027113 | HPR211 | 2019-01-01 | Equipment | 20366505 | 21082210 | 18880728
MCR027114 | HPR211 | 2019-01-01 | Subcontract | 40278962 | 41694416 | 45473468
MCR027115 | HPR211 | 2019-01-01 | Overhead | 13271310 | 13737681 | 9700257
MCR027116 | HPR211 | 2019-02-01 | Labor | 19340631 | 13190559 | 15386721
MCR027117 | HPR211 | 2019-02-01 | Material | 52140432 | 35560445 | 37183122
MCR027118 | HPR211 | 2019-02-01 | Equipment | 19465159 | 13275489 | 15269513
MCR027119 | HPR211 | 2019-02-01 | Subcontract | 38496363 | 26255015 | 22925770
MCR027120 | HPR211 | 2019-02-01 | Overhead | 12683971 | 8650631 | 8330281
MCR027121 | HPR211 | 2019-03-01 | Labor | 18313235 | 19529552 | 24682603
MCR027122 | HPR211 | 2019-03-01 | Material | 49370674 | 52649745 | 53191762
MCR027123 | HPR211 | 2019-03-01 | Equipment | 18431148 | 19655296 | 20196955
MCR027124 | HPR211 | 2019-03-01 | Subcontract | 36451394 | 38872400 | 45252547
MCR027125 | HPR211 | 2019-03-01 | Overhead | 12010184 | 12807869 | 9535375
MCR027126 | HPR211 | 2019-04-01 | Labor | 17162319 | 23458030 | 30455616
MCR027127 | HPR211 | 2019-04-01 | Material | 46267919 | 63240534 | 63299832
MCR027128 | HPR211 | 2019-04-01 | Equipment | 17272822 | 23609069 | 22754628
MCR027129 | HPR211 | 2019-04-01 | Subcontract | 34160565 | 46691800 | 48469836
MCR027130 | HPR211 | 2019-04-01 | Overhead | 11255391 | 15384243 | 9356787
MCR027131 | HPR211 | 2019-05-01 | Labor | 15896992 | 27314541 | 33524610
MCR027132 | HPR211 | 2019-05-01 | Material | 42856721 | 73637306 | 80523830
MCR027133 | HPR211 | 2019-05-01 | Equipment | 15999347 | 27490410 | 27411430
MCR027134 | HPR211 | 2019-05-01 | Subcontract | 31642007 | 54367953 | 56476743
MCR027135 | HPR211 | 2019-05-01 | Overhead | 10425564 | 17913420 | 10485310
MCR027136 | HPR211 | 2019-06-01 | Labor | 14527354 | 17463935 | 19975593
MCR027137 | HPR211 | 2019-06-01 | Material | 39164312 | 47081044 | 47171435
MCR027138 | HPR211 | 2019-06-01 | Equipment | 14620891 | 17576379 | 21219477
MCR027139 | HPR211 | 2019-06-01 | Subcontract | 28915825 | 34760913 | 33488543
MCR027140 | HPR211 | 2019-06-01 | Overhead | 9527328 | 11453196 | 9743898
MCR027141 | HPR211 | 2019-07-01 | Labor | 13064746 | 8071264 | 9534707
MCR027142 | HPR211 | 2019-07-01 | Material | 35221265 | 21759330 | 32128147
MCR027143 | HPR211 | 2019-07-01 | Equipment | 13148865 | 8123232 | 5661455
MCR027144 | HPR211 | 2019-07-01 | Subcontract | 26004591 | 16065365 | 18144798
MCR027145 | HPR211 | 2019-07-01 | Overhead | 8568120 | 5293295 | 9777695
MCR027146 | HPR211 | 2019-08-01 | Labor | 11522093 | 8965583 | 10498787
MCR027147 | HPR211 | 2019-08-01 | Material | 31062426 | 24170326 | 21370970
MCR027148 | HPR211 | 2019-08-01 | Equipment | 11596280 | 9023309 | 9575694
MCR027149 | HPR211 | 2019-08-01 | Subcontract | 22934034 | 17845454 | 18401923
MCR027150 | HPR211 | 2019-08-01 | Overhead | 7556418 | 5879808 | 9335734
MCR027151 | HPR211 | 2019-09-01 | Labor | 9914413 | 11835295 | 15501864
MCR027152 | HPR211 | 2019-09-01 | Material | 26728280 | 31906787 | 35482357
MCR027153 | HPR211 | 2019-09-01 | Equipment | 9978249 | 11911498 | 11927670
MCR027154 | HPR211 | 2019-09-01 | Subcontract | 19734044 | 23557443 | 43228070
MCR027155 | HPR211 | 2019-09-01 | Overhead | 6502070 | 7761822 | 10184258
MCR027156 | HPR211 | 2019-10-01 | Labor | 8259593 | 10248306 | 11344185
MCR027157 | HPR211 | 2019-10-01 | Material | 22267048 | 27628421 | 27608166
MCR027158 | HPR211 | 2019-10-01 | Equipment | 8312774 | 10314291 | 11488851
MCR027159 | HPR211 | 2019-10-01 | Subcontract | 16440224 | 20398637 | 39508165
MCR027160 | HPR211 | 2019-10-01 | Overhead | 5416806 | 6721043 | 8571582
MCR027161 | HPR211 | 2019-11-01 | Labor | 6579666 | 10810991 | 12260872
MCR027162 | HPR211 | 2019-11-01 | Material | 17738129 | 29145365 | 31549330
MCR027163 | HPR211 | 2019-11-01 | Equipment | 6622030 | 10880600 | 11318207
MCR027164 | HPR211 | 2019-11-01 | Subcontract | 13096429 | 21518628 | 50395150
MCR027165 | HPR211 | 2019-11-01 | Overhead | 4315076 | 7090063 | 10008364
MCR027166 | HPR211 | 2019-12-01 | Labor | 4903102 | 10028990 | 11786113
MCR027167 | HPR211 | 2019-12-01 | Material | 13218278 | 27037166 | 32833299
MCR027168 | HPR211 | 2019-12-01 | Equipment | 4934671 | 10093563 | 9898200
MCR027169 | HPR211 | 2019-12-01 | Subcontract | 9759329 | 19962101 | 36661773
MCR027170 | HPR211 | 2019-12-01 | Overhead | 3215552 | 6577211 | 9634959
MCR027171 | HPR211 | 2020-01-01 | Labor | 3269490 | 10774194 | 11912714
MCR027172 | HPR211 | 2020-01-01 | Material | 8814222 | 29046163 | 32350542
MCR027173 | HPR211 | 2020-01-01 | Equipment | 3290541 | 10843565 | 11728644
MCR027174 | HPR211 | 2020-01-01 | Subcontract | 6507723 | 21445385 | 36089241
MCR027175 | HPR211 | 2020-01-01 | Overhead | 2144196 | 7065931 | 10357951
MCR027176 | HPR211 | 2020-02-01 | Labor | 1741419 | 8512593 | 9501542
MCR027177 | HPR211 | 2020-02-01 | Material | 4694693 | 22949109 | 22371243
MCR027178 | HPR211 | 2020-02-01 | Equipment | 1752631 | 8567402 | 8048445
MCR027179 | HPR211 | 2020-02-01 | Subcontract | 3466190 | 16943804 | 43688424
MCR027180 | HPR211 | 2020-02-01 | Overhead | 1142057 | 5582728 | 8503152
MCR027181 | HPR211 | 2020-03-01 | Labor | 455330 | 10536240 | 14580910
MCR027182 | HPR211 | 2020-03-01 | Material | 1227525 | 28404662 | 33488789
MCR027183 | HPR211 | 2020-03-01 | Equipment | 458262 | 10604079 | 11761647
MCR027184 | HPR211 | 2020-03-01 | Subcontract | 906307 | 20971752 | 35217709
MCR027185 | HPR211 | 2020-03-01 | Overhead | 298615 | 6909876 | 9847923
MCR027186 | HPR211 | 2020-04-01 | Labor | 0 | 13728194 | 15880850
MCR027187 | HPR211 | 2020-04-01 | Material | 0 | 37009855 | 44036653
MCR027188 | HPR211 | 2020-04-01 | Equipment | 0 | 13816585 | 11957767
MCR027189 | HPR211 | 2020-04-01 | Subcontract | 0 | 27325145 | 48926936
MCR027190 | HPR211 | 2020-04-01 | Overhead | 0 | 9003223 | 9587546
MCR027191 | HPR211 | 2020-05-01 | Labor | 0 | 4645110 | 3975481
MCR027192 | HPR211 | 2020-05-01 | Material | 0 | 12522757 | 10284296
MCR027193 | HPR211 | 2020-05-01 | Equipment | 0 | 4675018 | 6464301
MCR027194 | HPR211 | 2020-05-01 | Subcontract | 0 | 9245812 | 25280824
MCR027195 | HPR211 | 2020-05-01 | Overhead | 0 | 3046355 | 9327775
MCR027196 | HPR211 | 2020-06-01 | Labor | 0 | 6687102 | 8444405
MCR027197 | HPR211 | 2020-06-01 | Material | 0 | 18027767 | 21158696
MCR027198 | HPR211 | 2020-06-01 | Equipment | 0 | 6730158 | 6052561
MCR027199 | HPR211 | 2020-06-01 | Subcontract | 0 | 13310275 | 38642836
MCR027200 | HPR211 | 2020-06-01 | Overhead | 0 | 4385535 | 9598335
MCR027201 | HPR211 | 2020-07-01 | Labor | 0 | 2298438 | 2270646
MCR027202 | HPR211 | 2020-07-01 | Material | 0 | 6196363 | 6233625
MCR027203 | HPR211 | 2020-07-01 | Equipment | 0 | 2313237 | 3026503
MCR027204 | HPR211 | 2020-07-01 | Subcontract | 0 | 4574904 | 27797488
MCR027205 | HPR211 | 2020-07-01 | Overhead | 0 | 1507362 | 10179747
MCR027206 | HPR211 | 2020-08-01 | Labor | 0 | 3117249 | 3736244
MCR027207 | HPR211 | 2020-08-01 | Material | 0 | 8403795 | 8802342
MCR027208 | HPR211 | 2020-08-01 | Equipment | 0 | 3137320 | 3708096
MCR027209 | HPR211 | 2020-08-01 | Subcontract | 0 | 6204697 | 28383671
MCR027210 | HPR211 | 2020-08-01 | Overhead | 0 | 2044354 | 8983834
MCR027211 | HPR211 | 2020-09-01 | Labor | 0 | 2551067 | 2753794
MCR027212 | HPR211 | 2020-09-01 | Material | 0 | 6877424 | 8169653
MCR027213 | HPR211 | 2020-09-01 | Equipment | 0 | 2567492 | 2665691
MCR027214 | HPR211 | 2020-09-01 | Subcontract | 0 | 5077745 | 28296839
MCR027215 | HPR211 | 2020-09-01 | Overhead | 0 | 1673040 | 9833107
MCR027216 | HPR211 | 2020-10-01 | Labor | 0 | 1194525 | 1523886
MCR027217 | HPR211 | 2020-10-01 | Material | 0 | 3220320 | 3282015
MCR027218 | HPR211 | 2020-10-01 | Equipment | 0 | 1202216 | 1441945
MCR027219 | HPR211 | 2020-10-01 | Subcontract | 0 | 2377629 | 12433188
MCR027220 | HPR211 | 2020-10-01 | Overhead | 0 | 783393 | 9175038
MCR027221 | HPR211 | 2020-11-01 | Labor | 0 | 103613 | 112790
MCR027222 | HPR211 | 2020-11-01 | Material | 0 | 279332 | 343907
MCR027223 | HPR211 | 2020-11-01 | Equipment | 0 | 104281 | 68580
MCR027224 | HPR211 | 2020-11-01 | Subcontract | 0 | 206236 | 21481402
MCR027225 | HPR211 | 2020-11-01 | Overhead | 0 | 67952 | 9390837
MCR027226 | HPR212 | 2019-01-01 | Labor | 5254827 | 2281062 | 2480024
MCR027227 | HPR212 | 2019-01-01 | Material | 11599813 | 5035350 | 4453079
MCR027228 | HPR212 | 2019-01-01 | Equipment | 2340399 | 1015941 | 1078706
MCR027229 | HPR212 | 2019-01-01 | Subcontract | 14828604 | 6436932 | 6257231
MCR027230 | HPR212 | 2019-01-01 | Overhead | 3397632 | 1474874 | 17070480
MCR027231 | HPR212 | 2019-02-01 | Labor | 14658761 | 12512389 | 13411697
MCR027232 | HPR212 | 2019-02-01 | Material | 32358607 | 27620580 | 27105543
MCR027233 | HPR212 | 2019-02-01 | Equipment | 6528731 | 5572778 | 6148170
MCR027234 | HPR212 | 2019-02-01 | Subcontract | 41365576 | 35308726 | 37087968
MCR027235 | HPR212 | 2019-02-01 | Overhead | 9477965 | 8090178 | 16810942
MCR027236 | HPR212 | 2019-03-01 | Labor | 22440154 | 23442789 | 28350522
MCR027237 | HPR212 | 2019-03-01 | Material | 49535711 | 51748986 | 52835498
MCR027238 | HPR212 | 2019-03-01 | Equipment | 9994414 | 10440968 | 12331061
MCR027239 | HPR212 | 2019-03-01 | Subcontract | 63323900 | 66153237 | 68375702
MCR027240 | HPR212 | 2019-03-01 | Overhead | 14509207 | 15157484 | 16014529
MCR027241 | HPR212 | 2019-04-01 | Labor | 28649527 | 18310233 | 16575498
MCR027242 | HPR212 | 2019-04-01 | Material | 63242645 | 40419080 | 38497178
MCR027243 | HPR212 | 2019-04-01 | Equipment | 12759949 | 8155026 | 8295502
MCR027244 | HPR212 | 2019-04-01 | Subcontract | 80846138 | 51669669 | 54721530
MCR027245 | HPR212 | 2019-04-01 | Overhead | 18524023 | 11838910 | 16197223
MCR027246 | HPR212 | 2019-05-01 | Labor | 33340887 | 32362742 | 34841037
MCR027247 | HPR212 | 2019-05-01 | Material | 73598627 | 71439414 | 80153066
MCR027248 | HPR212 | 2019-05-01 | Equipment | 14849391 | 14413744 | 14977948
MCR027249 | HPR212 | 2019-05-01 | Subcontract | 94084691 | 91324465 | 106266558
MCR027250 | HPR212 | 2019-05-01 | Overhead | 21557331 | 20924889 | 16789114
MCR027251 | HPR212 | 2019-06-01 | Labor | 36572314 | 18652617 | 19356379
MCR027252 | HPR212 | 2019-06-01 | Material | 80731868 | 41174880 | 38157195
MCR027253 | HPR212 | 2019-06-01 | Equipment | 16288606 | 8307518 | 8572605
MCR027254 | HPR212 | 2019-06-01 | Subcontract | 103203460 | 52635845 | 51096950
MCR027255 | HPR212 | 2019-06-01 | Overhead | 23646686 | 12060286 | 15701121
MCR027256 | HPR212 | 2019-07-01 | Labor | 38406722 | 19876602 | 24592841
MCR027257 | HPR212 | 2019-07-01 | Material | 84781249 | 43876777 | 43427091
MCR027258 | HPR212 | 2019-07-01 | Equipment | 17105617 | 8852657 | 9098590
MCR027259 | HPR212 | 2019-07-01 | Subcontract | 108379980 | 56089810 | 53731984
MCR027260 | HPR212 | 2019-07-01 | Overhead | 24832765 | 12851683 | 15518744
MCR027261 | HPR212 | 2019-08-01 | Labor | 38912849 | 10651348 | 10904078
MCR027262 | HPR212 | 2019-08-01 | Material | 85898504 | 23512411 | 25382039
MCR027263 | HPR212 | 2019-08-01 | Equipment | 17331036 | 4743906 | 5575725
MCR027264 | HPR212 | 2019-08-01 | Subcontract | 109808220 | 30057054 | 35564392
MCR027265 | HPR212 | 2019-08-01 | Overhead | 25160014 | 6886879 | 13956014
MCR027266 | HPR212 | 2019-09-01 | Labor | 38166584 | 29642012 | 34825384
MCR027267 | HPR212 | 2019-09-01 | Material | 84251153 | 65433515 | 66204113
MCR027268 | HPR212 | 2019-09-01 | Equipment | 16998664 | 13201983 | 15420036
MCR027269 | HPR212 | 2019-09-01 | Subcontract | 107702332 | 83646833 | 88242524
MCR027270 | HPR212 | 2019-09-01 | Overhead | 24677498 | 19165737 | 16357215
MCR027271 | HPR212 | 2019-10-01 | Labor | 36252812 | 30784180 | 34209679
MCR027272 | HPR212 | 2019-10-01 | Material | 80026582 | 67954803 | 65028278
MCR027273 | HPR212 | 2019-10-01 | Equipment | 16146307 | 13710683 | 11955609
MCR027274 | HPR212 | 2019-10-01 | Subcontract | 102301858 | 86869919 | 93491722
MCR027275 | HPR212 | 2019-10-01 | Overhead | 23440104 | 19904232 | 14996391
MCR027276 | HPR212 | 2019-11-01 | Labor | 33268079 | 29052878 | 35242545
MCR027277 | HPR212 | 2019-11-01 | Material | 73437908 | 64133024 | 63705699
MCR027278 | HPR212 | 2019-11-01 | Equipment | 14816964 | 12939594 | 14375186
MCR027279 | HPR212 | 2019-11-01 | Subcontract | 93879236 | 81984353 | 71848758
MCR027280 | HPR212 | 2019-11-01 | Overhead | 21510255 | 18784818 | 15078042
MCR027281 | HPR212 | 2019-12-01 | Labor | 29324613 | 33633374 | 34204343
MCR027282 | HPR212 | 2019-12-01 | Material | 64732868 | 74244280 | 76425919
MCR027283 | HPR212 | 2019-12-01 | Equipment | 13060619 | 14979659 | 14676387
MCR027284 | HPR212 | 2019-12-01 | Subcontract | 82751163 | 94910062 | 117431133
MCR027285 | HPR212 | 2019-12-01 | Overhead | 18960515 | 21746445 | 14966835
MCR027286 | HPR212 | 2020-01-01 | Labor | 24556820 | 14426161 | 17407691
MCR027287 | HPR212 | 2020-01-01 | Material | 54208163 | 31845153 | 35006194
MCR027288 | HPR212 | 2020-01-01 | Equipment | 10937136 | 6425135 | 7174585
MCR027289 | HPR212 | 2020-01-01 | Subcontract | 69296922 | 40709203 | 35573472
MCR027290 | HPR212 | 2020-01-01 | Overhead | 15877787 | 9327572 | 15347136
MCR027291 | HPR212 | 2020-02-01 | Labor | 19132736 | 30732346 | 34809159
MCR027292 | HPR212 | 2020-02-01 | Material | 42234722 | 67840380 | 63306466
MCR027293 | HPR212 | 2020-02-01 | Equipment | 8521353 | 13687597 | 14835373
MCR027294 | HPR212 | 2020-02-01 | Subcontract | 53990693 | 86723646 | 91286458
MCR027295 | HPR212 | 2020-02-01 | Overhead | 12370718 | 19870718 | 16332702
MCR027296 | HPR212 | 2020-03-01 | Labor | 13276959 | 19087729 | 22528405
MCR027297 | HPR212 | 2020-03-01 | Material | 29308338 | 42135372 | 51888043
MCR027298 | HPR212 | 2020-03-01 | Equipment | 5913303 | 8501308 | 8438070
MCR027299 | HPR212 | 2020-03-01 | Subcontract | 37466269 | 53863688 | 53423432
MCR027300 | HPR212 | 2020-03-01 | Overhead | 8584529 | 12341618 | 16741974
MCR027301 | HPR212 | 2020-04-01 | Labor | 7327596 | 19216807 | 20206434
MCR027302 | HPR212 | 2020-04-01 | Material | 16175364 | 42420306 | 39953178
MCR027303 | HPR212 | 2020-04-01 | Equipment | 3263570 | 8558797 | 8895150
MCR027304 | HPR212 | 2020-04-01 | Subcontract | 20677752 | 54227934 | 74136651
MCR027305 | HPR212 | 2020-04-01 | Overhead | 4737828 | 12425077 | 15558817
MCR027306 | HPR212 | 2020-05-01 | Labor | 1972941 | 25574041 | 32634716
MCR027307 | HPR212 | 2020-05-01 | Material | 4355185 | 56453637 | 61105158
MCR027308 | HPR212 | 2020-05-01 | Equipment | 878710 | 11390187 | 11944527
MCR027309 | HPR212 | 2020-05-01 | Subcontract | 5567444 | 72167420 | 108061941
MCR027310 | HPR212 | 2020-05-01 | Overhead | 1275651 | 16535495 | 17957651
MCR027311 | HPR212 | 2020-06-01 | Labor | 0 | 23479701 | 30055893
MCR027312 | HPR212 | 2020-06-01 | Material | 0 | 51830467 | 55903980
MCR027313 | HPR212 | 2020-06-01 | Equipment | 0 | 10457408 | 9639451
MCR027314 | HPR212 | 2020-06-01 | Subcontract | 0 | 66257398 | 93165133
MCR027315 | HPR212 | 2020-06-01 | Overhead | 0 | 15181350 | 15755431
MCR027316 | HPR212 | 2020-07-01 | Labor | 0 | 10120287 | 10409688
MCR027317 | HPR212 | 2020-07-01 | Material | 0 | 22340114 | 21289355
MCR027318 | HPR212 | 2020-07-01 | Equipment | 0 | 4507381 | 5856167
MCR027319 | HPR212 | 2020-07-01 | Subcontract | 0 | 28558450 | 44626774
MCR027320 | HPR212 | 2020-07-01 | Overhead | 0 | 6543508 | 16777794
MCR027321 | HPR212 | 2020-08-01 | Labor | 0 | 7406717 | 8856831
MCR027322 | HPR212 | 2020-08-01 | Material | 0 | 16350022 | 16710198
MCR027323 | HPR212 | 2020-08-01 | Equipment | 0 | 3298810 | 3510859
MCR027324 | HPR212 | 2020-08-01 | Subcontract | 0 | 20901025 | 45503604
MCR027325 | HPR212 | 2020-08-01 | Overhead | 0 | 4788986 | 16996242
MCR027326 | HPR212 | 2020-09-01 | Labor | 0 | 6786479 | 6454961
MCR027327 | HPR212 | 2020-09-01 | Material | 0 | 14980872 | 16623308
MCR027328 | HPR212 | 2020-09-01 | Equipment | 0 | 3022568 | 3960906
MCR027329 | HPR212 | 2020-09-01 | Subcontract | 0 | 19150775 | 58594841
MCR027330 | HPR212 | 2020-09-01 | Overhead | 0 | 4387957 | 15412138
MCR027331 | HPR212 | 2020-10-01 | Labor | 0 | 2768681 | 3962792
MCR027332 | HPR212 | 2020-10-01 | Material | 0 | 6111750 | 6635841
MCR027333 | HPR212 | 2020-10-01 | Equipment | 0 | 1233118 | 1273732
MCR027334 | HPR212 | 2020-10-01 | Subcontract | 0 | 7812946 | 24040329
MCR027335 | HPR212 | 2020-10-01 | Overhead | 0 | 1790156 | 16240052
MCR027336 | HPR212 | 2020-11-01 | Labor | 0 | 714004 | 820294
MCR027337 | HPR212 | 2020-11-01 | Material | 0 | 1576134 | 1360801
MCR027338 | HPR212 | 2020-11-01 | Equipment | 0 | 318004 | 415238
MCR027339 | HPR212 | 2020-11-01 | Subcontract | 0 | 2014848 | 25483257
MCR027340 | HPR212 | 2020-11-01 | Overhead | 0 | 461656 | 15428958
MCR027341 | HPR213 | 2021-01-01 | Labor | 5826205 | 4754845 | 4415028
MCR027342 | HPR213 | 2021-01-01 | Material | 11308930 | 9229371 | 10441472
MCR027343 | HPR213 | 2021-01-01 | Equipment | 1892089 | 1544160 | 1452269
MCR027344 | HPR213 | 2021-01-01 | Subcontract | 10170397 | 8300199 | 8139287
MCR027345 | HPR213 | 2021-01-01 | Overhead | 2640847 | 2155231 | 11517775
MCR027346 | HPR213 | 2021-02-01 | Labor | 16083333 | 12335151 | 10491513
MCR027347 | HPR213 | 2021-02-01 | Material | 31218485 | 23943093 | 25012312
MCR027348 | HPR213 | 2021-02-01 | Equipment | 5223143 | 4005902 | 4901834
MCR027349 | HPR213 | 2021-02-01 | Subcontract | 28075547 | 21532609 | 18616395
MCR027350 | HPR213 | 2021-02-01 | Overhead | 7290102 | 5591162 | 11985400
MCR027351 | HPR213 | 2021-03-01 | Labor | 24299747 | 33138536 | 33274669
MCR027352 | HPR213 | 2021-03-01 | Material | 47166920 | 64323415 | 68570353
MCR027353 | HPR213 | 2021-03-01 | Equipment | 7891464 | 10761905 | 9541405
MCR027354 | HPR213 | 2021-03-01 | Subcontract | 42418364 | 57847620 | 61746312
MCR027355 | HPR213 | 2021-03-01 | Overhead | 11014361 | 15020725 | 11229645
MCR027356 | HPR213 | 2021-04-01 | Labor | 30549199 | 18124246 | 16842172
MCR027357 | HPR213 | 2021-04-01 | Material | 59297393 | 35179991 | 37849687
MCR027358 | HPR213 | 2021-04-01 | Equipment | 9921005 | 5885939 | 7331328
MCR027359 | HPR213 | 2021-04-01 | Subcontract | 53327595 | 31638226 | 25662245
MCR027360 | HPR213 | 2021-04-01 | Overhead | 13847054 | 8215188 | 10985747
MCR027361 | HPR213 | 2021-05-01 | Labor | 34911414 | 31027800 | 27161661
MCR027362 | HPR213 | 2021-05-01 | Material | 67764653 | 60226381 | 65164944
MCR027363 | HPR213 | 2021-05-01 | Equipment | 11337656 | 10076433 | 10615028
MCR027364 | HPR213 | 2021-05-01 | Subcontract | 60942409 | 54163056 | 53359340
MCR027365 | HPR213 | 2021-05-01 | Overhead | 15824319 | 14063990 | 9711771
MCR027366 | HPR213 | 2021-06-01 | Labor | 37473298 | 17470538 | 20005477
MCR027367 | HPR213 | 2021-06-01 | Material | 72737387 | 33911114 | 36225650
MCR027368 | HPR213 | 2021-06-01 | Equipment | 12169641 | 5673644 | 5986513
MCR027369 | HPR213 | 2021-06-01 | Subcontract | 65414510 | 30497094 | 27009414
MCR027370 | HPR213 | 2021-06-01 | Overhead | 16985545 | 7918882 | 11056148
MCR027371 | HPR213 | 2021-07-01 | Labor | 38330547 | 19740161 | 20326728
MCR027372 | HPR213 | 2021-07-01 | Material | 74401347 | 38316556 | 40286672
MCR027373 | HPR213 | 2021-07-01 | Equipment | 12448037 | 6410716 | 6758003
MCR027374 | HPR213 | 2021-07-01 | Subcontract | 66910950 | 34459015 | 39599901
MCR027375 | HPR213 | 2021-07-01 | Overhead | 17374111 | 8947635 | 10863236
MCR027376 | HPR213 | 2021-08-01 | Labor | 37589884 | 12118317 | 11858561
MCR027377 | HPR213 | 2021-08-01 | Material | 72963686 | 23522208 | 28410498
MCR027378 | HPR213 | 2021-08-01 | Equipment | 12207503 | 3935484 | 4084141
MCR027379 | HPR213 | 2021-08-01 | Subcontract | 65618027 | 21154097 | 15904065
MCR027380 | HPR213 | 2021-08-01 | Overhead | 17038390 | 5492877 | 10893986
MCR027381 | HPR213 | 2021-09-01 | Labor | 35372268 | 24808934 | 24259713
MCR027382 | HPR213 | 2021-09-01 | Material | 68659191 | 48155276 | 62948964
MCR027383 | HPR213 | 2021-09-01 | Equipment | 11487321 | 8056825 | 7814580
MCR027384 | HPR213 | 2021-09-01 | Subcontract | 61746889 | 43307217 | 42945539
MCR027385 | HPR213 | 2021-09-01 | Overhead | 16033210 | 11245161 | 11893263
MCR027386 | HPR213 | 2021-10-01 | Labor | 31817732 | 24217287 | 27192942
MCR027387 | HPR213 | 2021-10-01 | Material | 61759674 | 47006862 | 49932466
MCR027388 | HPR213 | 2021-10-01 | Equipment | 10332967 | 7864685 | 8173642
MCR027389 | HPR213 | 2021-10-01 | Subcontract | 55541985 | 42274421 | 41525024
MCR027390 | HPR213 | 2021-10-01 | Overhead | 14422043 | 10976985 | 12286135
MCR027391 | HPR213 | 2021-11-01 | Labor | 27093174 | 35072872 | 35138834
MCR027392 | HPR213 | 2021-11-01 | Material | 52589091 | 68078049 | 87535333
MCR027393 | HPR213 | 2021-11-01 | Equipment | 8798644 | 11390090 | 11805393
MCR027394 | HPR213 | 2021-11-01 | Subcontract | 47294655 | 61224254 | 55595044
MCR027395 | HPR213 | 2021-11-01 | Overhead | 12280540 | 15897502 | 10794277
MCR027396 | HPR213 | 2021-12-01 | Labor | 21406014 | 49684486 | 54708656
MCR027397 | HPR213 | 2021-12-01 | Material | 41550053 | 96439862 | 101407530
MCR027398 | HPR213 | 2021-12-01 | Equipment | 6951710 | 16135285 | 16383230
MCR027399 | HPR213 | 2021-12-01 | Subcontract | 37366979 | 86730726 | 83863765
MCR027400 | HPR213 | 2021-12-01 | Overhead | 9702717 | 22520518 | 11578231
MCR027401 | HPR213 | 2022-01-01 | Labor | 15031453 | 24771673 | 19261003
MCR027402 | HPR213 | 2022-01-01 | Material | 29176739 | 48082951 | 62745878
MCR027403 | HPR213 | 2022-01-01 | Equipment | 4881540 | 8044724 | 7642583
MCR027404 | HPR213 | 2022-01-01 | Subcontract | 26239355 | 43242173 | 44635751
MCR027405 | HPR213 | 2022-01-01 | Overhead | 6813316 | 11228272 | 10990468
MCR027406 | HPR213 | 2022-02-01 | Labor | 8379790 | 12856629 | 31932897
MCR027407 | HPR213 | 2022-02-01 | Material | 16265555 | 24955305 | 40053911
MCR027408 | HPR213 | 2022-02-01 | Equipment | 2721379 | 4175254 | 4688462
MCR027409 | HPR213 | 2022-02-01 | Subcontract | 14628012 | 22442916 | 18051505
MCR027410 | HPR213 | 2022-02-01 | Overhead | 3798313 | 5827532 | 11500764
MCR027411 | HPR213 | 2022-03-01 | Labor | 2274268 | 14845950 | 37779990
MCR027412 | HPR213 | 2022-03-01 | Material | 4414459 | 28816669 | 55972933
MCR027413 | HPR213 | 2022-03-01 | Equipment | 738580 | 4821297 | 4937277
MCR027414 | HPR213 | 2022-03-01 | Subcontract | 3970031 | 25915535 | 29141888
MCR027415 | HPR213 | 2022-03-01 | Overhead | 1030859 | 6729233 | 10636004
MCR027416 | HPR213 | 2022-04-01 | Labor | 0 | 13021883 | 8626760
MCR027417 | HPR213 | 2022-04-01 | Material | 0 | 25276070 | 32339041
MCR027418 | HPR213 | 2022-04-01 | Equipment | 0 | 4228921 | 4708357
MCR027419 | HPR213 | 2022-04-01 | Subcontract | 0 | 22731388 | 19051163
MCR027420 | HPR213 | 2022-04-01 | Overhead | 0 | 5902437 | 12652115
MCR027421 | HPR213 | 2022-05-01 | Labor | 0 | 10474580 | 8700853
MCR027422 | HPR213 | 2022-05-01 | Material | 0 | 20331640 | 22458564
MCR027423 | HPR213 | 2022-05-01 | Equipment | 0 | 3401672 | 3298242
MCR027424 | HPR213 | 2022-05-01 | Subcontract | 0 | 18284741 | 20522697
MCR027425 | HPR213 | 2022-05-01 | Overhead | 0 | 4747820 | 10888843
MCR027426 | HPR213 | 2022-06-01 | Labor | 0 | 6850986 | 7124892
MCR027427 | HPR213 | 2022-06-01 | Material | 0 | 13298077 | 17507864
MCR027428 | HPR213 | 2022-06-01 | Equipment | 0 | 2224892 | 2808252
MCR027429 | HPR213 | 2022-06-01 | Subcontract | 0 | 11959285 | 10674730
MCR027430 | HPR213 | 2022-06-01 | Overhead | 0 | 3105350 | 10755246
MCR027431 | HPR213 | 2022-07-01 | Labor | 0 | 1123453 | 1212435
MCR027432 | HPR213 | 2022-07-01 | Material | 0 | 2180674 | 2549836
MCR027433 | HPR213 | 2022-07-01 | Equipment | 0 | 364847 | 337939
MCR027434 | HPR213 | 2022-07-01 | Subcontract | 0 | 1961133 | 1406552
MCR027435 | HPR213 | 2022-07-01 | Overhead | 0 | 509228 | 11514735
MCR027436 | HPR214 | 2017-03-01 | Labor | 13859758 | 5717537 | 5604323
MCR027437 | HPR214 | 2017-03-01 | Material | 35260299 | 14545857 | 13924156
MCR027438 | HPR214 | 2017-03-01 | Equipment | 6344161 | 2617143 | 2516080
MCR027439 | HPR214 | 2017-03-01 | Subcontract | 40687870 | 16784882 | 18101523
MCR027440 | HPR214 | 2017-03-01 | Overhead | 8270077 | 3411638 | 25328888
MCR027441 | HPR214 | 2017-04-01 | Labor | 36993534 | 49253292 | 47723520
MCR027442 | HPR214 | 2017-04-01 | Material | 94114418 | 125304195 | 118379148
MCR027443 | HPR214 | 2017-04-01 | Equipment | 16933408 | 22545186 | 22358214
MCR027444 | HPR214 | 2017-04-01 | Subcontract | 108601323 | 144592101 | 140610294
MCR027445 | HPR214 | 2017-04-01 | Overhead | 22073933 | 29389295 | 27271308
MCR027446 | HPR214 | 2017-05-01 | Labor | 53492438 | 28219680 | 26920785
MCR027447 | HPR214 | 2017-05-01 | Material | 136088910 | 71793054 | 77421927
MCR027448 | HPR214 | 2017-05-01 | Equipment | 24485611 | 12917267 | 13215510
MCR027449 | HPR214 | 2017-05-01 | Subcontract | 157036893 | 82844062 | 102088846
MCR027450 | HPR214 | 2017-05-01 | Overhead | 31918781 | 16838600 | 26106126
MCR027451 | HPR214 | 2017-06-01 | Labor | 63709905 | 61235133 | 68582373
MCR027452 | HPR214 | 2017-06-01 | Material | 162082940 | 155786926 | 156124201
MCR027453 | HPR214 | 2017-06-01 | Equipment | 29162551 | 28029750 | 28992168
MCR027454 | HPR214 | 2017-06-01 | Subcontract | 187032148 | 179766997 | 155245935
MCR027455 | HPR214 | 2017-06-01 | Overhead | 38015514 | 36538824 | 25530607
MCR027456 | HPR214 | 2017-07-01 | Labor | 68043308 | 44512021 | 45540540
MCR027457 | HPR214 | 2017-07-01 | Material | 173107453 | 113242032 | 105167233
MCR027458 | HPR214 | 2017-07-01 | Equipment | 31146122 | 20374918 | 23519979
MCR027459 | HPR214 | 2017-07-01 | Subcontract | 199753649 | 130673225 | 167244917
MCR027460 | HPR214 | 2017-07-01 | Overhead | 40601243 | 26560192 | 25740814
MCR027461 | HPR214 | 2017-08-01 | Labor | 66948318 | 42809688 | 42609167
MCR027462 | HPR214 | 2017-08-01 | Material | 170321714 | 108911165 | 127595766
MCR027463 | HPR214 | 2017-08-01 | Equipment | 30644901 | 19595692 | 22441663
MCR027464 | HPR214 | 2017-08-01 | Subcontract | 196539105 | 125675714 | 124951751
MCR027465 | HPR214 | 2017-08-01 | Overhead | 39947866 | 25544415 | 25763526
MCR027466 | HPR214 | 2017-09-01 | Labor | 60961778 | 70254331 | 70868266
MCR027467 | HPR214 | 2017-09-01 | Material | 155091490 | 178732466 | 167874527
MCR027468 | HPR214 | 2017-09-01 | Equipment | 27904624 | 32158194 | 32488968
MCR027469 | HPR214 | 2017-09-01 | Subcontract | 178964513 | 206244513 | 203701850
MCR027470 | HPR214 | 2017-09-01 | Overhead | 36375714 | 41920554 | 28192465
MCR027471 | HPR214 | 2017-10-01 | Labor | 50741396 | 40640318 | 41859795
MCR027472 | HPR214 | 2017-10-01 | Material | 129090047 | 103392120 | 108653636
MCR027473 | HPR214 | 2017-10-01 | Equipment | 23226350 | 18602686 | 19084967
MCR027474 | HPR214 | 2017-10-01 | Subcontract | 148960704 | 119307129 | 120446552
MCR027475 | HPR214 | 2017-10-01 | Overhead | 30277243 | 24249959 | 27161856
MCR027476 | HPR214 | 2017-11-01 | Labor | 37143980 | 28166651 | 30974020
MCR027477 | HPR214 | 2017-11-01 | Material | 94497165 | 71658144 | 65096216
MCR027478 | HPR214 | 2017-11-01 | Equipment | 17002273 | 12892993 | 12259125
MCR027479 | HPR214 | 2017-11-01 | Subcontract | 109042986 | 82688385 | 92482403
MCR027480 | HPR214 | 2017-11-01 | Overhead | 22163704 | 16806958 | 24131555
MCR027481 | HPR214 | 2017-12-01 | Labor | 21415856 | 36155444 | 37894220
MCR027482 | HPR214 | 2017-12-01 | Material | 54483598 | 91982253 | 86221245
MCR027483 | HPR214 | 2017-12-01 | Equipment | 9802887 | 16549781 | 15081738
MCR027484 | HPR214 | 2017-12-01 | Subcontract | 62870185 | 106140957 | 112875369
MCR027485 | HPR214 | 2017-12-01 | Overhead | 12778779 | 21573847 | 24465914
MCR027486 | HPR214 | 2018-01-01 | Labor | 5963020 | 31114275 | 32293103
MCR027487 | HPR214 | 2018-01-01 | Material | 15170386 | 79157128 | 98640236
MCR027488 | HPR214 | 2018-01-01 | Equipment | 2729511 | 14242238 | 15019738
MCR027489 | HPR214 | 2018-01-01 | Subcontract | 17505543 | 91341678 | 104557041
MCR027490 | HPR214 | 2018-01-01 | Overhead | 3558117 | 18565797 | 25668520
MCR027491 | HPR214 | 2018-02-01 | Labor | 0 | 30758634 | 36303267
MCR027492 | HPR214 | 2018-02-01 | Material | 0 | 78252350 | 75451964
MCR027493 | HPR214 | 2018-02-01 | Equipment | 0 | 14079447 | 14758254
MCR027494 | HPR214 | 2018-02-01 | Subcontract | 0 | 90297629 | 78324119
MCR027495 | HPR214 | 2018-02-01 | Overhead | 0 | 18353587 | 25361471
MCR027496 | HPR214 | 2018-03-01 | Labor | 0 | 6859714 | 4259213
MCR027497 | HPR214 | 2018-03-01 | Material | 0 | 17451645 | 19837407
MCR027498 | HPR214 | 2018-03-01 | Equipment | 0 | 3139963 | 3880742
MCR027499 | HPR214 | 2018-03-01 | Subcontract | 0 | 20137954 | 29898001
MCR027500 | HPR214 | 2018-03-01 | Overhead | 0 | 4093172 | 24364296
MCR027501 | HPR214 | 2018-04-01 | Labor | 0 | 3576575 | 5268525
MCR027502 | HPR214 | 2018-04-01 | Material | 0 | 9099084 | 10988774
MCR027503 | HPR214 | 2018-04-01 | Equipment | 0 | 1637140 | 1445773
MCR027504 | HPR214 | 2018-04-01 | Subcontract | 0 | 10499694 | 7843023
MCR027505 | HPR214 | 2018-04-01 | Overhead | 0 | 2134132 | 24007214
MCR027506 | HPR215 | 2021-03-01 | Labor | 4248611 | 1487450 | 1606143
MCR027507 | HPR215 | 2021-03-01 | Material | 13091246 | 4583281 | 4904417
MCR027508 | HPR215 | 2021-03-01 | Equipment | 3146445 | 1101579 | 1025534
MCR027509 | HPR215 | 2021-03-01 | Subcontract | 14665459 | 5134417 | 5615671
MCR027510 | HPR215 | 2021-03-01 | Overhead | 3021751 | 1057923 | 13877977
MCR027511 | HPR215 | 2021-04-01 | Labor | 11794088 | 6094036 | 7061774
MCR027512 | HPR215 | 2021-04-01 | Material | 36341125 | 18777553 | 21222251
MCR027513 | HPR215 | 2021-04-01 | Equipment | 8734488 | 4513133 | 5405369
MCR027514 | HPR215 | 2021-04-01 | Subcontract | 40711117 | 21035539 | 17071879
MCR027515 | HPR215 | 2021-04-01 | Overhead | 8388341 | 4334278 | 12250404
MCR027516 | HPR215 | 2021-05-01 | Labor | 17945105 | 9447705 | 8502614
MCR027517 | HPR215 | 2021-05-01 | Material | 55294253 | 29111215 | 30011439
MCR027518 | HPR215 | 2021-05-01 | Equipment | 13289820 | 6996800 | 7221916
MCR027519 | HPR215 | 2021-05-01 | Subcontract | 61943344 | 32611816 | 37185762
MCR027520 | HPR215 | 2021-05-01 | Overhead | 12763145 | 6719517 | 14285415
MCR027521 | HPR215 | 2021-06-01 | Labor | 22748309 | 28885796 | 29004359
MCR027522 | HPR215 | 2021-06-01 | Material | 70094367 | 89005804 | 104391683
MCR027523 | HPR215 | 2021-06-01 | Equipment | 16846987 | 21392298 | 21766123
MCR027524 | HPR215 | 2021-06-01 | Subcontract | 78523161 | 99708684 | 97107855
MCR027525 | HPR215 | 2021-06-01 | Overhead | 16179341 | 20544522 | 13822458
MCR027526 | HPR215 | 2021-07-01 | Labor | 26253826 | 12746550 | 14695463
MCR027527 | HPR215 | 2021-07-01 | Material | 80895914 | 39275945 | 32966045
MCR027528 | HPR215 | 2021-07-01 | Equipment | 19443108 | 9439864 | 11109000
MCR027529 | HPR215 | 2021-07-01 | Subcontract | 90623586 | 43998847 | 43495853
MCR027530 | HPR215 | 2021-07-01 | Overhead | 18672579 | 9065763 | 14054668
MCR027531 | HPR215 | 2021-08-01 | Labor | 28515893 | 8544811 | 8548512
MCR027532 | HPR215 | 2021-08-01 | Material | 87866022 | 26329128 | 29459644
MCR027533 | HPR215 | 2021-08-01 | Equipment | 21118354 | 6328133 | 6393689
MCR027534 | HPR215 | 2021-08-01 | Subcontract | 98431844 | 29495185 | 21523864
MCR027535 | HPR215 | 2021-08-01 | Overhead | 20281435 | 6077349 | 13174189
MCR027536 | HPR215 | 2021-09-01 | Labor | 29593704 | 12349585 | 13617669
MCR027537 | HPR215 | 2021-09-01 | Material | 91187080 | 38052776 | 44323887
MCR027538 | HPR215 | 2021-09-01 | Equipment | 21916562 | 9145879 | 9638722
MCR027539 | HPR215 | 2021-09-01 | Subcontract | 102152257 | 42628593 | 44842708
MCR027540 | HPR215 | 2021-09-01 | Overhead | 21048009 | 8783428 | 13671496
MCR027541 | HPR215 | 2021-10-01 | Labor | 29552526 | 14052481 | 14712613
MCR027542 | HPR215 | 2021-10-01 | Material | 91060200 | 43299911 | 42718589
MCR027543 | HPR215 | 2021-10-01 | Equipment | 21886066 | 10407013 | 11955095
MCR027544 | HPR215 | 2021-10-01 | Subcontract | 102010119 | 48506692 | 52594794
MCR027545 | HPR215 | 2021-10-01 | Overhead | 21018723 | 9994584 | 12691550
MCR027546 | HPR215 | 2021-11-01 | Labor | 28465261 | 13925160 | 15168619
MCR027547 | HPR215 | 2021-11-01 | Material | 87710009 | 42907596 | 47991392
MCR027548 | HPR215 | 2021-11-01 | Equipment | 21080857 | 10312722 | 10076550
MCR027549 | HPR215 | 2021-11-01 | Subcontract | 98257070 | 48067201 | 40816939
MCR027550 | HPR215 | 2021-11-01 | Overhead | 20245424 | 9904029 | 12729189
MCR027551 | HPR215 | 2021-12-01 | Labor | 26414677 | 15805845 | 17390527
MCR027552 | HPR215 | 2021-12-01 | Material | 81391547 | 48702551 | 47226799
MCR027553 | HPR215 | 2021-12-01 | Equipment | 19562232 | 11705523 | 12379396
MCR027554 | HPR215 | 2021-12-01 | Subcontract | 91178818 | 54558995 | 58777882
MCR027555 | HPR215 | 2021-12-01 | Overhead | 18786982 | 11241634 | 12926122
MCR027556 | HPR215 | 2022-01-01 | Labor | 23496801 | 22130597 | 24641047
MCR027557 | HPR215 | 2022-01-01 | Material | 72400696 | 68191009 | 85689561
MCR027558 | HPR215 | 2022-01-01 | Equipment | 17401306 | 16389520 | 16589105
MCR027559 | HPR215 | 2022-01-01 | Subcontract | 81106824 | 76390926 | 76315575
MCR027560 | HPR215 | 2022-01-01 | Overhead | 16711693 | 15740004 | 12800892
MCR027561 | HPR215 | 2022-02-01 | Labor | 19826364 | 43370260 | 65247684
MCR027562 | HPR215 | 2022-02-01 | Material | 61090977 | 133636784 | 168129863
MCR027563 | HPR215 | 2022-02-01 | Equipment | 14683047 | 32119230 | 33254792
MCR027564 | HPR215 | 2022-02-01 | Subcontract | 68437120 | 149706505 | 155496266
MCR027565 | HPR215 | 2022-02-01 | Overhead | 14101158 | 30846347 | 14533574
MCR027566 | HPR215 | 2022-03-01 | Labor | 15546389 | 39972200 | 52407798
MCR027567 | HPR215 | 2022-03-01 | Material | 47903090 | 123166343 | 145030280
MCR027568 | HPR215 | 2022-03-01 | Equipment | 11513375 | 29602688 | 32232140
MCR027569 | HPR215 | 2022-03-01 | Subcontract | 53663400 | 137977001 | 127181878
MCR027570 | HPR215 | 2022-03-01 | Overhead | 11057100 | 28429536 | 14099285
MCR027571 | HPR215 | 2022-04-01 | Labor | 10847364 | 12788083 | 15981128
MCR027572 | HPR215 | 2022-04-01 | Material | 33423983 | 39403922 | 50197272
MCR027573 | HPR215 | 2022-04-01 | Equipment | 8033361 | 9470623 | 8676651
MCR027574 | HPR215 | 2022-04-01 | Subcontract | 37443191 | 44142213 | 46463179
MCR027575 | HPR215 | 2022-04-01 | Overhead | 7715000 | 9095303 | 14386371
MCR027576 | HPR215 | 2022-05-01 | Labor | 6014712 | 17514488 | 20430375
MCR027577 | HPR215 | 2022-05-01 | Material | 18533132 | 53967394 | 43453812
MCR027578 | HPR215 | 2022-05-01 | Equipment | 4454387 | 12970913 | 16073722
MCR027579 | HPR215 | 2022-05-01 | Subcontract | 20761727 | 60456932 | 52358218
MCR027580 | HPR215 | 2022-05-01 | Overhead | 4277860 | 12456877 | 13164100
MCR027581 | HPR215 | 2022-06-01 | Labor | 1625470 | 12431076 | 11278316
MCR027582 | HPR215 | 2022-06-01 | Material | 5008562 | 38303876 | 45166215
MCR027583 | HPR215 | 2022-06-01 | Equipment | 1203794 | 9206230 | 8108882
MCR027584 | HPR215 | 2022-06-01 | Subcontract | 5610838 | 42909887 | 53418363
MCR027585 | HPR215 | 2022-06-01 | Overhead | 1156088 | 8841388 | 14399296
MCR027586 | HPR215 | 2022-07-01 | Labor | 0 | 9575420 | 11337738
MCR027587 | HPR215 | 2022-07-01 | Material | 0 | 29504741 | 34541485
MCR027588 | HPR215 | 2022-07-01 | Equipment | 0 | 7091383 | 8193902
MCR027589 | HPR215 | 2022-07-01 | Subcontract | 0 | 33052663 | 27566406
MCR027590 | HPR215 | 2022-07-01 | Overhead | 0 | 6810351 | 14409017
MCR027591 | HPR215 | 2022-08-01 | Labor | 0 | 7136338 | 6295206
MCR027592 | HPR215 | 2022-08-01 | Material | 0 | 21989198 | 23195197
MCR027593 | HPR215 | 2022-08-01 | Equipment | 0 | 5285043 | 4838996
MCR027594 | HPR215 | 2022-08-01 | Subcontract | 0 | 24633383 | 20961973
MCR027595 | HPR215 | 2022-08-01 | Overhead | 0 | 5075597 | 14239913
MCR027596 | HPR215 | 2022-09-01 | Labor | 0 | 8670569 | 9265702
MCR027597 | HPR215 | 2022-09-01 | Material | 0 | 26716624 | 27537821
MCR027598 | HPR215 | 2022-09-01 | Equipment | 0 | 6421266 | 6844207
MCR027599 | HPR215 | 2022-09-01 | Subcontract | 0 | 29929278 | 30440583
MCR027600 | HPR215 | 2022-09-01 | Overhead | 0 | 6166792 | 12498882
MCR027601 | HPR215 | 2022-10-01 | Labor | 0 | 3188415 | 3511352
MCR027602 | HPR215 | 2022-10-01 | Material | 0 | 9824464 | 11724580
MCR027603 | HPR215 | 2022-10-01 | Equipment | 0 | 2361283 | 3310460
MCR027604 | HPR215 | 2022-10-01 | Subcontract | 0 | 11005848 | 11111704
MCR027605 | HPR215 | 2022-10-01 | Overhead | 0 | 2267705 | 13153947
MCR027606 | HPR215 | 2022-11-01 | Labor | 0 | 2324717 | 2583220
MCR027607 | HPR215 | 2022-11-01 | Material | 0 | 7163151 | 8128566
MCR027608 | HPR215 | 2022-11-01 | Equipment | 0 | 1721643 | 1934775
MCR027609 | HPR215 | 2022-11-01 | Subcontract | 0 | 8024514 | 7941575
MCR027610 | HPR215 | 2022-11-01 | Overhead | 0 | 1653415 | 12140998
MCR027611 | HPR215 | 2022-12-01 | Labor | 0 | 447518 | 388286
MCR027612 | HPR215 | 2022-12-01 | Material | 0 | 1378939 | 1187126
MCR027613 | HPR215 | 2022-12-01 | Equipment | 0 | 331424 | 440437
MCR027614 | HPR215 | 2022-12-01 | Subcontract | 0 | 1544755 | 989213
MCR027615 | HPR215 | 2022-12-01 | Overhead | 0 | 318290 | 12766917
MCR027616 | HPR216 | 2021-11-01 | Labor | 4663871 | 4549946 | 4961600
MCR027617 | HPR216 | 2021-11-01 | Material | 9659207 | 9423260 | 10760634
MCR027618 | HPR216 | 2021-11-01 | Equipment | 2381219 | 2323052 | 2050337
MCR027619 | HPR216 | 2021-11-01 | Subcontract | 10668829 | 10408219 | 9852892
MCR027620 | HPR216 | 2021-11-01 | Overhead | 2856778 | 2786995 | 14233608
MCR027621 | HPR216 | 2021-12-01 | Labor | 13066388 | 12943255 | 12820302
MCR027622 | HPR216 | 2021-12-01 | Material | 27061412 | 26806396 | 26891314
MCR027623 | HPR216 | 2021-12-01 | Equipment | 6671267 | 6608399 | 7357824
MCR027624 | HPR216 | 2021-12-01 | Subcontract | 29889987 | 29608316 | 28181845
MCR027625 | HPR216 | 2021-12-01 | Overhead | 8003602 | 7928179 | 14342230
MCR027626 | HPR216 | 2022-01-01 | Labor | 20109397 | 27779261 | 30014468
MCR027627 | HPR216 | 2022-01-01 | Material | 41647982 | 57532811 | 58712426
MCR027628 | HPR216 | 2022-01-01 | Equipment | 10267195 | 14183174 | 12676668
MCR027629 | HPR216 | 2022-01-01 | Subcontract | 46001208 | 63546387 | 55904368
MCR027630 | HPR216 | 2022-01-01 | Overhead | 12317683 | 17015732 | 14863280
MCR027631 | HPR216 | 2022-02-01 | Labor | 25832490 | 23422022 | 25486267
MCR027632 | HPR216 | 2022-02-01 | Material | 53500911 | 48508661 | 45034622
MCR027633 | HPR216 | 2022-02-01 | Equipment | 13189217 | 11958511 | 12352012
MCR027634 | HPR216 | 2022-02-01 | Subcontract | 59093056 | 53578994 | 47867373
MCR027635 | HPR216 | 2022-02-01 | Overhead | 15823269 | 14346776 | 14116687
MCR027636 | HPR216 | 2022-03-01 | Labor | 30277798 | 22637228 | 25172271
MCR027637 | HPR216 | 2022-03-01 | Material | 62707458 | 46883298 | 52271404
MCR027638 | HPR216 | 2022-03-01 | Equipment | 15458845 | 11557822 | 13732953
MCR027639 | HPR216 | 2022-03-01 | Subcontract | 69261911 | 51783741 | 54009593
MCR027640 | HPR216 | 2022-03-01 | Overhead | 18546170 | 13866064 | 13510967
MCR027641 | HPR216 | 2022-04-01 | Labor | 33490397 | 30227700 | 32711366
MCR027642 | HPR216 | 2022-04-01 | Material | 69360978 | 62603702 | 65002221
MCR027643 | HPR216 | 2022-04-01 | Equipment | 17099092 | 15433266 | 15211147
MCR027644 | HPR216 | 2022-04-01 | Subcontract | 76610885 | 69147310 | 58278022
MCR027645 | HPR216 | 2022-04-01 | Overhead | 20513995 | 18515484 | 12841082
MCR027646 | HPR216 | 2022-05-01 | Labor | 35518806 | 25682443 | 25277644
MCR027647 | HPR216 | 2022-05-01 | Material | 73561956 | 53190153 | 47148374
MCR027648 | HPR216 | 2022-05-01 | Equipment | 18134730 | 13112608 | 12838080
MCR027649 | HPR216 | 2022-05-01 | Subcontract | 81250968 | 58749816 | 57403729
MCR027650 | HPR216 | 2022-05-01 | Overhead | 21756464 | 15731360 | 13736260
MCR027651 | HPR216 | 2022-06-01 | Labor | 36415631 | 20292679 | 22733980
MCR027652 | HPR216 | 2022-06-01 | Material | 75419344 | 42027572 | 44922083
MCR027653 | HPR216 | 2022-06-01 | Equipment | 18592620 | 10360772 | 12908452
MCR027654 | HPR216 | 2022-06-01 | Subcontract | 83302498 | 46420474 | 44117449
MCR027655 | HPR216 | 2022-06-01 | Overhead | 22305799 | 12429949 | 14430406
MCR027656 | HPR216 | 2022-07-01 | Labor | 36238410 | 19757256 | 20336985
MCR027657 | HPR216 | 2022-07-01 | Material | 75052306 | 40918673 | 44565165
MCR027658 | HPR216 | 2022-07-01 | Equipment | 18502136 | 10087403 | 9681150
MCR027659 | HPR216 | 2022-07-01 | Subcontract | 82897095 | 45195669 | 40736235
MCR027660 | HPR216 | 2022-07-01 | Overhead | 22197245 | 12101984 | 13386726
MCR027661 | HPR216 | 2022-08-01 | Labor | 35050745 | 11174182 | 13933808
MCR027662 | HPR216 | 2022-08-01 | Material | 72592567 | 23142520 | 26710268
MCR027663 | HPR216 | 2022-08-01 | Equipment | 17895754 | 5705169 | 5931150
MCR027664 | HPR216 | 2022-08-01 | Subcontract | 80180254 | 25561475 | 24690152
MCR027665 | HPR216 | 2022-08-01 | Overhead | 21469760 | 6844562 | 14898943
MCR027666 | HPR216 | 2022-09-01 | Labor | 32923880 | 22660867 | 26357544
MCR027667 | HPR216 | 2022-09-01 | Material | 68187680 | 46932257 | 50786386
MCR027668 | HPR216 | 2022-09-01 | Equipment | 16809847 | 11569891 | 11996310
MCR027669 | HPR216 | 2022-09-01 | Subcontract | 75314949 | 51837818 | 50588378
MCR027670 | HPR216 | 2022-09-01 | Overhead | 20166984 | 13880544 | 12858026
MCR027671 | HPR216 | 2022-10-01 | Labor | 29938975 | 43376694 | 39903510
MCR027672 | HPR216 | 2022-10-01 | Material | 62005732 | 89836197 | 80521477
MCR027673 | HPR216 | 2022-10-01 | Equipment | 15285853 | 22146709 | 23905616
MCR027674 | HPR216 | 2022-10-01 | Subcontract | 68486838 | 99226262 | 82576704
MCR027675 | HPR216 | 2022-10-01 | Overhead | 18338630 | 26569685 | 15124609
MCR027676 | HPR216 | 2022-11-01 | Labor | 26190554 | 27841594 | 28592712
MCR027677 | HPR216 | 2022-11-01 | Material | 54242486 | 57661907 | 64562410
MCR027678 | HPR216 | 2022-11-01 | Equipment | 13372032 | 14214999 | 11479673
MCR027679 | HPR216 | 2022-11-01 | Subcontract | 59912144 | 63688977 | 67207047
MCR027680 | HPR216 | 2022-11-01 | Overhead | 16042595 | 17053913 | 13763328
MCR027681 | HPR216 | 2022-12-01 | Labor | 21792073 | 38711748 | 41349919
MCR027682 | HPR216 | 2022-12-01 | Material | 45132922 | 80174764 | 76537007
MCR027683 | HPR216 | 2022-12-01 | Equipment | 11126313 | 19764941 | 20589117
MCR027684 | HPR216 | 2022-12-01 | Subcontract | 49850409 | 88554975 | 74926599
MCR027685 | HPR216 | 2022-12-01 | Overhead | 13348378 | 23712248 | 15121767
MCR027686 | HPR216 | 2023-01-01 | Labor | 16885762 | 30382637 | 48611979
MCR027687 | HPR216 | 2023-01-01 | Material | 34971606 | 62924588 | 92433658
MCR027688 | HPR216 | 2023-01-01 | Equipment | 8621313 | 15512372 | 16688188
MCR027689 | HPR216 | 2023-01-01 | Subcontract | 38626989 | 69501736 | 72412297
MCR027690 | HPR216 | 2023-01-01 | Overhead | 10343098 | 18610388 | 14763500
MCR027691 | HPR216 | 2023-02-01 | Labor | 11662366 | 16105797 | 40434362
MCR027692 | HPR216 | 2023-02-01 | Material | 24153583 | 33356243 | 42567880
MCR027693 | HPR216 | 2023-02-01 | Equipment | 5954419 | 8223088 | 7909498
MCR027694 | HPR216 | 2023-02-01 | Subcontract | 26678220 | 36842780 | 66247884
MCR027695 | HPR216 | 2023-02-01 | Overhead | 7143592 | 9865342 | 13698376
MCR027696 | HPR216 | 2023-03-01 | Labor | 6410271 | 11885703 | 12918751
MCR027697 | HPR216 | 2023-03-01 | Material | 13276125 | 24616129 | 28795927
MCR027698 | HPR216 | 2023-03-01 | Equipment | 3272873 | 6068448 | 6444513
MCR027699 | HPR216 | 2023-03-01 | Subcontract | 14663802 | 27189113 | 39220467
MCR027700 | HPR216 | 2023-03-01 | Overhead | 3926507 | 7280393 | 14511658
MCR027701 | HPR216 | 2023-04-01 | Labor | 1720317 | 14548212 | 15779689
MCR027702 | HPR216 | 2023-04-01 | Material | 3562899 | 30130374 | 31060485
MCR027703 | HPR216 | 2023-04-01 | Equipment | 878337 | 7427837 | 7420098
MCR027704 | HPR216 | 2023-04-01 | Subcontract | 3935308 | 33279730 | 42256790
MCR027705 | HPR216 | 2023-04-01 | Overhead | 1053752 | 8911269 | 13807152
MCR027706 | HPR216 | 2023-05-01 | Labor | 0 | 9108298 | 9361477
MCR027707 | HPR216 | 2023-05-01 | Material | 0 | 18863929 | 17323244
MCR027708 | HPR216 | 2023-05-01 | Equipment | 0 | 4650397 | 4182482
MCR027709 | HPR216 | 2023-05-01 | Subcontract | 0 | 20835668 | 38800064
MCR027710 | HPR216 | 2023-05-01 | Overhead | 0 | 5579139 | 14648718
MCR027711 | HPR216 | 2023-06-01 | Labor | 0 | 4099131 | 4608155
MCR027712 | HPR216 | 2023-06-01 | Material | 0 | 8489590 | 9361142
MCR027713 | HPR216 | 2023-06-01 | Equipment | 0 | 2092881 | 2200784
MCR027714 | HPR216 | 2023-06-01 | Subcontract | 0 | 9376958 | 26704928
MCR027715 | HPR216 | 2023-06-01 | Overhead | 0 | 2510856 | 12620584
MCR027716 | HPR216 | 2023-07-01 | Labor | 0 | 1001479 | 618953
MCR027717 | HPR216 | 2023-07-01 | Material | 0 | 2074134 | 1733341
MCR027718 | HPR216 | 2023-07-01 | Equipment | 0 | 511322 | 634455
MCR027719 | HPR216 | 2023-07-01 | Subcontract | 0 | 2290931 | 22573964
MCR027720 | HPR216 | 2023-07-01 | Overhead | 0 | 613440 | 15406378
MCR027721 | HPR217 | 2018-09-01 | Labor | 5021079 | 6017273 | 6873957
MCR027722 | HPR217 | 2018-09-01 | Material | 14982179 | 17954679 | 17358773
MCR027723 | HPR217 | 2018-09-01 | Equipment | 3652524 | 4377193 | 3999885
MCR027724 | HPR217 | 2018-09-01 | Subcontract | 13593537 | 16290527 | 16585511
MCR027725 | HPR217 | 2018-09-01 | Overhead | 3473047 | 4162108 | 15720180
MCR027726 | HPR217 | 2018-10-01 | Labor | 13938448 | 19779914 | 17281757
MCR027727 | HPR217 | 2018-10-01 | Material | 41590327 | 59020425 | 62310826
MCR027728 | HPR217 | 2018-10-01 | Equipment | 10139357 | 14388662 | 13009132
MCR027729 | HPR217 | 2018-10-01 | Subcontract | 37735475 | 53550043 | 46498395
MCR027730 | HPR217 | 2018-10-01 | Overhead | 9641131 | 13681634 | 14885820
MCR027731 | HPR217 | 2018-11-01 | Labor | 21207821 | 17290656 | 17452598
MCR027732 | HPR217 | 2018-11-01 | Material | 63281092 | 51592836 | 49240740
MCR027733 | HPR217 | 2018-11-01 | Equipment | 15427375 | 12577881 | 13161423
MCR027734 | HPR217 | 2018-11-01 | Subcontract | 57415805 | 46810890 | 46854364
MCR027735 | HPR217 | 2018-11-01 | Overhead | 14669308 | 11959831 | 15361359
MCR027736 | HPR217 | 2018-12-01 | Labor | 26884327 | 18089965 | 18644569
MCR027737 | HPR217 | 2018-12-01 | Material | 80218972 | 53977857 | 54032714
MCR027738 | HPR217 | 2018-12-01 | Equipment | 19556681 | 13159328 | 13747213
MCR027739 | HPR217 | 2018-12-01 | Subcontract | 72783776 | 48974852 | 45967213
MCR027740 | HPR217 | 2018-12-01 | Overhead | 18595709 | 12512707 | 14689555
MCR027741 | HPR217 | 2019-01-01 | Labor | 31027204 | 32705968 | 39007905
MCR027742 | HPR217 | 2019-01-01 | Material | 92580721 | 97589912 | 98100345
MCR027743 | HPR217 | 2019-01-01 | Equipment | 22570367 | 23791564 | 23299234
MCR027744 | HPR217 | 2019-01-01 | Subcontract | 83999761 | 88544668 | 88560329
MCR027745 | HPR217 | 2019-01-01 | Overhead | 21461309 | 22622499 | 14395115
MCR027746 | HPR217 | 2019-02-01 | Labor | 33700552 | 40141638 | 40668137
MCR027747 | HPR217 | 2019-02-01 | Material | 100557608 | 119776883 | 111274337
MCR027748 | HPR217 | 2019-02-01 | Equipment | 24515062 | 29200553 | 32061654
MCR027749 | HPR217 | 2019-02-01 | Subcontract | 91237300 | 108675213 | 95104120
MCR027750 | HPR217 | 2019-02-01 | Overhead | 23310446 | 27765702 | 14914697
MCR027751 | HPR217 | 2019-03-01 | Labor | 34974326 | 24447521 | 24496713
MCR027752 | HPR217 | 2019-03-01 | Material | 104358368 | 72947892 | 77087269
MCR027753 | HPR217 | 2019-03-01 | Equipment | 25441654 | 17784056 | 16372162
MCR027754 | HPR217 | 2019-03-01 | Subcontract | 94685782 | 66186625 | 72364092
MCR027755 | HPR217 | 2019-03-01 | Overhead | 24191508 | 16910186 | 15496904
MCR027756 | HPR217 | 2019-04-01 | Labor | 34925662 | 40431733 | 48747711
MCR027757 | HPR217 | 2019-04-01 | Material | 104213162 | 120642486 | 120240322
MCR027758 | HPR217 | 2019-04-01 | Equipment | 25406254 | 29411579 | 31367463
MCR027759 | HPR217 | 2019-04-01 | Subcontract | 94554034 | 109460586 | 110396765
MCR027760 | HPR217 | 2019-04-01 | Overhead | 24157847 | 27966359 | 15214339
MCR027761 | HPR217 | 2019-05-01 | Labor | 33640714 | 25592481 | 30105224
MCR027762 | HPR217 | 2019-05-01 | Material | 100379060 | 76364288 | 78290759
MCR027763 | HPR217 | 2019-05-01 | Equipment | 24471534 | 18616943 | 19056274
MCR027764 | HPR217 | 2019-05-01 | Subcontract | 91075301 | 69286368 | 61840213
MCR027765 | HPR217 | 2019-05-01 | Overhead | 23269057 | 17702148 | 15378193
MCR027766 | HPR217 | 2019-06-01 | Labor | 31217301 | 35639004 | 35946538
MCR027767 | HPR217 | 2019-06-01 | Material | 93147944 | 106341672 | 98505953
MCR027768 | HPR217 | 2019-06-01 | Equipment | 22708651 | 25925166 | 24496098
MCR027769 | HPR217 | 2019-06-01 | Subcontract | 84514410 | 96485261 | 101545681
MCR027770 | HPR217 | 2019-06-01 | Overhead | 21592798 | 24651261 | 15568991
MCR027771 | HPR217 | 2019-07-01 | Labor | 27768907 | 21112195 | 22340151
MCR027772 | HPR217 | 2019-07-01 | Material | 82858432 | 62995757 | 67911233
MCR027773 | HPR217 | 2019-07-01 | Equipment | 20200158 | 15357813 | 14950490
MCR027774 | HPR217 | 2019-07-01 | Subcontract | 75178594 | 57156917 | 56984252
MCR027775 | HPR217 | 2019-07-01 | Overhead | 19207567 | 14603164 | 15078270
MCR027776 | HPR217 | 2019-08-01 | Labor | 23431124 | 31949625 | 37097829
MCR027777 | HPR217 | 2019-08-01 | Material | 69915109 | 95333094 | 104520337
MCR027778 | HPR217 | 2019-08-01 | Equipment | 17044690 | 23241372 | 24928109
MCR027779 | HPR217 | 2019-08-01 | Subcontract | 63434939 | 86497027 | 95222297
MCR027780 | HPR217 | 2019-08-01 | Overhead | 16207151 | 22099342 | 15863686
MCR027781 | HPR217 | 2019-09-01 | Labor | 18372979 | 27248803 | 27278440
MCR027782 | HPR217 | 2019-09-01 | Material | 54822331 | 81306517 | 80722990
MCR027783 | HPR217 | 2019-09-01 | Equipment | 13365203 | 19821815 | 18169716
MCR027784 | HPR217 | 2019-09-01 | Subcontract | 49741055 | 73770520 | 84232295
MCR027785 | HPR217 | 2019-09-01 | Overhead | 12708467 | 18847815 | 15084350
MCR027786 | HPR217 | 2019-10-01 | Labor | 12819593 | 9256933 | 8868633
MCR027787 | HPR217 | 2019-10-01 | Material | 38251826 | 27621358 | 25549352
MCR027788 | HPR217 | 2019-10-01 | Equipment | 9325459 | 6733845 | 6827783
MCR027789 | HPR217 | 2019-10-01 | Subcontract | 34706407 | 25061238 | 55244279
MCR027790 | HPR217 | 2019-10-01 | Overhead | 8867227 | 6402958 | 14794855
MCR027791 | HPR217 | 2019-11-01 | Labor | 7108286 | 6644743 | 7708278
MCR027792 | HPR217 | 2019-11-01 | Material | 21210104 | 19826960 | 19582494
MCR027793 | HPR217 | 2019-11-01 | Equipment | 5170837 | 4833639 | 4361151
MCR027794 | HPR217 | 2019-11-01 | Subcontract | 19244219 | 17989273 | 40894283
MCR027795 | HPR217 | 2019-11-01 | Overhead | 4916754 | 4596124 | 15015902
MCR027796 | HPR217 | 2019-12-01 | Labor | 1921008 | 1610878 | 1667786
MCR027797 | HPR217 | 2019-12-01 | Material | 5732011 | 4806630 | 5397234
MCR027798 | HPR217 | 2019-12-01 | Equipment | 1397414 | 1171814 | 1526402
MCR027799 | HPR217 | 2019-12-01 | Subcontract | 5200733 | 4361121 | 24251868
MCR027800 | HPR217 | 2019-12-01 | Overhead | 1328748 | 1114234 | 16548591
MCR027801 | HPR218 | 2023-04-01 | Labor | 3088353 | 1308634 | 1405085
MCR027802 | HPR218 | 2023-04-01 | Material | 7302017 | 3094099 | 3137563
MCR027803 | HPR218 | 2023-04-01 | Equipment | 1475155 | 625071 | 648079
MCR027804 | HPR218 | 2023-04-01 | Subcontract | 15904452 | 6739227 | 6537793
MCR027805 | HPR218 | 2023-04-01 | Overhead | 2118712 | 897766 | 12999754
MCR027806 | HPR218 | 2023-05-01 | Labor | 8808961 | 4906924 | 4991599
MCR027807 | HPR218 | 2023-05-01 | Material | 20827667 | 11601798 | 10947169
MCR027808 | HPR218 | 2023-05-01 | Equipment | 4207610 | 2343798 | 2344244
MCR027809 | HPR218 | 2023-05-01 | Subcontract | 45364540 | 25269763 | 26481870
MCR027810 | HPR218 | 2023-05-01 | Overhead | 6043238 | 3366312 | 14047794
MCR027811 | HPR218 | 2023-06-01 | Labor | 13855671 | 8528938 | 10312031
MCR027812 | HPR218 | 2023-06-01 | Material | 32759968 | 20165588 | 18856940
MCR027813 | HPR218 | 2023-06-01 | Equipment | 6618176 | 4073857 | 4793412
MCR027814 | HPR218 | 2023-06-01 | Subcontract | 71354170 | 43922472 | 49514163
MCR027815 | HPR218 | 2023-06-01 | Overhead | 9505446 | 5851132 | 12920241
MCR027816 | HPR218 | 2023-07-01 | Labor | 18242616 | 6319689 | 6586626
MCR027817 | HPR218 | 2023-07-01 | Material | 43132340 | 14942100 | 13797057
MCR027818 | HPR218 | 2023-07-01 | Equipment | 8713605 | 3018606 | 2894795
MCR027819 | HPR218 | 2023-07-01 | Subcontract | 93946134 | 32545245 | 29087218
MCR027820 | HPR218 | 2023-07-01 | Overhead | 12515035 | 4335515 | 13787488
MCR027821 | HPR218 | 2023-08-01 | Labor | 21984574 | 7963689 | 7716103
MCR027822 | HPR218 | 2023-08-01 | Material | 51979723 | 18829129 | 18840459
MCR027823 | HPR218 | 2023-08-01 | Equipment | 10500955 | 3803865 | 3194379
MCR027824 | HPR218 | 2023-08-01 | Subcontract | 113216533 | 41011544 | 42417238
MCR027825 | HPR218 | 2023-08-01 | Overhead | 15082141 | 5463353 | 13870177
MCR027826 | HPR218 | 2023-09-01 | Labor | 25097033 | 16347780 | 17462407
MCR027827 | HPR218 | 2023-09-01 | Material | 59338738 | 38652243 | 32726437
MCR027828 | HPR218 | 2023-09-01 | Equipment | 11987625 | 7808535 | 8822910
MCR027829 | HPR218 | 2023-09-01 | Subcontract | 129245132 | 84188078 | 94898059
MCR027830 | HPR218 | 2023-09-01 | Overhead | 17217391 | 11215115 | 14176526
MCR027831 | HPR218 | 2023-10-01 | Labor | 27596279 | 10658322 | 12444833
MCR027832 | HPR218 | 2023-10-01 | Material | 65247885 | 25200243 | 24468771
MCR027833 | HPR218 | 2023-10-01 | Equipment | 13181393 | 5090959 | 5349325
MCR027834 | HPR218 | 2023-10-01 | Subcontract | 142115789 | 54888406 | 54148199
MCR027835 | HPR218 | 2023-10-01 | Overhead | 18931956 | 7311960 | 14757495
MCR027836 | HPR218 | 2023-11-01 | Labor | 29499485 | 14457729 | 15219396
MCR027837 | HPR218 | 2023-11-01 | Material | 69747773 | 34183459 | 31697827
MCR027838 | HPR218 | 2023-11-01 | Equipment | 14090461 | 6905750 | 7835065
MCR027839 | HPR218 | 2023-11-01 | Subcontract | 151916951 | 74454662 | 82252204
MCR027840 | HPR218 | 2023-11-01 | Overhead | 20237618 | 9918478 | 14518573
MCR027841 | HPR218 | 2023-12-01 | Labor | 30824833 | 21055421 | 23801952
MCR027842 | HPR218 | 2023-12-01 | Material | 72881390 | 49782860 | 39475062
MCR027843 | HPR218 | 2023-12-01 | Equipment | 14723515 | 10057145 | 10490868
MCR027844 | HPR218 | 2023-12-01 | Subcontract | 158742252 | 108431566 | 95094797
MCR027845 | HPR218 | 2023-12-01 | Overhead | 21146850 | 14444712 | 13237916
MCR027846 | HPR218 | 2024-01-01 | Labor | 31591654 | 12667498 | 14332474
MCR027847 | HPR218 | 2024-01-01 | Material | 74694441 | 29950684 | 34436821
MCR027848 | HPR218 | 2024-01-01 | Equipment | 15089788 | 6050644 | 5990552
MCR027849 | HPR218 | 2024-01-01 | Subcontract | 162691242 | 65235296 | 82750843
MCR027850 | HPR218 | 2024-01-01 | Overhead | 21672915 | 8690320 | 13998727
MCR027851 | HPR218 | 2024-02-01 | Labor | 31820600 | 25363232 | 25303497
MCR027852 | HPR218 | 2024-02-01 | Material | 75235754 | 59968130 | 57883589
MCR027853 | HPR218 | 2024-02-01 | Equipment | 15199144 | 12114775 | 12361605
MCR027854 | HPR218 | 2024-02-01 | Subcontract | 163870271 | 130616005 | 131547015
MCR027855 | HPR218 | 2024-02-01 | Overhead | 21829979 | 17400012 | 14473124
MCR027856 | HPR218 | 2024-03-01 | Labor | 31533857 | 18206130 | 20640979
MCR027857 | HPR218 | 2024-03-01 | Material | 74557787 | 43046074 | 40131849
MCR027858 | HPR218 | 2024-03-01 | Equipment | 15062181 | 8696178 | 10075998
MCR027859 | HPR218 | 2024-03-01 | Subcontract | 162393597 | 93758239 | 95877087
MCR027860 | HPR218 | 2024-03-01 | Overhead | 21633264 | 12490005 | 13988011
MCR027861 | HPR218 | 2024-04-01 | Labor | 30755419 | 28728503 | 29398008
MCR027862 | HPR218 | 2024-04-01 | Material | 72717270 | 67924885 | 64464832
MCR027863 | HPR218 | 2024-04-01 | Equipment | 14690359 | 13722201 | 14718946
MCR027864 | HPR218 | 2024-04-01 | Subcontract | 158384784 | 147946537 | 157460613
MCR027865 | HPR218 | 2024-04-01 | Overhead | 21099230 | 19708699 | 13808023
MCR027866 | HPR218 | 2024-05-01 | Labor | 29511436 | 17136690 | 17589505
MCR027867 | HPR218 | 2024-05-01 | Material | 69776030 | 40517521 | 41415377
MCR027868 | HPR218 | 2024-05-01 | Equipment | 14096169 | 8185359 | 8475655
MCR027869 | HPR218 | 2024-05-01 | Subcontract | 151978498 | 88250822 | 103634052
MCR027870 | HPR218 | 2024-05-01 | Overhead | 20245817 | 11756334 | 12961712
MCR027871 | HPR218 | 2024-06-01 | Labor | 27830675 | 21237669 | 25655705
MCR027872 | HPR218 | 2024-06-01 | Material | 65802084 | 50213762 | 52075920
MCR027873 | HPR218 | 2024-06-01 | Equipment | 13293352 | 10144196 | 11131744
MCR027874 | HPR218 | 2024-06-01 | Subcontract | 143322884 | 109370111 | 111472087
MCR027875 | HPR218 | 2024-06-01 | Overhead | 19092759 | 14569740 | 13692989
MCR027876 | HPR218 | 2024-07-01 | Labor | 25745142 | 25900742 | 24079548
MCR027877 | HPR218 | 2024-07-01 | Material | 60871107 | 61239004 | 56381110
MCR027878 | HPR218 | 2024-07-01 | Equipment | 12297195 | 12371518 | 12022695
MCR027879 | HPR218 | 2024-07-01 | Subcontract | 132582771 | 133384085 | 122115693
MCR027880 | HPR218 | 2024-07-01 | Overhead | 17662015 | 17768762 | 13257784
MCR027881 | HPR218 | 2024-08-01 | Labor | 23290955 | 19085949 | 21702032
MCR027882 | HPR218 | 2024-08-01 | Material | 55068495 | 45126294 | 41847479
MCR027883 | HPR218 | 2024-08-01 | Equipment | 11124950 | 9116424 | 10307788
MCR027884 | HPR218 | 2024-08-01 | Subcontract | 119944159 | 98289146 | 101354863
MCR027885 | HPR218 | 2024-08-01 | Overhead | 15978362 | 13093589 | 14161530
MCR027886 | HPR218 | 2024-09-01 | Labor | 20509606 | 21920580 | 21710164
MCR027887 | HPR218 | 2024-09-01 | Material | 48492350 | 51828417 | 47490990
MCR027888 | HPR218 | 2024-09-01 | Equipment | 9796436 | 10470389 | 11793686
MCR027889 | HPR218 | 2024-09-01 | Subcontract | 105620720 | 112886976 | 117247944
MCR027890 | HPR218 | 2024-09-01 | Overhead | 14070265 | 15038239 | 12982902
MCR027891 | HPR218 | 2024-10-01 | Labor | 17449891 | 13450015 | 31073431
MCR027892 | HPR218 | 2024-10-01 | Material | 41258043 | 31800846 | 58721413
MCR027893 | HPR218 | 2024-10-01 | Equipment | 8334959 | 6424414 | 7261981
MCR027894 | HPR218 | 2024-10-01 | Subcontract | 89863745 | 69265117 | 68315708
MCR027895 | HPR218 | 2024-10-01 | Overhead | 11971200 | 9227153 | 13765013
MCR027896 | HPR218 | 2024-11-01 | Labor | 14171050 | 19699227 | 37144461
MCR027897 | HPR218 | 2024-11-01 | Material | 33505641 | 46576312 | 59778144
MCR027898 | HPR218 | 2024-11-01 | Equipment | 6768817 | 9409357 | 10117997
MCR027899 | HPR218 | 2024-11-01 | Subcontract | 72978314 | 101447416 | 98347262
MCR027900 | HPR218 | 2024-11-01 | Overhead | 9721807 | 13514318 | 14093240
MCR027901 | HPR218 | 2024-12-01 | Labor | 10748358 | 14766093 | 17175056
MCR027902 | HPR218 | 2024-12-01 | Material | 25413122 | 34912545 | 35296526
MCR027903 | HPR218 | 2024-12-01 | Equipment | 5133965 | 7053040 | 7419862
MCR027904 | HPR218 | 2024-12-01 | Subcontract | 55352077 | 76042677 | 77037883
MCR027905 | HPR218 | 2024-12-01 | Overhead | 7373727 | 10130026 | 13741088
MCR027906 | HPR218 | 2025-01-01 | Labor | 7284439 | 18402406 | 18231827
MCR027907 | HPR218 | 2025-01-01 | Material | 17223129 | 43510143 | 41717555
MCR027908 | HPR218 | 2025-01-01 | Equipment | 3479420 | 8789929 | 8937511
MCR027909 | HPR218 | 2025-01-01 | Subcontract | 37513531 | 94769023 | 106588009
MCR027910 | HPR218 | 2025-01-01 | Overhead | 4997365 | 12624656 | 14827792
MCR027911 | HPR218 | 2025-02-01 | Labor | 3937705 | 21563785 | 24989871
MCR027912 | HPR218 | 2025-02-01 | Material | 9310202 | 50984822 | 51726784
MCR027913 | HPR218 | 2025-02-01 | Equipment | 1880849 | 10299965 | 10665879
MCR027914 | HPR218 | 2025-02-01 | Subcontract | 20278460 | 111049549 | 109852246
MCR027915 | HPR218 | 2025-02-01 | Overhead | 2701395 | 14793467 | 15127373
MCR027916 | HPR218 | 2025-03-01 | Labor | 1042469 | 23832989 | 26639173
MCR027917 | HPR218 | 2025-03-01 | Material | 2464784 | 56350067 | 53135499
MCR027918 | HPR218 | 2025-03-01 | Equipment | 497936 | 11383853 | 12875606
MCR027919 | HPR218 | 2025-03-01 | Subcontract | 5368523 | 122735537 | 166545711
MCR027920 | HPR218 | 2025-03-01 | Overhead | 715168 | 16350216 | 14872862
MCR027921 | HPR218 | 2025-04-01 | Labor | 0 | 14268561 | 14235626
MCR027922 | HPR218 | 2025-04-01 | Material | 0 | 33736194 | 31254682
MCR027923 | HPR218 | 2025-04-01 | Equipment | 0 | 6815394 | 8273274
MCR027924 | HPR218 | 2025-04-01 | Subcontract | 0 | 73480479 | 110126414
MCR027925 | HPR218 | 2025-04-01 | Overhead | 0 | 9788703 | 13221327
MCR027926 | HPR218 | 2025-05-01 | Labor | 0 | 14523076 | 13882102
MCR027927 | HPR218 | 2025-05-01 | Material | 0 | 34337963 | 34612463
MCR027928 | HPR218 | 2025-05-01 | Equipment | 0 | 6936963 | 7572320
MCR027929 | HPR218 | 2025-05-01 | Subcontract | 0 | 74791185 | 133611902
MCR027930 | HPR218 | 2025-05-01 | Overhead | 0 | 9963308 | 13466624
MCR027931 | HPR218 | 2025-06-01 | Labor | 0 | 18181732 | 20907212
MCR027932 | HPR218 | 2025-06-01 | Material | 0 | 42988388 | 40363858
MCR027933 | HPR218 | 2025-06-01 | Equipment | 0 | 8684524 | 8710539
MCR027934 | HPR218 | 2025-06-01 | Subcontract | 0 | 93632594 | 144085231
MCR027935 | HPR218 | 2025-06-01 | Overhead | 0 | 12473267 | 14221860
MCR027936 | HPR218 | 2025-07-01 | Labor | 0 | 12202953 | 13267634
MCR027937 | HPR218 | 2025-07-01 | Material | 0 | 28852328 | 27533238
MCR027938 | HPR218 | 2025-07-01 | Equipment | 0 | 5828754 | 7120965
MCR027939 | HPR218 | 2025-07-01 | Subcontract | 0 | 62842978 | 139634683
MCR027940 | HPR218 | 2025-07-01 | Overhead | 0 | 8371628 | 13166620
MCR027941 | HPR218 | 2025-08-01 | Labor | 0 | 6235911 | 6776805
MCR027942 | HPR218 | 2025-08-01 | Material | 0 | 14744016 | 14083950
MCR027943 | HPR218 | 2025-08-01 | Equipment | 0 | 2978589 | 3128553
MCR027944 | HPR218 | 2025-08-01 | Subcontract | 0 | 32113799 | 92773099
MCR027945 | HPR218 | 2025-08-01 | Overhead | 0 | 4278040 | 13192165
MCR027946 | HPR218 | 2025-09-01 | Labor | 0 | 9125703 | 10098917
MCR027947 | HPR218 | 2025-09-01 | Material | 0 | 21576562 | 20613393
MCR027948 | HPR218 | 2025-09-01 | Equipment | 0 | 4358902 | 4964816
MCR027949 | HPR218 | 2025-09-01 | Subcontract | 0 | 46995703 | 64334763
MCR027950 | HPR218 | 2025-09-01 | Overhead | 0 | 6260533 | 14054132
MCR027951 | HPR218 | 2025-10-01 | Labor | 0 | 9661413 | 10000633
MCR027952 | HPR218 | 2025-10-01 | Material | 0 | 22843180 | 21206480
MCR027953 | HPR218 | 2025-10-01 | Equipment | 0 | 4614784 | 6111156
MCR027954 | HPR218 | 2025-10-01 | Subcontract | 0 | 49754510 | 129498777
MCR027955 | HPR218 | 2025-10-01 | Overhead | 0 | 6628047 | 13867652
MCR027956 | HPR218 | 2025-11-01 | Labor | 0 | 3739265 | 4334813
MCR027957 | HPR218 | 2025-11-01 | Material | 0 | 8841017 | 8703900
MCR027958 | HPR218 | 2025-11-01 | Equipment | 0 | 1786064 | 2385049
MCR027959 | HPR218 | 2025-11-01 | Subcontract | 0 | 19256533 | 51931159
MCR027960 | HPR218 | 2025-11-01 | Overhead | 0 | 2565259 | 14627569
MCR027961 | HPR218 | 2025-12-01 | Labor | 0 | 2503843 | 2582146
MCR027962 | HPR218 | 2025-12-01 | Material | 0 | 5920018 | 6245037
MCR027963 | HPR218 | 2025-12-01 | Equipment | 0 | 1195963 | 1366912
MCR027964 | HPR218 | 2025-12-01 | Subcontract | 0 | 12894335 | 56359169
MCR027965 | HPR218 | 2025-12-01 | Overhead | 0 | 1717719 | 12970520
MCR027966 | HPR218 | 2026-01-01 | Labor | 0 | 1845024 | 2021338
MCR027967 | HPR218 | 2026-01-01 | Material | 0 | 4362324 | 4330995
MCR027968 | HPR218 | 2026-01-01 | Equipment | 0 | 881278 | 1133382
MCR027969 | HPR218 | 2026-01-01 | Subcontract | 0 | 9501535 | 46072748
MCR027970 | HPR218 | 2026-01-01 | Overhead | 0 | 1265747 | 14525692
MCR027971 | HPR218 | 2026-02-01 | Labor | 0 | 424943 | 554245
MCR027972 | HPR218 | 2026-02-01 | Material | 0 | 1004724 | 633953
MCR027973 | HPR218 | 2026-02-01 | Equipment | 0 | 202975 | 264361
MCR027974 | HPR218 | 2026-02-01 | Subcontract | 0 | 2188381 | 35268851
MCR027975 | HPR218 | 2026-02-01 | Overhead | 0 | 291525 | 14303647
MCR027976 | HPR219 | 2021-09-01 | Labor | 13235399 | 16605493 | 15604719
MCR027977 | HPR219 | 2021-09-01 | Material | 27065047 | 33956549 | 36534867
MCR027978 | HPR219 | 2021-09-01 | Equipment | 5765466 | 7233512 | 7601147
MCR027979 | HPR219 | 2021-09-01 | Subcontract | 28096219 | 35250286 | 36395236
MCR027980 | HPR219 | 2021-09-01 | Overhead | 7150155 | 8970781 | 29130420
MCR027981 | HPR219 | 2021-10-01 | Labor | 36301412 | 31185368 | 32643236
MCR027982 | HPR219 | 2021-10-01 | Material | 74232704 | 63770914 | 73328238
MCR027983 | HPR219 | 2021-10-01 | Equipment | 15813242 | 13584644 | 13247080
MCR027984 | HPR219 | 2021-10-01 | Subcontract | 77060953 | 66200571 | 76756754
MCR027985 | HPR219 | 2021-10-01 | Overhead | 19611101 | 16847262 | 29561877
MCR027986 | HPR219 | 2021-11-01 | Labor | 54397824 | 42947121 | 44866174
MCR027987 | HPR219 | 2021-11-01 | Material | 111238032 | 87822505 | 87730814
MCR027988 | HPR219 | 2021-11-01 | Equipment | 23696212 | 18708176 | 19850281
MCR027989 | HPR219 | 2021-11-01 | Subcontract | 115476175 | 91168521 | 93734449
MCR027990 | HPR219 | 2021-11-01 | Overhead | 29387320 | 23201310 | 31054929
MCR027991 | HPR219 | 2021-12-01 | Labor | 67719935 | 45225258 | 46082885
MCR027992 | HPR219 | 2021-12-01 | Material | 138480397 | 92481064 | 103875488
MCR027993 | HPR219 | 2021-12-01 | Equipment | 29499451 | 19700554 | 20858860
MCR027994 | HPR219 | 2021-12-01 | Subcontract | 143756467 | 96004570 | 88011238
MCR027995 | HPR219 | 2021-12-01 | Overhead | 36584320 | 24432027 | 28559978
MCR027996 | HPR219 | 2022-01-01 | Labor | 76480369 | 74819963 | 83441294
MCR027997 | HPR219 | 2022-01-01 | Material | 156394596 | 152999234 | 168329575
MCR027998 | HPR219 | 2022-01-01 | Equipment | 33315580 | 32592291 | 33640076
MCR027999 | HPR219 | 2022-01-01 | Subcontract | 162353193 | 158828468 | 168869413
MCR028000 | HPR219 | 2022-01-01 | Overhead | 41316967 | 40419966 | 27526548
MCR028001 | HPR219 | 2022-02-01 | Labor | 80912940 | 57861560 | 62460063
MCR028002 | HPR219 | 2022-02-01 | Material | 165458754 | 118321021 | 140385603
MCR028003 | HPR219 | 2022-02-01 | Equipment | 35246450 | 25205049 | 27511431
MCR028004 | HPR219 | 2022-02-01 | Subcontract | 171762694 | 122829024 | 119398491
MCR028005 | HPR219 | 2022-02-01 | Overhead | 43711574 | 31258533 | 25013238
MCR028006 | HPR219 | 2022-03-01 | Labor | 81277986 | 62989802 | 53130921
MCR028007 | HPR219 | 2022-03-01 | Material | 166205235 | 128807755 | 116228223
MCR028008 | HPR219 | 2022-03-01 | Equipment | 35405467 | 27438960 | 26641226
MCR028009 | HPR219 | 2022-03-01 | Subcontract | 172537615 | 133715301 | 153761318
MCR028010 | HPR219 | 2022-03-01 | Overhead | 43908782 | 34028962 | 29829688
MCR028011 | HPR219 | 2022-04-01 | Labor | 77870017 | 69459365 | 73618779
MCR028012 | HPR219 | 2022-04-01 | Material | 159236284 | 142037355 | 165310694
MCR028013 | HPR219 | 2022-04-01 | Equipment | 33920924 | 30257163 | 32042919
MCR028014 | HPR219 | 2022-04-01 | Subcontract | 165303149 | 147448945 | 144947273
MCR028015 | HPR219 | 2022-04-01 | Overhead | 42067696 | 37524012 | 28866300
MCR028016 | HPR219 | 2022-05-01 | Labor | 71029244 | 63989399 | 66797270
MCR028017 | HPR219 | 2022-05-01 | Material | 145247598 | 130851830 | 161521273
MCR028018 | HPR219 | 2022-05-01 | Equipment | 30941018 | 27874394 | 27865950
MCR028019 | HPR219 | 2022-05-01 | Subcontract | 150781498 | 135837254 | 154249962
MCR028020 | HPR219 | 2022-05-01 | Overhead | 38372107 | 34568974 | 28663009
MCR028021 | HPR219 | 2022-06-01 | Labor | 61160071 | 56141026 | 57598422
MCR028022 | HPR219 | 2022-06-01 | Material | 125066140 | 114802703 | 94989307
MCR028023 | HPR219 | 2022-06-01 | Equipment | 26641911 | 24455568 | 26756053
MCR028024 | HPR219 | 2022-06-01 | Subcontract | 129831130 | 119176659 | 133919955
MCR028025 | HPR219 | 2022-06-01 | Overhead | 33040487 | 30329050 | 26954451
MCR028026 | HPR219 | 2022-07-01 | Labor | 48763466 | 36655995 | 48054432
MCR028027 | HPR219 | 2022-07-01 | Material | 99716342 | 74957790 | 107339106
MCR028028 | HPR219 | 2022-07-01 | Equipment | 21241832 | 15967702 | 15222775
MCR028029 | HPR219 | 2022-07-01 | Subcontract | 103515511 | 77813665 | 80696377
MCR028030 | HPR219 | 2022-07-01 | Overhead | 26343473 | 19802657 | 27646437
MCR028031 | HPR219 | 2022-08-01 | Labor | 34501391 | 43248462 | 48711629
MCR028032 | HPR219 | 2022-08-01 | Material | 70551845 | 88438717 | 89604873
MCR028033 | HPR219 | 2022-08-01 | Equipment | 15029136 | 18839443 | 18320507
MCR028034 | HPR219 | 2022-08-01 | Subcontract | 73239854 | 91808211 | 92546238
MCR028035 | HPR219 | 2022-08-01 | Overhead | 18638676 | 23364104 | 28646651
MCR028036 | HPR219 | 2022-09-01 | Labor | 19355438 | 67289534 | 74174138
MCR028037 | HPR219 | 2022-09-01 | Material | 39579907 | 137600271 | 141894980
MCR028038 | HPR219 | 2022-09-01 | Equipment | 8431414 | 29311964 | 27820110
MCR028039 | HPR219 | 2022-09-01 | Subcontract | 41087892 | 142842809 | 175523888
MCR028040 | HPR219 | 2022-09-01 | Overhead | 10456382 | 36351805 | 28925336
MCR028041 | HPR219 | 2022-10-01 | Labor | 5278895 | 36570675 | 37598002
MCR028042 | HPR219 | 2022-10-01 | Material | 10794804 | 74783320 | 98110739
MCR028043 | HPR219 | 2022-10-01 | Equipment | 2299537 | 15930536 | 15665866
MCR028044 | HPR219 | 2022-10-01 | Subcontract | 11206084 | 77632547 | 71820667
MCR028045 | HPR219 | 2022-10-01 | Overhead | 2851816 | 19756565 | 28212610
MCR028046 | HPR219 | 2022-11-01 | Labor | 0 | 18554723 | 18569800
MCR028047 | HPR219 | 2022-11-01 | Material | 0 | 37942527 | 43676484
MCR028048 | HPR219 | 2022-11-01 | Equipment | 0 | 8082615 | 7988428
MCR028049 | HPR219 | 2022-11-01 | Subcontract | 0 | 39388128 | 44884647
MCR028050 | HPR219 | 2022-11-01 | Overhead | 0 | 10023813 | 27595369
MCR028051 | HPR219 | 2022-12-01 | Labor | 0 | 4740641 | 5778542
MCR028052 | HPR219 | 2022-12-01 | Material | 0 | 9694131 | 10951777
MCR028053 | HPR219 | 2022-12-01 | Equipment | 0 | 2065069 | 2882305
MCR028054 | HPR219 | 2022-12-01 | Subcontract | 0 | 10063475 | 5835337
MCR028055 | HPR219 | 2022-12-01 | Overhead | 0 | 2561035 | 26367392
MCR028056 | HPR220 | 2022-07-01 | Labor | 4530685 | 2073446 | 2126440
MCR028057 | HPR220 | 2022-07-01 | Material | 12061755 | 5520004 | 5977985
MCR028058 | HPR220 | 2022-07-01 | Equipment | 2376504 | 1087596 | 1094970
MCR028059 | HPR220 | 2022-07-01 | Subcontract | 11558740 | 5289802 | 4738220
MCR028060 | HPR220 | 2022-07-01 | Overhead | 2686334 | 1229388 | 14025580
MCR028061 | HPR220 | 2022-08-01 | Labor | 12693250 | 5864057 | 5677374
MCR028062 | HPR220 | 2022-08-01 | Material | 33792436 | 15611508 | 15601343
MCR028063 | HPR220 | 2022-08-01 | Equipment | 6658058 | 3075905 | 3308614
MCR028064 | HPR220 | 2022-08-01 | Subcontract | 32383180 | 14960456 | 15827458
MCR028065 | HPR220 | 2022-08-01 | Overhead | 7526083 | 3476917 | 13040836
MCR028066 | HPR220 | 2022-09-01 | Labor | 19535132 | 11481653 | 11197868
MCR028067 | HPR220 | 2022-09-01 | Material | 52007145 | 30566879 | 32806025
MCR028068 | HPR220 | 2022-09-01 | Equipment | 10246867 | 6022533 | 6325522
MCR028069 | HPR220 | 2022-09-01 | Subcontract | 49838275 | 29292139 | 28730645
MCR028070 | HPR220 | 2022-09-01 | Overhead | 11582772 | 6807703 | 13080298
MCR028071 | HPR220 | 2022-10-01 | Labor | 25094789 | 18018516 | 20575947
MCR028072 | HPR220 | 2022-10-01 | Material | 66808269 | 47969556 | 42955105
MCR028073 | HPR220 | 2022-10-01 | Equipment | 13163104 | 9451349 | 10674458
MCR028074 | HPR220 | 2022-10-01 | Subcontract | 64022144 | 45969067 | 40528982
MCR028075 | HPR220 | 2022-10-01 | Overhead | 14879205 | 10683540 | 14764175
MCR028076 | HPR220 | 2022-11-01 | Labor | 29413152 | 8909875 | 8094521
MCR028077 | HPR220 | 2022-11-01 | Material | 78304774 | 23720198 | 27231255
MCR028078 | HPR220 | 2022-11-01 | Equipment | 15428238 | 4673545 | 4419163
MCR028079 | HPR220 | 2022-11-01 | Subcontract | 75039207 | 22730987 | 24854182
MCR028080 | HPR220 | 2022-11-01 | Overhead | 17439649 | 5282844 | 12163426
MCR028081 | HPR220 | 2022-12-01 | Labor | 32534009 | 18323585 | 20000735
MCR028082 | HPR220 | 2022-12-01 | Material | 86613234 | 48781720 | 48109372
MCR028083 | HPR220 | 2022-12-01 | Equipment | 17065238 | 9611368 | 9738592
MCR028084 | HPR220 | 2022-12-01 | Subcontract | 83001176 | 46747361 | 39116421
MCR028085 | HPR220 | 2022-12-01 | Overhead | 19290067 | 10864421 | 12557205
MCR028086 | HPR220 | 2023-01-01 | Labor | 34504493 | 17385921 | 18369125
MCR028087 | HPR220 | 2023-01-01 | Material | 91859127 | 46285438 | 47320768
MCR028088 | HPR220 | 2023-01-01 | Equipment | 18098826 | 9119530 | 10071246
MCR028089 | HPR220 | 2023-01-01 | Subcontract | 88028298 | 44355182 | 45723394
MCR028090 | HPR220 | 2023-01-01 | Overhead | 20458407 | 10308462 | 12270993
MCR028091 | HPR220 | 2023-02-01 | Labor | 35375707 | 30724143 | 31270161
MCR028092 | HPR220 | 2023-02-01 | Material | 94178506 | 81794943 | 82018522
MCR028093 | HPR220 | 2023-02-01 | Equipment | 18555809 | 16115899 | 17443600
MCR028094 | HPR220 | 2023-02-01 | Subcontract | 90250951 | 78383823 | 80208498
MCR028095 | HPR220 | 2023-02-01 | Overhead | 20974967 | 18216962 | 13076309
MCR028096 | HPR220 | 2023-03-01 | Labor | 35203546 | 17794374 | 17925330
MCR028097 | HPR220 | 2023-03-01 | Material | 93720174 | 47372835 | 42269901
MCR028098 | HPR220 | 2023-03-01 | Equipment | 18465504 | 9333778 | 7962284
MCR028099 | HPR220 | 2023-03-01 | Subcontract | 89811733 | 45397231 | 46707638
MCR028100 | HPR220 | 2023-03-01 | Overhead | 20872890 | 10550642 | 14555142
MCR028101 | HPR220 | 2023-04-01 | Labor | 34049797 | 26006213 | 25856161
MCR028102 | HPR220 | 2023-04-01 | Material | 90648621 | 69234695 | 50163119
MCR028103 | HPR220 | 2023-04-01 | Equipment | 17860322 | 13641178 | 14132292
MCR028104 | HPR220 | 2023-04-01 | Subcontract | 86868274 | 66347379 | 59283495
MCR028105 | HPR220 | 2023-04-01 | Overhead | 20188809 | 15419606 | 13413522
MCR028106 | HPR220 | 2023-05-01 | Labor | 31983670 | 26075096 | 27995951
MCR028107 | HPR220 | 2023-05-01 | Material | 85148100 | 69418078 | 68545948
MCR028108 | HPR220 | 2023-05-01 | Equipment | 16776565 | 13677309 | 16680038
MCR028109 | HPR220 | 2023-05-01 | Subcontract | 81597143 | 66523115 | 65559905
MCR028110 | HPR220 | 2023-05-01 | Overhead | 18963760 | 15460448 | 13670837
MCR028111 | HPR220 | 2023-06-01 | Labor | 29084005 | 60469368 | 60738368
MCR028112 | HPR220 | 2023-06-01 | Material | 77428507 | 160983772 | 156282933
MCR028113 | HPR220 | 2023-06-01 | Equipment | 15255589 | 31718320 | 34452355
MCR028114 | HPR220 | 2023-06-01 | Subcontract | 74199483 | 154270217 | 161500461
MCR028115 | HPR220 | 2023-06-01 | Overhead | 17244491 | 35853503 | 12861111
MCR028116 | HPR220 | 2023-07-01 | Labor | 25442628 | 10107628 | 11549395
MCR028117 | HPR220 | 2023-07-01 | Material | 67734298 | 26908899 | 21968396
MCR028118 | HPR220 | 2023-07-01 | Equipment | 13345557 | 5301808 | 3785629
MCR028119 | HPR220 | 2023-07-01 | Subcontract | 64909554 | 25786709 | 19946583
MCR028120 | HPR220 | 2023-07-01 | Overhead | 15085445 | 5993016 | 14150583
MCR028121 | HPR220 | 2023-08-01 | Labor | 21169755 | 27072942 | 27066808
MCR028122 | HPR220 | 2023-08-01 | Material | 56358899 | 72074580 | 74865440
MCR028123 | HPR220 | 2023-08-01 | Equipment | 11104285 | 14200715 | 15943658
MCR028124 | HPR220 | 2023-08-01 | Subcontract | 54008547 | 69068832 | 68453973
MCR028125 | HPR220 | 2023-08-01 | Overhead | 12551973 | 16052091 | 14615638
MCR028126 | HPR220 | 2023-09-01 | Labor | 16403554 | 24992591 | 51295028
MCR028127 | HPR220 | 2023-09-01 | Material | 43670144 | 66536193 | 84363561
MCR028128 | HPR220 | 2023-09-01 | Equipment | 8604244 | 13109497 | 12881645
MCR028129 | HPR220 | 2023-09-01 | Subcontract | 41848955 | 63761414 | 53299180
MCR028130 | HPR220 | 2023-09-01 | Overhead | 9725997 | 14818609 | 13052295
MCR028131 | HPR220 | 2023-10-01 | Labor | 11329323 | 25875228 | 43365347
MCR028132 | HPR220 | 2023-10-01 | Material | 30161339 | 68885981 | 93501502
MCR028133 | HPR220 | 2023-10-01 | Equipment | 5942630 | 13572471 | 14495002
MCR028134 | HPR220 | 2023-10-01 | Subcontract | 28903512 | 66013208 | 67164922
MCR028135 | HPR220 | 2023-10-01 | Overhead | 6717383 | 15341942 | 13653372
MCR028136 | HPR220 | 2023-11-01 | Labor | 6227213 | 21917882 | 24131738
MCR028137 | HPR220 | 2023-11-01 | Material | 16578314 | 58350591 | 52570838
MCR028138 | HPR220 | 2023-11-01 | Equipment | 3266393 | 11496704 | 11039398
MCR028139 | HPR220 | 2023-11-01 | Subcontract | 15886944 | 55917179 | 59016758
MCR028140 | HPR220 | 2023-11-01 | Overhead | 3692239 | 12995553 | 15187503
MCR028141 | HPR220 | 2023-12-01 | Labor | 1671190 | 15269218 | 15025040
MCR028142 | HPR220 | 2023-12-01 | Material | 4449103 | 40650274 | 44496752
MCR028143 | HPR220 | 2023-12-01 | Equipment | 876598 | 8009245 | 8596873
MCR028144 | HPR220 | 2023-12-01 | Subcontract | 4263561 | 38955023 | 38976093
MCR028145 | HPR220 | 2023-12-01 | Overhead | 990882 | 9053426 | 12590552
MCR028146 | HPR220 | 2024-01-01 | Labor | 0 | 17484526 | 18752249
MCR028147 | HPR220 | 2024-01-01 | Material | 0 | 46547948 | 39032355
MCR028148 | HPR220 | 2024-01-01 | Equipment | 0 | 9171252 | 10082445
MCR028149 | HPR220 | 2024-01-01 | Subcontract | 0 | 44606745 | 42411167
MCR028150 | HPR220 | 2024-01-01 | Overhead | 0 | 10366927 | 13288853
MCR028151 | HPR220 | 2024-02-01 | Labor | 0 | 5972183 | 6223210
MCR028152 | HPR220 | 2024-02-01 | Material | 0 | 15899364 | 14557057
MCR028153 | HPR220 | 2024-02-01 | Equipment | 0 | 3132621 | 3421121
MCR028154 | HPR220 | 2024-02-01 | Subcontract | 0 | 15236308 | 13913710
MCR028155 | HPR220 | 2024-02-01 | Overhead | 0 | 3541027 | 13994135
MCR028156 | HPR220 | 2024-03-01 | Labor | 0 | 10496744 | 11481917
MCR028157 | HPR220 | 2024-03-01 | Material | 0 | 27944818 | 21729131
MCR028158 | HPR220 | 2024-03-01 | Equipment | 0 | 5505913 | 6240286
MCR028159 | HPR220 | 2024-03-01 | Subcontract | 0 | 26779427 | 29104340
MCR028160 | HPR220 | 2024-03-01 | Overhead | 0 | 6223731 | 12747034
MCR028161 | HPR220 | 2024-04-01 | Labor | 0 | 3069220 | 2666081
MCR028162 | HPR220 | 2024-04-01 | Material | 0 | 8170991 | 9464385
MCR028163 | HPR220 | 2024-04-01 | Equipment | 0 | 1609915 | 1825617
MCR028164 | HPR220 | 2024-04-01 | Subcontract | 0 | 7830234 | 5498915
MCR028165 | HPR220 | 2024-04-01 | Overhead | 0 | 1819802 | 14269505
MCR028166 | HPR220 | 2024-05-01 | Labor | 0 | 861486 | 974031
MCR028167 | HPR220 | 2024-05-01 | Material | 0 | 2293480 | 2882905
MCR028168 | HPR220 | 2024-05-01 | Equipment | 0 | 451880 | 425070
MCR028169 | HPR220 | 2024-05-01 | Subcontract | 0 | 2197835 | 2021614
MCR028170 | HPR220 | 2024-05-01 | Overhead | 0 | 510792 | 13122625
MCR028171 | HPR221 | 2018-03-01 | Labor | 1316668 | 535660 | 660358
MCR028172 | HPR221 | 2018-03-01 | Material | 5358718 | 2180087 | 2264922
MCR028173 | HPR221 | 2018-03-01 | Equipment | 3247037 | 1320992 | 1389836
MCR028174 | HPR221 | 2018-03-01 | Subcontract | 2697530 | 1097436 | 1138574
MCR028175 | HPR221 | 2018-03-01 | Overhead | 1266195 | 515126 | 9150221
MCR028176 | HPR221 | 2018-04-01 | Labor | 3777587 | 2202614 | 2345588
MCR028177 | HPR221 | 2018-04-01 | Material | 15374436 | 8964438 | 8338097
MCR028178 | HPR221 | 2018-04-01 | Equipment | 9315913 | 5431870 | 5249582
MCR028179 | HPR221 | 2018-04-01 | Subcontract | 7739352 | 4512617 | 4691350
MCR028180 | HPR221 | 2018-04-01 | Overhead | 3632779 | 2118180 | 9571862
MCR028181 | HPR221 | 2018-05-01 | Labor | 5983300 | 5171201 | 6082594
MCR028182 | HPR221 | 2018-05-01 | Material | 24351485 | 21046316 | 21278015
MCR028183 | HPR221 | 2018-05-01 | Equipment | 14755425 | 12752706 | 13024812
MCR028184 | HPR221 | 2018-05-01 | Subcontract | 12258317 | 10594525 | 9665375
MCR028185 | HPR221 | 2018-05-01 | Overhead | 5753939 | 4972970 | 9230184
MCR028186 | HPR221 | 2018-06-01 | Labor | 7938502 | 6216520 | 7420017
MCR028187 | HPR221 | 2018-06-01 | Material | 32308980 | 25300670 | 24577954
MCR028188 | HPR221 | 2018-06-01 | Equipment | 19577151 | 15330569 | 15740589
MCR028189 | HPR221 | 2018-06-01 | Subcontract | 16264048 | 12736128 | 13575002
MCR028190 | HPR221 | 2018-06-01 | Overhead | 7634191 | 5978218 | 9868810
MCR028191 | HPR221 | 2018-07-01 | Labor | 9648076 | 3438647 | 3467816
MCR028192 | HPR221 | 2018-07-01 | Material | 39266789 | 13994982 | 13623804
MCR028193 | HPR221 | 2018-07-01 | Equipment | 23793134 | 8480053 | 9106784
MCR028194 | HPR221 | 2018-07-01 | Subcontract | 19766546 | 7044947 | 6689678
MCR028195 | HPR221 | 2018-07-01 | Overhead | 9278230 | 3306832 | 9660882
MCR028196 | HPR221 | 2018-08-01 | Labor | 11117107 | 4571747 | 4353848
MCR028197 | HPR221 | 2018-08-01 | Material | 45245614 | 18606595 | 18918301
MCR028198 | HPR221 | 2018-08-01 | Equipment | 27415915 | 11274393 | 11473374
MCR028199 | HPR221 | 2018-08-01 | Subcontract | 22776232 | 9366391 | 9897275
MCR028200 | HPR221 | 2018-08-01 | Overhead | 10690949 | 4396496 | 9459320
MCR028201 | HPR221 | 2018-09-01 | Labor | 12350907 | 5962395 | 7515585
MCR028202 | HPR221 | 2018-09-01 | Material | 50267065 | 24266404 | 23322545
MCR028203 | HPR221 | 2018-09-01 | Equipment | 30458589 | 14703871 | 14516466
MCR028204 | HPR221 | 2018-09-01 | Subcontract | 25303985 | 12215488 | 13050801
MCR028205 | HPR221 | 2018-09-01 | Overhead | 11877452 | 5733835 | 9672365
MCR028206 | HPR221 | 2018-10-01 | Labor | 13355031 | 18054758 | 19688510
MCR028207 | HPR221 | 2018-10-01 | Material | 54353760 | 73481219 | 81176364
MCR028208 | HPR221 | 2018-10-01 | Equipment | 32934862 | 44524865 | 44098535
MCR028209 | HPR221 | 2018-10-01 | Subcontract | 27361190 | 36989780 | 40662094
MCR028210 | HPR221 | 2018-10-01 | Overhead | 12843085 | 17362654 | 10168555
MCR028211 | HPR221 | 2018-11-01 | Labor | 14135312 | 9077667 | 10674857
MCR028212 | HPR221 | 2018-11-01 | Material | 57529432 | 36945280 | 31253944
MCR028213 | HPR221 | 2018-11-01 | Equipment | 34859114 | 22386449 | 21027529
MCR028214 | HPR221 | 2018-11-01 | Subcontract | 28959795 | 18597919 | 15683527
MCR028215 | HPR221 | 2018-11-01 | Overhead | 13593455 | 8729688 | 9554739
MCR028216 | HPR221 | 2018-12-01 | Labor | 14697888 | 10135520 | 12041982
MCR028217 | HPR221 | 2018-12-01 | Material | 59819064 | 41250645 | 41299167
MCR028218 | HPR221 | 2018-12-01 | Equipment | 36246483 | 24995222 | 29589819
MCR028219 | HPR221 | 2018-12-01 | Subcontract | 30112375 | 20765201 | 19418334
MCR028220 | HPR221 | 2018-12-01 | Overhead | 14134465 | 9746990 | 9522200
MCR028221 | HPR221 | 2019-01-01 | Labor | 15049241 | 8411317 | 8454266
MCR028222 | HPR221 | 2019-01-01 | Material | 61249041 | 34233293 | 39053621
MCR028223 | HPR221 | 2019-01-01 | Equipment | 37112956 | 20743161 | 20305270
MCR028224 | HPR221 | 2019-01-01 | Subcontract | 30832212 | 17232729 | 20927075
MCR028225 | HPR221 | 2019-01-01 | Overhead | 14472350 | 8088881 | 9387891
MCR028226 | HPR221 | 2019-02-01 | Labor | 15196245 | 8654316 | 11558462
MCR028227 | HPR221 | 2019-02-01 | Material | 61847335 | 35222278 | 32840333
MCR028228 | HPR221 | 2019-02-01 | Equipment | 37475484 | 21342422 | 21286244
MCR028229 | HPR221 | 2019-02-01 | Subcontract | 31133388 | 17730576 | 16105657
MCR028230 | HPR221 | 2019-02-01 | Overhead | 14613719 | 8322565 | 10030315
MCR028231 | HPR221 | 2019-03-01 | Labor | 15146219 | 19317820 | 22627353
MCR028232 | HPR221 | 2019-03-01 | Material | 61643732 | 78621767 | 79988992
MCR028233 | HPR221 | 2019-03-01 | Equipment | 37352114 | 47639704 | 50211170
MCR028234 | HPR221 | 2019-03-01 | Subcontract | 31030896 | 39577485 | 42040491
MCR028235 | HPR221 | 2019-03-01 | Overhead | 14565610 | 18577299 | 10095911
MCR028236 | HPR221 | 2019-04-01 | Labor | 14906994 | 11534983 | 14165301
MCR028237 | HPR221 | 2019-04-01 | Material | 60670107 | 46946332 | 47548246
MCR028238 | HPR221 | 2019-04-01 | Equipment | 36762160 | 28446440 | 31735075
MCR028239 | HPR221 | 2019-04-01 | Subcontract | 30540782 | 23632358 | 25054521
MCR028240 | HPR221 | 2019-04-01 | Overhead | 14335555 | 11092806 | 8869516
MCR028241 | HPR221 | 2019-05-01 | Labor | 14487000 | 15115744 | 18647311
MCR028242 | HPR221 | 2019-05-01 | Material | 58960769 | 61519702 | 58788103
MCR028243 | HPR221 | 2019-05-01 | Equipment | 35726412 | 37276959 | 45023756
MCR028244 | HPR221 | 2019-05-01 | Subcontract | 29680317 | 30968461 | 27653457
MCR028245 | HPR221 | 2019-05-01 | Overhead | 13931661 | 14536304 | 9102222
MCR028246 | HPR221 | 2019-06-01 | Labor | 13895371 | 8770601 | 9133527
MCR028247 | HPR221 | 2019-06-01 | Material | 56552895 | 35695549 | 41241185
MCR028248 | HPR221 | 2019-06-01 | Equipment | 34267396 | 21629193 | 17301670
MCR028249 | HPR221 | 2019-06-01 | Subcontract | 28468215 | 17968816 | 18302570
MCR028250 | HPR221 | 2019-06-01 | Overhead | 13362712 | 8434393 | 9651910
MCR028251 | HPR221 | 2019-07-01 | Labor | 13142087 | 9821520 | 11037311
MCR028252 | HPR221 | 2019-07-01 | Material | 53487097 | 39972694 | 43779118
MCR028253 | HPR221 | 2019-07-01 | Equipment | 32409720 | 24220866 | 25098767
MCR028254 | HPR221 | 2019-07-01 | Subcontract | 26924920 | 20121892 | 21878178
MCR028255 | HPR221 | 2019-07-01 | Overhead | 12638304 | 9445026 | 9154072
MCR028256 | HPR221 | 2019-08-01 | Labor | 12238151 | 8509899 | 10245961
MCR028257 | HPR221 | 2019-08-01 | Material | 49808159 | 34634513 | 34693618
MCR028258 | HPR221 | 2019-08-01 | Equipment | 30180522 | 20986274 | 20082652
MCR028259 | HPR221 | 2019-08-01 | Subcontract | 25072976 | 17434700 | 18328834
MCR028260 | HPR221 | 2019-08-01 | Overhead | 11769019 | 8183684 | 9277278
MCR028261 | HPR221 | 2019-09-01 | Labor | 11195840 | 15649983 | 15711947
MCR028262 | HPR221 | 2019-09-01 | Material | 45566050 | 63694008 | 63504670
MCR028263 | HPR221 | 2019-09-01 | Equipment | 27610078 | 38594448 | 44119847
MCR028264 | HPR221 | 2019-09-01 | Subcontract | 22937537 | 32062986 | 31953434
MCR028265 | HPR221 | 2019-09-01 | Overhead | 10766664 | 15050064 | 8224268
MCR028266 | HPR221 | 2019-10-01 | Labor | 10029053 | 11102271 | 14769562
MCR028267 | HPR221 | 2019-10-01 | Material | 40817331 | 45185233 | 52015255
MCR028268 | HPR221 | 2019-10-01 | Equipment | 24732662 | 27379328 | 25701933
MCR028269 | HPR221 | 2019-10-01 | Subcontract | 20547075 | 22745837 | 23938634
MCR028270 | HPR221 | 2019-10-01 | Overhead | 9644603 | 10676682 | 9171754
MCR028271 | HPR221 | 2019-11-01 | Labor | 8753810 | 11442343 | 14164835
MCR028272 | HPR221 | 2019-11-01 | Material | 35627210 | 46569293 | 42393256
MCR028273 | HPR221 | 2019-11-01 | Equipment | 21587784 | 28217979 | 25682712
MCR028274 | HPR221 | 2019-11-01 | Subcontract | 17934415 | 23442560 | 19088072
MCR028275 | HPR221 | 2019-11-01 | Overhead | 8418245 | 11003717 | 8558450
MCR028276 | HPR221 | 2019-12-01 | Labor | 7389030 | 8239740 | 9299124
MCR028277 | HPR221 | 2019-12-01 | Material | 30072678 | 33534992 | 36449085
MCR028278 | HPR221 | 2019-12-01 | Equipment | 18222097 | 20320035 | 22451396
MCR028279 | HPR221 | 2019-12-01 | Subcontract | 15138314 | 16881211 | 17951636
MCR028280 | HPR221 | 2019-12-01 | Overhead | 7105782 | 7923881 | 8940272
MCR028281 | HPR221 | 2020-01-01 | Labor | 5957785 | 8762984 | 9737066
MCR028282 | HPR221 | 2020-01-01 | Material | 24247644 | 35664546 | 36016113
MCR028283 | HPR221 | 2020-01-01 | Equipment | 14692504 | 21610407 | 23461413
MCR028284 | HPR221 | 2020-01-01 | Subcontract | 12206044 | 17953209 | 20769752
MCR028285 | HPR221 | 2020-01-01 | Overhead | 5729402 | 8427067 | 9696952
MCR028286 | HPR221 | 2020-02-01 | Labor | 4489554 | 12249429 | 14295124
MCR028287 | HPR221 | 2020-02-01 | Material | 18272077 | 49854060 | 53410227
MCR028288 | HPR221 | 2020-02-01 | Equipment | 11071697 | 30208335 | 28695045
MCR028289 | HPR221 | 2020-02-01 | Subcontract | 9197998 | 25096082 | 26487279
MCR028290 | HPR221 | 2020-02-01 | Overhead | 4317454 | 11779864 | 9517596
MCR028291 | HPR221 | 2020-03-01 | Labor | 3024783 | 6837885 | 7714914
MCR028292 | HPR221 | 2020-03-01 | Material | 12310591 | 27829570 | 26639853
MCR028293 | HPR221 | 2020-03-01 | Equipment | 7459422 | 16862919 | 17100077
MCR028294 | HPR221 | 2020-03-01 | Subcontract | 6197040 | 14009153 | 12902733
MCR028295 | HPR221 | 2020-03-01 | Overhead | 2908832 | 6575764 | 9065405
MCR028296 | HPR221 | 2020-04-01 | Labor | 1626399 | 6068455 | 6547305
MCR028297 | HPR221 | 2020-04-01 | Material | 6619297 | 24698058 | 29438049
MCR028298 | HPR221 | 2020-04-01 | Equipment | 4010866 | 14965425 | 16774850
MCR028299 | HPR221 | 2020-04-01 | Subcontract | 3332094 | 12432779 | 13755310
MCR028300 | HPR221 | 2020-04-01 | Overhead | 1564054 | 5835829 | 9392105
MCR028301 | HPR221 | 2020-05-01 | Labor | 428667 | 8129361 | 8884486
MCR028302 | HPR221 | 2020-05-01 | Material | 1744635 | 33085757 | 31906589
MCR028303 | HPR221 | 2020-05-01 | Equipment | 1057136 | 20047828 | 21931307
MCR028304 | HPR221 | 2020-05-01 | Subcontract | 878233 | 16655070 | 18029507
MCR028305 | HPR221 | 2020-05-01 | Overhead | 412234 | 7817733 | 8764700
MCR028306 | HPR221 | 2020-06-01 | Labor | 0 | 3260010 | 4018328
MCR028307 | HPR221 | 2020-06-01 | Material | 0 | 13267944 | 12039833
MCR028308 | HPR221 | 2020-06-01 | Equipment | 0 | 8039516 | 9020222
MCR028309 | HPR221 | 2020-06-01 | Subcontract | 0 | 6678963 | 6424507
MCR028310 | HPR221 | 2020-06-01 | Overhead | 0 | 3135042 | 8460524
MCR028311 | HPR221 | 2020-07-01 | Labor | 0 | 2398578 | 3060847
MCR028312 | HPR221 | 2020-07-01 | Material | 0 | 9761995 | 11632549
MCR028313 | HPR221 | 2020-07-01 | Equipment | 0 | 5915137 | 5142648
MCR028314 | HPR221 | 2020-07-01 | Subcontract | 0 | 4914100 | 4488817
MCR028315 | HPR221 | 2020-07-01 | Overhead | 0 | 2306632 | 9266288
MCR028316 | HPR221 | 2020-08-01 | Labor | 0 | 1971740 | 2363802
MCR028317 | HPR221 | 2020-08-01 | Material | 0 | 8024801 | 7311909
MCR028318 | HPR221 | 2020-08-01 | Equipment | 0 | 4862510 | 5141379
MCR028319 | HPR221 | 2020-08-01 | Subcontract | 0 | 4039612 | 3853553
MCR028320 | HPR221 | 2020-08-01 | Overhead | 0 | 1896156 | 9322099
MCR028321 | HPR221 | 2020-09-01 | Labor | 0 | 3853788 | 3971343
MCR028322 | HPR221 | 2020-09-01 | Material | 0 | 15684565 | 16952565
MCR028323 | HPR221 | 2020-09-01 | Equipment | 0 | 9503831 | 11691436
MCR028324 | HPR221 | 2020-09-01 | Subcontract | 0 | 7895468 | 8311185
MCR028325 | HPR221 | 2020-09-01 | Overhead | 0 | 3706058 | 9242901
MCR028326 | HPR221 | 2020-10-01 | Labor | 0 | 3571227 | 4478010
MCR028327 | HPR221 | 2020-10-01 | Material | 0 | 14534569 | 13895490
MCR028328 | HPR221 | 2020-10-01 | Equipment | 0 | 8807008 | 9320906
MCR028329 | HPR221 | 2020-10-01 | Subcontract | 0 | 7316570 | 6658321
MCR028330 | HPR221 | 2020-10-01 | Overhead | 0 | 3434329 | 9428293
MCR028331 | HPR221 | 2020-11-01 | Labor | 0 | 951507 | 1009710
MCR028332 | HPR221 | 2020-11-01 | Material | 0 | 3872545 | 4199798
MCR028333 | HPR221 | 2020-11-01 | Equipment | 0 | 2346512 | 2581486
MCR028334 | HPR221 | 2020-11-01 | Subcontract | 0 | 1949404 | 2158112
MCR028335 | HPR221 | 2020-11-01 | Overhead | 0 | 915032 | 9045621
MCR028336 | HPR221 | 2020-12-01 | Labor | 0 | 1050725 | 1138783
MCR028337 | HPR221 | 2020-12-01 | Material | 0 | 4276354 | 4634665
MCR028338 | HPR221 | 2020-12-01 | Equipment | 0 | 2591194 | 3172297
MCR028339 | HPR221 | 2020-12-01 | Subcontract | 0 | 2152678 | 2105494
MCR028340 | HPR221 | 2020-12-01 | Overhead | 0 | 1010447 | 8846583
MCR028341 | HPR221 | 2021-01-01 | Labor | 0 | 233652 | 317265
MCR028342 | HPR221 | 2021-01-01 | Material | 0 | 950942 | 963482
MCR028343 | HPR221 | 2021-01-01 | Equipment | 0 | 576209 | 529123
MCR028344 | HPR221 | 2021-01-01 | Subcontract | 0 | 478695 | 548999
MCR028345 | HPR221 | 2021-01-01 | Overhead | 0 | 224695 | 9752996
MCR028346 | HPR222 | 2020-12-01 | Labor | 5435086 | 4854539 | 4581890
MCR028347 | HPR222 | 2020-12-01 | Material | 25931165 | 23161338 | 21355871
MCR028348 | HPR222 | 2020-12-01 | Equipment | 11976474 | 10697211 | 9837858
MCR028349 | HPR222 | 2020-12-01 | Subcontract | 13307203 | 11885799 | 10963602
MCR028350 | HPR222 | 2020-12-01 | Overhead | 5405089 | 4827747 | 27045651
MCR028351 | HPR222 | 2021-01-01 | Labor | 15161606 | 12170016 | 12658950
MCR028352 | HPR222 | 2021-01-01 | Material | 72337061 | 58063980 | 58202929
MCR028353 | HPR222 | 2021-01-01 | Equipment | 33409332 | 26817219 | 27438455
MCR028354 | HPR222 | 2021-01-01 | Subcontract | 37121508 | 29796932 | 27979082
MCR028355 | HPR222 | 2021-01-01 | Overhead | 15077929 | 12102849 | 24425450
MCR028356 | HPR222 | 2021-02-01 | Labor | 23209927 | 14552488 | 13714559
MCR028357 | HPR222 | 2021-02-01 | Material | 110736153 | 69430918 | 65411646
MCR028358 | HPR222 | 2021-02-01 | Equipment | 51144197 | 32067112 | 29757014
MCR028359 | HPR222 | 2021-02-01 | Subcontract | 56826929 | 35630151 | 33788181
MCR028360 | HPR222 | 2021-02-01 | Overhead | 23081831 | 14472173 | 24895014
MCR028361 | HPR222 | 2021-03-01 | Labor | 29632303 | 20234558 | 23960931
MCR028362 | HPR222 | 2021-03-01 | Material | 141377749 | 96540465 | 110219320
MCR028363 | HPR222 | 2021-03-01 | Equipment | 65296213 | 44587828 | 41134323
MCR028364 | HPR222 | 2021-03-01 | Subcontract | 72551403 | 49542069 | 42191089
MCR028365 | HPR222 | 2021-03-01 | Overhead | 29468762 | 20122884 | 25548515
MCR028366 | HPR222 | 2021-04-01 | Labor | 34484592 | 31709580 | 32261682
MCR028367 | HPR222 | 2021-04-01 | Material | 164528351 | 151288580 | 138966941
MCR028368 | HPR222 | 2021-04-01 | Equipment | 75988466 | 69873594 | 71796112
MCR028369 | HPR222 | 2021-04-01 | Subcontract | 84431693 | 77637385 | 67367696
MCR028370 | HPR222 | 2021-04-01 | Overhead | 34294271 | 31534575 | 25625594
MCR028371 | HPR222 | 2021-05-01 | Labor | 37826868 | 37636941 | 33196528
MCR028372 | HPR222 | 2021-05-01 | Material | 180474579 | 179568423 | 194592233
MCR028373 | HPR222 | 2021-05-01 | Equipment | 83353333 | 82934819 | 81432669
MCR028374 | HPR222 | 2021-05-01 | Subcontract | 92614884 | 92149868 | 97118802
MCR028375 | HPR222 | 2021-05-01 | Overhead | 37618101 | 37429222 | 25969642
MCR028376 | HPR222 | 2021-06-01 | Labor | 39724203 | 40048694 | 40314875
MCR028377 | HPR222 | 2021-06-01 | Material | 189526895 | 191075065 | 195787989
MCR028378 | HPR222 | 2021-06-01 | Equipment | 87534203 | 88249235 | 90534807
MCR028379 | HPR222 | 2021-06-01 | Subcontract | 97260299 | 98054780 | 81776374
MCR028380 | HPR222 | 2021-06-01 | Overhead | 39504965 | 39827665 | 25410994
MCR028381 | HPR222 | 2021-07-01 | Labor | 40247692 | 19054533 | 19968557
MCR028382 | HPR222 | 2021-07-01 | Material | 192024496 | 90910481 | 83392523
MCR028383 | HPR222 | 2021-07-01 | Equipment | 88687736 | 41987584 | 39311026
MCR028384 | HPR222 | 2021-07-01 | Subcontract | 98542003 | 46652907 | 55134308
MCR028385 | HPR222 | 2021-07-01 | Overhead | 40025565 | 18949371 | 26543337
MCR028386 | HPR222 | 2021-08-01 | Labor | 39475827 | 33836687 | 27962868
MCR028387 | HPR222 | 2021-08-01 | Material | 188341874 | 161437155 | 181661076
MCR028388 | HPR222 | 2021-08-01 | Equipment | 86986893 | 74560777 | 68889009
MCR028389 | HPR222 | 2021-08-01 | Subcontract | 96652176 | 82845371 | 76160660
MCR028390 | HPR222 | 2021-08-01 | Overhead | 39257959 | 33649943 | 22376638
MCR028391 | HPR222 | 2021-09-01 | Labor | 37496406 | 31796738 | 28785108
MCR028392 | HPR222 | 2021-09-01 | Material | 178897924 | 151704413 | 159922072
MCR028393 | HPR222 | 2021-09-01 | Equipment | 82625145 | 70065649 | 81315979
MCR028394 | HPR222 | 2021-09-01 | Subcontract | 91805786 | 77850780 | 68157560
MCR028395 | HPR222 | 2021-09-01 | Overhead | 37289463 | 31621251 | 23363800
MCR028396 | HPR222 | 2021-10-01 | Labor | 34409287 | 41318266 | 39525525
MCR028397 | HPR222 | 2021-10-01 | Material | 164169067 | 197132280 | 168310329
MCR028398 | HPR222 | 2021-10-01 | Equipment | 75822528 | 91046798 | 90759317
MCR028399 | HPR222 | 2021-10-01 | Subcontract | 84247317 | 101163185 | 106173416
MCR028400 | HPR222 | 2021-10-01 | Overhead | 34219382 | 41090230 | 24243333
MCR028401 | HPR222 | 2021-11-01 | Labor | 30330546 | 24602809 | 26024312
MCR028402 | HPR222 | 2021-11-01 | Material | 144709114 | 117381686 | 133271451
MCR028403 | HPR222 | 2021-11-01 | Equipment | 66834825 | 54213479 | 58021680
MCR028404 | HPR222 | 2021-11-01 | Subcontract | 74260973 | 60237244 | 50289861
MCR028405 | HPR222 | 2021-11-01 | Overhead | 30163152 | 24467026 | 26269386
MCR028406 | HPR222 | 2021-12-01 | Labor | 25399202 | 33863031 | 37703749
MCR028407 | HPR222 | 2021-12-01 | Material | 121181333 | 161562841 | 161410663
MCR028408 | HPR222 | 2021-12-01 | Equipment | 55968370 | 74618826 | 81628613
MCR028409 | HPR222 | 2021-12-01 | Subcontract | 62187125 | 82909869 | 77027266
MCR028410 | HPR222 | 2021-12-01 | Overhead | 25259024 | 33676141 | 25761910
MCR028411 | HPR222 | 2022-01-01 | Labor | 19789054 | 11152322 | 6826868
MCR028412 | HPR222 | 2022-01-01 | Material | 94414931 | 53208491 | 64114815
MCR028413 | HPR222 | 2022-01-01 | Equipment | 43606137 | 24574680 | 18211687
MCR028414 | HPR222 | 2022-01-01 | Subcontract | 48451300 | 27305221 | 22241725
MCR028415 | HPR222 | 2022-01-01 | Overhead | 19679838 | 11090772 | 24250919
MCR028416 | HPR222 | 2022-02-01 | Labor | 13732404 | 19909203 | 19808542
MCR028417 | HPR222 | 2022-02-01 | Material | 65518240 | 94988172 | 114125754
MCR028418 | HPR222 | 2022-02-01 | Equipment | 30260016 | 43870892 | 53817029
MCR028419 | HPR222 | 2022-02-01 | Subcontract | 33622266 | 48745472 | 41731405
MCR028420 | HPR222 | 2022-02-01 | Overhead | 13656615 | 19799324 | 25319700
MCR028421 | HPR222 | 2022-03-01 | Labor | 7578957 | 24818494 | 24107991
MCR028422 | HPR222 | 2022-03-01 | Material | 36159723 | 118410737 | 118804170
MCR028423 | HPR222 | 2022-03-01 | Equipment | 16700598 | 54688753 | 50198292
MCR028424 | HPR222 | 2022-03-01 | Subcontract | 18556234 | 60765326 | 56919581
MCR028425 | HPR222 | 2022-03-01 | Overhead | 7537129 | 24681521 | 25328166
MCR028426 | HPR222 | 2022-04-01 | Labor | 2040619 | 18933616 | 17879221
MCR028427 | HPR222 | 2022-04-01 | Material | 9735935 | 90333579 | 96554168
MCR028428 | HPR222 | 2022-04-01 | Equipment | 4496603 | 41721139 | 41481495
MCR028429 | HPR222 | 2022-04-01 | Subcontract | 4996230 | 46356855 | 45835477
MCR028430 | HPR222 | 2022-04-01 | Overhead | 2029357 | 18829121 | 25260733
MCR028431 | HPR222 | 2022-05-01 | Labor | 0 | 10916652 | 9665509
MCR028432 | HPR222 | 2022-05-01 | Material | 0 | 52084097 | 51810734
MCR028433 | HPR222 | 2022-05-01 | Equipment | 0 | 24055372 | 21680749
MCR028434 | HPR222 | 2022-05-01 | Subcontract | 0 | 26728211 | 25351466
MCR028435 | HPR222 | 2022-05-01 | Overhead | 0 | 10856403 | 24768247
MCR028436 | HPR222 | 2022-06-01 | Labor | 0 | 3805896 | 4335357
MCR028437 | HPR222 | 2022-06-01 | Material | 0 | 18158189 | 15555075
MCR028438 | HPR222 | 2022-06-01 | Equipment | 0 | 8386475 | 9935748
MCR028439 | HPR222 | 2022-06-01 | Subcontract | 0 | 9318313 | 8118622
MCR028440 | HPR222 | 2022-06-01 | Overhead | 0 | 3784891 | 25353734
MCR028441 | HPR222 | 2022-07-01 | Labor | 0 | 759516 | 901071
MCR028442 | HPR222 | 2022-07-01 | Material | 0 | 3623701 | 4154287
MCR028443 | HPR222 | 2022-07-01 | Equipment | 0 | 1673629 | 1638157
MCR028444 | HPR222 | 2022-07-01 | Subcontract | 0 | 1859589 | 2164083
MCR028445 | HPR222 | 2022-07-01 | Overhead | 0 | 755324 | 26598071
MCR028446 | HPR223 | 2022-03-01 | Labor | 6456639 | 3447950 | 3628336
MCR028447 | HPR223 | 2022-03-01 | Material | 13280421 | 7091961 | 7850100
MCR028448 | HPR223 | 2022-03-01 | Equipment | 2989740 | 1596570 | 1723790
MCR028449 | HPR223 | 2022-03-01 | Subcontract | 24925105 | 13310411 | 14637473
MCR028450 | HPR223 | 2022-03-01 | Overhead | 4347811 | 2321802 | 20296282
MCR028451 | HPR223 | 2022-04-01 | Labor | 18089040 | 5205837 | 6459611
MCR028452 | HPR223 | 2022-04-01 | Material | 37206671 | 10707693 | 10529873
MCR028453 | HPR223 | 2022-04-01 | Equipment | 8376110 | 2410557 | 2454310
MCR028454 | HPR223 | 2022-04-01 | Subcontract | 69830634 | 20096530 | 20539006
MCR028455 | HPR223 | 2022-04-01 | Overhead | 12180908 | 3505538 | 20128475
MCR028456 | HPR223 | 2022-05-01 | Labor | 27839345 | 11022620 | 10865450
MCR028457 | HPR223 | 2022-05-01 | Material | 57261712 | 22672015 | 23213483
MCR028458 | HPR223 | 2022-05-01 | Equipment | 12890978 | 5104012 | 5831107
MCR028459 | HPR223 | 2022-05-01 | Subcontract | 107470555 | 42551541 | 49499110
MCR028460 | HPR223 | 2022-05-01 | Overhead | 18746628 | 7422479 | 21702537
MCR028461 | HPR223 | 2022-06-01 | Labor | 35762365 | 9545844 | 10155078
MCR028462 | HPR223 | 2022-06-01 | Material | 73558275 | 19634490 | 21729644
MCR028463 | HPR223 | 2022-06-01 | Equipment | 16559723 | 4420192 | 4539727
MCR028464 | HPR223 | 2022-06-01 | Subcontract | 138056450 | 36850618 | 37204562
MCR028465 | HPR223 | 2022-06-01 | Overhead | 24081879 | 6428038 | 22188379
MCR028466 | HPR223 | 2022-07-01 | Labor | 41916427 | 17660113 | 22208574
MCR028467 | HPR223 | 2022-07-01 | Material | 86216335 | 36324428 | 38843313
MCR028468 | HPR223 | 2022-07-01 | Equipment | 19409355 | 8177496 | 8485804
MCR028469 | HPR223 | 2022-07-01 | Subcontract | 161813489 | 68174813 | 78360756
MCR028470 | HPR223 | 2022-07-01 | Overhead | 28225938 | 11892074 | 23879282
MCR028471 | HPR223 | 2022-08-01 | Labor | 46363932 | 13038825 | 13246810
MCR028472 | HPR223 | 2022-08-01 | Material | 95364244 | 26819073 | 25286726
MCR028473 | HPR223 | 2022-08-01 | Equipment | 21468767 | 6037613 | 6401274
MCR028474 | HPR223 | 2022-08-01 | Subcontract | 178982567 | 50334867 | 42820606
MCR028475 | HPR223 | 2022-08-01 | Overhead | 31220827 | 8780163 | 22318578
MCR028476 | HPR223 | 2022-09-01 | Labor | 49172051 | 28449543 | 31003344
MCR028477 | HPR223 | 2022-09-01 | Material | 101140159 | 58516805 | 54903703
MCR028478 | HPR223 | 2022-09-01 | Equipment | 22769064 | 13173529 | 14853732
MCR028479 | HPR223 | 2022-09-01 | Subcontract | 189822984 | 109826153 | 113007461
MCR028480 | HPR223 | 2022-09-01 | Overhead | 33111775 | 19157527 | 19708801
MCR028481 | HPR223 | 2022-10-01 | Labor | 50413611 | 37885519 | 42930595
MCR028482 | HPR223 | 2022-10-01 | Material | 103693877 | 77925311 | 84201232
MCR028483 | HPR223 | 2022-10-01 | Equipment | 23343966 | 17542847 | 19449308
MCR028484 | HPR223 | 2022-10-01 | Subcontract | 194615882 | 146252639 | 152669845
MCR028485 | HPR223 | 2022-10-01 | Overhead | 33947824 | 25511581 | 21267040
MCR028486 | HPR223 | 2022-11-01 | Labor | 50168267 | 18233317 | 21782718
MCR028487 | HPR223 | 2022-11-01 | Material | 103189237 | 37503431 | 34307600
MCR028488 | HPR223 | 2022-11-01 | Equipment | 23230360 | 8442917 | 8547471
MCR028489 | HPR223 | 2022-11-01 | Subcontract | 193668757 | 70387601 | 79964466
MCR028490 | HPR223 | 2022-11-01 | Overhead | 33782612 | 12278062 | 22934357
MCR028491 | HPR223 | 2022-12-01 | Labor | 48524069 | 35703725 | 39089568
MCR028492 | HPR223 | 2022-12-01 | Material | 99807348 | 73437660 | 88992858
MCR028493 | HPR223 | 2022-12-01 | Equipment | 22469016 | 16532570 | 17854061
MCR028494 | HPR223 | 2022-12-01 | Subcontract | 187321523 | 137830076 | 153408729
MCR028495 | HPR223 | 2022-12-01 | Overhead | 32675432 | 24042391 | 19848941
MCR028496 | HPR223 | 2023-01-01 | Labor | 45579648 | 35105515 | 41666432
MCR028497 | HPR223 | 2023-01-01 | Material | 93751079 | 72207224 | 70871155
MCR028498 | HPR223 | 2023-01-01 | Equipment | 21105605 | 16255569 | 17068665
MCR028499 | HPR223 | 2023-01-01 | Subcontract | 175954931 | 135520756 | 149616526
MCR028500 | HPR223 | 2023-01-01 | Overhead | 30692701 | 23639565 | 21655096
MCR028501 | HPR223 | 2023-02-01 | Labor | 41447362 | 22457019 | 23624423
MCR028502 | HPR223 | 2023-02-01 | Material | 85251534 | 46191005 | 38307693
MCR028503 | HPR223 | 2023-02-01 | Equipment | 19192155 | 10398698 | 9542504
MCR028504 | HPR223 | 2023-02-01 | Subcontract | 160002720 | 86692709 | 85078189
MCR028505 | HPR223 | 2023-02-01 | Overhead | 27910077 | 15122244 | 22063041
MCR028506 | HPR223 | 2023-03-01 | Labor | 36258067 | 37670879 | 49588212
MCR028507 | HPR223 | 2023-03-01 | Material | 74577865 | 77483827 | 71927857
MCR028508 | HPR223 | 2023-03-01 | Equipment | 16789257 | 17443459 | 20282734
MCR028509 | HPR223 | 2023-03-01 | Subcontract | 139970048 | 145424048 | 157399709
MCR028510 | HPR223 | 2023-03-01 | Overhead | 24415677 | 25367046 | 24254173
MCR028511 | HPR223 | 2023-04-01 | Labor | 30168833 | 47187584 | 49033554
MCR028512 | HPR223 | 2023-04-01 | Material | 62053147 | 97058382 | 110711429
MCR028513 | HPR223 | 2023-04-01 | Equipment | 13969644 | 21850158 | 26568470
MCR028514 | HPR223 | 2023-04-01 | Subcontract | 116463270 | 182162178 | 207739972
MCR028515 | HPR223 | 2023-04-01 | Overhead | 20315272 | 31775462 | 20729844
MCR028516 | HPR223 | 2023-05-01 | Labor | 23376562 | 37917587 | 49695403
MCR028517 | HPR223 | 2023-05-01 | Material | 48082378 | 77991271 | 71070638
MCR028518 | HPR223 | 2023-05-01 | Equipment | 10824491 | 17557697 | 18294464
MCR028519 | HPR223 | 2023-05-01 | Subcontract | 90242498 | 146376435 | 131442619
MCR028520 | HPR223 | 2023-05-01 | Overhead | 15741451 | 25533175 | 21784520
MCR028521 | HPR223 | 2023-06-01 | Labor | 16145319 | 40172336 | 40837873
MCR028522 | HPR223 | 2023-06-01 | Material | 33208704 | 82628980 | 73930053
MCR028523 | HPR223 | 2023-06-01 | Equipment | 7476072 | 18601755 | 18485891
MCR028524 | HPR223 | 2023-06-01 | Subcontract | 62327125 | 155080629 | 187312293
MCR028525 | HPR223 | 2023-06-01 | Overhead | 10872033 | 27051492 | 22568346
MCR028526 | HPR223 | 2023-07-01 | Labor | 8874346 | 21210843 | 23951591
MCR028527 | HPR223 | 2023-07-01 | Material | 18253312 | 43627792 | 48609513
MCR028528 | HPR223 | 2023-07-01 | Equipment | 4109256 | 9821657 | 10792461
MCR028529 | HPR223 | 2023-07-01 | Subcontract | 34258382 | 81881992 | 72467085
MCR028530 | HPR223 | 2023-07-01 | Overhead | 5975861 | 14283086 | 21757358
MCR028531 | HPR223 | 2023-08-01 | Labor | 2381598 | 41364267 | 44148438
MCR028532 | HPR223 | 2023-08-01 | Material | 4898621 | 85080618 | 86333388
MCR028533 | HPR223 | 2023-08-01 | Equipment | 1102796 | 19153678 | 18954227
MCR028534 | HPR223 | 2023-08-01 | Subcontract | 9193883 | 159681941 | 228843104
MCR028535 | HPR223 | 2023-08-01 | Overhead | 1603735 | 27854122 | 20751884
MCR028536 | HPR223 | 2023-09-01 | Labor | 0 | 21499876 | 23830103
MCR028537 | HPR223 | 2023-09-01 | Material | 0 | 44222293 | 41282745
MCR028538 | HPR223 | 2023-09-01 | Equipment | 0 | 9955494 | 11829194
MCR028539 | HPR223 | 2023-09-01 | Subcontract | 0 | 82997769 | 108754257
MCR028540 | HPR223 | 2023-09-01 | Overhead | 0 | 14477717 | 22000223
MCR028541 | HPR223 | 2023-10-01 | Labor | 0 | 26304142 | 32057397
MCR028542 | HPR223 | 2023-10-01 | Material | 0 | 54104009 | 54067326
MCR028543 | HPR223 | 2023-10-01 | Equipment | 0 | 12180104 | 11848790
MCR028544 | HPR223 | 2023-10-01 | Subcontract | 0 | 101544081 | 167391173
MCR028545 | HPR223 | 2023-10-01 | Overhead | 0 | 17712843 | 20451696
MCR028546 | HPR223 | 2023-11-01 | Labor | 0 | 18996119 | 18902159
MCR028547 | HPR223 | 2023-11-01 | Material | 0 | 39072409 | 44724916
MCR028548 | HPR223 | 2023-11-01 | Equipment | 0 | 8796132 | 11142463
MCR028549 | HPR223 | 2023-11-01 | Subcontract | 0 | 73332309 | 105173310
MCR028550 | HPR223 | 2023-11-01 | Overhead | 0 | 12791722 | 20904105
MCR028551 | HPR223 | 2023-12-01 | Labor | 0 | 25414539 | 30026479
MCR028552 | HPR223 | 2023-12-01 | Material | 0 | 52274217 | 44745662
MCR028553 | HPR223 | 2023-12-01 | Equipment | 0 | 11768174 | 13542235
MCR028554 | HPR223 | 2023-12-01 | Subcontract | 0 | 98109870 | 134659163
MCR028555 | HPR223 | 2023-12-01 | Overhead | 0 | 17113796 | 21138561
MCR028556 | HPR223 | 2024-01-01 | Labor | 0 | 10890645 | 11346852
MCR028557 | HPR223 | 2024-01-01 | Material | 0 | 22400561 | 23024726
MCR028558 | HPR223 | 2024-01-01 | Equipment | 0 | 5042901 | 5732098
MCR028559 | HPR223 | 2024-01-01 | Subcontract | 0 | 42042067 | 81293134
MCR028560 | HPR223 | 2024-01-01 | Overhead | 0 | 7333608 | 20876698
MCR028561 | HPR223 | 2024-02-01 | Labor | 0 | 7703652 | 9889931
MCR028562 | HPR223 | 2024-02-01 | Material | 0 | 15845354 | 16773457
MCR028563 | HPR223 | 2024-02-01 | Equipment | 0 | 3567167 | 4279537
MCR028564 | HPR223 | 2024-02-01 | Subcontract | 0 | 29739052 | 60602797
MCR028565 | HPR223 | 2024-02-01 | Overhead | 0 | 5187532 | 21516340
MCR028566 | HPR223 | 2024-03-01 | Labor | 0 | 3990808 | 3172109
MCR028567 | HPR223 | 2024-03-01 | Material | 0 | 8208543 | 9063325
MCR028568 | HPR223 | 2024-03-01 | Equipment | 0 | 1847939 | 2603124
MCR028569 | HPR223 | 2024-03-01 | Subcontract | 0 | 15406048 | 68125545
MCR028570 | HPR223 | 2024-03-01 | Overhead | 0 | 2687354 | 21490988
MCR028571 | HPR223 | 2024-04-01 | Labor | 0 | 858378 | 981969
MCR028572 | HPR223 | 2024-04-01 | Material | 0 | 1765567 | 1396650
MCR028573 | HPR223 | 2024-04-01 | Equipment | 0 | 397471 | 418367
MCR028574 | HPR223 | 2024-04-01 | Subcontract | 0 | 3313670 | 66475888
MCR028575 | HPR223 | 2024-04-01 | Overhead | 0 | 578020 | 22198940
MCR028576 | HPR224 | 2016-03-01 | Labor | 2412430 | 879013 | 1027598
MCR028577 | HPR224 | 2016-03-01 | Material | 4451717 | 1622065 | 1659233
MCR028578 | HPR224 | 2016-03-01 | Equipment | 1009526 | 367839 | 389280
MCR028579 | HPR224 | 2016-03-01 | Subcontract | 7048942 | 2568412 | 2927526
MCR028580 | HPR224 | 2016-03-01 | Overhead | 1466211 | 534241 | 12239144
MCR028581 | HPR224 | 2016-04-01 | Labor | 6943571 | 4163601 | 4248547
MCR028582 | HPR224 | 2016-04-01 | Material | 12813145 | 7683196 | 7069099
MCR028583 | HPR224 | 2016-04-01 | Equipment | 2905666 | 1742336 | 1723341
MCR028584 | HPR224 | 2016-04-01 | Subcontract | 20288602 | 12165734 | 13290593
MCR028585 | HPR224 | 2016-04-01 | Overhead | 4220119 | 2530527 | 11150347
MCR028586 | HPR224 | 2016-05-01 | Labor | 11039535 | 6239466 | 6297471
MCR028587 | HPR224 | 2016-05-01 | Material | 20371531 | 11513843 | 11617728
MCR028588 | HPR224 | 2016-05-01 | Equipment | 4619698 | 2611020 | 2858282
MCR028589 | HPR224 | 2016-05-01 | Subcontract | 32256708 | 18231259 | 18200678
MCR028590 | HPR224 | 2016-05-01 | Overhead | 6709538 | 3792183 | 11588280
MCR028591 | HPR224 | 2016-06-01 | Labor | 14707725 | 13477333 | 14291602
MCR028592 | HPR224 | 2016-06-01 | Material | 27140533 | 24870060 | 19981323
MCR028593 | HPR224 | 2016-06-01 | Equipment | 6154720 | 5639840 | 5767025
MCR028594 | HPR224 | 2016-06-01 | Subcontract | 42974888 | 39379773 | 39080008
MCR028595 | HPR224 | 2016-06-01 | Overhead | 8938967 | 8191167 | 11122027
MCR028596 | HPR224 | 2016-07-01 | Labor | 17955813 | 6219980 | 7041308
MCR028597 | HPR224 | 2016-07-01 | Material | 33134311 | 11477885 | 16223827
MCR028598 | HPR224 | 2016-07-01 | Equipment | 7513943 | 2602866 | 2564538
MCR028599 | HPR224 | 2016-07-01 | Subcontract | 52465561 | 18174323 | 18048305
MCR028600 | HPR224 | 2016-07-01 | Overhead | 10913069 | 3780340 | 10315080
MCR028601 | HPR224 | 2016-08-01 | Labor | 20791765 | 5867885 | 7954354
MCR028602 | HPR224 | 2016-08-01 | Material | 38367565 | 10828154 | 9771420
MCR028603 | HPR224 | 2016-08-01 | Equipment | 8700700 | 2455525 | 2509029
MCR028604 | HPR224 | 2016-08-01 | Subcontract | 60752005 | 17145526 | 19975108
MCR028605 | HPR224 | 2016-08-01 | Overhead | 12636686 | 3566345 | 11926621
MCR028606 | HPR224 | 2016-09-01 | Labor | 23223870 | 10178992 | 11193593
MCR028607 | HPR224 | 2016-09-01 | Material | 42855589 | 18783549 | 20423040
MCR028608 | HPR224 | 2016-09-01 | Equipment | 9718459 | 4259588 | 4701011
MCR028609 | HPR224 | 2016-09-01 | Subcontract | 67858436 | 29742264 | 28673678
MCR028610 | HPR224 | 2016-09-01 | Overhead | 14114855 | 6186523 | 11878085
MCR028611 | HPR224 | 2016-10-01 | Labor | 25260765 | 8793944 | 8846228
MCR028612 | HPR224 | 2016-10-01 | Material | 46614322 | 16227685 | 15041224
MCR028613 | HPR224 | 2016-10-01 | Equipment | 10570836 | 3679989 | 3561751
MCR028614 | HPR224 | 2016-10-01 | Subcontract | 73810092 | 25695256 | 29829752
MCR028615 | HPR224 | 2016-10-01 | Overhead | 15352826 | 5344727 | 10653554
MCR028616 | HPR224 | 2016-11-01 | Labor | 26911474 | 17953635 | 21390858
MCR028617 | HPR224 | 2016-11-01 | Material | 49660417 | 33130293 | 34113877
MCR028618 | HPR224 | 2016-11-01 | Equipment | 11261606 | 7513032 | 7472022
MCR028619 | HPR224 | 2016-11-01 | Subcontract | 78633343 | 52459199 | 51106510
MCR028620 | HPR224 | 2016-11-01 | Overhead | 16356084 | 10911746 | 10611667
MCR028621 | HPR224 | 2016-12-01 | Labor | 28185449 | 31881880 | 39959001
MCR028622 | HPR224 | 2016-12-01 | Material | 52011315 | 58832431 | 58855122
MCR028623 | HPR224 | 2016-12-01 | Equipment | 11794724 | 13341564 | 15544879
MCR028624 | HPR224 | 2016-12-01 | Subcontract | 82355803 | 93156501 | 100059816
MCR028625 | HPR224 | 2016-12-01 | Overhead | 17130372 | 19376965 | 11242441
MCR028626 | HPR224 | 2017-01-01 | Labor | 29092613 | 11717528 | 9836562
MCR028627 | HPR224 | 2017-01-01 | Material | 53685328 | 21622649 | 19448101
MCR028628 | HPR224 | 2017-01-01 | Equipment | 12174344 | 4903417 | 3928859
MCR028629 | HPR224 | 2017-01-01 | Subcontract | 85006471 | 34237754 | 35752988
MCR028630 | HPR224 | 2017-01-01 | Overhead | 17681723 | 7121605 | 11566717
MCR028631 | HPR224 | 2017-02-01 | Labor | 29643423 | 40027436 | 48073533
MCR028632 | HPR224 | 2017-02-01 | Material | 54701750 | 73863630 | 82960148
MCR028633 | HPR224 | 2017-02-01 | Equipment | 12404840 | 16750223 | 17008613
MCR028634 | HPR224 | 2017-02-01 | Subcontract | 86615895 | 116957216 | 138254239
MCR028635 | HPR224 | 2017-02-01 | Overhead | 18016490 | 24327619 | 12319730
MCR028636 | HPR224 | 2017-03-01 | Labor | 29848928 | 27129169 | 31303293
MCR028637 | HPR224 | 2017-03-01 | Material | 55080974 | 50062136 | 38525205
MCR028638 | HPR224 | 2017-03-01 | Equipment | 12490838 | 11352704 | 11607177
MCR028639 | HPR224 | 2017-03-01 | Subcontract | 87216366 | 79269433 | 75632639
MCR028640 | HPR224 | 2017-03-01 | Overhead | 18141391 | 16488393 | 11904207
MCR028641 | HPR224 | 2017-04-01 | Labor | 29720855 | 21823850 | 25181374
MCR028642 | HPR224 | 2017-04-01 | Material | 54844638 | 40272097 | 44440587
MCR028643 | HPR224 | 2017-04-01 | Equipment | 12437243 | 9132595 | 9545212
MCR028644 | HPR224 | 2017-04-01 | Subcontract | 86842146 | 63767681 | 70589849
MCR028645 | HPR224 | 2017-04-01 | Overhead | 18063551 | 13263960 | 11951858
MCR028646 | HPR224 | 2017-05-01 | Labor | 29271703 | 16760076 | 19545018
MCR028647 | HPR224 | 2017-05-01 | Material | 54015807 | 30927788 | 28940614
MCR028648 | HPR224 | 2017-05-01 | Equipment | 12249287 | 7013565 | 7837480
MCR028649 | HPR224 | 2017-05-01 | Subcontract | 85529758 | 48971706 | 47050422
MCR028650 | HPR224 | 2017-05-01 | Overhead | 17790569 | 10186332 | 12258702
MCR028651 | HPR224 | 2017-06-01 | Labor | 28514862 | 28312992 | 34042177
MCR028652 | HPR224 | 2017-06-01 | Material | 52619189 | 52246673 | 49281886
MCR028653 | HPR224 | 2017-06-01 | Equipment | 11932573 | 11848097 | 11768133
MCR028654 | HPR224 | 2017-06-01 | Subcontract | 83318324 | 82728475 | 93727394
MCR028655 | HPR224 | 2017-06-01 | Overhead | 17330581 | 17207889 | 12030549
MCR028656 | HPR224 | 2017-07-01 | Labor | 27464760 | 15311292 | 18831071
MCR028657 | HPR224 | 2017-07-01 | Material | 50681410 | 28254311 | 30210116
MCR028658 | HPR224 | 2017-07-01 | Equipment | 11493139 | 6407294 | 6816508
MCR028659 | HPR224 | 2017-07-01 | Subcontract | 80250004 | 44738466 | 41861765
MCR028660 | HPR224 | 2017-07-01 | Overhead | 16692357 | 9305799 | 10860005
MCR028661 | HPR224 | 2017-08-01 | Labor | 26137053 | 23769822 | 27190856
MCR028662 | HPR224 | 2017-08-01 | Material | 48231360 | 43863048 | 43559926
MCR028663 | HPR224 | 2017-08-01 | Equipment | 10937535 | 9946923 | 11401558
MCR028664 | HPR224 | 2017-08-01 | Subcontract | 76370543 | 69453668 | 77030830
MCR028665 | HPR224 | 2017-08-01 | Overhead | 15885411 | 14446671 | 11141235
MCR028666 | HPR224 | 2017-09-01 | Labor | 24548866 | 20421312 | 21344711
MCR028667 | HPR224 | 2017-09-01 | Material | 45300637 | 37683958 | 39370015
MCR028668 | HPR224 | 2017-09-01 | Equipment | 10272929 | 8545677 | 8782713
MCR028669 | HPR224 | 2017-09-01 | Subcontract | 71729976 | 59669567 | 51952373
MCR028670 | HPR224 | 2017-09-01 | Overhead | 14920153 | 12411534 | 10935026
MCR028671 | HPR224 | 2017-10-01 | Labor | 22719111 | 35379151 | 42486106
MCR028672 | HPR224 | 2017-10-01 | Material | 41924145 | 65286034 | 62223985
MCR028673 | HPR224 | 2017-10-01 | Equipment | 9507234 | 14805063 | 16473321
MCR028674 | HPR224 | 2017-10-01 | Subcontract | 66383568 | 103375272 | 105492945
MCR028675 | HPR224 | 2017-10-01 | Overhead | 13808076 | 21502515 | 11480221
MCR028676 | HPR224 | 2017-11-01 | Labor | 20668929 | 15150243 | 18810168
MCR028677 | HPR224 | 2017-11-01 | Material | 38140892 | 27957122 | 28821193
MCR028678 | HPR224 | 2017-11-01 | Equipment | 8649297 | 6339900 | 6263004
MCR028679 | HPR224 | 2017-11-01 | Subcontract | 60393086 | 44267892 | 48219802
MCR028680 | HPR224 | 2017-11-01 | Overhead | 12562030 | 9207918 | 11930979
MCR028681 | HPR224 | 2017-12-01 | Labor | 18422291 | 16616938 | 17947315
MCR028682 | HPR224 | 2017-12-01 | Material | 33995116 | 30663651 | 33665630
MCR028683 | HPR224 | 2017-12-01 | Equipment | 7709150 | 6953666 | 6747748
MCR028684 | HPR224 | 2017-12-01 | Subcontract | 53828577 | 48553466 | 52738267
MCR028685 | HPR224 | 2017-12-01 | Overhead | 11196583 | 10099336 | 12358243
MCR028686 | HPR224 | 2018-01-01 | Labor | 16006896 | 22017937 | 25697760
MCR028687 | HPR224 | 2018-01-01 | Material | 29537926 | 40630251 | 37932980
MCR028688 | HPR224 | 2018-01-01 | Equipment | 6698383 | 9213814 | 11436491
MCR028689 | HPR224 | 2018-01-01 | Subcontract | 46770969 | 64334789 | 67482191
MCR028690 | HPR224 | 2018-01-01 | Overhead | 9728569 | 13381921 | 10479196
MCR028691 | HPR224 | 2018-02-01 | Labor | 13455524 | 15310021 | 18973884
MCR028692 | HPR224 | 2018-02-01 | Material | 24829816 | 28251964 | 30243015
MCR028693 | HPR224 | 2018-02-01 | Equipment | 5630714 | 6406762 | 5625138
MCR028694 | HPR224 | 2018-02-01 | Subcontract | 39316050 | 44734751 | 41472719
MCR028695 | HPR224 | 2018-02-01 | Overhead | 8177913 | 9305027 | 11985077
MCR028696 | HPR224 | 2018-03-01 | Labor | 10808273 | 22726999 | 22846253
MCR028697 | HPR224 | 2018-03-01 | Material | 19944777 | 41938700 | 45911910
MCR028698 | HPR224 | 2018-03-01 | Equipment | 4522922 | 9510534 | 9879415
MCR028699 | HPR224 | 2018-03-01 | Subcontract | 31580976 | 66406614 | 79072295
MCR028700 | HPR224 | 2018-03-01 | Overhead | 6568983 | 13812870 | 11602579
MCR028701 | HPR224 | 2018-04-01 | Labor | 8116529 | 20280977 | 30325324
MCR028702 | HPR224 | 2018-04-01 | Material | 14977634 | 37424996 | 39934487
MCR028703 | HPR224 | 2018-04-01 | Equipment | 3396512 | 8486951 | 8972664
MCR028704 | HPR224 | 2018-04-01 | Subcontract | 23715899 | 59259520 | 51785232
MCR028705 | HPR224 | 2018-04-01 | Overhead | 4933012 | 12326243 | 11677476
MCR028706 | HPR224 | 2018-05-01 | Labor | 5451071 | 22394074 | 26424692
MCR028707 | HPR224 | 2018-05-01 | Material | 10058997 | 41324345 | 41944473
MCR028708 | HPR224 | 2018-05-01 | Equipment | 2281102 | 9371216 | 9546157
MCR028709 | HPR224 | 2018-05-01 | Subcontract | 15927627 | 65433832 | 67536146
MCR028710 | HPR224 | 2018-05-01 | Overhead | 3313017 | 13610527 | 11312736
MCR028711 | HPR224 | 2018-06-01 | Labor | 2922527 | 12286281 | 13296603
MCR028712 | HPR224 | 2018-06-01 | Material | 5393012 | 22672182 | 19040300
MCR028713 | HPR224 | 2018-06-01 | Equipment | 1222986 | 5141422 | 4802933
MCR028714 | HPR224 | 2018-06-01 | Subcontract | 8539408 | 35899606 | 45787995
MCR028715 | HPR224 | 2018-06-01 | Overhead | 1776235 | 7467277 | 10934352
MCR028716 | HPR224 | 2018-07-01 | Labor | 768417 | 10645353 | 10097482
MCR028717 | HPR224 | 2018-07-01 | Material | 1417979 | 19644136 | 20753385
MCR028718 | HPR224 | 2018-07-01 | Equipment | 321558 | 4454745 | 5509665
MCR028719 | HPR224 | 2018-07-01 | Subcontract | 2245258 | 31104935 | 28827132
MCR028720 | HPR224 | 2018-07-01 | Overhead | 467024 | 6469964 | 11058029
MCR028721 | HPR224 | 2018-08-01 | Labor | 0 | 8686907 | 11146673
MCR028722 | HPR224 | 2018-08-01 | Material | 0 | 16030167 | 17244310
MCR028723 | HPR224 | 2018-08-01 | Equipment | 0 | 3635197 | 3481505
MCR028724 | HPR224 | 2018-08-01 | Subcontract | 0 | 25382501 | 24210235
MCR028725 | HPR224 | 2018-08-01 | Overhead | 0 | 5279673 | 11822059
MCR028726 | HPR224 | 2018-09-01 | Labor | 0 | 7968320 | 9290668
MCR028727 | HPR224 | 2018-09-01 | Material | 0 | 14704141 | 13301578
MCR028728 | HPR224 | 2018-09-01 | Equipment | 0 | 3334491 | 3322053
MCR028729 | HPR224 | 2018-09-01 | Subcontract | 0 | 23282844 | 26413276
MCR028730 | HPR224 | 2018-09-01 | Overhead | 0 | 4842935 | 10749590
MCR028731 | HPR224 | 2018-10-01 | Labor | 0 | 8919515 | 10665844
MCR028732 | HPR224 | 2018-10-01 | Material | 0 | 16459405 | 15829527
MCR028733 | HPR224 | 2018-10-01 | Equipment | 0 | 3732537 | 4219326
MCR028734 | HPR224 | 2018-10-01 | Subcontract | 0 | 26062165 | 27699854
MCR028735 | HPR224 | 2018-10-01 | Overhead | 0 | 5421046 | 11176574
MCR028736 | HPR224 | 2018-11-01 | Labor | 0 | 8569271 | 11178524
MCR028737 | HPR224 | 2018-11-01 | Material | 0 | 15813091 | 17216800
MCR028738 | HPR224 | 2018-11-01 | Equipment | 0 | 3585971 | 4688557
MCR028739 | HPR224 | 2018-11-01 | Subcontract | 0 | 25038779 | 29812372
MCR028740 | HPR224 | 2018-11-01 | Overhead | 0 | 5208177 | 10846535
MCR028741 | HPR224 | 2018-12-01 | Labor | 0 | 3992336 | 3801985
MCR028742 | HPR224 | 2018-12-01 | Material | 0 | 7367157 | 7142614
MCR028743 | HPR224 | 2018-12-01 | Equipment | 0 | 1670667 | 1397801
MCR028744 | HPR224 | 2018-12-01 | Subcontract | 0 | 11665310 | 10005390
MCR028745 | HPR224 | 2018-12-01 | Overhead | 0 | 2426436 | 11892665
MCR028746 | HPR224 | 2019-01-01 | Labor | 0 | 4889548 | 5542990
MCR028747 | HPR224 | 2019-01-01 | Material | 0 | 9022805 | 9569127
MCR028748 | HPR224 | 2019-01-01 | Equipment | 0 | 2046122 | 2022677
MCR028749 | HPR224 | 2019-01-01 | Subcontract | 0 | 14286898 | 15145447
MCR028750 | HPR224 | 2019-01-01 | Overhead | 0 | 2971738 | 12053531
MCR028751 | HPR224 | 2019-02-01 | Labor | 0 | 2643094 | 3007345
MCR028752 | HPR224 | 2019-02-01 | Material | 0 | 4877368 | 4894147
MCR028753 | HPR224 | 2019-02-01 | Equipment | 0 | 1106052 | 1627556
MCR028754 | HPR224 | 2019-02-01 | Subcontract | 0 | 7722927 | 6372441
MCR028755 | HPR224 | 2019-02-01 | Overhead | 0 | 1606403 | 11355987
MCR028756 | HPR224 | 2019-03-01 | Labor | 0 | 1289773 | 1713033
MCR028757 | HPR224 | 2019-03-01 | Material | 0 | 2380050 | 2380868
MCR028758 | HPR224 | 2019-03-01 | Equipment | 0 | 539729 | 561361
MCR028759 | HPR224 | 2019-03-01 | Subcontract | 0 | 3768621 | 4255940
MCR028760 | HPR224 | 2019-03-01 | Overhead | 0 | 783890 | 11639412
MCR028761 | HPR224 | 2019-04-01 | Labor | 0 | 319085 | 277568
MCR028762 | HPR224 | 2019-04-01 | Material | 0 | 588816 | 708320
MCR028763 | HPR224 | 2019-04-01 | Equipment | 0 | 133527 | 182071
MCR028764 | HPR224 | 2019-04-01 | Subcontract | 0 | 932343 | 1330145
MCR028765 | HPR224 | 2019-04-01 | Overhead | 0 | 193932 | 12172535
MCR028766 | HPR225 | 2021-11-01 | Labor | 4667871 | 2066341 | 1934760
MCR028767 | HPR225 | 2021-11-01 | Material | 11405742 | 5049015 | 4729746
MCR028768 | HPR225 | 2021-11-01 | Equipment | 2329807 | 1031343 | 1129855
MCR028769 | HPR225 | 2021-11-01 | Subcontract | 13576692 | 6010036 | 5628150
MCR028770 | HPR225 | 2021-11-01 | Overhead | 3239194 | 1433904 | 16749004
MCR028771 | HPR225 | 2021-12-01 | Labor | 13077594 | 11045665 | 11813139
MCR028772 | HPR225 | 2021-12-01 | Material | 31954538 | 26989607 | 30957627
MCR028773 | HPR225 | 2021-12-01 | Equipment | 6527229 | 5513062 | 5329402
MCR028774 | HPR225 | 2021-12-01 | Subcontract | 38036711 | 32126764 | 32684026
MCR028775 | HPR225 | 2021-12-01 | Overhead | 9074985 | 7664961 | 16669139
MCR028776 | HPR225 | 2022-01-01 | Labor | 20126643 | 28263574 | 31264242
MCR028777 | HPR225 | 2022-01-01 | Material | 49178587 | 69060829 | 71480144
MCR028778 | HPR225 | 2022-01-01 | Equipment | 10045519 | 14106787 | 13783999
MCR028779 | HPR225 | 2022-01-01 | Subcontract | 58539158 | 82205753 | 79345301
MCR028780 | HPR225 | 2022-01-01 | Overhead | 13966560 | 19613052 | 15782431
MCR028781 | HPR225 | 2022-02-01 | Labor | 25854644 | 11417620 | 9628434
MCR028782 | HPR225 | 2022-02-01 | Material | 63174710 | 27898464 | 25450762
MCR028783 | HPR225 | 2022-02-01 | Equipment | 12904452 | 5698711 | 6166274
MCR028784 | HPR225 | 2022-02-01 | Subcontract | 75199280 | 33208612 | 35408126
MCR028785 | HPR225 | 2022-02-01 | Overhead | 17941414 | 7923074 | 17615259
MCR028786 | HPR225 | 2022-03-01 | Labor | 30303764 | 28561196 | 29964891
MCR028787 | HPR225 | 2022-03-01 | Material | 74045945 | 69788053 | 72713726
MCR028788 | HPR225 | 2022-03-01 | Equipment | 15125077 | 14255334 | 18513737
MCR028789 | HPR225 | 2022-03-01 | Subcontract | 88139727 | 83071396 | 86321404
MCR028790 | HPR225 | 2022-03-01 | Overhead | 21028809 | 19819582 | 16691818
MCR028791 | HPR225 | 2022-04-01 | Labor | 33519118 | 27290421 | 29530714
MCR028792 | HPR225 | 2022-04-01 | Material | 81902525 | 66682970 | 71647800
MCR028793 | HPR225 | 2022-04-01 | Equipment | 16729910 | 13621071 | 9889019
MCR028794 | HPR225 | 2022-04-01 | Subcontract | 97491716 | 79375296 | 76366918
MCR028795 | HPR225 | 2022-04-01 | Overhead | 23260052 | 18937748 | 17393146
MCR028796 | HPR225 | 2022-05-01 | Labor | 35549267 | 49151579 | 50751190
MCR028797 | HPR225 | 2022-05-01 | Material | 86863105 | 120099771 | 109468958
MCR028798 | HPR225 | 2022-05-01 | Equipment | 17743189 | 24532313 | 26351503
MCR028799 | HPR225 | 2022-05-01 | Subcontract | 103396485 | 142959363 | 139773055
MCR028800 | HPR225 | 2022-05-01 | Overhead | 24668841 | 34107947 | 16494954
MCR028801 | HPR225 | 2022-06-01 | Labor | 36446861 | 41324186 | 50480998
MCR028802 | HPR225 | 2022-06-01 | Material | 89056338 | 100973873 | 117095207
MCR028803 | HPR225 | 2022-06-01 | Equipment | 18191192 | 20625540 | 19882946
MCR028804 | HPR225 | 2022-06-01 | Subcontract | 106007174 | 120193073 | 110945708
MCR028805 | HPR225 | 2022-06-01 | Overhead | 25291712 | 28676254 | 16628270
MCR028806 | HPR225 | 2022-07-01 | Labor | 36269488 | 25013955 | 25857004
MCR028807 | HPR225 | 2022-07-01 | Material | 88622933 | 61120523 | 58353630
MCR028808 | HPR225 | 2022-07-01 | Equipment | 18102662 | 12484851 | 12811977
MCR028809 | HPR225 | 2022-07-01 | Subcontract | 105491276 | 72754102 | 82942929
MCR028810 | HPR225 | 2022-07-01 | Overhead | 25168627 | 17358031 | 16434744
MCR028811 | HPR225 | 2022-08-01 | Labor | 35080804 | 16830444 | 16253318
MCR028812 | HPR225 | 2022-08-01 | Material | 85718436 | 41124467 | 39798528
MCR028813 | HPR225 | 2022-08-01 | Equipment | 17509371 | 8400335 | 8120741
MCR028814 | HPR225 | 2022-08-01 | Subcontract | 102033941 | 48952030 | 55526916
MCR028815 | HPR225 | 2022-08-01 | Overhead | 24343759 | 11679216 | 16714231
MCR028816 | HPR225 | 2022-09-01 | Labor | 32952115 | 41206849 | 46992692
MCR028817 | HPR225 | 2022-09-01 | Material | 80517076 | 100687163 | 114935936
MCR028818 | HPR225 | 2022-09-01 | Equipment | 16446910 | 20566975 | 21399714
MCR028819 | HPR225 | 2022-09-01 | Subcontract | 95842563 | 119851791 | 118536011
MCR028820 | HPR225 | 2022-09-01 | Overhead | 22866590 | 28594829 | 17053266
MCR028821 | HPR225 | 2022-10-01 | Labor | 29964651 | 31383241 | 32170416
MCR028822 | HPR225 | 2022-10-01 | Material | 73217336 | 76683599 | 77614808
MCR028823 | HPR225 | 2022-10-01 | Equipment | 14955820 | 15663861 | 15553178
MCR028824 | HPR225 | 2022-10-01 | Subcontract | 87153402 | 91279429 | 87663879
MCR028825 | HPR225 | 2022-10-01 | Overhead | 20793487 | 21777895 | 15717594
MCR028826 | HPR225 | 2022-11-01 | Labor | 26213014 | 27630909 | 25678678
MCR028827 | HPR225 | 2022-11-01 | Material | 64050374 | 67514937 | 55275550
MCR028828 | HPR225 | 2022-11-01 | Equipment | 13083321 | 13791014 | 15010492
MCR028829 | HPR225 | 2022-11-01 | Subcontract | 76241616 | 80365618 | 89311073
MCR028830 | HPR225 | 2022-11-01 | Overhead | 18190099 | 19174024 | 14857098
MCR028831 | HPR225 | 2022-12-01 | Labor | 21810762 | 31057025 | 33798682
MCR028832 | HPR225 | 2022-12-01 | Material | 53293658 | 75886506 | 75191142
MCR028833 | HPR225 | 2022-12-01 | Equipment | 10886088 | 15501041 | 13497884
MCR028834 | HPR225 | 2022-12-01 | Subcontract | 63437485 | 90330618 | 81114341
MCR028835 | HPR225 | 2022-12-01 | Overhead | 15135227 | 21551523 | 15709375
MCR028836 | HPR225 | 2023-01-01 | Labor | 16900243 | 14979933 | 14454853
MCR028837 | HPR225 | 2023-01-01 | Material | 41295018 | 36602823 | 42352780
MCR028838 | HPR225 | 2023-01-01 | Equipment | 8435173 | 7476716 | 9136766
MCR028839 | HPR225 | 2023-01-01 | Subcontract | 49155044 | 43569744 | 48104634
MCR028840 | HPR225 | 2023-01-01 | Overhead | 11727652 | 10395084 | 15999465
MCR028841 | HPR225 | 2023-02-01 | Labor | 11672367 | 14127880 | 14750044
MCR028842 | HPR225 | 2023-02-01 | Material | 28520928 | 34520868 | 32623138
MCR028843 | HPR225 | 2023-02-01 | Equipment | 5825859 | 7051443 | 6062032
MCR028844 | HPR225 | 2023-02-01 | Subcontract | 33949554 | 41091513 | 40061211
MCR028845 | HPR225 | 2023-02-01 | Overhead | 8099851 | 9803815 | 17219268
MCR028846 | HPR225 | 2023-03-01 | Labor | 6415769 | 9318857 | 9869962
MCR028847 | HPR225 | 2023-03-01 | Material | 15676655 | 22770226 | 21468584
MCR028848 | HPR225 | 2023-03-01 | Equipment | 3202209 | 4651185 | 4944789
MCR028849 | HPR225 | 2023-03-01 | Subcontract | 18660524 | 27104273 | 30478877
MCR028850 | HPR225 | 2023-03-01 | Overhead | 4452119 | 6466671 | 15147012
MCR028851 | HPR225 | 2023-04-01 | Labor | 1721793 | 5971391 | 5736642
MCR028852 | HPR225 | 2023-04-01 | Material | 4207126 | 14590838 | 16351465
MCR028853 | HPR225 | 2023-04-01 | Equipment | 859373 | 2980414 | 2823457
MCR028854 | HPR225 | 2023-04-01 | Subcontract | 5007904 | 17368034 | 16254515
MCR028855 | HPR225 | 2023-04-01 | Overhead | 1194810 | 4143751 | 16356953
MCR028856 | HPR225 | 2023-05-01 | Labor | 0 | 1905701 | 1978947
MCR028857 | HPR225 | 2023-05-01 | Material | 0 | 4656498 | 4585825
MCR028858 | HPR225 | 2023-05-01 | Equipment | 0 | 951165 | 1062900
MCR028859 | HPR225 | 2023-05-01 | Subcontract | 0 | 5542808 | 5726336
MCR028860 | HPR225 | 2023-05-01 | Overhead | 0 | 1322430 | 15243214
MCR028861 | HPR226 | 2019-09-01 | Labor | 4484285 | 3911083 | 3439103
MCR028862 | HPR226 | 2019-09-01 | Material | 12193540 | 10634905 | 10277277
MCR028863 | HPR226 | 2019-09-01 | Equipment | 3366241 | 2935952 | 3261318
MCR028864 | HPR226 | 2019-09-01 | Subcontract | 10474391 | 9135506 | 8399830
MCR028865 | HPR226 | 2019-09-01 | Overhead | 2963196 | 2584426 | 16317450
MCR028866 | HPR226 | 2019-10-01 | Labor | 12693580 | 9480074 | 10620663
MCR028867 | HPR226 | 2019-10-01 | Material | 34516019 | 25777945 | 28916261
MCR028868 | HPR226 | 2019-10-01 | Equipment | 9528754 | 7116455 | 6852935
MCR028869 | HPR226 | 2019-10-01 | Subcontract | 29649658 | 22143552 | 24347739
MCR028870 | HPR226 | 2019-10-01 | Overhead | 8387861 | 6264390 | 18080783
MCR028871 | HPR226 | 2019-11-01 | Labor | 19783640 | 11901987 | 12694412
MCR028872 | HPR226 | 2019-11-01 | Material | 53795106 | 32363540 | 31396523
MCR028873 | HPR226 | 2019-11-01 | Equipment | 14851084 | 8934524 | 9071854
MCR028874 | HPR226 | 2019-11-01 | Subcontract | 46210614 | 27800653 | 24897622
MCR028875 | HPR226 | 2019-11-01 | Overhead | 13072940 | 7864779 | 17943290
MCR028876 | HPR226 | 2019-12-01 | Labor | 25781757 | 19664432 | 18792978
MCR028877 | HPR226 | 2019-12-01 | Material | 70105012 | 53470959 | 53985467
MCR028878 | HPR226 | 2019-12-01 | Equipment | 19353720 | 14761598 | 15267579
MCR028879 | HPR226 | 2019-12-01 | Subcontract | 60221012 | 45932169 | 50073069
MCR028880 | HPR226 | 2019-12-01 | Overhead | 17036469 | 12994168 | 18119349
MCR028881 | HPR226 | 2020-01-01 | Labor | 30716676 | 22584695 | 27321224
MCR028882 | HPR226 | 2020-01-01 | Material | 83523904 | 61411654 | 64337001
MCR028883 | HPR226 | 2020-01-01 | Equipment | 23058241 | 16953766 | 17651861
MCR028884 | HPR226 | 2020-01-01 | Subcontract | 71747994 | 52753317 | 58552794
MCR028885 | HPR226 | 2020-01-01 | Overhead | 20297442 | 14923865 | 19418483
MCR028886 | HPR226 | 2020-02-01 | Labor | 34618783 | 27055259 | 27242787
MCR028887 | HPR226 | 2020-02-01 | Material | 94134402 | 73567884 | 75861473
MCR028888 | HPR226 | 2020-02-01 | Equipment | 25987455 | 20309707 | 20216072
MCR028889 | HPR226 | 2020-02-01 | Subcontract | 80862533 | 63195658 | 70211367
MCR028890 | HPR226 | 2020-02-01 | Overhead | 22875937 | 17877994 | 17229564
MCR028891 | HPR226 | 2020-03-01 | Labor | 37520327 | 28635728 | 33001595
MCR028892 | HPR226 | 2020-03-01 | Material | 102024197 | 77865451 | 79575969
MCR028893 | HPR226 | 2020-03-01 | Equipment | 28165572 | 21496126 | 19546182
MCR028894 | HPR226 | 2020-03-01 | Subcontract | 87639959 | 66887317 | 66074387
MCR028895 | HPR226 | 2020-03-01 | Overhead | 24793264 | 18922361 | 17320382
MCR028896 | HPR226 | 2020-04-01 | Labor | 39455698 | 24974610 | 23605360
MCR028897 | HPR226 | 2020-04-01 | Material | 107286802 | 67910243 | 66769026
MCR028898 | HPR226 | 2020-04-01 | Equipment | 29618406 | 18747816 | 19544525
MCR028899 | HPR226 | 2020-04-01 | Subcontract | 92160597 | 58335680 | 52741253
MCR028900 | HPR226 | 2020-04-01 | Overhead | 26072148 | 16503110 | 17629028
MCR028901 | HPR226 | 2020-05-01 | Labor | 40461768 | 28692142 | 33834246
MCR028902 | HPR226 | 2020-05-01 | Material | 110022477 | 78018848 | 81974157
MCR028903 | HPR226 | 2020-05-01 | Equipment | 30373638 | 21538474 | 24801132
MCR028904 | HPR226 | 2020-05-01 | Subcontract | 94510573 | 67019088 | 79682175
MCR028905 | HPR226 | 2020-05-01 | Overhead | 26736955 | 18959638 | 16405093
MCR028906 | HPR226 | 2020-06-01 | Labor | 40578322 | 26903001 | 27433008
MCR028907 | HPR226 | 2020-06-01 | Material | 110339409 | 73153867 | 72846321
MCR028908 | HPR226 | 2020-06-01 | Equipment | 30461132 | 20195410 | 20386896
MCR028909 | HPR226 | 2020-06-01 | Subcontract | 94782821 | 62840013 | 65774910
MCR028910 | HPR226 | 2020-06-01 | Overhead | 26813973 | 17777382 | 16630392
MCR028911 | HPR226 | 2020-07-01 | Labor | 39848617 | 23257212 | 27128001
MCR028912 | HPR226 | 2020-07-01 | Material | 108355215 | 63240343 | 60391347
MCR028913 | HPR226 | 2020-07-01 | Equipment | 29913361 | 17458608 | 16269127
MCR028914 | HPR226 | 2020-07-01 | Subcontract | 93078375 | 54324182 | 53600303
MCR028915 | HPR226 | 2020-07-01 | Overhead | 26331787 | 15368261 | 16469957
MCR028916 | HPR226 | 2020-08-01 | Labor | 38320105 | 59963027 | 60709865
MCR028917 | HPR226 | 2020-08-01 | Material | 104198928 | 163049743 | 184354150
MCR028918 | HPR226 | 2020-08-01 | Equipment | 28765945 | 45012746 | 44989681
MCR028919 | HPR226 | 2020-08-01 | Subcontract | 89508078 | 140061604 | 138671450
MCR028920 | HPR226 | 2020-08-01 | Overhead | 25321753 | 39623299 | 17671646
MCR028921 | HPR226 | 2020-09-01 | Labor | 36045422 | 23163726 | 25481172
MCR028922 | HPR226 | 2020-09-01 | Material | 98013677 | 62986138 | 53423771
MCR028923 | HPR226 | 2020-09-01 | Equipment | 27058398 | 17388430 | 17594119
MCR028924 | HPR226 | 2020-09-01 | Subcontract | 84194876 | 54105817 | 61561481
MCR028925 | HPR226 | 2020-09-01 | Overhead | 23818653 | 15306486 | 16387088
MCR028926 | HPR226 | 2020-10-01 | Labor | 33083760 | 27585820 | 62691487
MCR028927 | HPR226 | 2020-10-01 | Material | 89960410 | 75010571 | 121911170
MCR028928 | HPR226 | 2020-10-01 | Equipment | 24835151 | 20707986 | 21795043
MCR028929 | HPR226 | 2020-10-01 | Subcontract | 77277026 | 64434943 | 59367665
MCR028930 | HPR226 | 2020-10-01 | Overhead | 21861600 | 18228586 | 15885691
MCR028931 | HPR226 | 2020-11-01 | Labor | 29502847 | 30920120 | 67774755
MCR028932 | HPR226 | 2020-11-01 | Material | 80223294 | 84077104 | 95874890
MCR028933 | HPR226 | 2020-11-01 | Equipment | 22147050 | 23210961 | 22337347
MCR028934 | HPR226 | 2020-11-01 | Subcontract | 68912732 | 72223199 | 86747994
MCR028935 | HPR226 | 2020-11-01 | Overhead | 19495349 | 20431877 | 16378517
MCR028936 | HPR226 | 2020-12-01 | Labor | 25381975 | 36302135 | 40654143
MCR028937 | HPR226 | 2020-12-01 | Material | 69017938 | 98711722 | 113254992
MCR028938 | HPR226 | 2020-12-01 | Equipment | 19053614 | 27251105 | 28520771
MCR028939 | HPR226 | 2020-12-01 | Subcontract | 59287203 | 84794504 | 80300480
MCR028940 | HPR226 | 2020-12-01 | Overhead | 16772295 | 23988288 | 17066046
MCR028941 | HPR226 | 2021-01-01 | Labor | 20816903 | 43032461 | 51090762
MCR028942 | HPR226 | 2021-01-01 | Material | 56604725 | 117012633 | 130214521
MCR028943 | HPR226 | 2021-01-01 | Equipment | 15626729 | 32303393 | 34384778
MCR028944 | HPR226 | 2021-01-01 | Subcontract | 48624109 | 100515197 | 122468713
MCR028945 | HPR226 | 2021-01-01 | Overhead | 13755716 | 28435657 | 17925342
MCR028946 | HPR226 | 2021-02-01 | Labor | 15928548 | 16781482 | 14893885
MCR028947 | HPR226 | 2021-02-01 | Material | 43312450 | 45631724 | 41453155
MCR028948 | HPR226 | 2021-02-01 | Equipment | 11957163 | 12597439 | 10015689
MCR028949 | HPR226 | 2021-02-01 | Subcontract | 37205892 | 39198176 | 31574664
MCR028950 | HPR226 | 2021-02-01 | Overhead | 10525513 | 11089128 | 17120892
MCR028951 | HPR226 | 2021-03-01 | Labor | 10880527 | 21804728 | 24748145
MCR028952 | HPR226 | 2021-03-01 | Material | 29586016 | 59290790 | 70565749
MCR028953 | HPR226 | 2021-03-01 | Equipment | 8167739 | 16368264 | 19818987
MCR028954 | HPR226 | 2021-03-01 | Subcontract | 25414728 | 50931471 | 50689309
MCR028955 | HPR226 | 2021-03-01 | Overhead | 7189803 | 14408466 | 16280865
MCR028956 | HPR226 | 2021-04-01 | Labor | 5923036 | 26353465 | 28943556
MCR028957 | HPR226 | 2021-04-01 | Material | 16105750 | 71659585 | 71460212
MCR028958 | HPR226 | 2021-04-01 | Equipment | 4446275 | 19782887 | 18104519
MCR028959 | HPR226 | 2021-04-01 | Subcontract | 13835025 | 61556408 | 59748793
MCR028960 | HPR226 | 2021-04-01 | Overhead | 3913916 | 17414251 | 16892673
MCR028961 | HPR226 | 2021-05-01 | Labor | 1577153 | 18481102 | 22384072
MCR028962 | HPR226 | 2021-05-01 | Material | 4288548 | 50253281 | 58782863
MCR028963 | HPR226 | 2021-05-01 | Equipment | 1183929 | 13873301 | 15227627
MCR028964 | HPR226 | 2021-05-01 | Subcontract | 3683912 | 43168146 | 48967400
MCR028965 | HPR226 | 2021-05-01 | Overhead | 1042175 | 12212229 | 17377172
MCR028966 | HPR226 | 2021-06-01 | Labor | 0 | 6350994 | 5125550
MCR028967 | HPR226 | 2021-06-01 | Material | 0 | 17269441 | 22636605
MCR028968 | HPR226 | 2021-06-01 | Equipment | 0 | 4767533 | 3828911
MCR028969 | HPR226 | 2021-06-01 | Subcontract | 0 | 14834648 | 15382673
MCR028970 | HPR226 | 2021-06-01 | Overhead | 0 | 4196708 | 16959676
MCR028971 | HPR226 | 2021-07-01 | Labor | 0 | 4737038 | 5158891
MCR028972 | HPR226 | 2021-07-01 | Material | 0 | 12880818 | 12242195
MCR028973 | HPR226 | 2021-07-01 | Equipment | 0 | 3555976 | 3849336
MCR028974 | HPR226 | 2021-07-01 | Subcontract | 0 | 11064770 | 12923226
MCR028975 | HPR226 | 2021-07-01 | Overhead | 0 | 3130213 | 15755404
MCR028976 | HPR226 | 2021-08-01 | Labor | 0 | 867409 | 922700
MCR028977 | HPR226 | 2021-08-01 | Material | 0 | 2358632 | 2624509
MCR028978 | HPR226 | 2021-08-01 | Equipment | 0 | 651142 | 479924
MCR028979 | HPR226 | 2021-08-01 | Subcontract | 0 | 2026092 | 1460551
MCR028980 | HPR226 | 2021-08-01 | Overhead | 0 | 573180 | 17277927
MCR028981 | HPR227 | 2022-02-01 | Labor | 2401003 | 1255818 | 1157991
MCR028982 | HPR227 | 2022-02-01 | Material | 7720888 | 4038324 | 4108740
MCR028983 | HPR227 | 2022-02-01 | Equipment | 2077874 | 1086808 | 976230
MCR028984 | HPR227 | 2022-02-01 | Subcontract | 7543377 | 3945479 | 3725949
MCR028985 | HPR227 | 2022-02-01 | Overhead | 1687313 | 882530 | 11372268
MCR028986 | HPR227 | 2022-03-01 | Labor | 6848421 | 3973767 | 4107508
MCR028987 | HPR227 | 2022-03-01 | Material | 22022421 | 12778416 | 14765974
MCR028988 | HPR227 | 2022-03-01 | Equipment | 5926754 | 3438974 | 3416904
MCR028989 | HPR227 | 2022-03-01 | Subcontract | 21516104 | 12484628 | 14632290
MCR028990 | HPR227 | 2022-03-01 | Overhead | 4812752 | 2792579 | 11259374
MCR028991 | HPR227 | 2022-04-01 | Labor | 10771925 | 10907366 | 9860316
MCR028992 | HPR227 | 2022-04-01 | Material | 34639205 | 35074741 | 35072487
MCR028993 | HPR227 | 2022-04-01 | Equipment | 9322229 | 9439442 | 9032504
MCR028994 | HPR227 | 2022-04-01 | Subcontract | 33842816 | 34268339 | 32137607
MCR028995 | HPR227 | 2022-04-01 | Overhead | 7570008 | 7665190 | 11174789
MCR028996 | HPR227 | 2022-05-01 | Labor | 14182502 | 11281703 | 12187377
MCR028997 | HPR227 | 2022-05-01 | Material | 45606576 | 36278497 | 38483860
MCR028998 | HPR227 | 2022-05-01 | Equipment | 12273808 | 9763402 | 11115629
MCR028999 | HPR227 | 2022-05-01 | Subcontract | 44558037 | 35444419 | 37706737
MCR029000 | HPR227 | 2022-05-01 | Overhead | 9966803 | 7928257 | 11696042
MCR029001 | HPR227 | 2022-06-01 | Labor | 17091642 | 10449460 | 11311258
MCR029002 | HPR227 | 2022-06-01 | Material | 54961478 | 33602258 | 35857028
MCR029003 | HPR227 | 2022-06-01 | Equipment | 14791434 | 9043162 | 10367634
MCR029004 | HPR227 | 2022-06-01 | Subcontract | 53697860 | 32829709 | 35028812
MCR029005 | HPR227 | 2022-06-01 | Overhead | 12011212 | 7343395 | 11151835
MCR029006 | HPR227 | 2022-07-01 | Labor | 19511387 | 8152135 | 7619955
MCR029007 | HPR227 | 2022-07-01 | Material | 62742635 | 26214764 | 25807818
MCR029008 | HPR227 | 2022-07-01 | Equipment | 16885527 | 7055013 | 6875664
MCR029009 | HPR227 | 2022-07-01 | Subcontract | 61300120 | 25612061 | 26391820
MCR029010 | HPR227 | 2022-07-01 | Overhead | 13711696 | 5728941 | 10883142
MCR029011 | HPR227 | 2022-08-01 | Labor | 21454395 | 8521033 | 6877360
MCR029012 | HPR227 | 2022-08-01 | Material | 68990754 | 27401029 | 21789092
MCR029013 | HPR227 | 2022-08-01 | Equipment | 18567043 | 7374265 | 7019723
MCR029014 | HPR227 | 2022-08-01 | Subcontract | 67404589 | 26771052 | 24223433
MCR029015 | HPR227 | 2022-08-01 | Overhead | 15077152 | 5988186 | 10535185
MCR029016 | HPR227 | 2022-09-01 | Labor | 22934020 | 18486412 | 18430725
MCR029017 | HPR227 | 2022-09-01 | Material | 73748772 | 59446629 | 67097785
MCR029018 | HPR227 | 2022-09-01 | Equipment | 19847538 | 15998494 | 17530163
MCR029019 | HPR227 | 2022-09-01 | Subcontract | 72053215 | 58079893 | 63874997
MCR029020 | HPR227 | 2022-09-01 | Overhead | 16116963 | 12991391 | 11707277
MCR029021 | HPR227 | 2022-10-01 | Labor | 23964396 | 16027153 | 15964529
MCR029022 | HPR227 | 2022-10-01 | Material | 77062145 | 51538407 | 54172931
MCR029023 | HPR227 | 2022-10-01 | Equipment | 20739246 | 13870204 | 14068391
MCR029024 | HPR227 | 2022-10-01 | Subcontract | 75290411 | 50353488 | 60157538
MCR029025 | HPR227 | 2022-10-01 | Overhead | 16841063 | 11263138 | 11400695
MCR029026 | HPR227 | 2022-11-01 | Labor | 24560552 | 15519119 | 15134707
MCR029027 | HPR227 | 2022-11-01 | Material | 78979200 | 49904726 | 50768586
MCR029028 | HPR227 | 2022-11-01 | Equipment | 21255170 | 13430542 | 12159075
MCR029029 | HPR227 | 2022-11-01 | Subcontract | 77163391 | 48757367 | 48014041
MCR029030 | HPR227 | 2022-11-01 | Overhead | 17260014 | 10906115 | 11439574
MCR029031 | HPR227 | 2022-12-01 | Labor | 24738543 | 18371159 | 17820852
MCR029032 | HPR227 | 2022-12-01 | Material | 79551565 | 59076013 | 64348287
MCR029033 | HPR227 | 2022-12-01 | Equipment | 21409207 | 15898752 | 17273389
MCR029034 | HPR227 | 2022-12-01 | Subcontract | 77722597 | 57717797 | 60731341
MCR029035 | HPR227 | 2022-12-01 | Overhead | 17385098 | 12910397 | 11280095
MCR029036 | HPR227 | 2023-01-01 | Labor | 24515618 | 22638584 | 22177088
MCR029037 | HPR227 | 2023-01-01 | Material | 78834707 | 72798741 | 65661971
MCR029038 | HPR227 | 2023-01-01 | Equipment | 21216284 | 19591863 | 19675673
MCR029039 | HPR227 | 2023-01-01 | Subcontract | 77022220 | 71125027 | 76039492
MCR029040 | HPR227 | 2023-01-01 | Overhead | 17228437 | 15909345 | 11110525
MCR029041 | HPR227 | 2023-02-01 | Labor | 23910431 | 22018117 | 20428173
MCR029042 | HPR227 | 2023-02-01 | Material | 76888610 | 70803509 | 74703019
MCR029043 | HPR227 | 2023-02-01 | Equipment | 20692543 | 19054898 | 18196961
MCR029044 | HPR227 | 2023-02-01 | Subcontract | 75120866 | 69175667 | 57500221
MCR029045 | HPR227 | 2023-02-01 | Overhead | 16803139 | 15473309 | 10720402
MCR029046 | HPR227 | 2023-03-01 | Labor | 22943311 | 25906833 | 26424545
MCR029047 | HPR227 | 2023-03-01 | Material | 73778650 | 83308427 | 83814679
MCR029048 | HPR227 | 2023-03-01 | Equipment | 19855579 | 22420268 | 19789275
MCR029049 | HPR227 | 2023-03-01 | Subcontract | 72082407 | 81393085 | 86535309
MCR029050 | HPR227 | 2023-03-01 | Overhead | 16123493 | 18206118 | 10584591
MCR029051 | HPR227 | 2023-04-01 | Labor | 21636623 | 21302496 | 21776264
MCR029052 | HPR227 | 2023-04-01 | Material | 69576743 | 68502292 | 71917945
MCR029053 | HPR227 | 2023-04-01 | Equipment | 18724747 | 18435587 | 22103729
MCR029054 | HPR227 | 2023-04-01 | Subcontract | 67977105 | 66927357 | 75849139
MCR029055 | HPR227 | 2023-04-01 | Overhead | 15205213 | 14970404 | 11189786
MCR029056 | HPR227 | 2023-05-01 | Labor | 20015251 | 18746990 | 19291527
MCR029057 | HPR227 | 2023-05-01 | Material | 64362907 | 60284569 | 60187160
MCR029058 | HPR227 | 2023-05-01 | Equipment | 17321580 | 16224003 | 18987891
MCR029059 | HPR227 | 2023-05-01 | Subcontract | 62883141 | 58898568 | 57336454
MCR029060 | HPR227 | 2023-05-01 | Overhead | 14065788 | 13174513 | 11396953
MCR029061 | HPR227 | 2023-06-01 | Labor | 18107273 | 14797913 | 14474639
MCR029062 | HPR227 | 2023-06-01 | Material | 58227435 | 47585547 | 42720783
MCR029063 | HPR227 | 2023-06-01 | Equipment | 15670380 | 12806396 | 11226783
MCR029064 | HPR227 | 2023-06-01 | Subcontract | 56888729 | 46491509 | 46909300
MCR029065 | HPR227 | 2023-06-01 | Overhead | 12724950 | 10399285 | 10369025
MCR029066 | HPR227 | 2023-07-01 | Labor | 15944947 | 7661267 | 27374000
MCR029067 | HPR227 | 2023-07-01 | Material | 51274057 | 24636284 | 62918621
MCR029068 | HPR227 | 2023-07-01 | Equipment | 13799061 | 6630207 | 7111912
MCR029069 | HPR227 | 2023-07-01 | Subcontract | 50095216 | 24069872 | 28104581
MCR029070 | HPR227 | 2023-07-01 | Overhead | 11205367 | 5383982 | 10441350
MCR029071 | HPR227 | 2023-08-01 | Labor | 13566208 | 9473556 | 25604608
MCR029072 | HPR227 | 2023-08-01 | Material | 43624762 | 30464050 | 47767971
MCR029073 | HPR227 | 2023-08-01 | Equipment | 11740455 | 8198596 | 8291953
MCR029074 | HPR227 | 2023-08-01 | Subcontract | 42621786 | 29763651 | 32140664
MCR029075 | HPR227 | 2023-08-01 | Overhead | 9533700 | 6657575 | 10968986
MCR029076 | HPR227 | 2023-09-01 | Labor | 11017112 | 25256040 | 26815708
MCR029077 | HPR227 | 2023-09-01 | Material | 35427653 | 81215678 | 74488746
MCR029078 | HPR227 | 2023-09-01 | Equipment | 9534419 | 21857059 | 21055217
MCR029079 | HPR227 | 2023-09-01 | Subcontract | 34613137 | 79348450 | 83768806
MCR029080 | HPR227 | 2023-09-01 | Overhead | 7742314 | 17748771 | 12055794
MCR029081 | HPR227 | 2023-10-01 | Labor | 8356182 | 24665045 | 26031146
MCR029082 | HPR227 | 2023-10-01 | Material | 26870916 | 79315219 | 76858518
MCR029083 | HPR227 | 2023-10-01 | Equipment | 7231599 | 21345601 | 23049445
MCR029084 | HPR227 | 2023-10-01 | Subcontract | 26253128 | 77491685 | 87185560
MCR029085 | HPR227 | 2023-10-01 | Overhead | 5872336 | 17333447 | 10942820
MCR029086 | HPR227 | 2023-11-01 | Labor | 5663200 | 8461604 | 8448989
MCR029087 | HPR227 | 2023-11-01 | Material | 18211113 | 27209921 | 31000803
MCR029088 | HPR227 | 2023-11-01 | Equipment | 4901041 | 7322833 | 6222287
MCR029089 | HPR227 | 2023-11-01 | Subcontract | 17792422 | 26584339 | 55237848
MCR029090 | HPR227 | 2023-11-01 | Overhead | 3979834 | 5946422 | 11166117
MCR029091 | HPR227 | 2023-12-01 | Labor | 3061321 | 11991862 | 12849082
MCR029092 | HPR227 | 2023-12-01 | Material | 9844270 | 38562150 | 37143833
MCR029093 | HPR227 | 2023-12-01 | Equipment | 2649326 | 10377986 | 11108271
MCR029094 | HPR227 | 2023-12-01 | Subcontract | 9617941 | 37675568 | 76584304
MCR029095 | HPR227 | 2023-12-01 | Overhead | 2151354 | 8427323 | 10735204
MCR029096 | HPR227 | 2024-01-01 | Labor | 810455 | 9326474 | 10987223
MCR029097 | HPR227 | 2024-01-01 | Material | 2606174 | 29991078 | 29187268
MCR029098 | HPR227 | 2024-01-01 | Equipment | 701383 | 8071308 | 9819199
MCR029099 | HPR227 | 2024-01-01 | Subcontract | 2546255 | 29301554 | 51843725
MCR029100 | HPR227 | 2024-01-01 | Overhead | 569550 | 6554212 | 10758056
MCR029101 | HPR227 | 2024-02-01 | Labor | 0 | 14724093 | 14338230
MCR029102 | HPR227 | 2024-02-01 | Material | 0 | 47348167 | 52081626
MCR029103 | HPR227 | 2024-02-01 | Equipment | 0 | 12742511 | 11962249
MCR029104 | HPR227 | 2024-02-01 | Subcontract | 0 | 46259586 | 69710310
MCR029105 | HPR227 | 2024-02-01 | Overhead | 0 | 10347408 | 11175066
MCR029106 | HPR227 | 2024-03-01 | Labor | 0 | 7070041 | 8322974
MCR029107 | HPR227 | 2024-03-01 | Material | 0 | 22735084 | 16431339
MCR029108 | HPR227 | 2024-03-01 | Equipment | 0 | 6118549 | 7301857
MCR029109 | HPR227 | 2024-03-01 | Subcontract | 0 | 22212382 | 43686283
MCR029110 | HPR227 | 2024-03-01 | Overhead | 0 | 4968496 | 10446498
MCR029111 | HPR227 | 2024-04-01 | Labor | 0 | 4068750 | 3141015
MCR029112 | HPR227 | 2024-04-01 | Material | 0 | 13083851 | 14627475
MCR029113 | HPR227 | 2024-04-01 | Equipment | 0 | 3521174 | 3495303
MCR029114 | HPR227 | 2024-04-01 | Subcontract | 0 | 12783041 | 45979381
MCR029115 | HPR227 | 2024-04-01 | Overhead | 0 | 2859328 | 11626151
MCR029116 | HPR227 | 2024-05-01 | Labor | 0 | 4755582 | 5800990
MCR029117 | HPR227 | 2024-05-01 | Material | 0 | 15292492 | 17037693
MCR029118 | HPR227 | 2024-05-01 | Equipment | 0 | 4115571 | 4533046
MCR029119 | HPR227 | 2024-05-01 | Subcontract | 0 | 14940903 | 49494855
MCR029120 | HPR227 | 2024-05-01 | Overhead | 0 | 3342002 | 11048775
MCR029121 | HPR227 | 2024-06-01 | Labor | 0 | 1790486 | 1876961
MCR029122 | HPR227 | 2024-06-01 | Material | 0 | 5757655 | 5100874
MCR029123 | HPR227 | 2024-06-01 | Equipment | 0 | 1549521 | 1654152
MCR029124 | HPR227 | 2024-06-01 | Subcontract | 0 | 5625281 | 25704646
MCR029125 | HPR227 | 2024-06-01 | Overhead | 0 | 1258271 | 11630841
MCR029126 | HPR227 | 2024-07-01 | Labor | 0 | 405859 | 405163
MCR029127 | HPR227 | 2024-07-01 | Material | 0 | 1305119 | 1432512
MCR029128 | HPR227 | 2024-07-01 | Equipment | 0 | 351238 | 314519
MCR029129 | HPR227 | 2024-07-01 | Subcontract | 0 | 1275113 | 31302954
MCR029130 | HPR227 | 2024-07-01 | Overhead | 0 | 285219 | 9970633
MCR029131 | HPR228 | 2020-05-01 | Labor | 2057296 | 802053 | 936809
MCR029132 | HPR228 | 2020-05-01 | Material | 11089168 | 4323197 | 4223705
MCR029133 | HPR228 | 2020-05-01 | Equipment | 4685617 | 1826724 | 2011090
MCR029134 | HPR228 | 2020-05-01 | Subcontract | 4956620 | 1932376 | 1884814
MCR029135 | HPR228 | 2020-05-01 | Overhead | 2536060 | 988703 | 16444101
MCR029136 | HPR228 | 2020-06-01 | Labor | 5868062 | 2210058 | 2231120
MCR029137 | HPR228 | 2020-06-01 | Material | 31629822 | 11912576 | 12514725
MCR029138 | HPR228 | 2020-06-01 | Equipment | 13364866 | 5033540 | 5208810
MCR029139 | HPR228 | 2020-06-01 | Subcontract | 14137851 | 5324666 | 5831557
MCR029140 | HPR228 | 2020-06-01 | Overhead | 7233648 | 2724372 | 18401614
MCR029141 | HPR228 | 2020-07-01 | Labor | 9229911 | 4118135 | 4821626
MCR029142 | HPR228 | 2020-07-01 | Material | 49750746 | 22197426 | 23133919
MCR029143 | HPR228 | 2020-07-01 | Equipment | 21021682 | 9379301 | 10313415
MCR029144 | HPR228 | 2020-07-01 | Subcontract | 22237515 | 9921773 | 10183407
MCR029145 | HPR228 | 2020-07-01 | Overhead | 11377851 | 5076487 | 17758848
MCR029146 | HPR228 | 2020-08-01 | Labor | 12152261 | 5486313 | 5218861
MCR029147 | HPR228 | 2020-08-01 | Material | 65502693 | 29572135 | 26190369
MCR029148 | HPR228 | 2020-08-01 | Equipment | 27677510 | 12495411 | 11483403
MCR029149 | HPR228 | 2020-08-01 | Subcontract | 29278297 | 13218109 | 14403692
MCR029150 | HPR228 | 2020-08-01 | Overhead | 14980276 | 6763061 | 17537393
MCR029151 | HPR228 | 2020-09-01 | Labor | 14644954 | 8892439 | 10748376
MCR029152 | HPR228 | 2020-09-01 | Material | 78938722 | 47931716 | 52877022
MCR029153 | HPR228 | 2020-09-01 | Equipment | 33354770 | 20253069 | 22747022
MCR029154 | HPR228 | 2020-09-01 | Subcontract | 35283913 | 21424447 | 21005739
MCR029155 | HPR228 | 2020-09-01 | Overhead | 18053056 | 10961844 | 16812563
MCR029156 | HPR228 | 2020-10-01 | Labor | 16718309 | 11217014 | 11865494
MCR029157 | HPR228 | 2020-10-01 | Material | 90114450 | 60461561 | 57010871
MCR029158 | HPR228 | 2020-10-01 | Equipment | 38076963 | 25547430 | 27629691
MCR029159 | HPR228 | 2020-10-01 | Subcontract | 40279223 | 27025019 | 28738733
MCR029160 | HPR228 | 2020-10-01 | Overhead | 20608913 | 13827383 | 15695445
MCR029161 | HPR228 | 2020-11-01 | Labor | 18383174 | 7474090 | 7587831
MCR029162 | HPR228 | 2020-11-01 | Material | 99088345 | 40286582 | 43202083
MCR029163 | HPR228 | 2020-11-01 | Equipment | 41868793 | 17022694 | 16255532
MCR029164 | HPR228 | 2020-11-01 | Subcontract | 44290361 | 18007237 | 19149279
MCR029165 | HPR228 | 2020-11-01 | Overhead | 22661217 | 9213424 | 16721543
MCR029166 | HPR228 | 2020-12-01 | Labor | 19650988 | 17864962 | 20342376
MCR029167 | HPR228 | 2020-12-01 | Material | 105922075 | 96295095 | 97687201
MCR029168 | HPR228 | 2020-12-01 | Equipment | 44756317 | 40688533 | 41373581
MCR029169 | HPR228 | 2020-12-01 | Subcontract | 47344892 | 43041839 | 41061684
MCR029170 | HPR228 | 2020-12-01 | Overhead | 24224071 | 22022409 | 17599523
MCR029171 | HPR228 | 2021-01-01 | Labor | 20533865 | 20451278 | 20614192
MCR029172 | HPR228 | 2021-01-01 | Material | 110680925 | 110235770 | 105281457
MCR029173 | HPR228 | 2021-01-01 | Equipment | 46767122 | 46579026 | 48081704
MCR029174 | HPR228 | 2021-01-01 | Subcontract | 49471995 | 49273021 | 53423727
MCR029175 | HPR228 | 2021-01-01 | Overhead | 25312406 | 25210600 | 17305947
MCR029176 | HPR228 | 2021-02-01 | Labor | 21044680 | 11104706 | 14475528
MCR029177 | HPR228 | 2021-02-01 | Material | 113434306 | 59856202 | 69773457
MCR029178 | HPR228 | 2021-02-01 | Equipment | 47930535 | 25291642 | 30149404
MCR029179 | HPR228 | 2021-02-01 | Subcontract | 50702697 | 26754436 | 26980833
MCR029180 | HPR228 | 2021-02-01 | Overhead | 25942096 | 13688939 | 16998468
MCR029181 | HPR228 | 2021-03-01 | Labor | 21197192 | 6676937 | 21615513
MCR029182 | HPR228 | 2021-03-01 | Material | 114256368 | 35989792 | 80387099
MCR029183 | HPR228 | 2021-03-01 | Equipment | 48277890 | 15207128 | 16144232
MCR029184 | HPR228 | 2021-03-01 | Subcontract | 51070142 | 16086664 | 16732025
MCR029185 | HPR228 | 2021-03-01 | Overhead | 26130099 | 8230761 | 15039789
MCR029186 | HPR228 | 2021-04-01 | Labor | 21006179 | 19109348 | 34853068
MCR029187 | HPR228 | 2021-04-01 | Material | 113226777 | 103002543 | 174710262
MCR029188 | HPR228 | 2021-04-01 | Equipment | 47842846 | 43522698 | 44207800
MCR029189 | HPR228 | 2021-04-01 | Subcontract | 50609936 | 46039923 | 45511372
MCR029190 | HPR228 | 2021-04-01 | Overhead | 25894635 | 23556382 | 14669645
MCR029191 | HPR228 | 2021-05-01 | Labor | 20487625 | 11383156 | 9465742
MCR029192 | HPR228 | 2021-05-01 | Material | 110431685 | 61357094 | 44534285
MCR029193 | HPR228 | 2021-05-01 | Equipment | 46661808 | 25925829 | 30451367
MCR029194 | HPR228 | 2021-05-01 | Subcontract | 49360590 | 27425303 | 29273957
MCR029195 | HPR228 | 2021-05-01 | Overhead | 25255405 | 14032189 | 15775241
MCR029196 | HPR228 | 2021-06-01 | Labor | 19658950 | 23575440 | 26196157
MCR029197 | HPR228 | 2021-06-01 | Material | 105964987 | 127075519 | 128682835
MCR029198 | HPR228 | 2021-06-01 | Equipment | 44774449 | 53694494 | 62846093
MCR029199 | HPR228 | 2021-06-01 | Subcontract | 47364073 | 56800027 | 59194796
MCR029200 | HPR228 | 2021-06-01 | Overhead | 24233885 | 29061802 | 17606865
MCR029201 | HPR228 | 2021-07-01 | Labor | 18539316 | 10094166 | 10025960
MCR029202 | HPR228 | 2021-07-01 | Material | 99929975 | 54409224 | 62372347
MCR029203 | HPR228 | 2021-07-01 | Equipment | 42224415 | 22990075 | 16589173
MCR029204 | HPR228 | 2021-07-01 | Subcontract | 44666552 | 24319754 | 20205726
MCR029205 | HPR228 | 2021-07-01 | Overhead | 22853695 | 12443231 | 16274290
MCR029206 | HPR228 | 2021-08-01 | Labor | 17150045 | 13868599 | 14552600
MCR029207 | HPR228 | 2021-08-01 | Material | 92441575 | 74754043 | 73839059
MCR029208 | HPR228 | 2021-08-01 | Equipment | 39060266 | 31586576 | 38630692
MCR029209 | HPR228 | 2021-08-01 | Subcontract | 41319398 | 33413451 | 33235264
MCR029210 | HPR228 | 2021-08-01 | Overhead | 21141120 | 17096032 | 17158681
MCR029211 | HPR228 | 2021-09-01 | Labor | 15515196 | 18551092 | 19679628
MCR029212 | HPR228 | 2021-09-01 | Material | 83629470 | 99993454 | 116867660
MCR029213 | HPR228 | 2021-09-01 | Equipment | 35336799 | 42251237 | 43366862
MCR029214 | HPR228 | 2021-09-01 | Subcontract | 37380576 | 44694926 | 39352400
MCR029215 | HPR228 | 2021-09-01 | Overhead | 19125817 | 22868212 | 16669905
MCR029216 | HPR228 | 2021-10-01 | Labor | 13662409 | 10516159 | 11525320
MCR029217 | HPR228 | 2021-10-01 | Material | 73642643 | 56683836 | 57730897
MCR029218 | HPR228 | 2021-10-01 | Equipment | 31116965 | 23951190 | 23889830
MCR029219 | HPR228 | 2021-10-01 | Subcontract | 32916679 | 25336457 | 28302367
MCR029220 | HPR228 | 2021-10-01 | Overhead | 16841858 | 12963429 | 16614078
MCR029221 | HPR228 | 2021-11-01 | Labor | 11624189 | 12691280 | 13104960
MCR029222 | HPR228 | 2021-11-01 | Material | 62656302 | 68408097 | 76394541
MCR029223 | HPR228 | 2021-11-01 | Equipment | 26474796 | 28905160 | 29639305
MCR029224 | HPR228 | 2021-11-01 | Subcontract | 28006021 | 30576950 | 30027242
MCR029225 | HPR228 | 2021-11-01 | Overhead | 14329314 | 15644733 | 16531212
MCR029226 | HPR228 | 2021-12-01 | Labor | 9440000 | 12484322 | 11924733
MCR029227 | HPR228 | 2021-12-01 | Material | 50883159 | 67292561 | 65994291
MCR029228 | HPR228 | 2021-12-01 | Equipment | 21500172 | 28433801 | 32453361
MCR029229 | HPR228 | 2021-12-01 | Subcontract | 22743679 | 30078329 | 31852317
MCR029230 | HPR228 | 2021-12-01 | Overhead | 11636831 | 15389613 | 15839024
MCR029231 | HPR228 | 2022-01-01 | Labor | 7159985 | 9174264 | 11097113
MCR029232 | HPR228 | 2022-01-01 | Material | 38593500 | 49450800 | 51214376
MCR029233 | HPR228 | 2022-01-01 | Equipment | 16307299 | 20894943 | 22124774
MCR029234 | HPR228 | 2022-01-01 | Subcontract | 17250465 | 22103445 | 22623524
MCR029235 | HPR228 | 2022-01-01 | Overhead | 8826221 | 11309254 | 18078532
MCR029236 | HPR228 | 2022-02-01 | Labor | 4852506 | 14000346 | 13607817
MCR029237 | HPR228 | 2022-02-01 | Material | 26155811 | 75464181 | 76707655
MCR029238 | HPR228 | 2022-02-01 | Equipment | 11051877 | 31886637 | 31011793
MCR029239 | HPR228 | 2022-02-01 | Subcontract | 11691085 | 33730867 | 32620260
MCR029240 | HPR228 | 2022-02-01 | Overhead | 5981758 | 17258439 | 15808291
MCR029241 | HPR228 | 2022-03-01 | Labor | 2623090 | 9366384 | 10632093
MCR029242 | HPR228 | 2022-03-01 | Material | 14138887 | 50486355 | 59659773
MCR029243 | HPR228 | 2022-03-01 | Equipment | 5974246 | 21332506 | 25353743
MCR029244 | HPR228 | 2022-03-01 | Subcontract | 6319779 | 22566316 | 32572202
MCR029245 | HPR228 | 2022-03-01 | Overhead | 3233522 | 11546083 | 16180799
MCR029246 | HPR228 | 2022-04-01 | Labor | 694437 | 11748728 | 12493420
MCR029247 | HPR228 | 2022-04-01 | Material | 3743131 | 63327587 | 69987626
MCR029248 | HPR228 | 2022-04-01 | Equipment | 1581623 | 26758441 | 32882443
MCR029249 | HPR228 | 2022-04-01 | Subcontract | 1673099 | 28306071 | 53382591
MCR029250 | HPR228 | 2022-04-01 | Overhead | 856043 | 14482835 | 16089029
MCR029251 | HPR228 | 2022-05-01 | Labor | 0 | 8592004 | 8456371
MCR029252 | HPR228 | 2022-05-01 | Material | 0 | 46312321 | 51309977
MCR029253 | HPR228 | 2022-05-01 | Equipment | 0 | 19568810 | 17488324
MCR029254 | HPR228 | 2022-05-01 | Subcontract | 0 | 20700612 | 36837156
MCR029255 | HPR228 | 2022-05-01 | Overhead | 0 | 10591493 | 15363665
MCR029256 | HPR228 | 2022-06-01 | Labor | 0 | 9114584 | 10904137
MCR029257 | HPR228 | 2022-06-01 | Material | 0 | 49129113 | 50504505
MCR029258 | HPR228 | 2022-06-01 | Equipment | 0 | 20759017 | 23347933
MCR029259 | HPR228 | 2022-06-01 | Subcontract | 0 | 21959658 | 34248718
MCR029260 | HPR228 | 2022-06-01 | Overhead | 0 | 11235685 | 16412605
MCR029261 | HPR228 | 2022-07-01 | Labor | 0 | 6275918 | 5655538
MCR029262 | HPR228 | 2022-07-01 | Material | 0 | 33828234 | 38587052
MCR029263 | HPR228 | 2022-07-01 | Equipment | 0 | 14293783 | 14202357
MCR029264 | HPR228 | 2022-07-01 | Subcontract | 0 | 15120494 | 34697423
MCR029265 | HPR228 | 2022-07-01 | Overhead | 0 | 7736419 | 16176302
MCR029266 | HPR228 | 2022-08-01 | Labor | 0 | 5963300 | 6114841
MCR029267 | HPR228 | 2022-08-01 | Material | 0 | 32143171 | 40030239
MCR029268 | HPR228 | 2022-08-01 | Equipment | 0 | 13581777 | 17269124
MCR029269 | HPR228 | 2022-08-01 | Subcontract | 0 | 14367307 | 33679422
MCR029270 | HPR228 | 2022-08-01 | Overhead | 0 | 7351050 | 16913775
MCR029271 | HPR228 | 2022-09-01 | Labor | 0 | 4301967 | 4515862
MCR029272 | HPR228 | 2022-09-01 | Material | 0 | 23188315 | 21248810
MCR029273 | HPR228 | 2022-09-01 | Equipment | 0 | 9797991 | 9532949
MCR029274 | HPR228 | 2022-09-01 | Subcontract | 0 | 10364678 | 18959788
MCR029275 | HPR228 | 2022-09-01 | Overhead | 0 | 5303100 | 15836988
MCR029276 | HPR228 | 2022-10-01 | Labor | 0 | 8471783 | 8908995
MCR029277 | HPR228 | 2022-10-01 | Material | 0 | 45664310 | 55306783
MCR029278 | HPR228 | 2022-10-01 | Equipment | 0 | 19294999 | 21122295
MCR029279 | HPR228 | 2022-10-01 | Subcontract | 0 | 20410965 | 33653817
MCR029280 | HPR228 | 2022-10-01 | Overhead | 0 | 10443295 | 16450814
MCR029281 | HPR228 | 2022-11-01 | Labor | 0 | 3331605 | 3391227
MCR029282 | HPR228 | 2022-11-01 | Material | 0 | 17957901 | 16823400
MCR029283 | HPR228 | 2022-11-01 | Equipment | 0 | 7587932 | 10103026
MCR029284 | HPR228 | 2022-11-01 | Subcontract | 0 | 8026796 | 30288038
MCR029285 | HPR228 | 2022-11-01 | Overhead | 0 | 4106920 | 16124489
MCR029286 | HPR228 | 2022-12-01 | Labor | 0 | 1643987 | 1879995
MCR029287 | HPR228 | 2022-12-01 | Material | 0 | 8861360 | 9423777
MCR029288 | HPR228 | 2022-12-01 | Equipment | 0 | 3744279 | 4622947
MCR029289 | HPR228 | 2022-12-01 | Subcontract | 0 | 3960838 | 26105488
MCR029290 | HPR228 | 2022-12-01 | Overhead | 0 | 2026567 | 17494304
MCR029291 | HPR228 | 2023-01-01 | Labor | 0 | 1748503 | 1504367
MCR029292 | HPR228 | 2023-01-01 | Material | 0 | 9424718 | 9998076
MCR029293 | HPR228 | 2023-01-01 | Equipment | 0 | 3982321 | 4990918
MCR029294 | HPR228 | 2023-01-01 | Subcontract | 0 | 4212646 | 23298680
MCR029295 | HPR228 | 2023-01-01 | Overhead | 0 | 2155406 | 16878830
MCR029296 | HPR228 | 2023-02-01 | Labor | 0 | 1090616 | 1408945
MCR029297 | HPR228 | 2023-02-01 | Material | 0 | 5878599 | 6793099
MCR029298 | HPR228 | 2023-02-01 | Equipment | 0 | 2483943 | 2983263
MCR029299 | HPR228 | 2023-02-01 | Subcontract | 0 | 2627607 | 18111467
MCR029300 | HPR228 | 2023-02-01 | Overhead | 0 | 1344418 | 15794493
MCR029301 | HPR228 | 2023-03-01 | Labor | 0 | 499082 | 459468
MCR029302 | HPR228 | 2023-03-01 | Material | 0 | 2690133 | 2371582
MCR029303 | HPR228 | 2023-03-01 | Equipment | 0 | 1136689 | 2057110
MCR029304 | HPR228 | 2023-03-01 | Subcontract | 0 | 1202432 | 20730631
MCR029305 | HPR228 | 2023-03-01 | Overhead | 0 | 615226 | 17843992
MCR029306 | HPR229 | 2020-12-01 | Labor | 3237225 | 2274631 | 2296088
MCR029307 | HPR229 | 2020-12-01 | Material | 11539647 | 8108314 | 8948156
MCR029308 | HPR229 | 2020-12-01 | Equipment | 2754856 | 1935695 | 1771856
MCR029309 | HPR229 | 2020-12-01 | Subcontract | 9077420 | 6378234 | 6474962
MCR029310 | HPR229 | 2020-12-01 | Overhead | 2386473 | 1676851 | 11132707
MCR029311 | HPR229 | 2021-01-01 | Labor | 8986493 | 4636981 | 4306157
MCR029312 | HPR229 | 2021-01-01 | Material | 32033907 | 16529318 | 17686241
MCR029313 | HPR229 | 2021-01-01 | Equipment | 7647443 | 3946038 | 4709944
MCR029314 | HPR229 | 2021-01-01 | Subcontract | 25198795 | 13002438 | 13100760
MCR029315 | HPR229 | 2021-01-01 | Overhead | 6624816 | 3418368 | 11819039
MCR029316 | HPR229 | 2021-02-01 | Labor | 13673254 | 13764819 | 13014013
MCR029317 | HPR229 | 2021-02-01 | Material | 48740675 | 49067072 | 51246145
MCR029318 | HPR229 | 2021-02-01 | Equipment | 11635844 | 11713765 | 11614348
MCR029319 | HPR229 | 2021-02-01 | Subcontract | 38340821 | 38597575 | 37372230
MCR029320 | HPR229 | 2021-02-01 | Overhead | 10079883 | 10147384 | 9965547
MCR029321 | HPR229 | 2021-03-01 | Labor | 17333051 | 17653746 | 20121114
MCR029322 | HPR229 | 2021-03-01 | Material | 61786652 | 62929825 | 70956754
MCR029323 | HPR229 | 2021-03-01 | Equipment | 14750305 | 15023215 | 14410365
MCR029324 | HPR229 | 2021-03-01 | Subcontract | 48603163 | 49502417 | 56213248
MCR029325 | HPR229 | 2021-03-01 | Overhead | 12777874 | 13014290 | 10317047
MCR029326 | HPR229 | 2021-04-01 | Labor | 20004075 | 22181105 | 20026601
MCR029327 | HPR229 | 2021-04-01 | Material | 71307979 | 79068376 | 80576812
MCR029328 | HPR229 | 2021-04-01 | Equipment | 17023328 | 18875965 | 22889756
MCR029329 | HPR229 | 2021-04-01 | Subcontract | 56092914 | 62197466 | 65671158
MCR029330 | HPR229 | 2021-04-01 | Overhead | 14746945 | 16351845 | 10626044
MCR029331 | HPR229 | 2021-05-01 | Labor | 21727655 | 22515629 | 24598638
MCR029332 | HPR229 | 2021-05-01 | Material | 77451977 | 80260845 | 85338040
MCR029333 | HPR229 | 2021-05-01 | Equipment | 18490083 | 19160643 | 16419187
MCR029334 | HPR229 | 2021-05-01 | Subcontract | 60925960 | 63135497 | 60354573
MCR029335 | HPR229 | 2021-05-01 | Overhead | 16017563 | 16598455 | 11063489
MCR029336 | HPR229 | 2021-06-01 | Labor | 22548892 | 11741130 | 11260716
MCR029337 | HPR229 | 2021-06-01 | Material | 80379417 | 41853284 | 55489064
MCR029338 | HPR229 | 2021-06-01 | Equipment | 19188949 | 9991620 | 10020111
MCR029339 | HPR229 | 2021-06-01 | Subcontract | 63228769 | 32923001 | 37553822
MCR029340 | HPR229 | 2021-06-01 | Overhead | 16622977 | 8655526 | 10488988
MCR029341 | HPR229 | 2021-07-01 | Labor | 22517517 | 12922936 | 12688551
MCR029342 | HPR229 | 2021-07-01 | Material | 80267575 | 46066037 | 52752685
MCR029343 | HPR229 | 2021-07-01 | Equipment | 19162250 | 10997329 | 11430826
MCR029344 | HPR229 | 2021-07-01 | Subcontract | 63140791 | 36236874 | 31242151
MCR029345 | HPR229 | 2021-07-01 | Overhead | 16599847 | 9526751 | 9452773
MCR029346 | HPR229 | 2021-08-01 | Labor | 21689076 | 18854299 | 19884024
MCR029347 | HPR229 | 2021-08-01 | Material | 77314454 | 67209401 | 81998525
MCR029348 | HPR229 | 2021-08-01 | Equipment | 18457252 | 16044876 | 16990858
MCR029349 | HPR229 | 2021-08-01 | Subcontract | 60817781 | 52868855 | 59805161
MCR029350 | HPR229 | 2021-08-01 | Overhead | 15989123 | 13899333 | 10498536
MCR029351 | HPR229 | 2021-09-01 | Labor | 20126636 | 22648626 | 22121841
MCR029352 | HPR229 | 2021-09-01 | Material | 71744868 | 80734937 | 98614399
MCR029353 | HPR229 | 2021-09-01 | Equipment | 17127627 | 19273823 | 20134043
MCR029354 | HPR229 | 2021-09-01 | Subcontract | 56436584 | 63508431 | 54075103
MCR029355 | HPR229 | 2021-09-01 | Overhead | 14837297 | 16696501 | 9750406
MCR029356 | HPR229 | 2021-10-01 | Labor | 17903364 | 19400912 | 20023598
MCR029357 | HPR229 | 2021-10-01 | Material | 63819630 | 69157898 | 78808387
MCR029358 | HPR229 | 2021-10-01 | Equipment | 15235637 | 16510040 | 13708938
MCR029359 | HPR229 | 2021-10-01 | Subcontract | 50202362 | 54401598 | 59073362
MCR029360 | HPR229 | 2021-10-01 | Overhead | 13198307 | 14302295 | 9836676
MCR029361 | HPR229 | 2021-11-01 | Labor | 15106678 | 16510232 | 16846055
MCR029362 | HPR229 | 2021-11-01 | Material | 53850360 | 58853571 | 74825430
MCR029363 | HPR229 | 2021-11-01 | Equipment | 12855677 | 14050092 | 16309549
MCR029364 | HPR229 | 2021-11-01 | Subcontract | 42360247 | 46295917 | 49043770
MCR029365 | HPR229 | 2021-11-01 | Overhead | 11136598 | 12171294 | 10501100
MCR029366 | HPR229 | 2021-12-01 | Labor | 11845555 | 14821545 | 14688941
MCR029367 | HPR229 | 2021-12-01 | Material | 42225526 | 52833954 | 67810474
MCR029368 | HPR229 | 2021-12-01 | Equipment | 10080485 | 12613031 | 10990478
MCR029369 | HPR229 | 2021-12-01 | Subcontract | 33215817 | 41560713 | 40189216
MCR029370 | HPR229 | 2021-12-01 | Overhead | 8732508 | 10926399 | 11557540
MCR029371 | HPR229 | 2022-01-01 | Labor | 8265138 | 12027718 | 13920989
MCR029372 | HPR229 | 2022-01-01 | Material | 29462510 | 42874877 | 47325607
MCR029373 | HPR229 | 2022-01-01 | Equipment | 7033574 | 10235504 | 10970459
MCR029374 | HPR229 | 2022-01-01 | Subcontract | 23176060 | 33726616 | 35931804
MCR029375 | HPR229 | 2022-01-01 | Overhead | 6093035 | 8866798 | 11045448
MCR029376 | HPR229 | 2022-02-01 | Labor | 4582904 | 8932990 | 8627297
MCR029377 | HPR229 | 2022-02-01 | Material | 16336551 | 31843185 | 35111900
MCR029378 | HPR229 | 2022-02-01 | Equipment | 3900019 | 7601912 | 6662663
MCR029379 | HPR229 | 2022-02-01 | Subcontract | 12850802 | 25048768 | 29195152
MCR029380 | HPR229 | 2022-02-01 | Overhead | 3378503 | 6585374 | 10159204
MCR029381 | HPR229 | 2022-03-01 | Labor | 1238526 | 5384566 | 5219860
MCR029382 | HPR229 | 2022-03-01 | Material | 4414938 | 19194214 | 30683319
MCR029383 | HPR229 | 2022-03-01 | Equipment | 1053977 | 4582228 | 5709160
MCR029384 | HPR229 | 2022-03-01 | Subcontract | 3472918 | 15098723 | 12450758
MCR029385 | HPR229 | 2022-03-01 | Overhead | 913037 | 3969486 | 10255437
MCR029386 | HPR229 | 2022-04-01 | Labor | 0 | 3164756 | 3875505
MCR029387 | HPR229 | 2022-04-01 | Material | 0 | 11281319 | 12367347
MCR029388 | HPR229 | 2022-04-01 | Equipment | 0 | 2693185 | 2571355
MCR029389 | HPR229 | 2022-04-01 | Subcontract | 0 | 8874211 | 9271184
MCR029390 | HPR229 | 2022-04-01 | Overhead | 0 | 2333049 | 10676937
MCR029391 | HPR229 | 2022-05-01 | Labor | 0 | 1349419 | 1211285
MCR029392 | HPR229 | 2022-05-01 | Material | 0 | 4810236 | 5389668
MCR029393 | HPR229 | 2022-05-01 | Equipment | 0 | 1148346 | 1206018
MCR029394 | HPR229 | 2022-05-01 | Subcontract | 0 | 3783870 | 4612075
MCR029395 | HPR229 | 2022-05-01 | Overhead | 0 | 994788 | 10943634
MCR029396 | HPR230 | 2023-02-01 | Labor | 3540486 | 3264501 | 3197737
MCR029397 | HPR230 | 2023-02-01 | Material | 8867434 | 8176208 | 8667928
MCR029398 | HPR230 | 2023-02-01 | Equipment | 2822865 | 2602820 | 3035694
MCR029399 | HPR230 | 2023-02-01 | Subcontract | 14371930 | 13251623 | 13211540
MCR029400 | HPR230 | 2023-02-01 | Overhead | 2939338 | 2710214 | 12897665
MCR029401 | HPR230 | 2023-03-01 | Labor | 9773570 | 7233432 | 7380062
MCR029402 | HPR230 | 2023-03-01 | Material | 24478697 | 18116714 | 17313288
MCR029403 | HPR230 | 2023-03-01 | Equipment | 7792565 | 5767287 | 6047669
MCR029404 | HPR230 | 2023-03-01 | Subcontract | 39673948 | 29362739 | 32737721
MCR029405 | HPR230 | 2023-03-01 | Overhead | 8114091 | 6005249 | 12341369
MCR029406 | HPR230 | 2023-04-01 | Labor | 14766547 | 9965394 | 11222275
MCR029407 | HPR230 | 2023-04-01 | Material | 36984010 | 24959136 | 21152794
MCR029408 | HPR230 | 2023-04-01 | Equipment | 11773515 | 7945509 | 8149625
MCR029409 | HPR230 | 2023-04-01 | Subcontract | 59941985 | 40452622 | 41522590
MCR029410 | HPR230 | 2023-04-01 | Overhead | 12259298 | 8273345 | 12355590
MCR029411 | HPR230 | 2023-05-01 | Labor | 18564233 | 19464095 | 24216448
MCR029412 | HPR230 | 2023-05-01 | Material | 46495623 | 48749399 | 46322985
MCR029413 | HPR230 | 2023-05-01 | Equipment | 14801449 | 15518918 | 14422535
MCR029414 | HPR230 | 2023-05-01 | Subcontract | 75357971 | 79010789 | 81383217
MCR029415 | HPR230 | 2023-05-01 | Overhead | 15412166 | 16159238 | 12778405
MCR029416 | HPR230 | 2023-06-01 | Labor | 21215078 | 26673787 | 25849684
MCR029417 | HPR230 | 2023-06-01 | Material | 53134879 | 66806656 | 64124809
MCR029418 | HPR230 | 2023-06-01 | Equipment | 16914994 | 21267277 | 23971363
MCR029419 | HPR230 | 2023-06-01 | Subcontract | 86118572 | 108277161 | 100246493
MCR029420 | HPR230 | 2023-06-01 | Overhead | 17612917 | 22144778 | 11976530
MCR029421 | HPR230 | 2023-07-01 | Labor | 22771892 | 17495117 | 20160678
MCR029422 | HPR230 | 2023-07-01 | Material | 57034044 | 43817935 | 40973432
MCR029423 | HPR230 | 2023-07-01 | Equipment | 18156257 | 13949032 | 14662660
MCR029424 | HPR230 | 2023-07-01 | Subcontract | 92438161 | 71018098 | 90743688
MCR029425 | HPR230 | 2023-07-01 | Overhead | 18905396 | 14524578 | 13045232
MCR029426 | HPR230 | 2023-08-01 | Labor | 23292828 | 19190662 | 19899196
MCR029427 | HPR230 | 2023-08-01 | Material | 58338770 | 48064564 | 41363853
MCR029428 | HPR230 | 2023-08-01 | Equipment | 18571604 | 15300906 | 13780298
MCR029429 | HPR230 | 2023-08-01 | Subcontract | 94552801 | 77900839 | 64598701
MCR029430 | HPR230 | 2023-08-01 | Overhead | 19337880 | 15932231 | 12270676
MCR029431 | HPR230 | 2023-09-01 | Labor | 22842739 | 30509041 | 32837562
MCR029432 | HPR230 | 2023-09-01 | Material | 57211487 | 76412360 | 75336730
MCR029433 | HPR230 | 2023-09-01 | Equipment | 18212745 | 24325164 | 23620255
MCR029434 | HPR230 | 2023-09-01 | Subcontract | 92725753 | 123845646 | 118000354
MCR029435 | HPR230 | 2023-09-01 | Overhead | 18964214 | 25328835 | 12528522
MCR029436 | HPR230 | 2023-10-01 | Labor | 21495131 | 28180256 | 30313041
MCR029437 | HPR230 | 2023-10-01 | Material | 53836294 | 70579729 | 62237125
MCR029438 | HPR230 | 2023-10-01 | Equipment | 17138283 | 22468400 | 23766153
MCR029439 | HPR230 | 2023-10-01 | Subcontract | 87255394 | 114392385 | 120689053
MCR029440 | HPR230 | 2023-10-01 | Overhead | 17845419 | 23395460 | 11529993
MCR029441 | HPR230 | 2023-11-01 | Labor | 19335100 | 17257948 | 21199410
MCR029442 | HPR230 | 2023-11-01 | Material | 48426320 | 43223927 | 38069444
MCR029443 | HPR230 | 2023-11-01 | Equipment | 15416068 | 13759935 | 11635547
MCR029444 | HPR230 | 2023-11-01 | Subcontract | 78487157 | 70055356 | 71964935
MCR029445 | HPR230 | 2023-11-01 | Overhead | 16052145 | 14327678 | 13996840
MCR029446 | HPR230 | 2023-12-01 | Labor | 16464065 | 21424467 | 25939827
MCR029447 | HPR230 | 2023-12-01 | Material | 41235582 | 53659310 | 56620789
MCR029448 | HPR230 | 2023-12-01 | Equipment | 13126964 | 17081942 | 18450806
MCR029449 | HPR230 | 2023-12-01 | Subcontract | 66832739 | 86968546 | 91945133
MCR029450 | HPR230 | 2023-12-01 | Overhead | 13668591 | 17786753 | 12687001
MCR029451 | HPR230 | 2024-01-01 | Labor | 13008074 | 7971135 | 9187381
MCR029452 | HPR230 | 2024-01-01 | Material | 32579773 | 19964353 | 15000757
MCR029453 | HPR230 | 2024-01-01 | Equipment | 10371468 | 6355466 | 6537209
MCR029454 | HPR230 | 2024-01-01 | Subcontract | 52803801 | 32357306 | 32167137
MCR029455 | HPR230 | 2024-01-01 | Overhead | 10799401 | 6617696 | 12670141
MCR029456 | HPR230 | 2024-02-01 | Labor | 9134361 | 8248487 | 9228580
MCR029457 | HPR230 | 2024-02-01 | Material | 22877745 | 20659003 | 19812546
MCR029458 | HPR230 | 2024-02-01 | Equipment | 7282917 | 6576601 | 5659274
MCR029459 | HPR230 | 2024-02-01 | Subcontract | 37079200 | 33483163 | 31487846
MCR029460 | HPR230 | 2024-02-01 | Overhead | 7583415 | 6847956 | 12130357
MCR029461 | HPR230 | 2024-03-01 | Labor | 5092257 | 4172256 | 4864966
MCR029462 | HPR230 | 2024-03-01 | Material | 12753969 | 10449753 | 9523529
MCR029463 | HPR230 | 2024-03-01 | Equipment | 4060107 | 3326582 | 2979470
MCR029464 | HPR230 | 2024-03-01 | Subcontract | 20671048 | 16936480 | 18580344
MCR029465 | HPR230 | 2024-03-01 | Overhead | 4227630 | 3463838 | 12650080
MCR029466 | HPR230 | 2024-04-01 | Labor | 1382035 | 1627817 | 1826097
MCR029467 | HPR230 | 2024-04-01 | Material | 3461417 | 4077000 | 3917851
MCR029468 | HPR230 | 2024-04-01 | Equipment | 1101910 | 1297875 | 1408124
MCR029469 | HPR230 | 2024-04-01 | Subcontract | 5610107 | 6607815 | 6587045
MCR029470 | HPR230 | 2024-04-01 | Overhead | 1147376 | 1351426 | 12761691
MCR029471 | HPR231 | 2020-07-01 | Labor | 6880111 | 2868911 | 2802408
MCR029472 | HPR231 | 2020-07-01 | Material | 14171335 | 5909251 | 6233732
MCR029473 | HPR231 | 2020-07-01 | Equipment | 2751654 | 1147402 | 1265426
MCR029474 | HPR231 | 2020-07-01 | Subcontract | 13241123 | 5521366 | 5455942
MCR029475 | HPR231 | 2020-07-01 | Overhead | 3509546 | 1463432 | 16248471
MCR029476 | HPR231 | 2020-08-01 | Labor | 19275445 | 5769216 | 6708293
MCR029477 | HPR231 | 2020-08-01 | Material | 39702673 | 11883166 | 10653423
MCR029478 | HPR231 | 2020-08-01 | Equipment | 7709085 | 2307360 | 2464754
MCR029479 | HPR231 | 2020-08-01 | Subcontract | 37096575 | 11103151 | 11893565
MCR029480 | HPR231 | 2020-08-01 | Overhead | 9832408 | 2942878 | 16254057
MCR029481 | HPR231 | 2020-09-01 | Labor | 29665243 | 12120932 | 12506676
MCR029482 | HPR231 | 2020-09-01 | Material | 61103101 | 24966138 | 22982099
MCR029483 | HPR231 | 2020-09-01 | Equipment | 11864416 | 4847686 | 5117264
MCR029484 | HPR231 | 2020-09-01 | Subcontract | 57092272 | 23327352 | 25077579
MCR029485 | HPR231 | 2020-09-01 | Overhead | 15132246 | 6182890 | 16114558
MCR029486 | HPR231 | 2020-10-01 | Labor | 38107909 | 16101973 | 18053665
MCR029487 | HPR231 | 2020-10-01 | Material | 78492916 | 33166101 | 32366853
MCR029488 | HPR231 | 2020-10-01 | Equipment | 15241003 | 6439876 | 7037364
MCR029489 | HPR231 | 2020-10-01 | Subcontract | 73340613 | 30989066 | 29510090
MCR029490 | HPR231 | 2020-10-01 | Overhead | 19438852 | 8213619 | 17693618
MCR029491 | HPR231 | 2020-11-01 | Labor | 44665597 | 28685301 | 32888753
MCR029492 | HPR231 | 2020-11-01 | Material | 92000139 | 59084661 | 64775012
MCR029493 | HPR231 | 2020-11-01 | Equipment | 17863707 | 11472494 | 11775516
MCR029494 | HPR231 | 2020-11-01 | Subcontract | 85961217 | 55206323 | 55999258
MCR029495 | HPR231 | 2020-11-01 | Overhead | 22783930 | 14632378 | 17630271
MCR029496 | HPR231 | 2020-12-01 | Labor | 49404801 | 28721230 | 27787684
MCR029497 | HPR231 | 2020-12-01 | Material | 101761733 | 59158666 | 58665163
MCR029498 | HPR231 | 2020-12-01 | Equipment | 19759120 | 11486864 | 12658793
MCR029499 | HPR231 | 2020-12-01 | Subcontract | 95082057 | 55275470 | 57876291
MCR029500 | HPR231 | 2020-12-01 | Overhead | 25201399 | 14650705 | 18061719
MCR029501 | HPR231 | 2021-01-01 | Labor | 52397096 | 30040474 | 31573722
MCR029502 | HPR231 | 2021-01-01 | Material | 107925124 | 61875985 | 58167808
MCR029503 | HPR231 | 2021-01-01 | Equipment | 20955868 | 12014487 | 11559377
MCR029504 | HPR231 | 2021-01-01 | Subcontract | 100840881 | 57814423 | 51932074
MCR029505 | HPR231 | 2021-01-01 | Overhead | 26727769 | 15323652 | 17123584
MCR029506 | HPR231 | 2021-02-01 | Labor | 53720086 | 32616776 | 32076127
MCR029507 | HPR231 | 2021-02-01 | Material | 110650159 | 67182532 | 66549079
MCR029508 | HPR231 | 2021-02-01 | Equipment | 21484989 | 13044861 | 13811615
MCR029509 | HPR231 | 2021-02-01 | Subcontract | 103387043 | 62772647 | 75106276
MCR029510 | HPR231 | 2021-02-01 | Overhead | 27402627 | 16637824 | 17889874
MCR029511 | HPR231 | 2021-03-01 | Labor | 53458650 | 55222871 | 56558132
MCR029512 | HPR231 | 2021-03-01 | Material | 110111665 | 113745524 | 117007137
MCR029513 | HPR231 | 2021-03-01 | Equipment | 21380430 | 22086018 | 21890021
MCR029514 | HPR231 | 2021-03-01 | Subcontract | 102883896 | 106279227 | 107514767
MCR029515 | HPR231 | 2021-03-01 | Overhead | 27269268 | 28169197 | 17744505
MCR029516 | HPR231 | 2021-04-01 | Labor | 51706615 | 37386715 | 43695912
MCR029517 | HPR231 | 2021-04-01 | Material | 106502903 | 77007432 | 101701616
MCR029518 | HPR231 | 2021-04-01 | Equipment | 20679715 | 14952566 | 16597210
MCR029519 | HPR231 | 2021-04-01 | Subcontract | 99512014 | 71952636 | 73759664
MCR029520 | HPR231 | 2021-04-01 | Overhead | 26375554 | 19070970 | 15667082
MCR029521 | HPR231 | 2021-05-01 | Labor | 48569079 | 29101788 | 30705211
MCR029522 | HPR231 | 2021-05-01 | Material | 100040350 | 59942523 | 57619887
MCR029523 | HPR231 | 2021-05-01 | Equipment | 19424878 | 11639066 | 11320907
MCR029524 | HPR231 | 2021-05-01 | Subcontract | 93473666 | 56007874 | 56116695
MCR029525 | HPR231 | 2021-05-01 | Overhead | 24775097 | 14844828 | 18754883
MCR029526 | HPR231 | 2021-06-01 | Labor | 44165768 | 26001559 | 26697750
MCR029527 | HPR231 | 2021-06-01 | Material | 90970615 | 53556812 | 70641224
MCR029528 | HPR231 | 2021-06-01 | Equipment | 17663804 | 10399149 | 10346988
MCR029529 | HPR231 | 2021-06-01 | Subcontract | 84999271 | 50041324 | 57347526
MCR029530 | HPR231 | 2021-06-01 | Overhead | 22528967 | 13263400 | 16697814
MCR029531 | HPR231 | 2021-07-01 | Labor | 38636123 | 31912847 | 33055621
MCR029532 | HPR231 | 2021-07-01 | Material | 79580905 | 65732612 | 63551090
MCR029533 | HPR231 | 2021-07-01 | Equipment | 15452259 | 12763330 | 15159397
MCR029534 | HPR231 | 2021-07-01 | Subcontract | 74357186 | 61417900 | 60412048
MCR029535 | HPR231 | 2021-07-01 | Overhead | 19708294 | 16278750 | 17615339
MCR029536 | HPR231 | 2021-08-01 | Labor | 32147515 | 33569037 | 40982330
MCR029537 | HPR231 | 2021-08-01 | Material | 66215969 | 69143955 | 86594034
MCR029538 | HPR231 | 2021-08-01 | Equipment | 12857183 | 13425712 | 15030558
MCR029539 | HPR231 | 2021-08-01 | Subcontract | 61869529 | 64605321 | 60947536
MCR029540 | HPR231 | 2021-08-01 | Overhead | 16398453 | 17123572 | 15608730
MCR029541 | HPR231 | 2021-09-01 | Labor | 24909759 | 45994148 | 49225004
MCR029542 | HPR231 | 2021-09-01 | Material | 51307974 | 94736627 | 102811752
MCR029543 | HPR231 | 2021-09-01 | Equipment | 9962492 | 18395052 | 16812244
MCR029544 | HPR231 | 2021-09-01 | Subcontract | 47940101 | 88518081 | 95580269
MCR029545 | HPR231 | 2021-09-01 | Overhead | 12706473 | 23461624 | 17223695
MCR029546 | HPR231 | 2021-10-01 | Labor | 17204241 | 47331417 | 54124020
MCR029547 | HPR231 | 2021-10-01 | Material | 35436503 | 97491072 | 106148443
MCR029548 | HPR231 | 2021-10-01 | Equipment | 6880721 | 18929884 | 20592310
MCR029549 | HPR231 | 2021-10-01 | Subcontract | 33110438 | 91091724 | 101364618
MCR029550 | HPR231 | 2021-10-01 | Overhead | 8775887 | 24143765 | 16626275
MCR029551 | HPR231 | 2021-11-01 | Labor | 9456388 | 22414846 | 20980141
MCR029552 | HPR231 | 2021-11-01 | Material | 19477832 | 46169068 | 73262855
MCR029553 | HPR231 | 2021-11-01 | Equipment | 3782019 | 8964668 | 8595398
MCR029554 | HPR231 | 2021-11-01 | Subcontract | 18199300 | 43138514 | 39208817
MCR029555 | HPR231 | 2021-11-01 | Overhead | 4823705 | 11433818 | 16664041
MCR029556 | HPR231 | 2021-12-01 | Labor | 2537800 | 31595822 | 38995498
MCR029557 | HPR231 | 2021-12-01 | Material | 5227244 | 65079617 | 70921719
MCR029558 | HPR231 | 2021-12-01 | Equipment | 1014976 | 12636537 | 13853391
MCR029559 | HPR231 | 2021-12-01 | Subcontract | 4884125 | 60807768 | 85570402
MCR029560 | HPR231 | 2021-12-01 | Overhead | 1294532 | 16117035 | 16918117
MCR029561 | HPR231 | 2022-01-01 | Labor | 0 | 25164615 | 29136980
MCR029562 | HPR231 | 2022-01-01 | Material | 0 | 51832914 | 67162868
MCR029563 | HPR231 | 2022-01-01 | Equipment | 0 | 10064419 | 10188150
MCR029564 | HPR231 | 2022-01-01 | Subcontract | 0 | 48430583 | 79374909
MCR029565 | HPR231 | 2022-01-01 | Overhead | 0 | 12836475 | 17510042
MCR029566 | HPR231 | 2022-02-01 | Labor | 0 | 24327020 | 23911102
MCR029567 | HPR231 | 2022-02-01 | Material | 0 | 50107675 | 44711085
MCR029568 | HPR231 | 2022-02-01 | Equipment | 0 | 9729429 | 11546707
MCR029569 | HPR231 | 2022-02-01 | Subcontract | 0 | 46818589 | 75158527
MCR029570 | HPR231 | 2022-02-01 | Overhead | 0 | 12409218 | 16546026
MCR029571 | HPR231 | 2022-03-01 | Labor | 0 | 24768454 | 28395810
MCR029572 | HPR231 | 2022-03-01 | Material | 0 | 51016920 | 74620167
MCR029573 | HPR231 | 2022-03-01 | Equipment | 0 | 9905977 | 10519869
MCR029574 | HPR231 | 2022-03-01 | Subcontract | 0 | 47668151 | 75869116
MCR029575 | HPR231 | 2022-03-01 | Overhead | 0 | 12634393 | 16153805
MCR029576 | HPR231 | 2022-04-01 | Labor | 0 | 11131580 | 12662848
MCR029577 | HPR231 | 2022-04-01 | Material | 0 | 22928316 | 31772396
MCR029578 | HPR231 | 2022-04-01 | Equipment | 0 | 4452001 | 5218022
MCR029579 | HPR231 | 2022-04-01 | Subcontract | 0 | 21423294 | 42586334
MCR029580 | HPR231 | 2022-04-01 | Overhead | 0 | 5678221 | 17030709
MCR029581 | HPR231 | 2022-05-01 | Labor | 0 | 7777595 | 8389826
MCR029582 | HPR231 | 2022-05-01 | Material | 0 | 16019931 | 19023126
MCR029583 | HPR231 | 2022-05-01 | Equipment | 0 | 3110597 | 3397474
MCR029584 | HPR231 | 2022-05-01 | Subcontract | 0 | 14968377 | 42283284
MCR029585 | HPR231 | 2022-05-01 | Overhead | 0 | 3967353 | 17049241
MCR029586 | HPR231 | 2022-06-01 | Labor | 0 | 4716944 | 5732488
MCR029587 | HPR231 | 2022-06-01 | Material | 0 | 9715743 | 11762278
MCR029588 | HPR231 | 2022-06-01 | Equipment | 0 | 1886510 | 2453227
MCR029589 | HPR231 | 2022-06-01 | Subcontract | 0 | 9077999 | 26288289
MCR029590 | HPR231 | 2022-06-01 | Overhead | 0 | 2406114 | 16082557
MCR029591 | HPR231 | 2022-07-01 | Labor | 0 | 1566156 | 1391624
MCR029592 | HPR231 | 2022-07-01 | Material | 0 | 3225897 | 4261499
MCR029593 | HPR231 | 2022-07-01 | Equipment | 0 | 626374 | 742727
MCR029594 | HPR231 | 2022-07-01 | Subcontract | 0 | 3014148 | 23634527
MCR029595 | HPR231 | 2022-07-01 | Overhead | 0 | 798897 | 18381876
MCR029596 | HPR232 | 2021-03-01 | Labor | 20977219 | 10782959 | 12038214
MCR029597 | HPR232 | 2021-03-01 | Material | 47323102 | 24325582 | 22451903
MCR029598 | HPR232 | 2021-03-01 | Equipment | 21286438 | 10941907 | 11229042
MCR029599 | HPR232 | 2021-03-01 | Subcontract | 43218793 | 22215837 | 21716722
MCR029600 | HPR232 | 2021-03-01 | Overhead | 14982246 | 7701352 | 61446594
MCR029601 | HPR232 | 2021-04-01 | Labor | 57907955 | 29493460 | 33145894
MCR029602 | HPR232 | 2021-04-01 | Material | 130636195 | 66535132 | 81073551
MCR029603 | HPR232 | 2021-04-01 | Equipment | 58761558 | 29928214 | 31306441
MCR029604 | HPR232 | 2021-04-01 | Subcontract | 119306184 | 60764573 | 65915092
MCR029605 | HPR232 | 2021-04-01 | Overhead | 41358734 | 21064673 | 66047887
MCR029606 | HPR232 | 2021-05-01 | Labor | 87491110 | 55225802 | 63141880
MCR029607 | HPR232 | 2021-05-01 | Material | 197373672 | 124585450 | 138639562
MCR029608 | HPR232 | 2021-05-01 | Equipment | 88780789 | 56039868 | 56438499
MCR029609 | HPR232 | 2021-05-01 | Subcontract | 180255553 | 113780217 | 101607376
MCR029610 | HPR232 | 2021-05-01 | Overhead | 62487468 | 39443099 | 62350720
MCR029611 | HPR232 | 2021-06-01 | Labor | 109992229 | 95279526 | 114174844
MCR029612 | HPR232 | 2021-06-01 | Material | 248134583 | 214943779 | 213192550
MCR029613 | HPR232 | 2021-06-01 | Equipment | 111613590 | 96684011 | 100856174
MCR029614 | HPR232 | 2021-06-01 | Subcontract | 226613996 | 196301813 | 218640390
MCR029615 | HPR232 | 2021-06-01 | Overhead | 78558106 | 68050072 | 60358731
MCR029616 | HPR232 | 2021-07-01 | Labor | 125698365 | 59897818 | 64291148
MCR029617 | HPR232 | 2021-07-01 | Material | 283566499 | 135125184 | 182114591
MCR029618 | HPR232 | 2021-07-01 | Equipment | 127551245 | 60780753 | 60282305
MCR029619 | HPR232 | 2021-07-01 | Subcontract | 258972919 | 123405845 | 127795629
MCR029620 | HPR232 | 2021-07-01 | Overhead | 89775665 | 42779924 | 63688266
MCR029621 | HPR232 | 2021-08-01 | Labor | 134922414 | 63176505 | 81429673
MCR029622 | HPR232 | 2021-08-01 | Material | 304375293 | 142521667 | 150205742
MCR029623 | HPR232 | 2021-08-01 | Equipment | 136911263 | 64107771 | 68359869
MCR029624 | HPR232 | 2021-08-01 | Subcontract | 277976977 | 130160834 | 115445284
MCR029625 | HPR232 | 2021-08-01 | Overhead | 96363620 | 45121611 | 60970740
MCR029626 | HPR232 | 2021-09-01 | Labor | 138008935 | 97199479 | 101657064
MCR029627 | HPR232 | 2021-09-01 | Material | 311338262 | 219275056 | 247899552
MCR029628 | HPR232 | 2021-09-01 | Equipment | 140043281 | 98632266 | 94564094
MCR029629 | HPR232 | 2021-09-01 | Subcontract | 284336051 | 200257441 | 182233928
MCR029630 | HPR232 | 2021-09-01 | Overhead | 98568059 | 69421332 | 60197157
MCR029631 | HPR232 | 2021-10-01 | Labor | 135342182 | 150803118 | 192331879
MCR029632 | HPR232 | 2021-10-01 | Material | 305322259 | 340201022 | 411653257
MCR029633 | HPR232 | 2021-10-01 | Equipment | 137337219 | 153026059 | 173239316
MCR029634 | HPR232 | 2021-10-01 | Subcontract | 278841814 | 310695559 | 302777879
MCR029635 | HPR232 | 2021-10-01 | Overhead | 96663424 | 107705857 | 63462563
MCR029636 | HPR232 | 2021-11-01 | Labor | 127357665 | 82711335 | 96097899
MCR029637 | HPR232 | 2021-11-01 | Material | 287309761 | 186590842 | 213390351
MCR029638 | HPR232 | 2021-11-01 | Equipment | 129235005 | 83930557 | 91078636
MCR029639 | HPR232 | 2021-11-01 | Subcontract | 262391531 | 170407913 | 203765821
MCR029640 | HPR232 | 2021-11-01 | Overhead | 90960762 | 59073681 | 64161443
MCR029641 | HPR232 | 2021-12-01 | Labor | 114559578 | 128606303 | 151364477
MCR029642 | HPR232 | 2021-12-01 | Material | 258438193 | 290126600 | 374264558
MCR029643 | HPR232 | 2021-12-01 | Equipment | 116248264 | 130502049 | 134774711
MCR029644 | HPR232 | 2021-12-01 | Subcontract | 236023979 | 264964066 | 251417081
MCR029645 | HPR232 | 2021-12-01 | Overhead | 81820175 | 91852558 | 63838840
MCR029646 | HPR232 | 2022-01-01 | Labor | 97548830 | 86801983 | 173022740
MCR029647 | HPR232 | 2022-01-01 | Material | 220063168 | 195819050 | 303126751
MCR029648 | HPR232 | 2022-01-01 | Equipment | 98986767 | 88081504 | 91076937
MCR029649 | HPR232 | 2022-01-01 | Subcontract | 200977200 | 178835762 | 181859085
MCR029650 | HPR232 | 2022-01-01 | Overhead | 69670843 | 61995283 | 59199350
MCR029651 | HPR232 | 2022-02-01 | Labor | 77072242 | 92705003 | 162000066
MCR029652 | HPR232 | 2022-02-01 | Material | 173869452 | 209135841 | 338361725
MCR029653 | HPR232 | 2022-02-01 | Equipment | 78208340 | 94071539 | 97186063
MCR029654 | HPR232 | 2022-02-01 | Subcontract | 158789842 | 190997595 | 182702096
MCR029655 | HPR232 | 2022-02-01 | Overhead | 55046156 | 66211309 | 66598638
MCR029656 | HPR232 | 2022-03-01 | Labor | 54120669 | 57100327 | 72154522
MCR029657 | HPR232 | 2022-03-01 | Material | 122092349 | 128814243 | 169076451
MCR029658 | HPR232 | 2022-03-01 | Equipment | 54918445 | 57942025 | 60996451
MCR029659 | HPR232 | 2022-03-01 | Subcontract | 111503342 | 117642249 | 136349431
MCR029660 | HPR232 | 2022-03-01 | Overhead | 38653797 | 40781913 | 65845891
MCR029661 | HPR232 | 2022-04-01 | Labor | 30171389 | 110818124 | 134559682
MCR029662 | HPR232 | 2022-04-01 | Material | 68064491 | 249997743 | 329595769
MCR029663 | HPR232 | 2022-04-01 | Equipment | 30616136 | 112451659 | 109743785
MCR029664 | HPR232 | 2022-04-01 | Subcontract | 62161292 | 228315565 | 282435625
MCR029665 | HPR232 | 2022-04-01 | Overhead | 21548860 | 79147973 | 62837207
MCR029666 | HPR232 | 2022-05-01 | Labor | 8188492 | 46050885 | 64817338
MCR029667 | HPR232 | 2022-05-01 | Material | 18472650 | 103887494 | 116823392
MCR029668 | HPR232 | 2022-05-01 | Equipment | 8309196 | 46729706 | 51734091
MCR029669 | HPR232 | 2022-05-01 | Subcontract | 16870527 | 94877384 | 150358895
MCR029670 | HPR232 | 2022-05-01 | Overhead | 5848344 | 32890235 | 63283867
MCR029671 | HPR232 | 2022-06-01 | Labor | 0 | 88490362 | 120588981
MCR029672 | HPR232 | 2022-06-01 | Material | 0 | 199627913 | 224999368
MCR029673 | HPR232 | 2022-06-01 | Equipment | 0 | 89794771 | 115445263
MCR029674 | HPR232 | 2022-06-01 | Subcontract | 0 | 182314285 | 241657341
MCR029675 | HPR232 | 2022-06-01 | Overhead | 0 | 63201149 | 60337062
MCR029676 | HPR232 | 2022-07-01 | Labor | 0 | 18973830 | 17570397
MCR029677 | HPR232 | 2022-07-01 | Material | 0 | 42803600 | 70478207
MCR029678 | HPR232 | 2022-07-01 | Equipment | 0 | 19253517 | 10244396
MCR029679 | HPR232 | 2022-07-01 | Subcontract | 0 | 39091266 | 73505727
MCR029680 | HPR232 | 2022-07-01 | Overhead | 0 | 13551395 | 64674451
MCR029681 | HPR232 | 2022-08-01 | Labor | 0 | 15979808 | 23228115
MCR029682 | HPR232 | 2022-08-01 | Material | 0 | 36049301 | 53931577
MCR029683 | HPR232 | 2022-08-01 | Equipment | 0 | 16215361 | 16349819
MCR029684 | HPR232 | 2022-08-01 | Subcontract | 0 | 32922764 | 68116182
MCR029685 | HPR232 | 2022-08-01 | Overhead | 0 | 11413020 | 58587232
MCR029686 | HPR232 | 2022-09-01 | Labor | 0 | 22776753 | 27213520
MCR029687 | HPR232 | 2022-09-01 | Material | 0 | 51382721 | 56999717
MCR029688 | HPR232 | 2022-09-01 | Equipment | 0 | 23112498 | 30671519
MCR029689 | HPR232 | 2022-09-01 | Subcontract | 0 | 46926324 | 125263616
MCR029690 | HPR232 | 2022-09-01 | Overhead | 0 | 16267500 | 64454203
MCR029691 | HPR232 | 2022-10-01 | Labor | 0 | 6485893 | 8104123
MCR029692 | HPR232 | 2022-10-01 | Material | 0 | 14631709 | 19125482
MCR029693 | HPR232 | 2022-10-01 | Equipment | 0 | 6581499 | 6994597
MCR029694 | HPR232 | 2022-10-01 | Subcontract | 0 | 13362708 | 77245065
MCR029695 | HPR232 | 2022-10-01 | Overhead | 0 | 4632322 | 64215108
MCR029696 | HPR233 | 2018-02-01 | Labor | 5950137 | 4458214 | 4563606
MCR029697 | HPR233 | 2018-02-01 | Material | 16922493 | 12679387 | 14403336
MCR029698 | HPR233 | 2018-02-01 | Equipment | 5411616 | 4054720 | 3967789
MCR029699 | HPR233 | 2018-02-01 | Subcontract | 18269051 | 13688313 | 13517101
MCR029700 | HPR233 | 2018-02-01 | Overhead | 4369802 | 3274128 | 28364915
MCR029701 | HPR233 | 2018-03-01 | Labor | 16889848 | 9626557 | 10455562
MCR029702 | HPR233 | 2018-03-01 | Material | 48035585 | 27378416 | 26297910
MCR029703 | HPR233 | 2018-03-01 | Equipment | 15361220 | 8755298 | 8495457
MCR029704 | HPR233 | 2018-03-01 | Subcontract | 51857877 | 29556974 | 33173428
MCR029705 | HPR233 | 2018-03-01 | Overhead | 12403965 | 7069778 | 24139340
MCR029706 | HPR233 | 2018-04-01 | Labor | 26412395 | 29656832 | 30126223
MCR029707 | HPR233 | 2018-04-01 | Material | 75118190 | 84345532 | 87908190
MCR029708 | HPR233 | 2018-04-01 | Equipment | 24021921 | 26972718 | 28840811
MCR029709 | HPR233 | 2018-04-01 | Subcontract | 81095502 | 91057083 | 94769666
MCR029710 | HPR233 | 2018-04-01 | Overhead | 19397357 | 21780083 | 25550011
MCR029711 | HPR233 | 2018-05-01 | Labor | 34550558 | 27066568 | 29823749
MCR029712 | HPR233 | 2018-05-01 | Material | 98263538 | 76978690 | 80147462
MCR029713 | HPR233 | 2018-05-01 | Equipment | 31423534 | 24616887 | 24974978
MCR029714 | HPR233 | 2018-05-01 | Subcontract | 106082575 | 83104046 | 80043117
MCR029715 | HPR233 | 2018-05-01 | Overhead | 25374053 | 19877784 | 26441335
MCR029716 | HPR233 | 2018-06-01 | Labor | 41338770 | 31427422 | 37386677
MCR029717 | HPR233 | 2018-06-01 | Material | 117569556 | 89381181 | 88287908
MCR029718 | HPR233 | 2018-06-01 | Equipment | 37597373 | 28583059 | 28957272
MCR029719 | HPR233 | 2018-06-01 | Subcontract | 126924813 | 96493429 | 94940055
MCR029720 | HPR233 | 2018-06-01 | Overhead | 30359340 | 23080410 | 23604860
MCR029721 | HPR233 | 2018-07-01 | Labor | 46813312 | 33546191 | 33064494
MCR029722 | HPR233 | 2018-07-01 | Material | 133139432 | 95407068 | 103743777
MCR029723 | HPR233 | 2018-07-01 | Equipment | 42576438 | 30510068 | 28101812
MCR029724 | HPR233 | 2018-07-01 | Subcontract | 143733616 | 102998809 | 109947432
MCR029725 | HPR233 | 2018-07-01 | Overhead | 34379863 | 24636442 | 27366485
MCR029726 | HPR233 | 2018-08-01 | Labor | 51012556 | 24784458 | 27453778
MCR029727 | HPR233 | 2018-08-01 | Material | 145082295 | 70488255 | 72032697
MCR029728 | HPR233 | 2018-08-01 | Equipment | 46395626 | 22541322 | 25589075
MCR029729 | HPR233 | 2018-08-01 | Subcontract | 156626798 | 76097154 | 80550923
MCR029730 | HPR233 | 2018-08-01 | Overhead | 37463803 | 18201794 | 25514519
MCR029731 | HPR233 | 2018-09-01 | Labor | 53977252 | 62837080 | 67529343
MCR029732 | HPR233 | 2018-09-01 | Material | 153514040 | 178711841 | 207326485
MCR029733 | HPR233 | 2018-09-01 | Equipment | 49092000 | 57149963 | 61179666
MCR029734 | HPR233 | 2018-09-01 | Subcontract | 165729474 | 192932318 | 194687207
MCR029735 | HPR233 | 2018-09-01 | Overhead | 39641086 | 46147775 | 24785057
MCR029736 | HPR233 | 2018-10-01 | Labor | 55750881 | 33805967 | 39062465
MCR029737 | HPR233 | 2018-10-01 | Material | 158558330 | 96145882 | 71278331
MCR029738 | HPR233 | 2018-10-01 | Equipment | 50705105 | 30746332 | 31192361
MCR029739 | HPR233 | 2018-10-01 | Subcontract | 171175150 | 103796412 | 124281027
MCR029740 | HPR233 | 2018-10-01 | Overhead | 40943645 | 24827222 | 25358203
MCR029741 | HPR233 | 2018-11-01 | Labor | 56380095 | 26569756 | 30420429
MCR029742 | HPR233 | 2018-11-01 | Material | 160347848 | 75565732 | 88081634
MCR029743 | HPR233 | 2018-11-01 | Equipment | 51277372 | 24165040 | 23906561
MCR029744 | HPR233 | 2018-11-01 | Subcontract | 173107063 | 81578656 | 70197151
MCR029745 | HPR233 | 2018-11-01 | Overhead | 41405742 | 19512923 | 26813142
MCR029746 | HPR233 | 2018-12-01 | Labor | 55915273 | 69006099 | 76170746
MCR029747 | HPR233 | 2018-12-01 | Material | 159025869 | 196256842 | 209668827
MCR029748 | HPR233 | 2018-12-01 | Equipment | 50854619 | 62760649 | 72633009
MCR029749 | HPR233 | 2018-12-01 | Subcontract | 171679892 | 211873411 | 205393423
MCR029750 | HPR233 | 2018-12-01 | Overhead | 41064375 | 50678324 | 26013767
MCR029751 | HPR233 | 2019-01-01 | Labor | 54411230 | 68841210 | 77861094
MCR029752 | HPR233 | 2019-01-01 | Material | 154748297 | 195787891 | 213560173
MCR029753 | HPR233 | 2019-01-01 | Equipment | 49486701 | 62610684 | 55935991
MCR029754 | HPR233 | 2019-01-01 | Subcontract | 167061944 | 211367144 | 234561180
MCR029755 | HPR233 | 2019-01-01 | Overhead | 39959801 | 50557230 | 24015516
MCR029756 | HPR233 | 2019-02-01 | Labor | 51928162 | 60661618 | 66729307
MCR029757 | HPR233 | 2019-02-01 | Material | 147686326 | 172524715 | 147285618
MCR029758 | HPR233 | 2019-02-01 | Equipment | 47228365 | 55171392 | 57236803
MCR029759 | HPR233 | 2019-02-01 | Subcontract | 159438037 | 186252869 | 177254403
MCR029760 | HPR233 | 2019-02-01 | Overhead | 38136227 | 44550108 | 24992451
MCR029761 | HPR233 | 2019-03-01 | Labor | 48532908 | 39135555 | 38000773
MCR029762 | HPR233 | 2019-03-01 | Material | 138030051 | 111303502 | 135323718
MCR029763 | HPR233 | 2019-03-01 | Equipment | 44140401 | 35593562 | 38496291
MCR029764 | HPR233 | 2019-03-01 | Subcontract | 149013392 | 120160156 | 119401712
MCR029765 | HPR233 | 2019-03-01 | Overhead | 35642740 | 28741291 | 26103735
MCR029766 | HPR233 | 2019-04-01 | Labor | 44300719 | 46861099 | 48832722
MCR029767 | HPR233 | 2019-04-01 | Material | 125993491 | 133275340 | 151383700
MCR029768 | HPR233 | 2019-04-01 | Equipment | 40291249 | 42619900 | 39303574
MCR029769 | HPR233 | 2019-04-01 | Subcontract | 136019058 | 143880339 | 167554666
MCR029770 | HPR233 | 2019-04-01 | Overhead | 32534606 | 34414958 | 26331163
MCR029771 | HPR233 | 2019-05-01 | Labor | 39317823 | 52563999 | 63872262
MCR029772 | HPR233 | 2019-05-01 | Material | 111821882 | 149494678 | 152870746
MCR029773 | HPR233 | 2019-05-01 | Equipment | 35759334 | 47806655 | 50088166
MCR029774 | HPR233 | 2019-05-01 | Subcontract | 120719784 | 161390284 | 156939504
MCR029775 | HPR233 | 2019-05-01 | Overhead | 28875149 | 38603188 | 27676096
MCR029776 | HPR233 | 2019-06-01 | Labor | 33685325 | 29589794 | 25778195
MCR029777 | HPR233 | 2019-06-01 | Material | 95802773 | 84154874 | 86229557
MCR029778 | HPR233 | 2019-06-01 | Equipment | 30636609 | 26911748 | 25111012
MCR029779 | HPR233 | 2019-06-01 | Subcontract | 103426000 | 90851255 | 92551405
MCR029780 | HPR233 | 2019-06-01 | Overhead | 24738623 | 21730850 | 27159683
MCR029781 | HPR233 | 2019-07-01 | Labor | 27525553 | 26023883 | 31025212
MCR029782 | HPR233 | 2019-07-01 | Material | 78284069 | 74013242 | 83944175
MCR029783 | HPR233 | 2019-07-01 | Equipment | 25034332 | 23668572 | 27276446
MCR029784 | HPR233 | 2019-07-01 | Subcontract | 84513297 | 79902631 | 96392411
MCR029785 | HPR233 | 2019-07-01 | Overhead | 20214864 | 19112032 | 24840875
MCR029786 | HPR233 | 2019-08-01 | Labor | 20993314 | 31249618 | 34866129
MCR029787 | HPR233 | 2019-08-01 | Material | 59706049 | 88875498 | 104156428
MCR029788 | HPR233 | 2019-08-01 | Equipment | 19093298 | 28421348 | 28825715
MCR029789 | HPR233 | 2019-08-01 | Subcontract | 64456984 | 95947508 | 89235339
MCR029790 | HPR233 | 2019-08-01 | Overhead | 15417564 | 22949831 | 25979101
MCR029791 | HPR233 | 2019-09-01 | Labor | 14298633 | 21735717 | 25610418
MCR029792 | HPR233 | 2019-09-01 | Material | 40666037 | 61817482 | 60103334
MCR029793 | HPR233 | 2019-09-01 | Equipment | 13004525 | 19768510 | 17648760
MCR029794 | HPR233 | 2019-09-01 | Subcontract | 43901919 | 66736429 | 68822900
MCR029795 | HPR233 | 2019-09-01 | Overhead | 10500967 | 15962788 | 25976852
MCR029796 | HPR233 | 2019-10-01 | Labor | 7763745 | 22306604 | 20621643
MCR029797 | HPR233 | 2019-10-01 | Material | 22080484 | 63441112 | 65249393
MCR029798 | HPR233 | 2019-10-01 | Equipment | 7061081 | 20287728 | 20538271
MCR029799 | HPR233 | 2019-10-01 | Subcontract | 23837475 | 68489254 | 81995504
MCR029800 | HPR233 | 2019-10-01 | Overhead | 5701722 | 16382049 | 26029376
MCR029801 | HPR233 | 2019-11-01 | Labor | 2062927 | 17926676 | 20777585
MCR029802 | HPR233 | 2019-11-01 | Material | 5867069 | 50984375 | 51999452
MCR029803 | HPR233 | 2019-11-01 | Equipment | 1876220 | 16304209 | 17992793
MCR029804 | HPR233 | 2019-11-01 | Subcontract | 6333924 | 55041309 | 51471836
MCR029805 | HPR233 | 2019-11-01 | Overhead | 1515021 | 13165415 | 27145916
MCR029806 | HPR233 | 2019-12-01 | Labor | 0 | 10405899 | 10978269
MCR029807 | HPR233 | 2019-12-01 | Material | 0 | 29594905 | 33544782
MCR029808 | HPR233 | 2019-12-01 | Equipment | 0 | 9464105 | 7596478
MCR029809 | HPR233 | 2019-12-01 | Subcontract | 0 | 31949834 | 28441949
MCR029810 | HPR233 | 2019-12-01 | Overhead | 0 | 7642129 | 25699990
MCR029811 | HPR233 | 2020-01-01 | Labor | 0 | 7582379 | 8641454
MCR029812 | HPR233 | 2020-01-01 | Material | 0 | 21564670 | 21048469
MCR029813 | HPR233 | 2020-01-01 | Equipment | 0 | 6896130 | 7880532
MCR029814 | HPR233 | 2020-01-01 | Subcontract | 0 | 23280616 | 27904783
MCR029815 | HPR233 | 2020-01-01 | Overhead | 0 | 5568526 | 26040371
MCR029816 | HPR233 | 2020-02-01 | Labor | 0 | 2142224 | 2930077
MCR029817 | HPR233 | 2020-02-01 | Material | 0 | 6092593 | 6736438
MCR029818 | HPR233 | 2020-02-01 | Equipment | 0 | 1948340 | 2032295
MCR029819 | HPR233 | 2020-02-01 | Subcontract | 0 | 6577394 | 6200253
MCR029820 | HPR233 | 2020-02-01 | Overhead | 0 | 1573257 | 23230072
MCR029821 | HPR234 | 2017-04-01 | Labor | 1779288 | 1124629 | 1202470
MCR029822 | HPR234 | 2017-04-01 | Material | 3955866 | 2500372 | 2330020
MCR029823 | HPR234 | 2017-04-01 | Equipment | 1041849 | 658518 | 749702
MCR029824 | HPR234 | 2017-04-01 | Subcontract | 4608827 | 2913087 | 2922934
MCR029825 | HPR234 | 2017-04-01 | Overhead | 1167609 | 738007 | 8187327
MCR029826 | HPR234 | 2017-05-01 | Labor | 5104868 | 4386448 | 4630570
MCR029827 | HPR234 | 2017-05-01 | Material | 11349581 | 9752330 | 9541470
MCR029828 | HPR234 | 2017-05-01 | Equipment | 2989118 | 2568452 | 2600507
MCR029829 | HPR234 | 2017-05-01 | Subcontract | 13222959 | 11362062 | 10595803
MCR029830 | HPR234 | 2017-05-01 | Overhead | 3349928 | 2878486 | 8215666
MCR029831 | HPR234 | 2017-06-01 | Labor | 8085572 | 7056883 | 7404264
MCR029832 | HPR234 | 2017-06-01 | Material | 17976540 | 15689469 | 15951735
MCR029833 | HPR234 | 2017-06-01 | Equipment | 4734447 | 4132106 | 4264971
MCR029834 | HPR234 | 2017-06-01 | Subcontract | 20943772 | 18279194 | 18604491
MCR029835 | HPR234 | 2017-06-01 | Overhead | 5305933 | 4630884 | 8776400
MCR029836 | HPR234 | 2017-07-01 | Labor | 10727748 | 11879351 | 13820289
MCR029837 | HPR234 | 2017-07-01 | Material | 23850852 | 26411195 | 23338636
MCR029838 | HPR234 | 2017-07-01 | Equipment | 6281553 | 6955866 | 7256217
MCR029839 | HPR234 | 2017-07-01 | Subcontract | 27787706 | 30770662 | 31394807
MCR029840 | HPR234 | 2017-07-01 | Overhead | 7039788 | 7795496 | 9671575
MCR029841 | HPR234 | 2017-08-01 | Labor | 13037992 | 7872147 | 5907961
MCR029842 | HPR234 | 2017-08-01 | Material | 28987186 | 17502035 | 21652580
MCR029843 | HPR234 | 2017-08-01 | Equipment | 7634300 | 4609478 | 5222442
MCR029844 | HPR234 | 2017-08-01 | Subcontract | 33771849 | 20390945 | 24279492
MCR029845 | HPR234 | 2017-08-01 | Overhead | 8555822 | 5165879 | 9050173
MCR029846 | HPR234 | 2017-09-01 | Labor | 15023177 | 14429012 | 15027986
MCR029847 | HPR234 | 2017-09-01 | Material | 33400821 | 32079822 | 30523021
MCR029848 | HPR234 | 2017-09-01 | Equipment | 8796710 | 8448801 | 8665029
MCR029849 | HPR234 | 2017-09-01 | Subcontract | 38914006 | 37374960 | 40531402
MCR029850 | HPR234 | 2017-09-01 | Overhead | 9858545 | 9468641 | 7812567
MCR029851 | HPR234 | 2017-10-01 | Labor | 16690480 | 17588502 | 18200231
MCR029852 | HPR234 | 2017-10-01 | Material | 37107713 | 39104273 | 37019274
MCR029853 | HPR234 | 2017-10-01 | Equipment | 9772987 | 10298818 | 9522021
MCR029854 | HPR234 | 2017-10-01 | Subcontract | 43232762 | 45558876 | 48831230
MCR029855 | HPR234 | 2017-10-01 | Overhead | 10952667 | 11541969 | 8842281
MCR029856 | HPR234 | 2017-11-01 | Labor | 18047410 | 15272841 | 14735065
MCR029857 | HPR234 | 2017-11-01 | Material | 40124557 | 33955894 | 36467481
MCR029858 | HPR234 | 2017-11-01 | Equipment | 10567528 | 8942899 | 8717261
MCR029859 | HPR234 | 2017-11-01 | Subcontract | 46747570 | 39560700 | 35547305
MCR029860 | HPR234 | 2017-11-01 | Overhead | 11843115 | 10022380 | 8014289
MCR029861 | HPR234 | 2017-12-01 | Labor | 19101848 | 20086172 | 18279457
MCR029862 | HPR234 | 2017-12-01 | Material | 42468873 | 44657308 | 46978681
MCR029863 | HPR234 | 2017-12-01 | Equipment | 11184946 | 11761310 | 10936603
MCR029864 | HPR234 | 2017-12-01 | Subcontract | 49478843 | 52028503 | 57819866
MCR029865 | HPR234 | 2017-12-01 | Overhead | 12535060 | 13180996 | 8886875
MCR029866 | HPR234 | 2018-01-01 | Labor | 19862089 | 23207275 | 26976415
MCR029867 | HPR234 | 2018-01-01 | Material | 44159106 | 51596413 | 48304905
MCR029868 | HPR234 | 2018-01-01 | Equipment | 11630099 | 13588849 | 15878118
MCR029869 | HPR234 | 2018-01-01 | Subcontract | 51448067 | 60112986 | 61444444
MCR029870 | HPR234 | 2018-01-01 | Overhead | 13033947 | 15229134 | 7978806
MCR029871 | HPR234 | 2018-02-01 | Labor | 20336893 | 24641951 | 20242919
MCR029872 | HPR234 | 2018-02-01 | Material | 45214731 | 54786108 | 60578655
MCR029873 | HPR234 | 2018-02-01 | Equipment | 11908117 | 14428913 | 12133102
MCR029874 | HPR234 | 2018-02-01 | Subcontract | 52677935 | 63829176 | 74518181
MCR029875 | HPR234 | 2018-02-01 | Overhead | 13345524 | 16170600 | 8532499
MCR029876 | HPR234 | 2018-03-01 | Labor | 20535548 | 32304019 | 34682017
MCR029877 | HPR234 | 2018-03-01 | Material | 45656398 | 71821077 | 76420586
MCR029878 | HPR234 | 2018-03-01 | Equipment | 12024438 | 18915380 | 19942502
MCR029879 | HPR234 | 2018-03-01 | Subcontract | 53192505 | 83675960 | 87852583
MCR029880 | HPR234 | 2018-03-01 | Overhead | 13475886 | 21198620 | 8593586
MCR029881 | HPR234 | 2018-04-01 | Labor | 20467944 | 10052810 | 8735394
MCR029882 | HPR234 | 2018-04-01 | Material | 45506096 | 22350274 | 23405398
MCR029883 | HPR234 | 2018-04-01 | Equipment | 11984854 | 5886349 | 5745538
MCR029884 | HPR234 | 2018-04-01 | Subcontract | 53017394 | 26039440 | 21820848
MCR029885 | HPR234 | 2018-04-01 | Overhead | 13431523 | 6596879 | 9037753
MCR029886 | HPR234 | 2018-05-01 | Labor | 20144666 | 13096392 | 11993337
MCR029887 | HPR234 | 2018-05-01 | Material | 44787356 | 29117027 | 28557980
MCR029888 | HPR234 | 2018-05-01 | Equipment | 11795560 | 7668496 | 7899137
MCR029889 | HPR234 | 2018-05-01 | Subcontract | 52180017 | 33923122 | 40961276
MCR029890 | HPR234 | 2018-05-01 | Overhead | 13219381 | 8594146 | 8354763
MCR029891 | HPR234 | 2018-06-01 | Labor | 19577104 | 23177068 | 24708481
MCR029892 | HPR234 | 2018-06-01 | Material | 43525503 | 51529254 | 61917938
MCR029893 | HPR234 | 2018-06-01 | Equipment | 11463228 | 13571161 | 12676435
MCR029894 | HPR234 | 2018-06-01 | Subcontract | 50709881 | 60034742 | 62877367
MCR029895 | HPR234 | 2018-06-01 | Overhead | 12846934 | 15209311 | 8646807
MCR029896 | HPR234 | 2018-07-01 | Labor | 18777603 | 12081867 | 11870433
MCR029897 | HPR234 | 2018-07-01 | Material | 41747983 | 26861446 | 22572883
MCR029898 | HPR234 | 2018-07-01 | Equipment | 10995087 | 7074448 | 7942967
MCR029899 | HPR234 | 2018-07-01 | Subcontract | 48638961 | 31295232 | 32390422
MCR029900 | HPR234 | 2018-07-01 | Overhead | 12322283 | 7928391 | 8693503
MCR029901 | HPR234 | 2018-08-01 | Labor | 17759647 | 18719205 | 20143279
MCR029902 | HPR234 | 2018-08-01 | Material | 39484776 | 41618148 | 41066773
MCR029903 | HPR234 | 2018-08-01 | Equipment | 10399030 | 10960892 | 9386093
MCR029904 | HPR234 | 2018-08-01 | Subcontract | 46002186 | 48487696 | 47736996
MCR029905 | HPR234 | 2018-08-01 | Overhead | 11654278 | 12283961 | 9114570
MCR029906 | HPR234 | 2018-09-01 | Labor | 16538107 | 17235765 | 14142340
MCR029907 | HPR234 | 2018-09-01 | Material | 36768943 | 38320036 | 43863040
MCR029908 | HPR234 | 2018-09-01 | Equipment | 9683766 | 10092275 | 11047239
MCR029909 | HPR234 | 2018-09-01 | Subcontract | 42838074 | 44645192 | 46921132
MCR029910 | HPR234 | 2018-09-01 | Overhead | 10852676 | 11310494 | 8824532
MCR029911 | HPR234 | 2018-10-01 | Labor | 15129573 | 19565928 | 22305973
MCR029912 | HPR234 | 2018-10-01 | Material | 33637370 | 43500656 | 48120556
MCR029913 | HPR234 | 2018-10-01 | Equipment | 8859010 | 11456685 | 11578207
MCR029914 | HPR234 | 2018-10-01 | Subcontract | 39189600 | 50680932 | 55119195
MCR029915 | HPR234 | 2018-10-01 | Overhead | 9928365 | 12839600 | 8231166
MCR029916 | HPR234 | 2018-11-01 | Labor | 13552827 | 13058162 | 14334277
MCR029917 | HPR234 | 2018-11-01 | Material | 30131813 | 29032031 | 32349607
MCR029918 | HPR234 | 2018-11-01 | Equipment | 7935758 | 7646110 | 7881092
MCR029919 | HPR234 | 2018-11-01 | Subcontract | 35105411 | 33824097 | 32154763
MCR029920 | HPR234 | 2018-11-01 | Overhead | 8893669 | 8569058 | 8781257
MCR029921 | HPR234 | 2018-12-01 | Labor | 11829520 | 11511931 | 11378707
MCR029922 | HPR234 | 2018-12-01 | Material | 26300407 | 25594317 | 24069991
MCR029923 | HPR234 | 2018-12-01 | Equipment | 6926688 | 6740726 | 6693546
MCR029924 | HPR234 | 2018-12-01 | Subcontract | 30641587 | 29818949 | 35067923
MCR029925 | HPR234 | 2018-12-01 | Overhead | 7762796 | 7554387 | 8343988
MCR029926 | HPR234 | 2019-01-01 | Labor | 9985215 | 9889949 | 8983963
MCR029927 | HPR234 | 2019-01-01 | Material | 22199989 | 21988187 | 26127751
MCR029928 | HPR234 | 2019-01-01 | Equipment | 5846769 | 5790987 | 6101205
MCR029929 | HPR234 | 2019-01-01 | Subcontract | 25864349 | 25617587 | 24676132
MCR029930 | HPR234 | 2019-01-01 | Overhead | 6552521 | 6490006 | 8318267
MCR029931 | HPR234 | 2019-02-01 | Labor | 8051093 | 6737837 | 7688210
MCR029932 | HPR234 | 2019-02-01 | Material | 17899884 | 14980139 | 13029778
MCR029933 | HPR234 | 2019-02-01 | Equipment | 4714258 | 3945291 | 3950005
MCR029934 | HPR234 | 2019-02-01 | Subcontract | 20854462 | 17452781 | 18590949
MCR029935 | HPR234 | 2019-02-01 | Overhead | 5283308 | 4421519 | 8451292
MCR029936 | HPR234 | 2019-03-01 | Labor | 6066989 | 6081033 | 6031635
MCR029937 | HPR234 | 2019-03-01 | Material | 13488653 | 13519877 | 14415360
MCR029938 | HPR234 | 2019-03-01 | Equipment | 3552481 | 3560704 | 3674158
MCR029939 | HPR234 | 2019-03-01 | Subcontract | 15715108 | 15751485 | 16111277
MCR029940 | HPR234 | 2019-03-01 | Overhead | 3981294 | 3990510 | 8858330
MCR029941 | HPR234 | 2019-04-01 | Labor | 4087561 | 3683709 | 3845004
MCR029942 | HPR234 | 2019-04-01 | Material | 9087817 | 8189939 | 10639859
MCR029943 | HPR234 | 2019-04-01 | Equipment | 2393441 | 2156969 | 2111552
MCR029944 | HPR234 | 2019-04-01 | Subcontract | 10587864 | 9541782 | 9560960
MCR029945 | HPR234 | 2019-04-01 | Overhead | 2682349 | 2417332 | 8954739
MCR029946 | HPR234 | 2019-05-01 | Labor | 2197846 | 5117798 | 5280587
MCR029947 | HPR234 | 2019-05-01 | Material | 4886440 | 11378329 | 11936034
MCR029948 | HPR234 | 2019-05-01 | Equipment | 1286932 | 2996689 | 3060816
MCR029949 | HPR234 | 2019-05-01 | Subcontract | 5693002 | 13256451 | 13217274
MCR029950 | HPR234 | 2019-05-01 | Overhead | 1442275 | 3358413 | 8266252
MCR029951 | HPR234 | 2019-06-01 | Labor | 579282 | 2883349 | 2797672
MCR029952 | HPR234 | 2019-06-01 | Material | 1287909 | 6410509 | 7265380
MCR029953 | HPR234 | 2019-06-01 | Equipment | 339194 | 1688324 | 1542079
MCR029954 | HPR234 | 2019-06-01 | Subcontract | 1500493 | 7468636 | 7413001
MCR029955 | HPR234 | 2019-06-01 | Overhead | 380138 | 1892118 | 9411010
MCR029956 | HPR234 | 2019-07-01 | Labor | 0 | 335854 | 323783
MCR029957 | HPR234 | 2019-07-01 | Material | 0 | 746699 | 886538
MCR029958 | HPR234 | 2019-07-01 | Equipment | 0 | 196657 | 285571
MCR029959 | HPR234 | 2019-07-01 | Subcontract | 0 | 869950 | 1157108
MCR029960 | HPR234 | 2019-07-01 | Overhead | 0 | 220395 | 9047648
MCR029961 | HPR235 | 2021-04-01 | Labor | 1006733 | 737966 | 864613
MCR029962 | HPR235 | 2021-04-01 | Material | 4349841 | 3188566 | 3512089
MCR029963 | HPR235 | 2021-04-01 | Equipment | 2173389 | 1593160 | 1565493
MCR029964 | HPR235 | 2021-04-01 | Subcontract | 2080267 | 1524899 | 1609466
MCR029965 | HPR235 | 2021-04-01 | Overhead | 993741 | 728442 | 7663371
MCR029966 | HPR235 | 2021-05-01 | Labor | 2888367 | 1795647 | 2082957
MCR029967 | HPR235 | 2021-05-01 | Material | 12479916 | 7758546 | 8458253
MCR029968 | HPR235 | 2021-05-01 | Equipment | 6235563 | 3876541 | 4751218
MCR029969 | HPR235 | 2021-05-01 | Subcontract | 5968392 | 3710445 | 3412980
MCR029970 | HPR235 | 2021-05-01 | Overhead | 2851092 | 1772474 | 7355427
MCR029971 | HPR235 | 2021-06-01 | Labor | 4574869 | 5207026 | 5876741
MCR029972 | HPR235 | 2021-06-01 | Material | 19766872 | 22498266 | 23814594
MCR029973 | HPR235 | 2021-06-01 | Equipment | 9876475 | 11241210 | 11373177
MCR029974 | HPR235 | 2021-06-01 | Subcontract | 9453303 | 10759565 | 10157411
MCR029975 | HPR235 | 2021-06-01 | Overhead | 4515830 | 5139829 | 7472635
MCR029976 | HPR235 | 2021-07-01 | Labor | 6069829 | 3157755 | 3176313
MCR029977 | HPR235 | 2021-07-01 | Material | 26226222 | 13643873 | 17594115
MCR029978 | HPR235 | 2021-07-01 | Equipment | 13103875 | 6817132 | 7020620
MCR029979 | HPR235 | 2021-07-01 | Subcontract | 12542421 | 6525042 | 7022671
MCR029980 | HPR235 | 2021-07-01 | Overhead | 5991497 | 3117004 | 7021403
MCR029981 | HPR235 | 2021-08-01 | Labor | 7376980 | 4024336 | 4849294
MCR029982 | HPR235 | 2021-08-01 | Material | 31874096 | 17388156 | 19874512
MCR029983 | HPR235 | 2021-08-01 | Equipment | 15925824 | 8687955 | 10162879
MCR029984 | HPR235 | 2021-08-01 | Subcontract | 15243459 | 8315707 | 7501216
MCR029985 | HPR235 | 2021-08-01 | Overhead | 7281779 | 3972402 | 7593280
MCR029986 | HPR235 | 2021-09-01 | Labor | 8500211 | 4072761 | 4091052
MCR029987 | HPR235 | 2021-09-01 | Material | 36727298 | 17597387 | 18554532
MCR029988 | HPR235 | 2021-09-01 | Equipment | 18350715 | 8792496 | 9045732
MCR029989 | HPR235 | 2021-09-01 | Subcontract | 17564453 | 8415770 | 8944293
MCR029990 | HPR235 | 2021-09-01 | Overhead | 8390514 | 4020201 | 7604600
MCR029991 | HPR235 | 2021-10-01 | Labor | 9443582 | 3152293 | 3673988
MCR029992 | HPR235 | 2021-10-01 | Material | 40803368 | 13620272 | 17706669
MCR029993 | HPR235 | 2021-10-01 | Equipment | 20387315 | 6805340 | 6736533
MCR029994 | HPR235 | 2021-10-01 | Subcontract | 19513792 | 6513755 | 6697882
MCR029995 | HPR235 | 2021-10-01 | Overhead | 9321711 | 3111612 | 7736693
MCR029996 | HPR235 | 2021-11-01 | Labor | 10211342 | 6926752 | 7625627
MCR029997 | HPR235 | 2021-11-01 | Material | 44120668 | 29928773 | 37894329
MCR029998 | HPR235 | 2021-11-01 | Equipment | 22044797 | 14953847 | 13338289
MCR029999 | HPR235 | 2021-11-01 | Subcontract | 21100256 | 14313129 | 14179030
MCR030000 | HPR235 | 2021-11-01 | Overhead | 10079563 | 6837361 | 7688464
MCR030001 | HPR235 | 2021-12-01 | Labor | 10807950 | 9965641 | 11359742
MCR030002 | HPR235 | 2021-12-01 | Material | 46698461 | 43059055 | 49486090
MCR030003 | HPR235 | 2021-12-01 | Equipment | 23332786 | 21514364 | 25260029
MCR030004 | HPR235 | 2021-12-01 | Subcontract | 22333060 | 20592551 | 21764789
MCR030005 | HPR235 | 2021-12-01 | Overhead | 10668471 | 9837033 | 7037467
MCR030006 | HPR235 | 2022-01-01 | Labor | 11238099 | 8799956 | 10757202
MCR030007 | HPR235 | 2022-01-01 | Material | 48557028 | 38022422 | 48777432
MCR030008 | HPR235 | 2022-01-01 | Equipment | 24261415 | 18997821 | 18835002
MCR030009 | HPR235 | 2022-01-01 | Subcontract | 23221900 | 18183833 | 15390394
MCR030010 | HPR235 | 2022-01-01 | Overhead | 11093069 | 8686391 | 7624074
MCR030011 | HPR235 | 2022-02-01 | Labor | 11506746 | 10909595 | 10839287
MCR030012 | HPR235 | 2022-02-01 | Material | 49717786 | 47137647 | 57317775
MCR030013 | HPR235 | 2022-02-01 | Equipment | 24841385 | 23552224 | 23298346
MCR030014 | HPR235 | 2022-02-01 | Subcontract | 23777021 | 22543096 | 24254626
MCR030015 | HPR235 | 2022-02-01 | Overhead | 11358249 | 10768805 | 8097498
MCR030016 | HPR235 | 2022-03-01 | Labor | 11619146 | 6703081 | 15797102
MCR030017 | HPR235 | 2022-03-01 | Material | 50203440 | 28962345 | 59362122
MCR030018 | HPR235 | 2022-03-01 | Equipment | 25084041 | 14470974 | 13801345
MCR030019 | HPR235 | 2022-03-01 | Subcontract | 24009280 | 13850944 | 12837301
MCR030020 | HPR235 | 2022-03-01 | Overhead | 11469199 | 6616577 | 7891642
MCR030021 | HPR235 | 2022-04-01 | Labor | 11580896 | 6619888 | 13653997
MCR030022 | HPR235 | 2022-04-01 | Material | 50038169 | 28602890 | 45247713
MCR030023 | HPR235 | 2022-04-01 | Equipment | 25001464 | 14291372 | 16698340
MCR030024 | HPR235 | 2022-04-01 | Subcontract | 23930241 | 13679038 | 15263523
MCR030025 | HPR235 | 2022-04-01 | Overhead | 11431442 | 6534457 | 7301981
MCR030026 | HPR235 | 2022-05-01 | Labor | 11397983 | 11226624 | 11738100
MCR030027 | HPR235 | 2022-05-01 | Material | 49247847 | 48507450 | 57594932
MCR030028 | HPR235 | 2022-05-01 | Equipment | 24606581 | 24236643 | 23005126
MCR030029 | HPR235 | 2022-05-01 | Subcontract | 23552277 | 23198190 | 22145084
MCR030030 | HPR235 | 2022-05-01 | Overhead | 11250890 | 11081743 | 7718660
MCR030031 | HPR235 | 2022-06-01 | Labor | 11076852 | 14633568 | 17667148
MCR030032 | HPR235 | 2022-06-01 | Material | 47860323 | 63228004 | 83332878
MCR030033 | HPR235 | 2022-06-01 | Equipment | 23913307 | 31591736 | 30972105
MCR030034 | HPR235 | 2022-06-01 | Subcontract | 22888708 | 30238144 | 32365124
MCR030035 | HPR235 | 2022-06-01 | Overhead | 10933904 | 14444719 | 6857952
MCR030036 | HPR235 | 2022-07-01 | Labor | 10624490 | 5345443 | 6543754
MCR030037 | HPR235 | 2022-07-01 | Material | 45905776 | 23096327 | 24825730
MCR030038 | HPR235 | 2022-07-01 | Equipment | 22936722 | 11540030 | 14246752
MCR030039 | HPR235 | 2022-07-01 | Subcontract | 21953966 | 11045581 | 11455247
MCR030040 | HPR235 | 2022-07-01 | Overhead | 10487378 | 5276459 | 7510856
MCR030041 | HPR235 | 2022-08-01 | Labor | 10048523 | 4426071 | 4747814
MCR030042 | HPR235 | 2022-08-01 | Material | 43417170 | 19123950 | 26993849
MCR030043 | HPR235 | 2022-08-01 | Equipment | 21693295 | 9555240 | 9078789
MCR030044 | HPR235 | 2022-08-01 | Subcontract | 20763816 | 9145833 | 6963246
MCR030045 | HPR235 | 2022-08-01 | Overhead | 9918845 | 4368951 | 6532460
MCR030046 | HPR235 | 2022-09-01 | Labor | 9357368 | 8592149 | 10066927
MCR030047 | HPR235 | 2022-09-01 | Material | 40430859 | 37124539 | 37452772
MCR030048 | HPR235 | 2022-09-01 | Equipment | 20201192 | 18549196 | 18730448
MCR030049 | HPR235 | 2022-09-01 | Subcontract | 19335644 | 17754430 | 17043314
MCR030050 | HPR235 | 2022-09-01 | Overhead | 9236610 | 8481266 | 7057592
MCR030051 | HPR235 | 2022-10-01 | Labor | 8560411 | 8329653 | 9790892
MCR030052 | HPR235 | 2022-10-01 | Material | 36987405 | 35990357 | 51929768
MCR030053 | HPR235 | 2022-10-01 | Equipment | 18480678 | 17982504 | 20122239
MCR030054 | HPR235 | 2022-10-01 | Subcontract | 17688847 | 17212019 | 18740753
MCR030055 | HPR235 | 2022-10-01 | Overhead | 8449937 | 8222157 | 7742199
MCR030056 | HPR235 | 2022-11-01 | Labor | 7668278 | 7686510 | 8872999
MCR030057 | HPR235 | 2022-11-01 | Material | 33132720 | 33211496 | 37571245
MCR030058 | HPR235 | 2022-11-01 | Equipment | 16554692 | 16594052 | 15849364
MCR030059 | HPR235 | 2022-11-01 | Subcontract | 15845383 | 15883057 | 15693356
MCR030060 | HPR235 | 2022-11-01 | Overhead | 7569317 | 7587314 | 7327034
MCR030061 | HPR235 | 2022-12-01 | Labor | 6693219 | 7347095 | 9582546
MCR030062 | HPR235 | 2022-12-01 | Material | 28919734 | 31744970 | 39448199
MCR030063 | HPR235 | 2022-12-01 | Equipment | 14449683 | 15861306 | 17168980
MCR030064 | HPR235 | 2022-12-01 | Subcontract | 13830566 | 15181706 | 15884082
MCR030065 | HPR235 | 2022-12-01 | Overhead | 6606842 | 7252280 | 6952538
MCR030066 | HPR235 | 2023-01-01 | Labor | 5649699 | 4787019 | 4880715
MCR030067 | HPR235 | 2023-01-01 | Material | 24410945 | 20683516 | 26237678
MCR030068 | HPR235 | 2023-01-01 | Equipment | 12196876 | 10334474 | 11057029
MCR030069 | HPR235 | 2023-01-01 | Subcontract | 11674284 | 9891679 | 9854719
MCR030070 | HPR235 | 2023-01-01 | Overhead | 5576789 | 4725241 | 7839995
MCR030071 | HPR235 | 2023-02-01 | Labor | 4555361 | 5787415 | 6606170
MCR030072 | HPR235 | 2023-02-01 | Material | 19682581 | 25005981 | 26969035
MCR030073 | HPR235 | 2023-02-01 | Equipment | 9834359 | 12494184 | 11699311
MCR030074 | HPR235 | 2023-02-01 | Subcontract | 9412992 | 11958854 | 13700849
MCR030075 | HPR235 | 2023-02-01 | Overhead | 4496573 | 5712727 | 6913176
MCR030076 | HPR235 | 2023-03-01 | Labor | 3432742 | 10248744 | 11013651
MCR030077 | HPR235 | 2023-03-01 | Material | 14832024 | 44282273 | 51437482
MCR030078 | HPR235 | 2023-03-01 | Equipment | 7410789 | 22125543 | 26546655
MCR030079 | HPR235 | 2023-03-01 | Subcontract | 7093263 | 21177543 | 35761920
MCR030080 | HPR235 | 2023-03-01 | Overhead | 3388442 | 10116482 | 7676325
MCR030081 | HPR235 | 2023-04-01 | Labor | 2312768 | 8760590 | 11423179
MCR030082 | HPR235 | 2023-04-01 | Material | 9992896 | 37852330 | 46841703
MCR030083 | HPR235 | 2023-04-01 | Equipment | 4992929 | 18912835 | 20222742
MCR030084 | HPR235 | 2023-04-01 | Subcontract | 4779000 | 18102488 | 20997117
MCR030085 | HPR235 | 2023-04-01 | Overhead | 2282922 | 8647533 | 7099233
MCR030086 | HPR235 | 2023-05-01 | Labor | 1243555 | 6877665 | 9099070
MCR030087 | HPR235 | 2023-05-01 | Material | 5373093 | 29716678 | 32682806
MCR030088 | HPR235 | 2023-05-01 | Equipment | 2684654 | 14847874 | 16823753
MCR030089 | HPR235 | 2023-05-01 | Subcontract | 2569627 | 14211696 | 18740381
MCR030090 | HPR235 | 2023-05-01 | Overhead | 1227507 | 6788907 | 6762584
MCR030091 | HPR235 | 2023-06-01 | Labor | 327761 | 3994643 | 4257984
MCR030092 | HPR235 | 2023-06-01 | Material | 1416175 | 17259859 | 18678353
MCR030093 | HPR235 | 2023-06-01 | Equipment | 707589 | 8623852 | 7677257
MCR030094 | HPR235 | 2023-06-01 | Subcontract | 677271 | 8254351 | 12321765
MCR030095 | HPR235 | 2023-06-01 | Overhead | 323532 | 3943092 | 7237531
MCR030096 | HPR235 | 2023-07-01 | Labor | 0 | 3161660 | 4287104
MCR030097 | HPR235 | 2023-07-01 | Material | 0 | 13660747 | 15557521
MCR030098 | HPR235 | 2023-07-01 | Equipment | 0 | 6825563 | 8275453
MCR030099 | HPR235 | 2023-07-01 | Subcontract | 0 | 6533112 | 14304344
MCR030100 | HPR235 | 2023-07-01 | Overhead | 0 | 3120858 | 7209257
MCR030101 | HPR235 | 2023-08-01 | Labor | 0 | 3398478 | 3988647
MCR030102 | HPR235 | 2023-08-01 | Material | 0 | 14683979 | 17480763
MCR030103 | HPR235 | 2023-08-01 | Equipment | 0 | 7336819 | 6736519
MCR030104 | HPR235 | 2023-08-01 | Subcontract | 0 | 7022462 | 15975661
MCR030105 | HPR235 | 2023-08-01 | Overhead | 0 | 3354620 | 7017568
MCR030106 | HPR235 | 2023-09-01 | Labor | 0 | 2988814 | 3932378
MCR030107 | HPR235 | 2023-09-01 | Material | 0 | 12913922 | 14806879
MCR030108 | HPR235 | 2023-09-01 | Equipment | 0 | 6452413 | 6963571
MCR030109 | HPR235 | 2023-09-01 | Subcontract | 0 | 6175951 | 13144202
MCR030110 | HPR235 | 2023-09-01 | Overhead | 0 | 2950243 | 7044156
MCR030111 | HPR235 | 2023-10-01 | Labor | 0 | 3649672 | 4550919
MCR030112 | HPR235 | 2023-10-01 | Material | 0 | 15769325 | 19735950
MCR030113 | HPR235 | 2023-10-01 | Equipment | 0 | 7879109 | 8723486
MCR030114 | HPR235 | 2023-10-01 | Subcontract | 0 | 7541518 | 14890743
MCR030115 | HPR235 | 2023-10-01 | Overhead | 0 | 3602572 | 6887615
MCR030116 | HPR235 | 2023-11-01 | Labor | 0 | 2120628 | 2849116
MCR030117 | HPR235 | 2023-11-01 | Material | 0 | 9162708 | 9017256
MCR030118 | HPR235 | 2023-11-01 | Equipment | 0 | 4578127 | 5666251
MCR030119 | HPR235 | 2023-11-01 | Subcontract | 0 | 4381971 | 16660561
MCR030120 | HPR235 | 2023-11-01 | Overhead | 0 | 2093261 | 7339047
MCR030121 | HPR235 | 2023-12-01 | Labor | 0 | 1982571 | 2274552
MCR030122 | HPR235 | 2023-12-01 | Material | 0 | 8566195 | 9660623
MCR030123 | HPR235 | 2023-12-01 | Equipment | 0 | 4280081 | 4486526
MCR030124 | HPR235 | 2023-12-01 | Subcontract | 0 | 4096695 | 16856463
MCR030125 | HPR235 | 2023-12-01 | Overhead | 0 | 1956985 | 7249434
MCR030126 | HPR235 | 2024-01-01 | Labor | 0 | 1655378 | 1989319
MCR030127 | HPR235 | 2024-01-01 | Material | 0 | 7152476 | 7474246
MCR030128 | HPR235 | 2024-01-01 | Equipment | 0 | 3573719 | 4494199
MCR030129 | HPR235 | 2024-01-01 | Subcontract | 0 | 3420598 | 13261615
MCR030130 | HPR235 | 2024-01-01 | Overhead | 0 | 1634015 | 7714853
MCR030131 | HPR235 | 2024-02-01 | Labor | 0 | 508923 | 608611
MCR030132 | HPR235 | 2024-02-01 | Material | 0 | 2198928 | 2746329
MCR030133 | HPR235 | 2024-02-01 | Equipment | 0 | 1098690 | 1147638
MCR030134 | HPR235 | 2024-02-01 | Subcontract | 0 | 1051615 | 6309694
MCR030135 | HPR235 | 2024-02-01 | Overhead | 0 | 502355 | 8256196
MCR030136 | HPR235 | 2024-03-01 | Labor | 0 | 191751 | 260876
MCR030137 | HPR235 | 2024-03-01 | Material | 0 | 828508 | 1066006
MCR030138 | HPR235 | 2024-03-01 | Equipment | 0 | 413962 | 553383
MCR030139 | HPR235 | 2024-03-01 | Subcontract | 0 | 396225 | 11160571
MCR030140 | HPR235 | 2024-03-01 | Overhead | 0 | 189276 | 7672814
MCR030141 | HPR236 | 2019-01-01 | Labor | 5404949 | 4876491 | 4817371
MCR030142 | HPR236 | 2019-01-01 | Material | 16952871 | 15295341 | 15043822
MCR030143 | HPR236 | 2019-01-01 | Equipment | 4474006 | 4036570 | 4257538
MCR030144 | HPR236 | 2019-01-01 | Subcontract | 20198870 | 18223969 | 17254318
MCR030145 | HPR236 | 2019-01-01 | Overhead | 4064483 | 3667087 | 15408605
MCR030146 | HPR236 | 2019-02-01 | Labor | 14713036 | 7042223 | 8434697
MCR030147 | HPR236 | 2019-02-01 | Material | 46148119 | 22088259 | 21255515
MCR030148 | HPR236 | 2019-02-01 | Equipment | 12178880 | 5829279 | 6427335
MCR030149 | HPR236 | 2019-02-01 | Subcontract | 54984188 | 26317540 | 29691833
MCR030150 | HPR236 | 2019-02-01 | Overhead | 11064098 | 5295701 | 15204751
MCR030151 | HPR236 | 2019-03-01 | Labor | 21834363 | 15251052 | 17733535
MCR030152 | HPR236 | 2019-03-01 | Material | 68484489 | 47835631 | 47520421
MCR030153 | HPR236 | 2019-03-01 | Equipment | 18073637 | 12624229 | 14400167
MCR030154 | HPR236 | 2019-03-01 | Subcontract | 81597346 | 56994811 | 63902676
MCR030155 | HPR236 | 2019-03-01 | Overhead | 16419284 | 11468682 | 14835321
MCR030156 | HPR236 | 2019-04-01 | Labor | 26863096 | 18890607 | 20966006
MCR030157 | HPR236 | 2019-04-01 | Material | 84257343 | 59251263 | 57483941
MCR030158 | HPR236 | 2019-04-01 | Equipment | 22236227 | 15636911 | 14402119
MCR030159 | HPR236 | 2019-04-01 | Subcontract | 100390258 | 70596215 | 77005399
MCR030160 | HPR236 | 2019-04-01 | Overhead | 20200855 | 14205601 | 14333276
MCR030161 | HPR236 | 2019-05-01 | Labor | 29902637 | 23496912 | 25087239
MCR030162 | HPR236 | 2019-05-01 | Material | 93791006 | 73699152 | 80328225
MCR030163 | HPR236 | 2019-05-01 | Equipment | 24752242 | 19449831 | 21462750
MCR030164 | HPR236 | 2019-05-01 | Subcontract | 111749349 | 87810470 | 86054516
MCR030165 | HPR236 | 2019-05-01 | Overhead | 22486569 | 17669509 | 14935959
MCR030166 | HPR236 | 2019-06-01 | Labor | 31067926 | 31898099 | 29464206
MCR030167 | HPR236 | 2019-06-01 | Material | 97445989 | 100049864 | 121110811
MCR030168 | HPR236 | 2019-06-01 | Equipment | 25716823 | 26404008 | 31930502
MCR030169 | HPR236 | 2019-06-01 | Subcontract | 116104159 | 119206603 | 136554470
MCR030170 | HPR236 | 2019-06-01 | Overhead | 23362858 | 23987142 | 14145141
MCR030171 | HPR236 | 2019-07-01 | Labor | 30488737 | 9241255 | 13220539
MCR030172 | HPR236 | 2019-07-01 | Material | 95629336 | 28985623 | 19776646
MCR030173 | HPR236 | 2019-07-01 | Equipment | 25237393 | 7649552 | 5787310
MCR030174 | HPR236 | 2019-07-01 | Subcontract | 113939668 | 34535556 | 29733311
MCR030175 | HPR236 | 2019-07-01 | Overhead | 22927312 | 6949357 | 13469958
MCR030176 | HPR236 | 2019-08-01 | Labor | 28314634 | 13643293 | 16474977
MCR030177 | HPR236 | 2019-08-01 | Material | 88810158 | 42792821 | 44570649
MCR030178 | HPR236 | 2019-08-01 | Equipment | 23437754 | 11293388 | 12556048
MCR030179 | HPR236 | 2019-08-01 | Subcontract | 105814809 | 50986444 | 50748604
MCR030180 | HPR236 | 2019-08-01 | Overhead | 21292401 | 10259659 | 15697222
MCR030181 | HPR236 | 2019-09-01 | Labor | 24722902 | 14316626 | 14578145
MCR030182 | HPR236 | 2019-09-01 | Material | 77544526 | 44904759 | 47291329
MCR030183 | HPR236 | 2019-09-01 | Equipment | 20464658 | 11850747 | 11587406
MCR030184 | HPR236 | 2019-09-01 | Subcontract | 92392125 | 53502759 | 57127509
MCR030185 | HPR236 | 2019-09-01 | Overhead | 18591445 | 10766000 | 15155777
MCR030186 | HPR236 | 2019-10-01 | Labor | 19932408 | 27007380 | 31563504
MCR030187 | HPR236 | 2019-10-01 | Material | 62518920 | 84709899 | 76076799
MCR030188 | HPR236 | 2019-10-01 | Equipment | 16499273 | 22355661 | 25915396
MCR030189 | HPR236 | 2019-10-01 | Subcontract | 74489538 | 100929465 | 115779288
MCR030190 | HPR236 | 2019-10-01 | Overhead | 14989028 | 20309356 | 13699894
MCR030191 | HPR236 | 2019-11-01 | Labor | 14231084 | 18013143 | 16175363
MCR030192 | HPR236 | 2019-11-01 | Material | 44636452 | 56499057 | 67348583
MCR030193 | HPR236 | 2019-11-01 | Equipment | 11779938 | 14910580 | 16179301
MCR030194 | HPR236 | 2019-11-01 | Subcontract | 53183079 | 67317039 | 62402270
MCR030195 | HPR236 | 2019-11-01 | Overhead | 10701673 | 13545754 | 14529927
MCR030196 | HPR236 | 2019-12-01 | Labor | 8043392 | 14101398 | 16448416
MCR030197 | HPR236 | 2019-12-01 | Material | 25228473 | 44229687 | 42037793
MCR030198 | HPR236 | 2019-12-01 | Equipment | 6658008 | 11672590 | 10380716
MCR030199 | HPR236 | 2019-12-01 | Subcontract | 30059017 | 52698430 | 59862662
MCR030200 | HPR236 | 2019-12-01 | Overhead | 6048573 | 10604150 | 15956060
MCR030201 | HPR236 | 2020-01-01 | Labor | 2206329 | 23195342 | 26379266
MCR030202 | HPR236 | 2020-01-01 | Material | 6920254 | 72753263 | 68798848
MCR030203 | HPR236 | 2020-01-01 | Equipment | 1826314 | 19200203 | 19148323
MCR030204 | HPR236 | 2020-01-01 | Subcontract | 8245289 | 86683470 | 83562419
MCR030205 | HPR236 | 2020-01-01 | Overhead | 1659144 | 17442731 | 15064479
MCR030206 | HPR236 | 2020-02-01 | Labor | 0 | 13857843 | 13051153
MCR030207 | HPR236 | 2020-02-01 | Material | 0 | 43465767 | 54858687
MCR030208 | HPR236 | 2020-02-01 | Equipment | 0 | 11470984 | 14534281
MCR030209 | HPR236 | 2020-02-01 | Subcontract | 0 | 51788240 | 56416084
MCR030210 | HPR236 | 2020-02-01 | Overhead | 0 | 10420999 | 15288784
MCR030211 | HPR236 | 2020-03-01 | Labor | 0 | 10936145 | 12384943
MCR030212 | HPR236 | 2020-03-01 | Material | 0 | 34301724 | 34873382
MCR030213 | HPR236 | 2020-03-01 | Equipment | 0 | 9052516 | 9611569
MCR030214 | HPR236 | 2020-03-01 | Subcontract | 0 | 40869541 | 46330371
MCR030215 | HPR236 | 2020-03-01 | Overhead | 0 | 8223902 | 14049849
MCR030216 | HPR236 | 2020-04-01 | Labor | 0 | 7152628 | 7324977
MCR030217 | HPR236 | 2020-04-01 | Material | 0 | 22434550 | 21329000
MCR030218 | HPR236 | 2020-04-01 | Equipment | 0 | 5920668 | 5619661
MCR030219 | HPR236 | 2020-04-01 | Subcontract | 0 | 26730136 | 25423696
MCR030220 | HPR236 | 2020-04-01 | Overhead | 0 | 5378725 | 14972541
MCR030221 | HPR236 | 2020-05-01 | Labor | 0 | 3895723 | 4101088
MCR030222 | HPR236 | 2020-05-01 | Material | 0 | 12219115 | 14570474
MCR030223 | HPR236 | 2020-05-01 | Equipment | 0 | 3224728 | 4866621
MCR030224 | HPR236 | 2020-05-01 | Subcontract | 0 | 14558733 | 15047292
MCR030225 | HPR236 | 2020-05-01 | Overhead | 0 | 2929556 | 15229036
MCR030226 | HPR236 | 2020-06-01 | Labor | 0 | 909332 | 781494
MCR030227 | HPR236 | 2020-06-01 | Material | 0 | 2852162 | 1878578
MCR030228 | HPR236 | 2020-06-01 | Equipment | 0 | 752710 | 820846
MCR030229 | HPR236 | 2020-06-01 | Subcontract | 0 | 3398270 | 3823695
MCR030230 | HPR236 | 2020-06-01 | Overhead | 0 | 683811 | 15251226
MCR030231 | HPR237 | 2017-03-01 | Labor | 2466340 | 2366238 | 2697000
MCR030232 | HPR237 | 2017-03-01 | Material | 7406879 | 7106252 | 7358681
MCR030233 | HPR237 | 2017-03-01 | Equipment | 2609097 | 2503201 | 2519227
MCR030234 | HPR237 | 2017-03-01 | Subcontract | 8822590 | 8464503 | 8189766
MCR030235 | HPR237 | 2017-03-01 | Overhead | 2400718 | 2303278 | 12117529
MCR030236 | HPR237 | 2017-04-01 | Labor | 6936223 | 5614516 | 6191723
MCR030237 | HPR237 | 2017-04-01 | Material | 20830767 | 16861435 | 16185062
MCR030238 | HPR237 | 2017-04-01 | Equipment | 7337705 | 5939495 | 6052642
MCR030239 | HPR237 | 2017-04-01 | Subcontract | 24812247 | 20084238 | 18564255
MCR030240 | HPR237 | 2017-04-01 | Overhead | 6751668 | 5465128 | 12080716
MCR030241 | HPR237 | 2017-05-01 | Labor | 10725270 | 7820322 | 8607579
MCR030242 | HPR237 | 2017-05-01 | Material | 32209981 | 23485882 | 22438238
MCR030243 | HPR237 | 2017-05-01 | Equipment | 11346071 | 8272978 | 8340600
MCR030244 | HPR237 | 2017-05-01 | Subcontract | 38366424 | 27974848 | 32481093
MCR030245 | HPR237 | 2017-05-01 | Overhead | 10439899 | 7612244 | 12058709
MCR030246 | HPR237 | 2017-06-01 | Labor | 13852104 | 9976864 | 10542256
MCR030247 | HPR237 | 2017-06-01 | Material | 41600445 | 29962378 | 30330743
MCR030248 | HPR237 | 2017-06-01 | Equipment | 14653892 | 10554345 | 10709240
MCR030249 | HPR237 | 2017-06-01 | Subcontract | 49551731 | 35689225 | 34766070
MCR030250 | HPR237 | 2017-06-01 | Overhead | 13483536 | 9711406 | 12303885
MCR030251 | HPR237 | 2017-07-01 | Labor | 16336465 | 9283905 | 9287383
MCR030252 | HPR237 | 2017-07-01 | Material | 49061441 | 27881294 | 30683227
MCR030253 | HPR237 | 2017-07-01 | Equipment | 17282052 | 9821276 | 9456293
MCR030254 | HPR237 | 2017-07-01 | Subcontract | 58438781 | 33210375 | 36813484
MCR030255 | HPR237 | 2017-07-01 | Overhead | 15901794 | 9036885 | 12108135
MCR030256 | HPR237 | 2017-08-01 | Labor | 18199374 | 8967733 | 10304217
MCR030257 | HPR237 | 2017-08-01 | Material | 54656104 | 26931770 | 26033994
MCR030258 | HPR237 | 2017-08-01 | Equipment | 19252790 | 9486804 | 11698293
MCR030259 | HPR237 | 2017-08-01 | Subcontract | 65102777 | 32079364 | 35657912
MCR030260 | HPR237 | 2017-08-01 | Overhead | 17715136 | 8729125 | 13335039
MCR030261 | HPR237 | 2017-09-01 | Labor | 19463339 | 34942761 | 36696006
MCR030262 | HPR237 | 2017-09-01 | Material | 58452026 | 104939609 | 116410056
MCR030263 | HPR237 | 2017-09-01 | Equipment | 20589916 | 36965318 | 36394920
MCR030264 | HPR237 | 2017-09-01 | Subcontract | 69624232 | 124997202 | 122993555
MCR030265 | HPR237 | 2017-09-01 | Overhead | 18945470 | 34013026 | 12156364
MCR030266 | HPR237 | 2017-10-01 | Labor | 20152608 | 18818622 | 22107834
MCR030267 | HPR237 | 2017-10-01 | Material | 60522028 | 56515821 | 48227341
MCR030268 | HPR237 | 2017-10-01 | Equipment | 21319081 | 19907882 | 23358170
MCR030269 | HPR237 | 2017-10-01 | Subcontract | 72089883 | 67317952 | 72790086
MCR030270 | HPR237 | 2017-10-01 | Overhead | 19616399 | 18317908 | 11940787
MCR030271 | HPR237 | 2017-11-01 | Labor | 20293494 | 8296407 | 7372576
MCR030272 | HPR237 | 2017-11-01 | Material | 60945136 | 24915654 | 27736030
MCR030273 | HPR237 | 2017-11-01 | Equipment | 21468122 | 8776620 | 7135763
MCR030274 | HPR237 | 2017-11-01 | Subcontract | 72593862 | 29677898 | 35639568
MCR030275 | HPR237 | 2017-11-01 | Overhead | 19753537 | 8075662 | 11789992
MCR030276 | HPR237 | 2017-12-01 | Labor | 19914810 | 20306966 | 23114864
MCR030277 | HPR237 | 2017-12-01 | Material | 59807877 | 60985596 | 54752443
MCR030278 | HPR237 | 2017-12-01 | Equipment | 21067519 | 21482374 | 22362770
MCR030279 | HPR237 | 2017-12-01 | Subcontract | 71239233 | 72642055 | 77236583
MCR030280 | HPR237 | 2017-12-01 | Overhead | 19384929 | 19766651 | 12791788
MCR030281 | HPR237 | 2018-01-01 | Labor | 19048441 | 16779225 | 18355499
MCR030282 | HPR237 | 2018-01-01 | Material | 57206011 | 50391133 | 58277038
MCR030283 | HPR237 | 2018-01-01 | Equipment | 20151003 | 17750440 | 17115801
MCR030284 | HPR237 | 2018-01-01 | Subcontract | 68140061 | 60022623 | 64004237
MCR030285 | HPR237 | 2018-01-01 | Overhead | 18541612 | 16332774 | 11424576
MCR030286 | HPR237 | 2018-02-01 | Labor | 17730154 | 23685262 | 27720915
MCR030287 | HPR237 | 2018-02-01 | Material | 53246949 | 71131245 | 71498136
MCR030288 | HPR237 | 2018-02-01 | Equipment | 18756411 | 25056212 | 24785694
MCR030289 | HPR237 | 2018-02-01 | Subcontract | 63424285 | 84726889 | 90374924
MCR030290 | HPR237 | 2018-02-01 | Overhead | 17258401 | 23055059 | 12509898
MCR030291 | HPR237 | 2018-03-01 | Labor | 16000754 | 15332172 | 15714604
MCR030292 | HPR237 | 2018-03-01 | Material | 48053241 | 46045365 | 46602276
MCR030293 | HPR237 | 2018-03-01 | Equipment | 16926910 | 16219629 | 15711468
MCR030294 | HPR237 | 2018-03-01 | Subcontract | 57237879 | 54846228 | 50008853
MCR030295 | HPR237 | 2018-03-01 | Overhead | 15575016 | 14924223 | 12723579
MCR030296 | HPR237 | 2018-04-01 | Labor | 13907854 | 15158021 | 17425984
MCR030297 | HPR237 | 2018-04-01 | Material | 41767872 | 45522356 | 43072191
MCR030298 | HPR237 | 2018-04-01 | Equipment | 14712869 | 16035398 | 15399259
MCR030299 | HPR237 | 2018-04-01 | Subcontract | 49751158 | 54223255 | 61363512
MCR030300 | HPR237 | 2018-04-01 | Overhead | 13537802 | 14754706 | 11887541
MCR030301 | HPR237 | 2018-05-01 | Labor | 11508724 | 16102652 | 21034677
MCR030302 | HPR237 | 2018-05-01 | Material | 34562839 | 48359258 | 47300746
MCR030303 | HPR237 | 2018-05-01 | Equipment | 12174872 | 17034706 | 16395610
MCR030304 | HPR237 | 2018-05-01 | Subcontract | 41168994 | 57602387 | 65916010
MCR030305 | HPR237 | 2018-05-01 | Overhead | 11202507 | 15674202 | 12883406
MCR030306 | HPR237 | 2018-06-01 | Labor | 8875343 | 10338557 | 9744169
MCR030307 | HPR237 | 2018-06-01 | Material | 26654306 | 31048609 | 36073007
MCR030308 | HPR237 | 2018-06-01 | Equipment | 9389066 | 10936973 | 10463487
MCR030309 | HPR237 | 2018-06-01 | Subcontract | 31748867 | 36983073 | 36915561
MCR030310 | HPR237 | 2018-06-01 | Overhead | 8639193 | 10063475 | 12979489
MCR030311 | HPR237 | 2018-07-01 | Labor | 6104546 | 10232675 | 11884622
MCR030312 | HPR237 | 2018-07-01 | Material | 18333088 | 30730624 | 30679975
MCR030313 | HPR237 | 2018-07-01 | Equipment | 6457890 | 10824962 | 11022544
MCR030314 | HPR237 | 2018-07-01 | Subcontract | 21837176 | 36604311 | 36707704
MCR030315 | HPR237 | 2018-07-01 | Overhead | 5942120 | 9960410 | 12849614
MCR030316 | HPR237 | 2018-08-01 | Labor | 3343332 | 4727356 | 5228430
MCR030317 | HPR237 | 2018-08-01 | Material | 10040648 | 14197130 | 14895615
MCR030318 | HPR237 | 2018-08-01 | Equipment | 3536851 | 5000985 | 5531088
MCR030319 | HPR237 | 2018-08-01 | Subcontract | 11959763 | 16910693 | 20796228
MCR030320 | HPR237 | 2018-08-01 | Overhead | 3254375 | 4601574 | 12657240
MCR030321 | HPR237 | 2018-09-01 | Labor | 894644 | 3395573 | 4291068
MCR030322 | HPR237 | 2018-09-01 | Material | 2686783 | 10197537 | 9528099
MCR030323 | HPR237 | 2018-09-01 | Equipment | 946428 | 3592116 | 3456007
MCR030324 | HPR237 | 2018-09-01 | Subcontract | 3200320 | 12146640 | 12130293
MCR030325 | HPR237 | 2018-09-01 | Overhead | 870840 | 3305226 | 12457813
MCR030326 | HPR237 | 2018-10-01 | Labor | 0 | 3157448 | 3525624
MCR030327 | HPR237 | 2018-10-01 | Material | 0 | 9482403 | 8568418
MCR030328 | HPR237 | 2018-10-01 | Equipment | 0 | 3340207 | 3437240
MCR030329 | HPR237 | 2018-10-01 | Subcontract | 0 | 11294819 | 12232067
MCR030330 | HPR237 | 2018-10-01 | Overhead | 0 | 3073436 | 12162502
MCR030331 | HPR237 | 2018-11-01 | Labor | 0 | 450544 | 435710
MCR030332 | HPR237 | 2018-11-01 | Material | 0 | 1353067 | 2333241
MCR030333 | HPR237 | 2018-11-01 | Equipment | 0 | 476622 | 429293
MCR030334 | HPR237 | 2018-11-01 | Subcontract | 0 | 1611685 | 1084015
MCR030335 | HPR237 | 2018-11-01 | Overhead | 0 | 438556 | 13067053
MCR030336 | HPR238 | 2022-08-01 | Labor | 1422721 | 630346 | 627322
MCR030337 | HPR238 | 2022-08-01 | Material | 2947976 | 1306120 | 1427428
MCR030338 | HPR238 | 2022-08-01 | Equipment | 631049 | 279590 | 286786
MCR030339 | HPR238 | 2022-08-01 | Subcontract | 3545617 | 1570908 | 1485668
MCR030340 | HPR238 | 2022-08-01 | Overhead | 678796 | 300745 | 5790867
MCR030341 | HPR238 | 2022-09-01 | Labor | 4106313 | 4214494 | 3605198
MCR030342 | HPR238 | 2022-09-01 | Material | 8508562 | 8732720 | 8393913
MCR030343 | HPR238 | 2022-09-01 | Equipment | 1821358 | 1869342 | 2013629
MCR030344 | HPR238 | 2022-09-01 | Subcontract | 10233495 | 10503097 | 9498174
MCR030345 | HPR238 | 2022-09-01 | Overhead | 1959166 | 2010780 | 5740380
MCR030346 | HPR238 | 2022-10-01 | Labor | 6549901 | 7550395 | 6980828
MCR030347 | HPR238 | 2022-10-01 | Material | 13571845 | 15644936 | 17637150
MCR030348 | HPR238 | 2022-10-01 | Equipment | 2905214 | 3348984 | 3677869
MCR030349 | HPR238 | 2022-10-01 | Subcontract | 16323254 | 18816621 | 16024107
MCR030350 | HPR238 | 2022-10-01 | Overhead | 3125028 | 3602374 | 6260467
MCR030351 | HPR238 | 2022-11-01 | Labor | 8757283 | 9706560 | 9273724
MCR030352 | HPR238 | 2022-11-01 | Material | 18145690 | 20112659 | 17215565
MCR030353 | HPR238 | 2022-11-01 | Equipment | 3884300 | 4305353 | 4270651
MCR030354 | HPR238 | 2022-11-01 | Subcontract | 21824351 | 24190081 | 25755136
MCR030355 | HPR238 | 2022-11-01 | Overhead | 4178193 | 4631104 | 5571644
MCR030356 | HPR238 | 2022-12-01 | Labor | 10732380 | 6716483 | 6556575
MCR030357 | HPR238 | 2022-12-01 | Material | 22238229 | 13917014 | 15576408
MCR030358 | HPR238 | 2022-12-01 | Equipment | 4760356 | 2979101 | 2995094
MCR030359 | HPR238 | 2022-12-01 | Subcontract | 26746566 | 16738398 | 14991579
MCR030360 | HPR238 | 2022-12-01 | Overhead | 5120534 | 3204506 | 5923887
MCR030361 | HPR238 | 2023-01-01 | Labor | 12479258 | 15234567 | 16990817
MCR030362 | HPR238 | 2023-01-01 | Material | 25857879 | 31567069 | 33911681
MCR030363 | HPR238 | 2023-01-01 | Equipment | 5535185 | 6757305 | 6158028
MCR030364 | HPR238 | 2023-01-01 | Subcontract | 31100024 | 37966634 | 35622478
MCR030365 | HPR238 | 2023-01-01 | Overhead | 5953988 | 7268575 | 5649587
MCR030366 | HPR238 | 2023-02-01 | Labor | 14002128 | 21954459 | 16243145
MCR030367 | HPR238 | 2023-02-01 | Material | 29013371 | 45491146 | 38849168
MCR030368 | HPR238 | 2023-02-01 | Equipment | 6210655 | 9737918 | 11115060
MCR030369 | HPR238 | 2023-02-01 | Subcontract | 34895227 | 54713527 | 51022326
MCR030370 | HPR238 | 2023-02-01 | Overhead | 6680565 | 10474707 | 5810577
MCR030371 | HPR238 | 2023-03-01 | Labor | 15305369 | 13995769 | 15827784
MCR030372 | HPR238 | 2023-03-01 | Material | 31713775 | 29000195 | 31411530
MCR030373 | HPR238 | 2023-03-01 | Equipment | 6788709 | 6207835 | 5531541
MCR030374 | HPR238 | 2023-03-01 | Subcontract | 38143082 | 34879379 | 34707742
MCR030375 | HPR238 | 2023-03-01 | Overhead | 7302356 | 6677531 | 5358561
MCR030376 | HPR238 | 2023-04-01 | Labor | 16393536 | 16171660 | 14692172
MCR030377 | HPR238 | 2023-04-01 | Material | 33968531 | 33508788 | 37442952
MCR030378 | HPR238 | 2023-04-01 | Equipment | 7271366 | 7172953 | 6429748
MCR030379 | HPR238 | 2023-04-01 | Subcontract | 40854943 | 40301996 | 38106279
MCR030380 | HPR238 | 2023-04-01 | Overhead | 7821531 | 7715672 | 5960671
MCR030381 | HPR238 | 2023-05-01 | Labor | 17271380 | 33344384 | 30243163
MCR030382 | HPR238 | 2023-05-01 | Material | 35787484 | 69091852 | 72898075
MCR030383 | HPR238 | 2023-05-01 | Equipment | 7660735 | 14789929 | 15487688
MCR030384 | HPR238 | 2023-05-01 | Subcontract | 43042650 | 83098784 | 69473315
MCR030385 | HPR238 | 2023-05-01 | Overhead | 8240360 | 15908963 | 5951241
MCR030386 | HPR238 | 2023-06-01 | Labor | 17943868 | 14657890 | 24513008
MCR030387 | HPR238 | 2023-06-01 | Material | 37180925 | 30372155 | 46089207
MCR030388 | HPR238 | 2023-06-01 | Equipment | 7959017 | 6501519 | 6446031
MCR030389 | HPR238 | 2023-06-01 | Subcontract | 44718582 | 36529476 | 41249043
MCR030390 | HPR238 | 2023-06-01 | Overhead | 8561211 | 6993436 | 6042903
MCR030391 | HPR238 | 2023-07-01 | Labor | 18416204 | 16987911 | 36808603
MCR030392 | HPR238 | 2023-07-01 | Material | 38159638 | 35200117 | 50289769
MCR030393 | HPR238 | 2023-07-01 | Equipment | 8168522 | 7535002 | 7954434
MCR030394 | HPR238 | 2023-07-01 | Subcontract | 45895709 | 42336207 | 32591017
MCR030395 | HPR238 | 2023-07-01 | Overhead | 8786568 | 8105114 | 5737906
MCR030396 | HPR238 | 2023-08-01 | Labor | 18693859 | 18377917 | 13517368
MCR030397 | HPR238 | 2023-08-01 | Material | 38734958 | 38080305 | 38794701
MCR030398 | HPR238 | 2023-08-01 | Equipment | 8291676 | 8151540 | 6911735
MCR030399 | HPR238 | 2023-08-01 | Subcontract | 46587663 | 45800293 | 45147061
MCR030400 | HPR238 | 2023-08-01 | Overhead | 8919040 | 8768301 | 5653907
MCR030401 | HPR238 | 2023-09-01 | Labor | 18782598 | 16770393 | 16836171
MCR030402 | HPR238 | 2023-09-01 | Material | 38918832 | 34749405 | 37075236
MCR030403 | HPR238 | 2023-09-01 | Equipment | 8331037 | 7438522 | 8042551
MCR030404 | HPR238 | 2023-09-01 | Subcontract | 46808813 | 41794122 | 39713241
MCR030405 | HPR238 | 2023-09-01 | Overhead | 8961378 | 8001334 | 5814985
MCR030406 | HPR238 | 2023-10-01 | Labor | 18688521 | 12649606 | 11719044
MCR030407 | HPR238 | 2023-10-01 | Material | 38723898 | 26210851 | 24900981
MCR030408 | HPR238 | 2023-10-01 | Equipment | 8289309 | 5610743 | 5723188
MCR030409 | HPR238 | 2023-10-01 | Subcontract | 46574361 | 31524554 | 25852447
MCR030410 | HPR238 | 2023-10-01 | Overhead | 8916493 | 6035262 | 5754657
MCR030411 | HPR238 | 2023-11-01 | Labor | 18418107 | 14104863 | 13448576
MCR030412 | HPR238 | 2023-11-01 | Material | 38163581 | 29226244 | 27696129
MCR030413 | HPR238 | 2023-11-01 | Equipment | 8169366 | 6256223 | 5190983
MCR030414 | HPR238 | 2023-11-01 | Subcontract | 45900451 | 35151255 | 35531288
MCR030415 | HPR238 | 2023-11-01 | Overhead | 8787476 | 6729581 | 5872149
MCR030416 | HPR238 | 2023-12-01 | Labor | 17978266 | 15988537 | 14865471
MCR030417 | HPR238 | 2023-12-01 | Material | 37252201 | 33129345 | 30665186
MCR030418 | HPR238 | 2023-12-01 | Equipment | 7974275 | 7091729 | 7706620
MCR030419 | HPR238 | 2023-12-01 | Subcontract | 44804308 | 39845629 | 35977670
MCR030420 | HPR238 | 2023-12-01 | Overhead | 8577623 | 7628302 | 5531077
MCR030421 | HPR238 | 2024-01-01 | Labor | 17376410 | 16118161 | 15311374
MCR030422 | HPR238 | 2024-01-01 | Material | 36005115 | 33397935 | 39794559
MCR030423 | HPR238 | 2024-01-01 | Equipment | 7707321 | 7149223 | 6345933
MCR030424 | HPR238 | 2024-01-01 | Subcontract | 43304401 | 40168670 | 39782515
MCR030425 | HPR238 | 2024-01-01 | Overhead | 8290471 | 7690147 | 5555376
MCR030426 | HPR238 | 2024-02-01 | Labor | 16620535 | 26354966 | 19681437
MCR030427 | HPR238 | 2024-02-01 | Material | 34438889 | 54609298 | 48442396
MCR030428 | HPR238 | 2024-02-01 | Equipment | 7372052 | 11689767 | 11765122
MCR030429 | HPR238 | 2024-02-01 | Subcontract | 41420656 | 65680195 | 52855249
MCR030430 | HPR238 | 2024-02-01 | Overhead | 7929835 | 12574236 | 5517014
MCR030431 | HPR238 | 2024-03-01 | Labor | 15719326 | 11393135 | 11513629
MCR030432 | HPR238 | 2024-03-01 | Material | 32571521 | 23607357 | 24189041
MCR030433 | HPR238 | 2024-03-01 | Equipment | 6972320 | 5053434 | 5867517
MCR030434 | HPR238 | 2024-03-01 | Subcontract | 39174718 | 28393256 | 30885635
MCR030435 | HPR238 | 2024-03-01 | Overhead | 7499859 | 5435786 | 5779975
MCR030436 | HPR238 | 2024-04-01 | Labor | 14682295 | 11027105 | 11146303
MCR030437 | HPR238 | 2024-04-01 | Material | 30422722 | 22848918 | 22608537
MCR030438 | HPR238 | 2024-04-01 | Equipment | 6512344 | 4891081 | 4890696
MCR030439 | HPR238 | 2024-04-01 | Subcontract | 36590295 | 27481060 | 26058053
MCR030440 | HPR238 | 2024-04-01 | Overhead | 7005080 | 5261150 | 6086297
MCR030441 | HPR238 | 2024-05-01 | Labor | 13519965 | 15914909 | 14433330
MCR030442 | HPR238 | 2024-05-01 | Material | 28014295 | 32976784 | 33218257
MCR030443 | HPR238 | 2024-05-01 | Equipment | 5996791 | 7059071 | 6999746
MCR030444 | HPR238 | 2024-05-01 | Subcontract | 33693609 | 39662139 | 40804180
MCR030445 | HPR238 | 2024-05-01 | Overhead | 6450520 | 7593174 | 5628184
MCR030446 | HPR238 | 2024-06-01 | Labor | 12244114 | 8149762 | 7618350
MCR030447 | HPR238 | 2024-06-01 | Material | 25370645 | 16886866 | 17271673
MCR030448 | HPR238 | 2024-06-01 | Equipment | 5430887 | 3614834 | 3769741
MCR030449 | HPR238 | 2024-06-01 | Subcontract | 30514014 | 20310326 | 17145870
MCR030450 | HPR238 | 2024-06-01 | Overhead | 5841798 | 3888339 | 6635483
MCR030451 | HPR238 | 2024-07-01 | Labor | 10868125 | 8523213 | 7090008
MCR030452 | HPR238 | 2024-07-01 | Material | 22519501 | 17660683 | 16793595
MCR030453 | HPR238 | 2024-07-01 | Equipment | 4820566 | 3780478 | 3536255
MCR030454 | HPR238 | 2024-07-01 | Subcontract | 27084860 | 21241018 | 20230283
MCR030455 | HPR238 | 2024-07-01 | Overhead | 5185299 | 4066516 | 5592463
MCR030456 | HPR238 | 2024-08-01 | Labor | 9407488 | 8211410 | 7170749
MCR030457 | HPR238 | 2024-08-01 | Material | 19492961 | 17014605 | 18374817
MCR030458 | HPR238 | 2024-08-01 | Equipment | 4172699 | 3642178 | 3043933
MCR030459 | HPR238 | 2024-08-01 | Subcontract | 23444753 | 20463962 | 20457248
MCR030460 | HPR238 | 2024-08-01 | Overhead | 4488413 | 3917752 | 5400282
MCR030461 | HPR238 | 2024-09-01 | Labor | 7880581 | 9493766 | 7731526
MCR030462 | HPR238 | 2024-09-01 | Material | 16329105 | 19671735 | 16773344
MCR030463 | HPR238 | 2024-09-01 | Equipment | 3495438 | 4210968 | 4595683
MCR030464 | HPR238 | 2024-09-01 | Subcontract | 19639490 | 23659769 | 22867388
MCR030465 | HPR238 | 2024-09-01 | Overhead | 3759910 | 4529577 | 5899355
MCR030466 | HPR238 | 2024-10-01 | Labor | 6309937 | 5452702 | 4115749
MCR030467 | HPR238 | 2024-10-01 | Material | 13074623 | 11298372 | 12263534
MCR030468 | HPR238 | 2024-10-01 | Equipment | 2798778 | 2418550 | 2313723
MCR030469 | HPR238 | 2024-10-01 | Subcontract | 15725230 | 13588882 | 14877941
MCR030470 | HPR238 | 2024-10-01 | Overhead | 3010539 | 2601542 | 5856013
MCR030471 | HPR238 | 2024-11-01 | Labor | 4724522 | 3868605 | 3494141
MCR030472 | HPR238 | 2024-11-01 | Material | 9789534 | 8016015 | 7594192
MCR030473 | HPR238 | 2024-11-01 | Equipment | 2095566 | 1715923 | 1722058
MCR030474 | HPR238 | 2024-11-01 | Subcontract | 11774158 | 9641094 | 7730357
MCR030475 | HPR238 | 2024-11-01 | Overhead | 2254120 | 1845753 | 5897134
MCR030476 | HPR238 | 2024-12-01 | Labor | 3164370 | 4129871 | 2849502
MCR030477 | HPR238 | 2024-12-01 | Material | 6556792 | 8557375 | 8087327
MCR030478 | HPR238 | 2024-12-01 | Equipment | 1403559 | 1831808 | 1740455
MCR030479 | HPR238 | 2024-12-01 | Subcontract | 7886045 | 10292205 | 9417457
MCR030480 | HPR238 | 2024-12-01 | Overhead | 1509755 | 1970406 | 5794927
MCR030481 | HPR238 | 2025-01-01 | Labor | 1692315 | 2528552 | 2123229
MCR030482 | HPR238 | 2025-01-01 | Material | 3506594 | 5239333 | 5744691
MCR030483 | HPR238 | 2025-01-01 | Equipment | 750628 | 1121541 | 1153195
MCR030484 | HPR238 | 2025-01-01 | Subcontract | 4217483 | 6301499 | 5284728
MCR030485 | HPR238 | 2025-01-01 | Overhead | 807422 | 1206399 | 6030038
MCR030486 | HPR238 | 2025-02-01 | Labor | 444024 | 373310 | 530971
MCR030487 | HPR238 | 2025-02-01 | Material | 920049 | 773525 | 681028
MCR030488 | HPR238 | 2025-02-01 | Equipment | 196947 | 165582 | 120440
MCR030489 | HPR238 | 2025-02-01 | Subcontract | 1106570 | 930341 | 1377452
MCR030490 | HPR238 | 2025-02-01 | Overhead | 211849 | 178110 | 5745389
MCR030491 | HPR239 | 2020-05-01 | Labor | 2485379 | 2308920 | 2356358
MCR030492 | HPR239 | 2020-05-01 | Material | 5192877 | 4824190 | 4968282
MCR030493 | HPR239 | 2020-05-01 | Equipment | 1813476 | 1684721 | 1620705
MCR030494 | HPR239 | 2020-05-01 | Subcontract | 6993265 | 6496752 | 5972876
MCR030495 | HPR239 | 2020-05-01 | Overhead | 1827969 | 1698186 | 11588624
MCR030496 | HPR239 | 2020-06-01 | Labor | 7072758 | 3815402 | 4123044
MCR030497 | HPR239 | 2020-06-01 | Material | 14777613 | 7971788 | 7722285
MCR030498 | HPR239 | 2020-06-01 | Equipment | 5160692 | 2783937 | 2958937
MCR030499 | HPR239 | 2020-06-01 | Subcontract | 19901059 | 10735633 | 11843664
MCR030500 | HPR239 | 2020-06-01 | Overhead | 5201938 | 2806187 | 11682442
MCR030501 | HPR239 | 2020-07-01 | Labor | 11094083 | 9228258 | 9550964
MCR030502 | HPR239 | 2020-07-01 | Material | 23179651 | 19281251 | 19717745
MCR030503 | HPR239 | 2020-07-01 | Equipment | 8094883 | 6733469 | 6127415
MCR030504 | HPR239 | 2020-07-01 | Subcontract | 31216111 | 25966123 | 24936051
MCR030505 | HPR239 | 2020-07-01 | Overhead | 8159579 | 6787285 | 12036982
MCR030506 | HPR239 | 2020-08-01 | Labor | 14561807 | 10417507 | 10976463
MCR030507 | HPR239 | 2020-08-01 | Material | 30425011 | 21766033 | 23606175
MCR030508 | HPR239 | 2020-08-01 | Equipment | 10625134 | 7601214 | 8594201
MCR030509 | HPR239 | 2020-08-01 | Subcontract | 40973461 | 29312388 | 25989693
MCR030510 | HPR239 | 2020-08-01 | Overhead | 10710053 | 7661965 | 12052842
MCR030511 | HPR239 | 2020-09-01 | Labor | 17488978 | 11936784 | 12942406
MCR030512 | HPR239 | 2020-09-01 | Material | 36540957 | 24940365 | 22171232
MCR030513 | HPR239 | 2020-09-01 | Equipment | 12760967 | 8709766 | 10087972
MCR030514 | HPR239 | 2020-09-01 | Subcontract | 49209825 | 33587271 | 35563188
MCR030515 | HPR239 | 2020-09-01 | Overhead | 12862956 | 8779376 | 11242081
MCR030516 | HPR239 | 2020-10-01 | Labor | 19889308 | 13240314 | 13291564
MCR030517 | HPR239 | 2020-10-01 | Material | 41556136 | 27663922 | 33195911
MCR030518 | HPR239 | 2020-10-01 | Equipment | 14512386 | 9660897 | 9044998
MCR030519 | HPR239 | 2020-10-01 | Subcontract | 55963782 | 37255094 | 37197422
MCR030520 | HPR239 | 2020-10-01 | Overhead | 14628373 | 9738109 | 11281673
MCR030521 | HPR239 | 2020-11-01 | Labor | 21777252 | 13978490 | 14079636
MCR030522 | HPR239 | 2020-11-01 | Material | 45500750 | 29206247 | 29104944
MCR030523 | HPR239 | 2020-11-01 | Equipment | 15889939 | 10199513 | 10254381
MCR030524 | HPR239 | 2020-11-01 | Subcontract | 61276007 | 39332147 | 39798101
MCR030525 | HPR239 | 2020-11-01 | Overhead | 16016935 | 10281030 | 11361784
MCR030526 | HPR239 | 2020-12-01 | Labor | 23168105 | 10326845 | 11175141
MCR030527 | HPR239 | 2020-12-01 | Material | 48406757 | 21576607 | 21061738
MCR030528 | HPR239 | 2020-12-01 | Equipment | 16904786 | 7535062 | 8054797
MCR030529 | HPR239 | 2020-12-01 | Subcontract | 65189537 | 29057286 | 28440049
MCR030530 | HPR239 | 2020-12-01 | Overhead | 17039893 | 7595284 | 11375036
MCR030531 | HPR239 | 2021-01-01 | Labor | 24078119 | 18266555 | 21133736
MCR030532 | HPR239 | 2021-01-01 | Material | 50308116 | 38165604 | 39826928
MCR030533 | HPR239 | 2021-01-01 | Equipment | 17568785 | 13328332 | 13367075
MCR030534 | HPR239 | 2021-01-01 | Subcontract | 67750102 | 51397742 | 46125945
MCR030535 | HPR239 | 2021-01-01 | Overhead | 17709199 | 13434855 | 11752601
MCR030536 | HPR239 | 2021-02-01 | Labor | 24524649 | 13872483 | 14282821
MCR030537 | HPR239 | 2021-02-01 | Material | 51241081 | 28984758 | 28981005
MCR030538 | HPR239 | 2021-02-01 | Equipment | 17894598 | 10122164 | 10564767
MCR030539 | HPR239 | 2021-02-01 | Subcontract | 69006529 | 39033867 | 41888822
MCR030540 | HPR239 | 2021-02-01 | Overhead | 18037616 | 10203062 | 10867645
MCR030541 | HPR239 | 2021-03-01 | Labor | 24526323 | 17119477 | 17651753
MCR030542 | HPR239 | 2021-03-01 | Material | 51244580 | 35768932 | 41093928
MCR030543 | HPR239 | 2021-03-01 | Equipment | 17895820 | 12491358 | 12274240
MCR030544 | HPR239 | 2021-03-01 | Subcontract | 69011241 | 48170137 | 45939584
MCR030545 | HPR239 | 2021-03-01 | Overhead | 18038848 | 12591192 | 10091216
MCR030546 | HPR239 | 2021-04-01 | Labor | 24103277 | 15991212 | 17055541
MCR030547 | HPR239 | 2021-04-01 | Material | 50360678 | 33411569 | 32560917
MCR030548 | HPR239 | 2021-04-01 | Equipment | 17587141 | 11668111 | 12356907
MCR030549 | HPR239 | 2021-04-01 | Subcontract | 67820889 | 44995469 | 44629062
MCR030550 | HPR239 | 2021-04-01 | Overhead | 17727702 | 11761365 | 12232438
MCR030551 | HPR239 | 2021-05-01 | Labor | 23277434 | 37111779 | 36374758
MCR030552 | HPR239 | 2021-05-01 | Material | 48635187 | 77540262 | 103252758
MCR030553 | HPR239 | 2021-05-01 | Equipment | 16984559 | 27078895 | 27760464
MCR030554 | HPR239 | 2021-05-01 | Subcontract | 65497164 | 104423721 | 98561745
MCR030555 | HPR239 | 2021-05-01 | Overhead | 17120303 | 27295316 | 11906761
MCR030556 | HPR239 | 2021-06-01 | Labor | 22072894 | 15783702 | 20394870
MCR030557 | HPR239 | 2021-06-01 | Material | 46118456 | 32978003 | 26165472
MCR030558 | HPR239 | 2021-06-01 | Equipment | 16105656 | 11516699 | 12134136
MCR030559 | HPR239 | 2021-06-01 | Subcontract | 62107873 | 44411584 | 47430589
MCR030560 | HPR239 | 2021-06-01 | Overhead | 16234377 | 11608744 | 12707346
MCR030561 | HPR239 | 2021-07-01 | Labor | 20516441 | 18635382 | 20645892
MCR030562 | HPR239 | 2021-07-01 | Material | 42866450 | 38936219 | 46681762
MCR030563 | HPR239 | 2021-07-01 | Equipment | 14969979 | 13597449 | 13529422
MCR030564 | HPR239 | 2021-07-01 | Subcontract | 57728387 | 52435532 | 55185275
MCR030565 | HPR239 | 2021-07-01 | Overhead | 15089623 | 13706123 | 10911775
MCR030566 | HPR239 | 2021-08-01 | Labor | 18638270 | 15847150 | 16458146
MCR030567 | HPR239 | 2021-08-01 | Material | 38942254 | 33110569 | 37110044
MCR030568 | HPR239 | 2021-08-01 | Equipment | 13599557 | 11562995 | 12923712
MCR030569 | HPR239 | 2021-08-01 | Subcontract | 52443659 | 44590110 | 46136143
MCR030570 | HPR239 | 2021-08-01 | Overhead | 13708248 | 11655409 | 12224997
MCR030571 | HPR239 | 2021-09-01 | Labor | 16473020 | 24139002 | 23628410
MCR030572 | HPR239 | 2021-09-01 | Material | 34418244 | 50435322 | 59738516
MCR030573 | HPR239 | 2021-09-01 | Equipment | 12019666 | 17613209 | 18796849
MCR030574 | HPR239 | 2021-09-01 | Subcontract | 46351160 | 67921412 | 69636516
MCR030575 | HPR239 | 2021-09-01 | Overhead | 12115729 | 17753977 | 11070096
MCR030576 | HPR239 | 2021-10-01 | Labor | 14061371 | 20488393 | 19917407
MCR030577 | HPR239 | 2021-10-01 | Material | 29379417 | 42807847 | 49779857
MCR030578 | HPR239 | 2021-10-01 | Equipment | 10259988 | 14949514 | 17396714
MCR030579 | HPR239 | 2021-10-01 | Subcontract | 39565355 | 57649467 | 55477394
MCR030580 | HPR239 | 2021-10-01 | Overhead | 10341988 | 15068994 | 12379336
MCR030581 | HPR239 | 2021-11-01 | Labor | 11452630 | 10776363 | 12075143
MCR030582 | HPR239 | 2021-11-01 | Material | 23928789 | 22515816 | 33782183
MCR030583 | HPR239 | 2021-11-01 | Equipment | 8356500 | 7863056 | 5584673
MCR030584 | HPR239 | 2021-11-01 | Subcontract | 32224978 | 30322122 | 24232209
MCR030585 | HPR239 | 2021-11-01 | Overhead | 8423287 | 7925899 | 11778200
MCR030586 | HPR239 | 2021-12-01 | Labor | 8709322 | 10046558 | 12998747
MCR030587 | HPR239 | 2021-12-01 | Material | 18197001 | 20990983 | 24249836
MCR030588 | HPR239 | 2021-12-01 | Equipment | 6354824 | 7330548 | 8098631
MCR030589 | HPR239 | 2021-12-01 | Subcontract | 24505960 | 28268624 | 28962448
MCR030590 | HPR239 | 2021-12-01 | Overhead | 6405613 | 7389135 | 11351914
MCR030591 | HPR239 | 2022-01-01 | Labor | 5916488 | 17293133 | 18653950
MCR030592 | HPR239 | 2022-01-01 | Material | 12361736 | 36131765 | 39879826
MCR030593 | HPR239 | 2022-01-01 | Equipment | 4317011 | 12618068 | 13160593
MCR030594 | HPR239 | 2022-01-01 | Subcontract | 16647590 | 48658765 | 49342285
MCR030595 | HPR239 | 2022-01-01 | Overhead | 4351513 | 12718914 | 11233687
MCR030596 | HPR239 | 2022-02-01 | Labor | 3205013 | 18447461 | 18687631
MCR030597 | HPR239 | 2022-02-01 | Material | 6696460 | 38543583 | 50640324
MCR030598 | HPR239 | 2022-02-01 | Equipment | 2338562 | 13460331 | 14279107
MCR030599 | HPR239 | 2022-02-01 | Subcontract | 9018144 | 51906767 | 50541884
MCR030600 | HPR239 | 2022-02-01 | Overhead | 2357253 | 13567910 | 11087755
MCR030601 | HPR239 | 2022-03-01 | Labor | 849982 | 8764460 | 10510993
MCR030602 | HPR239 | 2022-03-01 | Material | 1775927 | 18312205 | 22453939
MCR030603 | HPR239 | 2022-03-01 | Equipment | 620196 | 6395056 | 6080414
MCR030604 | HPR239 | 2022-03-01 | Subcontract | 2391646 | 24661106 | 23595577
MCR030605 | HPR239 | 2022-03-01 | Overhead | 625152 | 6446166 | 10544018
MCR030606 | HPR239 | 2022-04-01 | Labor | 0 | 9284934 | 10362650
MCR030607 | HPR239 | 2022-04-01 | Material | 0 | 19399668 | 22127801
MCR030608 | HPR239 | 2022-04-01 | Equipment | 0 | 6774823 | 7384631
MCR030609 | HPR239 | 2022-04-01 | Subcontract | 0 | 26125596 | 26045886
MCR030610 | HPR239 | 2022-04-01 | Overhead | 0 | 6828969 | 11142277
MCR030611 | HPR239 | 2022-05-01 | Labor | 0 | 6697072 | 6685887
MCR030612 | HPR239 | 2022-05-01 | Material | 0 | 13992665 | 20541100
MCR030613 | HPR239 | 2022-05-01 | Equipment | 0 | 4886570 | 3849984
MCR030614 | HPR239 | 2022-05-01 | Subcontract | 0 | 18843967 | 17924587
MCR030615 | HPR239 | 2022-05-01 | Overhead | 0 | 4925624 | 11534575
MCR030616 | HPR239 | 2022-06-01 | Labor | 0 | 3362895 | 4189637
MCR030617 | HPR239 | 2022-06-01 | Material | 0 | 7026335 | 7132711
MCR030618 | HPR239 | 2022-06-01 | Equipment | 0 | 2453763 | 3660334
MCR030619 | HPR239 | 2022-06-01 | Subcontract | 0 | 9462388 | 9476158
MCR030620 | HPR239 | 2022-06-01 | Overhead | 0 | 2473374 | 11539237
MCR030621 | HPR239 | 2022-07-01 | Labor | 0 | 2292229 | 2546222
MCR030622 | HPR239 | 2022-07-01 | Material | 0 | 4789316 | 7131093
MCR030623 | HPR239 | 2022-07-01 | Equipment | 0 | 1672542 | 1501878
MCR030624 | HPR239 | 2022-07-01 | Subcontract | 0 | 6449787 | 6353889
MCR030625 | HPR239 | 2022-07-01 | Overhead | 0 | 1685910 | 11604749
MCR030626 | HPR239 | 2022-08-01 | Labor | 0 | 470142 | 567790
MCR030627 | HPR239 | 2022-08-01 | Material | 0 | 982300 | 905904
MCR030628 | HPR239 | 2022-08-01 | Equipment | 0 | 343042 | 492566
MCR030629 | HPR239 | 2022-08-01 | Subcontract | 0 | 1322867 | 1074739
MCR030630 | HPR239 | 2022-08-01 | Overhead | 0 | 345784 | 11640198
MCR030631 | HPR240 | 2023-05-01 | Labor | 7574673 | 8087092 | 8920685
MCR030632 | HPR240 | 2023-05-01 | Material | 20211219 | 21578486 | 19803637
MCR030633 | HPR240 | 2023-05-01 | Equipment | 4578270 | 4887985 | 5071244
MCR030634 | HPR240 | 2023-05-01 | Subcontract | 28534717 | 30465061 | 30204828
MCR030635 | HPR240 | 2023-05-01 | Overhead | 5012620 | 5351718 | 18376839
MCR030636 | HPR240 | 2023-06-01 | Labor | 20775448 | 10728028 | 10719841
MCR030637 | HPR240 | 2023-06-01 | Material | 55434354 | 28625199 | 30025618
MCR030638 | HPR240 | 2023-06-01 | Equipment | 12557058 | 6484215 | 6732204
MCR030639 | HPR240 | 2023-06-01 | Subcontract | 78263643 | 40413790 | 43886717
MCR030640 | HPR240 | 2023-06-01 | Overhead | 13748372 | 7099386 | 19133545
MCR030641 | HPR240 | 2023-07-01 | Labor | 31132099 | 13948357 | 12748427
MCR030642 | HPR240 | 2023-07-01 | Material | 83068622 | 37217882 | 42300534
MCR030643 | HPR240 | 2023-07-01 | Equipment | 18816807 | 8430641 | 9210308
MCR030644 | HPR240 | 2023-07-01 | Subcontract | 117278412 | 52545161 | 47719807
MCR030645 | HPR240 | 2023-07-01 | Overhead | 20601995 | 9230473 | 20166793
MCR030646 | HPR240 | 2023-08-01 | Labor | 38756398 | 16968537 | 18428351
MCR030647 | HPR240 | 2023-08-01 | Material | 103412255 | 45276517 | 43421356
MCR030648 | HPR240 | 2023-08-01 | Equipment | 23425072 | 10256093 | 10019622
MCR030649 | HPR240 | 2023-08-01 | Subcontract | 146000075 | 63922549 | 75572079
MCR030650 | HPR240 | 2023-08-01 | Overhead | 25647455 | 11229109 | 20194170
MCR030651 | HPR240 | 2023-09-01 | Labor | 43770030 | 68084436 | 76962326
MCR030652 | HPR240 | 2023-09-01 | Material | 116789944 | 181667168 | 170499568
MCR030653 | HPR240 | 2023-09-01 | Equipment | 26455403 | 41151472 | 42363081
MCR030654 | HPR240 | 2023-09-01 | Subcontract | 164887040 | 256482369 | 220571145
MCR030655 | HPR240 | 2023-09-01 | Overhead | 28965280 | 45055594 | 20242908
MCR030656 | HPR240 | 2023-10-01 | Labor | 46306809 | 24377579 | 19927981
MCR030657 | HPR240 | 2023-10-01 | Material | 123558737 | 65045788 | 76177064
MCR030658 | HPR240 | 2023-10-01 | Equipment | 27988678 | 14734252 | 14940477
MCR030659 | HPR240 | 2023-10-01 | Subcontract | 174443395 | 91833312 | 112562528
MCR030660 | HPR240 | 2023-10-01 | Overhead | 30644020 | 16132120 | 21498069
MCR030661 | HPR240 | 2023-11-01 | Labor | 46515726 | 26826248 | 31126932
MCR030662 | HPR240 | 2023-11-01 | Material | 124116182 | 71579480 | 74246994
MCR030663 | HPR240 | 2023-11-01 | Equipment | 28114951 | 16214272 | 15509214
MCR030664 | HPR240 | 2023-11-01 | Subcontract | 175230410 | 101057747 | 110984461
MCR030665 | HPR240 | 2023-11-01 | Overhead | 30782273 | 17752553 | 19907266
MCR030666 | HPR240 | 2023-12-01 | Labor | 44565331 | 36095290 | 33699752
MCR030667 | HPR240 | 2023-12-01 | Material | 118912016 | 96311720 | 101679136
MCR030668 | HPR240 | 2023-12-01 | Equipment | 26936097 | 21816650 | 23337898
MCR030669 | HPR240 | 2023-12-01 | Subcontract | 167883036 | 135975357 | 124329600
MCR030670 | HPR240 | 2023-12-01 | Overhead | 29491578 | 23886439 | 20347131
MCR030671 | HPR240 | 2024-01-01 | Labor | 40650329 | 36761445 | 39987858
MCR030672 | HPR240 | 2024-01-01 | Material | 108465761 | 98089197 | 85800376
MCR030673 | HPR240 | 2024-01-01 | Equipment | 24569798 | 22219286 | 21178634
MCR030674 | HPR240 | 2024-01-01 | Subcontract | 153134745 | 138484845 | 157641085
MCR030675 | HPR240 | 2024-01-01 | Overhead | 26900784 | 24327274 | 19523643
MCR030676 | HPR240 | 2024-02-01 | Labor | 35002160 | 26709396 | 34493496
MCR030677 | HPR240 | 2024-02-01 | Material | 93394963 | 71267689 | 80745678
MCR030678 | HPR240 | 2024-02-01 | Equipment | 21155943 | 16143645 | 19577802
MCR030679 | HPR240 | 2024-02-01 | Subcontract | 131857405 | 100617552 | 99502688
MCR030680 | HPR240 | 2024-02-01 | Overhead | 23163049 | 17675225 | 20916073
MCR030681 | HPR240 | 2024-03-01 | Labor | 27907533 | 42824456 | 44335749
MCR030682 | HPR240 | 2024-03-01 | Material | 74464632 | 114266902 | 120969736
MCR030683 | HPR240 | 2024-03-01 | Equipment | 16867821 | 25883880 | 24037989
MCR030684 | HPR240 | 2024-03-01 | Subcontract | 105131078 | 161324945 | 170652596
MCR030685 | HPR240 | 2024-03-01 | Overhead | 18468104 | 28339536 | 20924454
MCR030686 | HPR240 | 2024-04-01 | Labor | 19745288 | 30272210 | 26505181
MCR030687 | HPR240 | 2024-04-01 | Material | 52685619 | 80774212 | 71260424
MCR030688 | HPR240 | 2024-04-01 | Equipment | 11934412 | 18297074 | 18940028
MCR030689 | HPR240 | 2024-04-01 | Subcontract | 74382908 | 114039105 | 112464427
MCR030690 | HPR240 | 2024-04-01 | Overhead | 13066653 | 20032954 | 18891240
MCR030691 | HPR240 | 2024-05-01 | Labor | 11077197 | 24743611 | 33749689
MCR030692 | HPR240 | 2024-05-01 | Material | 29556872 | 66022457 | 73334316
MCR030693 | HPR240 | 2024-05-01 | Equipment | 6695259 | 14955489 | 13868195
MCR030694 | HPR240 | 2024-05-01 | Subcontract | 41729151 | 93212199 | 103643437
MCR030695 | HPR240 | 2024-05-01 | Overhead | 7330452 | 16374346 | 18539057
MCR030696 | HPR240 | 2024-06-01 | Labor | 3021133 | 29986687 | 26590237
MCR030697 | HPR240 | 2024-06-01 | Material | 8061177 | 80012363 | 87108247
MCR030698 | HPR240 | 2024-06-01 | Equipment | 1826028 | 18124499 | 20923589
MCR030699 | HPR240 | 2024-06-01 | Subcontract | 11380977 | 112963507 | 111395932
MCR030700 | HPR240 | 2024-06-01 | Overhead | 1999267 | 19844007 | 18041241
MCR030701 | HPR240 | 2024-07-01 | Labor | 0 | 13415128 | 16016713
MCR030702 | HPR240 | 2024-07-01 | Material | 0 | 35795086 | 36130102
MCR030703 | HPR240 | 2024-07-01 | Equipment | 0 | 8108347 | 8592906
MCR030704 | HPR240 | 2024-07-01 | Subcontract | 0 | 50536421 | 54545237
MCR030705 | HPR240 | 2024-07-01 | Overhead | 0 | 8877602 | 19813047
MCR030706 | HPR240 | 2024-08-01 | Labor | 0 | 5044846 | 6420097
MCR030707 | HPR240 | 2024-08-01 | Material | 0 | 13460974 | 14738530
MCR030708 | HPR240 | 2024-08-01 | Equipment | 0 | 3049196 | 3452241
MCR030709 | HPR240 | 2024-08-01 | Subcontract | 0 | 19004548 | 20466016
MCR030710 | HPR240 | 2024-08-01 | Overhead | 0 | 3338480 | 19180973
MCR030711 | HPR240 | 2024-09-01 | Labor | 0 | 1926810 | 1821514
MCR030712 | HPR240 | 2024-09-01 | Material | 0 | 5141234 | 4709510
MCR030713 | HPR240 | 2024-09-01 | Equipment | 0 | 1164599 | 1081607
MCR030714 | HPR240 | 2024-09-01 | Subcontract | 0 | 7258526 | 6259825
MCR030715 | HPR240 | 2024-09-01 | Overhead | 0 | 1275087 | 19974530

## material_price_index
month | steel_index | cement_index | labour_wage_index
2015-01-01 | 99.6 | 99.8 | 100.2
2015-02-01 | 98.8 | 99.6 | 99.9
2015-03-01 | 99.3 | 99.9 | 100.4
2015-04-01 | 99.9 | 99.8 | 101.4
2015-05-01 | 100 | 99.9 | 102.9
2015-06-01 | 100.4 | 100.1 | 102.3
2015-07-01 | 101.5 | 100.6 | 103.5
2015-08-01 | 102.2 | 101.3 | 103.9
2015-09-01 | 102.8 | 101.6 | 103.2
2015-10-01 | 103.4 | 101.8 | 104.5
2015-11-01 | 103.1 | 102.2 | 105.5
2015-12-01 | 103.8 | 102.5 | 105.2
2016-01-01 | 103.2 | 102.2 | 106.6
2016-02-01 | 103.3 | 102.3 | 106
2016-03-01 | 103.3 | 102.1 | 106.3
2016-04-01 | 102.7 | 102.5 | 107.3
2016-05-01 | 102.8 | 103.1 | 108.4
2016-06-01 | 103.9 | 103.4 | 108.4
2016-07-01 | 103.9 | 103.3 | 109.6
2016-08-01 | 103.5 | 103.7 | 108.9
2016-09-01 | 103.7 | 103.6 | 109.9
2016-10-01 | 104.3 | 103.9 | 111.4
2016-11-01 | 104.7 | 103.8 | 110
2016-12-01 | 104.9 | 103.6 | 112
2017-01-01 | 104.4 | 103.4 | 111.9
2017-02-01 | 104.9 | 103.6 | 112.5
2017-03-01 | 105.3 | 103.6 | 113.3
2017-04-01 | 106.2 | 103.9 | 113.3
2017-05-01 | 107.2 | 103.8 | 115
2017-06-01 | 107.7 | 104.1 | 115.4
2017-07-01 | 107.1 | 104.1 | 116.3
2017-08-01 | 106.6 | 104.7 | 116.3
2017-09-01 | 106.3 | 105.2 | 116.3
2017-10-01 | 106.7 | 105.3 | 117.7
2017-11-01 | 106.5 | 105.5 | 117.3
2017-12-01 | 107.4 | 105.8 | 118.1
2018-01-01 | 107.7 | 106.1 | 120.2
2018-02-01 | 108.1 | 106.3 | 120.2
2018-03-01 | 108.7 | 106.8 | 120.5
2018-04-01 | 109.1 | 106.8 | 121.6
2018-05-01 | 108.6 | 106.5 | 121.3
2018-06-01 | 110.1 | 106.7 | 122.3
2018-07-01 | 111 | 106.9 | 122.2
2018-08-01 | 112 | 107.3 | 123.1
2018-09-01 | 111.9 | 107.7 | 123.9
2018-10-01 | 111.2 | 108 | 125.2
2018-11-01 | 110.6 | 108.2 | 124.7
2018-12-01 | 110.3 | 108.4 | 126.2
2019-01-01 | 111 | 108.4 | 126.2
2019-02-01 | 111.6 | 108.3 | 126
2019-03-01 | 112.6 | 108.3 | 126.5
2019-04-01 | 113.9 | 108.4 | 127.8
2019-05-01 | 114.4 | 108 | 129.3
2019-06-01 | 114.8 | 108.1 | 129.5
2019-07-01 | 114.8 | 108 | 130.9
2019-08-01 | 114.9 | 108.2 | 130.7
2019-09-01 | 114.5 | 108.2 | 132
2019-10-01 | 115 | 108.4 | 132
2019-11-01 | 115.4 | 108.5 | 132.1
2019-12-01 | 115.4 | 109.1 | 133.5
2020-01-01 | 115.2 | 109.2 | 133.5
2020-02-01 | 115.6 | 109.3 | 133.8
2020-03-01 | 116.5 | 109.5 | 134.8
2020-04-01 | 116.8 | 109.2 | 135.6
2020-05-01 | 117.1 | 109.1 | 136.6
2020-06-01 | 117.1 | 109.7 | 137.5
2020-07-01 | 117.2 | 110 | 138.1
2020-08-01 | 117.2 | 110.3 | 139.5
2020-09-01 | 117.3 | 110.8 | 138.1
2020-10-01 | 117.2 | 110.9 | 139.7
2020-11-01 | 117.6 | 111.1 | 141.8
2020-12-01 | 118.5 | 111.2 | 141
2021-01-01 | 118.3 | 110.9 | 141.2
2021-02-01 | 122.8 | 111.3 | 142.2
2021-03-01 | 126.5 | 111.5 | 142.8
2021-04-01 | 130.1 | 120.7 | 143.7
2021-05-01 | 132.7 | 120.8 | 145.5
2021-06-01 | 135.1 | 120.8 | 144.6
2021-07-01 | 139 | 120.4 | 145.7
2021-08-01 | 141.7 | 120.6 | 147.5
2021-09-01 | 145.3 | 121.4 | 147.6
2021-10-01 | 148.2 | 121.9 | 148.4
2021-11-01 | 151 | 122 | 148.7
2021-12-01 | 154.2 | 121.9 | 150.1
2022-01-01 | 156.3 | 122.1 | 149.9
2022-02-01 | 156.6 | 122.5 | 151.6
2022-03-01 | 157.3 | 122.6 | 151.9
2022-04-01 | 159.1 | 123.1 | 152.5
2022-05-01 | 161.2 | 123 | 153.1
2022-06-01 | 161.8 | 123.5 | 154.5
2022-07-01 | 161.8 | 123.7 | 155
2022-08-01 | 161.2 | 123.8 | 155.4
2022-09-01 | 161.2 | 123.9 | 156.4
2022-10-01 | 159.7 | 124.2 | 156.6
2022-11-01 | 158.2 | 124.6 | 158.5
2022-12-01 | 157.1 | 124.8 | 159.3
2023-01-01 | 155.7 | 125.2 | 160
2023-02-01 | 135.4 | 126.1 | 160.3
2023-03-01 | 136.2 | 125.8 | 161.2
2023-04-01 | 135.8 | 125.4 | 161.1
2023-05-01 | 135.4 | 125.7 | 162.3
2023-06-01 | 135.4 | 125.6 | 163.2
2023-07-01 | 135.7 | 125.8 | 164
2023-08-01 | 135.7 | 125.6 | 165.2
2023-09-01 | 136.9 | 125.8 | 165.5
2023-10-01 | 136.8 | 126.4 | 166.2
2023-11-01 | 137.4 | 126.9 | 167.9
2023-12-01 | 137.3 | 126.8 | 168
2024-01-01 | 137.7 | 126.9 | 168.6
2024-02-01 | 137.7 | 127.3 | 168.8
2024-03-01 | 137.7 | 128.1 | 169.9
2024-04-01 | 138.7 | 128 | 171.3
2024-05-01 | 138.8 | 127.9 | 172.4
2024-06-01 | 139.9 | 128.5 | 172.2
2024-07-01 | 139.7 | 128.6 | 173.9
2024-08-01 | 139.7 | 128.5 | 175
2024-09-01 | 140.5 | 129 | 175.4
2024-10-01 | 139.5 | 128.7 | 176.5
2024-11-01 | 138.8 | 128.7 | 178.1
2024-12-01 | 139.1 | 129.2 | 177.9
2025-01-01 | 139.5 | 129.2 | 178.2
2025-02-01 | 140 | 129.6 | 179.8
2025-03-01 | 140.1 | 129.5 | 180.4
2025-04-01 | 139.6 | 129.9 | 181.7
2025-05-01 | 140.2 | 130.2 | 183
2025-06-01 | 140.7 | 130.9 | 183.9
2025-07-01 | 140.3 | 131 | 184.5
2025-08-01 | 140.6 | 131.1 | 186
2025-09-01 | 141.7 | 131.3 | 186.4
2025-10-01 | 142 | 131.8 | 187.6
2025-11-01 | 141.6 | 131.8 | 188.2
2025-12-01 | 141.6 | 131.9 | 189.1
2026-01-01 | 141.7 | 132.7 | 189.6
2026-02-01 | 142 | 133.1 | 190.8
2026-03-01 | 142.7 | 133.5 | 191.4
2026-04-01 | 142.5 | 133.5 | 192.5
2026-05-01 | 142.4 | 134 | 193.6
2026-06-01 | 143.1 | 133.9 | 195.1
2026-07-01 | 143.7 | 133.6 | 195.3
2026-08-01 | 144.6 | 133.6 | 196.7

## data_dictionary_v2
sheet_name | column_name | data_type | meaning
project_register | project_id | Text | PRJ001-PRJ030 are the current portfolio from dim_project (unchanged IDs, names, contract values and planned dates). HPR### are completed historical projects used for training.
project_register | portfolio | Text | Current portfolio or Completed (history).
project_register | project_type | Text | Building or infrastructure type.
project_register | client_type | Text | Government or Private.
project_register | contract_type | Text | Item rate with price variation, EPC lump sum, Lump sum or Cost plus fee. Decides who carries material price risk.
project_register | contract_value | Currency (INR) | Contract value (revenue).
project_register | tender_margin_pct | Percent | Margin priced in at tender.
project_register | bac | Currency (INR) | Budget at completion: the cost budget = contract value less tender margin.
project_register | planned_start / planned_finish / planned_months | Date / Integer | Baseline programme.
project_register | design_maturity_pct | Percent | Share of design complete at contract award.
project_register | complexity | Integer 1-5 | Technical complexity rating from the tender review.
project_register | pm_experience_years | Integer | Project manager experience.
project_register | status | Text | Completed or In progress at the August 2026 cost report.
project_register | actual_finish | Date | Month the work was completed (blank if in progress).
project_register | final_cost | Currency (INR) | Final actual cost for completed projects (blank if in progress).
fact_monthly_cost | row_id | Text | Unique row ID.
fact_monthly_cost | period_month | Date | Month of the cost report (first day of month).
fact_monthly_cost | cost_category | Text | Labor, Material, Equipment, Subcontract or Overhead (same categories as dim_cost_code).
fact_monthly_cost | planned_value | Currency (INR) | Budgeted cost of work scheduled that month (baseline S-curve).
fact_monthly_cost | earned_value | Currency (INR) | Budgeted cost of work performed that month.
fact_monthly_cost | actual_cost | Currency (INR) | Actual cost booked that month, including accrual adjustments.
material_price_index | steel_index / cement_index / labour_wage_index | Index | Monthly price indices, Jan 2015 = 100.